## Annex 3 – Schedule of Deliverables

|  |  |  |  |
| --- | --- | --- | --- |
| Deliverable, its part | Step | Result | Deadline |
| D1 i) | Provide detailed plan of all bellows hereof | Technical report | 3 months from contract signature |
| D1 ii) | Manufacture, assemble and test all bellows by the Contractor | Protocol on testing of Devices at Contractor’s place/Report on testing at Contractor’s place | 5 months from contract signature |
| D1 iii) | Deliver, assemble and test all bellows | Protocol on testing of Device at the research center ELI-Beamlines | 6 months from contract signature |
| D2 i) | Provide preliminary design of all vacuum pipes | Technical report | 1 month from contract signature |
| D2 ii) | Provide detailed plan of all vacuum pipes | Technical report | 3 months from contract signature |
| D2 iii) | Manufacture, assemble and test all vacuum pipes by the Contractor | Protocol on testing of Devices at Contractor’s place/Report on testing at Contractor’s place | 5 months from contract signature |
| D2 iv) | Deliver, assemble and test all vacuum pipes by the Client | Protocol on testing of Device at the research center ELI-Beamlines | 6 months from contract signature |
| D3 i) | Provide preliminary design of all frames for vacuum pipes | Technical report | 1 month from contract signature |
| D3 ii) | Provide detailed plan of all frames for vacuum pipes | Technical report | 3 months from contract signature |
| D3 iii) | Manufacture, assemble and test all frames for vacuum pipes by the Contractor | Protocol on testing of Devices at Contractor’s place/Report on testing at Contractor’s place | 5 months from contract signature |
| D3 iv) | Deliver, assemble and test all frames for vacuum pipes by the Client | Protocol on testing of Device at the research center ELI-Beamlines | 6 months from contract signature |
| D4 i) | Provide preliminary design of all frames for vacuum chambers | Technical report | 1 month from contract signature |
| D4 ii) | Provide detailed plan of all frames for vacuum chambers | Technical report | 3 months from contract signature |
| D4 iii) | Manufacture, assemble and test all frames for vacuum chambers by the Contractor | Protocol on testing of Devices at Contractor’s place/Report on testing at Contractor’s place | 5 months from contract signature |
| D4 iv) | Deliver, assemble and test all frames for vacuum chambers by the Client | Protocol on testing of Device at the research center ELI-Beamlines | 6 months from contract signature |
| D5 i) | Provide preliminary design of all vacuum chambers | Technical report | 1.5 month from contract signature |
| D5 ii) | Provide detailed plan of all vacuum chambers | Technical report | 3 months from contract signature |
| D5 iii) | Manufacture, assemble and test all vacuum chambers by the Contractor | Protocol on testing of Devices at Contractor’s place/Report on testing at Contractor’s place | 9 months from contract signature |
| D5 iv) | Deliver, assemble and test Device by the Client | Protocol on testing of Device at the research center ELI-Beamlines | 10 months from contract signature |