Waste-to-Energy Facility, EVO – Komořany, Most

DRAFT CONTRACT FOR WORK

TABLE OF CONTENTS

A.	CONTRACT AND INTERPRETATION	4

1.	PARTIES TO THE CONTRACT	4

2.	TERMS AND DEFINITIONS	5

3.	legal basis of the contract	8

4.	CONTRACT DOCUMENTS	8

5.	GOVERNING LAW	9

6.	RESOLUTION OF DISPUTES	9

7.	NOTICES	10

B.	SUBJECT OF THE CONTRACT	12

8.	PURPOSE OF THE WORK	12

9.	SUBJECT OF THE CONTRACT – THE WORK	12

10.	WORK TIMETABLE	14

11.	CONTRACTOR’S OBLIGATIONS IN EXECUTION OF THE WORK	17

12.	PURCHASER’S COOPERATION	19

C.	PAYMENT	21

13.	CONTRACT PRICE	21

14.	TERMS OF PAYMENT	22

15.	TAXES, CUSTOMS, AND FEES	26

16.	BANK GUARANTEES FOR THE WORK AND FOR THE DEPOSIT	26

D.	INTELLECTUAL PROPERTY	29

17.	LICENSES AND RIGHTS OF USE TO TECHNICAL INFORMATION	29

18.	confidentiality regarding information and contractual documents, Ethical conduct between the parties	29

E.	EXECUTION OF THE WORK	31

19.	PARTIES‘ REPRESENTATIVES	31

20.	INFORMATION SUBMITTED TO PURCHASER	32

21.	subcontracting	35

22.	STANDARDS AND LEGISLATION	36

23.	ENGINEERING WORK, DOCUMENTATION	37

24.	EXECUTION OF THE WORK	38

25.	DELIVERY AND DOCUMENTATION	39

26.	PACKAGING INSTRUCTIONS	39

27.	TRANSPORT	39

28.	WORK QUALITY ASSURANCE	40

29.	ASSEMBLY AND MECHANICAL COMPLETION	43

30.	COMMISSIONING	44

31.	PROVISIONAL ACCEPTANCE OF THE WORK	48

32.	TRIAL OPERATION	49

33.	GUARANTEE MEASUREMENT DURING TEST “B“, FINAL ACCEPTANCE OF THE WORK	51

34.	FULFILMENT OF THE CONTRACTOR’S OBLIGATIONS	52

35.	EMERGENCY WORKS	52

36.	PURCHASER OPERATIONS AND MAINTENANCE STAFF TRAINING	52

37.	REPLACEMENT PARTS AND RAPID-WEAR PARTS	52

38.	POST-WARRANTY SERVICING	53

39.	SITE AND ASSEMBLY SITES	53

40.	ADMINISTRATION RULES, OCCUPATIONAL HEALTH AND SAFETY	54

41.	WASTE MANAGEMENT, ENVIRONMENTAL PROTECTION	54

42.	PROTECTION OF THE WORK	56

F.	WARRANTIES AND RESPONSIBILITIES	56

43.	Guaranteed parameters	56

44.	CONTRACTUAL PENALTIES	56

45.	LIABILITY FOR DEFECTS IN THE WORK, QUALITY WARRANTY	72

46.	REIMBURSEMENT FOR DAMAGES, LIMITATION OF LIABILITY	76

47.	REIMBURSEMENT FOR PATENT CLAIMS	76

G.	RISK ALLOCATION	77

48.	TRANSFER OF OWNERSHIP	77

49.	DUE CARE OF THE WORK, TRANSFER OF LIABILITY FOR DAMAGE TO THE WORK	77

50.	PROPERTY LOSS AND DAMAGE, PERSONNEL ACCIDENT AND INJURY, CLAIM SETTLEMENT	78

51.	INSURANCE	79

52.	FORCE MAJEURE	81

H.	CHANGES TO THE WORK (CONTRACT)	82

53.	CHANGE PROCEEDINGS	82

54.	INTERRUPTION OF WORKS	84

55.	WITHDRAWAL FROM THE CONTRACT	85

I.	CONCLUDING PROVISIONS	89

56.	ASSIGNMENT OF CONTRACT AND PROHIBITION OF RETENTION	89

57.	FINAL PROVISIONS	89

# CONTRACT AND INTERPRETATION

# PARTIES TO THE CONTRACT

| purchaser | United Energy, a.s. |
| --- | --- |
| Registered address | Most – Komořany, , Teplárenská 2, , Postcode 434 03 |
| a company registered in Section B, File 1722 of the Commercial Register of the Regional Court of Ústí nad Labem, Czech Republic |  |
| Authorized signatories | Ing. Petr MAREŠ, Director Ing. Milan BOHÁČEK, Deputy Chairman of the Board |
| Authorized representatives for: |  |
| - Contract negotiations |  |
| - Technical matters |  |
| purchaser’s representative: |  |
| Business Registration No. / VAT No. | 273 09 959 / CZ27309959 |
| Bank account CZK: | Komerční banka, a.s., Most account no.: 15605491/0100 |
| Bank account EUR: | UniCredit Bank Czech Republic and Slovakia, a.s. account number: 2104168552/2700 IBAN CZ8427000000002104168552 SWIFT BACXCZPP |

and

| contractor |  |
| --- | --- |
| Registered address |  |
| Registered in [Commercial Register details]: |  |
| Authorized signatories |  |
| Authorized representatives for: |  |
| - Contract negotiations |  |
| - Technical matters |  |
| contractor’s representative: |  |
| Business Registration No. / VAT No. |  |
| Bank account: |  |

have concluded

based on the outcome of the procurement procedure for the “Waste-to-Energy Facility, EVO – Komořany, Most“ public contract announced in the Public Tenders Bulletin on 21. 11. 2022, Public Contract ref. no. Z2022-047348 and executed by the purchaser under Act No. 134/2016 Coll., on Public Procurement, as amended, hereby conclude this contract for work under which the contractor commits to the full and timely execution of the work at its own cost and risk and the purchaser commits to pay the contract price for the full and timely execution of the work under the conditions specified herein. The purpose of the contract is to ensure the work specified herein is executed, and commissioned in a proper and timely manner, and that all other parameters and obligations agreed in the contract are met.

Inspections shall be performed on the basis of an inspection agreement executed pursuant to Section 2562 et seq. of Act No. 89/2012 Coll.; thereunder, the inspector (i.e., the contractor) shall impartially determine the actual state of the subject of the inspection, and shall provide an inspection certificate (inspection report) to that effect, while the purchaser shall pay to the Inspector a fee that has been incorporated into the price of the work.

# TERMS AND DEFINITIONS

## For the purposes of this contract, certain terms shall be defined as follows:

"day" 	shall be a calendar day from 12:00 midnight to 12:00 midnight; this includes all days of the year regardless of their position in a week or their possible status as a bank or other holiday observed in the Czech Republic or elsewhere

"work" shall be the set of goods, rights of use, works, and services provided by the contractor in accordance with the specifications and conditions given in this contract and its enclosures; the work is to be a complete, operational, safe, continuously operable, reliable system possessing the parameters and serving the purpose set forth in this contract.

"contract documents" shall be the documents listed in Article 4 of the contract.

"fat" 	shall be the “factory acceptance test" conducted by the contractor prior to shipment of the goods to the site to demonstrate the goods have been produced in accordance with the contract and meet the contractual requirements.

"guarantee measurement“ shall be the testing performed as part of tests “A” and “B”, whose purpose is to determine whether the work as a whole or a specific part thereof is capable of achieving the guaranteed parameters listed in Enclosure 2 of the contract

"complex tests" shall be the tests performed in accordance with Article 30 of the contract, whose purpose is to verify that the technical parameters specified for the work in the contract have been met.

"performance test" shall be a test performed in accordance with Article 30 of this contract, whose purpose is to verify that the requirements on operational, safety, and reliability requirements specified for the work in the contract, as well as all other requirements specified in the contract, have been met.

"final acceptance" shall be the purchaser’s final acceptance of the separate technological part and the separate  building part of the work, which takes place as set forth in this contract, once the relevant warranty period has expired. This is executed by the purchaser signing of the final acceptance (FAC) protocol for the work, which shall be drafted in accordance with this contract.

“month“ shall be a calendar month from 12:00 midnight of the first day of the calendar month to 12:00 midnight of the last day of the calendar month.

"construction equipment" shall be the equipment, devices, and tools required for assembly, inspection, and other purposes and necessary to complete the work, that however are not part of the work itself and whose ownership shall not pass from the contractor to the purchaser.

"change form" shall be the form drafted pursuant to Subsection 53.2.2 of the contract, which specifies a change required by either party in accordance with Article 53 of the contract, as well as the conditions for the implementation of such changes.

"purchaser" shall be the legal person identified in Article 1 of the contract, or its potential legal successors. Procedurally, the purchaser shall be represented by a natural person (the purchaser’s representative) of the purchaser’s own appointment.

"trial operation“ shall be a period of six (6) months (unless agreed otherwise) during which the work shall operate under the full responsibility of the purchaser and during which the contractor shall be present, as specified in this contract, and which begins upon signature on preliminary acceptance of the work and ends upon the signature of the trial operation protocol.

"quality plan" shall be the quality document, drafted in accordance with this contract, and in particular in accordance with the ČSN ISO 10005 standard, which defines the concrete procedures and sequence of activities related to ensuring the quality of the work.

"subcontractor" shall be any entity directly or indirectly contracted by the contractor to supply goods or execute any part of the work on the contractor‘s behalf, as specified in Article 21 of the contract.

"works" shall be the activities of the contractor that are essential to the completion of the work and that include disassembly, assembly, installation, design work, and other similar activities of the contractor within the scope of this contract.

"project documentation for the execution of construction” or "project“ shall mean the documentation for the execution of construction in accordance with Building Act No. 183/2006 Coll. on Spatial Planning and the Building Code (Building Act), as amended, and Decree No. 499/2006 Coll. (on construction documentation), as amended, compiled by the contractor according to Enclosure 3 to the contract to such a depth and level of detail that facilitates the faultless execution of the Work.

"provisional acceptance" shall be the purchaser’s acceptance of the work once commissioning and the performance test have concluded successfully as required by the contract. Provisional acceptance is executed by the purchaser signing of the provisional acceptance protocol (PAC) for the work drafted by the contractor in accordance with Article 31 of the contract.

"preliminary change order" shall be an order from the purchaser to the contractor issued pursuant to Subsection 53.2.5 of the contract.

”services” shall be the activities required to complete the work, including engineering work (supervision, commissioning, etc.), technical assistance to the purchaser, training of the purchaser’s representatives, importation of goods, and similar obligations of the contractor under this contract.

"contract for work" or the "contract" shall be the present contract for work concluded pursuant to Section 2586 et seq. of Act No. 89/2012 Coll. – the Civil Code, as amended. The contract consists of the contract documents listed in Article 4 of the contract; unless expressly agreed otherwise, the rights and obligations of the parties to the contract are determined pursuant to Section 2586 et seq. of the Civil Code.

"contract price" shall be the sum of money agreed by the parties in this contract.

"site" shall be the site specified in Enclosure 1 of the contract, where the contractor shall undertake the work (mainly including the delivery, installation, commissioning, and testing of the work). The site shall include assembly sites as set forth in the design.

"test ‘A‘" shall be tests and inspections performed in order to determine whether the work as a whole or a specific part thereof meet the technical parameters agreed for test A in the contract, particularly in Chapter 10.8.2 of Enclosure 1 of the contract.

"test ‘B‘" shall be the process used to verify whether the work fulfils the guaranteed parameters agreed in Enclosure 2 to the contract, pursuant to Article 33 of the contract.

"mechanical completion" shall be a state wherein the work has been completed in accordance with the design, all assembly has been finished (to the point where commissioning may begin), the physical structure is solid and clean in terms of assembly and statics, and where all required “cold” testing as specified in Article 29 of the contract has been completed successfully.

"commissioning" shall be the commencement of operation of the work once mechanical completion has been achieved and all tests required by Article 30 of the contract have been performed. The commissioning phase culminates in a successful performance test.

"rights of use" shall be all intangible property rights required for the purchaser to be able to use the work as agreed in the contract.

"goods" 	shall be all non-real estate property such as equipment, devices, materials, physical products, items, and things of all manner that are to be procured, delivered, installed, and tested by the contractor under this contract, with construction equipment being excluded from the definition of goods. Replacement parts supplied under this contract are also considered goods.

"warranty period" shall be the period during which the contractor is liable for the faultless completion and operation of the work, as specified in the relevant provisions of this contract. The warranty period begins upon the signing of the preliminary acceptance protocol (PAC) for the work and ends upon the signing of the final acceptance protocol (FAC) for the work.

”site facilities” shall be all temporary structures and fittings that serve the professional and social needs of persons participating in the work. Site facilities also include structures and fittings owned by the purchaser or third parties that are placed at the contractor’s disposal for the duration of the work.

"purchaser’s representative" shall be the natural person identified in Subsection 7.1 (d) of the contract, or any other person appointed such by the purchaser, who is empowered to execute certain rights or obligations that may be delegated to them within the scope of the purchaser's authorization. The purchaser or its representative shall demonstrate the scope of such authorization to the contractor by presenting the purchaser’s power of attorney to that effect.

"contractor’s representative" shall be the natural person identified in Subsection 7.1 (e) of the contract, or any other person appointed such by the contractor, who is empowered to execute certain rights or obligations that may be delegated to them within the scope of the contractor's authorization. The contractor or its representative shall demonstrate the scope of such authorization to the purchaser by presenting the contractor’s power of attorney to that effect.

"contractor" shall be the legal person identified in Article 1 of the contract, or its potential legal successors. Procedurally, the contractor shall be represented by a natural person (the contractor’s representative) of the contractor’s own appointment.

"change“ shall be any change or modification to the work and / or this contract; changes shall be managed and executed pursuant to the provisions of Article 53 of the contract.

"change order“ shall be an order to make a change given by the purchaser on the basis of a duly approved change form pursuant to the provisions of Article 53 of the contract.

Wherever the contract requires that a statement, approval, consent, confirmation, or appointment of any kind be made or issued, such a statement, approval, consent, confirmation, or appointment shall, unless agreed otherwise, be made in writing, and all references to “statement”, “approval”, “consent”, “confirmation”, and “appointment” shall be interpreted to mean written expression. No such action shall, in and of itself, create or constitute an amendment to this contract. No such statement, approval, consent, confirmation, or appointment shall be withheld or delayed without reason.

No failure of the purchaser to exercise one or more of its rights under this contract shall not constitute, nor shall be construed to constitute, the purchaser’s waiver of such rights and / or the purchaser’s consent in any matter.

# legal basis of the contract

This contract is executed pursuant to Section 2586 et seq. of Act No. 89/2012 Coll. – the Civil Code, as amended (hereinafter, the “Civil Code”). Unless expressly agreed otherwise, the rights and obligations of the parties hereto shall be determined in accordance with the provisions of Section 2586 et seq. of the Civil Code; this shall apply, in reasonable proportion, even if part of the rights and obligations agreed herein do not satisfy the definition of “work” employed by the Civil Code.

The contract is based on laws and other generally binding legal regulations and technical standards relating to the work in accordance with the contract.

Should any law or other item of general legislation relevant to the execution of the contract change while the contract is being executed, the contractor shall be required to notify the purchaser of such changes in writing and without delay, and, if subsequently requested by the purchaser to do so, to change the nature and / or manner of execution of the work as required by such changes and in accordance with Article 53 of the contract.

The parties hereby declare that the contract is the product of negotiations between them. In view of this, the parties further declare that, for the purposes of legal interpretation of the contract, neither party considers itself the author of the text of the contract, and that therefore, phrasing admitting multiple interpretations should not be interpreted so as to favour or disfavour, or as favouring or disfavouring, either party.

# CONTRACT DOCUMENTS

The following enclosures form integral parts of the contract:

|  | Enclosure 1 | Purchaser’s technical requirements on the work |
| --- | --- | --- |
|  | Enclosure 2 | Guaranteed parameters |
|  | Enclosure 3 | Documentation |
|  | Enclosure 4 | Timetable and execution plan for the work |
|  | Enclosure 5 | Organisation of the work |
|  | Enclosure 6 | Purchaser’s cooperation |
|  | Enclosure 7 | Training |
|  | Enclosure 8 | List of subcontractors |
|  | Enclosure 9 | Bank guarantees for the work and for the deposit |
|  | Enclosure 10 | Price Specification |
|  | Enclosure 11 | Roadmap of key work milestones and prices |
|  | Enclosure 12 | Rules for Contractors |
|  | Enclosure 13 | Contractor’s technical specifications |
|  | Enclosure 14 | Information on processing of personal data obtained from data subject and from other sources |

## The various contract documents listed above complement and elaborate upon each other. This contract is treated as a single entity during its interpretation. In the event of ambiguity or conflict, the provisions of the present contract proper take precedence over the contents of the enclosures listed above. In the event of doubt regarding the interpretation of the enclosures, the contents of lower-numbered enclosures take precedence over the contents of higher-numbered enclosures.

# GOVERNING LAW

The contract shall be governed by Czech law, disregarding any conflicting provisions.

# RESOLUTION OF DISPUTES

Should any dispute or difference of opinion arise from or in relation to the contract between the purchaser and the contractor, including any and all issues of validity, termination, or execution, whether during the execution of the work or after its completion, the parties to the contract shall strive to resolve the dispute or difference of opinion via negotiation in good faith.

  - Should the parties fail to reach resolution by negotiation within thirty (30) days from start of negotiations pursuant to Article 6.1 of the contract, each party may officially notify the other party, in writing, of the existence of a dispute (including its nature and basic points of dispute).

## All disputes arising from or in relation to the contract where negotiation fails shall be decided upon with the exclusion of the jurisdiction of ordinary courts and with final authority by the Court of Arbitration of the Czech Chamber of Commerce and Agricultural Chamber of the Czech Republic, in accordance with that court’s rules of proceedings, by third-party arbitrators, one each selected by each party. The third arbitrator and chairman of the Arbitration Board shall be selected by joint appointment by the parties’ arbitrators. The Court of Arbitration shall decide based on the preferences of the parties as these are expressed in the contract, on the evidence presented, and on Czech law.

Both parties shall have the right to bring a claim before the Court of Arbitration. If either party brings a claim before the court, the party’s deposition is required, in particular, to precisely specify the decision sought, enumerate its claims, and precisely specify the provisions of general legislation and / or the contract being used to support the claim.

## Decisions of the Court of Arbitration are final and may not be appealed or suggested for revision or inspection, except where this is allowed by the court’s rules of proceedings. Both parties shall be required to comply with their obligations arising from such decisions within the time period given in the same.

Proceedings of the Court of Arbitration of the Czech Chamber of Commerce and Agricultural Chamber of the Czech Republic shall be held in Prague, Czech Republic, in Czech.

While arbitration proceedings are ongoing, both parties shall continue to carry out their obligations as specified in the Timetable and Execution Plan for the work until such time as the court returns a decision. Should the contractor cease carrying out its obligations despite the preceding, the purchaser shall  be entitled to assuage its claims by drawing down against the bank guarantee provided in relation to the work, without this affecting the purchaser’s other rights.

# NOTICES

Unless provided otherwise in this contract, any claims, transmission of communication, information, etc. pursuant to the contract shall be made in writing and delivered in person, by registered mail, by courier service, or by e-mail to the relevant party’s address as specified hereunder in this article. Unless the contract provides otherwise, the following shall apply:

#### Notices sent by registered mail or courier shall be considered sent, for registered mail, on the date of the receipt provided by the post office of posting (or on the day the shipment was accepted by a courier, as documented by the courier’s receipt), and shall be considered delivered on the third (3rd) day after the date marked on the post office’s receipt (date shipment was accepted by courier from sender).

#### Written notices delivered in person shall be considered delivered on the day they are handed over the counterparty, or on the day the counterparty refuses to take delivery.

#### Notices sent by e-mail:

##### Notices sent by e-mail without the guaranteed electronic signature of the authorised person of the sender which, as the case may be, also contain digitised or scanned text shall be considered delivered on the date on which such e-mail is received by the recipient’s electronic mail server. Notices sent by e-mail without the guaranteed electronic signature of the authorised person of the sender shall not be used for a communication which contains legal acts or by which any claim is asserted;

##### Notices sent by e-mail with the guaranteed electronic signature of the authorised person of the sender which also contain digitised scanned text shall be considered delivered on the date on which such e-mail is received by the recipient’s electronic mail server. Messages sent by e-mail with the guaranteed electronic signature of the authorised person of the sender may also be be used for a communication which contains legal acts or by which any claim is asserted.

#### Any and all notices, communications, reports, etc. intended for the purchaser under this contract shall be sent to the purchaser’s representative at:

United Energy, a.s.

....................... - ...................................

Teplárenská 2,

Postcode 434 03, Most – Komořany

landline: +420  ...............................

mobile phone: +420 .......................

e-mail: ..........................

to cover any absence, with a copy always sent to:

................................

………………………

…………………..

Teplárenská 2,

Postcode 434 03, Most – Komořany

landline: +420  ………………..

mobile phone: +420  ………………..

e-mail: ......................

#### Any and all notices, communications, reports, etc. intended for the contractor under this contract shall be sent to the contractor’s representative at:

Company name

........................

Company address

landline: .......................

mobile: ………………

e-mail: ...................

to cover any absence, with a copy always sent to:

Company name

........................

Company address

landline: .......................

mobile: ………………

e-mail: ...................

Each party shall notify, in writing and without delay, the other party of any changes that may occur in the address where notifications are to be sent, in the names of their representatives, or relevant phone numbers, fax numbers or email addresses.

# SUBJECT OF THE CONTRACT

# PURPOSE OF THE WORK

The purpose of the work shall be to build up the “Waste-to-Energy Facility, EVO - Komořany, Most” to enable:

  - Recovery of the energy contained in waste, whereby the terms “wastes” or “waste” shall mean any and all waste intended for energy recovery in the EVO; this is a mixture of waste – mixed municipal solid waste, trade waste having the nature of municipal solid waste, street sweepings, crushed large-volume waste and possibly other waste approved by public-law authorities for energy recovery at the EVO.

  - Reduction of the volume of waste deposited in landfill areas and thus an extension of the lifetime of the existing landfill areas.

  - Use of a part of waste as a secondary raw material. In this case, ferrous and non-ferrous metals will be used as a raw material for metallurgical plants and slag (after certification) will be used as building and backfill material.

# SUBJECT OF THE CONTRACT – THE WORK

By signing this contract, the contractor agrees to perform for the purchaser the work, consisting of the execution of the project “Waste-to-Energy Facility, EVO - Komořany, Most”, which is required to be a “turnkey” project and to meet all requirements, conditions, specifications, and other information given in the contract.

The work shall include, and “turnkey” should be taken to mean, in particular the following:

#### Carrying out of analysis, verification and evaluation of the existing and ensuring all required surveys, inputs, information and data necessary for execution of the work.

#### Elaboration of documentation for execution of the project (design) necessary for proper execution of the work in the extent and under the terms and conditions determined by the contract, especially by Enclosure 3 of the contract.

#### Creation and submission of all other documentation required by Enclosure 3 to the contract.

#### Erection and installation of site facilities necessary for execution of the work in accordance with the contract and operation of the site for the time of execution of the work including its disposal (especially with regard to environment protection, fire protection and OHS within the meaning of valid legislation).

#### Provision, i.e., supply and assembly, of the required publicity tools (project / construction information) in accordance with the Graphical Manual for Projects Financed from the Modernisation Fund as published at http://www.modernizacni-fond.cz.

#### Provision of the necessary geodetic services required to execute the work.

#### Arrangement of site management and transport to and from the site, including offloading, toll duty, taxation, insurance, security, and warehousing of all goods, materials, components, etc. required to complete the work.

#### Demolition/dismantling of existing equipment which is to be replaced by the equipment installed within the work, or which will not be further used after completion of the work.

#### Execution of the construction associated with the work in the scope and under the terms agreed in the contract.

#### Supply and installation of the technological part of the work, including machinery and relating equipment, instrumentation and control system and electrical equipment in the scope and on conditions stated by the contract.

#### Connection of the work to existing structures and systems at the connection points defined in Enclosure 1 of the contract.

#### Supply of spare parts and fast-wearing parts in the scope and under the conditions agreed in the contract.

#### Supply of any and all special tools and devices required to maintain the work once completed in the scope and on the terms agreed in the contract.

#### Overall coordination of all deliveries of goods, works, and services within the scope of the work.

#### Management, monitoring, execution, inspection, and documentation of the preparation and realization phases of the work, including updates and the provision of required organizational and planning documentation in the scope and on the terms agreed in the contract.

#### Maintenance of the construction log, execution or creation of the necessary conditions to conduct professional supervision pursuant to Regulation 499/2006 Coll., on Construction Project Documentation, as amended. In accordance with Section 152(6) of Act No. 183/2006 Coll. (Building Act), as amended, shall be maintained electronically.

#### Achievement and documentation of quality characteristics required by the contract and pursuant to the quality plan, including all applicable inspections and tests in the scope and on the terms agreed in the contract.

#### Achievement and submission of all certificates of quality, materials, material testing, assembly progress, completeness, performed inspections, necessary revision reports, protocols, approvals, attestations, consents, and certificates required to execute, operate / use, and gain official approval for the work in the scope and on the terms required by the contract.

#### Granting rights of use necessary for the use of the work including relevant documentation in the scope and on conditions required by the contract.

#### Removal of all waste generated in connection with execution of the work pursuant to valid legislation and under the conditions specified in the contract.

#### Training of the purchaser’s operations and maintenance staff, in the scope and on the terms agreed in the contract.

#### Participation of responsible personnel of the contractor in discussing and approving the documentation prepared in accordance with Enclosure 3 of the contract, in guarantee measurement and trial operation under the conditions determined by the contract.

#### Provide the necessary cooperation to the purchaser in the process of obtaining approval for test operation of the work and obtaining official approval or other approvals / statements / decisions from public authorities.

#### Commissioning of the work including performance of relevant tests and completion of the work in the scope and under the conditions as determined by the contract.

#### Provision of adequate conditions for the execution of the guarantee measurement by an independent entity, and participation in such tests, including the provision and submission of required documentation.

#### Provision of guarantees for the quality of the work in the extent specified in the contract and the removal, free of charge, of any defects that may arise during the warranty period, under the conditions specified in the contract.

#### Collaboration and support of the purchaser during coordination of the work with follow-up projects executed by other suppliers.

#### Collaboration with the "site coordinator of occupational health and safety" appointed by the purchaser in accordance with Act No. 309/2006 Coll., as amended, and Government Decree 591/2006 Coll., and observance of suggestions, recommendations and orders issued by the coordinator.

The contractor shall perform, within the limits of the work, all works and services and deliver all goods, including those not explicitly listed in the contract but that may, logically and in view of the contract, be reliably deduced to be necessary for the correct functioning and completion of the work, this on the same terms as if such works, services, and / or goods were listed in the contract.

The subject of the work consists of the delivery of goods, works, services, and rights of use, and is further specified in detail in the contract documents listed in Article 4 of the contract.

# WORK TIMETABLE

## The contractor shall execute the work pursuant to the contract, and shall abide by the detailed timetable given below, and shall deliver the duly completed work to the purchaser on the timetable specified below:

| - Submission of the approved administrative order approved by the purchaser in accordance with Article 40 of the contract | no later than forty-five (45) days after the date of contract signature |
| --- | --- |
| - Submission of the approved Documentation Preparation Plan | no later than sixty (60) days after the date of contract signature |
| - Submission of the approved documentation for execution of the project – phase 1 | no later than one hundred twenty (120) days after the date of contract signature |
| - Submission of the approved documentation for execution of the project – phase 2 | no later than thirty (30) days prior to the commencement of the works at the site, or prior the commencement of production, whichever occurs first |
| - Submission of the documentation for requests to modify construction in progress – Phase 1 (documentation for changes occurring during preparation of the design - phase 1) | no later than sixty (60) days prior to the commencement of work at the site |
| - Submission of the documentation for requests to modify construction in progress – Phase 2 (documentation for changes occurring during phase 2 of the design and during execution and commissioning) | no later than sixty (60) days prior to the date of provisional acceptance of the work |
| - Submission of the approved documentation for test operation approval | No later than forty-five (45) days prior to commissioning |
| - Submission of the approved Documentation for official approval of the finished work | no later than thirty (30) days prior to completion of test operation |
| - Submission of other documentation per Chapter 2 of Enclosure 3 of the contract | Per the timetable specified in Chapter 7 of Enclosure 3 of the contract |
| - Site acceptance by the contractor | Per the timetable given in Enclosure 4 of the contract |
| - Training of the purchaser’s operations and maintenance personnel | Per the timetable given in Enclosure 4 of the contract |
| - provisional acceptance of the work | Per the timetable given in Enclosure 4 of the contract |
| - TRIAL OPERATION | Six (6) months after the date of provisional acceptance of the work |
| - final acceptance of the technological part of the work | Twenty-four (24) months from the date of provisional acceptance of the work upon fulfilment of the conditions specified in the contract |
| - final acceptance of the building part of the work | Sixty (60) months from the date of provisional acceptance of the work upon fulfilment of the conditions specified in the contract |

Enclosure 4 of the contract contains the Timetable and Execution Plan for the work, which provides a detailed timetable for execution of the work.

The contractor shall fulfil its obligations per the timetable specified in the Timetable and Execution Plan for the work (Enclosure 4 of the contract), and in the Detailed Timetable and Execution Plan for the work prepared and approved pursuant to Subsection 24.2 of the contract. Early execution of any of the contractor’s obligations under the contract shall only be allowed with the written consent of the purchaser received prior to such execution.

Documentation submitted pursuant to Enclosure 3 of the contract shall be considered duly submitted upon its formal, documented acceptance and approval by the purchaser.

Delivery of goods required for execution of the work shall be considered duly made upon delivery of such goods to the site in a state deemed satisfactory and acceptable, and the formal, documented acceptance of such delivery by the purchaser where such formal, documented acceptance is required per the contract.

Works and services rendered on the site shall be considered duly rendered upon their correct performance at the site and formal, documented acceptance by the purchaser where such formal, documented acceptance is required per the contract.

Training of the purchaser’s personnel shall be considered duly provided upon its provision by the contractor pursuant to the contract, as documented by a training protocol with trainee attendance rolls attached.

Early execution of any of the contractor’s obligations under the contract shall only be allowed with the written consent of the purchaser received prior to such execution, which shall not be unduly withheld.

Under Subsection 100(1) PPA, the purchaser reserves the right to amend the deadlines specified under Subsection 10.1 of the contract in the following instances:

- if additional works or changes to the work are required and will be performed in accordance with Section 222 PPA and which have a demonstrable effect on the performance of the work, always for the time necessary to perform them;

- due to objective obstacles to the performance of the contract arising from the decision or intervention of state administration or local government bodies in the process leading to issuing decisions or statements under the Building Act and other legislation and exceeding the legal deadlines for issuing such decisions, for no longer than for the time necessary to meet the requirements arising there from.

- due to particularly unfavourable or unsuitable climatic conditions, which according to the measurements of the Czech Hydrometeorological Institute (CHMI) - Kopisty u Mostu station and also taking into account the temperature difference of measured values ​​between CHMI - Liberec station and the place of the work (taking into Kopisty u Mostu station), do not correspond to normal climatic conditions (i.e. they deviate from long-term daily temperature averages and / or precipitation - whether rain or snow - in the period and place of the work, according to the data on territorial temperatures and / or territorial precipitation available on the CHMI website http://portal.chmi.cz/historicka-data/pocasi/uzemni-teploty), and which at the same time demonstrably prevents the contractor from performing the relevant part of the work. Restrictions on the progress of work due to these particularly unfavourable or unsuitable climatic conditions will be documented by the contractor and assessed by the purchaser in relation to the possibility of performing the work according to technological procedures prescribed for the part of the work, whether by legislation or technical standards (especially ČSN standards), whether these are explicitly stated in the contract and its enclosures, or with the proviso that the contractor is also obliged to submit an updated time schedule, which shows that the change of dates is justified, i.e. it is not possible to change the work without changes in the dates of execution of the work. It will not be possible to change the dates of performance of the work in a situation where the contractor performs the work at a time of unsuitable climatic conditions for reasons attributable to the contractor. It will always be possible to change the dates of the work by the time of this delay and its beginning and end will be recorded in the construction log.

- for reasons specified in Article 54 of the contract.

# CONTRACTOR’S OBLIGATIONS IN EXECUTION OF THE WORK

The contractor shall execute the work in its own name, at its own risk and on its own responsibility, and in accordance with the contract.

The contractor shall execute the work via its own employees or via its subcontractors. All contractor and subcontractor employees performing certain selected construction activities specified in Section 158 of Act No. 183/2006 Coll., on Land Use Planning and Construction Procedures (Building Act), as amended (including e.g. design work, construction management, technical oversight, calculations in statics, surveying, etc.) are required by the law above and relevant special legislation to possess authorization to perform such activities valid throughout the period required to execute the work. The contractor is under obligation to document such authorization to the purchaser before commencing the relevant activities. The contractor undertakes to respect the instructions of the persons authorized by the purchaser in the contract and in the construction log and the instructions of the occupational health and safety coordinator.

The contractor shall act as an independent contractor executing the contract. Pursuant to the contract, the responsibility for the manner of execution of the work rests solely and fully with the contractor. All personnel, representatives, and subcontractors contracted by the contractor to execute the contract are fully answerable to the contractor, and shall not be considered employees of the purchaser; nothing in this contract or any agreements the contractor may execute in relation thereto may be interpreted to create a direct contractual relationship between such personnel, representatives, or subcontractors on the one side and the purchaser on the other.

The contractor and its subcontractors shall exercise all due professional care in the execution of the work, and shall not jeopardize the safety and reliability of the operation of any other systems belonging to the purchaser. The contractor shall deliver or execute the goods, works, rights of use and services included in the subject matter of the contract in the scope and quality defined in the contract so that the result is the complete work which operates in a smooth, safe and reliable manner and which delivers the required parameters and complies with the conditions specified in the contract.

The contractor and its subcontractors shall comply with all general legislation, current ČSN  standards, and harmonized ČSN EN and ČSN EN ISO standards relevant to the work, as well as the purchaser’s internal guidelines, pursuant to Article 22 of the contract.

The contractor hereby declares that it entered into the contract on the basis of certain data and information relating to the work provided by the purchaser, and of information that it gained by inspecting the site, and of other work-related information available to it, and attests that it holds this information sufficient to execute the work in accordance with the contract, and acknowledges that any failure on its part to familiarize itself with all such information and data does not absolve the contractor of its responsibility to properly estimate the difficulty and price associated with the due and timely completion of the work.

Should the data and information provided by the purchaser be found to be insufficient or insufficiently complete to execute the contract, it shall be the responsibility of the contractor to obtain any additional required data and information. The purchaser shall provide the contractor, upon the latter’s justified written request made without undue delay, with all required cooperation in obtaining such additional data. The contractor shall not be entitled to any additional payments or timetable extensions relating to the work for reasons of faulty interpretation of any source information relating to the work.

The contractor shall, at its own expense, obtain all authorizations, approvals, and consents from Czech public authorities that may be needed to execute the contract, and obtain all other authorizations, approvals, and consents that may be required to execute the contract and / or operate the work, except those that the contract or Czech Republic legislation require the purchaser to obtain in its own name.

The contractor undertakes that it shall, within the bounds of the subject-matter of performance under the contract, ensure the execution of all tasks and activities mandated by Sections 15 and 16 of Act No.  309/2006 Coll., on Additional Occupational Health and Safety Requirements. The contractor shall submit to the purchaser its proposed notice of commencement of works addressed to the local Labour Inspectorate branch with jurisdiction over the site at least thirty (30) days and which, after confirmation by the customer’s representative, will then be sent to the local Labour Inspectorate branch with general validity. The contractor will then ensure the posting of the confirmed notice of commencement of works at the site per the conditions under Section 15(1) of Act No. 309/2006 Coll. over the duration of execution of the work, and any relevant updates thereto. The contractor shall also prepare documentation required for the Occupational Health and Safety Plan, which it will submit to the purchaser no later than sixty (60) days before commencement of works at the site. Pursuant to the contract, a log shall be maintained throughout the execution of the work of official interactions between the contractor and the Occupational Health and Safety Coordinator assigned to the work in matters within that coordinator’s purview. This log shall be available to the purchaser on site.

The contractor shall maintain at the site, for the entire duration of the contractor's activities there and up to the signing of the provisional acceptance protocol for the work, a complete set of all essential documents, project documentation, drawings, reports, logs, transcripts, letters, notices, etc. relating to the execution of the work. Upon the purchaser’s request, the contractor shall, without delay, enable the purchaser to peruse such documentation or, upon prior agreement, to make copies of such documentation.

Pursuant to Article 46 of the contract, the contractor shall be liable for any and all damages arising to the purchaser in relation with the contractor’s breach of mandatory legislation and standards as set out in Subsection 11.5 of the contract.

The contractor shall provide the purchaser with rights of use to the work in the scope and on the terms specified in the contract. Unless agreed otherwise in the contract, such rights shall be transferred to the purchaser no later than on the date of provisional acceptance of the work. To the extent that rights of use are creative works or other works subject to licensable intellectual property rights, the contractor shall provide the purchaser, no later than upon provisional acceptance, an exclusive license including the right of transfer to legal successors (incl. any potential successors to ownership of the work), but not including sub-licensing rights, to all such intellectual property rights subjects, in the scope required to enable the proper use, maintenance, repair, renovation, and modification of the work. Compensation for the provision of such rights, including licenses, has been included in the contract price.

The contractor shall, pursuant to Article 46 of the contract, reimburse the purchaser for any and all damages that may arise to the purchaser as a result of any infringement, or claim of infringement, of any rights, trademarks, copyright, or other intellectual property rights relating to the equipment, works, and goods used in the work or in relation to it, registered or otherwise valid in the Czech Republic as of the date of signing of the contract.

The contractor shall indemnify and hold harmless the purchaser and its employees for any claims, proceedings, sanctions, or activities ordered in administrative proceedings, as well as for all claims of warranty, damage, or other claims, losses, costs, and expenses of any kind, including costs of legal representation in matters of loss of life or limb or of loss or damage to any property, arising in relation to the execution of the work for reasons attributable to the contractor.

The contractor shall perform all import / export customs duties associated with the implementation of the work in accordance with Czech law.

In the event that the contractor requires the placement of a temporary structure on, or other modifications to, the purchaser’s premises, such changes shall need to be agreed in advance, in writing, with the purchaser.

The contractor is responsible for the room and board, healthcare, and insurance for all its employees, and the employees of its subcontractors.

Pursuant to Section 2(e) of Act No. 320/2001 Coll., on Financial Control in Public Administration and amendment of certain acts (the Financial Control Act), as amended, the contractor shall provide effective cooperation in the execution of any financial inspections.

The contractor shall, without undue delay, inform the purchaser in the event that insolvency proceedings are brought against the contractor. In such an event, the contractor shall further take all necessary steps to protect the purchaser’s property, including all portions of the work whose ownership has already passed to the purchaser.

The contractor shall cooperate in the maintenance and regular updating of a list of all subcontractors and their employees, including each subcontractor’s percentage share of the work.

The contractor shall ensure public roads affected by construction at the site are cleaned as necessary.

The contractor warrants and represents that all goods provided under the contract shall be genuine, new, and not used.

In accordance with Subsection 3.3.1 of the Instructions for Awarding Public Contracts for Programmes Co-Financed from the Budget of the State Environmental Fund of the Czech Republic (SFŽP ČR), the contractor commits to provide its approval to SFŽP ČR representatives to take photographs and make video recordings and to provide these to third parties, and the contractor commits to bind all its subcontractors to the provision of this approval.

The provisions of this Article 11 do not affect the obligation of the contractor to meet all its obligations and duties given in the entirety of the contract.

# PURCHASER’S COOPERATION

The purchaser shall, on the basis of a justified request or notification from the contractor, without delay and at the purchaser’s own expense, obtain all authorizations, licenses, approvals, and consents for which Czech Republic legislation explicitly mandates that they be procured by the purchaser in its own name. The contractor shall, however, provide all cooperation required by the purchaser to obtain such authorizations, licenses, approvals, etc. If, during the execution of the contract, authorizations, licenses, approvals, or consents are issued that are material to the execution of the contract and that are delivered solely to the purchaser, the purchaser shall, without delay, inform the contractor of all material information contained in or arising from such documents. If such information affects the execution of the contract, the parties shall commence consultations pursuant to Article 53 of the contract.

The purchaser shall hand over the site to the contractor in the state described in Enclosure 1 of the contract, and shall make the site accessible to the contractor on or, if possible, before the date given for such in the Timetable and Execution Plan for the work and in the Detailed Timetable and Execution Plan for the work prepared pursuant to Subsection 24.2 of the contract, this on the basis of a written request of the contractor delivered to the purchaser no later than one week in advance. The purchaser shall prepare, and both parties shall sign, a site acceptance protocol for the hand-over of the site to contractor.

The purchaser shall furnish the services of an Occupational Health and Safety Coordinator pursuant to Act No. 309/2006 Coll. Technical supervision for the work shall be performed by the purchaser or a third party engaged by the purchaser; this party may not be the contractor, nor a party linked to the contractor.

The purchaser shall, no later than on the date of commencement of commissioning, provide duly qualified operators in the scope and on the terms agreed in the Project for Commissioning and Test Programs given in Enclosure 3 of the contract.

Between the commencement of commissioning and the date of signing of the provisional acceptance protocol for the work, the purchaser shall cover waste disposal and provide all consumables, utilities and services required to operate the work in the scope of the firing capacity diagram.

The purchaser shall, before the start of the complex tests, obtain a decision from a Czech Building Authority approving test operation of the work pursuant to Section 124 of Act No. 183/2006 Coll., on Land Use Planning and Construction Procedures (Building Act), as amended. The contractor shall, upon request, provide the purchaser with all required cooperation.

The purchaser shall secure the execution and evaluation of the guarantee measurements per the provisions of the contract at its own cost and via an authorised and independent party.

The facilities, premises, consumables, utilities, and services to be provided by the purchaser as part of its cooperation with the contractor on the execution of the work are listed in Enclosure 6 of the contract. Such consumables, utilities, and services shall be provided by the purchaser in return for payment, to be agreed in separate contracts.

- Consumables, utilities, and services shall be supplied on existing interfaces only. The contractor shall, upon receipt of written consent from the purchaser’s representative, distribute such consumables, utilities, and services from existing interfaces to where they may be needed. The purchaser shall designate the connection points for utilities (compressed air, electricity) and water mains for the contractor to use, and shall allow the contractor to make the required temporary connections.

The purchaser is required to provide the necessary cooperation and reference material required to prepare the design in the scope and per the timetable specified in Enclosure 3 of the contract.

The purchaser shall provide, free of charge, initial training on Occupational Health and Safety, fire protection, and environmental safety to personnel of the contractor and its subcontractors.

The purchaser shall, free of charge, allow the personnel of the contractor and its subcontractors entry onto the premises of Komořany water heating plant, Teplárna Komořany, United Energy, a. s. (hereinafter, “TKY“), provided such access is both necessary and brief.

Regardless of the provisions of this Article 12 of the contract, the purchaser shall be required to fulfil of its obligations and duties specified in the contract. The parties have agreed that, should the purchaser be in delay in its cooperation, but the delay not materially affect the contractor’s execution of the work and / or the contractor’s ability to execute the work on the timetable agreed in the contract, then the contractor shall not be entitled to any extensions of the timetable given in the contract, nor to a change in the contract price; furthermore, the provisions of Section 1968, second sentence (on Creditor Default) of the Civil Code shall not apply to such delays on the part of the purchaser.

The parties have agreed to exclude their relationship under this contract from applicability of the provisions of Section 2591 (on Purchaser Cooperation) of the Civil Code.

Everything not provided by the purchaser pursuant to the contract shall be provided by the contractor and included in the contract price.

# PAYMENT

# CONTRACT PRICE

## The purchaser commits to pay the contractor the contract price for proper execution of the work under the contract which totals:

EUR ……………………

(in words: …………………………………………………. EURO)

for the part of the work abroad (the part of performance whose price is determined in EUR)

and

..................................... CZK

(in words: ......................................... Czech koruna)

for the domestic part of the work (the part of performance whose price is determined in CZK).

## The contract price is exclusive of Value Added Tax (hereinafter, “VAT”) payable in the Czech Republic. VAT payment shall be handled pursuant to relevant legislation in effect at the time of the transaction(s) to be taxed.

The contract price includes all costs, risks, reserves, and profits of the contractor related to the proper and timely completion of the work, as well as all taxes, fees, tolls, licenses, and usage rights that may arise pursuant to the contract, and further all financial expenses related to the execution of the work and to the evolution of prices and exchange rates, until such time as the contractor’s obligations under this contract have been fulfilled.

- The contract price is a mutually-agreed fixed price, subject to no other changes than those explicitly provided for in the contract.

Enclosure 10 of the contract specifies price details and by-item breakdowns of the work. Prices of goods, rights of use, works, and services not explicitly listed in those price details but part of the contract are assumed to be included in the items that are listed in the price details.

The contractor shall provide the purchaser, for the purposes of booking of the work’s transfer into the purchaser’s ownership, with details of the contract price prepared in accordance with the purchaser’s accounting methods, no later than thirty (30) days before the provisional acceptance date agreed for the work in the contract, details of the purchaser’s accounting methods to be provided to the contractor ninety (90) days before the provisional acceptance date, unless the purchaser stipulates otherwise.

# TERMS OF PAYMENT

All justified payments associated with the work shall be made in the currencies in accordance with paragraph 13.1 of the contract.

Payments during execution of the work (instalments of the contract price) shall be made partly as the deposit payment specified in Subsection 14.4 (a), and partly as partial payments (instalments) against the purchaser's approval of duly reached milestones as specified in Enclosure 11 of the contract.

The contractor's claims of payment against the purchaser shall be made in writing, in the form of an advance invoice (request for payment in advance) with subsequent tax receipt issued against the received payment (advance), and of partial invoices – tax receipts including adequate description of the goods and rights of use supplied and / or works and services rendered, and including all other documentation required under the contract, and only once the contractor’s obligations required for payment under the contract have been met. The advance invoice and partial invoices / tax receipts must use the same definitions of works, services, rights of use, and goods that are used in the price tables, the Roadmap of Key work Milestones and Prices, and the Timetable and Execution Plan for the work.

- The advance invoice and partial invoices / tax receipts need to be demonstrably delivered to the purchaser at:

United Energy, a.s.

Teplárenská 2,

Postcode 434 03, Most – Komořany

Czech Republic

with the demonstrable date of delivery being the date on the purchaser’s stamp printed on the envelope upon taking delivery. The contracting authority shall not reject an electronic invoice (advance invoice or partial invoice – tax receipts) issued by the contractor for the performance of the public contract in the grounds of its format, if such format complies with the European standard for electronic invoices.

The parties have agreed on the following structure of payments:

#### Deposit – advance payment

#### A deposit of fifteen (15) per cent of the contract price for the work specified in Subsection 13.1 of the contract, plus VAT, shall be claimed by the contractor within twenty-one (21) days from the effective date of the contract, pursuant to Subsection 57.2 of the contract. The purchaser shall pay to the contractor the deposit within thirty (30) days of the effective date of the contract and receipt of the following:

##### the contractor’s advance invoice for the amount of the deposit, plus VAT

##### the contractor’s bank guarantee for the deposit, made out on the deposit amount exclusive of VAT, issued pursuant to Subsection 16.2 of the contract and to Enclosure 9 of the contract.

##### the contractor’s bank guarantee for the execution of the work, issued pursuant to Subsection 16.1 of the contract and to Enclosure 9 of the contract

The contractor shall provide the purchaser, no later than fifteen (15) days of the date of receipt of the Deposit payment pursuant to Subsection 14.4 (a) of the contract in the contractor’s account, with a tax receipt containing all information required of tax receipts by generally binding Czech legislation as it is in effect on the day the invoice (tax receipt) is issued, and further containing:

Identification of the deposit covered by the tax receipt

the contractor's corporate name and registered or office address

the purchaser’s corporate name and registered address, given as:

United Energy, a.s.

Teplárenská 2,

Postcode 434 03, Most – Komořany

Czech Republic

the purchaser’s and the contractor’s Business Registration numbers

the purchaser’s and the contractor’s VAT numbers

the contractor's Business Registry file ID information

the purchaser’s contract number

#### Invoicing based on work progress:

Upon the completion of the work’s milestones as specified in Enclosure 11 of the contract, the purchaser shall pay the contractor the consideration agreed for the milestone in question as milestones are met, as given in Enclosure 11 of the contract, and within thirty (30) days of the receipt form the contractor of:

##### copies of the progress reports pursuant to Subsection 20.3 (d) of the contract signed by the purchaser,

##### the contractor’s partial invoice

Partial invoices shall be made out to one hundred (100) per cent of the value agreed for partial payments, reduced for the aliquot part of the deposit (the advance payment) specified in Subsection 14.4 (a) of the contract.

The final partial invoice as per Enclosure 11 of the contract (i.e., the final payment) shall further include a detailed listing of the contract price for the work, for the purposes of the entry of the work’s various portions into the purchaser’s property, plant & equipment account, as required by Act No. 563/1991 Coll., on Accounting, as amended.

The contractor shall issue partial invoices / tax receipts for milestone payments as the requisite milestones are met, once milestones have been met.

Invoices issued by the contractor, given the contractor is a Value Added Tax (hereinafter, “VAT”) payer in the Czech Republic, shall also serve as tax receipts, and shall be issued on the day of the taxable transaction in question, but in any event no later than fifteen (15) days from that date, and shall meet all requirements on tax receipts pursuant to applicable general legislation as it is in effect on the invoice issue date. The invoice / tax receipt shall contain all information required by Section 435 (Information Required on Certain Documents and on the Internet) of the Civil Code, as well as all information required for tax receipts pursuant to Act No. 235/2004 Coll., on Value Added Tax, as amended (hereinafter, the “VAT Act”); in particular, the following:

- the contractor’s corporate name and registered office or place of business where taxable delivery is made;

Business Registry file ID information

the purchaser’s corporate name and registered address, including first and last name of the purchaser’s representative in matters of contract, the purchaser’s corporate name and registered address as follows:

United Energy, a.s.

Teplárenská 2,

Postcode 434 03, Most – Komořany

Czech Republic

the purchaser’s and the contractor’s VAT numbers

the purchaser’s and the contractor’s Business Registration numbers

Invoice number

Scope and subject of taxable transaction, incl. partial items and accounts

Date of issue

Price inclusive of VAT

Aliquot part of Deposit attributable to partial invoice, incl. number of advance invoice, to be deducted in before-tax amount and tax portions

Trading name, code, and SWIFT ID of the contractor's bank

Number of account payment is to be made into, including IBAN; account must be registered in the VAT Payers Registry

Invoice due date, pursuant to contract

the purchaser’s contract number and name of work,

the contractor's stamp and signature

In the event that milestone (part payment) deadlines given in the Roadmap of Key work Milestones and Prices and the Detailed Timetable and Execution Plan for the work pursuant to Subsection 24.2 of the contract or quality or other material provisions of the contract are not being met for reasons due to the contractor, the purchaser may postpone payment of subsequent partial invoices until such time that the non-conformity has been resolved. In that event, the contractor shall continue carrying out its obligations under the contract regardless.

The purchaser may return invoices lacking the formal requirements given in this Article 14 of the contract, or if otherwise defective, to the contractor at any time before the invoice due date. In that event, the purchaser shall always give the contractor the reasons for the return. Depending on the nature of the issue, the contractor shall then either correct or re-issue the invoice and any attachments. The original due date shall be considered void in the event of a justified invoice return. A new due date shall be set counting from the day when purchaser receives an amended, corrected, or re-issued invoice possessing all features required by the contract.

In the event that the contractor breaches its obligations under the contract, the purchaser may set off against the contractor's claims on the purchaser any of the purchaser’s justified claims on the contractor and their accessories; in particular, contractual penalties and penalties or other sanctions levied against the purchaser by public authorities in relation to the contractor's execution of the work (or execution of the work by other parties engaged to that end by the contractor), provided that the penalty or other pecuniary sanction is the fault of the contractor (or of another party engaged by the contractor to execute the work or a part thereof).

- This right of set-off further extends to all other claims, and their accessories, of the purchaser on the contractor (pursuant to the contract, or to other agreements between the purchaser and the contractor, or to enforceable judicial or administrative rulings), including contractual penalties and claims of damages, as well as claims relating to the purchaser’s provision of goods or services to the contractor in return for payment.

- The contractor may not, at its own discretion, set off any of its claims, even partially, against the purchaser's claims without the prior written consent of the purchaser.

- In the event that the contractor has pecuniary obligations vis-à-vis its subcontractors in the work which are unlawfully more than 1 month past due, and exceeding, in sum, ten (10) per cent of the value of the agreement concluded between the contractor and that individual subcontractor, the purchaser may pay the contract price for the work, or a part thereof, directly to the subcontractor, in accordance with the provisions of general legislation.

All banking fees and expenses arising to the purchaser with the purchaser’s bank in relation to the purchaser’s payments to the contractor shall be borne by the purchaser; other banking fees and expenses shall, unless agreed otherwise in the contract, be borne by the contractor and part of the contract price.

The contractor shall not be entitled to any financial or other advantages arising from its potential early completion of works or services or early supply of goods or rights of use, or from early completion of the work as a whole.

The prices of any additional work requested and duly approved by the purchaser shall be calculated on the terms given in Article 53 of the contract.

No payment made by the purchaser under Article 14 of the contract shall be considered to constitute the purchaser's acceptance of the work or any part thereof. No partial payment made by the purchaser shall be held to constitute acknowledgement of any debt owed by the purchaser to the contractor in the sense of Section 2054(2) (Other Ways of Recognising Debt) of the Civil Code.

The purchaser shall not be considered to be in delay or default on its obligation to pay invoices so long as the purchaser's account was debited for the amount due to the contractor no later than on the invoice / advance invoice due date.

If any party is in default with payment of a contractual fine, invoice, or other pecuniary obligation, or is in default with the fulfilment of an enforceable judicial decision involving a pecuniary obligation, the default interest shall be set to 0.03% of the outstanding amount for every day of default and until payment of the outstanding amount in full.

# TAXES, CUSTOMS, AND FEES

## The contractor hereby declares to have familiarized itself with the tax, customs, and administrative legislation of the Czech Republic and to have included in the contract price and to be prepared to pay all taxes, customs duties, and fees that are or may be required by the relevant public authorities in relation to the execution of the work.

## The contractor hereby declares that the bank account it has given in this contract is an account registered in the VAT Payers Registry of the Czech Tax Administration pursuant to Act No. 235/2004 Coll., on Value Added Tax, as amended.

## The contractor declares that, as of the date of signing of this contract, the Tax Administration has not declared it an unreliable taxpayer in the sense of Section 106(a) of Act No. 235/2004 Coll., on Value Added Tax, as amended; that the associated proceedings have not been brought against it, and that it is not subject to conditional deferral of such proceedings with the relevant Tax Authority.

## The contractor acknowledges and consents that, in the event that it ceases to meet the conditions given in Subsections 15.2 and 15.3 of the contract, the purchaser shall pay the amount of Value Added Tax given on the contractor’s tax receipts directly into the account of the contractor's Tax Administration office, while the contractor shall be paid the before-tax amount.

## In the event that the contractor fails to pay any taxes, customs duties, or fees, and that public authorities subsequently claim such payments from the purchaser and the purchaser pays, the purchaser may claim reimbursement from such payment and any other related costs and damages from the contractor. Should the contractor fail to reimburse the purchaser for such payments, costs, or damages within 30 days of being requested to do so, the purchaser may set off the amount owed against any of the contractor’s claims, or else demand satisfaction of its claim from the bank guarantee.

## The contractor shall ensure that the no obligation arises to the purchaser to guarantee or directly pay any taxes, fees, or other mandatory payments that are properly the responsibility of the contractor.

# BANK GUARANTEES FOR THE WORK AND FOR THE DEPOSIT

Bank guarantee for the work:

### The contractor shall procure and submit to the purchaser a bank guarantee for the proper execution of the work in the amount of ten per cent (10%) of the contract price exclusive of VAT, denominated in the same currency as the contract price. The contractor shall submit the bank guarantee to the purchaser within twenty-one (21) days from the effective date of the contract, pursuant to Subsection 57.2 of the contract. The bank guarantee for the execution of the work must be valid until at least sixty (60) days after the date of signing by both parties of the final acceptance protocol for the technological part of the work pursuant to Subsection 33.3 of the contract.

### The contractor shall, no later than thirty (30) days before the expiry of the bank guarantee for the work pursuant to the preceding Subsection 16.1.1 of the contract, submit to the purchaser a bank guarantee for the execution of the work in the amount of three per cent (3%) of the contract price exclusive of VAT, denominated in the same currency as the contract price. This bank guarantee shall be valid from the day following the date of expiry of the bank guarantee specified in the preceding Subsection 16.1.1 of the contract, and must remain valid until at least sixty (60) days after the date of signing by both parties of the final acceptance protocol for the building part of the work pursuant to Subsection 33.3 of the contract.

### The bank guarantee for execution of the work pursuant to Subsections 16.1.1 and 16.1.2 of the contract must be issued by a first-class European bank with a minimum S&P rating of BBB+ and which maintains its registered office or representative office in the Czech Republic and which has a bank license issued by the Czech National Bank and on which the contractor and the purchaser agree,

### The bank guarantee for the work shall be irrevocable, unconditional, payable upon first request and without the need to give due reason, and shall comply with the conditions given in the template form in Enclosure 9 of the contract. The purchaser shall have no fewer than seven (7) days to assess and approve the suitability of the form.

### The bank guarantee for the work shall be the responsibility of the contractor. All expenses related to the bank guarantee for the work and its provision shall be borne by the contractor and included in the contract price.

### In the event of delay in the final acceptance of technological part of the work or the building part of the work pursuant to Subsection 33.3 of the contract for reasons due to the contractor, the contractor shall, at its own expense, ensure the extension of the relevant bank guarantee for the work to comply with the conditions given in Subsection 16.1.1 or 16.1.2 of the contract. Should the contractor fail to do so, the purchaser may, fourteen (14) days before the expiry of the original bank guarantee for the work, use the existing bank guarantee for the work or a part thereof for the purchaser's benefit, without this affecting any of the purchaser's rights under the contract. All amounts withdrawn from the bank guarantee in this manner shall be returned to the contractor without delay once the contractor submits to the purchaser a duly extended bank guarantee.

### The bank guarantee for the work shall be a guarantee of all of the contractor’s obligations arising from or in relation to the contract. These obligations include the provision of the bank guarantees for the work pursuant to Subsection 16.1.2 of the contract.

### A template form for the bank guarantee for the work including parameters and terms required by the purchaser is provided in Enclosure 9 of the contract.

### The bank guarantees for execution of the work in accordance with Subsection 16.1.1 or 16.1.2 may be merged into a single bank guarantee if such bank guarantee is extended for the required bank guarantee period at least thirty (30) days prior to the expiration date of the bank guarantee for execution of the work in accordance 16.1.1 with Subsection and concurrently reduced from 10% to 3% of the contract price exclusive of VAT.

### In accordance with Subsections 16.1.1, 16.1.2 and 16.2.1, the bank guarantees may be replaced with adequate suretyship insurance in accordance with the provisions of Subsection 2868 et seq. of the Civil Code, under the same bank guarantee conditions laid down in this Article 16 of the contract

Bank guarantee for the deposit

### The contractor shall obtain a bank guarantee for the deposit in the amount given in Subsection 14.4 (a) of the contract and submit this guarantee to the purchaser in accordance with the contract. The bank guarantee for the deposit shall remain valid no less than thirty (30) days after the signing of the mechanical completion protocol for the work pursuant to Article 29 of the contract.

### The bank guarantee for the deposit pursuant to Subsection 16.2.1 of the contract must be issued by a first-class European bank with a minimum S&P rating of BBB+ and which maintains its registered office or representative office in the Czech Republic and which has a bank license issued by the Czech National Bank and on which the contractor and the purchaser agree,

### The bank guarantee for the deposit shall be irrevocable, unconditional, payable upon first request and without the need to give due reason, and shall comply with the conditions given in the template form in Enclosure 10 of the contract. The purchaser shall have no fewer than seven (7) days to assess and approve the suitability of the form.

### The bank guarantee for the Deposit shall be the responsibility of the contractor. All expenses related to the bank guarantee for the Deposit and its provision shall be borne by the contractor and included in the contract price.

### In the event of delay in the mechanical completion of the work pursuant to Article 29 of the contract for reasons due to the contractor, the contractor shall, at its own expense, ensure the extension of the bank guarantee for the Deposit to comply with the conditions given in Subsection 16.2.1 of the contract. Should the contractor fail to submit the extended guarantee to the purchaser within twenty-one (21) days from the purchaser's request, the purchaser may draw down against the existing bank guarantee for the Deposit up to its total value. All amounts withdrawn from the bank guarantee in this manner shall be returned to the contractor without delay once the contractor submits to the purchaser a duly extended bank guarantee.

### A template form for the bank guarantee for the deposit including parameters and terms required by the purchaser is provided in Enclosure 9 of the contract.

### Based on achievement of the partial milestones towards completion of the work, the contractor has the right to proportionally reduce the amount of the bank guarantee for the deposit and the purchaser is obliged upon written request from the contractor to provide the contractor to cooperate by issuing a written request to the bank issuing the bank guarantee for the deposit in which it states the following: “The guarantee amount of this bank guarantee is hereby reduced from ........ to….....” Such request to reduce the amount of the bank guarantee must be signed by the person(s) authorised to act on behalf of the purchaser, and must be delivered to the bank via registered mail, a courier service, or in person, and the signature(s) must be officially certified or verified by the purchaser's bank.

## If the bank which issued by the bank guarantee(s) under the contract enters into liquidation or has been declared bankrupt, or if other proceedings have been initiated as a result of bankruptcy of the bank, if the Czech National Bank license has been revoked, or the Czech National Bank has initiated proceedings to revoke a bank license or the bank has been forced into administration, the contractor is obliged to terminate the validity of such bank guarantee and to provide the customer with a new bank guarantee from a different bank, whereby the provisions of Subsections 16.1 to 16.3 of the contract apply in kind to such new bank guarantee(s). If the contractor fails to perform such obligation after prior written notification from the purchaser, the purchaser is authorised to withhold payment on any liabilities to the contractor in the corresponding amount and withhold such amount as security, whereby the purchaser must release all such withheld funds within fourteen (14) days from the submission of the new bank guarantee to the purchaser pursuant to Subsection 16.3 of the contract.

# INTELLECTUAL PROPERTY

# LICENSES AND RIGHTS OF USE TO TECHNICAL INFORMATION

For the purposes of the operation and maintenance of the work, as this consists of the individual tasks, procedures, and processes specified in the contract, and further for the purposes of repair, renovation, and modification of the work, the contractor shall provide to the purchaser a non-exclusive, non-transferable (excepting transfer to legal successors, including potential successors to ownership of the work), time-unlimited license valid in Czech Republic territory relating to patents or other industrial intangibles rights owned by the contractor or by a third party by whom the contractor is authorized to license such rights; the contractor shall also grant to the purchaser a non-exclusive, non-transferable (excepting transfer to legal successors, including potential successors to ownership of the work), time-unlimited right of use of know-how (if applicable) and other technical information provided to the purchaser under the contract, valid in Czech territory. No provision contained in such documents may not be interpreted as the transfer of ownership of any patents, trademarks, copyrights, know-how, or other intellectual property rights from the contractor or a third party to the purchaser if such a transfer would be outside the scope of the contract.

The fees for the provision licenses and rights specified in Subsection 17.1 are, in full, included of the contract price.

The purchaser and the contractor have agreed on the following scope expansion of the rights of use for documentation provided pursuant to Chapter 2 of Enclosure 3 of the contract:

#### The purchaser may familiarize third parties with the documentation specified above, to the extent necessary and to the extent that such parties may provide repair, maintenance, and / or operation services for systems included in the work pursuant to the contract.

#### The purchaser shall not use the documentation specified above to repair, maintain, or operate systems owned by third parties, shall not manufacture new units of similar systems on behalf or for third parties, and shall not provide the documentation to third parties that would perform such activities on behalf or for other third parties.

# confidentiality regarding information and contractual documents, Ethical conduct between the parties

Except for the provisions of Subsection 18.4 of the contract, each party shall hold as confidential all commercial and technical information, including specifications, plans, drawings, patterns, etc., as well as other information and materials, provided to them by the other party on papers (media) marked restricted-access or otherwise exchanged between the parties during the execution of the contract; neither party shall use such information for its financial or other benefit nor for the benefit of third parties, nor make such information accessible to third parties without the prior written permission of their counterparty in this contract, nor use such information and materials for any purpose other than to execute the contract. The requirement of permission shall be waived for provision of access to the subcontractors listed in Enclosure 8 of the contract, provided such disclosure is limited to the extent necessary to that particular subcontractor’s execution of the work and under the condition that confidentiality is maintained pursuant to the contract.

The obligation of confidentiality shall also be binding upon subcontractors and any third parties to whom the information specified in Subsection 18.1 of the contract may have been provided by the contractor with the purchaser's approval and on the terms specified by this Article 18 of the contract. The contractor shall ensure that such parties are bound by confidentiality at least to the same extent as the contractor. The contractor shall be liable for any subcontractor breaches of the obligation specified in this subsection.

All documents listed in Subsection 18.1 of the contract, whether or not marked as restricted-access documents (media) by the purchaser, and excepting the contract itself, are the property of the purchaser and, if requested by the purchaser, all copies thereof shall be returned to the purchaser once the contractor has executed the contract.

The purchaser and the contractor each may, even without the other party’s approval, disclose information that the other party has marked as restricted-access documents (media), to the extent necessary, if for the purposes of the contract:

#### Disclosure is required by public authorities, including financial or other authorities empowered to assess the work’s compliance with general legislation;

#### Disclosure is required for the activities of consultants or other parties involved in executing the contract; in such an event, the contractor shall ensure that the parties in question are made aware of the confidentiality obligations set forth in this article herein, and agree to be bound thereby.

The obligation to secure restricted-access documents (media) shall endure for a period specified by the party having marked the documents (media) as restricted-access. In the event that the party failed to specify such a period, the obligation to secure restricted-access documents (media) shall terminate automatically ten (10) years after the signing of the provisional acceptance protocol for the work, unless a longer period is required by relevant legislation.

The information types listed below shall be excluded from the obligation to hold as confidential restricted-access documents (media):

#### Information that is or has become public knowledge, through no fault of the recipient

#### Information legally obtained by the recipient from third parties not involved in the preparation and execution of the work

#### Information such as is commonly given in business reference lists

#### Information intended for publication, in the format and scope approved by the purchaser

In the performance of this contract, both parties shall obtain personal data protected by Regulation (EU) 2016/679 on the protection of individuals with regard to the processing of personal data and on the free movement of such data (hereinafter referred to as GDPR). Both parties are therefore obliged to maintain confidentiality about all the facts the disclosure of which to a third party could cause harm to another party and to protect and develop the reputation and reputation of the other party, its owners and associates (family members, members company bodies, employees, etc.).

Neither party may claim confidentiality in court / arbitration proceedings arising from or relating to the contract. This also includes proceedings before other public authorities, financial inspections, tax inspections, proceedings before European Union authorities, and provision of information to third parties bound by law to hold such information as confidential (e.g. auditors, attorneys).

The parties agree to adhere to the highest ethical and anti-corruption standards over the duration of the contract.

The parties therefore define the following term: “corrupt behaviour” is the offer, promise, or giving, or the requesting or acceptance of, any undue advantages or benefits, as well as the giving or acceptance of remuneration, unreasonable gifts, acts of hospitality, or direct or indirect reimbursement for expenses to or from any person employed by or acting as a member of the governing body of any private or public entity (including all persons making decisions on behalf of or acting in any capacity for any private or public entities or organizations), for the purpose of facilitating negotiations, receiving, retaining, or manipulating the course of business, or to gain any other advantage in the procurement procedure to award the contract and / or conclusion and performance of the contract.

The contractor shall ensure that itself and all entities controlled by it (defined as in Sections 74 through 77 of Act No. 90/2012 Coll., on Trading Companies and Associations, as amended) adhere to these anti-corruption provisions.

The contractor shall also ensure that its controlling entity, as defined in Sections 74 through 77 of Act No. 90/2012 Coll., on Trading Companies and Associations, as amended, adhere to these provisions vis-à-vis the purchaser.

The purchaser reserves the right to terminate the contract in the event that it becomes aware that the contractor, or an entity controlled by or controlling the contractor, engaged in corrupt behaviour in relation to the performance of the contract, directly or indirectly through a representative, and took no timely and adequate measures to remedy the situation.

# EXECUTION OF THE WORK

# PARTIES‘ REPRESENTATIVES

Purchaser’s representative

### The purchaser’s representative is identified in Subsection 7.1 (d) of the contract. The purchaser shall notify the contractor, without delay and in writing, if a different purchaser’s representative is assigned.

The purchaser’s representative shall represent the purchaser and act on the purchaser's behalf, in the scope given in the purchaser's power of attorney, throughout the duration of the contract, as well as communicate to the contractor all notices, instructions, information, and other information exchanges from the purchaser pursuant to the contract.

All notices, instructions, information, and other exchanges pursuant to the contract from the contractor to the purchaser shall be communicated to the purchaser’s representative, unless the contract specifies another recipient.

Authorisation of the purchaser’s representative has no prejudice towards the authorisation of the purchaser’s governing body to act on behalf of the purchaser.

contractor’s representative and construction manager (CONSTRUCTION FOREMAN)

### The contractor’s representative is identified in Subsection 7.1 (e) of the contract. The contractor shall notify the contractor, without delay and in writing, if a different contractor's representative is assigned.

### The contractor's representative shall represent the contractor and act on their behalf. The purchaser shall interact with the contractor's representative on the good-faith assumption that the latter is authorized to make all decisions they are making on behalf of the contractor. The contractor's representative communicates to the purchaser all notices, instructions, information, and other information exchanges pursuant to the contract from the contractor.

All notices, instructions, information, and other exchanges pursuant to the contract from the purchaser to the contractor shall be communicated to the contractor's representative, unless the contract specifies another recipient.

Authorisation of the contractor’s representative has no prejudice towards the authorisation of the contractor’s governing body to act on behalf of the contractor.

### The contractor’s representative shall participate in all progress meetings pursuant to Subsection 20.3 (c) of the contract, unless the purchaser and the contractor demonstrably agree otherwise.

### No later than at the date of commencement of works at the site, the contractor shall institute a construction office at the site and appoint a suitable staffer as the construction manager (i.e., the Construction Foreman in the sense of Act No. 183/2006 Coll., the Building Act, as amended) responsible for operations at the site. The construction manager manages the construction of the work, supervises all contractor works at the site and shall be present at the site at all times during standard business hours (usually, 8 a.m. to 5 p.m.) throughout the duration of the contractor’s activities at the site, unless on leave, sick, or absent in relation to the execution of the contract. Whenever the construction manager is absent from the site, they shall be deputized for in full by their deputy. The purchaser or their representative shall submit all notices, instruction, information, and other information exchanges relating to the works at the site to the construction manager or, if absent, to their deputy. The construction manager shall be authorized to make all such decisions as may be required for the on-site management of the execution of the work, and shall participate in all progress meetings pursuant to Subsection 20.3 (c) of the contract, unless the purchaser and the contractor demonstrably agree otherwise.

### The purchaser may request the contractor to replace any and all of the contractor’s personnel who demonstrate incompetence and / or gross negligence in the execution of their duties, or whose presence at the site is otherwise objectively unwelcome. Such contractor personnel may not continue to be employed, or be re-employed, at the site without the purchaser's approval. Such replacement requests shall be made in writing and duly justified. The contractor shall then carry out such requests without undue delay. The contractor shall replace any and all personnel removed under this clause by other suitable personnel without undue delay. This provision shall apply equally to subcontractor personnel.

# INFORMATION SUBMITTED TO PURCHASER

In preparing all documentation, i.e., drawings, specifications, calculations, protocols, lists, manuals, procedures, timetables, reports, etc. (hereinafter as “information”) relating to the execution of the work, the contractor shall employ all such knowledge, experience, due diligence, and professional care as may be required for a properly-engineered work.

All such information submitted by the contractor, or requested from the contractor by the purchaser, for the purchaser's approval shall be prepared by the contractor, at its own expense, and shall comply with the requirements of the contract. Excepting the provisions of Subsection 23.2 of the contract, the purchaser's approval, assessment, or consent to information provided by the contractor shall not affect the contractor’s responsibility for the correctness and completeness of the information provided, nor of the obligation to comply in full with the contract. The contractor may not modify or change information approved or consented to by the purchaser without a re-assessment of the modifications or changes by the purchaser. The purchaser's judgements as to the appropriateness and correctness of the information provided shall be final and binding upon the contractor. All information provided by the contractor for the purchaser's approval or consent pursuant to the contract shall be verified by the contractor and marked as correct and adequate in view of the goods and rights of use to be supplied and the works and services to be rendered by the contractor. Unless agreed otherwise, all information provided to the purchaser shall be in the Czech language.

Progress reports on the work

## The contractor shall keep the purchaser informed of its activities and progress in relation to the work. To that end, the contractor shall prepare and submit periodic progress reports, whose basic contents, format, number, timetable, and frequency is specified below in this Article 20 of the contract. The purchaser may, if justified, request modification or expansion of this basic scope of contents, format, number, timetable, and / or frequency, in which event the contractor shall comply with such requests without it affecting the contract price. The difficulties in implementation will be described in the summary of the report. The manner and format in which work progress reports are to be made shall be further agreed by the parties in the Administration Rules.

## The reports described in this Subsection 20.3 of the contract shall serve to inform the purchaser of the contractor’s progress. The contractor shall submit particularly the following:

#### Daily report (construction log)

The contractor shall prepare daily reports in the form of entries in the construction log kept at the site, detailing the works done during the preceding day. Pursuant to applicable legislation, the construction log shall begin on the day the contractor accepts custody of the site and end on the day of final acceptance of the work, where daily reporting shall be required until the date of provisional acceptance of the work, and on an as-needed basis thereafter. After the date of provisional acceptance of the work, the construction log shall be kept at the purchaser’s registered address. Construction log entries may not be used to initiate or execute changes pursuant to the contract in matters of the subject, price, quality, or timetable of the work. Individual daily entries shall be made in the construction log by the contractor’s representative or the construction manager (construction foreman).

#### Monthly report

The contractor shall prepare and submit to the purchaser, no later than on the fifth (5th) business day of the following month, a monthly report for the past month summarizing the extent of works done and progress made over that month (i.e., deliveries of works, goods, services, and / or rights of use). Monthly reports shall contain, at minimum:

##### Overview of the state of progress on engineering and design work detailing activities performed over the month in question;

##### Overview comparing actual progress on the work to progress planned, i.e., comparing the actual state of progress on the work to the Timetable and Execution Plan for the work and the Detailed Timetable and Execution Plan for the work prepared pursuant to Subsection 24.2 of the contract;

##### Overview of planned activities (i.e., deliveries of works, goods, services, and / or rights of use) of the contractor for the following month;

##### List of changes made, including list and status of change proceedings pursuant to Article 53 of the contract;

##### List of invoices issued and payments received by the contractor;

##### List of any major non-conformities, including their potential impact on the execution of the contract and details of remedial measures taken. Particular attention shall be given to areas in which the contractor is or might become delayed in the meeting of the key work execution milestones as given in Subsection 10.1 of the contract.

##### Any other documents the purchaser and contractor may agree on.

#### Progress meetings

The purchaser and the contractor shall meet at certain times specified by the purchaser to discuss the state of the contractor’s progress in the execution of the contract. The contractor's representative shall participate in such meetings, as shall, if pertinent, the construction manager and any other contractor staff who may have relevant contributions. These meetings shall cover the state of progress on the work, plans and proposals for future activities, the labour situation, engineering progress, Occupational Health and Safety concerns, supplies of equipment and materials, current and expected difficulties, any coordination in executing the work that may be required, change proceedings, and any other topics that may be pertinent. The contractor shall maintain a record of the proceedings, which both parties shall approve and sign at the end of the meeting to which the report pertains.

Progress meetings shall take place once a month until the contractor's acceptance of custody of the site, and once a week thereafter, always at the purchaser's offices, unless agreed otherwise. If required, other, extraordinary meetings may take place. The time and place for such extraordinary meetings shall be agreed individually and with regard to the topic.

Upon agreement, the parties may attend the progress meetings remotely using agreed electronic teleconferencing means.

#### Milestone Report

Upon completion of each of the milestones specified in the schedule of payments provided in Enclosure 11 of the contract, the contractor shall prepare and turn over a report to the purchaser which contains the following at a minimum:

##### List of works, goods, rights of use, and services provided in the completion of the milestone in question;

##### Assessment of milestone completion and meeting of conditions for the associated payment;

##### Comparison of milestone completion time against the Timetable and Execution Plan for the work and the Detailed Timetable and Execution Plan for the work prepared pursuant to Subsection 24.2 of the contract;

##### Any other documents the purchaser and contractor may agree on.

The purchaser shall, within seven (7) business days from the receipt of a Milestone Report from the contractor, unless agreed otherwise, either sign off on the Milestone Report, or else give, in writing, its reasons for not doing so.

##### In the event that the purchaser, within the above mentioned period of seven (7) business days, fails to both sign off on a milestone report and give the contractor in writing its reasons for not doing so, then that Milestone Report shall be considered signed and approved, and the contractor shall be entitled to invoice the payment due to it for the milestone in question.

# subcontracting

The list of approved subcontractors for principal works, services, and goods deliveries is part of Enclosure 8 of the contract. The contractor may propose amendments and deletions to this list as it sees fit. The contractor shall provide such changes to the purchaser for approval, in writing. All such changes shall be submitted in a timely manner so as not to delay to the work. No changes are valid without the purchaser's prior written approval. The purchaser shall not withhold such approval without cause. In the event the purchaser fails to make a statement on a proposed change within fifteen (15) days of receipt, that change shall be considered approved.

The purchaser reserves the right to refuse any subcontractors of works, services, and goods who are not listed in Enclosure 8 of the contract and who, in the purchaser’s opinion, lack sufficient skill and experience on similar projects, or who, to the purchaser’s knowledge, have a history of not fulfilling obligations, or whose financial and technological position is, in the purchaser’s opinion, insufficient to adequately guarantee the fulfilment of the obligations under the contract considered for that subcontractor. In that event, however, the purchaser shall provide due justification for its refusal of such a subcontractor to the contractor, in writing.

The contractor shall notify the purchaser in writing of any subcontracting agreements with subcontractors as specified in Enclosure 8 of the contract within a maximum of ten (10) days of entering into such subcontracting agreements, and not later than on the date of Handover of the approved documentation for execution of the project – phase 2 according to Subsection 10.1 (d) of the contract. Failure to enter into subcontracting agreements with subcontractors as specified in Enclosure 8 of the contract within the specified deadlines authorizes the purchaser not to accept the approved documentation for execution of the project – phase 2.

The purchaser's approval of a subcontractor and / or the execution of the work or a part thereof by a subcontractor does not in any way affect the contractor’s obligations and duties under the contract; the contractor bears responsibility for the work of its subcontractors as if it were the contractor’s own.

The purchaser may refuse to take delivery of goods, rights of use, works, and / or services delivered via a subcontractor not meeting the requirements of this Article 21 of the contract.

The contractor shall ensure that all its subcontracts contain explicit provisions to the effect that the contractor is authorized to assign its rights and obligations in such subcontracts to the purchaser or a third party in a manner that would make the subcontractor a direct contractor of the purchaser or a third party of the purchaser’s choosing, particularly in situations described in the contract (Subsection 55.2.2). Furthermore, the contractor shall ensure that its subcontracts contain provisions and obligations binding upon the subcontractor equivalent to the provisions and obligations binding upon the contractor under the contract. The contractor shall, upon the purchaser's request, demonstrate to the purchaser that its subcontracts contain such provisions.

In the event that the contractor, pursuant to Subsection 21.1 of the contract, proposes a change of subcontractor to the purchaser affecting a subcontractor through which the contractor demonstrated its qualifications for the procurement procedure for the work, the contractor shall demonstrate to the purchaser that, after the change of subcontractor, the contractor shall remain qualified as per the purchaser’s requirements given in the procurement procedure for the work, in the extent that the contractor’s qualifications may have been demonstrated through the subcontractor being replaced, such demonstration to be made in the same manner that was required in the procurement procedure for the work. This does not affect the provisions of Subsection 21.2 of the contract.

# STANDARDS AND LEGISLATION

The contractor shall comply with all of the following:

##### General legislation of the Czech Republic, as in effect at the time; and

##### ČSN standards, as in effect at the time, as well as harmonized ČSN EN and ČSN EN ISO standards, i.e., standards relevant to the work incorporating in full the requirements of common European standards or of harmonization acts approved by the authorities of the European Union as harmonized European standards, or European standards enacted as harmonized pursuant to the law of the European Union by agreement of notified parties, unless expressly stated otherwise; and

##### the purchaser’s internal regulations stipulated in Enclosure 12 of the contract.

## Foreign international or national standards can only be used, if their requirements are equal to or stricter than those of standards valid in the Czech Republic, following the prior consent of the purchaser. Should the contractor wish to use a foreign standard with no direct equivalent ČSN, ČSN EN, or ČSN EN ISO standard, it shall provide the text of the standard to the purchaser, in both its original language and certified Czech translation, along with the documentation affected by the standard, for the purchaser’s approval, unless the parties agree on another procedure.

The contractor shall provide to the purchaser, in order to demonstrate its compliance with the requirements of general legislation, mandatory standards, and the work’s quality assurance program, the relevant documentation pursuant to this subsection, no later than ten (10) days before the commencement of the complex tests pursuant to Subsection 30.2 of the contract, unless the contract specifies an earlier deadline or the parties agree otherwise.

The purchaser may refuse to accept the work not compliant with the requirements of this Article 22 of the contract, in which event the contractor shall, at its own expense, ensure the work is compliant with this Article 22 of the contract.

None of the provisions of this Article  22 of the contract shall relieve the contractor of responsibility for inspections, testing, quality, warranty, or any other obligations under the contract, nor entitle the contractor to an increase in the contract price or an extension in the timetable agreed in the contract.

# ENGINEERING WORK, DOCUMENTATION

The contractor shall complete the design and engineering works per the provisions of the contract, or, where not otherwise specified, in accordance with generally binding legislation and standards pursuant to Subsection 22.1 of the contract and good engineering practices.  The contractor is responsible for any non-conformity, mistakes or omissions in specifications, drawings and other technical documentation, whether these specifications, drawings or other documents were or were not approved by the purchaser provided that these differences, mistakes or omissions are not caused by inaccurate information provided to the contractor by the purchaser or on behalf of the purchaser and which the contractor reported without result pursuant to Subsection 23.2 of the contract.

The contractor shall not be liable for the consequences of incorrect instructions or information provided by the purchaser or in the purchaser's name, provided that the contractor gave the purchaser clear and demonstrable notice of the shortcomings of such instructions or information, in writing and without undue delay but no later than ten (10) business days from its receipt, and that the purchaser insisted in spite of such notice on the execution of such instructions and / or the use of such information, or that alternatively the contractor was not allowed to ascertain the correctness of such instructions or information despite its written request for the same. The parties have agreed to exclude their legal relationship under this contract from applicability of the provisions of Section 2594(2), (3), and (4) (Contractor Notification by the Purchaser), and of Section 2595 (on Faulty Purchaser Instructions, Contractor Withdrawal) of the Civil Code.

Scope, format, language, quantity, approval procedure, and other requirements on documentation are listed in Enclosure 3 of the contract. The contractor shall prepare and submit to the purchaser all documentation required by Enclosure 3 of the contract. The costs of preparation, including materials and submission, shall be borne by the contractor and part of the contract price.

In the event that the contractor, with the purchaser’s prior approval, uses a different digital file format for documents provided under this contract than required in the same, the contractor shall, at its own expense and without delay, provide to the purchaser any licenses that may be required, in the quantity necessary for the number of users agreed, including user manuals and, if required, training of the purchaser personnel in question on the use of such formats.

Pursuant to the quality plan, the contractor shall provide the purchaser with copies of all documentation prepared exclusively in relation to the work, for the purposes of the purchaser's approval of the contractor’s activities in supply, manufacture, shipping, assembly, installation, construction, and / or commissioning.

The procedure for documentation submission and approval shall be as specified in Enclosure 3 of the contract. The purchaser’s approval or inspection of the documentation provided by the contractor, whether with or without modifications, does in no way relieve the contractor of responsibility for any faults with the documentation or of any of its obligations under the contract.

The contractor shall be liable for and bear all costs of any and all damages that may arise from its provision of any goods and / or execution of any part of the work before receiving the purchaser’s approval.

# EXECUTION OF THE WORK

The work shall be executed in accordance with the provisions of the contract, and in particular the timetable specified in Article 10 of the contract, the Timetable and Execution Plan for the work and the Detailed Timetable and Execution Plan for the work prepared pursuant to Subsection 24.2 of the contract and the quality plan.

The contractor shall submit the Detailed Timetable and Execution Plan for the work to the purchaser for review together with the documentation for execution of the project – Phase 2. This Detailed Timetable and Execution Plan shall illustrate, in detail, the contractor’s and its subcontractors’ plans for execution of the work, shall comply with the milestones given in the Timetable and Execution Plan for the work, and shall not cause conflict with works performed by the purchaser or by parties authorized by the purchaser. Once the purchaser has approved the Detailed Timetable and Execution Plan for the work, it shall become a binding contract and shall replace the Timetable and Execution Plan for the work specified in Enclosure 4 of the contract. Until such time as the Detailed Timetable and Execution Plan for the work has been approved, the Timetable and Execution Plan for the work given in Enclosure 4 of the contract remains in effect.

The contractor may not commence manufacturing and execution of the work before receiving written approval on the relevant documentation for execution of the project from the purchaser and the depositing of such documentation with the purchaser, unless the parties demonstrably agree otherwise. Any delay in the execution of the work due to the contractor’s inability to commence works at the site for reasons of the contractor’s failure to deposit the approved documentation for execution of the project with the purchaser, shall be the responsibility of the contractor.

The contractor shall prepare execution timetables for activities relating to commissioning, which shall contain a disaggregated listing of the activities given in the Detailed Timetable and Execution Plan for the work. The commissioning execution timetables shall use hours as the unit of time and shall be submitted to the purchaser for approval no later than ninety (90) days before the commissioning commencement date.

- The commissioning execution timetables shall describe each activity in a level of detail no lesser than that found in the Detailed Timetable and Execution Plan for the work. If requested by the purchaser, the information in the commissioning execution timetables shall be amended to include further required data (e.g. resources, assignment of responsibility, etc.).

Before commencing assembly of the work, the purchaser and the contractor shall sign an assembly readiness protocol. The drafting of the protocol shall be the responsibility of the contractor. In the event that the purchaser refuses to sign the assembly readiness protocol, the purchaser shall inform the contractor of its reasons for doing so within five (5) days of receipt of the draft protocol. Should the purchaser, within five (5) days of receipt, fail to both sign the protocol and give the contractor in writing its reasons for not doing so, then the protocol shall be considered signed on the date of the purchaser’s receipt of the draft. The assembly readiness protocol shall in particular contain:

#### Attestation of the purchaser’s approval of the documentation required to commence assembly;

#### Attestation to the effect that all equipment and components thereof required to commence assembly have been delivered to the site and that the relevant tests, as completed and evaluated, have been carried out on them in accordance with the quality plan;

#### Attestation of the purchaser’s approval of the quality plan for assembly works;

#### Attestation to the effect that all staff participating in works covered by the protocol have been adequately briefed on all regulations relevant to the execution of the contract.

The contractor shall, throughout the execution of the work, monitor and document the progress of all deliveries and activities with regard to the conditions and timetable agreed in the Timetable and Execution Plan for the work (Enclosure 4 of the contract) and the Detailed Timetable and Execution Plan for the work prepared pursuant to Subsection 24.2 of the contract.

# DELIVERY AND DOCUMENTATION

All documents relating to the delivery of goods, rights of use, materials, and services to the site from outside the Czech Republic (i.e., customs, insurance, transit, tax, origin, etc. documents) shall be procured, handled, and tracked by the contractor.

The contractor shall deliver to the site all goods, materials, and work components sourced in the Czech Republic, including any and all taxes, insurance, shipping, and other costs, as well as licenses, approvals, etc. relating to the delivery of goods to the intended destination. Documents relating to the delivery of goods to the site (insurance, shipping, tax, etc.) shall be procured, handled, and tracked by the contractor.

All commenced deliveries of goods shall be reported by the contractor to the purchaser via e-mail, including the description of the goods, the delivery location, the shipping method, and the estimated time to arrival at the site; the purchaser should have this information no later than three (3) business days before the goods are due at the site. In the event that the purchaser does not receive such information by the time given above, the contractor shall be liable for any and all consequences, including demonstrable costs, arising to the purchaser as a result, and shall reimburse the purchaser for such costs without delay.

# PACKAGING INSTRUCTIONS

All deliveries under the contract shall be duly and carefully packaged in accordance with manufacturer instructions and with regard to the nature of the goods in question, in packaging suitable for long-distance shipping and loading and offloading, so as to prevent damage during transit and storage. The contractor shall ensure thermal and mechanical insulation is included such as can adequately prevent damage by water, rain, collision, and corrosion, as appropriate given the nature of the equipment, in order to ensure the safe shipping of goods to the site.

The contractor shall mark all packaging for transport with the name of the project “Waste-to-Energy Facility, EVO Komořany, Most” – intended for the contractor: ....................

# TRANSPORT

The contractor shall, at its own risk and expense, ship to the site all relevant goods, utilizing such shipping methods as it considers suitable given the goods being shipped.

# WORK QUALITY ASSURANCE

The contractor shall ensure that the work, including all related activities of the contractor and its subcontractors at all levels, is executed at the level of quality required by the contract, as set out particularly in this Article 28 of the contract, Enclosure 3 to the contract, general Czech legislation, and the quality plan and Inspection and Test Plan as approved by the purchaser.

The contractor declares that it has deployed a certified quality management system pursuant to the recommendations of the ČSN EN ISO 9001:2016 standard or other quality management system fulfilling the minimum requirements laid down in the above standards.

Throughout the duration of the contract, the contractor shall submit to the purchaser all documentation required by the quality plan and requested by the purchaser.

The quality aspects of the work’s execution pursuant to the contract shall be governed by the quality plan and the contractor’s Inspection and Test Plan, including any amendments to the latter in accordance with the contract. The quality plan and the Inspection and Test Plan for the execution of the work pursuant to the contract shall be prepared by the contractor and submitted to the purchaser for approval in the scope and on the timetable given in Enclosure 3 of the contract. The purchaser shall not deny approval of the quality plan and / or the Inspection and Test Plan without reason, and shall strive to give approval as soon as possible after receiving the contractor’s proposal. Should the purchaser, within fourteen (14) days of receipt, fail to both approve the draft quality plan and / or the draft Inspection and Test Plan, and to give the contractor its reasons and / or change requests, then the quality plan and / or Inspection and Test Plan shall be considered approved.

All inspections and testing performed in relation to the preparation and execution of the work by the contractor and / or its subcontractors shall be performed in accordance with the Inspection and Test Plan and related documentation, and in accordance with the contract.

The quality plan and Inspection and Test Plan may be amended via documented, purchaser-approved revisions.

During the execution of the contract, the contractor shall amend the quality plan and Inspection and Test Plan within thirty (30) days of the purchaser’s request in the event of changes in:

##### General legislation requirements; or

##### Internal purchaser regulations; or

##### Public oversight and administration requirements; or

##### Should inspection results mandate remedial and / or preventive measures; or

##### Based on other purchaser requirements in accordance with the contract.

- In the event that the reasons for such changes are not attributable to the contractor and the changes are material to the execution of the work, the parties shall commence consultations pursuant to Article 53 of the contract, unless agreed otherwise.

The purchaser-approved quality plan and Inspection and Test Plans governing the quality-related activities on the work shall be amended by the contractor and re-submitted for the purchaser’s approval in the event that the contractor wishes to make a change of any kind, particularly changes in the sequence, contents, and / or methods of inspections and / or tests, including for reasons of the non-compliance of the sequence, contents, and / or methods of inspections and tests with the Timetable and Execution Plan for the work, the Detailed Timetable and Execution Plan for the work prepared pursuant to Subsection 24.2 of the contract, or the scope of the work itself. The purchaser’s approval, or lack thereof, of quality plan and Inspection and Test Plan revisions proposed by the contractor does not relieve the contractor of responsibility for inspections and testing and the due execution of the work pursuant to the contract. Existing versions of the quality plan and Inspection and Test Plan remain in effect and binding upon the contractor until such time as the purchaser may approve a revision.

In the event that the purchaser becomes aware that the version of the quality plan and / or Inspection and Test Plan currently in effect does not conform to the contract, the contractor shall, within a reasonable timeframe specified by the purchaser, prepare and submit to the purchaser for approval a new revision of the quality plan and / or Inspection and Test Plan compliant with the contract. All expenses relating to the quality plan and Inspection and Test Plan revisions under this subsection shall be borne by the contractor.

Throughout the execution of the contract, the contractor shall allow the purchaser or its representatives, without delay, to perform an audit of the quality management system and to inspect and test the work or any part thereof, including goods, works, services, rights of use, drawings, and documentation, so that the purchaser may satisfy itself that these conform to the contract.

Tests and inspections may be performed at the contractor, at its subcontractors, at manufacturer facilities, and at the site.

Whenever the contractor is ready to perform such tests and inspections as are specified in the Inspection and Test Plan and marked “W” (Witness Point, i.e., a test or inspection requiring the purchaser to bear witness), the contractor shall, in reasonable advance but no later than twenty-one (21) days in advance, send by fax, e-mail or registered post a notice to the purchaser of the test or inspection and the time and place of its performance. The contractor shall obtain from its subcontractors or any third parties or manufacturers involved all permissions and consents required to enable the purchaser’s representatives to attend the test or inspection.

Results, protocols, or certificates attesting that inspections and tests have been performed shall be summarised in the “Inspection and Test Book”, which shall be submitted to the purchaser in electronic format and on paper not later than ten (10) days before the expected date of provisional acceptance of the work pursuant to Article 31 of the contract.

The contractor shall provide to the purchaser all protocols relating to the results of any such tests and inspections. In the event that the purchaser's representative fails to attend a test or inspection where their attendance is required, the contractor may perform the test or inspection without the purchaser’s participation, in which case the contractor shall the submit for the purchaser's assessment, within three (3) business days, the protocols summarizing the results. If the test or inspection in question is a Hold Point as these are defined in the Inspection and Test Plan, the contractor shall wait for the purchaser’s representative no less than twenty-four (24) hours from the agreed time of the test or inspection, unless the parties agree otherwise.

The purchaser may attend tests and inspections by sending a representative. Costs and expenses related to such attendance, such as travel and room and board expenses, shall be borne by the purchaser. In the event that the test or inspection results in a failure for reasons attributable to the contractor, the contractor shall reimburse the purchaser for all demonstrated and reasonable expenses related to the purchaser’s representative’s attendance of the test or inspection. The purchaser may invoice the contractor for costs related to attendance at a failed second and subsequent test or inspection at any point after that test or inspection, or may set off such costs against its financial liabilities vis-à-vis the contractor in any of its payments to the same.

In exceptional cases, the contractor shall allow the purchaser to perform tests and inspections of any kind that are not included in the Inspection and Test Plan, provided that:

##### Such a test or inspection does not jeopardize progress on the work, does not impact the proper functioning of the work part being tested or inspected, and does not compromise the contractor's performance of the contract. Should the contractor deem a test or inspection to jeopardize progress on the work, impact the proper functioning of the work part being tested or inspected, or compromise the contractor's performance of the contract, the contractor shall demonstrate this to the purchaser without delay. If the purchaser then insists on performing the test or inspection regardless, any impact on the performance of the contract shall be handled pursuant to Article 53 of the contract, the contractor shall be relieved of responsibility for potential damages; and

##### The contractor shall be reimbursed by the purchaser for all demonstrated and reasonable expenses resulting from the performance of such a test or inspection; and

##### The purchaser shall request the contractor to perform such a test or inspection no fewer than 10 business days in advance; and

##### The purchaser shall provide the contractor with all relevant inspection and background documents no fewer than 5 business days in advance.

For the purposes of monitoring of the progress of works at the site / assembly sites and the purchaser's technical supervision, the contractor shall allow the purchaser, during standard work hours, access to the site / assembly site at any time and without written notice; outside standard work hours, the contractor shall make all reasonable effort to allow the same. As part of its technical supervision, the purchaser may in particular monitor compliance of the works with the contract, the Design, and applicable technical standards and other legislation. The purchaser may note any issues identified during construction of the work in the construction log. The contractor shall ensure that its authorized staff are present during the purchaser’s technical supervision of deliveries and works, and that measures to remedy any issues pointed out are taken without delay. The purchaser’s technical supervisors may order contractor (including its subcontractors) personnel to interrupt the works if the contractor's representative cannot be reached and continuation of the works would jeopardize the safety, life, or limb of construction personnel and / or threaten major material damage.

The contractor shall lend the purchaser or its representative, free of charge, all required gear, equipment, measurement and test devices, media, etc., as well as provide due cooperation including access to drawings and production data, to the extent that this may be required for the purchaser to effectively participate in planned tests and inspections marked “W” or “H” in the Inspection and Test Plan. As regards gear, equipment, measurement and test devices, and media, the contractor shall be required to provide these per the above only if such gear, equipment, measurement and test devices, and media are available to the contractor directly at the site of the test or inspection in question. The purchaser shall be held liable for any damage to the gear, equipment, and measurement and test devices borrowed from the contractor.

In the event that any test or inspection fails for reasons not attributable to the purchaser, the contractor shall make all modifications (changes) required to meet the criteria specified, free of charge. The costs of repeated tests and inspections of such newly re-delivered or repaired portions of the work shall be borne by the contractor. The contractor shall also bear all costs and expenses that may arise to the purchaser in relation to a repeated test or inspection marked “W” or “H” in the Inspection and Test Plan.

No part of the work may be made inaccessible from the site before the tests and inspections required for the part by the contract and the Inspection and Test Plan are performed. The contractor shall notify the purchaser, in sufficient advance but no fewer than three (3) business days in advance (unless agreed otherwise), of the date at which any such parts of the work to be later made inaccessible shall be ready for the inspections and tests required by the Inspection and Test Plan and marked “W” or “H”. Such tests and inspections shall be performed by the contractor, with the purchaser attending. The contractor and the purchaser shall sign a protocol specifying the results of the test or inspection and clearing that part of the work to be made inaccessible. In the event that the purchaser fails to attend a test or inspection to which it had been duly invited per the above, the contractor may carry on with the work pursuant to the contract.

In the event the contractor makes a part of the work inaccessible without enabling the testing or inspections that may be required under the contract, the contractor shall, at its own expense, make that part of the work accessible in a manner sufficient to perform the test or inspection.

Any works or services to be performed by the contractor and any replacements or repairs to any part of the work, including goods, that may result from tests and inspections or failures thereof as described in this Article 28 of the contract, do not constitute a change to the work, and the contractor shall not, in the event, be entitled to any revisions of the quality plan, contract price, or the Timetable and Execution Plan for the work. Any and all costs relating to such services, works, goods, and rights of use shall be borne by the contractor, including costs of repeated testing and inspections and costs related thereto.

The determination, specification, and approval of relevant quality requirements for subcontractors are the responsibility of the contractor. Therefore, the contractor shall ensure that its subcontracts require its subcontractors to follow quality plans, inspection and test plans, and supplier inspection plans drafted by the contractor and consistent with the quality plan agreed to by the contractor in the contract.

Unless provided otherwise elsewhere in the contract, all inspections and testing, including related activities, pursuant to this Article 28 of the contract shall be performed by the contractor, and all costs relating to such tests and inspections, including costs of replacement for any parts destroyed in testing, shall be borne by the contractor and part of the contract price.

Nothing in this Article 28 of the contract relieves the contractor of any part of its responsibility for the execution and quality of the work, for guarantees, or any of its other obligations under the contract.

# ASSEMBLY AND MECHANICAL COMPLETION

The contractor commits to assemble the work in accordance with the provisions of the contract, and in particular the design, the quality plan and the Inspection and Test Plan.

## Assembly of the work shall commence upon the signing of the assembly readiness protocol by the purchaser and the contractor and shall be governed by the terms and timetables given in the Timetable and Execution Plan for the work and the Detailed Timetable and Execution Plan for the work prepared pursuant to Subsection 24.2 of the contract.

mechanical completion of the work constitutes an achievement of a state of the work’s parts, in terms of assembly works, such that commissioning may begin. As soon as, in the contractor’s view, a system is mechanically and structurally complete and clean, the contractor shall notify the purchaser in writing to that effect. Assembly also includes individual tests provided for in the contractor’s quality plan and Inspection and Test Plan pursuant to Article 28 of the contract. The primary goal of individual tests is to verify that the system in question has been assembled correctly and its manufacturing and assembly documentation is complete, without using operating media or permanent electrical connections.

The completion of individual tests shall be demonstrated by the relevant attestations and protocols from tests and inspections, issued pursuant to the Inspection and Test Plan, which the contractor shall prepare and submit to the purchaser.

Once all individual tests have been successfully completed, the purchaser and the contractor shall, without undue delay, sign the mechanical completion protocol for the work, on the basis of which preparations for the commissioning of the work may begin. The drafting of the protocol shall be the responsibility of the contractor.

Should the purchaser refuse to sign the mechanical completion protocol pursuant to Subsection 29.5 of the contract, the purchaser shall notify the contractor, in writing and no later than five (5) business days from the receipt of the draft protocol, of the defects and / or incomplete works that, in the purchaser’s view, prevent the start of commissioning and are attributable to the contractor. The contractor shall then remedy such defects and / or incomplete works and subsequently repeat the procedure given in Subsections 29.3 and 29.4 of the contract.

Should the purchaser, within five (5) business days of receipt, fail to both sign the protocol and inform the contractor in writing of defects and / or incomplete works preventing the start of commissioning, then the work shall be considered mechanically complete on the date of the purchaser’s receipt of the draft protocol.

# COMMISSIONING

Commissioning means putting the work into service after completion of assembly pursuant to Article 29 of the agreement. commissioning involves the following activities:

(a)	Preparation for complex tests;

(b)	complex tests, test “a“;

(c)	performance test.

The contractor shall begin preparing individual systems for complex tests gradually, so that individual functional systems and operating systems are brought online until the entire work is commissioned. The complex tests and performance test must be performed on the work as a whole.

The contractor shall commission the work in accordance with the Timetable and Execution plan for the work (Enclosure 4 of the contract) and the Detailed Timetable and Execution Plan for the work prepared pursuant to Subsection 24.2 of the contract. Commissioning shall take place during standard work hours, unless the parties agree otherwise. The contractor shall ensure the continuous presence of its authorized staff, the contractor's representative, or the construction manager at the site throughout commissioning activities so as to ensure reliable and safe operation, the performance of any repairs and procurement of any replacement parts that may be required, and compliance with operating guidelines. The costs of such contractor activities are part of the contract price.

All activities and manipulation performed by the purchaser’s operators between the start of commissioning and the date of provisional acceptance of the work shall be fully under the control and on the responsibility of the contractor, and shall be governed exclusively by the contractor’s instructions.

The contractor shall over the duration of commissioning provide at its own expense all oils, lubricating greases, fuels, operating fluids, chemicals and other consumable materials necessary to execution or commissioning of the work by the date of provisional acceptance of the work. The purchaser shall provide the contractor with waste and, pursuant to the provisions of Subsection 12.8 of the contract, all consumable materials, media, utilities, and services specified in Enclosure 6 of the contract.

Preparations for complex tests

### The contractor shall commence preparations for complex tests in accordance with the Inspection and Test Plan and the Project for commissioning, gradually on individual operating systems. Preparations for complex tests shall finish once all such tests and inspections have been performed and the operational capabilities of all operating systems have been verified.

### Preparations for complex tests consist of tests and inspections verifying the functionality of individual devices and functional systems, including the harmonization of such devices’ and systems’ joint operation. Preparations for complex tests further include the verification of linkages to the purchaser’s existing systems. Before commencing such testing, the contractor shall achieve mechanical completion on the systems in question, including individual tests, pursuant to Article 29 of the contract. The contractor shall immediately remedy any defects or incomplete works found that would impair the continuation of the commissioning process, and shall thereafter repeat the test in question. The contractor shall issue protocols on the completion and results of all tests and inspections.

### The end of preparations for complex tests shall be attested to by a protocol signed by the parties declaring the work ready for the complex tests. Minor defects and incomplete works not impairing the complex tests and acceptable as such to the purchaser shall be remedied on a timetable agreed in the complex tests readiness protocol. The drafting of the protocol shall be the responsibility of the contractor. The purchaser shall not refuse to sign the protocol without reason, and shall sign the protocol as soon after receipt as feasible. Should the purchaser, within five (5) business days of receipt, fail to both sign the protocol and give the contractor in writing its reasons for not signing, then for the purposes of the contract the protocol shall be considered approved on the date of the purchaser's receipt of the draft, and the contractor may commence the complex tests.

complex tests, test “a“

### Once preparations for complex tests pursuant to Subsection 30.1 of the contract are complete, the contractor shall perform the complex tests as specified in the Inspection and Test Plan, as approved by the purchaser. The complex tests shall verify the functionality of the work’s systems in different operating modes; pursuant to the Inspection and Test Plan, the inspections and tests included in test “A” shall also be performed, including the guarantee testing specified in Enclosure 2 of the contract for test “A”. The complex tests are to verify that the technical parameters and functionality agreed in the contract have been met, particularly those given in the complex tests program and general requirements on operability, reliability, safety, and quality of the work.

### The contractor shall complete the complex testing so as to minimise the number of start-ups, and specifically cold starts.

### As part of test “A”, an independent entity contracted for that purpose, attended by contractor representatives, shall perform the guarantee measurement, at the date given in the Detailed Timetable and Execution Plan for the work prepared pursuant to Subsection 24.2 of the contract. Guarantee test “A” shall be performed on a clean boiler. The guarantee measurement shall be performed in accordance with the guarantee measurement project, as prepared by the contractor pursuant to the requirements of Chapter 2.11 of Enclosure 3 of the contract. The guarantee measurement is the purchaser’s independent verification of the work’s compliance with the guaranteed parameters given in Enclosure 2 of the contract. The guarantee measurement consists of the independent entity authorised by the purchaser and at the purchaser’s cost performing measurements and assessments of all guaranteed parameters specified for test “A” under the contract.

In the event that, for reasons not attributable to the contractor, the full extent of the guarantee measurement of all guaranteed parameters assigned to test “A” cannot be performed during test “A”, the guarantee measurement of the remaining parameters shall be made during the trial operation Operation phase, at a date agreed by the contractor and the purchaser.

### In the event that, for reasons attributable to the contractor, the complex tests reveal that the parameters, functionality, and requirements on operability, reliability, safety, and quality specified for the work in the contract have not been achieved, the contractor shall, at its own expense, make all changes and modifications required to achieve those parameters, functionality, and requirements. The contractor shall notify the purchaser of the execution of such changes and modifications, and shall repeat the complex tests until such time as the technical parameters and requirements agreed have been met, unless agreed otherwise.

### In the event that, for reasons attributable to the contractor, repeated complex tests reveal that the parameters, functionality, and requirements on operability, reliability, safety, and quality specified for the work in Subsection 30.2.4 of the contract have not been achieved despite changes and modifications, but the work’s non-conformity with the contract-specified parameters, functionality, and requirements is found to be minor and deemed acceptable by the purchaser insofar that it does not impair the operability, reliability, or safety of the work, then the purchaser may authorize the contractor, in writing, to proceed to the performance test. The preceding shall, however, be conditioned on the contractor’s payment of the contractual penalty specified in Subsection 44.2 of the contract. If for reasons attributable to the contractor the limit values for the guaranteed parameters specified in Enclosure 2 of the contract are not achieved, and even after the changes, modifications and repetition of the complex tests pursuant to Subsection 30.2.4 of the contract, the purchaser has the right to withdraw from the contract and to draw funds from the bank guarantee for the work to the benefit of the purchaser, at the purchaser's own discretion.

### Once the complex tests have been successfully completed, the contractor and the purchaser shall sign a protocol attesting the successful completion of complex tests of the work, including the successful completion of test “A” and relevant guarantee measurements, and authorizing the work to proceed to the performance test stage. All test reports shall be appended to the complex tests protocol. The drafting of the protocol shall be the responsibility of the contractor. The purchaser shall not refuse to sign the protocol without reason, and shall sign the protocol as soon after receipt as feasible. Should the purchaser, within five (5) business days of receipt, fail to both sign the protocol and give the contractor in writing its reasons for not signing, then for the purposes of the contract the protocol shall be considered approved on the date of the purchaser’s receipt of the draft, and the contractor may commence the performance test.

PERFORMANCE TEST

### The performance test may commence only once complex tests have been successfully completed and the protocol to that effect has been signed, pursuant to Subsection 30.2.6 of the contract.

### The performance test consists of the continuous, problem-free operation of the work in the duration of two hundred forty (240) hours, and in all work operating modes allowed by the purchaser. The performance test is to demonstrate the operability, reliability, safety, and quality of the contractor's execution of the work as required by the contract, in the scope and specification provided in the Inspection and Test Plan, as approved, and in the performance test program, as approved. The contractor shall operate the work without service interventions throughout the performance test. Once the performance test has been completed, the contractor and the purchaser shall sign a protocol to that effect. The drafting of the protocol shall be the responsibility of the contractor. The purchaser shall not refuse to sign the protocol without reason, and shall sign the protocol as soon after receipt as feasible. Should the purchaser, within five (5) business days of receipt, fail to both sign the protocol and give the contractor in writing its reasons for not signing, then for the purposes of the contract the protocol shall be considered approved on the date of the purchaser’s receipt of the draft.

### In the event that, for reasons not attributable to the contractor, the performance test is interrupted, the contractor shall continue the performance test in accordance with the purchaser’s instructions once the causes of such interruption are resolved, and a technical state matching that at the beginning of the performance test is achieved. The contractor is entitled to reimbursement for demonstrable and expediently incurred additional costs associated with such interruption and subsequent completion of the performance test.

### In the event that, for reasons attributable to the contractor, the performance test is interrupted for more than twelve (12) hours but the contractor succeeds in resolving the cause of the interruption, the purchaser shall, at its own discretion, decide whether the performance test is to continue or be repeated whole.

### In the event that, for reasons attributable to the contractor, the performance test reveals that the requirements on the operability and reliability of the work have not been met, the contractor shall, at its own expense, make all changes and modifications required to meet those requirements. The contractor shall notify the purchaser of the execution of such changes and modifications, and shall repeat the performance test until such time as the requirements agreed in the performance test program have been met. In the event that more than two runs of the performance test are so required, the purchaser may request the contractor to reimburse the purchaser for all demonstrable expenses related to the third and all subsequent performance tests performed; the contractor, if so requested, shall be obliged to comply.

### In the event that, for reasons attributable to the contractor, repeated performance tests reveal that the requirements given in the performance test program have not been achieved despite the contractor’s changes and modifications pursuant to Subsection 30.3.5 of the contract, but the work’s non-conformity with the requirements is found to be minor and deemed acceptable by the purchaser insofar that it does not impair the operability, reliability, safety, or quality of the work, then the purchaser may agree, in writing, to accept the work, provided that all requirements of Article 31 of the contract are met.

### In the event that, for reasons not attributable to the contractor, the performance test cannot be completed within six (6) months from the date of mechanical completion, or within an alternative period agreed by the purchaser and the contractor, the parties shall then agree on an alternative manner of acceptance of the work in the sense of Article 31 of the contract. Such an agreement does not, however, relieve the contractor of the obligation to perform the performance test if and when that is made possible by the purchaser, nor of the contractor’s other obligations under the contract.

# PROVISIONAL ACCEPTANCE OF THE WORK

Provisional acceptance of the work provided that Subsection 31.2 of the contract is respected, if and when:

#### The performance test pursuant to Subsection 30.3.2 of the contract has been successfully completed and the performance test protocol has been signed; or

#### The performance test has not been successfully completed, but the purchaser decided, pursuant to Subsection 30.3.6 of the contract, to accept the work; or

#### The performance test has not been completed or was not performed at all, and the parties have agreed pursuant to Subsection 30.3.7 of the contract

#### and the contractor submits to the purchaser all documentation required by the contract to be submitted by the end of the performance test, or with regard to the state of the work if (b) above has been applied.

When the conditions for the provisional acceptance of the work given in Subsection 31.1 of the contract have been met, the contractor shall prepare the draft provisional acceptance protocol within seven (7) days of the submission of all required documents and fulfilment of all obligations required of the contractor at this point by the contract, and shall submit the protocol to the purchaser for approval. The protocol shall only be accepted if all of the contractor’s obligations under the contract (excepting obligations relating to operations during the warranty period) have been met, particularly, if the work has been properly executed as required by the contract, including training of the purchaser’s staff pursuant to Article 36 of the contract, submission of documentation required by the contract, and submission of the work to the purchaser without legal or material issues (minor, relatively unimportant incomplete works acceptable to the purchaser insofar as they do not impair the safe and reliable operation of the work, may be excepted, but shall be listed along with deadlines for their resolution in the provisional acceptance protocol for the work; in the event of doubt, potential issues shall not be considered minor, unimportant, or immaterial to the safe and reliable operation of the work).

Upon receipt of the contractor’s draft, the purchaser shall, within fifteen (15) days, either:

#### sign the provisional acceptance protocol; or

#### give the contractor, in writing, its reasons for not signing the provisional acceptance protocol.

#### In the event that the purchaser fails to acknowledge receipt of the draft provisional acceptance protocol within fifteen (15) days of receipt, or refuses to sign the provisional acceptance protocol despite the fact that the conditions for the protocol’s signing have been met and that the work is operational, then the provisional acceptance protocol for the work shall, for the purposes of the contract, be considered signed on the sixteenth (16th) day from the purchaser’s receipt of the draft. At that moment, the warranty period shall commence, the liability for damages to the work shall transfer to the purchaser, and the contractor may issue the final invoice for the work pursuant to the contract.

An integral part of the provisional acceptance (PAC) protocol for the work shall be a list of obvious defects and incomplete works found with the work that the purchaser considers acceptable pursuant to Subsection 31.2 of the contract, including the contractor’s and purchaser’s agreement on the manner and timetable for their remedy by the contractor and on penalizing the failure to meet these terms. Any apparent defects and incomplete works known on the work as of the date of issue of the provisional acceptance (PAC) protocol for the work may not, in any event, individually or together, impair the safe and economic operation of the work, nor negatively impact the work’s performance parameters.

An integral part of the work provisional acceptance protocol must be the agreement on vacating the site used for the work by the contractor during execution of the work (e.g. cleaning up the site, and especially the full or partial clean-up of areas, the removal or relocation of temporary structures and installations, the relocation of machinery, personnel, etc.) including finishing of the site area and the time limits for completing the process of vacating the site, which will not under any circumstances exceed thirty (30) days after signature of the provisional acceptance (PAC) protocol for the work. No contractor facilities remain at the site as of the date of signing of the provisional acceptance (PAC) protocol for the work may limit the safe operation and maintenance of the purchaser’s systems, including the work. The contractor shall likewise submit proof of waste disposal (documentation).

On the day of the purchaser’s signing of the provisional acceptance (PAC) protocol for the work, the work is considered accepted by the purchaser from the contractor and the warranty period begins. During the warranty period, the operation and staffing of the work are the responsibility and liability of the purchaser. This does not, however, affect the contractor’s warranty and responsibility for defects obligations as specified in the contract.

Regardless of the provisions of Article 31 of the contract, the parties may agree on provisional acceptance of selected parts of the work. The warranty period for such selected parts of the work begins on the date of signature of the relevant provisional acceptance protocol (PAC) for the selected part of the work.

# TRIAL OPERATION

The trial operation phase shall have a duration of six (6) months and begins on the date of signing of the provisional acceptance protocol for the work. trial operation shall end upon the signing of the trial operation protocol. The drafting of the protocol shall be the responsibility of the contractor. The purchaser shall not refuse to sign the protocol without reason, and shall sign the protocol as soon after receipt as feasible. Should the purchaser, within five (5) business days of receipt, fail to both sign the protocol and give the contractor in writing its reasons for not signing, then for the purposes of the contract the protocol shall be considered approved and signed and trial operation shall be considered ended on the date of the purchaser’s receipt of the draft.

Trial operation shall be performed by the purchaser’s duly trained staff, fully at the purchaser's responsibility, and in accordance with the operations guidelines for the work and potential contractor instructions. The contractor's representative shall be continuously present for the first three (3) months of trial operation, on business days from 6:00 a.m. to 2:00 p.m., unless agreed otherwise or unless operational exigencies not attributable to the purchaser require a more frequent and / or longer presence of the contractor. Between 2:00 p.m. and 6:00 a.m., the contractor shall make itself available via telephone. For the remaining three (3) months of trial operation, the contractor's representative or a qualified deputy a shall make themselves available upon the purchaser’s request. The contractor's representative or a qualified deputy appointed by a competent person shall also be available (on call) outside standard business hours and on public holidays and weekends, so that they are able to present themselves at the purchaser's premises within twenty-four (24) hours of the purchaser’s request, unless agreed otherwise with regard to the severity of the particular situation.

The contractor’s obligations during trial operations that are included in the contract price include, in particular:

#### Resolution of operational problems and performance of warranty repairs without delay. During the first three (3) months of trial operation, the contractor’s staff shall perform a personal inspection of the work no less frequently than 2 times per day.

#### Adjustments and tuning of systems in order to optimize operation in all operating modes, on the basis of changes proposed by the contractor and approved by the purchaser, including the amendment of actual-state and related documentation to reflect such changes.

#### Preparation of monthly reports on trial operation of the work and their submission to the purchaser for approval no later than on the tenth (10th) day of the month following the month being reported on. Such reports shall be based on operational records and systems inspections and shall, among others, list all discovered defects and malfunctions, including measures to resolve them, discuss the load on the equipment relative to its capacity, and assess the operation of the equipment with regard to public authorities’ requirements. A list of contents for monthly reports shall be prepared by the contractor and approved by the purchaser before the first such report is submitted.

#### Preparation of the final trial operation assessment report in the scope approved by the purchaser, and its submission to the purchaser within fourteen (14) days from the end of trial operation.

In the event that the contractor provides instructions to the purchaser's operators of the work during trial operation, the correctness of such instructions shall be the responsibility of the contractor. The contractor shall not be liable for any damages resulting from a failure on the part of the purchaser’s staff to follow the contractor’s instructions, or from failure of purchaser staff to follow operations and maintenance guidelines for the work.

The contractor’s obligations in relation to trial operation do not relieve the contractor of responsibilities relating to the warranty period.

Trial operation may include verification of the remaining guarantee parameters which were not verified during guarantee measurement during test “A” in accordance with Subsection 30.2.3 of the contract.

# GUARANTEE MEASUREMENT DURING TEST “B“, FINAL ACCEPTANCE OF THE WORK

During the twenty-four (24) month warranty period for the work’s technological systems pursuant to Subsection 45.1.1 of the contract, at a date specified by the purchaser, an independent entity contracted for that purpose at the purchaser’s expense shall, in the presence of purchaser and contractor representatives, perform and assess guarantee measurements of guaranteed parameters allocated to test “B”. Guarantee test “B” shall be carried out after 7500 hours of operation since the last boiler cleaning, the purchaser reserves the right to reduce the number of operating hours since the last boiler cleaning for test “B”. The guarantee measurement shall be performed pursuant to the Project for the guarantee measurement prepared by the contractor in accordance with the requirements of Chapter 2.11 of Enclosure 3 of the contract. The guarantee measurement during test “B” is for the purchaser to verify retrospectively that the work achieves the guaranteed parameters agreed in Enclosure 2 of the contract.

In the event that, for reasons not attributable to the purchaser, test “B” reveals that the guaranteed parameters given in Enclosure 2 of the contract have not been achieved, the contractor shall be liable to pay the purchaser the contractual penalty specified in Subsection 44.2 of the contract, unless the parties agree on a different procedure (i.e., execution of required changes and modifications). If, even after changes and modifications are made by the contractor, the limit values of guaranteed parameters given in Enclosure 2 of the contract are not achieved, the purchaser may, at its own discretion, withdraw from the contract and / or draw down against the bank guarantee for the work. All costs related to repeated guarantee measurements shall be borne by the contractor, through reimbursement of the purchaser against an invoice / tax receipt made out for the amount.

After successful completion of test “B” and expiration of the twenty-four (24) month warranty period pursuant to Subsection 45.1.1 of the contract (or an extension thereof pursuant to the contract), the contractor is obliged to provide the final acceptance protocol for the technological part of the work to the purchaser without undue delay for approval and which shall confirm the fulfilment of the contractor's contractual obligations related to the technological part of the work and after expiry of the sixty (60)-month warranty period for the building part of the work and rubberised components of the work in accordance with Subsection 45.1.1 of the contract, which shall confirm the fulfilment of the contractor's contractual obligations related to the building part of the work and the rubberised components of the work.

The purchaser shall not refuse to sign the protocols pursuant to Subsection 33.3 of the contract without reason, and shall sign the protocols as soon after receipt as feasible. Should the purchaser, within five (5) business days of receipt, fail to both sign a protocol and give the contractor in writing its reasons for not signing, then for the purposes of the contract that protocol shall be considered approved and signed on the date of the purchaser’s receipt of the draft.

# FULFILMENT OF THE CONTRACTOR’S OBLIGATIONS

Signature of the final acceptance protocol for the building part of the work in the sense of Subsection 33.3 of the contract does not terminate the contractor’s obligations that are agreed to remain in effect after final acceptance of the work, including the obligations of Subsection 57.4 of the contract.

# EMERGENCY WORKS

In the event that an emergency state arises in relation to the execution of the work that necessitates protective or repair works that may not be postponed and aim to prevent damage to the work or other property or injury to persons, the contractor shall commence such works immediately.

In the event that the contractor, despite the state of emergency, is unable or unwilling to commence the works pursuant to the previous subsection without delay, the purchaser may perform such works itself or have them performed in whichever manner the purchaser considers necessary to prevent damage to the work or other property, other damages, or injury to persons. In that event, the purchaser shall, without undue delay, notify the contractor that an emergency has arisen, that works were done and of the reasons and costs of such works, and discuss any impact the matter may have on the remainder of the contract. No such action of the purchaser shall affect the contractor’s liability for defects during the warranty period.

If such works are performed by the contractor pursuant to Subsection 35.1 of the contract with notification to the purchaser, and have arisen for reasons attributable to the purchaser, the purchaser shall, once the claim has been documented, reimburse the contractor for all demonstrable and reasonable expenses that may have arisen to it in relation to such works, without undue delay but no later than in the contractor’s usual invoice payment period pursuant to the contract; the parties shall also discuss any potential further impacts on the work. It shall be the duty of the contractor to demonstrate to the purchaser that such reasons are attributable to the purchaser.

If such works are performed by or on behalf of the purchaser pursuant to Subsection 35.2 of the contract, and have arisen for reasons attributable to the contractor, the contractor shall, once the claim has been documented, reimburse the purchaser for all demonstrable and reasonable expenses that may have arisen to it in relation to such works, against a special invoice / tax receipt made out by the purchaser for the amount and pursuant to the contract, with payment period the same as that of the contractor’s usual invoice payment period pursuant to the contract.

# PURCHASER OPERATIONS AND MAINTENANCE STAFF TRAINING

The contractor shall provide training for the purchaser’s personnel or representatives of purchaser-contracted third parties pursuant to Enclosure 7 of the contract; the training shall prepare such staffers for all tasks relating to their job description in the operation and / or maintenance of the work, and a training protocol shall be signed to attest the same.

# REPLACEMENT PARTS AND RAPID-WEAR PARTS

Replacement parts and rapid-wear parts for warranty period operation

The contractor shall, without undue delay, procure all replacement and rapid-wear parts required to operate the work for the twenty-four (24) month warranty period, or the sixty (60) month warranty period for the parts of the work for which the contract stipulates such warranty period length, and to use such replacement parts to remedy relevant defects on the work. Rapid-wear parts are not considered standard consumable materials. Such replacement and rapid-wear parts shall be included in the contract price.

Replacement parts and rapid-wear parts for operation in the two-year post-warranty period

The contractor shall prepare and provide to the purchaser as a part of the design a list, including prices, of recommended replacement and rapid-wear parts for operation of the work for two years after the end of the warranty period, including all information required to identify the part; i.e., name, number of units, replacement frequency for rapid-wear parts, prices, and manner of procurement of the replacement / rapid-wear part in question, i.e., whether the replacement / rapid wear part would be delivered directly by the contractor or by a subcontractor. The prices given in this list of replacement and rapid-wear parts for two-year post-warranty operation of the work shall be final for the contractor until the end of the warranty period pursuant to Subsection 45.1.1 of the contract, depending on the replacement / rapid wear part in question. The contractor acknowledges the purchaser’s right to demand, before the expiry of the warranty period agreed in the contract, the signing of a contract for the delivery of replacement and rapid-wear parts for two-year post-warranty operation of the work, in a scope of the purchaser’s choice. Deliveries of replacement and rapid-wear parts for the two-year post-warranty operation of the work are not subject to this contract, and if a contract is executed for that purpose, it shall be governed by Czech public procurement legislation; the purchaser shall have no obligation to contract for the delivery of replacement and rapid-wear parts for the two-year post-warranty operation of the work specifically with the contractor. In the event that the purchaser does contract with the contractor, the contractor shall extend to the purchaser the contractor’s best-customer terms on such replacement and rapid-wear parts deliveries.

# POST-WARRANTY SERVICING

The contractor acknowledges the purchaser's right to demand, after the expiry of the warranty period agreed in the contract, the signing of a contract for the provision of post-warranty servicing for the lifetime of the work. Post-warranty servicing are not subject to this contract, and if a contract is executed for that purpose, it shall be governed by Czech public procurement legislation (that is, the purchaser shall have no obligation to contract for post-warranty servicing specifically with the contractor, particularly if the latter fails to meet the legal requirements; in that event also, however, the contractor shall provide due cooperation to enable the proper provision of post-warranty servicing).

# SITE AND ASSEMBLY SITES

Information on the state and equipment of the site is provided in Enclosure 1 of the contract.

The contractor shall, in its execution of the work, keep the site and assembly areas free of all non-essential obstructions, and shall warehouse elsewhere or remove any and all supernumerary materials, waste, and surplus, as well as construction equipment that is no longer needed to perform works or services. No equipment of the contractor present at the site / assembly site shall limit the safe operation and maintenance of the purchaser’s systems, unless limitation is necessary to execute the work and agreed in advance between them. The parties declare that, for the duration of the work’s execution, the site (incl. assembly sites) shall be a work site of the contractor, and the contractor shall therefore be responsible for the safety of its or its subcontractors’ personnel present at the site / assembly site with its approval.

The costs of all temporary structures, access roads, and equipment on and off the site that are necessary to execute the work, including their public discussion, signing, operation, maintenance and disposal, shall be borne by the contractor and part of the contract price. The purchaser shall provide the contractor with the necessary cooperation (e.g. in public discussions, etc.).

The contractor shall respect the specified conditions and circumstances extant during its activities at the site. The purchaser shall ensure that none of its employees or other parties in any way related to them do not enter the site, unless such employees (persons) enter the site in accordance with the contract and within the performance of tasks under the contract.

# ADMINISTRATION RULES, OCCUPATIONAL HEALTH AND SAFETY

The organization of and procedures for the exchange of documents between the parties, as well as the publication, archiving, distribution, revision, and disposal of documents, in the execution of the contract, shall be governed by the Administration Rules. The Administration Rules shall specify the rules of communication between the parties and of the handling of documents in the performance of the contract. The contractor shall prepare the Administration Rules document pursuant to the requirements given in Chapter 2.1 of Enclosure 3 of the contract so as to cover all areas in the administration of the work pursuant to the contract; the contractor shall submit the Administration Rules, as approved by the purchaser, no later than forty-five (45) days after signature of the contract.

In the execution of the work, the contractor and all its subcontractors shall comply with generally binding occupational health and safety, fire protection and environmental protection regulations and is fully responsible for any violations thereof.

Enclosure 12 of the contract contains a link to the purchaser’s internal documents under the collective title of “Rules for Contractors”. The contractor shall follow these rules.

# WASTE MANAGEMENT, ENVIRONMENTAL PROTECTION

Throughout the execution of the work, the contractor shall be considered the source of all wastes arising from its activities on the work, including communal waste. The contractor shall therefore meet its obligations as the source of waste materials in the sense of Act No. 541/2020 Coll., on Waste and amending certain other acts, as amended, and the legislation implementing that Act. The contractor shall demonstrate and provide proof of the fulfilment of such obligations upon purchaser request.

Waste management (disposal) in relation to the contract shall be handled by the contractor, at its own expense. The contractor shall, upon the purchaser’s request, document compliance with its obligations under this Article 41 of the contract.

Areas in which the work is executed, including any roads that are used, must be kept clean and orderly. In the event that the contractor, within a technologically reasonable period from receiving the purchaser’s representative’s notice to that effect, fails to remedy a non-conforming situation attributable to the contractor, the purchaser may have clean-up performed by other means, in which case all demonstrable, reasonable expenses arising there from shall be charged to the contractor. As regards roads, the contractor shall maintain cleanliness regularly and with best possible care, so as to minimize the inconvenience or jeopardy to the operation and accessibility of the purchaser's other systems or to general traffic.

The contractor shall handle hazardous wastes and chemicals in relation to the work in accordance with the requirements of relevant legislation (including, among others, Act No. 541/2020 Coll., on Waste, and Act No. 350/2011 Coll., on Chemicals and Chemical Compounds).

The contractor shall ensure that wastes are not stolen or destroyed and that they do not negatively affect the surrounding area.

In the event that the contractor, in its execution of the work, discovers the presence of asbestos, the contractor shall inform the purchaser without delay, including detailed description of asbestos location and quantity, and shall postpone further works at that assembly location until the asbestos has been removed. In that event, the purchaser shall, without delay, contract a specialist company duly authorized under Czech Republic Law to remove and dispose of asbestos at its own cost. The parties shall also take effective measures to minimize the impact on the Timetable and Execution Plan for the work, and shall handle any such impact pursuant to Article 53 of the contract.

In the event of a leak of oil or other substances hazardous to the environment, particularly to surface water quality, the contractor shall, without delay, prevent further leakage and cover all costs of remedying the effects of the leak. The contractor shall also inform the purchaser without delay of any such leaks that may occur.

The purchaser’s representative, as well as other authorized purchaser personnel, are authorised to perform spot inspections of the contractor’s waste management practices.

The purchaser may unilaterally order the contractor to cease works if such works do not conform to environment protection, work safety, and fire protection legislation. In that event, the contractor may only resume such interrupted works once the non-conformity has been remedied, and such interruptions shall not affect the timetable of the work.

All damages and expenses relating to improper waste management shall be borne by the contractor. The contractor shall also be liable to reimburse to purchaser for any and all fines and remedial measures that may be levied against the purchaser as a result of faulty waste management practices of the contractor.

The contractor shall also comply with Act No. 114/1992 Coll., on Nature and Landscape Protection, as amended, including its implementing regulations. All damages and expenses relating to Nature and Landscape Protection Act breaches shall be borne by the contractor. The contractor shall also be liable to reimburse to purchaser for any and all fines and remedial measures that may be levied against the purchaser as a result of the contractor’s breaches of the law.

The contractor shall take adequate steps to ensure that its equipment related to the work (such as vehicles, construction machinery, etc.) does not leak operating fluids into the ground or groundwater, and shall ensure engines are not kept running needlessly. Unless agreed otherwise, the contractor shall not perform maintenance work on its equipment nor refill operating fluids at the site.

The contractor shall comply with its obligations under Act No. 254/2001 Coll., where these relate to the work; in particular, this concerns hazardous substance handling.

# PROTECTION OF THE WORK

The contractor shall, at its own risk and expense, provide and maintain any and all lighting, fencing, and security of the site that may be required for the proper execution and protection of the work or for the safety of the purchaser, owners of neighbouring properties and the public, throughout the execution of the work.

# WARRANTIES AND RESPONSIBILITIES

# Guaranteed parameters

The contractor hereby warrants and represents that the work shall, assuming operational guidelines are adhered to, be able to achieve the guaranteed parameters given in Enclosure 2 of the contract.

Verification to determine if the guarantee parameters were met shall be conducted by an independent company or entity contracted at the purchaser’s expense and with the involvement of the contractor's and the purchaser’s representatives per the guarantee measurement project prepared by the contractor and approved by the purchaser by the deadlines specified in Enclosure 2 of the contract.

# CONTRACTUAL PENALTIES

In the event that the contractor breaches its obligations given below in this Article 44 of the contract, excepting cases pursuant to Article 52 and Subsection 23.2 of the contract, the purchaser may, without limiting its other rights under the contract, including the right to reimbursement for damages in excess of contractual penalties as defined in Article 46 Subsection 46.2 of the contract, demand the payment of a contractual penalty from the contractor, in which event the contractor shall be required to pay.

Contractual penalties for the contractor’s delays

### The milestones subject to a contractual penalty in the event of contractor delay are as follows:

##### deadline for submission of the Administration Rules

##### deadline for submission of the design - phase 1

##### deadline for submission of the documentation for requests to modify construction in progress – stage 1

##### deadline for submission of the design - phase 2

##### deadline for submission of the documentation for requests to modify construction in progress – stage 2

##### deadline for submission of documentation for approval of test operation

##### deadline for submission of documentation for official approval of the finished work

##### deadline for provisional acceptance of the work

##### deadline for defect resolution

### In the event that the deadlines for any of the milestones given above are missed for reasons attributable to the contractor, the contractor shall be liable to pay to the purchaser a contractual penalty in the amount of:

### CZK five (5) thousand for every commenced day of default on the part of the contractor with the submission of the Administration Rules executed in accordance with Subsection 40.1 of the contract and approved by the purchaser.

### CZK twenty-five (25) thousand for every commenced day of default on the part of the contractor with the submission of the purchaser-approved design - phase 1 (Basic Design) in accordance with Chapter 2.5.1 of Enclosure 3 of the contract.

### CZK twenty-five (25) thousand for every commenced day of default on the part of the contractor with the submission of the purchaser-approved documentation for requests to modify construction in progress – Stage 1 in accordance with Chapter 2.6 of Enclosure 3 of the contract.

### CZK fifty (50) thousand for every commenced day of default on the part of the contractor with the submission of the purchaser-approved design - phase 2 (Detail Design) in accordance with Chapter 2.5.1 of Enclosure 3 of the contract.

### CZK twenty-five (25) thousand for every commenced day of default on the part of the contractor with the submission of the purchaser-approved documentation for requests to modify construction in progress – Stage 2 in accordance with Chapter 2.6 of Enclosure 3 of the contract.

### CZK one hundred (100) thousand for every commenced day of default on the part of the contractor with the submission of the documentation for approval of test operation.

### CZK twenty-five (25) thousand for every commenced day of default on the part of the contractor with the submission of the documentation for official approval of the finished work.

### CZK two (2) million four hundred seven (407) thousand for the first day of default on the part of the contractor with the provisional acceptance of the work in accordance with Article 31 of the contract, and for every additional day of default on the part of the contractor, the contractual fine for the previous day plus an additional CZK thirty-five (35) thousand. The contractual penalty calculation is as follows:

### Vpn=1n2 407 000+35 000×(n-1) [CZK]

where: Vpn= Total amount of the penalty for n-days of default in handover of the work

### In the event that the contractor has, under Subsection 45.6 of the contract, been granted a certain period to remove defects impeding the operation of the work, and the contractor has failed to remedy such defects in that period, then the purchaser may demand the contractor to pay, and the contractor shall then be required to pay, a contractual penalty in the amount of CZK two hundred fifty (250) thousand for each day, even begun, of contractor delay in the commencement of remedy of defects impeding the operation of the work, or in the amount of CZK fifty (50) thousand for each day, even begun, of contractor delay in the commencement of remedy of defects not impeding the operation of the work. Remedy of the defect in question does not relieve the contractor’s obligation to pay any contractual penalties due under subsection 44.1.2.9 of the contract.

### The burden of proof for delays attributable to the contractor shall rest with the purchaser.

### In the event that total contractual penalties levied under Subsection 42.1.2 of the contract reach fifteen per cent (15%) of the contract price, the purchaser may withdraw from the contract without renouncing any of its other rights under the contract.

Contractual penalties for failure to achieve the guarantee parameters of the work.

### The contractor hereby warrants and represents that the work as delivered shall achieve the guaranteed parameters given in Enclosure 2 of the contract. The guaranteed parameters shall be measured on the terms and timetable specified in the contract, particularly in Enclosure 2 of the contract. In the event that the guarantee measurement performed pursuant to the contract reveals that guaranteed parameters specified in Enclosure 2 of the contract have not been achieved, the contractor shall be liable to pay the purchaser contractual penalties as specified in Subsections 44.2.2 to 44.2.72 of the contract.

### For failure to deliver the guarantee parameter specified under Subsection 2.3.1 in Enclosure 2 of the contract (consumption of the DeNOx reducing agent) in the guarantee test “A”, the contractor shall pay a contractual penalty totalling

#### CZK one (1) million one hundred thirty-five (135) thousand for every commenced 0.1 kg of consumption of the reducing agent per tonne of waste for which the measured value of the reducing agent, recalculated at a hundred (100) per cent concentration, is higher than the guaranteed value, if the reducing agent is ammonia;

#### CZK seven hundred nine (709) thousand for every commenced 0.1 kg of consumption of the reducing agent per tonne of waste for which the measured value of the reducing agent, recalculated at a hundred (100) per cent concentration, is higher than the guaranteed value, if the reducing agent is urea.

### For failure to deliver the guarantee parameter specified under Subsection 2.3.1 in Enclosure 2 of the contract (consumption of the DeNOx reducing agent) in the guarantee test “B”, the contractor shall pay a contractual penalty totalling

#### CZK seven (7) million three hundred seventy-seven (377) thousand for every commenced 0.1 kg of consumption of the reducing agent per tonne of waste for which the measured value of the reducing agent, recalculated at a hundred (100) per cent concentration, is higher than the guaranteed value, if the reducing agent is ammonia;

#### CZK four (4) million six hundred ten (610) thousand for every commenced 0.1 kg of consumption of the reducing agent per tonne of waste for which the measured value of the reducing agent, recalculated at a hundred (100) per cent concentration, is higher than the guaranteed value, if the reducing agent is urea.

### For failure to deliver the guarantee parameter specified under Subsection 2.3.2 in Enclosure 2 of the contract (consumption of NaOH) in the guarantee test “A”, the contractor shall pay a contractual penalty in the amount of CZK seventeen (17) thousand for every commenced 0.1 kg/h of consumption by which the measured consumption is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.3.2 in Enclosure 2 of the contract (consumption of NaOH) in the guarantee test “B”, the contractor shall pay a contractual penalty in the amount of CZK one hundred eleven (111) thousand for every commenced 0.1 kg/h of consumption by which the measured consumption is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.3.3 in Enclosure 2 of the contract (consumption of Ca(OH)2) in the guarantee test “A”, the contractor shall pay a contractual penalty in the amount of CZK eleven (11) thousand for every commenced 0.1 kg/h of consumption by which the measured consumption is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.3.3 in Enclosure 2 of the contract (consumption of Ca(OH)2) in the guarantee test “B”, the contractor shall pay a contractual penalty in the amount of CZK seventy four (74) thousand for every commenced 0.1 kg/h of consumption by which the measured consumption is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.3.4 in Enclosure 2 of the contract (consumption of activated carbon) in the guarantee test “A”, the contractor shall pay a contractual penalty in the amount of CZK one hundred thirteen (113) thousand for every commenced 0.1 kg/h of consumption by which the measured consumption is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.3.4 in Enclosure 2 of the contract (consumption of activated carbon) in the guarantee test “B”, the contractor shall pay a contractual penalty in the amount of CZK seven hundred thirty-eight (738) thousand for every commenced 0.1 kg/h of consumption by which the measured consumption is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.3.5 in Enclosure 2 of the contract (consumption of NaHCO3) in the guarantee test “A”, the contractor shall pay a contractual penalty in the amount of CZK twenty-three (23) thousand for every commenced 0.1 kg/h of consumption by which the measured consumption is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.3.5 in Enclosure 2 of the contract (consumption of NaHCO3) in the guarantee test “B”, the contractor shall pay a contractual penalty in the amount of CZK one hundred forty-eight (148) thousand for every commenced 0.1 kg/h of consumption by which the measured consumption is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.3.6 in Enclosure 2 of the contract (consumption of CaO) in the guarantee test “A”, the contractor shall pay a contractual penalty in the amount of CZK eleven (11) thousand for every commenced 0.1 kg/h of consumption by which the measured consumption is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.3.6 in Enclosure 2 of the contract (consumption of CaO) in the guarantee test “B”, the contractor shall pay a contractual penalty in the amount of CZK seventy-four (74) thousand for every commenced 0.1 kg/h of consumption by which the measured consumption is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.3.7 in Enclosure 2 of the contract (consumption of NaCl) in the guarantee test “A”, the contractor shall pay a contractual penalty in the amount of CZK nine (9) thousand for every commenced 0.1 kg/h of consumption by which the measured consumption is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.3.7 in Enclosure 2 of the contract (consumption of NaCl) in the guarantee test “B”, the contractor shall pay a contractual penalty in the amount of CZK sixty-one (61) thousand for every commenced 0.1 kg/h of consumption by which the measured consumption is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.3.8 in Enclosure 2 of the contract (consumption of CaCO3) in the guarantee test “A”, the contractor shall pay a contractual penalty in the amount of CZK fifteen (15) thousand for every commenced 0.1 kg/h of consumption by which the measured consumption is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.3.8 in Enclosure 2 of the contract (consumption of CaCO3) in the guarantee test “B”, the contractor shall pay a contractual penalty in the amount of CZK ninety-eight (98) thousand for every commenced 0.1 kg/h of consumption by which the measured consumption is higher than the guaranteed value.

### For failure to deliver the guarantee parameters specified under Subsections 2.3.9.1 to 2.3.9.n in Enclosure 2 of the contract, Chapter 2.3, table of Other Reagents for Capturing Acid Components of Flue Gases and Heavy Metals (usage of other reagents for the capture of acid components of flue gases and heavy metals) in the guarantee test “A”, the contractor shall pay a contractual penalty calculated as follows for every reagent specified in the table of Other Reagents for which the guaranteed parameter of reagent usage is not delivered:

#### VP=JCi × 9 457×∆Si, where:

#### JCi is the unit price of reagent 2.3.9.i defined by the contracting authority in the procurement procedure,

#### ∆Si is the overage above the value of consumption for reagent 2.3.9.i, i.e. the value by which the measured value is higher than the consumption value for reagent 2.3.9.i for the capture of acid components of flue gases and heavy metals in kg/h stated by the economic operator in Volume C2 of the tender (Enclosure 2 of the contract - Guaranteed Parameters), Chapter 2.3, Table of Other Reagents for Capturing Acid Components of Flue Gases and Heavy Metals, guaranteed parameter 2.3.9.i.

#### VP is the amount of the penalty for failure to deliver on the guaranteed value of consumption of reagent 2.3.9.i in CZK,

#### i is the number of the reagent in the table.

### For failure to deliver the guarantee parameters specified under Subsections 2.3.9.1 to 2.3.9.n in Enclosure 2 of the contract, Chapter 2.3, table of Other Reagents for Capturing Acid Components of Flue Gases and Heavy Metals (usage of other reagents for the capture of acid components of flue gases and heavy metals) in the guarantee test “B”, the contractor shall pay a contractual penalty calculated as follows for every reagent specified in the table of Other Reagents for which the guaranteed parameter of reagent usage is not delivered:

#### VP=JCi × 132 399×∆Si, where:

#### JCi is the unit price of reagent 2.3.9.i defined by the contracting authority in the procurement procedure,

#### ∆Si is the overage above the value of consumption for reagent 2.3.9.i, i.e. the value by which the measured value is higher than the consumption value for reagent 2.3.9.i for the capture of acid components of flue gases and heavy metals in kg/h stated by the economic operator in Volume C2 of the tender (Enclosure 2 of the contract - Guaranteed Parameters), Chapter 2.3, Table of Other Reagents for Capturing Acid Components of Flue Gases and Heavy Metals, guaranteed parameter 2.3.9.i.

#### VP is the amount of the penalty for failure to deliver on the guaranteed value of consumption of reagent 2.3.9.i in CZK,

#### i is the number of the reagent in the table.

### For failure to deliver the guarantee parameter specified under Subsection 2.3.10 in Enclosure 2 of the contract (consumption of HCl) in the guarantee test “A”, the contractor shall pay a contractual penalty in the amount of CZK six (6) thousand for every commenced 0.1 kg/h of consumption by which the measured consumption is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.3.10 in Enclosure 2 of the contract (consumption of HCl) in the guarantee test “B”, the contractor shall pay a contractual penalty in the amount of CZK thirty-seven (37) thousand for every commenced 0.1 kg/h of consumption by which the measured consumption is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.3.11 in Enclosure 2 of the contract (consumption of Na2S) in the guarantee test “A”, the contractor shall pay a contractual penalty in the amount of CZK forty-seven (47) thousand for every commenced 0.1 kg/h of consumption by which the measured consumption is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.3.11 in Enclosure 2 of the contract (consumption of Na2S) in the guarantee test “B”, the contractor shall pay a contractual penalty in the amount of CZK three hundred seven (307) thousand for every commenced 0.1 kg/h of consumption by which the measured consumption is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.3.12 in Enclosure 2 of the contract (consumption of FeCl3) in the guarantee test “A”, the contractor shall pay a contractual penalty in the amount of CZK ten (10) thousand for every commenced 0.1 kg/h of consumption by which the measured consumption is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.3.12 in Enclosure 2 of the contract (consumption of FeCl3) in the guarantee test “B”, the contractor shall pay a contractual penalty in the amount of CZK sixty-eight (68) thousand for every commenced 0.1 kg/h of consumption by which the measured consumption is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.3.13 in Enclosure 2 of the contract (consumption of Cyclohexamine) in the guarantee test “A”, the contractor shall pay a contractual penalty in the amount of CZK three hundred seventy-eight (378) thousand for every commenced 0.1 kg/h of consumption by which the measured consumption is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.3.13 in Enclosure 2 of the contract (consumption of Cyclohexamine) in the guarantee test “B”, the contractor shall pay a contractual penalty in the amount of CZK two (2) million four hundred fifty-nine (459) thousand for every commenced 0.1 kg/h of consumption by which the measured consumption is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.3.14 in Enclosure 2 of the contract (consumption of Ca(OH)2) in the guarantee test “A”, the contractor shall pay a contractual penalty in the amount of CZK eleven (11) thousand for every commenced 0.1 kg/h of consumption by which the measured consumption is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.3.14 in Enclosure 2 of the contract (consumption of Ca(OH)2) in the guarantee test “B”, the contractor shall pay a contractual penalty in the amount of CZK seventy-four (74) thousand for every commenced 0.1 kg/h of consumption by which the measured consumption is higher than the guaranteed value.

### For failure to deliver the guarantee parameters specified under Subsections 2.3.15.1 to 2.3.15.n in Enclosure 2 of the contract, Chapter 2.3, table of Other Reagents for Wastewater Treatment and Feed Water Chemical Treatment (usage of other reagents for wastewater treatment and feed water chemical treatment) in the guarantee test “A”, the contractor shall pay a contractual penalty calculated as follows for every reagent specified in the table of Other Reagents for which the guaranteed parameter of reagent usage is not delivered:

#### VP=JCi × 9 457×∆Si, where:

#### JCi is the unit price of reagent 2.3.15.i defined by the contracting authority in the procurement procedure,

#### ∆Si is the overage above the value of consumption for reagent 2.3.15.i, i.e. the value by which the measured value is higher than the consumption value for reagent 2.3.15.i for wastewater treatment and feed water chemical treatment in kg/h stated by the economic operator in Volume C2 of the tender (Enclosure 2 of the contract - Guaranteed Parameters), Chapter 2.3, Table of Other Reagents for Wastewater Treatment and Feed Water Chemical Treatment, guaranteed parameter 2.3.15.i.

#### VP is the amount of the penalty for failure to deliver on the guaranteed value of consumption of reagent 2.3.15.i in CZK,

#### i is the number of the reagent in the table.

### For failure to deliver the guarantee parameters specified under Subsections 2.3.15.1 to 2.3.15.n in Enclosure 2 of the contract, Chapter 2.3, table of Other Reagents for Wastewater Treatment and Feed Water Chemical Treatment (usage of other reagents for wastewater treatment and feed water chemical treatment) in the guarantee test “B”, the contractor shall pay a contractual penalty calculated as follows for every reagent specified in the table of Other Reagents for which the guaranteed parameter of reagent usage is not delivered:

#### VP=JCi × 132 399×∆Si, where:

#### JCi is the unit price of reagent 2.3.15.i defined by the contracting authority in the procurement procedure,

#### ∆Si is the overage above the value of consumption for reagent 2.3.15.i, i.e. the value by which the measured value is higher than the consumption value for reagent 2.3.15.i for wastewater treatment and feed water chemical treatment in kg/h stated by the economic operator in Volume C2 of the tender (Enclosure 2 of the contract - Guaranteed Parameters), Chapter 2.3, Table of Other Reagents for Wastewater Treatment and Feed Water Chemical Treatment, guaranteed parameter 2.3.15.i.

#### VP is the amount of the penalty for failure to deliver on the guaranteed value of consumption of reagent 2.3.15.i in CZK,

#### i is the number of the reagent in the table.

### For failure to deliver the guarantee parameter specified under Subsection 2.5.1 in Enclosure 2 of the contract (Slag production) in the guarantee test “A”, the contractor shall pay a contractual penalty in the amount of CZK two (2) thousand for every commenced 1 kg/h of production by which the measured production is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.5.1 in Enclosure 2 of the contract (Slag production) in the guarantee test “B”, the contractor shall pay a contractual penalty in the amount of CZK twelve (12) thousand for every commenced 1 kg/h of production by which the measured production is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.5.2 in Enclosure 2 of the contract (Production of washed fly ash – classified as other waste) in the guarantee test “A”, the contractor shall pay a contractual penalty in the amount of CZK three (3) thousand for every commenced 0.1 kg/h of production by which the measured production is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.5.2 in Enclosure 2 of the contract (Production of washed fly ash – classified as other waste) in the guarantee test “B”, the contractor shall pay a contractual penalty in the amount of CZK twenty (20) thousand for every commenced 0.1 kg/h of production by which the measured production is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.5.3 in Enclosure 2 of the contract (Production of filter cake – classified as other waste) in the guarantee test “A”, the contractor shall pay a contractual penalty in the amount of CZK three (3) thousand for every commenced 0.1 kg/h of production by which the measured production is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.5.3 in Enclosure 2 of the contract (Production of filter cake – classified as other waste) in the guarantee test “B”, the contractor shall pay a contractual penalty in the amount of CZK twenty (20) thousand for every commenced 0.1 kg/h of production by which the measured production is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.5.4 in Enclosure 2 of the contract (Production of other waste (not specified above) and classified as other waste) in the guarantee test “A”, the contractor shall pay a contractual penalty in the amount of CZK three (3) thousand for every commenced 0.1 kg/h of production by which the measured production is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.5.4 in Enclosure 2 of the contract (Production of other waste (not specified above) and classified as other waste) in the guarantee test “B”, the contractor shall pay a contractual penalty in the amount of CZK twenty (20) thousand for every commenced 0.1 kg/h of production by which the measured production is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.5.5 in Enclosure 5 of the contract (Production of filter cake – classified as hazardous waste) in the guarantee test “A”, the contractor shall pay a contractual penalty in the amount of CZK eight (8) thousand for every commenced 0.1 kg/h of production by which the measured production is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.5.5 in Enclosure 5 of the contract (Production of filter cake – classified as hazardous waste) in the guarantee test “B”, the contractor shall pay a contractual penalty in the amount of CZK forty-nine (49) thousand for every commenced 0.1 kg/h of production by which the measured production is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.5.6 in Enclosure 2 of the contract (Production of bag filter dust – classified as hazardous waste) in the guarantee test “A”, the contractor shall pay a contractual penalty in the amount of CZK eight (8) thousand for every commenced 0.1 kg/h of production by which the measured production is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.5.6 in Enclosure 2 of the contract (Production of bag filter dust – classified as hazardous waste) in the guarantee test “B”, the contractor shall pay a contractual penalty in the amount of CZK forty-nine (49) thousand for every commenced 0.1 kg/h of production by which the measured production is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.5.7 in Enclosure 2 of the contract (Production of other (not specified above) hazardous waste) in the guarantee test “A”, the contractor shall pay a contractual penalty in the amount of CZK eight (8) thousand for every commenced 0.1 kg/h of production by which the measured production is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.5.7 in Enclosure 2 of the contract (Production of other (not specified above) hazardous waste) in the guarantee test “B”, the contractor shall pay a contractual penalty in the amount of CZK forty-nine (49) thousand for every commenced 0.1 kg/h of production by which the measured production is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.6.3 in Enclosure 2 of the contract (Clarified water consumption) in the guarantee test “A”, the contractor shall pay a contractual penalty in the amount of CZK twenty-eight (28) thousand for every commenced 0.1 m3/h of consumption by which the measured consumption is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.6.3 in Enclosure 2 of the contract (Clarified water consumption) in the guarantee test “B”, the contractor shall pay a contractual penalty in the amount of CZK one hundred eighty-four (184) thousand for every commenced 0.1 m3/h of consumption by which the measured consumption is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.3.4 in Enclosure . 2 of the contract (Demineralised water consumption) in the guarantee test “A”, the contractor shall pay a contractual penalty in the amount of CZK forty-seven (47) thousand for every commenced 0.1 m3/h of consumption by which the measured consumption is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.3.4 in Enclosure . 2 of the contract (Demineralised water consumption) in the guarantee test “B”, the contractor shall pay a contractual penalty in the amount of CZK three hundred seven (307) thousand for every commenced 0.1 m3/h of consumption by which the measured consumption is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.6.5 in Enclosure 2 of the contract (Raw water consumption) in the guarantee test “A”, the contractor shall pay a contractual penalty in the amount of CZK nineteen (19) thousand for every commenced 0.1 m3/h of consumption by which the measured consumption is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.6.5 in Enclosure 2 of the contract (Raw water consumption) in the guarantee test “B”, the contractor shall pay a contractual penalty in the amount of CZK one hundred twenty-three (123) thousand for every commenced 0.1 m3/h of consumption by which the measured consumption is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.8.1 in Enclosure 2 of the contract (Electrical output transferred form the EVO outlet to the 35 kV distribution network (net) without heat delivery to the hot water piping system) in the guarantee test “A”, the contractor shall pay a contractual penalty in the amount of CZK one hundred fifty-five (155) thousand for every commenced 0.01 MWe, by which the measured electrical output is lower than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.8.1 in Enclosure 2 of the contract (Electrical output transferred form the EVO outlet to the 35 kV distribution network (net) without heat delivery to the hot water piping system) in the guarantee test “B”, the contractor shall pay a contractual penalty in the amount of CZK one (1) million seven (7) thousand for every commenced 0.01 MWe, by which the measured electrical output is lower than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.8.2 in Enclosure 2 of the contract (Electrical output at the terminals of the turbo generator (gross) in EVO operation without heat delivery to the hot water piping system) in the guarantee test “A”, the contractor shall pay a contractual penalty in the amount of CZK thirteen (13) thousand for every commenced 0.01 MWe, by which the measured electrical output is lower than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.8.2 in Enclosure 2 of the contract (Electrical output at the terminals of the turbo generator (gross) in EVO operation without heat delivery to the hot water piping system) in the guarantee test “B”, the contractor shall pay a contractual penalty in the amount of CZK eighty-six (86) thousand for every commenced 0.01 MWe, by which the measured electrical output is lower than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.8.3 in Enclosure 2 of the contract (Electrical output transferred from the EVO outlet to the 35 kV distribution network (net) with 32.0 MWt of heat delivery to the hot water piping system) in the guarantee test “A”, the contractor shall pay a contractual penalty in the amount of CZK two hundred eighty eight (288) thousand for every commenced 0.01 MWe, by which the measured electrical output is lower than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.8.3 in Enclosure 2 of the contract (Electrical output transferred from the EVO outlet to the 35 kV distribution network (net) with 32.0 MWt of heat delivery to the hot water piping system) in the guarantee test “B”, the contractor shall pay a contractual penalty in the amount of CZK one (1) million eight hundred seventy (870) thousand for every commenced 0.01 MWe, by which the measured electrical output is lower than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.8.4 in Enclosure 2 of the contract (Electrical output at the turbo generator terminals (gross) in EVO operation with 32.0 MWt of heat delivery to the hot water piping system) in the guarantee test “A”, the contractor shall pay a contractual penalty in the amount of CZK twenty-five (25) thousand for every commenced 0.01 MWe, by which the measured electrical output is lower than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.8.4 in Enclosure 2 of the contract (Electrical output at the turbo generator terminals (gross) in EVO operation with 32.0 MWt of heat delivery to the hot water piping system) in the guarantee test “B”, the contractor shall pay a contractual penalty in the amount of CZK one hundred sixty (160) thousand for every commenced 0.01 MWe, by which the measured electrical output is lower than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.8.5 in Enclosure 2 of the contract (Rated stable thermal output for heat delivery to the hot water piping system) in the guarantee test “A”, the contractor shall pay a contractual penalty in the amount of CZK one hundred eleven (111) thousand for every commenced 0.01 MWe, by which the measured thermal output is lower than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.8.5 in Enclosure 2 of the contract (Rated stable thermal output for heat delivery to the hot water piping system) in the guarantee test “B”, the contractor shall pay a contractual penalty in the amount of CZK seven hundred nineteen (719) thousand for every commenced 0.01 MWe, by which the measured thermal output is lower than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.10.1 in Enclosure 2 of the contract (maximum boiler grate wear), the contractor shall pay a contractual penalty calculated as follows:

### VP=20-Zrošt×∆Orošt×7 093 000, where:

#### ∆Orošt is the value of the increase in maximum grate bars replacement, i.e. the value by which the value of the actual annual grate bars replacement in relation to the the total quantity of grate bars in %/year (expressed as a decimal number) for the duration of the grate warranty under Article 45.1.1.1 ii) of the contract is higher than the guaranteed value,

#### Zrošt is the length of the grate warranty under Article 45.1.1.1 ii) of the contract, converted into years,

#### VP is the amount of the penalty for failing to deliver the guaranteed parameter.

### For failure to deliver the guarantee parameter specified under Subsection 2.10.2 in Enclosure 2 of the contract (maximum boiler lining wear – tiles), the contractor shall pay a contractual penalty calculated as follows:

### VP=20-Zvyzdívky×∆Ovyzdívky×31 000, where:

#### ∆Ovyzdívky is the value of the increase in maximum boiler lining wear in m2, i.e. the value by which the actual average annual boiler lining wear in m2/year over the duration of the warranty on boiler heat transfer surfaces under Article 45.1.1.1 iii) of the contract is higher than the guaranteed value,

#### Zvyzdívky is the length of the warranty on boiler heat transfer surfaces under Article 45.1.1.1 iii) of the contract, converted into years,

#### VP is the amount of the penalty for failing to deliver the guaranteed parameter.

### Any liner damage of greater than 0.8 m2 will be counted twice when the wear is determined.

### For failure to deliver the guarantee parameter specified under Subsection 2.10.3 in Enclosure 2 of the contract (maximum wear of the refractory concrete (or of another similar material with the same function) reducing the boiler lifetime), the contractor shall pay a contractual penalty calculated as follows:

### VP=20-Zvyzdívky×∆Ožárobeton×31 000, where:

#### ∆Ožárobeton is the value of the increase in maximum wear of the refractory concrete in m2, i.e. the value by which the actual average annual refractory concrete wear in m2/year over the duration of the warranty on boiler heat transfer surfaces under Article 45.1.1.1 iii) of the contract is higher than the guaranteed value,

#### Zvyzdívky is the length of the warranty on boiler heat transfer surfaces under Article 45.1.1.1 iii) of the contract, converted into years,

#### VP is the amount of the penalty for failing to deliver the guaranteed parameter.

### Any liner damage of greater than 1 m2 will be counted twice when the wear is determined.

### For failure to deliver the guarantee parameter specified under Subsection 2.10.4 in Enclosure 2 of the contract (abrasive and / or corrosion loss of the original thickness of the anti-corrosion alloy cladding of the outlet superheater), the contractor shall pay a contractual penalty calculated as follows:

### VP=20-Zpřehřívák×∆Opřehřívák×4 433 000, where:

#### ∆Opřehřívák is the value of the increase in maximum abrasive and / or corrosion loss of the original thickness of the anti-corrosion alloy cladding of the outlet superheater, i.e. the value by which the actual annual abrasive and / or corrosion loss of the original thickness in %/year (expressed as a decimal number) for the duration of the superheater warranty under Article 45.1.1.1 iv) of the contract is higher than the guaranteed value,

#### Zpřehřívák is the length of the superheater warranty under Article 45.1.1.1 iv) of the contract, converted into years,

#### VP is the amount of the penalty for failing to deliver the guaranteed parameter.

### For failure to deliver the guarantee parameter specified under Subsection 2.10.5 in Enclosure 2 of the contract (abrasive and / or corrosion loss of the original thickness of the anti-corrosion alloy cladding outside the outlet superheater), the contractor shall pay a contractual penalty calculated as follows:

### VP=20-Zvyzdívky×∆Oslitina×Vslitina×101 000, where:

#### ∆Oslitina is the value of the increase in maximum abrasive and / or corrosion loss of the original thickness of the anti-corrosion alloy cladding outside the outlet superheater, i.e. the value by which the actual annual abrasive and / or corrosion loss outside the outlet superheater in %/year (expressed as a decimal number) for the duration of the warranty on boiler heat transfer surfaces under Article 45.1.1.1 iii) of the contract is higher than the guaranteed value,

#### Zvyzdívky is the length of the warranty on boiler heat transfer surfaces under Article 45.1.1.1 iii) of the contract, converted into years,

#### Vslitina is the total area of protected boiler heat transfer surfaces with anti-corrosion alloy cladding (other than of the outlet superheater),

#### VP is the amount of the penalty for failing to deliver the guaranteed parameter.

### For failure to deliver the guarantee parameter specified under Subsection 2.10.6 in Enclosure 2 of the contract (abrasive and / or corrosion loss of any part of the boiler pressure unit other than parts protected by anti-corrosion alloy cladding), the contractor shall pay a contractual penalty in the amount of CZK four hundred fifty (450) thousand for every commenced per cent by which the measured value of such loss is higher than the guaranteed value.

### For failure to deliver the guarantee parameter specified under Subsection 2.10.7 in Enclosure 2 of the contract (abrasive or corrosive loss on any part of the flue gas transportation and treatment unit (vents, filters, flaps,...), the contractor shall pay a contractual penalty in the amount of CZK four hundred fifty (450) thousand for every commenced per cent by which the measured value of such loss is higher than the guaranteed value.

### If failing to meet the guaranteed parameter specified under points 2.11.1 and 2.11.2 in Enclosure 2 to the contract (availability of steam production) in the 1st year of operation, the contractor shall pay a contractual penalty in the amount determined according to the formula:

## PDVP=(mVPG×qiVPG×DPG)-(mVPR×qiVPR×DPR)×1.5, where:

#### mVPG is the guaranteed value of the amount of the output steam out of the boiler in the point “D” of the capacity diagram in kg/s stated by the economic operator/participant in Volume C2 of the tender (Enclosure 2 of the contract - Guaranteed Parameters), guaranteed parameter 2.11.1. (Mass flow rate of steam at the temperature and pressure of the output steam according to chapter 2.6),

#### qiVPG is the enthalpy of the output steam at the temperature and pressure of the output steam according to chapter 2.6 Volume C2 of the tender (Enclosure 2 of the contract - Guaranteed Parameters) in kJ/kg,

#### DPG is the guaranteed value of availability of operation in h stated by the economic operator/participant in Volume C2 of the tender (Enclosure 2 of the contract - Guaranteed Parameters), guaranteed parameter 2.11.2.

#### mVPR is the actual value of the amount of the output steam out of the boiler in the point “D” of the capacity diagram in kg/s achieved in the relevant guarantee measurement according to Enclosure 2 of the contract - Guaranteed Parameters) for the guaranteed parameter 2.11.1. (Mass flow rate of steam at the temperature and pressure of the output steam according to chapter 2.6),

#### qiVPR is the enthalpy of the output steam at the actual temperature and pressure of the output steam according to chapter 2.6 in kJ/kg achieved in the relevant guarantee measurement according to Enclosure 2 of the contract - Guaranteed Parameters,

#### DPR is the actual value of availability of operation in h achived in the given year,

#### PDVP is the calculated value of the contractual penalty in CZK.

### If failing to meet the guaranteed parameter specified under points 2.11.1 and 2.11.2 in Enclosure 2 to the contract (availability of steam production) in the 2nd year of operation, the contractor shall pay a contractual penalty in the amount determined according to the formula:

## PDVP=(mVPG×qiVPG×DPG)-(mVPR×qiVPR×DPR)×20.5, where:

#### mVPG is the guaranteed value of the amount of the output steam out of the boiler in the point “D” of the capacity diagram in kg/s stated by the economic operator/participant in Volume C2 of the tender (Enclosure 2 of the contract - Guaranteed Parameters), guaranteed parameter 2.11.1. (Mass flow rate of steam at the temperature and pressure of the output steam according to chapter 2.6),

#### qiVPG is the enthalpy of the output steam at the temperature and pressure of the output steam according to chapter 2.6 Volume C2 of the tender (Enclosure 2 of the contract - Guaranteed Parameters) in kJ/kg,

#### DPG is the guaranteed value of availability of operation in h stated by the economic operator/participant in Volume C2 of the tender (Enclosure 2 of the contract - Guaranteed Parameters), guaranteed parameter 2.11.2.

#### mVPR is the actual value of the amount of the output steam out of the boiler in the point “D” of the capacity diagram in kg/s achieved in the relevant guarantee measurement according to Enclosure 2 of the contract - Guaranteed Parameters) for the guaranteed parameter 2.11.1. (Mass flow rate of steam at the temperature and pressure of the output steam according to chapter 2.6),

#### qiVPR is the enthalpy of the output steam at the actual temperature and pressure of the output steam according to chapter 2.6 in kJ/kg achieved in the relevant guarantee measurement according to Enclosure 2 of the contract - Guaranteed Parameters,

#### DPR is the actual value of availability of operation in h achived in the given year,

#### PDVP is the calculated value of the contractual penalty in CZK.

### If failing to meet the guaranteed parameter specified under Subsection 2.11.3 of Enclosure 2 to the contract (availability of steam-water cycle [VWSC]) in the 1st year of operation, the contractor shall pay a contractual penalty of four (4) thousand Czech koruna for each commenced one h by which the actual availability of the steam-water cycle [VWSC] in the relevant year of operation, determined in accordance with chapter 2.11.3 of Enclosure 2 to the contract, is lower than the guaranteed value. Furthermore, if the actual value falls short of the limit value given in Subsection 2.11.1 of Enclosure 2 of the contract, the purchaser shall, in addition to the contractual penalty, have the right to withdraw from the contract.

### If failing to meet the guaranteed parameter specified under Subsection 2.11.3 of Enclosure 2 to the contract (availability of steam-water cycle [VWSC]) in the 2nd year of operation, the contractor shall pay a contractual penalty of  fifty-one (51) thousand Czech koruna for each commenced one h by which the actual availability of the steam-water cycle [VWSC] in the relevant year of operation, determined in accordance with chapter 2.11.3 of Enclosure 2 to the contract, is lower than the guaranteed value. Furthermore, if the actual value falls short of the limit value given in Subsection 2.11.1 of Enclosure 2 of the contract, the purchaser shall, in addition to the contractual penalty, have the right to withdraw from the contract.

### Failure to achieve any of the limit values specified in Enclosure 2 to the contract under subsections:

| 2.1.1 | Continuous heat output of the combustion section |
| --- | --- |
| 2.1.2 | Minimum heat output of the combustion section |
| 2.1.3 | Minimum amount of waste combusted (mass flow) |
| 2.1.4 | Permanent amount of waste combusted (mass flow) |
| 2.1.5 | Peak amount of waste combusted (mass flow): |
| 2.1.6 | Flue gas holding time at a temperature of at least 850°C in the entire range of the firing capacity diagram (downstream of the last air inlet) |
| 2.1.7 | Under-burning in cinder (slag) and grate through fraction in the entire range of the firing capacity diagram; related to the dry matter as loss on ignition |
| 2.1.8 | Peak thermal output of the combustion section |
| 2.2.1 | Dust |
| 2.2.2 | Cadmium, thallium (Cd+Tl) |
| 2.2.3 | Other heavy metals, total (Sb, As, Pb, Cr, Co, Cu, Mn, Ni, V) |
| 2.2.4 | Hydrogen chloride (HCl) |
| 2.2.5 | Hydrogen fluoride (HF) |
| 2.2.6 | Sulphur dioxide (SO2) |
| 2.2.7 | Oxides of nitrogen (NOx as NO2) |
| 2.2.8 | Carbon monoxide (CO) |
| 2.2.9 | Ammonia (NH3) |
| 2.2.10 | TVOC |
| 2.2.11 | PCDD/F |
| 2.2.12 | PCDD/F + PCB with dioxin effect |
| 2.2.13 | Mercury and its compounds (Hg) |
| 2.4.1 | Total insoluble solids (TSS) |
| 2.4.2 | Total organic carbon (TOC) |
| 2.4.3 | pH |
| 2.4.4 | Mercury and its compounds expressed as Hg |
| 2.4.5 | Cadmium and its compounds expressed as Cd |
| 2.4.6 | Thallium and its compounds expressed as Tl |
| 2.4.7 | Arsenic and its compounds expressed as As |
| 2.4.8 | Lead and its compounds expressed as Pb |
| 2.4.9 | Chromium and its compounds expressed as Cr |
| 2.4.10 | Copper and its compounds expressed as Cu |
| 2.4.11 | Nickel and its compounds expressed as Ni |
| 2.4.12 | Zinc and its compounds expressed as Zn |
| 2.4.13 | Antimony and its compounds expressed as Sb |
| 2.4.14 | Ammonium nitrogen (N-NH4+) |
| 2.4.15 | Sulphates (SO42-) |
| 2.4.16 | Total of PCDD/F |
| 2.4.17 | RAS – Soluble inorganic salts |
| 2.6.1 | Rated temperature of overheated steam on the boiler outlet |
| 2.6.2 | Oscillation of the thermal power output of the boiler |
| 2.7.1 | Thermal efficiency of the boiler in the point “D” (η) |
| 2.8.5 | Rated stable thermal output for heat delivery to the hot water piping system (while concurrently achieving guaranteed parameter 2.8.3) |
| 2.8.6 | Gross electrical efficiency in maximum condensing operation of the turbo generator (state 1) |
| 2.9.1 | Vacuum drop |
| 2.11.1 2.11.2 | Annual capacity availability of steam production [VDP] Availability of operation (steam production) |
| 2.11.3 | Availability of steam-water cycle (VWSC) |
| 2.12.1 | Uninterrupted boiler operation time |
| 2.13 | Noisiness |

### shall be considered to constitute a material breach of the contract on the part of the contractor. In that event, the purchaser may refuse to accept the work and / or withdraw from the contract and / or have the work brought into compliance with the contract at the contractor’s expense, unless the latter is performed by the contractor pursuant to Article 30.2.4 of the contract, without limiting the purchaser’s other rights under the contract, including the right to be paid contractual penalties and to reimbursement for damages by the contractor.

### In the event that a particular parameter has been determined to not have been achieved, and therefore a breach of contract arises, but the defect in question does not impede the safe and reliable operation of the work, the purchaser may, at its own discretion, declare the contractor's payment of the relevant contractual penalties, as defined above, to be sufficient satisfaction of the purchaser's claims in relation to such a defect, and that therefore, once the contractual penalty has been paid, the purchaser shall thereafter refrain from requiring the contractor to change or modify the work so as to remedy that particular defect.

### In the event that total contractual penalties levied under Subsections 44.2.2 to 44.2.69 of the contract reach fifteen per cent (15%) of the contract price, the purchaser may withdraw from the contract without renouncing any of its other rights under the contract, including rights to the payment of contractual penalties, reimbursement of damages, and draw from the bank guarantee for the work.

### In the event that the guarantee measurement finds parameter values superior to those specified in the contract, the purchaser shall not be required to provide benefits or compensation of any kind to the contractor.

Contractual penalties for breaches of selected contractor obligations

### For material breaches of the “Contractors' Code of Conduct” given in Enclosure 12 of the contract, the contractor shall pay a contractual penalty in the amount of CZK five (5) thousand, for each instance of breach; this applies to material breaches for which a penalty is not specified directly in the Contractors' Code of Conduct.

### In the event of a breach of confidentiality regarding information and contractual documents pursuant to Subsection 18 of the contract attributable to the contractor, the purchaser shall be entitled to a contractual penalty in the amount of CZK two hundred (200) thousand per instance of breach, unless the breach in question is deemed completely immaterial.

Common provisions for contractual penalties

### The purchaser’s entitlement to the payment of a contractual penalty shall not be conditioned on any formal steps of the purchaser other than written notice to the contractor to the effect that a contractual penalty is being levied, which shall include the rationale and calculation for the contractual penalty.

### The purchaser may surrender its right to any individual contractual penalty under the contract, without this affecting any of its other rights thereunder.

### The contractor shall pay all contractual penalties levied by direct bank transfer into the purchaser’s account within thirty (30) days from receipt of the purchaser’s invoice for the amount. The purchaser may, particularly if the contractor fails to pay a duly levied contractual penalty within the period specified, set off its claim to the payment of such penalty against the following or any other subsequent payment due to the contractor, or else draw down for the amount against the bank guarantee for the work.

### Unless agreed otherwise elsewhere in the contract, payment of contractual penalties by the contractor or alternatively the use of part or the entirety of the bank guarantee for the work for that purpose by the purchaser does not relieve the contractor of any of its other obligations under the contract.

### The total amount of contractual penalties that may be levied by the purchaser against the contractor under this Article 44 of the contract shall be limited to the equivalent of twenty (20) per cent of the contract price for the work. No such limitation shall apply, however, to contractual penalties due as a result of felony, intent, or gross negligence.

### The contractor shall reimburse the purchaser for damage exceeding any agreed contractual penalties pursuant to Article 46, Subsection 46.2 of the contract.

# LIABILITY FOR DEFECTS IN THE WORK, QUALITY WARRANTY

The contractor shall provide the purchaser with a warranty (warranty period) for quality; i.e., shall warrant that the work as a whole and all parts thereof are free of any and all defects, material and legal. The work or a part thereof shall be considered defective whenever non-conforming to the results specified in the contract, the work’s purpose and use as given in the contract, or lacks the parameters and properties explicitly agreed in the contract or required by general legislation and ČSN standards effective at the time of execution of the work. The warranty period, as further specified below in this Article 45 of the contract, shall commence on the day of work provisional acceptance in the sense of Article 31 of the contract.

### MATERIAL WARRANTY

### 45.1.1.1	 The contractor provides the purchaser with a quality warranty (warranty period) for proper construction, good quality, the correct selection of materials and the diligent execution of the works lasting twenty-four (24) months for the technological part of the work, with the following exceptions for which a different warranty period is agreed:

- Rubberised components of the work 	sixty (60) months

- Grate				................... (to be completed by the participant, at least 24 months)

- Protection for heat transfer surfaces .......... (to be completed by the participant, at least 24 months)

- Outlet superheater		................... (to be completed by the participant, at least 24 months)

The contractor shall also provide the purchaser with a quality warranty (warranty period) for proper construction, good quality, the correct selection of materials and the diligent execution of the works lasting sixty (60) months for the building part of the work.

### 45.1.1.2	The contractor shall guarantee the quality of the equipment design corresponding to the state of the art at the date of the submission of the bid given operation, maintenance and repair requirements. The contractor commits to take particular care to minimise wear through appropriate selection of materials and workmanship.

### 45.1.1.3	The contractor shall guarantee a subsystem design for the equipment to facilitate replacement of rapid-wear parts during operation between scheduled inspections is possible without cooling the equipment.

### COMPLETENESS WARRANTY

### 45.1.2.1	The contractor shall provide the purchaser with warranty for the completeness and correctness of documentation and sources prepared for and submitted to the purchaser in the execution of the work. Deliveries of goods and performance of works are part of the contractor’s obligations even if not explicitly listed in the contract but demonstrably required for the manufacture, flawless operation, monitoring, and maintenance, and operational and personnel safety of the system in question (regulations, official requirements, etc.).

### FUNCTIONAL WARRANTY

### 45.1.3.1	The contractor shall provide the purchaser with a warranty period for the correct functioning of the work of sixty (60) months.

### 45.1.3.2	If it becomes apparent over the warranty period that the work or a part thereof is incapable of performing its particular function despite professional repair, performed by the purchaser once the material warranty runs out, then the contractor shall, at its own expense, take such measures as may be required to restore correct functioning and ensure guaranteed parameters are met. Such measures shall be taken by the contractor upon consultation with the purchaser at a suitable time.

### PERFORMANCE WARRANTY

### 45.1.4.1	The contractor provides the purchaser with a warranty that the work will deliver the guarantee parameters as specified in Enclosure 2 of the contract over the twenty-four months of the warranty period.

The contractor shall not be held liable for warranty claims duly made during the warranty period if it can demonstrate that the defect in question arose in direct result of the purchaser’s operation of the work or a part thereof during the warranty period contrary to the requirements of operational regulations, maintenance regulations and / or contrary to the technical conditions specified in the contract. Until such time as the purchaser is demonstrated to have been at fault, it shall be assumed that the contractor is. Without regard for who is at fault for a defect being claimed under warranty, the contractor shall commence and carry on such works as are required to remedy the defect, so as to remedy the defect without undue delay. In the event that the contractor can demonstrate its lack of fault in relation to the defect, the purchaser shall reimburse the contractor for all reasonable and demonstrable expenses related to that defect’s remedy.

The purchaser shall provide the contractor with all required cooperation, particularly with information on the system’s operation and maintenance, operating states, etc.

Upon request, the purchaser shall provide the contractor with access to the work for purposes of investigating the cause of a defect.

In the event that, during the warranty period, it becomes apparent that the work has defects, the purchaser may, without limiting its other rights under the contract:

#### Require defect removal by repair of the work, if, in the purchaser's opinion, the defect in question is repairable; and / or

#### Require defect removal by replacement of the defective parts of the work, if, in the purchaser’s opinion, the defect in question is not repairable per (a) above; and / or

#### Require the remedy of any legal defects.

If a defect cannot be removed in any of the ways given in (a) through (c) above, the purchaser may, at its own discretion and with regard to the nature of the defect:

(i)		Require a reasonable discount of the contract price for the work; or

(ii)	Withdraw from the contract, in the case of non-removable defects impeding the operation of the work; or

(iii)	Have defects removed by a third party at the contractor’s expense.

The purchaser may change its choice of any of the claim types given above or combine claim types at any time.

Before commencing works to remedy a defect, the contractor shall report the cause of the defect and have the time and manner of removal (and any counter-claims) approved by the purchaser.

In the cases specified in Letters (a) and (b) of Subsection 45.5 of the contract, the contractor commits to arrive at the site of the defect and begin works to remedy such defect

- within twelve (12) hours from the defect being reported, for major defects impeding the safe and reliable operation of the work;

- within forty-eight (48) hours from the defect being reported, for defects not impeding the safe and reliable operation of the work, unless agreed otherwise with regard to the nature of the defect.

In the event of defect removal pursuant to Subsection 45.5 of the contract, the contractor shall remedy the defect without delay, but no later than within 30 days, unless agreed otherwise with regard to the nature of the defect.

In the event that the same defect occurs on the same system three times during the warranty period, the contractor shall, without undue delay, make design changes to the defective system and update the actual-state documentation.

In the event that the contractor fails to remedy duly claimed defects of the work within the time frame given in Subsections 45.5 to 45.7 of the contract, or that the contractor refuses to remedy such defects within that time frame, the purchaser may, with prior notice to the contractor, remedy the defect on its own or have it remedied, at the contractor’s expense, without limiting any of the purchaser’s rights under the contract. The contractor shall reimburse the purchaser for demonstrable and reasonable costs incurred in connection with removal of defects by the purchaser, and within thirty (30) days of receipt of the relevant invoice from the purchaser. In the event of non-payment of such an invoice, the purchaser may satisfy its claims by drawing down against the bank guarantee for the work.

If defective parts of the work are repaired or replaced during the warranty period, the warranty period for the work or part thereof is extended by the period during which the work or part thereof could not be operated as a result of a defect which was identified and included in a warranty claim in a proper and timely manner. The contractor shall, at its own expense, extend the term of the bank guarantee for execution of the work by a corresponding period; if it fails to do so, the purchaser may draw funds from the bank guarantee in part or in full with no prejudice towards its other rights under the contract fourteen (14) days prior to expiration of the existing bank guarantee for execution of the work. All amounts withdrawn from the bank guarantee in this manner shall be returned to the contractor without delay once the contractor submits to the purchaser a duly extended bank guarantee.

Replaced or newly-installed parts of the work shall be covered by a warranty period of twenty-four (24) months, beginning on the day of replacement / installation. Such warranty period shall be limited to a maximum of twelve (12) months from the date of final acceptance of the technological part of the work (if it relates to the technological part of the work) or twelve (12) months from the date of final acceptance of the building part of the work (if it relates to the building part of the work or rubberised components of the work), while the longer time limit shall be applied in the event of any doubts.

The acceptance of new deliveries made as part of defect removal and defect warranties relating to such deliveries shall be governed by the relevant contractor provisions governing the place and manner in which warranty claims may be made and fulfilled.

The removal of any defect shall not affect the purchaser’s right to be paid contractual penalties and reimbursed for damages.

The periods specified in Subsections 45.5 and 45.6 of the contract shall commence on the day the notice of defect is delivered to the contractor, where notices sent by e-mail shall be considered delivered on the day and hour that the e-mail in question was sent, while notices sent by registered post shall be considered delivered on the third business day from the date given on the post office stamp on the sender’s receipt.

None of the provisions of this Article 45 relieve the contractor of any of its other obligations under the contract or general legislation.

# REIMBURSEMENT FOR DAMAGES, LIMITATION OF LIABILITY

The purchaser may require the contractor to reimburse the purchaser, and the contractor shall then be required to pay, for any damages caused to the purchaser by the contractor and / or its subcontractors through a breach of their obligations under the contract or in relation to the performance of the contract, including cases of breach under the contract covered by contractual penalty provisions, and then even in amounts exceeding such contractual penalties, pursuant to Article 46, Subsection 46.2 of the contract. Reimbursement for damages (indemnity) shall be governed by the provisions of Section 2894 et seq. of the Civil Code.

Without regard for the provisions of Subsection 46.1 of the contract, the parties hereby declare (pursuant to Section 2898 (Contractual Limitations of Indemnity) of the Civil Code) that the contractor’s total liability for damages and other costs that may arise in relation to a breach of any one (1) or several contractual or legal obligations by the contractor in relation to the performance of the contract, shall not exceed one hundred per cent (100%) of the total contract price. The parties therefore declare the maximum obligation of the contractor to reimburse for damages and other costs, including the payment of contractual penalties, to be limited by the amount equivalent to one hundred per cent (100%) of the total contract price. The parties agree that reimbursement for indirect, and later damages, lost profit, loss of production, market losses, or damage to reputation is completely excluded and will not be applied.

Compensation for damages and contractual penalties are governed exclusively by the agreements contained in the contract, with the exception of Section 2898 of the Civil Code.

# REIMBURSEMENT FOR PATENT CLAIMS

Provided that the purchaser adheres to the provisions of Subsection 47.2 of the contract, the contractor shall reimburse the purchaser for any and all damages, claims of warranty or other claims, losses, and expenses that may arise to the purchaser as a result of any breach or claimed breach of any rights, trademarks, copyrights, or other intellectual property rights in relation to the equipment, works, and goods used in the work or in relation to the same, that may be registered or otherwise valid in the Czech Republic as of the signature date of the contract.

In the event any proceedings or claims are brought against the purchaser as a result of the matters listed in Subsection 47.1 of the contract, the purchaser shall notify the contractor, in writing, to that effect, and the contractor shall, at its own expense, but on behalf of the purchaser, participate in such proceedings and handle such claims and take steps to resolve such proceedings and claims. The purchaser shall, upon request, provide the contractor with all reasonable cooperation in handling such claims and proceedings. The contractor shall reimburse the purchaser for any and all demonstrable expenses related to such cooperation.

In the event that the contractor fails to notify the purchaser, within ten (10) days of receipt of notice per the preceding paragraph, that it has commenced participation in the relevant proceedings or handling of the relevant claims, the purchaser may enter such proceedings in its own name and require the contractor to reimburse all demonstrable and reasonable costs of the proceedings or incurred in relation thereto. In the event that the contractor does notify the purchaser, within ten (10) days of receipt of notice per the preceding paragraph, that it has commenced participation in the relevant proceedings or handling of the relevant claims, the purchaser may not subsequently make any statements that might prejudice the defence against such claims or proceedings.

The party entitled to claims under this Article 47 of the contract shall use all reasonable means to mitigate any losses or damage that might arise. In the event of failure to do so, the other party’s responsibility shall be proportionally reduced.

The contractor's obligations under this Article of the contract shall remain in effect vis-à-vis any potential future successors to ownership of the work, provided that such future successors honour the purchaser's obligations under Subsection 47.2 of the contract.

If the work or any part thereof is found to violate any of the above patents or otherwise registered intellectual property rights and operation of the work or any part thereof is prohibited by law, the contractor shall at its own expense and promptly:

- Replace or modify the part of the work or its component in violation of the patent in such a way that does not negatively impact the functionality of the work, and / or

- Acquire the right of use for the purchaser to enable it to use this part of the work, or component thereof.

# RISK ALLOCATION

# TRANSFER OF OWNERSHIP

The ownership rights for goods (including documentation) that are part of the work, unless already held by the purchaser, shall transfer from the contractor to the purchaser upon their delivery to the site at the purchaser’s premises; for services and works, upon their execution; for rights of use, upon their provision pursuant to the contract, or upon payment, whichever occurs earlier. Where the contractor works with or otherwise handles purchaser property, the contractor may only do so insofar as it is required to duly execute the work.

Ownership rights to contractor construction equipment used by the contractor and /or subcontractors in the execution of the work shall remain with the contractor or the relevant subcontractor.

Any ownership rights that have not been transferred in accordance with the above shall transfer from the contractor to the purchaser upon the signing of the provisional acceptance protocol for the work pursuant to Article 31 of the contract.

# DUE CARE OF THE WORK, TRANSFER OF LIABILITY FOR DAMAGE TO THE WORK

Regardless of transfer of ownership to the work or parts of the work pursuant to Subsection 48.1 of the contract, the risk of damage to the work, as well as the risks of loss, damage, or any other devaluation transfers from the contractor to the purchaser at the moment of signature of the protocol for provisional acceptance of the work by the contractor and the purchaser. This does not affect the contractor’s obligations with regard to warranty.

In the event of damage, loss, or any other devaluation of the work or any part thereof occurring before risks transfer to the purchaser, excepting cases specified in Subsection 52.5 of the contract, the contractor shall, at its own expense, remedy the loss, damage, or other devaluation and shall ensure the work and all parts thereof, including goods, are returned in all respects to a flawless condition compliant with the terms of the contract. Without regard for the above, if the damage, loss, or devaluation of the work or a part thereof is attributable to the purchaser, the purchaser shall reimburse the contractor for all demonstrable, reasonable expenses that may arise to the contractor in relation with the remedy of the damage in question; in the event that the damage affects other obligations under the contract, the parties shall proceed pursuant to Section 53 of the contract.

The contractor shall also be liable for all losses and damage to the work and the purchaser's or third parties’ property caused by the contractor or its subcontractors during the execution of works and services or in relation to the fulfilment of their obligations under the contract, including obligations pursuant to Article 45 of the contract.

# PROPERTY LOSS AND DAMAGE, PERSONNEL ACCIDENT AND INJURY, CLAIM SETTLEMENT

The contractor shall indemnify and hold harmless the purchaser and its employees for any claims, proceedings, sanctions, or activities ordered in administrative proceedings, as well as for all claims of warranty, damage, or other claims, losses, costs, and expenses of any kind, including costs of legal representation in matters of loss of life or limb or of loss or damage to any property, arising in relation to the execution of the work for reasons attributable to the contractor.

The purchaser shall indemnify and hold harmless the contractor and its employees for any claims, proceedings, sanctions, or activities ordered in administrative proceedings, as well as for all claims of warranty, damage, or other claims, losses, costs, and expenses of any kind, including costs of legal representation in matters of loss of life or limb or of loss or damage to any property, arising in relation to the execution of the work for reasons attributable to the purchaser.

In the event of any proceedings or claims, of warranty or otherwise, against the purchaser arising for reasons attributable to the contractor pursuant to Subsection 50.1 of the contract, the purchaser shall notify the contractor of the matter, in writing, and the contractor shall, at its own expense but in the purchaser’s name, take all steps and participate in all negotiations that may be required for the proceedings against the purchaser to be discontinued (if applicable), or, failing that, for the impact upon the purchaser to be minimized.

In the event of any proceedings or claims, of warranty or otherwise, against the contractor arising for reasons attributable to the purchaser pursuant to Subsection 50.2 of the contract, the contractor shall notify the purchaser of the matter, in writing, and the purchaser shall, at its own expense but in the contractor’s name, take all steps and participate in all negotiations that may be required for the proceedings against the contractor to be discontinued (if applicable), or, failing that, for the impact upon the contractor to be minimized.

If the contractor fails to notify the purchaser, within seven (7) days of receipt of notification as per the above, to the effect that the contractor shall proceed pursuant to Subsection 50.3 of the contract, then the purchaser may, at its own discretion, decide to enter such proceedings in its own name but at the contractor’s expense. In the event that the contractor does so notify the purchaser, within seven (7) days of receipt of notice per the above, the purchaser may not subsequently make any statements that might compromise the contractor’s position in such proceedings or claims procedures. Depending on the particular situation, the seven (7) day period may be shortened.

In the event that the purchaser fails to notify the contractor, within seven (7) days of receipt of notification as per the above, to the effect that the purchaser shall proceed pursuant to Subsection 50.4 of the contract, then the contractor may, at its own discretion, decide to enter such proceedings in its own name but at the purchaser’s expense. In the event that the purchaser does so notify the contractor, within seven (7) days of receipt of notice per the above, the contractor may not subsequently make any statements that might compromise the purchaser's position in such proceedings or claims procedures. Depending on the particular situation, the seven (7) day period may be shortened.

The purchaser shall, upon request, provide the contractor with all reasonable cooperation in proceedings under Subsection 50.3 of the contract. The contractor shall reimburse the purchaser for any and all demonstrable expenses related to such cooperation.

The contractor shall, upon request, provide the purchaser with all reasonable cooperation in proceedings under Subsection 50.4 of the contract. The purchaser shall reimburse the contractor for any and all demonstrable expenses related to such cooperation.

The entitled party under this Article 50 of the contract shall use all reasonable means to mitigate any losses or damage that might arise. In the event of failure to do so, the other party’s responsibility shall be proportionally reduced.

Before commencing any works, the parties are obliged to exchange information regarding risks. The contractor, through its authorized representative, shall submit a written or electronic risk assessment document to the purchaser’s work and environmental safety department, and from which it will receive the purchaser’s risk assessment document. This obligation applies equally to the contractor’s subcontractors.

The contractor shall notify the purchaser, without undue delay, of any injuries that may occur at the workplace. The contractor shall request the purchaser’s representative’s cooperation in investigating any workplace injuries that may occur in the execution of the work.

# INSURANCE

The contractor shall, at its own expense, enter into and maintain, or cause to be entered into and maintained, a construction and assembly insurance policy (CAR / EAR) in the scope specified below, throughout the construction and / or assembly of the work, up until the end of vacating of the entire site pursuant to Subsection 31.4 of the contract.

#### Insurance of contract subject

#### This insurance shall cover physical losses and damage to the work and all parts thereof, including defects in the design, arising before the purchaser’s provisional acceptance of the work. Between the date of signature of the provisional acceptance protocol and the date of signature of the final acceptance protocol in accordance with Subsection 33.3 of the contract, this insurance shall cover physical losses and damage to the work and all parts thereof arising from activities of the contractor and / or its subcontractors in a scope of coverage commensurate with the LEG 3 standard for construction and assembly insurance. Such insurance shall not cover physical losses or damage to site facilities, construction equipment and tools, or construction and other machinery owned by the contractor or its subcontractors.

#### Insurance of third-party liability, including cross-liability

#### This insurance shall cover all bodily injury, illness or death suffered by third parties (including the purchaser’s employees) and losses and damage to third-party property (including the purchaser’s property and any and all parts of the work already accepted by the purchaser) that may arise in relation to the execution of the work, and which are attributable to the contractor.

The coverage limit for purchaser, contractor, and subcontractor third-party liability insurance shall be no less than three hundred (300) million Czech koruna, with a deductible n of no more than ten (10) per cent. The coverage limit for the subject of the contract shall be equal to the contract price for the work. If contract price changes while the contract remains in effect, in a manner consistent with the contract, then the contractor shall change its coverage limit to match the new total contract price amount.

All above specified policies shall be entered into with an insurer acceptable to and approved by the purchaser, on terms acceptable to and approved by the purchaser; the purchaser shall not refuse such approval without reason. The contractor shall submit the terms of insurance, including contractual agreements, to the purchaser for approval at least twenty-one (21) days before the planned date of signature of the insurance policy. The purchaser shall comply with the terms of the insurance policy applicable to it and which it approved as specified herein, and in particular agreements related to safety and fire prevention measures.

Construction and assembly insurance shall be entered into with an insurer or insurers of good standing authorized to offer such policies under Act No. 277/2009 Coll., on Insurance and on amendment of certain other acts (the Insurance Act), as amended.

The purchaser and the contractor's subcontractors shall be listed as co-policyholders / co-beneficiaries in all insurance contracts entered into by the contractor pursuant to Article 51.1 of the contract.

The contractor shall, at its own expense, enter into and maintain a professional liability insurance policy throughout the construction and / or assembly of the work, up until the site has been fully disposed of pursuant to Subsection 31.4 of the contract. This policy shall cover all loss of life or limb of third parties (including purchaser employees) and losses and damage to property (including purchaser property, including any parts of the work already accepted by the purchaser), including net financial losses that may arise in relation to the execution of the work due to faults with the contractor’s design or with other professional activities of the contractor related to the execution of the work. The coverage limit of the contractor’s professional liability insurance shall not be less than fifty (50) million Czech koruna.

Before commencing relevant activities, the contractor shall submit to the purchaser documentation of its insurance – an insurance certificate (or attestation of insurance, or copy of insurance contract), to demonstrate that it has valid and effective insurance as required. All insurance policies shall provide that the purchaser be notified, no later than twenty-one (21) days in advance, of any impending cancellation or changes, by all involved insurers. In the event of the contractor’s failure to comply with the requirements of this Subsection 51.7 of the contract, the purchaser may, without limiting its other rights under the contract, enter into the insurance policies required by the contract, at the contractor’s expense.

Shipping Insurance

- This insurance shall cover losses and damage to goods that may arise during transport from the contractor, its subcontractors, or manufacturers (including warehousing for periods common in shipping insurance) to the site. Shipping insurance shall cover one hundred (100) per cent of the value of the goods being shipped as priced in the contract.

The contractor and its subcontractors are free to enter into any additional insurance related to the work, over and above the scope of the mandatory insurance required by this Article 51 of the contract; however, the price for such insurance is the contractor’s expense and may not be part of the contract price.

None of the provisions of the Article 51 of the contract relieve the contractor of its obligations and responsibilities under the contract.

# FORCE MAJEURE

The parties shall not be liable for any full or partial failure to meet their respective obligations under the contract in the event (and to the extent) that such failure is the result of an exceptional, unforeseeable, insurmountable event or circumstance arising independently of the will of the parties, as defined in Section 2913(2) of the Civil Code. Responsibility shall not, however, be excluded in the event that the circumstance arises only when the party in question is already delayed in meeting its obligations, or that the circumstance originated from its economic circumstances or operating options.

For the purposes of this provision, “force majeure” shall be defined to mean an exceptional, unpreventable event or circumstance that is outside the control of the party invoking force majeure provisions, that the party could not reasonably have foreseen when entering into the contract, and that prevents the party from fulfilling its obligations under the contract. Events and circumstances classifiable as force majeure shall include war, revolution, wildfire, flood, transport embargo, general strike, and industry-wide strike.

The party claiming force majeure shall notify the other party to that effect, including causes, without delay but no later than five (5) days from the day the notifying party became aware of the force majeure situation, via e-mail, with subsequent confirmation by registered post. The same procedure shall be used to notify the other party when the force majeure situation is no longer in effect. Upon request, the party claiming force majeure shall suitably document the claim to the other party.

Regardless of the other provisions of the contract, the contractor shall not be liable for loss or damage to the work or the purchaser’s property caused by war, unrest or operations of war, invasion, civil war, revolution, establishment of a military dictatorship, confiscation and nationalization, nuclear reaction, nuclear radiation or contamination and shock wave insofar as such events might impede the execution of the work in the Czech Republic, and which are outside of the contractor’s control and for which no insurance is available on the insurance market.

Unless agreed otherwise between the parties, the execution of obligations under the contract shall continue insofar and as long as that is reasonably possible, and the parties shall further seek alternative means to perform the contract free of force majeure influence. In the event that force majeure impacts the contract price, the timetable for executing the work, or other provisions of the contract, the parties shall commence negotiations to amend the contract price, the timetable for executing the work, or other provisions of the contract, pursuant to Article 53 of the contract.

# CHANGES TO THE WORK (CONTRACT)

# CHANGE PROCEEDINGS

Change requests

### The purchaser may propose and subsequently require the contractor to carry out any changes, provided the terms of this Article 53 of the contract are observed.

### The contractor may, during the performance of the contract, propose to the purchaser any change that the contractor may consider essential or beneficial to improving the quality and / or economic efficiency of the work. The purchaser may, at its discretion, either approve or refuse any such change proposed by the contractor.

### changes may also arise for other reasons specified in the contract, particularly those given in Article 3 of the contract – Legal Interpretation of the contract; Article 52 of the contract – Force Majeure; and Article 54 of the contract – Interruption of works.

### Without regard to the provisions of Subsections 53.1.1 and 53.1.2 of the contract, no changes or modifications to the work made essential through a failure of the contractor to meet its obligations or required to ensure work compliance with the contract, but not covered by the types of changes specified in Subsection 53.1.3 of the contract, shall be considered changes, and shall therefore not affect the contract price, the work timetable, nor any other contract provisions.

Purchaser-initiated changes

### In the event that the purchaser proposes a change under Subsection 53.1.1 of the contract, the purchaser shall send a change request to the contractor. The contractor shall then prepare and, without undue delay but, unless agreed otherwise, no later than within ten (10) days of change request receipt, submit to the purchaser a preliminary calculation of the costs of making the change and processing the change proposal. This preliminary calculation shall further contain the contractor’s proposed timetable for the completion of the change proposal and of the change itself, including preliminary estimates of the impact on the remainder of the work’s timetable pursuant to the contract. Once the purchaser has received the preliminary calculation and received any clarification or explanation it may require from the contractor, the purchaser shall either:

- Non-bindingly accept the contractor's preliminary calculation, upon which the parties shall proceed pursuant to Article 53.2.2 of the contract; or

- dispute the contractor’s preliminary calculation and request the contractor to reassess its proposal within the timeframe specified by the purchaser. If the contractor's revised calculation is acceptable to the purchaser, the parties shall then proceed pursuant to Subsection 53.2.2 of the contract; otherwise

- The purchaser shall notify the contractor of its intention to discontinue change proceedings.

### Upon receipt of the purchaser’s decision pursuant to Subsections 53.2.1 (a) or (b) of the contract, the contractor shall, within the period agreed, prepare the change proposal. The contractor shall also prepare a change proposal for changes proposed under Subsections 53.3.1 and 53.4.1 of the contract. The change proposal shall contain:

- Detailed description of change

- Impact of the change on contract timetable

- Impact of the change on other purchaser systems

- Impact of the change on the contract price for the work and / or terms of payment under the contract

- Impact of the change on the technical guarantees for the work

- Impact of the change on other provisions of the contract

- Calculation of costs of making the change

- Proposed method of purchaser's payment for change costs.

### Upon receipt of the change proposal, the purchaser and the contractor shall, without delay, reach an agreement on whether or not the proposed change is to be made. If the purchaser decides to carry through with the change, it shall issue a change order to the contractor within seven (7) days of its decision.

### In the event that the purchaser is unable to decide within seven (7) days, it shall notify the contractor to that effect, including information on when the contractor can expect a decision.

### In the event that the purchaser decides, for whatever reason, not to carry through with the Change, it shall notify the contractor to that effect. In that event, the contractor shall be entitled to be reimbursed for any demonstrable costs that may have arisen to it in the preparation of the change proposal, such reimbursement not to exceed the amount given by the contractor in its preliminary calculation for the change proposal pursuant to Subsection 53.2.1 of the contract.

### In the event that the purchaser and the contractor fail to reach consensus on a final price for the change, or on any other matters discussed in the change proposal, within the seven (7) day period specified above, then the purchaser may, regardless, order the contractor to make the change via a preliminary change order, which can contain any of or all changes to the execution of the work requested by the purchaser in relation to the change proceedings at hand. Upon receipt of the preliminary change order, the contractor shall, without delay and on a technologically reasonable timetable, perform all changes ordered in the preliminary change order. The parties shall then attempt to resolve any open issues that may remain in the change proposal.

### In the event that the parties fail to reach agreement within sixty (60) days of the issue of a preliminary change order pursuant to Subsection 53.2.5 of the contract, the matter may be further handled pursuant to Article 6 of the contract. Until such time as the parties either reach an agreement or an enforceable decision is made pursuant to Article 6 of the contract on the final price of the change, and / or on any other matters discussed in the change proposal, the preliminary change order shall be considered to constitute a full and accurate definition of the change.

contractor-initiated changes

### In the event that the contractor is proposing a change pursuant to Subsection 53.1.2 of the contract, it shall submit to the purchaser a written change proposal, including the rationale for the proposed change and the information required by Subsection 53.2.2 of the contract.

### Upon the purchaser’s receipt of the change proposal, the parties shall proceed as described in Subsection 53.2.3 of the contract. If, however, the purchaser decides not to accept the contractor's change proposal pursuant to this Subsection 53.3 of the contract, and therefore to not carry through with the change, the contractor shall have no right to claim reimbursement for costs related to the preparation of the change proposal.

General provisions for change

### changes arising from other changes, particularly from changes in general legislation, due to force majeure, and interruptions of the works, shall be carried out, within reason, pursuant to Subsection 53.2.1 et seq. of the contract.

### Without regard to any other provisions of the contract, all contractor claims of increase in the contract price, reimbursement of additional costs, change of timetable, or any other changes to the contract, whether resulting from contract provisions or from legislation, shall be made to the purchaser, in writing, no later than thirty (30) days from the moment that the contractor becomes aware, or should have become aware if exercising due professional care, of the existence of the particular reason for the increase in the contract price, additional costs, timetable changes, or other changes to the contract. In the event that the contractor fails to make its claim to the purchaser within the period given above, all such claims shall be considered null and void and unenforceable against the purchaser. If the contractor makes its claims within the period provided, the parties shall further proceed pursuant to Subsection 53.3 of the contract.

### changes to the concluded contract shall must comply with Section 222 of Act No. 134/2016 Coll., on Public Procurement, as amended, or with the exclusion implemented in the procurement documents under Section 100 PPA, or as stipulated in Subsection 10.9 of the contract.

# INTERRUPTION OF WORKS

The contractor shall, upon the purchaser’s written request, interrupt works for such a period of time (not exceeding six (6) months) and in such a manner as the purchaser may consider necessary; the contractor shall duly secure and protect the work during such works interruptions.

In the event that an interruption of works pursuant to this Article 54 of the contract affects the execution of the work on the timetable agreed in the contract, or affects other areas of the contract, further procedure shall be governed by Article 53 of the contract. In that event, both parties shall take reasonable measures to minimize any delay in completion of the work. The purchaser shall reimburse the contractor for any and all related demonstrable, reasonable costs that may arise to the latter in relation to interruption of the works, particularly costs of warehousing over two (2) months, conservation, refurbishment, capacity shifting, extension of bank guarantees, extending the stay of the contractor's personnel, insurance, etc. unless the interruption in progress on the work is caused by reasons attributable to the contractor.

The contractor may not remove any goods or parts of the work or construction equipment during such interruption without the prior written approval of the purchaser.

The provisions of Section 267(1) second sentence of the Civil Code do not apply.

# WITHDRAWAL FROM THE CONTRACT

DISCRETIONARY PURCHASER WITHDRAWAL FROM THE CONTRACT

### The purchaser may, at any time and at its own discretion, withdraw from the contract. Withdrawal under this Subsection 55.1.1 of the contract shall be effected via a written notice of withdrawal, which shall be effective upon receipt by the contractor, unless a later date is specified therein.

### Upon receipt of a notice of withdrawal pursuant to Subsection 55.1.1 of the contract, the contractor shall, either immediately or as of the date given in the notice:

#### Cease all further works, excepting any the purchaser may have specified in the Notice of Withdrawal for the sole purpose of protecting the already-completed portions of the work;

#### Terminate all contracts with subcontractors;

#### Within a mutually-agreed, technologically reasonable time frame, remove from the site all construction equipment and recall all contractor and subcontractor personnel, clear the site of all surplus materials, detritus, and waste of any kind, then return the site to the purchaser in a clean and safe condition;

#### Once payments pursuant to Subsection 55.1.3 of the contract have been made, then:

##### Hand over to the purchaser those parts of the work that have been completed before the withdrawal date;

##### Transfer to the purchaser all rights to completed parts of the work, particularly to any goods in place as of the date of withdrawal pursuant to Subsection 55.1.1 of the contract such as to which the contractor may be obligated under other provisions of the contract to transfer rights to the purchaser, and, upon the purchaser’s request, make all reasonable effort to transfer the contractor’s subcontracts relating to the work to the purchaser;

##### Submit to the purchaser all documentation created by the contractor and its subcontractors in relation to the work as of the effective date of the notice of withdrawal pursuant to Subsection 55.1.1 of the contract such as the contractor may be obligated under other provisions of the contract to submit to the purchaser within progress on the work.

### In the event of purchaser withdrawal from the contract under Subsection 55.1.1 of the contract, the purchaser shall pay to the contractor:

#### the portion of the contract price corresponding to duly completed parts of the work, including partially-complete parts, as of the effective date of withdrawal. Where the contract price clearly does not correspond to the partially-complete parts of the work, the purchaser shall provide reimbursement for reasonably incurred costs,

#### all demonstrable and reasonable expenses that the contractor may have incurred in the protection of the work pursuant to Subsection 55.1.2 (a) of the contract; and

#### all demonstrable and reasonable expenses that the contractor may have incurred from works pursuant to Subsection 55.1.2 of the contract.

WITHDRAWAL FROM THE CONTRACT DUE TO MATERIAL BREACH OF THE CONTRACT BY THE CONTRACTOR

### Without limiting or excluding any of its other rights under the contract, the purchaser may, via a written notice of withdrawal delivered to the contractor, withdraw from the contract for cause in the event of the following material breaches of contract by the contractor:

#### In the event that, during the performance of the contract, the contractor is liquidated, or that insolvency proceedings are brought against the contractor in relation to actual or impending contractor insolvency, or that the contractor otherwise becomes insolvent; or

#### In the event that the purchaser (within its rights under the contract) refuses to approve the contractor’s documentation for execution of the design prepared pursuant to Chapter 2.6 of Enclosure 3 of the contract, provided the three revisions (amendments) permitted to the contractor under the contract have already been refused; or

#### In the event that the contractor, in breach of Article 56 of the contract, assigns or transfers the contract or any part thereof, or any of its rights or obligations under the contract or interests in the contract, to another party; or

#### In the event that the total contractual penalties duly charged to the contractor reach any of the limits specified in Subsections 44.1.4, 44.2.75 or 44.4.5 of the contract, or that the completion of any of the part-payment milestones given in Enclosure 11 of the contract is delayed by more than ninety (90) days; or

#### In the event that, for reasons attributable to the contractor, the limit values of guaranteed parameters specified in Enclosure 2 of the contract for the guarantee measurements during test “A” and test “B” remain unachieved despite required changes and modifications having been made by the contractor pursuant to the contract; or

#### if the CONTRACTOR has its own overdue financial obligations to any of its subcontractors involved in completing the work, and which are more than 1 month past due and exceeding in total ten (10) per cent of the price of the contract concluded between the CONTRACTOR and every one of its subcontractors; or

#### In the event that, despite written notices from the purchaser to that effect, the contractor is not proceeding with the work in accordance with the contract, or is repeatedly neglecting its obligations under the contract; or

#### In the event that the contractor fails to submit to the purchaser bank guarantees on the terms specified in Article 16 of the contract; or

#### In the event that the contractor fails to secure insurance pursuant to Article 51 of the contract; or

#### In the event of any breaches of contract originally deemed immaterial, if such breaches are not remedied during an additional, reasonable period provided by the purchaser for that purpose; or

#### In the event that force majeure conditions pursuant to Article 52 of the contract persist longer than 180 days.

#### purchaser withdrawal from the contract under this Subsection 55.2.1 of the contract is effective on the day of delivery of the notice of withdrawal to the contractor, unless the notice specifies a later date.

### Upon receipt of a notice of withdrawal pursuant to Subsection 55.2.1 of the contract, the contractor shall, either immediately or as of the date given in the Notice:

#### Cease all further works, excepting any the purchaser may have specified in the notice of withdrawal for the sole purpose of protecting the already-completed portions of the work;

#### Terminate all subcontracts, or, if requested by the purchaser, assign to the purchaser or to a third party (a replacement contractor) all subcontracts relating to the execution of the work that the purchaser may consider essential to the completion of the work;

#### Within a mutually-agreed, technologically reasonable time frame, remove from the site all construction equipment and recall all contractor and subcontractor personnel, clear the site of all surplus materials, detritus, and waste of any kind, then return the site to the purchaser in a clean and safe condition;

#### Transfer to the purchaser all rights to completed parts of the work, particularly to any goods in place as of the date of withdrawal pursuant to Subsection 55.2.1 of the contract such as to which the contractor may be obligated under other provisions of the contract to transfer rights to the purchaser;

#### Submit to the purchaser all documentation created by the contractor and its subcontractors in relation to the work as of the effective date of the notice of withdrawal pursuant to Subsection 55.2.1 of the contract such as the contractor may be obligated under other provisions of the contract to submit to the purchaser for a work in progress.

### In the event of purchaser withdrawal under Subsection 55.2 of the contract, the purchaser may access the site and bar the contractor from further access. The purchaser may complete the works itself or via a third party. The purchaser may seize, and use, for payment to the contractor, any construction equipment that may remain at the site to complete the work, for such a period as the purchaser may consider essential to complete the work; for the avoidance of doubt, failure to reach agreement on related payments does not affect the purchaser’s right to use the construction equipment in this manner. Once the work has been completed, or earlier if the state of works permits, the purchaser shall return the construction equipment to the contractor, by means of notice to the contractor to the effect that the construction equipment in question is available for pick-up at the site. This subsection does not apply to withdrawal for the reason specified in Subsection 55.2.1 (k) of the contract.

### In the event of purchaser withdrawal from the contract under Subsection 55.2.1 of the contract, the purchaser shall pay to the contractor:

#### The portion of the contract price corresponding to duly completed parts of the work, including partially-complete parts in proportion to their degree of completion, as of the effective date of withdrawal from the contract;

#### Fair-value compensation for any unused or partially-used goods that may remain at the site in relation to the work; and

#### all demonstrable and reasonable expenses that the contractor may have incurred from works pursuant to Subsection 55.2.2 (a) of the contract.

#### Any and all contractor debts vis-à-vis the purchaser older than the withdrawal date shall be set off against contractor claims under this article. Once the contractor has duly completed its activities pursuant to Subsection 55.2.2 of the contract, and once all other claims the purchaser and the contractor may have on one another have been duly settled in accordance with the contract, the purchaser shall return to the contractor the bank guarantees provided by the contractor pursuant to the contract.

### In the event of purchaser completion of the work pursuant to Subsection 55.2.3 of the contract, the costs of such purchaser works shall be calculated. If the sum of the contractor’s claim under Subsection 55.2.4 of the contract and demonstrated, reasonable expenses of the purchaser on completing the work exceeds the contract price, the contractor shall be liable to cover the shortfall. If the shortfall exceeds the contractor’s claim under Subsection 55.2.4 of the contract, the contractor shall compensate the purchaser for the difference; if the shortfall is less than the contractor's claim under Subsection 55.2.4 of the contract, the purchaser shall compensate the contractor for the difference. The purchaser and the contractor shall negotiate, in writing, the manner of calculation of the above, as well as the terms and means of payment. This subsection does not apply to withdrawal for the reason specified in Subsection 55.2.1 (k) of the contract.

CONTRACTOR WITHDRAWAL FROM THE CONTRACT

### Without limiting or excluding any of its other rights or means of redress under the contract, the contractor may, via a written Notice of Withdrawal delivered to the purchaser, only withdraw from the contract for cause in the event of those material breaches of contract by the purchaser specified below. Notice of withdrawal pursuant to this Subsection 55.3.1 of the contract shall be effective upon delivery to the purchaser, unless a later date is given in the notice. The contractor may withdraw:

- In the event that, during the performance of the contract, the purchaser is liquidated, or insolvency proceedings are brought against the purchaser in relation to actual or impending purchaser insolvency, or that the purchaser otherwise becomes insolvent; or

- In the event that the purchaser fails to pay to the contractor any amount due under the contract within three (3) months of the due date, despite having been notified in writing of its delay in payment and no fewer than fourteen (14) additional days have passed since the purchaser's receipt of such contractor notice; or

- In the event that force majeure conditions pursuant to Article 52 of the contract are impeding the execution of the work, and that the situation persists for more than one hundred eighty (180) days.

The parties hereby expressly declare that the contractor may not withdraw from the contract for any reasons other than those explicitly stated in the contract. To clarify, the parties have agreed to exclude the contract from the application of Sections 2002 through 2005 of the Civil Code.

### In the event of contractor withdrawal under Subsection 55.3.1 of the contract, the contractor shall, either immediately or at the date given in the notice of withdrawal, proceed in accordance with Subsection 55.1.2 of the contract.

### In the event of contractor withdrawal under Subsection 55.3.1 of the contract, the contractor shall make all payments to the purchaser specified in Subsection 55.1.3 of the contract.

Any and all payments made by the purchaser to the contractor under the contract, including any advance payments, except any default interest for late payment of invoices on the part of the purchaser, may be set off against any and all amounts owed by the purchaser to the contractor under this Subsection 55 of the contract.

Termination of the contract by withdrawal does not terminate (i) any purchaser claims to payment of contractual fines, reimbursement of damages and other costs and expenses, and other contractor payments under the contract; (ii) any claims under warranty for the work or for hidden defects; (iii) the provisions of the contracton confidentiality, applicable law, and dispute resolution; or (iv) any other rights and obligations under the contract obviously intended to survive termination.

In the event of withdrawal from the contract under this Article 55 of the contract, the purchaser shall, once both parties’ claims under the contract have been settled, return to the contractor the contractor's bank guarantees submitted pursuant to the contract.

The provisions on termination of the contract contained in Enclosure 12 of the contract are not valid for this contract.

# CONCLUDING PROVISIONS

# ASSIGNMENT OF CONTRACT AND PROHIBITION OF RETENTION

## The parties have mutually excluded the ability of either of the parties without the prior written consent of the other party to assign the contract or any part thereof, or any rights or obligations hereunder or interests herein, to a third party. Likewise, the parties exclude the ability to offer any rights or obligations hereunder or interests herein to a third party as collateral without the prior written approval of the purchaser.

## The parties have agreed that the contractor shall not be entitled to retain, i.e., to exercise its right to retention of, any goods or future parts of the work under the contract, including any documentation.

# FINAL PROVISIONS

## This contract may only be amended by agreement of the parties, in the form of numbered, written amendments executed pursuant to Section 222 of Act No. 134/2016 PPA, duly signed by the authorized signatories of both parties, which shall then become an integral part of the contract. For an amendment to the contract to be valid, full consensus must be reached on its contents. Therefore, the parties exclude the applicability of the provisions of Section 1726 (Lack of Consensus) of the Civil Code, whereby an amendment could otherwise be executed without full consensus.

The contract shall become valid and take effect on the day of signature of the contract by both parties.

Unless incorporated into the contract, all agreements and understandings between the parties, oral and written, prior to the contract and related to the subject of the contract, shall terminate upon the signing of the contract.

The parties have agreed that the following shall survive the signing of the final acceptance protocol for the work and / or the termination of the contract: (i) any purchaser claims to payment of contractual fines, reimbursement of damages and other costs and expenses, and other contractor payments under the contract; (ii) any claims under warranty for the work or for hidden defects; (iii) the provisions of the contract on confidentiality, applicable law, and dispute resolution; and (iv) any other rights and obligations under the contract obviously intended to survive signature of the final acceptance protocol and / or termination of the contract.

In the event that any provision of the contract is found to be or to have become invalid, ineffective, and / or unenforceable, such a provision shall be considered separable from the remainder of the contract and, as such, shall not affect the validity, effectiveness, and / or enforceability of the contract as a whole. In such an event, the parties shall replace the invalid, ineffective, and / or unenforceable provision with an alternative provision that is in line with the purpose of the contract and the will of the parties as expressed in the contract.

The contractor hereby assumes the risk of change of circumstances in the sense of Section 1765(2) (Right to Resume Negotiations) of the Civil Code. Therefore, the provisions of Section 1765(1) (Right to Resume Negotiations) and Section 1766 (on Restoration of Balance of Rights and Obligations by a Court) of the Civil Code shall be excluded from applicability to the contract.

The contract is prepared in 4 identical counterparts in Czech, each of which has the same legal force as an original version. This contract is executed in four (4) identical counterparts in the Czech language, each of which shall have the legal force of an original. Upon signing, each party shall receive two (2) counterparts.

The contract shall be binding in full upon any potential legal successors to either party.

The contractor hereby acknowledges that the purchaser, in the performance of the contract, needs to process, in a certain necessary scope, the personal data of contractor personnel including its subcontractors involved in the performance of the contract. The rights of such contractor personnel in relation to the processing of their personal data by the purchaser are set forth in the Information Memorandum included in Enclosure 14 of the contract. The contractor shall make acquainted its personnel including its subcontractors with this document.

The parties declare to have familiarized themselves with the entirety of the contract, including all enclosures thereto and to have no doubts as to interpretation of the contract, and declare the contract to be an expression of their free will; in attestation of this, the parties adjoin their signatures.

In Most, Komořany, dated ..................

For the purchaser:	For the contractor:

| ............................................................ Ing. Milan Boháček Deputy Chairman of the Board of Directors United Energy, a.s. | ............................................................ ................ .................... |
| --- | --- |
| ............................................................ Ing. Petr Mareš Director United Energy, a.s. | ............................................................ ………………….. …............................... |