enclosure 11

Roadmap of Key Work Milestones and Prices

Enclosure 11 – Roadmap of Key Work Milestones and Pricesas described hereinafter shall be filled in / completed and submitted by the Contractor / Participant in Volume C11 of the Indicative tender / Tender (as an enclosure to the draft contract for work) in accordance with the instructions of the contracting entity for the preparation of Volume e C11 contained in Part 4 of the Tender Documentation.

Roadmap of Key Work Milestones and Prices

Table 1

| schedule of ADVANCE payments) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Payment title | Anticipated term for advance payment invoice issuance | PERCENTAGE CONTRACT PRICE PAYMENT without VAT |  |  | Performance conditions for payment |
|  |  | % | (in thousand CZK) | (in thousand EUR) |  |
| 1st advance (advance payment) | in accordance with clause 14.4(a) of the contract | 15 | ................. | ................. | in accordance with clause 14.4(a) of the contract. |

Table 2

| SCHEDULE OF PARTIAL PAYMENTS FOR CONTRACT PRICE |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Payment name | Expected date of issue of the invoice for partial supply | Amount of part payment of the contract price excl. VAT |  |  | Content of the milestone for the part payment |
|  |  | % | (in CZK 1000) | (in EUR 1000) |  |
| 1st part payment (based on the progress of the work) | in accordance with Enclosure 4 to the contract | 0.3 | ................. | ................. | MilESTONE I Handover of approved documentation for execution of the project – phase 1 (Basic Design) and confirmation of the fulfilment of the milestone by the purchaser in accordance with the contract. |
| 2nd part payment (based on the progress of the work) | in accordance with Enclosure 4 to the contract | 1 | ................. | ................. | MilESTONE II Handover of approved documentation for execution of the project – phase 2 (Detail Design) of the building part of the work (in the order of the last completed SO/IO) and confirmation of the fulfilment of the milestone by the purchaser in accordance with the contract. |
| 3rd part payment (based on the progress of the work) | in accordance with Enclosure 4 to the contract | 2 | ................. | ................. | MilESTONE III Handover of approved documentation for execution of the project – phase 2 (Detail Design) of the technological part of the work (in the order of the last completed PS/DPS) and confirmation of the fulfilment of the milestone by the purchaser in accordance with the contract. |
| 4th part payment (based on the progress of the work) | in accordance with Enclosure 4 to the contract |  | ................. | ................. | MilESTONE IV Ordering of the boiler, including the grate (DPS 01.03) by the contractor from the manufacturer/subcontractor with a complete specification of the delivery and confirmation of the fulfilment of the milestone by the purchaser in accordance with the contract. |
| 5th part payment (based on the progress of the work) | in accordance with Enclosure 4 to the contract |  | ................. | ................. | MilESTONE V Ordering of the flue gas treatment (DPS 01.04) by the contractor from the manufacturer / subcontractor with a complete specification of the delivery and confirmation of the fulfilment of the milestone by the purchaser in accordance with the contract. |
| 6th part payment (based on the progress of the work) | in accordance with Enclosure 4 to the contract |  | ................. | ................. | MilESTONE VI Ordering of the turbo-generator (PS 02) by the contractor from the manufacturer / subcontractor with a complete specification of the delivery and confirmation of the fulfilment of the milestone by the purchaser in accordance with the contract. |
| 7th part payment (based on the progress of the work) | in accordance with Enclosure 4 to the contract |  | ................. | ................. | MilESTONE VII Delivery of the boiler, including the grate (DPS 01.03) by the contractor to the site and confirmation of the fulfilment of the milestone by the purchaser in accordance with the contract. |
| 8th part payment (based on the progress of the work) | in accordance with Enclosure 4 to the contract |  | ................. | ................. | MilESTONE VIII Delivery of the flue gas treatment (DPS 01.04) by the contractor to the site and confirmation of the fulfilment of the milestone by the purchaser in accordance with the contract. |
| 9th part payment (based on the progress of the work) | in accordance with Enclosure 4 to the contract |  | ................. | ................. | MilESTONE IX Delivery of the turbo-generator (PS 02) by the contractor to the site and confirmation of the fulfilment of the milestone by the purchaser in accordance with the contract. |
| 10th part payment (based on the progress of the work) | in accordance with Enclosure 4 to the contract | 15% | ................. | ................. | MilESTONE X Signing of the certificate of the mechanical completion of the work in accordance with the contract and confirmation of the fulfilment of the milestone by the purchaser in accordance with the contract. |
| 11th part payment (based on the progress of the work) | in accordance with Enclosure 4 to the contract | 10% | ................. | ................. | MilESTONE XI Signing of the provisional acceptance of the work certificate in accordance with the contract and confirmation of the fulfilment of the milestone by the purchaser in accordance with the contract. |
| TOTAL, excl. VAT |  | 100% | ….............. | ….............. |  |