Environmental Improvements on TKY II Heating Plant - Wet Desulfurization

DRAFT CONTRACT FOR WORK

contents

A.	CONTRACT AND INTERPRETATION	4

1.	PARTIES TO THE CONTRACT	4

2.	TERMS AND DEFINITIONS	5

3.	LEGAL INTERPRETATION OF THE CONTRACT	8

4.	CONTRACT DOCUMENTS	8

5.	APPLICABLE LAW	9

6.	RESOLUTION OF DISPUTES	9

7.	NOTICES	10

B.	SUBJECT OF THE CONTRACT	12

8.	PURPOSE OF THE WORK	12

9.	SUBJECT OF THE CONTRACT – THE WORK	12

10.	WORK TIMETABLE	14

11.	CONTRACTOR’S OBLIGATIONS IN EXECUTION OF THE WORK	18

12.	PURCHASER’S COOPERATION	21

C.	PAYMENT	23

13.	CONTRACT PRICE	23

14.	TERMS OF PAYMENT	23

15.	TAXES, CUSTOMS, AND FEES	27

16.	BANK GUARANTEES FOR THE WORK AND FOR THE DEPOSIT	27

D.	INTELLECTUAL PROPERTY	30

17.	LICENSES AND RIGHTS OF USE TO TECHNICAL INFORMATION	30

18.	INFORMATION AND CONTRACT DOCUMENTS SECURITY	30

E.	EXECUTION OF THE WORK	32

19.	PARTIES‘ REPRESENTATIVES	32

20.	INFORMATION SUBMITTED TO PURCHASER	33

21.	SUBCONTRACTING	35

22.	STANDARDS AND LEGISLATION	36

23.	ENGINEERING WORK, DOCUMENTATION	37

24.	EXECUTION OF THE WORK	38

25.	DELIVERY AND DOCUMENTATION	39

26.	SHIPPING, PACKAGING INSTRUCTIONS	40

27.	WORK QUALITY ASSURANCE	40

28.	ASSEMBLY AND MECHANICAL COMPLETION	44

29.	COMMISSIONING	44

30.	WORK PROVISIONAL ACCEPTANCE	48

31.	TRIAL OPERATION	49

32.	GUARANTEE MEASUREMENT under test “B“, WORK FINAL ACCEPTANCE	51

33.	EMERGENCY WORKS	52

34.	PURCHASER OPERATIONS AND MAINTENANCE STAFF TRAINING	52

35.	REPLACEMENT PARTS AND RAPID-WEAR PARTS	52

36.	POST-WARRANTY SERVICING	53

37.	SITE AND ASSEMBLY SITES	53

38.	ADMINISTRATION RULES, OCCUPATIONAL HEALTH AND SAFETY	54

39.	WASTE MANAGEMENT, ENVIRONMENT PROTECTION	54

40.	WORK SECURITY	55

F.	GUARANTEES AND LIABILITIES	56

41.	GUARANTEED PARAMETERS	56

42.	CONTRACTUAL PENALTIES	56

43.	LIABILITY FOR DEFECTS, QUALITY GUARANTEE	65

44.	REIMBURSEMENT FOR DAMAGES, LIMITATION OF LIABILITY	68

45.	REIMBURSEMENT FOR PATENT CLAIMS	68

G.	RISK ALLOCATION	70

46.	TRANSFER OF OWNERSHIP	70

47.	DUE CARE OF THE WORK, TRANSFER OF LIABILITY FOR DAMAGE TO THE WORK	70

48.	PROPERTY LOSS AND DAMAGE, PERSONNEL ACCIDENT AND INJURY, CLAIM SETTLEMENT	70

49.	INSURANCE	72

50.	FORCE MAJEURE	73

H.	CHANGES TO THE WORK (CONTRACT)	75

51.	CHANGE PROCEEDINGS	75

52.	INTERRUPTION OF WORKS	77

53.	WITHDRAWAL FROM THE CONTRACT	77

I.	CONCLUDING PROVISIONS	82

54.	ASSIGNMENT OF CONTRACT AND PROHIBITION OF RETENTION	82

55.	ETHICAL CONDUCT BETWEEN THE PARTIES	82

56.	FINAL PROVISIONS	82

# CONTRACT AND INTERPRETATION

# PARTIES TO THE CONTRACT

| purchaser | United Energy, a.s. |
| --- | --- |
| Registered address | 2 Teplárenská St., 434 03 Most – Komořany, Czech Republic |
| a company registered in Section B, File 1722 of the Commercial Register of the Regional Court of Ústí nad Labem, Czech Republic |  |
| Authorized signatories | Ing. Milan BOHÁČEK, Deputy Chairman of the Board Ing. Petr MAREŠ, Director |
| Authorized representatives for: |  |
| - Contract negotiations | ................... |
| - Technical matters | ................... |
| Purchaser’s Representative: | .................. |
| Business Registration no. / VAT no. | 273 09 959 / CZ27309959 |
| Bank account: | Komerční banka a.s., Most branch, 15605491/0100 |

and

| contractor |  |
| --- | --- |
| Registered address |  |
| Registered in [Commercial Register details] |  |
| Authorized signatories |  |
| Authorized representatives for: |  |
| - Contract negotiations |  |
| - Technical matters |  |
| Contractor’s Representative: |  |
| Business Registration no. / VAT no. |  |
| Bank account: |  |

have concluded

pursuant to the outcome of the procurement process for the Public Contract “Environmental Improvements on TKY II Heating Plant - Wet Desulfurization“, announced in the Public Tenders Bulletin on 3. 10. 2018, Public Contract no. Z2018-033521, organized by the Purchaser pursuant to the provisions of Act No. 134/2016 on Public Procurement, as amended, and of the Public Tender Guidelines of the 2014 – 2020 Operational Programme Environment, the following Contract for Work, whereby the Contractor shall execute, at its own risk and expense and in a proper and timely manner, the Work, while the Purchaser shall, in a proper and timely manner, accept the completed Work and pay the Contract Price, on the terms specified below in this Contract. The purpose of the Contract is to ensure the Work specified herein is executed, and commissioned in a proper and timely manner, and that all other parameters and obligations agreed in the Contract are met.

Inspections shall be performed on the basis of an Inspection Agreement executed pursuant to Section 2562 et seq. of Act No. 89/2012; thereunder, the Inspector (i.e., the Contractor) shall impartially determine the actual state of the subject of the inspection, and shall provide an inspection certificate (inspection report) to that effect, while the Purchaser shall pay to the Inspector a fee that has been incorporated into the price of the Work.

# TERMS AND DEFINITIONS

For the purposes of this Contract, certain terms shall be defined as follows:

"day" 	shall be a calendar day from 12:00 midnight to 12:00 midnight; this includes all days of the year regardless of their position in a week or their possible status as a bank or other holiday observed in the Czech Republic or elsewhere

"work" shall be the set of Goods, Rights of Use, Works, and Services provided by the Contractor in accordance with the specifications and conditions given in this Contract and its Supplements; the Work is to be a complete, operational, safe, continuously operable, reliable system possessing the parameters and serving the purpose set forth in this Contract.

"contract documents" shall be the documents listed in Section 4 of the Contract.

"guarantee measurement“ shall be the testing performed as part of Tests “A” and “B”, whose purpose is to determine whether the Work as a whole or a specific part thereof is capable of achieving the guaranteed parameters listed in Supplement 2 to the Contract

"complex tests" shall be the tests performed in accordance with Section 29 of this Contract, whose purpose is to verify that the technical parameters specified for the Work in the Contract have been met.

"performance test" shall be a test performed in accordance with Section 29 of this Contract, whose purpose is to verify that the requirements on operational, safety, and reliability requirements specified for the Work in the Contract, as well as all other requirements specified in the Contract, have been met.

"final acceptance" shall be the Purchaser‘s final acceptance of the Work, which takes place as set forth in this Contract, once the relevant Warranty Period has expired. The Final Acceptance is executed by the Purchaser’s signing of the Final Acceptance Protocol (FAC), which shall be drafted in accordance with this Contract.

“month“ shall be a calendar month from 12:00 midnight of the first day of the calendar month to 12:00 midnight of the last day of the calendar month.

“wet lime scrubbing“ means the capture of acidic compounds from flue-gas (in particular SO2) by absorption into water or an aqueous solution using lime or lime hydrate.

"construction equipment" shall be the equipment, devices, and tools required for assembly, inspection, and other purposes and necessary to complete the Work, that however are not part of the Work itself and whose ownership shall not pass from the Contractor to the Purchaser.

"change form" shall be the form drafted pursuant to Subsection 51.2.2. of the Contract, which specifies Changes required by either party in accordance with Section 51 of the Contract, as well as the conditions for the implementation of such changes.

"purchaser" shall be the legal entity identified in Section 1 of the Contract, or its potential legal successors. Procedurally, the Purchaser shall be represented by a natural person (the Purchaser’s Representative) of the Purchaser’s own appointment.

"trial operation“ shall be a period of twelve (12) months (unless agreed otherwise) during which the Work shall operate under the full responsibility of the Purchaser and during which the Contractor shall be present, as specified in this Contract, and which begins upon the signing of the Preliminary Acceptance Protocol and ends upon the signing of the Trial Operation Protocol.

"quality plan" shall be the quality document, drafted in accordance with this Contract, which defines the concrete procedures and sequence of activities related to ensuring the quality of the Work.

"works" shall be the activities of the Contractor that are essential to the completion of the Work and that include assembly, installation, design work, and other similar activities of the Contractor within the scope of this Contract.

"documentation for execution of the project“ or the "design“ shall be the documentation so defined in Act No. 183/2006 on Land Use Planning and Construction Procedures (the Construction Act), as amended, and Czech Government Decree No. 499/2006 (on Construction Documentation), as amended, this documentation to be prepared in sufficient depth of detail to allow successful completion of the Work.

"provisional acceptance" shall be the Purchaser‘s acceptance of the Work once Commissioning and the Performance Test have concluded successfully as required by the Contract. Provisional Acceptance is executed by the Purchaser’s signing of the preliminary Acceptance Protocol (PAC) drafted in accordance with Section 30 of the Contract.

"preliminary change order" shall be an order from the Purchaser to the Contractor issued pursuant to Subsection 51.2.5 of this Contract.

”services” shall be the activities required to complete the Work, including engineering work (supervision, Commissioning, etc.), technical assistance to the Purchaser, training of Purchaser’s Representatives, importation of Goods, and similar obligations of the Contractor under this Contract.

"contract for work" or the "contract" shall be the present Contract, concluded pursuant to Section 2586 et seq. of Act No. 89/2012 – the Civil Code, as amended. The Contract consists of the Contract Documents listed in Section 4 of the Contract; unless expressly agreed otherwise, the rights and obligations of the Parties to the Contract are determined pursuant to Section 2586 et seq. of the Czech Civil Code.

"contract price" shall be the sum of money agreed by the Parties in this Contract.

"site" shall be the site specified in Supplement 1 to the Contract, where the Contractor shall undertake the Work (mainly including the delivery, installation, Commissioning, and testing of the Work). The Site shall include assembly sites as set forth in the Design.

"subcontractor" shall be any entity directly or indirectly contracted by the Contractor to supply Goods or execute any part of the Work on the Contractor‘s behalf, as specified in Section 21 of the Contract.

"test ‘A‘" shall be tests and inspections performed in order to determine whether the Work as a whole or a specific part thereof meet the technical parameters agreed for Test A in the Contract, particularly in Subsection 10.8.2 of Supplement 1 to the Contract.

"test ‘B‘" shall be the process used to verify whether the Work fulfills the guaranteed parameters agreed in Supplement 2 to the Contract, pursuant to Section 32 of the Contract.

"mechanical completion" shall be a state wherein the Work has been completed in accordance with the Design, all assembly has been finished (to the point where Commissioning may begin), the physical structure is solid and clean in terms of assembly and statics, and where all required “cold” testing as specified in Section 28 of the Contract has been completed successfully.

"commissioning" shall be the commencement of operation of the Work once Mechanical Completion has been achieved and all tests required by Section 29 of the Contract have been performed. The Commissioning phase culminates in a successful Performance Test.

"rights of use" shall be all intangible property rights required for the Purchaser to be able to use the Work as agreed in the Contract.

"goods" 	shall be all non-real estate property such as equipment, devices, materials, physical products, items, and things of all manner that are to be procured, delivered, installed, and tested by the Contractor under this Contract, with Construction Equipment being excluded from the definition of Goods. Replacement parts supplied under this Contract are also considered Goods.

"warranty period" shall be the period during which the Contractor is liable for the faultless completion and operation of the Work, as specified in the relevant provisions of this Contract. The Warranty Period begins upon the signing of the Preliminary Acceptance Protocol (PAC) and ends upon the signing of the Final Acceptance Protocol (FAC).

”site facilities” shall be all temporary structures and fittings that serve the professional and social needs of persons participating in the Work. Site Facilities also include structures and fittings owned by the Purchaser or third parties that are placed at the Contractor’s disposal for the duration of the Work.

"purchaser’s representative" shall be the natural person identified in Subsection 7-d of the Contract, or any other person appointed such by the Purchaser, who is empowered to execute certain rights or obligations that may be delegated to them within the scope of the Purchaser’s authorization. The Purchaser or its Representative shall demonstrate the scope of such authorization to the Contractor by presenting the Purchaser’s Power of Attorney to that effect.

"contractor’s representative" shall be the natural person identified in Subsection 7-e of the Contract, or any other person appointed such by the Contractor, who is empowered to execute certain rights or obligations that may be delegated to them within the scope of the Contractor‘s authorization. The Contractor or its Representative shall demonstrate the scope of such authorization to the Purchaser by presenting the Contractor’s Power of Attorney to that effect.

"contractor" shall be the legal entity identified in Section 1 of the Contract, or its potential legal successors. Procedurally, the Contractor shall be represented by a natural person (the Contractor’s Representative) of the Contractor’s own appointment.

"change“ shall be any change or modification to the Work and / or this Contract; Changes shall be managed and executed pursuant to the provisions of Section 51 of the Contract.

"change order“ shall be an order to make a Change given by the Purchaser on the basis of a duly approved Change Form pursuant to the provisions of Section 51 of the Contract.

Wherever the Contract requires that a statement, approval, consent, confirmation, or appointment of any kind be made or issued, such a statement, approval, consent, confirmation, or appointment shall, unless agreed otherwise, be made in writing, and all references to “statement”, “approval”, “consent”, “confirmation”, and “appointment” shall be interpreted to mean written expression. No such action shall, in and of itself, create or constitute an amendment to this Contract. No such statement, approval, consent, confirmation, or appointment shall be withheld or delayed without reason.

No failure of the Purchaser to exercise one or more of its rights under this Agreement shall constitute, nor shall be construed to constitute, the Purchaser‘s surrender of such rights and /or the Purchaser’s consent in any matter.

# LEGAL INTERPRETATION OF THE CONTRACT

This Contract is executed pursuant to Section 2586 et seq. of Act No. 89/2012 – the Civil Code, as amended (hereinafter, the “Civil Code”). Unless expressly agreed otherwise, the rights and obligations of the Parties hereto shall be determined in accordance with the provisions of Section 2586 et seq. of the Civil Code; this shall apply, in reasonable proportion, even if part of the rights and obligations agreed herein do not satisfy the definition of “Work” employed by the Civil Code.

The Contract has been drafted on the basis of the laws and other general legislation applicable to the Work in the Czech Republic, as these are in effect on the day of signing of the Contract.

Should any law or other item of general legislation relevant to the execution of the Contract change while the Contract is being executed, the Contractor shall be required to notify the Purchaser of such changes in writing and without delay, and, if subsequently requested by the Purchaser to do so, to change the nature and / or manner of execution of the Work as required by such changes and in accordance with Section 51 of the Contract.

The Parties hereby declare that the Contract is the product of negotiations between them. In view of this, the Parties further declare that, for the purposes of legal interpretation of the Contract, neither Party considers itself the author of the Contract‘s text, and that therefore, phrasing admitting multiple interpretations should not be interpreted so as to favor or disfavor, or as favoring or disfavoring, either Party.

# CONTRACT DOCUMENTS

This Contract consists of the entirety of the Contract Documents listed below, all of which are an integral part of the Contract and are binding upon the Contractor in its execution of the Work.

|  | The present Contract, consisting of 56 Sections |  |
| --- | --- | --- |
|  | Supplement 1 | Purchaser’s Technical Requirements on the Work |
|  | Supplement 2 | Guaranteed Parameters |
|  | Supplement 3 | Documentation |
|  | Supplement 4 | Timetable and Execution Plan for the Work |
|  | Supplement 5 | Purchaser’s Cooperation |
|  | Supplement 6 | Training |
|  | Supplement 7 | List of Subcontractors |
|  | Supplement 8 | Bank Guarantees for the Work and for the Deposit |
|  | Supplement 9 | Price Specification |
|  | Supplement 10 | Roadmap of Key Work Milestones and Prices |
|  | Supplement 11 | Contractors' Code of Conduct |
|  | Supplement 12 | Contractor’s Technical Specifications |
|  | Supplement 13 | Information on Processing of Personal Data obtained from Data Subject and from other Sources |

The various Contract Documents listed above complement and elaborate upon each other. When interpreting the Contract, the entirety of the Contract Documents should be considered as an integral whole. In the event of ambiguity or conflict, the provisions of the present Contract proper take precedence over the contents of the Supplements listed above. In the event of doubt regarding the interpretation of Supplements, the contents of lower-numbered Supplements take precedence over the contents of higher-numbered Supplements.

# APPLICABLE LAW

The law applicable to the Contract shall be exclusively the law of the Czech Republic, as it is in effect at any given time.

# RESOLUTION OF DISPUTES

Should any dispute or difference of opinion arise from or in relation to the Contract between the Purchaser and the Contractor, including any and all issues of validity, termination, or execution, whether during the execution of the Work or after its completion, the Parties to the Contract shall strive to resolve the dispute or difference of opinion via negotiation in good faith.

  - Should the Parties fail to reach resolution by negotiation within thirty (30) days from start of negotiations pursuant to Section 6.1 of the Contract, each Party may officially notify the other Party, in writing, of the existence of a dispute (including its nature and basic points of dispute).

All disputes arising from or in relation to the Contract where negotiation fails shall be decided with final authority by the Court of Arbitration of the Czech Chamber of Commerce and Agricultural Chamber of the Czech Republic, in accordance with that Court’s rules of proceedings, by third-party arbitrators, one each selected by each Party. The third arbitrator and chairman of the Arbitration Board shall be selected by joint appointment by the Parties’ arbitrators. The Court of Arbitration shall decide based on the preferences of the Parties as these are expressed in the Contract, on the evidence presented, and on the law of the Czech Republic.

Both Parties shall have the right to bring a claim before the Court of Arbitration. If either Party brings a claim before the Court, the Party’s deposition is required, in particular, to precisely specify the decision sought, enumerate its claims, and precisely specify the provisions of general legislation and / or the Contract being used to support the claim.

Decisions of the Court of Arbitration are final and may not be appealed or suggested for revision or inspection, except where this is allowed by the Court’s rules of proceedings. Both Parties shall be required to comply with their obligations arising from such decisions within the time period given in the same.

Proceedings of the Court of Arbitration of the Czech Chamber of Commerce and Agricultural Chamber of the Czech Republic shall be held in Prague, Czech Republic, in the Czech language.

While arbitration proceedings are underway, both Parties shall continue to carry out their obligations as specified in the Timetable and Execution Plan for the Work until such time as the Court returns a decision. Should the Contractor cease carrying out its obligations despite the preceding, the Purchaser shall  be entitled to assuage its claims by drawing down against the bank guarantee provided in relation to the Work, without this affecting the Purchaser’s other rights.

# NOTICES

Unless specified otherwise in this Contract, any claims, notifications, communication, etc. pursuant to the Contract shall be made in writing and delivered in person, by registered mail, or by courier, to the relevant Party’s address as given below in this Section. Unless the Contract provides otherwise, the following shall apply:

#### Notices sent via e-mail containing digitized or scanned text to also be hand-delivered, mailed, or delivered by courier no later than three (3) Days after the e-mail in question has been sent, shall be considered delivered on the Day the e-mail is sent.

#### Notices sent by registered mail or courier shall be considered sent, for registered mail, on the date of the receipt provided by the post office of posting (or on the Day the shipment was accepted by a courier, as documented by the courier’s receipt), and shall be considered delivered on the third (3rd) Day after the date marked on the post office’s receipt (date shipment was accepted by courier from sender).

#### Written notices delivered in person shall be considered delivered on the Day they are handed over the counterparty, or on the Day the counterparty refuses to take delivery.

#### Any and all notices, communications, reports, etc. intended for the Purchaser under this Contract shall be sent to the Purchaser’s Representative at:

United Energy, a.s.

……………………..

…………………..

2 Teplárenská St.

434 03 Most – Komořany, Czech Republic

landline: +420  ……………….

mobile: +420  ………………..

e-mail: ............................

against potential unavailability, copy to be sent to:

United Energy, a.s.

………………………

…………………..

2 Teplárenská St.

434 03 Most – Komořany, Czech Republic

landline: +420  ………………..

mobile: +420  ………………..

e-mail: ......................

#### Any and all notices, communications, reports, etc. intended for the Contractor under this Contract shall be sent to the Contractor’s Representative at:

Company name

........................

Company address

landline: .......................

mobile: ………………

e-mail: ...................

against potential unavailability, copy to be sent to:

Company name

........................

Company address

landline: .......................

mobile: ………………

e-mail: ...................

Each Party shall notify, in writing and without delay, the other Party of any changes that may occur in the address where notifications are to be sent, in the names of their representatives, or in the relevant telephone numbers and e-mail addresses.

# SUBJECT OF THE CONTRACT

# PURPOSE OF THE WORK

The purpose of the Work is the construction of a desulphurization system using wet lime scrubbing for boilers K6 through K10, such a system to ensure new emissions standards are met as required by this Contract and by Act No. 201/2012 on Air Quality Protection and the related Directive no. 415/2012 of the Czech Ministry of the Environment, which specify the pollutant emission limits and other conditions for the operation of stationary pollution sources.

# SUBJECT OF THE CONTRACT – THE WORK

By signing this Contract, the Contractor agrees to perform for the Purchaser the Work, consisting of the realization of the project “Environmental Improvements on TKY II Heating Plant - Wet Desulfurization“, which is required to be a “turnkey” project and to meet all requirements, conditions, specifications, and other information given in the Contract.

The Work shall include, and “turnkey” should be taken to mean, in particular the following:

#### Assessment and evaluation of existing, and potentially the execution of additional, surveys, documentation, information, and data required to perform the Work.

#### Creation and submission of the Documentation for Execution of the Project such as may be required for the due completion of the Work in the scope and under the terms specified in the Contract.

#### Creation and submission of all other documentation required by Supplement 3 to the Contract.

#### Construction of Site Facilities such as may be required to complete the Work as specified in the Contract and to operate the Site throughout the Work, including disposal (particularly, with regard to environmental protection, fire safety, and occupational health and safety as required by applicable legislation).

#### Provision, i.e., supply and assembly, of the required publicity tools (project / construction information) pursuant to the Rules for Applicants and Beneficiaries and the Required Publicity Graphics Manual published at http://www.opzp.cz/obecne-pokyny/pravidla-publicity.

#### Arrangement of Site management and transport to and from the Site, including offloading, toll duty, taxation, insurance, security, and warehousing of all Goods, materials, components, etc. required to complete the Work.

#### Demolition / disassembly of existing equipment that is to be replaced by newly installed equipment during the Work, or that becomes redundant through the completion of the Work.

#### Execution of the construction associated with the Work in the scope and under the terms agreed in the Contract.

#### Provision and assembly of the technology associated with the Work, including machinery and related systems, monitoring and control systems, and electrical technology in the scope and on the terms specified in the Contract.

#### Connection of the Work to existing structures and systems at the connection points defined in Supplement 1 to the Contract.

#### Supply of replacement parts in the scope and on the terms agreed in the Contract.

#### Supply of any and all special tools and devices required to maintain the Work once completed in the scope and on the terms agreed in the Contract.

#### Overall coordination of all deliveries of Goods, Works, and Services within the scope of the Work.

#### Management, monitoring, execution, inspection, and documentation of the preparation and realization phases of the Work, including updates and the provision of required organizational and planning documentation in the scope and on the terms agreed in the Contract.

#### Maintenance of a Construction Log, execution and / or provision of adequate conditions for the execution of expert oversight pursuant to Czech Ordnance no. 499/2006 on Construction Documentation, as amended (the Construction Log to comply with the requirements given in Czech Ordnance no. 499/2006 on Construction documentation, as amended).

#### Achievement and documentation of quality characteristics required by the Contract and pursuant to the Quality Plan, including all applicable inspections and tests in the scope and on the terms agreed in the Contract.

#### Achievement and submission of all certificates of quality, materials, material testing, assembly progress, completeness, performed inspections, necessary revision reports, protocols, approvals, attestations, consents, and certificates required to execute, operate / use, and gain official approval for the Work in the scope and on the terms required by the Contract.

#### Note: Certification of stabilizate, energo gypsum and fly ash of fabric filter is the responsibility of the Purchaser, the Contractor shall provide effective co-operation.

#### Provision of Rights of Use required for use of the Work, including relevant documentation, in the scope and on the terms agreed in the Contract.

#### Removal of all waste materials arising from the realization of the Work, on the terms required by the Contract.

#### Training of the Purchaser’s operations and maintenance staff, in the scope and on the terms agreed in the Contract.

#### Participation of the Contractor’s responsible staff in the discussion and approval of the documentation prepared pursuant to Supplement 3 to the Contract, during Guarantee Measurement, Commissioning, and the official approval for use process, on the terms required by the Contract.

#### Commissioning of the Work, including all relevant tests and inspections and the completion of the Work on the terms required by the Contract.

#### Provision of adequate conditions for the execution of the Guarantee Measurement by an independent entity, and participation in such tests, including the provision and submission of required documentation.

#### Provision of guarantees for the quality of the Work in the extent specified in the Contract and the removal, free of charge, of any defects that may arise during the Warranty Period, under the conditions specified in the Contract.

#### Cooperation with and support of the Purchaser in coordinating the Work with related projects executed by other providers.

#### Cooperation with the Occupational Health and Safety Coordinator and compliance with the suggestions, recommendations, and directives of the same.

The Contractor shall perform, within the scope of the Work, all Works and Services and deliver all Goods, including those not explicitly listed in the Contract but that may, logically and in view of the Contract, be reliably deduced to be necessary for the correct functioning and completion of the Work, this on the same terms as if such Works, Services, and Goods were listed in the Contract.

The subject of the Work consists of the delivery of Goods, Works, Services, and Rights of Use, and is further specified in detail in the Contract Documents listed in Section 4 of the Contract.

# WORK TIMETABLE

The Contractor shall execute the Work pursuant to the Contract, and shall abide by the detailed timetable given below, and shall deliver the duly completed Work to the Purchaser on the timetable specified below:

- Work execution timetable:

| - Acceptance of Site for construction and IS marking (once demolitions finish) | Fifty-one (51) Days after effective date of Contract |
| --- | --- |
| - Construction and IS marking. | No later than fifty-seven (57) Days after effective date of Contract |
| - Site turned over to Contractor | Fifty-seven (57) Days after effective date of Contract |
| - Mechanical Completion of Work as defined in Contract | No later than five hundred eighty-one (581) Days after effective date of Contract |
| - Training of Purchaser personnel on Work operation and maintenance | On timetable given in Supplement 6 to Contract |
| - Preparation for Complex Tests of Work as defined in Contract | Thirty-four (34) Days after Mechanical Completion of Work |
| - Complex Tests of Work pursuant to Contract (including execution and evaluation of Guarantee Measurement pursuant to Contract) | Eighty-three (83) Days after end of preparations for Work Complex Tests |
| - Performance Test of Work pursuant to Contract | Spanning four hundred fifty-six (456) hours, once Complex Tests are completed |
| - Submission of material certificates to Purchaser pursuant to Contract (Section 5.3.1 of Supplement 1 to Contract) | No later than 5 days before PAC |
| - Provisional Acceptance of Work (PAC) pursuant to Contract | No later than seven hundred twenty-one (721) Days after effective date of Contract |
| - End of Work Trial Operation | Twelve (12) months after Work Provisional Acceptance date |
| - Final Acceptance of Work pursuant to Contract | In phases as Warranty Periods on various portions of Work run out, pursuant to Section 43.1.1 of the Contract and other Contract conditions |

- Timetable for submission of documentation related to execution of Work:

| Section1) |  | Document | Submitted to Purchaser |
| --- | --- | --- | --- |
|  | 2.1 | Administration Rules | no later than thirty (30) Days after date of Contract signing |
|  | 2.2 | Documentation Plan (PLTD) | no later than twenty-five (25) Days after date of Contract signing |
|  | 2.3 | Quality documentation: |  |
|  |  | - Quality Plan (for Work as a whole) | no later than twenty-five (25) Days after date of Contract signing |
|  |  | - Inspection and Testing Plan, by project phase and by individual SO/IO/PS/DPS, for: |  |
|  |  | - Design work (structural design) | no later than eleven (11) Days after date of Contract signing |
|  |  | - Own manufacturing | no later than seventy (70) Days after date of Contract signing |
|  |  | - Construction and assembly | no later than twenty-five (25) Days after date of Contract signing |
|  |  | - Commissioning | no later than fifty-six (56) Days before date of Mechanical Completion |
|  |  | - Trial Operation | no later than fifty-six (56) Days before date of Mechanical Completion |
|  |  | - Testing plans: |  |
|  |  | - for FAT | no later than 56 Days after Documentation for Execution of the Project (Design) for Work technological section, as discussed with and approved by Purchaser, has been submitted |
|  |  | - for Commissioning | no later than fifty-six (56) Days before date of Mechanical Completion |
|  |  | - Inspection and Test Book | updated regularly as tests and inspections proceed; complete Inspection and Test Book to be continuously submitted to Purchaser for review and subsequently handed over before PAC signing |
|  | 2.4 | Documentation for Execution of the Project (Design) |  |
|  |  | - Structural section (SO, IO) | no later than eighty-one (81) Days after date of Contract signing |
|  |  | - Technological section (PS, DPS) | no later than one hundred sixty-five (165) Days after date of Contract signing |
|  | 2.5 | Documentation for requests to modify construction in progress: | No later than 56 Days after Documentation for Execution of the Project (Design) for Work technological section, as discussed with and approved by Purchaser, has been submitted. Any changes arising from design changes during execution – no later than thirty (30) days after Purchaser approval of design change. |
|  | 2.6 | Accompanying technical documentation | no later than two (2) Days after Mechanical Completion, the welding documentation to be continuously handed over to the Purchaser for review. |
|  | 2.7 | Project for Commissioning | no later than two (2) Days after Mechanical Completion |
|  | 2.8 | Project for Guarantee Measurement validating guaranteed parameters: |  |
|  |  | - Proposed methods | no later than two hundred seventy-nine (279) Days after date of Contract signing |
|  |  | - Guarantee Measurement project | no later than three hundred sixty-three (363) Days after date of Contract signing |
|  | 2.9 | Operations Rules |  |
|  |  | - Preliminary | no later than two (2) Days after Mechanical Completion |
|  |  | - Final | no later than upon PAC signing |
|  | 2.10 | Maintenance guidelines | no later than upon PAC signing |
|  | 2.11 | Documents required for official trial operation approval | no later than on the day of Complex Tests of Work |
|  | 2.11 | Documents required for official approval of finished project | no later than ninety (90) Days after PAC. |
|  | 2.12 | Documentation for personnel training | on timetable given in Supplement 6 to Contract |
|  | 2.13 | Documentation of Work actual state as built | Four (4) complete sets with changes marked, no later than on the day of Complex Tests of Work. Ten (10) complete sets of final version, no later than 30 Days after end of Trial Operation. |

Notes: 1) The Sections indicated are sections of Supplement 3 to the Contract.

All deadlines for documentation submission given above apply to documentation approved by the Purchaser.

The Contractor shall fulfill its obligations on the timetable given in Section 10.1 of the Contract, in the Timetable and Execution Plan for the Work (Supplement 4 to the Contract), and in the Detailed Timetable and Execution Plan for the Work prepared and approved pursuant to Section 24.2 of the Contract.

Documentation submitted pursuant to Supplement 3 to the Contract shall be considered duly submitted upon its formal, documented acceptance and approval by the Purchaser.

Delivery of Goods required for the Work shall be considered duly made upon delivery of such Goods to the Site in a state deemed satisfactory and acceptable, and the formal, documented acceptance of such delivery by the Purchaser.

Works and Services rendered on the Site shall be considered duly rendered upon their correct performance at the Site and formal, documented acceptance by the Purchaser.

Purchaser personnel training shall be considered duly provided upon its provision by the Contractor pursuant to the Contract, as documented by a training protocol with trainee attendance rolls attached.

Early execution of any of the Contractor’s obligations under the Contract shall only be allowed with the written consent of the Purchaser received prior to such execution.

# CONTRACTOR’S OBLIGATIONS IN EXECUTION OF THE WORK

The Contractor shall execute the Work in its own name, at its own risk and on its own responsibility, and in accordance with the Contract.

The Contractor shall execute the Work via its own employees or via the employees of its Subcontractors. All Contractor and Subcontractor employees performing certain selected construction activities specified in Section 158 of Act No. 183/2006 on Land Use Planning and Construction Procedures (the Construction Act), as amended (including e.g. design work, construction management, technical oversight, calculations in statics, surveying, etc.) are required by the above named Act and relevant special legislation to possess authorization to perform such activities valid throughout the period required to execute the Work. The Contractor shall follow the instructions of the Purchaser’s technical supervisors and the Occupational Health and Safety Coordinator.

The Contractor shall act as an independent Contractor executing a Contract. Pursuant to the Contract, the responsibility for the manner of realization of the Work rests solely and fully with the Contractor. All personnel, representatives, and Subcontractors contracted by the Contractor to execute the Contract are fully answerable to the Contractor, and shall not be considered employees of the Purchaser; nothing in this Contract or any agreements the Contractor may execute in relation thereto may be interpreted to create a direct contractual relationship between such personnel, representatives, or Subcontractors on the one side and the Purchaser on the other.

The Contractor and its Subcontractors shall exercise all due professional care in the execution of the Work, and shall not jeopardize the safety and reliability of the operation of any other systems belonging to the Purchaser. The Contractor shall deliver and execute all Goods, Works, Rights of Use, and Services relating to this Contract in the scope and at the level of quality required by the Contract, and so as to achieve a complete and continuously, safely, and reliably operable Work fulfilling the parameters required and compliant with the terms of the Contract. The Contractor hereby warrants and represents that the Work shall be functional and shall have no negative impact on the use value and useful life of existing structures and systems and modified portions of existing technology.

The Contractor shall comply with all general legislation, current CSN standards, and harmonized CSN EN and CSN EN ISO standards relevant to the Work, as well as the Purchaser’s internal guidelines, pursuant to Section 22 of the Contract.

The Contractor hereby declares that it entered into the Contract on the basis of certain data and information relating to the Work provided by the Purchaser, and of information that it gained by inspecting the Site, and of other Work-related information available to it, and attests that it holds this information sufficient to execute the Work in accordance with the Contract, and acknowledges that any failure on its part to familiarize itself with all such information and data does not absolve the Contractor of its responsibility to properly estimate the difficulty and price associated with the due and timely completion of the Work.

Should the data and information provided by the Purchaser be found to be insufficient or insufficiently complete to execute the Contract, it shall be the responsibility of the Contractor to obtain any additional required data and information. The Purchaser shall provide the Contractor, upon the latter’s justified written request made without undue delay, with all required cooperation in obtaining such additional data. The Contractor shall not be entitled to any additional payments or timetable extensions relating to the Work for reasons of faulty interpretation of any source information relating to the Work.

The Contractor shall, at its own expense, obtain all authorizations, approvals, and consents from Czech public authorities that may be needed to execute the Contract, and obtain all other authorizations, approvals, and consents that may be required to execute the Contract and / or operate the Work, except those that the Contract or Czech Republic legislation require the Purchaser to obtain in its own name.

The Contractor shall, in relation to this Contract, ensure the execution of all tasks and activities mandated by Sections 15 and 16 of Czech Republic Law no, 309/2006, on Additional Occupational Health and Safety Requirements. The Contractor shall submit to the Purchaser, no later than thirty (30) Days before assuming responsibility for the Site, the draft Notice of Commencement of Works for the Office of Labor Inspection branch relevant to the Site; once approved by the Purchaser’s authorized representative, this Notice shall be sent to the Office of Labor Inspection branch office. The Contractor shall ensure that the Notice as approved is displayed on the Site throughout the execution of the Work and updated as necessary. The Contractor shall also prepare documentation required for the Occupational Health and Safety Plan, which it will submit to the Purchaser no later than sixty (60) days before commencement of works at the Site. Pursuant to the Contract, a log shall be maintained throughout the execution of the Work of official interactions between the Contractor and the Occupational Health and Safety Coordinator assigned to the Work in matters within that Coordinator’s purview. This log shall be made available to the Purchaser at the site on the same terms as the Construction Log.

The Contractor shall maintain at the Site, for the entire duration of the Contractor’s activities there and up to the signing of the Provisional Acceptance Protocol for the Work, a complete set of all essential documents, project documentation, drawings, reports, logs, transcripts, letters, notices, etc. relating to the execution of the Work. Upon the Purchaser’s request, the Contractor shall, without delay, enable the Purchaser to peruse such documentation or, upon prior agreement, to make copies of such documentation.

Pursuant to Section 44 of the Contract, the Contractor shall be liable for any and all damages arising to the Purchaser in relation with the Contractor’s breach of mandatory legislation and standards as set out in Section 11.5 of the Contract.

The Contractor shall provide the Purchaser with Rights of Use to the Work in the scope and on the terms specified in the Contract. Unless agreed otherwise in the Contract, such rights shall be transferred to the Purchaser no later than on the date of Provisional Acceptance of the Work. To the extent that Rights of Use are creative works or other works subject to licensable intellectual property rights, the Contractor shall provide the Purchaser, no later than upon Provisional Acceptance, a non-exclusive license including the right of transfer to legal successors (incl. any potential successors to ownership of the Work), but not including sub-licensing rights, to all such intellectual property rights subjects, in the scope required to enable the proper use, maintenance, repair, renovation, and modification of the Work. Compensation for the provision of such rights, including licenses, has been included in the Contract Price.

The Contractor shall, pursuant to Section 44 of the Contract, reimburse the Purchaser for any and all damages that may arise to the Purchaser as a result of any infringement, or claim of infringement, of any rights, trademarks, copyright, or other intellectual property rights relating to the equipment, Works, and Goods used in the Work or in relation to it, registered or otherwise valid in the Czech Republic as of the date of signing of the Contract.

The Contractor shall indemnify and hold harmless the Purchaser and its employees for any lawsuits, proceedings, sanctions and orders arising from administrative proceedings, warranty and other claims, damages, losses, expenses, and costs of any kind, including costs of legal representation in matters of loss of life or limb of any natural persons and of loss or damage to any property, arising in relation the execution of the Work from matters within the responsibility of the Contractor.

In the event that the Contractor requires the placement of a temporary structure on, or other modifications to, the Purchaser’s premises, such changes shall need to be agreed in advance, in writing, with the Purchaser.

Room and board, healthcare, and insurance of the Contractor’s and its Subcontractors’ personnel shall be the responsibility of the Contractor.

Pursuant to Section 2-e of Act No. 320/2001 on Financial Inspection in the Public Administration and the Amendment of Certain Other Laws (the Financial Inspection Act), as amended, the Contractor shall provide effective cooperation in the execution of any financial inspections.

The Contractor shall, without undue delay, inform the Purchaser in the event that insolvency proceedings are brought against the Contractor. In such an event, the Contractor shall further take all necessary steps to protect the Purchaser’s property, including all portions of the Work whose ownership has already passed to the Purchaser.

The Contractor shall cooperate in the maintenance and regular updating of a list of all Subcontractors and their employees, including Subcontractor percentage shares in the Work.

The Contractor shall ensure public roads affected by construction at the Site are cleaned as necessary.

The Contractor warrants and represents that all Goods provided under the Contract shall be genuine, new, and not used.

The Contractor shall, as part of the Work, have prepared, executed, and evaluated by an independent third party the Guarantee Measurement; the third party to perform the Guarantee Measurement must be approved by the Purchaser.

The provisions of this Section 11 do not affect the obligation of the Contractor to meet all its obligations and duties given in the entirety of the Contract.

# PURCHASER’S COOPERATION

The Purchaser shall, on the basis of a justified request or notice from the Contractor, without delay and at the Purchaser’s own expense, obtain all authorizations, licenses, approvals, and consents for which Czech Republic legislation explicitly mandates that they be procured by the Purchaser in its own name. The Contractor shall, however, provide all cooperation required by the Purchaser to obtain such authorizations, licenses, approvals, etc. If, during the execution of the Contract, authorizations, licenses, approvals, or consents are issued that are material to the execution of the Contract and that are delivered solely to the Purchaser, the Purchaser shall, without delay, inform the Contractor of all material information contained in or arising from such documents. If such information affects the execution of the Contract, the Parties shall commence consultations pursuant to Section 51 of the Contract.

The Purchaser shall hand over the Site to the Contractor in the state described in Supplement 1 to the Contract, and shall make the Site accessible to the Contractor on or, if possible, before the date given for such in the Timetable and Execution Plan for the Work and in the Detailed Timetable and Execution Plan for the Work prepared pursuant to Section 24.2 of the Contract, this on the basis of a written request of the Contractor delivered to the Purchaser no later than one week in advance. The Purchaser shall prepare, and both Parties shall sign, a Site Acceptance Protocol for the hand-over of the Site to Contractor.

The Purchaser shall furnish the services of an Occupational Health and Safety Coordinator pursuant to Act No. 309/2006.

Technical supervision of the Work shall be performed by the Purchaser or a third party engaged by the Purchaser; this party may not be the Contractor, nor a party linked to the Contractor.

The Purchaser shall, no later than on the date of commencement of Commissioning, provide duly qualified operators in the scope and on the terms agreed in the Project for Commissioning and in the Test Programs given in Supplement 3 to the Contract.

Between the commencement of Commissioning and the date of signing of the Provisional Acceptance Protocol for the Work, the Purchaser shall provide all consumables, grid energy, and services required to properly operate the Work.

The Purchaser shall, before the start of the Complex Tests, obtain a Decision from the Czech Office of Construction approving trial operation of the Work pursuant to Section 124 of Act No. 183/2006 on Land Use Planning and Construction Procedures (the Construction Act), as amended. The Contractor shall, upon request, provide the Purchaser with all required cooperation.

The facilities, premises, consumables, grid energy, and services to be provided by the Purchaser as part of its cooperation with the Contractor on the execution of the Work are listed in Supplement 5 to the Contract. Such consumables, grid energy, and services shall be provided by the Purchaser in return for payment, to be agreed in separate contracts.

- Consumables, grid energy, and services shall be supplied on existing interfaces only. The Contractor shall, upon receipt of the Purchaser’s Representative’s written consent, distribute such consumables, energy, and services from existing interfaces to where they may be needed. The Purchaser shall designate connection points to grid energy (pressurized air, electricity) and water mains for the Contractor to use, and shall allow the Contractor to make the required temporary connections.

Everything not provided by the Purchaser pursuant to the Contract shall be provided by the Contractor and included in the Contract Price.

The Purchaser shall coordinate the Contractor’s activities at the Site with the activities of the Purchaser and any legal or physical persons of the Purchaser’s engagement, particularly as regards connection points for related technologies, access paths, handling and storage dump areas, etc.

In the preparation of the project documentation, the Purchaser shall allow the Contractor to peruse such project documentation as the Purchaser may have available on the actual state of the equipment affected by the Work and on current operating procedures, or the Purchaser may allow the Contractor to borrow prints or make electronic copies of such documentation, if available.

The Purchaser shall provide, free of charge, initial training on Occupational Health and Safety, fire safety, and environmental safety to personnel of the Contractor and its Subcontractors.

The Purchaser shall, free of charge, allow the personnel of the Contractor and its Subcontractors entry onto the premises of Komořany water heating plant, Teplárna Komořany, United Energy, a. s. (hereinafter, “TKY“), provided such access is both necessary and brief.

Regardless of the provisions of this Section 12 of the Contract, the Purchaser shall be required to fulfill of its obligations and duties given in the Contract. The Parties have agreed that, should the Purchaser be in delay in its cooperation, but the delay not materially affect the Contractor’s execution of the Work and / or the Contractor’s ability to execute the Work on the timetable agreed in the Contract, then the Contractor shall not be entitled to any extensions of the timetable given in the Contract, nor to a change in the Contract Price; furthermore, the provisions of Sentence 2 of Section 1968 (on Creditor Default) of the Czech Civil Code shall not apply to such Purchaser delays.

The Parties have agreed to exclude their relationship under this Contract from applicability of the provisions of Section 2591 (on Purchaser Cooperation) of the Czech Civil Code.

Regardless of the provisions of this Section 12, the Purchaser remains bound to meet all its obligations and duties agreed in the Contract.

# PAYMENT

# CONTRACT PRICE

In consideration of the Contractor’s due completion of the Work pursuant to the Contract, the Purchaser shall pay to the Contractor the Contract Price, in the amount of:

CZK [enter amount in format (…)X,XXX,XXX.00]

(that is, [enter amount in words] Czech koruna)

The Contract Price amount is exclusive of Value Added Tax (hereinafter, “VAT”) payable in the Czech Republic. VAT payment shall be handled pursuant to relevant legislation in effect at the time of the transaction(s) to be taxed.

The Contract Price includes all costs, risks, reserves, and profits of the Contractor related to the proper and timely completion of the Work, as well as all taxes, fees, tolls, licenses, and usage rights that may arise pursuant to the Contract, and further all financial expenses related to the execution of the Work and to the evolution of prices and exchange rates, until such time as the Contractor’s obligations under this Contract have been fulfilled.

The Contract Price is a mutually-agreed fixed price, subject to no other changes than those explicitly provided for in the Contract.

Supplement 9 to the Contract specifies price details and by-item breakdowns of the Work. Prices of Goods, Rights of Use, Works, and Services not explicitly listed in those price details but part of the Contract are assumed to be included in the items that are listed in the price details.

The Contractor shall provide the Purchaser, for the purposes of booking of the Work’s transfer into the Purchaser’s ownership, with details of the Contract Price prepared in accordance with the Purchaser’s accounting methods, no later than thirty (30) Days before the Provisional Acceptance date agreed for the Work in the Contract, details of the Purchaser’s accounting methods to be provided to the Contractor ninety (90) days before the Provisional Acceptance date.

# TERMS OF PAYMENT

All payments due in relation to the Work shall be made in Czech koruna (CZK) pursuant to Section 13.1 of the Contract.

Payments during the Work’s execution (installments of the Contract Price) shall be made partly as the deposit payment specified in Section 14.4-a, and partly as partial payments (installments) against the Purchaser’s approval of duly reached milestones as specified in Supplement 10 to the Contract.

The Contractor’s claims of payment against the Purchaser shall be made in writing, in the form of an advance invoice (request for payment in advance) with subsequent tax receipt issued against the received payment (advance), and of partial invoices – tax receipts including adequate description of the Goods and Rights of Use supplied and / or Works and Services rendered, and including all other documentation required under the Contract, and only once the Contractor’s obligations required for payment under the Contract have been met. The advance invoice and partial invoices / tax receipts must use the same definitions of Works, Services, Rights of Use, and Goods that are used in the price tables, the Roadmap of Key Work Milestones and Prices, and the Timetable and Execution Plan for the Work.

- The advance invoice and partial invoices / tax receipts need to be demonstrably delivered to the Purchaser at:

United Energy, a.s.

2 Teplárenská St.

434 03 Most – Komořany, Czech Republic

Czech Republic

with the demonstrable date of delivery being the date on the Purchaser’s stamp printed on the envelope upon taking delivery.

The Parties have agreed on the following payment structure for the Contract Price:

#### Deposit

#### A Deposit of fifteen (15) per cent of the Contract Price for the Work specified in Section 13.1 of the Contract, plus VAT, shall be claimed by the Contractor within twenty-one (21) days from the effective date of the Contract, pursuant to Section 56.2 of the Contract. The Purchaser shall pay to the Contractor the Deposit within thirty (30) days of the effective date of the Contract and the Purchaser’s receipt of the following:

##### Contractor’s advance invoice for the amount of the Deposit, plus VAT

##### Contractor’s bank guarantee for the Deposit, made out on the Deposit amount exclusive of VAT, issued pursuant to Section 16.2 of the Contract and to Supplement 8 of the Contract.

##### Contractor’s bank guarantee for the execution of the Work, issued pursuant to Section 16.1 of the Contract and to Supplement 8 of the Contract.

The Contractor shall provide the Purchaser, no later than fifteen (15) days of the date of receipt of the Deposit payment pursuant to Section 14.4-a of the Contract in the Contractor’s account, with a tax receipt containing all information required of tax receipts by Czech general legislation as it is in effect on the Day the invoice (tax receipt) is issued, and further containing:

Identification of the deposit covered by the tax receipt

Contractor’s trading name and registered or office address

Purchaser’s trading name and registered address, given as:

United Energy, a.s.

2 Teplárenská St.

434 03 Most – Komořany, Czech Republic

Purchaser’s and Contractor’s Business Registration numbers

Purchaser’s and Contractor’s VAT numbers

Contractor’s Business Registry file ID information

Purchaser’s Contract number

#### Invoicing based on Work progress:

Upon the completion of the Work’s milestones as specified in Supplement 10 of the Contract, the Purchaser shall pay to the Contractor the consideration agreed for the milestone in question as milestones are met, as given in Supplement 10 to the Contract, and within thirty (30) Days of the receipt form the Contractor of:

##### Copy of Progress Report as defined in Section 20.3-d of the Contract, signed by Purchaser

##### Contractor’s partial invoice

Partial invoices shall be made out to one hundred (100) per cent of the value agreed for partial payments, reduced for the aliquot part of the Deposit (the advance payment) specified in Section 14.4-a of the Contract.

The final partial invoice as per Supplement 10 of the Contract (i.e., the final payment) shall further include a detailed listing of the Work’s Contract Price, for the purposes of the entry of the Work’s various portions into the Purchaser’s Property, Plant & Equipment account, as required by Act No. 563/1991 on Accounting, as amended.

The Contractor shall issue partial invoices / tax receipts for milestone payments as the requisite milestones are met, once milestones have been met.

Invoices issued by the Contractor, the Contractor being a Value Added Tax (hereinafter, “VAT”) payer in the Czech Republic, shall also serve as tax receipts, and shall be issued on the Day of the taxable transaction in question, but in any event no later than fifteen (15) Days from that Day, and shall meet all requirements on tax receipts pursuant to applicable general legislation as it is in effect on the Day of invoice issue. The invoice / tax receipt shall contain all information required by Section 435 (on Information Required on Certain Documents and on the Internet) of the Czech Civil Code, as well as all information required for tax receipts pursuant to Act No. 235/2004 on Value Added Tax, as amended (hereinafter, the “VAT Act”); in particular, the following:

Invoicing Contractor’s trading name and registered or office address

Business Registry file ID information

Purchaser’s trading name and registered address, including first and last name of Purchaser’s representative in matters of contract, Purchaser trading name and registered address as follows:

United Energy, a.s.

2 Teplárenská St.

434 03 Most – Komořany, Czech Republic

Purchaser’s and Contractor’s VAT numbers

Purchaser’s and Contractor’s Business Registration numbers

Invoice number

Scope and subject of taxable transaction, incl. partial items and accounts

Date of taxable transaction, being the date of completion of milestone given in Progress Report as signed by Purchaser and appended to invoice

Date of issue

Price inclusive of VAT

Aliquot part of Deposit attributable to partial invoice, incl. number of advance invoice, to be deducted in before-tax amount and tax portions

Purchaser’s Contract number and name of Work

Trading name, code, and SWIFT ID of Contractor’s bank

Number of account payment is to be made into, including IBAN; account must be registered in the VAT Payers Registry

Invoice due date, pursuant to Contract

Contractor’s stamp and signature

In the event that milestone (part payment) deadlines given in the Roadmap of Key Work Milestones and Prices and the Detailed Timetable and Execution Plan for the Work pursuant to Section 24.2 of the Contract or quality or other material provisions of the Contract are not being met for reasons due to the Contractor, the Purchaser may postpone payment of subsequent partial invoices until such time that the non-conformity has been resolved. In that event, the Contractor shall continue carrying out its obligations under the Contract regardless.

The Purchaser may return invoices lacking the formal requirements given in this Section 14 of the Contract, or otherwise non-conforming, to the Contractor at any time before the invoice due date. In that event, the Purchaser shall always give the Contractor the reasons for the return. Depending on the nature of the issue, the Contractor shall then either correct or re-issue the invoice and any attachments. The original due date shall be considered void in the event of a justified invoice return. A new due date shall be set counting from the day when Purchaser receives an amended, corrected, or re-issued invoice possessing all features required by the Contract.

In the event that the Contractor breaches its obligations under the Contract, the Purchaser may set off against the Contractor’s claims on the Purchaser any of the Purchaser’s justified claims on the Contractor and their accessories; in particular, contractual penalties and penalties or other sanctions levied against the Purchaser by public authorities in relation to the Contractor’s execution of the Work (or execution of the Work by other parties engaged to that end by the Contractor), provided that the penalty or other pecuniary sanction is the fault of the Contractor (or of another party engaged by the Contractor to execute the Work or a part thereof).

- This right of set-off further extends to all other claims, and their accessories, of the Purchaser on the Contractor (pursuant to the Contract, or to other agreements between the Purchaser and the Contractor, or to enforceable judicial or administrative rulings), including contractual penalties and claims of damages, as well as claims relating to the Purchaser’s provision of goods or services to the Contractor in return for payment.

- The Contractor may not, at its own discretion, set off any of its claims, even partially, against the Purchaser’s claims without the prior written consent of the Purchaser.

- In the event that the Contractor has pecuniary obligations vis-à-vis its Subcontractors in the Work exceeding, in sum, ten (10) per cent of the value of the agreement concluded between the Contractor and that individual Subcontractor, the Purchaser may pay the Contract Price for the Work, or a part thereof, directly to the Subcontractor, in accordance with the provisions of general legislation.

All banking fees and expenses arising to the Purchaser with the Purchaser’s bank in relation to the Purchaser’s payments to the Contractor shall be borne by the Purchaser; other banking fees and expenses shall, unless agreed otherwise in the Contract, be borne by the Contractor and part of the Contract Price.

The Contractor shall not be entitled to any financial or other advantages arising from its potential early completion of Works or Services or early supply of Goods or Rights of Use, or from early completion of the Work as a whole.

The prices of any additional work requested and duly approved by the Purchaser shall be calculated on the terms given in Section 51 of the Contract.

No payment made by the Purchaser under Section 14 of the Contract shall be considered to constitute the Purchaser’s acceptance of the Work or any part thereof. No partial payment made by the Purchaser shall be held to constitute acknowledgment of any debt owed by the Purchaser to the Contractor in the sense of Section 2054, Subs. 2 (on Further Manners in Which Debt May Be Acknowledged) of the Czech Civil Code.

The Purchaser shall not be considered to be in delay or default on its obligation to pay invoices so long as the Purchaser’s account was debited for the amount due to the Contractor no later than on the invoice / advance invoice due date.

The Parties have agreed to an interest rate on arrears in the amount of the 1W PRIBOR rate + 1% p.a. for each day of delay in payment begun.

# TAXES, CUSTOMS, AND FEES

## The Contractor hereby declares to have familiarized itself with the tax, customs, and administrative legislation of the Czech Republic and to have included in the Contract Price and to be prepared to pay all taxes, customs duties, and fees that are or may be required by the relevant public authorities in relation to the execution of the Work.

## The Contractor hereby declares that the bank account it has given in this Contract is an account registered in the VAT Payers Registry of the Czech Tax Administration pursuant to Act No. 235/2004 on Value Added Tax, as amended.

## The Contractor declares that, as of the date of signing of this Contract, the Tax Administration has not issued against it an Unreliable Payer Ruling in the sense of Section 206-a of Act No. 235/2004 on Value Added Tax, as amended; that the associated proceedings have not been brought against it, and that it is not subject to conditional deferral of such proceedings with the relevant Tax Authority.

## The Contractor acknowledges and consents that, in the event that it ceases to meet the conditions given in Sections 15.2 and 15.3 of the Contract, the Purchaser shall pay the amount of Value Added Tax given on the Contractor’s tax receipts directly into the account of the Contractor’s Tax Administration office, while the Contractor shall be paid the before-tax amount.

## In the event that the Contractor fails to pay any taxes, customs duties, or fees, and that public authorities subsequently claim such payments from the Purchaser and the Purchaser pays, the Purchaser may claim reimbursement from such payment and any other related costs and damages from the Contractor. Should the Contractor fail to reimburse the Purchaser for such payments, costs, or damages within 30 Days of being requested to do so, the Purchaser may set off the amount owed against any of the Contractor’s claims, or else demand satisfaction of its claim from the bank guarantee.

## The Contractor shall ensure that the no obligation arises to the Purchaser to guarantee or directly pay any taxes, fees, or other mandatory payments that are properly the responsibility of the Contractor.

# BANK GUARANTEES FOR THE WORK AND FOR THE DEPOSIT

Bank guarantee for the Work:

### The Contractor shall procure and submit to the Purchaser a bank guarantee for the execution of the Work in the amount of ten per cent (10%) of the Contract Price exclusive of VAT, denominated in the same currency as the Contract Price. The Contractor shall submit the bank guarantee to the Purchaser within twenty-one (21) days from the effective date of the Contract, pursuant to Section 56.2 of the Contract. The bank guarantee for the execution of the Work must be valid until at least sixty (60) days after the date of signing by both Parties of the Final Acceptance Protocol for the technology section of the Work pursuant to Section 32.3 of the Contract.

### The Contractor shall, no later than thirty (30) days before the expiry of the bank guarantee for the Work pursuant to the preceding Section 16.1.1 of the Contract, submit to the Purchaser a bank guarantee for the execution of the Work in the amount of six per cent (6%) of the Contract Price exclusive of VAT, denominated in the same currency as the Contract Price. This bank guarantee shall be valid from the day following the date of expiry of the bank guarantee specified in the preceding Section 16.1.1 of the Contract, and must remain valid until at least sixty (60) days after the date of signing by both Parties of the Final Acceptance Protocol for the technology section of the Work pursuant to Section 32.4 of the Contract.

### The Contractor shall, no later than thirty (30) days before the expiry of the bank guarantee for the Work pursuant to the preceding Section 16.1.2 of the Contract, submit to the Purchaser a bank guarantee for the execution of the Work in the amount of three per cent (3%) of the Contract Price exclusive of VAT, denominated in the same currency as the Contract Price. This bank guarantee shall be valid from the day following the date of expiry of the bank guarantee specified in the preceding Section 16.1.2 of the Contract, and must remain valid until at least sixty (60) days after the date of signing by both Parties of the Final Acceptance Protocol for the Work pursuant to Section 32.5 of the Contract.

### The bank guarantees for the Work defined in Sections 16.1.1, 16.1.2, and 16.1.3 of the Contract shall be issued by a first-class European bank rated by Standard & Poor’s no lower than A– and acceptable to both the Contractor and the Purchaser.

### The bank guarantee for the Work shall be irrevocable, unconditional, payable upon first request and without the need to give due reason, and shall comply with the conditions given in the template form in Supplement 8 of the Contract. The Purchaser shall have no fewer than seven (7) days to assess and approve the selected bank and the form.

### The bank guarantee for the Work shall be the responsibility of the Contractor. All expenses related to the bank guarantee for the Work and its provision shall be borne by the Contractor and included in the Contract Price.

### In the event of delay in the Final Acceptance of portions of the Work pursuant to Section 32.3, 32.4, or 32.5 of the Contract for reasons due to the Contractor, the Contractor shall, at its own expense, ensure the extension of the relevant bank guarantee for the Work to comply with the conditions given in Section 16.1 of the Contract. Should the Contractor fail to do so, the Purchaser may, fourteen (14) days before the expiry of the original bank guarantee for the Work, use the existing bank guarantee for the Work or a part thereof for the Purchaser’s benefit, without this affecting any of the Purchaser’s rights under the Contract. The Purchaser shall return any such amounts drawn from the bank guarantee to the Contractor immediately after the Contractor submits to the Purchaser a duly extended bank guarantee.

### The bank guarantee for the Work shall be a guarantee of all of the Contractor’s obligations arising from or in relation to the Contract. These obligations include the provision of the bank guarantees for the Work pursuant to Sections 16.1.2 and 16.1.3 of the Contract.

### A template form for the bank guarantee for the Work including parameters and terms required by the Purchaser is provided in Supplement 8 of the Contract.

Bank guarantee for the Deposit:

### The Contractor shall obtain a bank guarantee for the Deposit in the amount given in Section 14.4-a of the Contract and submit this guarantee to the Purchaser in accordance with the Contract. The bank guarantee for the Deposit shall remain valid no less than thirty (30) days after the signing of the Provisional Acceptance Protocol for the Work pursuant to Section 30 of the Contract.

### The bank guarantee for the Deposit defined in Section 16.2.1 of the Contract shall be issued by a first-class European bank rated by Standard & Poor’s no lower than A– and acceptable to both the Contractor and the Purchaser

### The bank guarantee for the Deposit shall be irrevocable, unconditional, payable upon first request and without the need to give due reason, and shall comply with the conditions given in the template form in Supplement 8 of the Contract. The Purchaser shall have no fewer than seven (7) days to assess and approve the selected bank and the form.

### The bank guarantee for the Deposit shall be the responsibility of the Contractor. All expenses related to the bank guarantee for the Deposit and its provision shall be borne by the Contractor and included in the Contract Price.

### In the event of delay in the Mechanical Completion of the Work pursuant to Section 28 of the Contract for reasons due to the Contractor, the Contractor shall, at its own expense, ensure the extension of the bank guarantee for the Deposit to comply with the conditions given in Section 16.2.1 of the Contract. Should the Contractor fail to submit the extended guarantee to the Purchaser within twenty-one (21) days from the Purchaser’s request, the Purchaser may draw down against the existing bank guarantee for the Deposit up to its total value.

### A template form for the bank guarantee for the Deposit including parameters and terms required by the Purchaser is provided in Supplement 8 of the Contract.

# INTELLECTUAL PROPERTY

# LICENSES AND RIGHTS OF USE TO TECHNICAL INFORMATION

For the purposes of the operation and maintenance of the Work, as this consists of the individual tasks, procedures, and processes specified in the Contract, and further for the purposes of repair, renovation, and modification of the Work, the Contractor shall provide to the Purchaser a non-exclusive, non-transferrable (excepting transfer to legal successors, including potential successors to ownership of the Work), time-unlimited license valid in Czech Republic territory relating to patents or other industrial intangibles rights owned by the Contractor or by a third party by whom the Contractor is authorized to license such rights; the Contractor shall also grant to the Purchaser a non-exclusive, non-transferrable (excepting transfer to legal successors, including potential successors to ownership of the Work), time-unlimited right of use of know-how (if applicable) and other technical information provided to the Purchaser under the Contract, valid in Czech Republic territory. No provision contained in such documents may not be interpreted as the transfer of ownership of any patents, trademarks, copyrights, know-how, or other intellectual property rights from the Contractor or a third party to the Purchaser if such a transfer would be outside the scope of the Contract.

The fees for the provision licenses and rights specified in Section 17.1 are, in full, included of the Contract Price.

The Purchaser and the Contractor have agreed on the following scope expansion of the Rights of Use for documentation provided pursuant to Section 2 of Supplement 3 to the Contract:

#### The Purchaser may familiarize third parties with the documentation specified above, to the extent necessary and to the extent that such parties may provide repair, modification, maintenance, and / or operation services for systems included in the Work pursuant to the Contract.

#### The Purchaser shall not use the documentation specified above to repair, maintain, or operate systems owned by third parties, shall not manufacture new units of similar systems on behalf or for third parties, and shall not provide the documentation to third parties that would perform such activities on behalf or for other third parties.

# INFORMATION AND CONTRACT DOCUMENTS SECURITY

Except for the provisions of Section 18.4 of the Contract, each Party shall hold as confidential all commercial and technical information, including specifications, plans, drawings, patterns, etc., as well as other information and materials, provided to them by the other Party on papers (media) marked restricted-access or otherwise exchanged between the Parties during the execution of the Contract; neither Party shall use such information for its financial or other benefit nor for the benefit of third parties, nor make such information accessible to third parties without the prior written permission of their counterparty in this Contract, nor use such information and materials for any purpose other than to execute the Contract. The requirement of permission shall be waived for provision of access to the Subcontractors listed in Supplement 7 of the Contract, provided such disclosure is limited to the extent necessary to that particular Subcontractor’s execution of the Work.

The obligation of confidentiality shall also be binding upon Subcontractors and any third parties to whom the information specified in Section 18.1 of the Contract may have been provided by the Contractor with the Purchaser’s approval and on the terms specified by this Section 18 of the Contract. The Contractor shall ensure that such parties are bound by confidentiality at least to the same extent as the Contractor. The Contractor shall be liable for any Subcontractor breaches of the obligation specified in this Section 18.2.

All documents listed in Section 18.1 of the Contract, whether or not marked as restricted-access documents (media) by the Purchaser, and excepting the Contract itself, are the property of the Purchaser and, if requested by the Purchaser, all copies thereof shall be returned to the Purchaser once the Contractor has executed the Contract.

The Purchaser and the Contractor each may, even without the other Party’s approval, disclose information that the other Party has marked as restricted-access documents (media), to the extent necessary, if for the purposes of the Contract:

#### Disclosure is required by public authorities, including financial or other authorities empowered to assess the Work’s compliance with general legislation;

#### Disclosure is required for the activities of consultants or other parties involved in executing the Contract; in such an event, the Contractor shall ensure that the parties in question are made aware of the confidentiality obligations set forth in this Section, and agree to be bound thereby.

The obligation to secure restricted-access documents (media) shall endure for a period specified by the Party having marked the documents (media) as restricted-access. In the event that the Party failed to specify such a period, the obligation to secure restricted-access documents (media) shall terminate automatically ten (10) years after the signing of the Provisional Acceptance Protocol for the Work, unless a longer period is required by applicable legislation.

The information types listed below shall be excluded from the obligation to hold as confidential restricted-access documents (media):

#### Information that is or has become public knowledge, through no fault of the recipient

#### Information legally obtained by the recipient from third parties not involved in the preparation and execution of the Work

#### Information such as is commonly given in business reference lists

#### Information intended for publication, in the format and scope approved by the Purchaser

In the performance of this Contract, both Parties shall obtain personal data protected by Regulation (EU) 2016/679 on the protection of individuals with regard to the processing of personal data and on the free movement of such data (hereinafter referred to as GDPR). Both Parties are therefore obliged to maintain confidentiality about all the facts the disclosure of which to a third party could cause harm to another party and to protect and develop the reputation and reputation of the other party, its owners and associates (family members, members company bodies, employees, etc.).

Neither Party may claim confidentiality in court / arbitration proceedings arising from or relating to the Contract. This also includes proceedings before other public authorities, financial inspections, tax inspections, proceedings before European Union authorities, and provision of information to third parties bound by law to hold such information as confidential (e.g. auditors, attorneys).

# EXECUTION OF THE WORK

# PARTIES‘ REPRESENTATIVES

Purchaser’s Representative

### The Purchaser’s Representative is identified in Section 7.1-d of the Contract. The Purchaser shall notify the Contractor, without delay and in writing, if a different Purchaser’s Representative is assigned.

The Purchaser’s Representative shall represent the Purchaser and act on the Purchaser’s behalf, in the scope given in the Purchaser’s Power of Attorney, throughout the duration of the Contract, as well as communicate to the Contractor all notices, instructions, information, and other information exchanges pursuant to the Contract from the Purchaser.

All notices, instructions, information, and other exchanges pursuant to the Contract from the Contractor to the Purchaser shall be communicated to the Purchaser’s Representative, unless the Contract specifies another recipient.

Contrator’s Representative and Construction Manager (Construction Foreman)

### The Contractor’s Representative is identified in Section 7.1-e of the Contract. The Contractor shall notify the Contractor, without delay and in writing, if a different Contractor’s Representative is assigned.

### The Contractor’s Representative shall represent the Contractor and act on the Contractor’s behalf. The Purchaser shall interact with the Contractor’s Representative on the good-faith assumption that the latter is authorized to make all decisions they are making on behalf of the Contractor. The Contractor’s Representative communicates to the Purchaser all notices, instructions, information, and other information exchanges pursuant to the Contract from the Contractor.

All notices, instructions, information, and other exchanges pursuant to the Contract from the Purchaser to the Contractor shall be communicated to the Contractor’s Representative, unless the Contract specifies another recipient

### The Contractor’s Representative shall participate in all progress meetings pursuant to Section 20.3-c of the Contract, unless the Purchaser and the Contractor demonstrably agree otherwise.

### No later than at the date of commencement of works at the Site, the Contractor shall institute a Construction Office at the Site and appoint a suitable staffer as the Construction Manager (i.e., the Construction Foreman in the sense of Act No. 183/2006, the Construction Act, as amended) responsible for operations at the Site. The Construction Manager manages the construction of the Work, supervises all Contractor Works at the Site and shall be present at the site at all times during standard business hours (usually, 8 a.m. to 5 p.m.) throughout the duration of the Contractor’s activities at the Site, unless on leave, sick, or absent in relation to the execution of the Contract. Whenever the Construction Manager is absent from the Site, they shall be deputized for in full by their Deputy. The Purchaser or their Representative shall submit all notices, instruction, information, and other information exchanges relating to the Works at the Site to the Construction Manager or, if absent, to their Deputy. The Construction Manager shall be authorized to make all such decisions as may be required for the on-site management of the execution of the Work, and shall participate in all progress meetings pursuant to Section 20.3-c of the Contract, unless the Purchaser and the Contractor demonstrably agree otherwise

### The Purchaser may request the Contractor to replace any and all of the Contractor’s personnel who demonstrate incompetence and / or gross negligence in the execution of their duties, or whose presence at the Site is otherwise objectively unwelcome. Such Contractor personnel may not continue to be employed, or be re-employed, at the Site without the Purchaser’s approval. Such replacement requests shall be made in writing and duly justified. The Contractor shall then carry out such requests without undue delay. The Contractor shall replace any and all personnel removed under this clause by other suitable personnel without undue delay. This provision shall apply equally to Subcontractor personnel.

# INFORMATION SUBMITTED TO PURCHASER

In preparing all documentation, i.e., drawings, specifications, calculations, protocols, lists, manuals, procedures, timetables, reports, etc. (hereinafter in this Section, “information”) relating to the execution of the Work, the Contractor shall employ all such knowledge, experience, dilligence, and professional care as may be required for a properly-engineered Work.

All such information submitted by the Contractor, or requested from the Contractor by the Purchaser, for the Purchaser’s approval shall be prepared by the Contractor, at its own expense, and shall comply with the requirements of the Contract. Excepting the provisions of Section 23.2 of the Contract, the Purchaser’s approval, assessment, or consent to information provided by the Contractor shall not affect the Contractor’s responsibility for the correctness and completeness of the information provided, nor of the obligation to comply in full with the Contract. The Contractor may not modify or change information approved or consented to by the Purchaser without a re-assessment of the modifications or changes by the Purchaser. The Purchaser’s judgments as to the appropriateness and correctness of the information provided shall be final and binding upon the Contractor. All information provided by the Contractor for the Purchaser’s approval or consent pursuant to the Contract shall be verified by the Contractor and marked as correct and adequate in view of the Goods and Rights of Use to be supplied and the Works and Services to be rendered by the Contractor. Unless agreed otherwise, all information provided to the Purchaser shall be in the Czech language.

Progress reports on the Work

## The Contractor shall keep the Purchaser informed of its activities and progress in relation to the Work. To that end, the Contractor shall prepare and submit periodic Progress Reports, whose basic contents, format, number, timetable, and frequency is specified below in this Section 20.3 of the Contract. The Purchaser may, if justified, request modification or expansion of this basic scope of contents, format, number, timetable, and / or frequency, in which event the Contractor shall comply with such requests without it affecting the Contract Price. The manner and format in which Work Progress Reports are to be made shall be further agreed by the Parties in the Administration Rules.

## The reports described in this Section 20.3 of the Contract shall serve to inform the Purchaser of the Contractor’s progress. The Contractor shall submit particularly the following:

#### Daily report (Construction Log)

The Contractor shall prepare daily reports in the form of entries in the Construction Log kept at the Site, detailing the Works done during the preceding Day. Pursuant to applicable legislation, the Construction Log shall begin on the day the Contractor accepts custody of the Site and end on the day of Work Final Acceptance, where daily reporting shall be required until the date of Work Provisional Acceptance, and on an as-needed basis thereafter. After the Work Provisional Acceptance date, the Construction Log shall be kept at the Purchaser’s registered address. Construction Log entries may not be used to initiate or execute Changes pursuant to the Contract in matters of the subject, price, quality, or timetable of the Work. Individual daily entries shall be made in the Construction Log by the Contractor’s Representative or the Construction Manager (Construction Foreman).

#### Monthly Report

The Contractor shall prepare and submit to the Purchaser, no later than on the fifth (5th) business day of the following Month, a Monthly Report for the past Month summarizing the extent of works done and progress made over that Month (i.e., deliveries of Works, Goods, Services, and / or Rights of Use). Monthly Reports shall contain, at minimum:

##### Overview of the state of progress on engineering and design work detailing activities performed over the Month in question

##### Overview comparing actual progress on the Work to progress planned, i.e., comparing the actual state of progress on the Work to the Timetable and Execution Plan for the Work and the Detailed Timetable and Execution Plan for the Work prepared pursuant to Section 24.2 of the Contract

##### Overview of planned activities (i.e., deliveries of Works, Goods, Services, and / or Rights of Use) of the Contractor for the following Month

##### List of Changes made, including list and status of change proceedings pursuant to Section 51 of the Contract

##### List of invoices issued and payments received by the Contractor

##### List of any major non-conformities, including their potential impact on the execution of the Contract and details of remedial measures taken. Particular attention shall be given to areas in which the Contractor is or might become delayed in the meeting of the key Work execution milestones as given in Section 10.1 of the Contract.

##### Any other documents the Purchaser and Contractor may agree on

#### Progress Meetings

The Purchaser and the Contractor shall meet at certain times specified by the Purchaser to discuss the state of the Contractor’s progress in the execution of the Contract. The Contractor’s Representative shall participate in such meetings, as shall, if pertinent, the Construction Manager and any other Contractor staff who may have relevant contributions. These meetings shall cover the state of progress on the Work, plans and proposals for future activities, the labor situation, engineering progress, Occupational Health and Safety concerns, supplies of equipment and materials, current and expected difficulties, any coordination in executing the Work that may be required, change proceedings, and any other topics that may be pertinent. The Contractor shall maintain a record of the proceedings, which both Parties shall approve and sign at the end of the meeting to which the report pertains.

Progress Meetings shall take place once a month until the Contractor’s acceptance of custody of the Site, and once a week thereafter, always at the Purchaser’s offices, unless agreed otherwise. If required, other, extraordinary meetings may take place. The time and place for such extraordinary meetings shall be agreed individually and with regard to the topic.

#### Milestone Report

Upon the completion of each of the milestones given in the Roadmap of Key Work Milestones and Prices contained in Supplement 10 of the Contract, the Contractor shall prepare and submit to the Purchaser a Milestone Report, containing, at minimum:

##### List of Works, Goods, Rights of Use, and Services provided in the completion of the milestone in question

##### Assessment of milestone completion and meeting of conditions for the associated payment

##### Comparison of milestone completion time against the Timetable and Execution Plan for the Work and the Detailed Timetable and Execution Plan for the Work prepared pursuant to Section 24.2 of the Contract

##### Any other documents the Purchaser and Contractor may agree on

The Purchaser shall, within seven (7) business days from the receipt of a Milestone Report from the Contractor, unless agreed otherwise, either sign off on the Milestone Report, or else give, in writing, its reasons for not doing so.

##### In the event that the Purchaser, within the above mentioned period of seven (7) business days, fails to both sign off on a milestone report and give the Contractor in writing its reasons for not doing so, then that Milestone Report shall be considered signed and approved, and the Contractor shall be entitled to invoice the payment due to it for the milestone in question.

# SUBCONTRACTING

The list of approved Subcontractors for principal Works, Services, and Goods deliveries is part of Supplement 7 to the Contract. The Contractor may propose amendments and deletions to this list as it sees fit. The Contractor shall provide such changes to the Purchaser for approval, in writing. All such changes shall be submitted in a timely manner so as not to delay to the Work. No changes are valid without the Purchaser’s prior written approval. The Purchaser shall not withhold such approval without cause. In the event the Purchaser fails to make a statement on a proposed change within seven (7) days of receipt, that change shall be considered approved.

The Purchaser reserves the right to refuse any Subcontractors of Works, Services, and Goods who are not listed in Supplement 7 to the Contract and who, in the Purchaser’s opinion, lack sufficient skill and experience on similar projects, or who, to the Purchaser’s knowledge, have a history of not fulfilling obligations, or whose financial and technological position is, in the Purchaser’s opinion, insufficient to adequately guarantee the fulfillment of the obligations under the Contract considered for that Subcontractor. In that event, however, the Purchaser shall provide due justification for its refusal of such a Subcontractor to the Contractor, in writing.

The Contractor shall notify the Purchaser of any Subcontractor agreements it has entered into within ten (10) days of entering into such agreements.

The Purchaser’s approval of a Subcontractor and / or the execution of the Work or a part thereof by a Subcontractor does not in any way affect the Contractor’s obligations and duties under the Contract; the Contractor bears responsibility for the work of its Subcontractors as if it were the Contractor’s own.

The Purchaser may refuse to take delivery of Goods, Rights of Use, Works, and / or Services delivered via a Subcontractor not meeting the requirements of this Section 21 of the Contract.

The Contractor shall ensure that all its subcontracts contain explicit provisions to the effect that the Contractor is authorized to assign its rights and obligations in such subcontracts to the Purchaser or a third party in a manner that would make the Subcontractor a direct contractor of the Purchaser or a third party of the Purchaser’s choosing, particularly in situations described in the Contract (Section 53.2.2). Furthermore, the Contractor shall ensure that its subcontracts contain provisions and obligations binding upon the Subcontractors equivalent to the provisions and obligations binding upon the Contractor under the Contract. The Contractor shall, upon the Purchaser’s request, demonstrate to the Purchaser that its subcontracts contain such provisions.

In the event that the Contractor, pursuant to Section 21.1 of the Contract, proposes a change of Subcontractor to the Purchaser affecting a Subcontractor through which the Contractor demonstrated fitness to qualify for the procurement process for the Work, the Contractor shall demonstrate to the Purchaser that, after the change of Subcontractor, the Contractor shall remain qualified as per the Purchaser’s requirements given in the procurement process for the Work, in the extent that the Contractor’s qualifications may have been demonstrated through the Subcontractor being replaced, such demonstration to be made in the same manner that was required in the procurement process for the Work. This does not affect the provisions of Section 21.2 of the Contract.

# STANDARDS AND LEGISLATION

The Contractor shall comply with all of the following:

##### General legislation of the Czech Republic, as in effect at the time; and

##### CSN standards, as in effect at the time, as well as harmonized CSN EN and CSN EN ISO standards, i.e., standards relevant to the Work incorporating in full the requirements of common European standards or of harmonization acts approved by the authorities of the European Union as harmonized European standards, or European standards enacted as harmonized pursuant to the law of the European Union by agreement of notified parties, unless expressly stated otherwise; and

##### The Purchaser’s internal guideline “Supplier Rules”, which has been included in Supplement 11 of the Contract

The use of foreign national or international standards shall only be allowed if the requirements of such standards are at least as stringent as those of standards in effect in the Czech Republic, and with the Purchaser’s prior approval. Should the Contractor wish to use a foreign standard with no direct equivalent CSN, CSN EN, or CSN EN ISO standard, the Contractor shall provide the text of the standard to the Purchaser, in both its original language and certified Czech translation, along with the documentation affected by the standard, for the Purchaser’s approval, unless the Parties agree on another procedure.

The Contractor shall provide to the Purchaser, in order to demonstrate its compliance with the requirements of general legislation, mandatory standards, and the Work’s quality assurance program, the relevant documentation pursuant to this Section, no later than ten (10) days before the commencement of the Complex Tests pursuant to Section 29.2 of the Contract, unless the Contract specifies an earlier deadline or the Parties agree otherwise.

The Purchaser may refuse to accept a Work not compliant with the requirements of this Section 22 of the Contract, in which event the Contractor shall, at its own expense, ensure the Work’s compliance with this Section 22 of the Contract.

None of the provisions of this Section 22 of the Contract shall relieve the Contractor of responsibility for inspections, testing, quality, warranty, or any other obligations under the Contract, nor entitle the Contractor to an increase in the Contract Price or an extension in the timetable agreed in the Contract.

# ENGINEERING WORK, DOCUMENTATION

The Contractor shall perform design and engineering Works in accordance with the Contract or, if the Contract does not provide for the matter at hand, in accordance with relevant general legislation and standards as specified in Section 22.1 of the Contract and with engineering best practice. The Contractor shall be liable for any non-conformities, errors, and omissions that may occur in the specifications, drawings, and other technical documentation prepared by the same, whether or not such specifications, drawings, or other documentation have been approved by the Purchaser, provided that such non-conformities, errors, or omissions are not the result of faulty information provided to the Contractor, in writing, by the Purchaser or in the Purchaser’s name, such shortcomings of the information having been fruitlessly pointed out by the Contractor in the sense of Section 23.2 of the Contract.

The Contractor shall not be liable for the consequences of incorrect instructions or information provided by the Purchaser or in the Purchaser’s name, provided that the Contractor gave the Purchaser clear and demonstrable notice of the shortcomings of such instructions or information, in writing and without undue delay but no later than ten (10) business days from its receipt, and that the Purchaser insisted in spite of such notice on the execution of such instructions and / or the use of such information, or that alternatively the Contractor was not allowed to ascertain the correctness of such instructions or information despite its written request for the same. The Parties have agreed to exclude their legal relationship under this Contract from applicability of the provisions of Section 2594, Subsections 2, 3, and 4 (on Contractor Notification of Purchaser), and of Section 2595 (on Faulty Purchaser Instructions, Contractor Withdrawal) of the Czech Civil Code.

Scope, format, language, quantity, approval procedure, and other requirements on documentation are listed in Supplement 3 to the Contract. The Contractor shall prepare and submit to the Purchaser all documentation required by Supplement 3 to the Contract. The costs of preparation, including materials and submission, shall be borne by the Contractor and part of the Contract Price.

In the event that the Contractor, with the Purchaser’s prior approval, uses a different digital file format for documents provided under this Contract than required in the same, the Contractor shall, at its own expense and without delay, provide to the Purchaser any licenses that may be required, in the quantity necessary for the number of users agreed, including user manuals and, if required, training of the Purchaser personnel in question on the use of such formats.

Pursuant to the Quality Plan, the Contractor shall provide the Purchaser with copies of all documentation prepared exclusively in relation to the Work, for the purposes of the Purchaser’s approval of the Contractor’s activities in supply, manufacture, shipping, assembly, installation, construction, and / or Commissioning.

The procedure for documentation submission and approval shall be as specified in Supplement 3 to the Contract. The Purchaser’s approval or inspection of the documentation provided by the Contractor, whether with or without modifications, does in no way relieve the Contractor of responsibility for any faults with the documentation or of any of its obligations under the Contract.

The Contractor shall be liable for and bear all costs of any and all damages that may arise from its provision of any Goods and / or execution of any part of the Work before receiving the Purchaser’s approval.

# EXECUTION OF THE WORK

The Work shall be executed in accordance with the provisions of the Contract, particularly, on the timetable given in Section 10 of the Contract and in accordance with the Timetable and Execution Plan for the Work and the Detailed Timetable and Execution Plan for the Work prepared pursuant to Section 24.2 of the Contract, and in accordance with the Quality Plan.

The Contractor shall submit for the Purchaser assessment, along with the Documentation for Execution of the Project, the Detailed Timetable and Execution Plan for the Work. This Detailed Timetable and Execution Plan shall illustrate, in detail, the Contractor’s and its Subcontractors’ plans for execution of the Work, shall comply with the deadlines given in Section 10 of the Contract and the milestones given in the Timetable and Execution Plan for the Work, and shall not cause conflict with works performed by the Purchaser or by parties authorized by the Purchaser. Once the Purchaser has approved the Detailed Timetable and Execution Plan for the Work, it shall become a binding contract and shall replace the Timetable and Execution Plan for the Work specified in Supplement 4 of the Contract. Until such time as the Detailed Timetable and Execution Plan for the Work has been approved, the Timetable and Execution Plan for the Work given in Supplement 4 to the Contract remains in effect.

The Work is to be executed while the Teplárna Komořany (TKY) heating plant continues full operation. Should any works be required that may only be performed while the Purchaser’s systems are offline, but where TKY as such may remain in operation, such works shall be performed during a shutdown period chosen by the Purchaser, based on consultation with the Contractor and the Purchaser’s operational exigencies. The Contractor shall submit to the Purchaser any requests to shut down Purchaser systems no later than 90 Days before the date on which shutdown is requested to commence, unless the Parties demonstrably agree otherwise.

The Purchaser shall inform the Contractor of the date of system shutdown pursuant to Section 24.3 of the Contract no later than seven (7) Days before the shutdown date. The Contractor shall consider the Purchaser’s notice final.

The Contractor may not commence manufacturing and execution of the Work before receiving written approval on the relevant Documentation for Execution of the Project from the Purchaser and the depositing of such documentation with the Purchaser, unless the Parties demonstrably agree otherwise. Any delay in the execution of the Work due to the Contractor’s inability to commence works at the Site for reasons of the Contractor’s failure to deposit the approved Documentation for Execution of the Project with the Purchaser, shall be the responsibility of the Contractor.

The Contractor shall prepare execution timetables for activities relating to Commissioning, which shall contain a disaggregated listing of the activities given in the Detailed Timetable and Execution Plan for the Work. The Commissioning execution timetables shall use hours as the unit of time and shall be submitted to the Purchaser for approval no later than ninety (90) Days before the Commissioning commencement date.

- The Commissioning execution timetables shall describe each activity in a level of detail no lesser than that found in the Detailed Timetable and Execution Plan for the Work. If requested by the Purchaser, the information in the Commissioning execution timetables shall be amended to include further required data (e.g. resources, assignment of responsibility, etc.).

Before commencing assembly of the Work, the Purchaser and the Contractor shall sign an Assembly Readiness Protocol. The drafting of the Protocol shall be the responsibility of the Contractor. In the event that the Purchaser refuses to sign the Assembly Readiness Protocol, the Purchaser shall inform the Contractor of its reasons for doing so within five (5) Days of receipt of the draft Protocol. Should the Purchaser, within five (5) Days of receipt, fail to both sign the Protocol and give the Contractor in writing its reasons for not doing so, then the Protocol shall be considered signed on the date of the Purchaser’s receipt of the draft. The Assembly Readiness Protocol shall in particular contain:

#### Attestation of the Purchaser’s approval of the documentation required to commence assembly

#### Attestation to the effect that all equipment and components required to commence assembly have been delivered to the Site and duly tested in accordance with the Quality Plan

#### Attestation of the Purchaser’s approval of the Quality Plan for assembly works

#### Attestation to the effect that all staff participating in works covered by the Protocol have been adequately briefed on all regulations relevant to the execution of the Contract

The Contractor shall, throughout the execution of the Work, monitor and document the progress of all deliveries and activities with regard to the conditions and timetable agreed in the Timetable and Execution Plan for the Work (Supplement 5 to the Contract) and the Detailed Timetable and Execution Plan for the Work prepared pursuant to Section 24.2 of the Contract.

# DELIVERY AND DOCUMENTATION

All documents relating to the delivery of Goods, Rights of Use, materials, and Services to the Site from outside the Czech Republic (i.e., customs, insurance, transit, tax, origin, etc. documents) shall be procured, handled, and tracked by the Contractor.

The Contractor shall deliver to the Site all Goods, materials, and Work components sourced in the Czech Republic, including any and all taxes, insurance, shipping, and other costs, as well as licenses, approvals, etc. relating to the delivery of Goods to the intended destination. Documents relating to the delivery of Goods to the Site (insurance, shipping, tax, etc.) shall be procured, handled, and tracked by the Contractor.

All commenced deliveries of Goods shall be reported by the Contractor to the Purchaser via e-mail, including the description of the Goods, the delivery location, the shipping method, and the estimated time to arrival at the Site; the Purchaser should have this information no later than three (3) business days before the Goods are due at the Site. In the event that the Purchaser does not receive such information by the time given above, the Contractor shall be liable for any and all consequences, including demonstrable costs, arising to the Purchaser as a result, and shall reimburse the Purchaser for such costs without delay.

# SHIPPING, PACKAGING INSTRUCTIONS

The Contractor shall, at its own risk and expense, ship to the Site all relevant Goods, utilizing such shipping methods as it considers suitable given the goods being shipped.

All deliveries under the Contract shall be duly and carefully packaged in accordance with manufacturer instructions and with regard to the nature of the Goods in question, in packaging suitable for long-distance shipping and loading and offloading, so as to prevent damage during transit and storage. The Contractor shall ensure thermal and mechanical insulation is included such as can adequately prevent damage by water, rain, collision, and corrosion, as appropriate given the nature of the equipment, in order to ensure the safe shipping of Goods to the Site.

The Contractor shall mark all transit packaging with the project name, “Environmental Improvements on TKY II Heating Plant - Wet Desulfurization – recipient: [add contractor name], Contractor“.

# WORK QUALITY ASSURANCE

The Contractor shall ensure that the Work, including all related activities of the Contractor and its Subcontractors at all levels, is executed at the level of quality required by the Contract, as set out particularly in this Section 27 of the Contract, Supplement 3 to the Contract, Czech Republic general legislation, and the Quality Plan and Inspection and Test Plan as approved by the Purchaser.

Throughout the duration of the Contract, the Contractor shall submit to the Purchaser all documentation required by the Quality Plan and requested by the Purchaser.

The quality aspects of the Work’s execution pursuant to the Contract shall be governed by the Quality Plan and the Contractor’s Inspection and Test Plan, including any amendments to the latter in accordance with the Contract. The Quality Plan and the Inspection and Test Plan for the execution of the Work pursuant to the Contract shall be prepared by the Contractor and submitted to the Purchaser for approval in the scope and on the timetable given in Supplement 3 to the Contract. The Purchaser shall not deny approval of the Quality Plan and / or the Inspection and Test Plan without reason, and shall strive to give approval as soon as possible after receiving the Contractor’s draft. Should the Purchaser, within fourteen (14) days of receipt, fail to both approve the draft Quality Plan and / or the draft Inspection and Test Plan, and to give the Contractor its reasons and / or change requests, then the Quality Plan and / or Inspection and Test Plan shall be considered approved.

All inspections and testing performed in relation to the preparation and execution of the Work by the Contractor and / or its Subcontractors shall be performed in accordance with the Inspection and Test Plan and related documentation, and in accordance with the Contract.

The Quality Plan and Inspection and Test Plan may be amended via documented, Purchaser-approved revisions.

During the execution of the Contract, the Contractor shall amend the Quality Plan and Inspection and Test Plan within thirty (30) days of the Purchaser’s request in the event of changes in:

##### General legislation requirements; or

##### Internal Purchaser regulations; or

##### Public oversight and administration requirements; or

##### Should inspection results mandate remedial and / or preventive measures; or

##### Based on other Purchaser requirements in accordance with the Contract

- In the event that the reasons for such changes are not attributable to the Contractor and the changes are material to the execution of the Work, the Parties shall commence consultations pursuant to Section 51 of the Contract, unless agreed otherwise.

The Purchaser-approved Quality Plan and Inspection and Test Plans governing the quality-related activities on the Work shall be amended by the Contractor and re-submitted for the Purchaser’s approval in the event that the Contractor wishes to make a change of any kind, particularly changes in the sequence, contents, and / or methods of inspections and / or tests, including for reasons of the non-compliance of the sequence, contents, and / or methods of inspections and tests with the Timetable and Execution Plan for the Work, the Detailed Timetable and Execution Plan for the Work prepared pursuant to Section 24.2 of the Contract, or the scope of the Work itself. The Purchaser’s approval, or lack thereof, of Quality Plan and Inspection and Test Plan revisions proposed by the Contractor does not relieve the Contractor of responsibility for inspections and testing and the due execution of the Work pursuant to the Contract. Existing versions of the Quality Plan and Inspection and Test Plan remain in effect and binding upon the Contractor until such time as the Purchaser may approve a revision.

In the event that the Purchaser becomes aware that the version of the Quality Plan and / or Inspection and Test Plan currently in effect does not conform to the Contract, the Contractor shall, within a reasonable timeframe specified by the Purchaser, prepare and submit to the Purchaser for approval a new revision of the Quality Plan and / or Inspection and Test Plan compliant with the Contract. All expenses relating to Quality Plan and Inspection and Test Plan revisions under this Section 27.8 shall be borne by the Contractor.

Throughout the execution of the Contract, the Contractor shall allow the Purchaser or its representatives, without delay, to perform an audit of the quality management system and to inspect and test the Work or any part thereof, including Goods, Works, Services, Rights of Use, drawings, and documentation, so that the Purchaser may satisfy itself that these conform to the Contract.

Tests and inspections may be performed at the Contractor, at its Subcontractors, at manufacturer facilities, and at the Site.

Whenever the Contractor is ready to perform such tests and inspections as are specified in the Inspection and Test Plan and marked “W” (Witness Point, i.e., a test or inspection requiring the Purchaser to bear witness), the Contractor shall, in reasonable advance but no later than fourteen (14) days in advance, send by fax, e-mail or registered post a notice to the Purchaser of the test or inspection and the time and place of its performance. The Contractor shall obtain from its Subcontractors or any third parties or manufacturers involved all permissions and consents required to enable the Purchaser’s representatives to attend the test or inspection.

Results, protocol, and certificates attesting that a test or inspection has been performed shall be filed in the “Inspection and Test Book”, which shall be submitted to the Purchaser no later than five (5) days before the expected Work Provisional Acceptance date, pursuant to Section 30 of the Contract.

The Contractor shall provide to the Purchaser all protocols relating to the results of any such tests and inspections. In the event that the Purchaser’s representative fails to attend a test or inspection where their attendance is required, the Contractor may perform the test or inspection without the Purchaser’s participation, in which case the Contractor shall the submit for the Purchaser’s assessment, within three (3) business days, the protocols summarizing the results. If the test or inspection in question is a Hold Point as these are defined in the Inspection and Test Plan, the Contractor shall wait for the Purchaser’s representative no less than twenty-four (24) hours from the agreed time of the test or inspection, unless the Parties agree otherwise.

The Purchaser may attend tests and inspections by sending a representative. Costs and expenses related to such attendance, such as travel and room and board expenses, shall be borne by the Purchaser. In the event that the test or inspection results in a failure for reasons attributable to the Contractor, the Contractor shall reimburse the Purchaser for all demonstrated and reasonable expenses related to the Purchaser’s representative’s attendance of the test or inspection. The Purchaser may invoice the Contractor for costs related to attendance at a failed test or inspection at any point after that test or inspection, or may set off such costs against its financial liabilities vis-à-vis the Contractor in any of its payments to the same.

In exceptional cases, the Contractor shall allow the Purchaser to perform tests and inspections of any kind that are not included in the Inspection and Test Plan, provided that:

##### Such a test or inspection does not jeopardize progress on the Work, does not impact the proper functioning of the Work part being tested or inspected, and does not compromise the Contractor’s performance of the Contract. Should the Contractor deem a test or inspection to jeopardize progress on the Work, impact the proper functioning of the Work part being tested or inspected, or compromise the Contractor’s performance of the Contract, the Contractor shall demonstrate this to the Purchaser without delay. If the Purchaser then insists on performing the test or inspection regardless, any impact on the performance of the Contract shall be handled pursuant to Section 51 of the Contract, the Contractor shall be relieved of responsibility for potential damages; and

##### The Contractor shall be reimbursed by the Purchaser for all demonstrated and reasonable expenses resulting from the performance of such a test or inspection; and

##### The Purchaser shall request the Contractor to perform such a test or inspection no fewer than 10 business days in advance; and

##### The Purchaser shall provide the Contractor with all relevant inspection and background documents no fewer than 5 business days in advance.

For the purposes of monitoring of the progress of Works at the Site / assembly sites and the Purchaser’s technical supervision, the Contractor shall allow the Purchaser, during standard work hours, access to the Site / assembly site at any time and without written notice; outside standard work hours, the Contractor shall make all reasonable effort to allow the same. As part of its technical supervision, the Purchaser may in particular monitor compliance of the Works with the Contract, the Design, and applicable technical standards and other legislation. The Purchaser may note any issues found with the Works monitored in the Construction Log. The Contractor shall ensure that its authorized staff are present during the Purchaser’s technical supervision of deliveries and Works, and that measures to remedy any issues pointed out are taken without delay. The Purchaser’s technical supervisors may order Contractor (and / or Subcontractor) personnel to interrupt the Works if the Contractor’s Representative cannot be reached and continuation of the Works would jeopardize the safety, life, or limb of construction personnel and / or threaten major material damage.

The Contractor shall lend to the Purchaser or its representative, free of charge, all required gear, equipment, measurement and test devices, media, etc., as well as provide due cooperation including access to drawings and production data, to the extent that this may be required for the Purchaser to effectively participate in planned tests and inspections marked “W” or “H” in the Inspection and Test Plan. As regards gear, equipment, measurement and test devices, and media, the Contractor shall be required to provide these per the above only if such gear, equipment, measurement and test devices, and media are available to the Contractor directly at the site of the test or inspection in question. The Purchaser shall be held liable for any damage to the gear, equipment, and measurement and test devices borrowed from the Contractor.

In the event that any test or inspection fails for reasons not attributable to the Purchaser, the Contractor shall make all modifications (changes) required to meet the criteria specified, free of charge. The costs of repeated tests and inspections of such newly re-delivered or repaired portions of the Work shall be borne by the Contractor. The Contractor shall also bear all costs and expenses that may arise to the Purchaser in relation to a repeated test or inspection marked “W” or “H” in the Inspection and Test Plan.

No part of the Work may be made inaccessible from the Site before the tests and inspections required for the part by the Contract and the Inspection and Test Plan are performed. The Contractor shall notify the Purchaser, in sufficient advance but no fewer than three (3) business days in advance (unless agreed otherwise), of the date at which any such parts of the Work to be later made inaccessible shall be ready for the inspections and tests required by the Inspection and Test Plan and marked “W” or “H”. Such tests and inspections shall be performed by the Contractor, with the Purchaser attending. The Contractor and the Purchaser shall sign a protocol specifying the results of the test or inspection and clearing that part of the Work to be made inaccessible. In the event that the Purchaser fails to attend a test or inspection to which it had been duly invited per the above, the Contractor may carry on with the Work pursuant to the Contract.

In the event the Contractor makes a part of the Work inaccessible without enabling the testing or inspections that may be required under the Contract, the Contractor shall, at its own expense, make that part of the Work accessible in a manner sufficient to perform the test or inspection.

Any Works or Services to be performed by the Contractor and any replacements or repairs to any part of the Work, including Goods, that may result from tests and inspections or failures thereof as described in this Section 27 of the Contract, do not constitute a change to the Work, and the Contractor shall not, in the event, be entitled to any revisions of the Quality Plan, Contract Price, or the Timetable and Execution Plan for the Work. Any and all costs relating to such Services, Works, Goods, and Rights of Use shall be borne by the Contractor, including costs of repeated testing and inspections and costs related thereto.

The determination, specification, and approval of quality requirements on Subcontractors are the responsibility of the Contractor. Therefore, the Contractor shall ensure that its subcontracts require its Subcontractors to follow quality plans, inspection and test plans, and supplier inspection plans drafted by the Contractor and consistent with the Quality Plan agreed to by the Contractor in the Contract.

Unless provided otherwise elsewhere in the Contract, all inspections and testing, including related activities, pursuant to this Section 27 of the Contract shall be performed by the Contractor, and all costs relating to such tests and inspections, including costs of replacement for any parts destroyed in testing, shall be borne by the Contractor and part of the Contract Price.

Nothing in this Section 27 of the Contract relieves the Contractor of any part of its responsibility for the execution and quality of the Work, for guarantees, or any of its other obligations under the Contract.

# ASSEMBLY AND MECHANICAL COMPLETION

The Contractor shall assemble the Work in accordance with the Contract, particularly with the Documentation for Execution of the Project, the Quality Plan, and the Inspection and Test Plan.

Assembly of the Work shall commence upon the signing of the Assembly Readiness Protocol by the Purchaser and the Contractor pursuant to Section 24.7 of the Contract, and shall be governed by the terms and timetables given in the Timetable and Execution Plan for the Work and the Detailed Timetable and Execution Plan for the Work prepared pursuant to Section 24.2 of the Contract.

Mechnical Completion of the Work constitutes an achievement of a state of the Work’s parts, in terms of assembly works, such that Commissioning may begin. As soon as, in the Contractor’s view, a system is mechanically and structurally complete and clean, the Contractor shall notify the Purchaser in writing to that effect. Assembly also includes individual tests provided for in the Contractor’s Quality Plan and Inspection and Test Plan pursuant to Section 27 of the Contract. The primary goal of individual tests is to verify that the system in question has been assembled correctly and its manufacturing and assembly documentation is complete, without using operating media or permanent electrical connections.

The completion of individual tests shall be demonstrated by the relevant attestations and protocols from tests and inspections, issued pursuant to the Inspection and Test Plan, which the Contractor shall prepare and submit to the Purchaser.

Once all individual tests have been successfully completed, the Purchaser and the Contractor shall, without undue delay, sign the Mechanical Completion Protocol for the Work, on the basis of which preparations for the Commissioning of the Work may begin. The drafting of the Protocol shall be the responsibility of the Contractor.

Should the Purchaser refuse to sign the Mechanical Completion Protocol pursuant to Section 29.5 of the Contract, the Purchaser shall notify the Contractor, in writing and no later than five (5) business days from the receipt of the draft Protocol, of the defects and / or incomplete works that, in the Purchaser’s view, prevent the start of Commissioning and are attributable to the Contractor. The Contractor shall then remedy such defects and / or incomplete works and subsequently repeat the procedure given in Section 28.3 and 28.4 of the Contract.

Should the Purchaser, within five (5) business days of receipt, fail to both sign the Protocol and inform the Contractor in writing of defects and / or incomplete works preventing the start of Commissioning, then the Work shall be considered Mechanically Complete on the date of the Purchaser’s receipt of the draft Protocol.

# COMMISSIONING

Once Mechanical Completion of the Work has been achieved and individual tests pursuant to Section 28 of the Contract performed, the Contractor shall commence Commissioning. Commissioning entails the following:

(a)	Preparation for Complex Tests

(b)	Complex Tests, Test “a“

(c)	Performance Test.

The Contractor shall begin preparing individual systems for Complex Tests gradually, so that individual functional systems and operating systems are brought online until the entire Work is commissioned. The Complex Tests and Performance Test need to be performed on the Work as a whole.

The Contractor shall Commission the work in accordance with the Timetable and Execution plan for the Work (Supplement 4 to the Contract) and the Detailed Timetable and Execution Plan for the Work prepared pursuant to Section 24.2 of the Contract. Commissioning shall take place during standard work hours, unless the Parties agree otherwise. The Contractor shall ensure the continuous presence of its authorized staff, the Contractor’s Representative, or the Construction Manager at the Site throughout Commissioning activities so as to ensure reliable and safe operation, the performance of any repairs and procurement of any replacement parts that may be required, and compliance with operating guidelines. The costs of such Contractor activities are part of the Contract Price.

The Contractor hereby consents for the Purchaser to use the Work under construction, from the start date of Commissioning until the signing of the Provisional Acceptance Protocol, as part of the EKY II system technology. The Purchaser’s use of the Work under this Section of the Contract does not relieve the Contractor of its obligation to execute the Work properly and on the timetable, nor of its responsibility for the Work and the risk of damage thereto, excepting any damages the Purchaser may cause as a result of failing to observe the Contractor’s instructions.

All activities and manipulation performed by the Purchaser’s operators between the start of Commissioning and the date of Provisional Acceptance of the Work shall be fully under the control and on the responsibility of the Contractor, and shall be governed exclusively by the Contractor’s instructions.

Throughout the performance of the Contract, all inputs and outputs of the Work’s technological process remain the property of the Purchaser. The Purchaser shall ensure that all inputs required to Commission the Work are made available to the Contractor, in the scope and quality specified in the Contract.

Preparations for Complex Tests

### The Contractor shall commence preparations for Complex Tests in accordance with the Inspection and Test Plan and the Project for Commissioning, gradually on individual operating systems. Preparations for Complex Tests shall finish once all such tests and inspections have been performed and the operational capabilities of all operating systems have been verified.

### Preparations for Complex Tests consist of tests and inspections verifying the functionality of individual devices and functional systems, including the harmonization of such devices’ and systems’ joint operation. Preparations for Complex Tests further include the verification of linkages to the Purchaser’s existing systems. Before commencing such testing, the Contractor shall achieve Mechanical Completion on the systems in question, including individual tests, pursuant to Section 28 of the Contract. The Contractor shall immediately remedy any defects or incomplete works found that would impair the continuation of the Commissioning process, and shall thereafter repeat the test in question. The Contractor shall issue protocols on the completion and results of all tests and inspections.

### The end of preparations for Complex Tests shall be attested to by a Protocol signed by the Parties declaring the Work ready for the Complex Tests. Minor defects and incomplete works not impairing the Complex Tests and acceptable as such to the Purchaser shall be remedied on a timetable agreed in the Complex Tests readiness Protocol. The drafting of the Protocol shall be the responsibility of the Contractor. The Purchaser shall not refuse to sign the Protocol without reason, and shall sign the protocol as soon after receipt as feasible. Should the Purchaser, within five (5) business days of receipt, fail to both sign the Protocol and give the Contractor in writing its reasons for not signing, then for the purposes of the Contract the Protocol shall be considered approved on the date of the Purchaser’s receipt of the draft, and the Contractor may commence the Complex Tests.

Complex Tests, Test “a“

### Once preparations for Complex Tests pursuant to Section 29.1 of the Contract are complete, the Contractor shall perform the Complex Tests as specified in the Inspection and Test Plan, as approved by the Purchaser. The Complex Tests shall verify the functionality of the Work’s systems in different operating modes; pursuant to the Inspection and Test Plan, the inspections and tests included in Test “A” shall also be performed, including the guarantee testing specified in Supplement 2 of the Contract for Test “A”. The Complex Tests are to verify that the technical parameters and functionality agreed in the Contract have been met, particularly those given in the Complex Tests Program and general requirements on Work operability, reliability, safety, and quality.

### The initial operating fluids (e.g. lubricants etc.) shall be delivered by the Contractor and included in the Contract Price.

### As part of Test “A”, an independent entity contracted for that purpose, attended by Contractor representatives, shall perform the Guarantee Measurement, at the date given in the Detailed Timetable and Execution Plan for the Work prepared pursuant to Section 24.2 of the Contract. The Guarantee Measurement shall be performed in accordance with the Project for the Guarantee Measurement, as prepared by the Contractor pursuant to the requirements of Section 2.8 of Supplement 3 to the Contract. The Guarantee Measurement is the Purchaser’s independent verification of the Work’s compliance with the guaranteed parameters given in Supplement 2 of the Contract. The Guarantee Measurement consists of the independent entity performing measurements and assessments of all guaranteed parameters specified for Test “A” under the Contract.

In the event that, for reasons not attributable to the Contractor, the full extent of the Guarantee Measurement of all guaranteed parameters assigned to Test “A” cannot be performed during Test “A”, the Guarantee Measurement of the remaining parameters shall be made during the Trial Operation phase, at a date agreed by the Contractor and the Purchaser.

### In the event that, for reasons attributable to the Contractor, the Complex Tests reveal that the parameters, functionality, and requirements on operability, reliability, safety, and quality specified for the Work in the Contract have not been achieved, the Contractor shall, at its own expense, make all changes and modifications required to achieve those parameters, functionality, and requirements. The Contractor shall notify the Purchaser of the execution of such changes and modifications, and shall repeat the Complex Tests until such time as the technical parameters and requirements agreed have been met, unless agreed otherwise.

### In the event that, for reasons attributable to the Contractor, repeated Complex Tests reveal that the parameters, functionality, and requirements on operability, reliability, safety, and quality specified for the Work in the Contract have not been achieved despite changes and modifications, but the Work’s non-conformity with the Contract-specified parameters, functionality, and requirements is found to be minor and deemed acceptable by the Purchaser insofar that it does not impair the operability, reliability, or safety of the Work, then the Purchaser may authorize the Contractor, in writing, to proceed to the Performance Test. The preceding shall, however, be conditioned on the Contractor’s payment of the contractual penalty specified in Section 42.2 of the Contract. If, for reasons attributable to the Contractor, the limit values of guaranteed parameters are not achieved, the Purchaser may, at its own discretion, withdraw from the Contract and / or draw down against the bank guarantee for the Work.

### Once the Complex Tests have been successfully completed, the Contractor and the Purchaser shall sign a protocol attesting the successful completion of Complex Tests of the Work, including the successful completion of Test “A” and relevant Guarantee Measurements, and authorizing the Work to proceed to the Performance Test stage. All protocols from individual tests shall be appended to the Complex Tests Protocol. The drafting of the Protocol shall be the responsibility of the Contractor. The Purchaser shall not refuse to sign the Protocol without reason, and shall sign the protocol as soon after receipt as feasible. Should the Purchaser, within five (5) business days of receipt, fail to both sign the Protocol and give the Contractor in writing its reasons for not signing, then for the purposes of the Contract the Protocol shall be considered approved on the date of the Purchaser’s receipt of the draft, and the Contractor may commence the Performance Test.

Performance Test

### The Performance Test may commence only once Complex Tests have been successfully completed and the protocol to that effect has been signed, pursuant to Section 29.2.6 of the Contract.

### The Performance Test consists of the continuous, problem-free operation of the Work in the duration of four hundred fifty-six (456) hours, and in all Work operating modes allowed by the Purchaser. The Performance Test is to demonstrate the operability, reliability, safety, and quality of the Contractor’s execution of the Work as required by the Contract, in the scope and specification provided in the Inspection and Test Plan, as approved, and in the Performance Test Program, as approved. The Contractor shall operate the Work without servicing interventions throughout the Performance Test. Once the Performance Test has been completed, the Contractor and the Purchaser shall sign a Protocol to that effect. The drafting of the Protocol shall be the responsibility of the Contractor. The Purchaser shall not refuse to sign the Protocol without reason, and shall sign the protocol as soon after receipt as feasible. Should the Purchaser, within five (5) business days of receipt, fail to both sign the Protocol and give the Contractor in writing its reasons for not signing, then for the purposes of the Contract the Protocol shall be considered approved on the date of the Purchaser’s receipt of the draft.

### In the event that, for reasons not attributable to the Contractor, the Performance Test is interrupted, the Contractor shall continue the Performance Test in accordance with the Purchaser’s instructions once the problem has been resolved.

### In the event that, for reasons attributable to the Contractor, the Performance Test is interrupted for more than twelve (12) hours but the Contractor succeeds in resolving the cause of the interruption, the Purchaser shall, at its own discretion, decide whether the Performance Test is to continue or be repeated whole.

### In the event that, for reasons attributable to the Contractor, the Performance Test reveals that the requirements on Work operability and reliability have not been met, the Contractor shall, at its own expense, make all changes and modifications required to meet those requirements. The Contractor shall notify the Purchaser of the execution of such changes and modifications, and shall repeat the Performance Test until such time as the requirements agreed in the Performance Test Program have been met. In the event that more than two runs of the Performance Test are so required, the Purchaser may request the Contractor to reimburse the Purchaser for all demonstrable expenses related to the third and all subsequent Performance Tests performed; the Contractor, if so requested, shall be obliged to comply.

### In the event that, for reasons attributable to the Contractor, repeated Performance Tests reveal that the requirements given in the Performance Test Program have not been achieved despite the Contractor’s changes and modifications pursuant to Section 29.3.5 of the Contract, but the Work’s non-conformity with the requirements is found to be minor and deemed acceptable by the Purchaser insofar that it does not impair the operability, reliability, safety, or quality of the Work, then the Purchaser may agree, in writing, to accept the Work, provided that all requirements of Section 30 of the Contract are met.

### In the event that, for reasons not attributable to the Contractor, the Performance Test cannot be completed within six (6) months from the date of Mechanical Completion, or within an alternative period agreed by the Purchaser and the Contractor, the Parties shall then agree on an alternative manner of acceptance of the Work in the sense of Section 30 of the Contract. Such an agreement does not, however, relieve the Contractor of the obligation to perform the Performance Test if and when that is made possible by the Purchaser, nor of the Contractor’s other obligations under the Contract.

# WORK PROVISIONAL ACCEPTANCE

The Work shall be Provisionally Accepted, provided that Section 30.2 of the Contract is respected, if and when:

#### The Performance Test pursuant to Section 29.3.2 of the Contract has been successfully completed and the Performance Test Protocol has been signed; or

#### The Performance Test has not been successfully completed, but the Purchaser decided, pursuant to Section 29.3.6 of the Contract, to accept the Work; or

#### The Performance Test has not been completed or was not performed at all, and the Parties have agreed pursuant to Section 29.3.7 of the Contract

#### The Contractor submits to the Purchaser all documentation required by the Contract to be submitted by the end of the Performance Test, or with regard to the state of the Work if (b) above has been applied.

When the conditions for the Provisional Acceptance of the Work given in Section 30.1 of the Contract have been met, the Contractor shall prepare the draft Provisional Acceptance Protocol within seven (7) days of the submission of all required documents and fulfillment of all obligations required of the Contractor at this point by the Contract, and shall submit the Protocol to the Purchaser for approval. The Protocol shall only be accepted if all of the Contractor’s obligations under the Contract (excepting obligations relating to Trial Operation of the Work) have been met, particularly, if the Work has been properly executed as required by the Contract, including Purchaser staff training pursuant to Section 34 of the Contract, submission of documentation required by the Contract, and submission of the Work to the purchaser without legal or material issues (minor, relatively unimportant incomplete works acceptable to the Purchaser insofar as they do not impair the safe and reliable operation of the Work, may be excepted, but shall be listed along with deadlines for their resolution in the Provisional Acceptance Protocol for the Work; in the event of doubt, potential issues shall not be considered minor, unimportant, or immaterial to the safe and reliable operation of the Work).

Upon receipt of the Contractor’s draft, the Purchaser shall, within seven (7) days, either:

#### Sign the Provisional Acceptance Protocol; or

#### Give the Contractor, in writing, its reasons for not signing the Provisional Acceptance Protocol.

#### In the event that the Purchaser fails to acknowledge receipt of the draft Provisional Acceptance Protocol within seven (7) days of receipt, or refuses to sign the Provisional Acceptance Protocol despite the fact that the conditions for the Protocol’s signing have been met and that the Work is operational, then the Provisional Acceptance Protocol for the Work shall, for the purposes of the Contract, be considered signed on the eighth (8th) Days from the Purchaser’s receipt of the draft. At that moment, the Warranty Period shall commence, the liability for damages to the Work shall transfer to the Purchaser, and the Contractor may issue the final invoice for the Work pursuant to the Contract.

An integral part of the Provisional Acceptance (PAC) Protocol for the Work shall be a list of obvious defects and incomplete works found with the Work that the Purchaser considers acceptable pursuant to Section 30.2 of the Contract, including the Contractor’s and Purchaser’s agreement on the manner and timetable for their remedy by the Contractor. Any apparent defects and incomplete works known on the Work as of the date of issue of the Provisional Acceptance (PAC) Protocol may not, in any event, individually or together, impair the safe and economic operation of the Work, nor negatively impact the Work’s performance parameters.

An integral part of the Provisional Acceptance Protocol for the Work shall further be an agreement on the disposal of the Work’s construction Site (i.e., cleanup of the Site, including in particular the complete clearance of open areas, removal or relocation of temporary structures and systems, relocation of machinery, personnel, etc.), including the final disposition of the Site area, unless this would be detrimental to further progress on the Work. No Contractor systems found at the Site as of the date of signing of the Work Provisional Acceptance (PAC) Protocol may limit the safe operation and maintenance of the Purchaser’s systems, including the Work. The Purchaser’s and Contractor’s agreement on the Site shall specify a date for the completion of Site disposal, which shall in no event exceed thirty (30) Days from the signing of the Work Provisional Acceptance (PAC) Protocol. The Contractor shall also submit to the Purchaser documentation of waste disposal practices.

On the day of the Purchaser’s signing of the Provisional Acceptance (PAC) Protocol for the Work, the Work is considered accepted by the Purchaser from the Contractor and the Warranty Period begins. During the Warranty Period, the operation and staffing of the Work are the responsibility and liability of the Purchaser. This does not, however, affect the Contractor’s warranty and responsibility for defects obligations as specified in the Contract.

# TRIAL OPERATION

The Trial Operation phase shall have a duration of twelve (12) months and begins on the date of signing of the Provisional Acceptance Protocol for the Work. Trial Operation shall end upon the signing of the Trial Operation Protocol. The drafting of the Protocol shall be the responsibility of the Contractor. The Purchaser shall not refuse to sign the Protocol without reason, and shall sign the protocol as soon after receipt as feasible. Should the Purchaser, within five (5) business days of receipt, fail to both sign the Protocol and give the Contractor in writing its reasons for not signing, then for the purposes of the Contract the Protocol shall be considered approved and signed and Trial Operation shall be considered ended on the date of the Purchaser’s receipt of the draft.

Trial Operation shall be performed by the Purchaser’s duly trained staff, fully at the Purchaser’s responsibility, and in accordance with the operations guidelines for the Work and potential Contractor instructions. The Contractor’s Representative or a qualified deputy appointed by the Representative shall be continuously present for the first six (6) months of Trial Operation, on business days from 6:00 a.m. to 2 p.m., unless agreed otherwise or unless operational exigencies not attributable to the Purchaser require a more frequent and / or longer presence of the Contractor. Between 2:00 p.m. and 6:00 a.m., the Contractor shall make itself available via telephone. For the remaining six (6) months of Trial Operation, the Contractor’s Representative or a qualified deputy appointed by the Representative shall make themselves available upon the Purchaser’s request. The Contractor’s Representative or a qualified deputy appointed by the Representative shall also be available (on call) outside standard business hours and on public holidays and weekends, so that they are able to present themselves at the Purchaser’s premises within twenty-four (24) hours of the Purchaser’s request, unless agreed otherwise with regard to the severity of the particular situation.

The Contractor’s obligations during Trial Operations that are included in the Contract Price include, in particular:

#### Resolution of operational problems and performance of warranty repairs without delay. During the first three (3) months of Trial Operation, the Contractor’s staff shall perform a personal inspection of the Work no less frequently than 2 times per day.

#### Adjustments and tuning of systems in order to optimize operation in all operating modes, on the basis of changes proposed by the Contractor and approved by the Purchaser, including the amendment of actual-state and related documentation to reflect such changes

#### Preparation of monthly reports on the Work’s Trial Operation and their submission to the Purchaser for approval no later than on the tenth (10th) day of the month following the month being reported on. Such reports shall be based on operational records and systems inspections and shall, among others, list all discovered defects and malfunctions, including measures to resolve them, discuss the load on the Work relative to its capacity, and assess the operation of the Work with regard to public authorities’ requirements. A list of contents for monthly reports shall be prepared by the Contractor and approved by the Purchaser before the first such report is submitted.

#### Preparation of the final Trial Operation assessment report in the scope approved by the Purchaser, and its submission to the Purchaser within fourteen (14) days from the end of Trial Operation

In the event that the Contractor provides instructions to the Purchaser’s operators of the Work during Trial Operation, the correctness of such instructions shall be the responsibility of the Contractor. The Contractor shall not be liable for any damages resulting from a failure on the part of the Purchaser’s staff to follow the Contractor’s instructions, or from failure of Purchaser staff to follow operations and maintenance guidelines for the Work.

The Contractor’s obligations in relation to Trial Operation do not relieve the Contractor of responsibilities relating to the Warranty Period.

# GUARANTEE MEASUREMENT DURING test “B“, WORK FINAL ACCEPTANCE

During the second year of the twenty-four (24) months long Warranty Period for the Work’s technological systems pursuant to Section 43.1.1-i of the Contract, at a date specified by the Purchaser, an independent entity contracted for that purpose shall, in the presence of Purchaser and Contractor representatives, perform and assess Guarantee Measurements of guaranteed parameters allocated to Test “B”. The Guarantee Measurement shall be performed pursuant to the Project for the Guarantee Measurement prepared by the Contractor in accordance with the requirements of Section 2.8 of Supplement 3 to the Contract. The Guarantee Measurement during Test “B” is for the Purchaser to verify retrospectively that the Work achieves the guaranteed parameters agreed in Supplement 2 to the Contract.

In the event that, for reasons not attributable to the Purchaser, Test “B” reveals that the guaranteed parameters given in Supplement 2 to the Contract have not been achieved, the Contractor shall be liable to pay to the Purchaser the contractual penalty specified in Section 42.2 of the Contract, unless the Parties agree on a different procedure (i.e., execution of required changes and modifications). If, even after changes and modifications are made by the Contractor, the limit values of guaranteed parameters given in Supplement 2 to the Contract are not achieved, the Purchaser may, at its own discretion, withdraw from the Contract and / or draw down against the bank guarantee for the Work. All costs related to repeated Guarantee Measurements shall be borne by the Contractor, through reimbursement of the Purchaser against an invoice / tax receipt made out for the amount.

Once Test “B” has been successfully performed and the Warranty Period of twenty-four (24) months pursuant to Section 43.1.1-a (i) of the Contract has expired (or been extended in accordance with the Contract), the Contractor shall submit for the Purchaser’s approval and signing, without undue delay, the Final Acceptance Protocol for the technology section of the Work, whereby the Contractor’s relevant obligations under the Contract shall be considered fulfilled.

Once the Warranty Period of thirty-six (36) months pursuant to Section 43.1.1-a (ii) of the Contract has expired (or been extended in accordance with the Contract), the Contractor shall submit for the Purchaser’s approval and signing, without undue delay, the Final Acceptance Protocol for those technology sections of the Work that fall under the thirty-six (36) month warranty, whereby the Contractor’s relevant obligations under the Contract shall be considered fulfilled.

Once the Warranty Period of sixty (60) months pursuant to Section 43.1.1-a (iii) of the Contract has expired, the Contractor shall submit for the Purchaser’s approval and signing, without undue delay, the Final Acceptance Protocol for the Work, whereby the Contractor’s relevant obligations under the Contract shall be considered fulfilled.

The Purchaser shall not refuse to sign the Protocols pursuant to Section 32.3, 32.4, and 32.5 of the Contract without reason, and shall sign the protocols as soon after receipt as feasible. Should the Purchaser, within five (5) business days of receipt, fail to both sign a Protocol and give the Contractor in writing its reasons for not signing, then for the purposes of the Contract that Protocol shall be considered approved and signed on the date of the Purchaser’s receipt of the draft.

Signing of the Work Final Acceptance Protocol in the sense of Section 32.5 of the Contract does not terminate those of the Contractor’s obligations that are agreed to remain in effect after the Work’s Final Acceptance, including the obligations of Section 56.7 of the Contract.

# EMERGENCY WORKS

In the event that an emergency state arises in relation to the execution of the Work that necessitates protective or repair Works that may not be postponed and aim to prevent damage to the Work or other property or injury to persons, the Contractor shall commence such works immediately.

In the event that the Contractor, despite the state of emergency, is unable or unwilling to commence the Works pursuant to the previous Section without delay, the Purchaser may perform such Works itself or have them performed in whichever manner the Purchaser considers necessary to prevent damage to the Work or other property, other damages, or injury to persons. In that event, the Purchaser shall, without undue delay, notify the Contractor that an emergency has arisen, that Works were done and of the reasons and costs of such Works, and discuss any impact the matter may have on the remainder of the Contract. No such action of the Purchaser shall affect the Contractor’s liability for defects during the Warranty Period.

If such Works are performed by the Contractor pursuant to Section 33.1 of the Contract with notification to the Purchaser, and have arisen for reasons attributable to the Purchaser, the Purchaser shall, once the claim has been documented, reimburse the Contractor for all demonstrable and reasonable expenses that may have arisen to it in relation to such Works, without undue delay but no later than in the Contractor’s usual invoice payment period pursuant to the Contract; the Parties shall also discuss any potential further impacts on the Work. It shall be the duty of the Contractor to demonstrate to the Purchaser that such reasons are attributable to the Purchaser.

If such Works are performed by or on behalf of the Purchaser pursuant to Section 33.2 of the Contract, and have arisen for reasons attributable to the Contractor, the Contractor shall, once the claim has been documented, reimburse the Purchaser for all demonstrable and reasonable expenses that may have arisen to it in relation to such Works, against a special invoice / tax receipt made out by the Purchaser for the amount and pursuant to the Contract, with payment period the same as that of the Contractor’s usual invoice payment period pursuant to the Contract;

# PURCHASER OPERATIONS AND MAINTENANCE STAFF TRAINING

The Contractor shall provide training for the Purchaser’s representatives or representatives of Purchaser-contracted third parties pursuant to Supplement 6 to the Contract; the training shall prepare such staffers for all tasks relating to their job description in the operation and / or maintenance of the Work, and a training protocol shall be signed to attest the same.

# REPLACEMENT PARTS AND RAPID-WEAR PARTS

Replacement parts and rapid-wear parts for Warranty Period operation

The Contractor shall, without undue delay, procure all replacement and rapid-wear parts required to operate the Work for the twenty-four (24) month Warranty Period, or the thirty-six (36) month and / or sixty (60) month Warranty Period for the parts of the Work for which the Contract stipulates such Warranty Period length, and to use such parts to remedy relevant defects on the Work. Such replacement and rapid-wear parts shall be included in the Contract Price.

Replacement parts and rapid-wear parts for operation in the two-year post-warranty period

Supplement 12 shall contain a list, including prices, of recommended replacement and rapid-wear parts for operation of the Work for two years after the end of the Warranty Period, including all information required to identify the part; i.e., name, number of units, replacement frequency for rapid-wear parts, prices, and manner of procurement of the replacement / rapid-wear part in question, i.e., whether the replacement / rapid wear part would be delivered directly by the Contractor or by a Subcontractor. The prices given in this list of replacement and rapid-wear parts for two-year post-warranty operation of the Work shall be final for the Contractor until the end of the Warranty Period pursuant to Section 43.1.1-a (i) and / or 43.1.1-a (ii) of the Contract, depending on the replacement / rapid wear part in question. The Contractor acknowledges the Purchaser’s right to demand, before the expiry of the Warranty Period agreed in the Contract, the signing of a contract for the delivery of replacement and rapid-wear parts for two-year post-warranty operation of the Work, in a scope of the Purchaser’s choice. Deliveries of replacement and rapid-wear parts for the two-year post-warranty operation of the Work are not subject to this Contract, and if a contract is executed for that purpose, it shall be governed by Czech public procurement legislation; the Purchaser shall have no obligation to contract for the delivery of replacement and rapid-wear parts for the two-year post-warranty operation of the Work specifically with the Contractor. In the event that the Purchaser does contract with the Contractor, the Contractor shall extend to the Purchaser the Contractor’s best-customer terms on such replacement and rapid-wear parts deliveries.

The list of recommended replacement and rapid-wear parts for the two-year post-warranty operation of the Work given in Supplement 12 to the Contract shall be further specified by the Contractor and submitted to the Purchaser as part of the Documentation for Execution of the Project.

# POST-WARRANTY SERVICING

The Contractor acknowledges the Purchaser’s right to demand, after the expiry of the Warranty Period agreed in the Contract, the signing of a contract for the provision of post-warranty servicing for the lifetime of the Work. Post-warranty servicing are not subject to this Contract, and if a contract is executed for that purpose, it shall be governed by Czech public procurement legislation (that is, the Purchaser shall have no obligation to contract for post-warranty servicing specifically with the Contractor, particularly if the latter fails to meet the legal requirements; in that event also, however, the Contractor shall provide due cooperation to enable the proper provision of post-warranty servicing).

# SITE AND ASSEMBLY SITES

Information on the state and equipment of the Site is provided in Supplement 1 to the Contract.

The Contractor shall, in its execution of the Work, keep the Site and assembly sites free of all non-essential obstructions, and shall warehouse elsewhere or remove any and all supernumerary materials, waste, and surplus, as well as Construction Equipment that is no longer needed to perform Works or Services. No equipment of the Contractor present at the Site / assembly site shall limit the safe operation and maintenance of the Purchaser’s systems, unless limitation is necessary to execute the Work and agreed in advance between the Parties. The Parties declare that, for the duration of the Work’s execution, the Site (incl. assembly sites) shall be a work site of the Contractor, and the Contractor shall therefore be responsible for the safety of its or its Subcontractors’ personnel present at the Site / assembly site.

The costs of all temporary structures, access roads, and equipment on and off the Site that are necessary to execute the Work, including maintenance and disposal, shall be borne by the Contractor and part of the Contract Price. The Purchaser shall, however, provide the Contractor with required cooperation.

# ADMINISTRATION RULES, OCCUPATIONAL HEALTH AND SAFETY

The organization of and procedures for the exchange of documents between the Parties, as well as the publication, archiving, distribution, revision, and disposal of documents, in the execution of the Contract, shall be governed by the Administration Rules. The Administration Rules shall specify the rules of communication between the Parties and of the handling of documents in the performance of the Contract. The Contractor shall prepare the Administration Rules document pursuant to the requirements given in Section 2.1 of Supplement 3 to the Contract so as to cover all areas in the administration of the Work pursuant to the Contract; the Contractor shall submit the Administration Rules, as approved by the Purchaser, no later than thirty (30) Days after Contract signing.

In its execution of the Work, the Contractor shall adhere to all currently valid legislation and regulations in the areas of Occupational Health and Safety, fire safety, and environment protection, and shall be fully liable for any breaches thereof.

The Contractor shall comply with the rules set out in the “Requirements on Suppliers” document, which is part of Supplement 11 to the Contract.

# WASTE MANAGEMENT, ENVIRONMENT PROTECTION

Throughout the execution of the Work, the Contractor shall be considered the source of all wastes arising from its activities on the Work, including communal waste. The Contractor shall therefore meet its obligations as the Source of Waste Materials in the sense of Act No. 185/2001, the Act on Wastes and Amending Certain Other Acts, as amended, and the legislation implementing that Act.

Waste management (disposal) in relation to the Contract shall be handled by the Contractor, at its own expense. The Contractor shall, upon the Purchaser’s request, document compliance with its obligations under this Section 39 of the Contract.

The Contractor shall keep the Work Site and surroundings, including any roads utilized, clean and orderly. In the event that the Contractor, within a technologically reasonable period from receiving the Purchaser’s Representative’s notice to that effect, fails to remedy a non-conforming situation attributable to the Contractor, the Purchaser may have cleanup performed by other means, in which case all demonstrable, reasonable expenses arising therefrom shall be charged to the Contractor. As regards roads, the Contractor shall maintain cleanliness regularly and with best possible care, so as to minimize the inconvenience or jeopardy to the operation and accessibility of the Purchaser’s other systems or to general traffic.

The Contractor shall handle hazardous wastes and chemicals in relation to the Work in accordance with the requirements of relevant legislation (including, among others, Act No. 185/2001, the Wastes Act, and Act No. 350/2011 on Chemicals and Chemical Compounds).

The Contractor shall ensure that wastes are not stolen or destroyed and that they do not negatively affect the surrounding area.

In the event that the Contractor, in its execution of the Work, discovers the presence of asbestos, the Contractor shall inform the Purchaser without delay, including detailed description of asbestos location and quantity, and shall postpone further works at that location until the asbestos has been disposed of. In that event, the Purchaser shall, without delay, contract a specialist company duly authorized under Czech Republic Law to remove and dispose of asbestos. The Parties shall also take effective measures to minimize the impact on the Timetable and Execution Plan for the Work, and shall handle any such impact pursuant to Section 51 of the Contract.

In the event of a leak of oil or other substances hazardous to the environment, particularly to surface water quality, the Contractor shall, without delay, prevent further leakage and cover all costs of remedying the effects of the leak. The Contractor shall also inform the Purchaser without delay of any such leaks that may occur.

The Purchaser’s Representative, as well as other authorized Purchaser personnel, shall have the right to perform spot inspections of the Contractor’s waste management practices.

The Purchaser may unilaterally order the Contractor to cease works if such works do not conform to environment protection, work safety, and fire safety legislation. In that event, the Contractor may only resume such works once the non-conformity has been remedied, and such interruptions shall not affect the Work’s timetable.

All damages and expenses relating to improper waste management shall be borne by the Contractor. The Contractor shall also be liable to reimburse to Purchaser for any and all fines and remedial measures that may be levied against the Purchaser as a result of faulty waste management practices of the Contractor.

The Contractor shall also comply with Act No. 114/1992, the Nature and Landscape Protection Act, as amended, including the legislation implementing that Act. All damages and expenses relating to Nature and Landscape Protection Act breaches shall be borne by the Contractor. The Contractor shall also be liable to reimburse to Purchaser for any and all fines and remedial measures that may be levied against the Purchaser as a result of the Contractor’s breaches of the Act.

The Contractor shall take adequate steps to ensure that its Work-related equipment (such as vehicles, construction machinery, etc.) does not leak operating fluids into the ground or groundwater, and shall ensure engines are not kept running needlessly. Unless agreed otherwise, the Contractor shall not perform maintenance work on its equipment nor refill operating fluids at the Site.

The Contractor shall comply with its obligations under Act No. 254/2001 where these relate to the Work; in particular, this concerns hazardous substance handling.

# WORK SECURITY

The Contractor shall, at its own risk and expense, provide and maintain any and all lighting, fencing, and security of the Site that may be required for the proper execution and protection of the Work or for the safety of the Purchaser, owners of neighboring properties, throughout the execution of the Work.

# GUARANTEES AND LIABILITIES

# GUARANTEED PARAMETERS

The Contractor hereby warrants and represents that the Work shall, assuming operational guidelines are adhered to, be able to achieve the guaranteed parameters given in Supplement 2 to the Contract.

The Guarantee Measurement to verify that guaranteed parameters have been met shall be performed and evaluated by an independent entity contracted by the Contractor and approved by the Purchaser, attended by Contractor and Purchaser representatives, in accordance with the Project for the Guarantee Measurement, as prepared by the Contractor and approved by the Purchaser, on the timetable given in Supplement 2 to the Contract.

# CONTRACTUAL PENALTIES

In the event that the Contractor breaches its obligations given below in this Section 42 of the Contract, excepting cases pursuant to Section 50 and Section 23.2 of the Contract, the Purchaser may, without limiting its other rights under the Contract, including the right to reimbursement for damages in excess of contractual penalties, demand the payment of a contractual penalty from the Contractor, in which event the Contractor shall be required to pay.

Contractual penalties for Contractor delays

### The milestones subject to a contractual penalty in the event of Contractor delay are as follows:

##### Deadline for submission of Documentation for Execution of the Project

##### Deadline for submission of documentation for request to change work-in-progress

##### Deadline for submission of documentation for Trial Operation approval

##### Deadline for submission of documentation for official approval of the finished Work

##### Deadline for Work Provisional Acceptance

##### Deadlines for remedy of obvious defects and incomplete works at the Work acceptable to the Purchaser, as listed in the Work’s Provisional Acceptance Protocol

##### Deadlines for commencement of defect remedy during Warranty Period pursuant to Section 43.5 of the Contract

##### Deadlines for defect resolution

### In the event that the deadlines for any of the milestones given above are missed for reasons attributable to the Contractor, the Contractor shall be liable to pay to the Purchaser a contractual penalty in the amount of:

##### CZK twenty-five (25) thousand for each day, even begun, of Contractor delay in submitting Purchaser-approved Documentation for Execution of the Project pursuant to Section 2.5.1 of Supplement 3 to the Contract, calculated separately for each of the deadlines given in Section 10.1-p of the Contract.

##### CZK twenty-five (25) thousand for each day, even begun, of Contractor delay in submitting Purchaser-approved documentation for request to change work-in-progress pursuant to Section 2.6 of Supplement 3 to the Contract, in accordance with Section 10.1-q of the Contract.

##### CZK one hundred (100) thousand for each day, even begun, of Contractor delay in submitting documentation for Trial Operation approval pursuant to Section 2.14 of Supplement 3 to the Contract, in accordance with Section 10.1-w of the Contract.

##### CZK twenty-five (25) thousand for each day, even begun, of Contractor delay in submitting documentation for official approval of the finished Work pursuant to Section 2.14 of Supplement 3 to the Contract, in accordance with Section 10.1-x of the Contract.

##### CZK three hundred (300) thousand for each day, even begun, of Contractor delay in Provisional Acceptance of the Work pursuant to Section 30 of the Contract.

##### CZK ten (10) thousand for each day, even begun, of Contractor delay in the remedy of obvious defects and incomplete works at the Work acceptable to the Purchaser, as listed in the Work’s Provisional Acceptance Protocol, pursuant to Section 30.2 of the Contract.

##### CZK one (1) thousand for each full hour of Contractor delay in the commencement of remedy of defects impeding the safe and reliable operation of the Work pursuant to Section 43.5-a of the Contract, for each case of delay in the commencement of remedy of such defects.

##### In the event that the Contractor has, under Section 43.6 of the Contract, been granted a certain period to remove defects impeding the operation of the Work, and the Contractor has failed to remedy such defects in that period, then the Purchaser may demand the Contractor to pay, and the Contractor shall then be required to pay, a contractual penalty in the amount of CZK two hundred fifty (250) thousand for each day, even begun, of Contractor delay in the commencement of remedy of defects impeding the operation of the Work, or in the amount of CZK fifty (50) thousand for each day, even begun, of Contractor delay in the commencement of remedy of defects not impeding the operation of the Work. Remedy of the defect in question does not relieve the Contractor’s obligation to pay any contractual penalties due under this Section 42.1.2-viii of the Contract.

### The burden of proof for delays attributable to the Contractor shall rest with the Purchaser.

### In the event that total contractual penalties levied under Section 42.1.2 of the Contract reach fifteen per cent (15%) of the Contract Price, the Purchaser may withdraw from the Contract without renouncing any of its other rights under the Contract.

Contractual penalties for failure to achieve Work guaranteed parameters

### The Contractor hereby warrants and represents that the Work as delivered shall achieve the guaranteed parameters given in Supplement 2 to the Contract. The guaranteed parameters shall be measured on the terms and timetable specified in the Contract, particularly in Supplement 2 to the Contract. In the event that the Guarantee Measurement performed pursuant to the Contract reveals that guaranteed parameters specified in Supplement 2 to the Contract have not been achieved, the Contractor shall be liable to pay to the Purchaser contractual penalties as specified in Sections 42.2.2 through 42.2.14 of the Contract.

### For failing to meet the guaranteed parameters given in Item 2.1.4 of Supplement 2 to the Contract (TZL separation efficiency in ABS), the Contractor shall be liable to pay a contractual penalty in the amount of CZK 177,000.00 for each 1 percentage point of difference from the guaranteed TZL separation value in the ABS.

### For failing to meet the guaranteed parameters given in Item 2.1.7 of Supplement 2 to the Contract (Emission (concentration) of droplets), the Contractor shall be liable to pay a contractual penalty in the amount of CZK 9,000.00 for each 1 mg/Nm3 above the guaranteed emission  of droplets value.

### For failing to meet the guaranteed parameters given in Items 2.2.1 through 2.2.6 of Supplement 2 to the Contract (Lime Consumption), the Contractor shall be liable to pay a contractual penalty in the amount of CZK 96,700.00 for each, even begun, 1 kg/h by which the weighted actual value exceeds the weighted value of the guaranteed consumption parameters.

### The weighted value of actual consumption shall be determined by the formula:

SV = kmax1 × Smax1 + k1 × S1 + k2 × S2 + k3 × S3 + k4 × S4 + kmax2 × Smax2

Where the individual terms are:

- SV =	Weighted value of actual consumption values

- Smax1 =	Actual consumption recorded in guarantee measurement at maximum power state and using lime var. 1

- kmax1 = 	0.04

- S1 = 	Actual consumption recorded in guarantee measurement at power state 1 and using lime var. 1

- k1 = 	0.12

- S2 = 	Actual consumption recorded in guarantee measurement at power state 2 and using lime var. 1

- k2 = 	0.3

- S3 = 	Actual consumption recorded in guarantee measurement at power state 3 and using lime var. 1

- k3 = 	0.38

- S4 = 	Actual consumption recorded in guarantee measurement at power state 4 and using lime var. 1

- k4 = 	0.12

- Smax2 = Actual consumption recorded in guarantee measurement at power state 1 and using lime var. 2

- kmax2 = 	0.04

### Weighted value of guaranteed consumption values shall be determined using the formula:

GV = kmax1 × Gmax1 + k1 × G1 + k2 × G2 + k3 × G3 + k4 × G4 + kmax2 × Gmax2

Where the individual terms are:

- GV =	Weighted value of guaranteed consumption values

- Gmax1 = Guaranteed consumption at maximum power state and using lime var. 1

- kmax1	= 0.04

- G1 = Guaranteed consumption at power state 1 and using lime var. 1

- k1	= 0.12

- G2 = Guaranteed consumption at power state 2 and using lime var. 1

- k2	= 0.3

- G3 = Guaranteed consumption at power state 3 and using lime var. 1

- k3	= 0.38

- G4 = Guaranteed consumption at power state 4 and using lime var. 1

- k4	= 0.12

- Gmax2 = Guaranteed consumption at power state 1 and using lime var. 2

- kmax2 = 	0.04

### For failing to meet the guaranteed parameter given in Items 2.3.1 of Supplement 2 to the Contract (Capacity of dry hydrate transportation route) the Contractor shall be liable to pay a contractual penalty in the amount of CZK 1,314.00 for every 1 kg / h, which will be less than the guaranteed value of the transport line capacity of thirteen (13) thousand kg / h, increased by an additional CZK 3,066.00 for every 1 kg / h, which the actual value of the transport line capacity will be less than ten (10) kg / h.

### For failing to meet the guaranteed parameter given in Item 2.3.2 of Supplement 2 to the Contract (Electric energy consumption of dry hydrate transportation route), the Contractor shall be liable to pay a contractual penalty in the amount of CZK 42,000.00 for each 1 kW (kW/h) by which the actual value exceeds the value of the guaranteed consumption.

### For failing to meet the guaranteed parameters given in Items 2.4.1 through 2.4.6 of Supplement 2 to the Contract (Electrical energy consumption – at 0% Energo-Gypsum output), including electric power consumption due to the use of pressurized air from the Purchaser’s sources (guaranteed parameters 2.5.1 through 2.5.12), the Contractor shall be liable to pay a contractual penalty in the amount of CZK 126,100.00 for each 1 kW by which the weighted actual value exceeds the weighted value of the guaranteed consumption parameters.

### Weighted value of actual consumption values shall be determined using the formula:

SV = [(kmax1 × SEmax1 + k1 × SE1 + k2 × SE2 + k3 × SE3 + k4 × SE4 + kmax2 × SEmax2) + (kmax1 × SV6max1 + k1 × S V61 + k2 × SV62 + k3 × SV63 + k4 × SV64 + kmax2 × S V6max2) × 0.115 + (kmax1 × SV3max1 + k1 × S31 + k2 × SV32 + k3 × SV33 + k4 × SV34 + kmax2 × SV3max2) × 0.102] × pAP

Where the individual terms are:

- SV =	Weighted value of actual consumption values

- SEmax1 = Actual electric power consumption in kW (kWh/h) recorded in guarantee measurement at maximum power state and using lime var. 1

- SV6max1 = Actual pressurized air consumption at 6 bar in Nm3/h recorded in guarantee measurement at maximum power state and using lime var. 1 (at 0% Energo-Gypsum output)

- SV3max1 = Actual pressurized air consumption at 3.5 bar recorded in guarantee measurement at maximum power state and using lime var. 1 (at 0% Energo-Gypsum output)

- kmax1	= 0.04

- SE1 = Actual electric power consumption in kW (kWh/h) recorded in guarantee measurement at power state 1 and using lime var. 1

- SV61 = Actual pressurized air consumption at 6 bar in Nm3/h recorded in guarantee measurement at power state 1 and using lime var. 1 (at 0% Energo-Gypsum output)

- SV31 = Actual pressurized air consumption at 3.5 bar in Nm3/h recorded in guarantee measurement at power state 1 and using lime var. 1 (at 0% Energo-Gypsum output)

- k1	= 0.12

- SE2 = Actual electric power consumption in kW (kWh/h) recorded in guarantee measurement at power state 2 and using lime var. 1

- SV62 = Actual pressurized air consumption at 6 bar in Nm3/h recorded in guarantee measurement at power state 2 and using lime var. 1 (at 0% Energo-Gypsum output)

- SV32 = Actual pressurized air consumption at 3.5 bar in Nm3/h recorded in guarantee measurement at power state 2 and using lime var. 1 (at 0% Energo-Gypsum output)

- k2	= 0.3

- SE3 = Actual electric power consumption in kW (kWh/h) recorded in guarantee measurement at power state 3 and using lime var. 1

- SV63 = Actual pressurized air consumption at 6 bar in Nm3/h recorded in guarantee measurement at power state 3 and using lime var. 1 (at 0% Energo-Gypsum output)

- SV33 = Actual pressurized air consumption at 3.5 bar in Nm3/h recorded in guarantee measurement at power state 3 and using lime var. 1 (at 0% Energo-Gypsum output)

- k3	= 0.38

- SE4 = Actual electric power consumption in kW (kWh/h) recorded in guarantee measurement at power state 4 and using lime var. 1

- SV64 = Actual pressurized air consumption at 6 bar in Nm3/h recorded in guarantee measurement at power state 4 and using lime var. 1 (at 0% Energo-Gypsum output)

- SV34 = Actual pressurized air consumption at 3.5 bar in Nm3/h recorded in guarantee measurement at power state 4 and using lime var. 1 (at 0% Energo-Gypsum output)

- k4	= 0.12

- SEmax2 = Actual electric power consumption in kW (kWh/h) recorded in guarantee measurement at power state 1 and using lime var. 2

- SV6max2 = Actual pressurized air consumption at 6 bar in Nm3/h recorded in guarantee measurement at maximum power state and using lime var. 2 (at 0% Energo-Gypsum output)

- SV3max2 = Actual pressurized air consumption at 3.5 bar recorded in guarantee measurement at maximum power state and using lime var. 2 (at 0% Energo-Gypsum output)

- kmax2	0.04

- pAP = 1

### Weighted value of guaranteed consumption values shall be determined using the formula:

GV = = [(kmax1 × GEmax1 + k1 × GE1 + k2 × GE2 + k3 × GE3 + k4 × GE4 + kmax2 × GEmax2) + (kmax1 × GV6max1 + k1 × GV61 + k2 × GV62 + k3 × GV63 + k4 × GV64 + kmax2 × GV6max2) × 0.115 + (kmax1 × GV3max1 + k1 × G31 + k2 × GV32 + k3 × GV33 + k4 × GV34 + kmax2 × GV3max2) × 0.102] × pAP

Where the individual terms are:

- GV =	Weighted value of guaranteed consumption values

- GEmax1 = Guaranteed electric power consumption in kW (kWh/h) at maximum power state and using lime var. 1

- GV6max1 = Guaranteed pressurized air consumption at 6 bar in Nm3/h at maximum power state and using lime var. 1 (at 0% Energo-Gypsum output)

- GV3max1 = Guaranteed pressurized air consumption at 3.5 bar at maximum power state and using lime var. 1 (at 0% Energo-Gypsum output)

- kmax1	= 0.04

- G1 = Guaranteed electric power consumption in kW (kWh/h) at power state 1 and using lime var. 1

- GV61 = Guaranteed pressurized air consumption at 6 bar in Nm3/h at power state 1 and using lime var. 1 (at 0% Energo-Gypsum output)

- GV31 = Guaranteed pressurized air consumption at 3.5 bar at power state 1 and using lime var. 1 (at 0% Energo-Gypsum output)

- k1	= 0.12

- GE2 = Guaranteed electric power consumption in kW (kWh/h) at power state 2 and using lime var. 1

- GV62 = Guaranteed pressurized air consumption at 6 bar in Nm3/h at power state 2 and using lime var. 1 (at 0% Energo-Gypsum output)

- GV32 = Guaranteed pressurized air consumption at 3.5 bar at power state 2 and using lime var. 1 (at 0% Energo-Gypsum output)

- k2	= 0.3

- GE3 = Guaranteed electric power consumption in kW (kWh/h) at power state 3 and using lime var. 1

- GV63 = Guaranteed pressurized air consumption at 6 bar in Nm3/h at power state 3 and using lime var. 1 (at 0% Energo-Gypsum output)

- GV33 = Guaranteed pressurized air consumption at 3.5 bar at power state 3 and using lime var. 1 (at 0% Energo-Gypsum output)

- k3	= 0.38

- GE4 = Guaranteed electric power consumption in kW (kWh/h) at power state 4 and using lime var. 1

- GV64 = Guaranteed pressurized air consumption at 6 bar in Nm3/h at power state 4 and using lime var. 1 (at 0% Energo-Gypsum output)

- GV34 = Guaranteed pressurized air consumption at 3.5 bar at power state 4 and using lime var. 1 (at 0% Energo-Gypsum output)

- k4	= 0.12

- GEmax2 = Guaranteed electric power consumption in kW (kWh/h) at power state 1 and using lime var. 2

- GV6max2 = Guaranteed pressurized air consumption at 6 bar in Nm3/h at maximum power state and using lime var. 2 (at 0% Energo-Gypsum output)

- GV3max2 = Guaranteed pressurized air consumption at 3.5 bar at maximum power state and using lime var. 2 (at 0% Energo-Gypsum output)

- kmax2	= 0.04

- pAP = 1

### The contractual penalty for failing to meet the guaranteed parameters given in Items 2.5.1 through 2.5.12 of Supplement 2 to the Contract (Compressed air consumption from Purchaser sources) shall be calculated and included in the contractual penalties pursuant to Section 42.2.7 of the Contract.

### For failing to meet the guaranteed parameter given in Item 2.5.13 of Supplement 2 to the Contract (Average hourly compressed air consumption at 6 bar for dry hydrate transport route at 13 000 kg/h), the Contractor shall be liable to pay a contractual penalty in the amount of CZK 14,500.00 for each 1 Nm3/h by which the actual consumption value exceeds the value of the guaranteed consumption.

### For failing to meet the guaranteed parameter given in Item 2.5.14 of Supplement 2 to the Contract (Average hourly compressed air consumption at 3.5 bar for dry hydrate transport route at 13 000 kg/h), the Contractor shall be liable to pay a contractual penalty in the amount of CZK 12,800.00 for each 1 Nm3/h by which the actual consumption value exceeds the value of the guaranteed consumption.

### For failing to meet the guaranteed parameters given in Items 2.7.1 through 2.7.3 of Supplement 2 to the Contract (Total water consumption – at 0% Energo-Gypsum output), the Contractor shall be liable to pay a contractual penalty in the amount of CZK 97,600.00 for each, even begun, 0.1 t/h by which the weighted value of actual consumption values exceeds the weighted guaranteed consumption value.

### Weighted value of actual values shall be determined using the formula:

SV = (kmax1 × Smax1 + k2 × S2 + kmax2 × Smax2)

Where the individual terms are:

- SV =	Weighted value of actual values

- Smax1 = Actual value at maximum power state and using lime var. 1

- kmax1 = 0.04

- S2 = Actual value at power state 2 and using lime var. 1

- k2	= 0.92

- Smax2 = Actual value at power state 1 and using lime var. 2

- kmax2	= 0.04

### Weighted value of guaranteed values shall be determined using the formula:

GV = (kmax1 × Gmax1 k2 × G2 + kmax2 × Gmax2)

Where the individual terms are:

- GV =	Weighted value of guaranteed values

- Gmax1 = Guaranteed value at maximum power state and using lime var. 1

- kmax1 = 0.04

- G2 = Guaranteed value at power state 2 and using lime var. 1

- k2	= 0.92

- Gmax2 = Guaranteed value at power state 1 and using lime var. 2

- kmax2	= 0.04

### For failing to achieve Work guaranteed availability as given in Item 2.8.1 of Supplement 2 to the Contract (Work Availability) during the 1st year of operation, the Contractor shall be liable to pay a contractual penalty in the amount of CZK 13,800.00 for each, even begun, one (1) hour by which the actual availability of the Work for the year falls short of the guaranteed availability for the year. Furthermore, if the actual value falls short of the limit value given in Item 2.8.1 of Supplement 2 to the Contract, the Purchaser shall, in addition to the contractual penalty, have the right to withdraw from the Contract.

### For failing to achieve Work guaranteed availability as given in Item 2.8.2 of Supplement 2 to the Contract (Work Availability) during the 2nd year of operation, the Contractor shall be liable to pay a contractual penalty in the amount of CZK 61,900.00 for each, even begun, one (1) hour by which the actual availability of the Work for the year falls short of the guaranteed availability for the year. Furthermore, if the actual value falls short of the limit value given in Item 2.8.2 of Supplement 2 to the Contract, the Purchaser shall, in addition to the contractual penalty, have the right to withdraw from the Contract.

### For failing to achieve Work guaranteed availability as given in Item 2.8.2 of Supplement 2 to the Contract (Work Availability) during the 3rd year of operation, the Contractor shall be liable to pay a contractual penalty in the amount of CZK 61,900.00 for each, even begun, one (1) hour by which the actual availability of the Work for the year falls short of the guaranteed availability for the year. Furthermore, if the actual value falls short of the limit value given in Item 2.8.2 of Supplement 2 to the Contract, the Purchaser shall, in addition to the contractual penalty, have the right to withdraw from the Contract.

### Failure to achieve any of the guaranteed parameters given in Supplement 2 to the Contract in Items:

| 2.1.1 | SO2 |
| --- | --- |
| 2.1.2 | TZL behind absorber |
| 2.1.3 | TZL behind LF in dry-chimney operation (behind each boiler) |
| 2.1.5 | HCl |
| 2.1.6 | HF |
| 2.1.8 | Condition of minimum temperature at stack (outlet) |
| 2.1.9 | Hg |
| 2.1.10 | NOx |
| 2.1.11 | CO |
| 2.9 | Noise |

### shall be considered to constitute a material breach of the Contract on the part of the Contractor. In that event, the Purchaser may refuse to accept the Work and / or withdraw from the Contract and / or have the Work brought into compliance with the Contract at the Contractor’s expense, unless the latter is performed by the Contractor pursuant to Section 29.2.4 of the Contract, without limiting the Purchaser’s other rights under the Contract, including the right to be paid contractual penalties and to reimbursement for damages by the Contractor.

### In the event that a particular parameter has been determined during Test “A” to not have been achieved, and therefore a breach of Contract arises, but the defect in question does not impede the safe and reliable operation of the Work, the Purchaser may, at its own discretion, declare the Contractor’s payment of the relevant contractual penalties, as defined above, to be sufficient satisfaction of the Purchaser’s claims in relation to such a defect, and that therefore, once the contractual penalty has been paid, the Purchaser shall thereafter refrain from requiring the Contractor to change or modify the Work so as to remedy that particular defect.

### A final accounting of all contractual penalties for failure to achieve guaranteed parameters shall be made once Test “B” has been performed. In the event that Test “B” measures values inferior to those found during Test “A”, the Contractor shall pay to the Purchaser, in addition to contractual penalties already paid, further contractual penalties corresponding to the difference in the values measured by Test “A” and by Test “B”, to be evaluated separately for each guaranteed parameter. If, however, Test “B” finds values superior to those found by Test “A”, the Contractor shall thereby have no automatic right to be paid bonuses or reimbursements of any kind by the Purchaser.

### In the event that total contractual penalties levied under Sections 42.2.2 through 42.2.14 of the Contract reach fifteen per cent (15%) of the Contract Price, the Purchaser may withdraw from the Contract without renouncing any of its other rights under the Contract, including rights to the payment of contractual penalties, reimbursement of damages, and drawdown against the bank guarantee for the Work.

### In the event that the Guarantee Measurement finds parameter values superior to those specified in the Contract, the Purchaser shall not be required to provide benefits or compensation of any kind to the Contractor.

Contractual penalties for breaches of selected Contractor obligations

### For material breaches of the “Requirements on Suppliers” given in Supplement 11 to the Contract, the Contractor shall be liable to pay a contractual penalty in the amount of CZK five (5) thousand, for each instance of breach; this applies to material breaches for which a penalty is not specified directly in the Requirements on Suppliers.

### For extension of planned shutdowns pursuant to Section 24.3 of the Contract beyond the period set by the Purchaser pursuant to Section 24.4 of the Contract, for reasons attributable to the Contractor, the Contractor shall be liable to pay a contractual penalty in the amount of CZK 10,000.00 for every, even begun, 2 hours of shutdown extension.

### In the event of breach of Section 18 of the Contract attributable to the Contractor, the Purchaser shall be entitled to be paid a contractual penalty in the amount of CZK two hundred (200) thousand per instance of breach, unless the breach in question is deemed completely immaterial.

Common provisions for contractual penalties

### The Purchaser’s entitlement to the payment of contractual penalties shall not be conditioned on any formal steps of the Purchaser other than written notice to the Contractor to the effect that a contractual penalty is being levied, which shall include the rationale and calculation for the penalty.

### The Purchaser may surrender its right to any individual contractual penalty under the Contract, without this affecting any of its other rights thereunder.

### The Contractor shall pay all contractual penalties levied by direct bank transfer into the Purchaser’s account within forty-five (45) days from receipt of the Purchaser’s invoice for the amount. The Purchaser may, particularly if the Contractor fails to pay a duly levied contractual penalty within the period specified, set off its claim to the payment of such penalty against the following or any other subsequent payment due to the Contractor, or else draw down for the amount against the bank guarantee for the Work.

### Unless agreed otherwise elsewhere in the Contract, payment of contractual penalties by the Contractor or alternatively the use of part or the entirety of the bank guarantee for the Work for that purpose by the Purchaser does not relieve the Contractor of any of its other obligations under the Contract.

### The total amount of contractual penalties that may be levied by the Purchaser against the Contractor under this Section 42 of the Contract shall be limited to the equivalent of twenty-five (25) per cent of the Contract Price for the Work. No such limitation shall apply, however, to contractual penalties due as a result of felony, intent, or gross negligence.

### The Contractor shall be liable to reimburse the Purchaser for damages even in excess of the contractual penalties agreed.

# LIABILITY FOR DEFECTS, QUALITY GUARANTEE

The Contractor shall provide the Purchaser with warranty (the Warranty Period) for quality; i.e., shall warrant that the Work as a whole and all parts thereof are free of any and all defects, material and legal. The Work or a part thereof shall be considered defective whenever non-conforming to the results specified in the Contract, the Work’s purpose and use as given in the Contract, or lacks the parameters and properties explicitly agreed in the Contract or required by general legislation and CSN standards effective at the time of the Work’s execution. The Warranty Period, as further specified below in this Section 43 of the Contract, shall commence on the day of Work Provisional Acceptance in the sense of Section 30 of the Contract.

### Materials Warranty

#### The Contractor shall provide the Purchaser with warranty (the Warranty Period) for the proper construction, good quality, correct material choices, and due professional care taken with the Work, in the duration of:

### Twenty-four (24) months on the technology systems of the Work (excepting Work systems under Section 43.1.1-a (ii) below)

### thirty-six (36) months on the following technology systems of the Work:

### interior protection of absorber area, including internal structure and systems

### stirrer plugs

### interior protection of wet flue and chimney sections

### interior protection of pipes and recirculation pumps

### sixty (60) months for the structural portions of the Work.

#### The Contractor shall guarantee the structural quality of all systems in line with the state of technology as of the signing of the Contract, with regard to operational, maintenance, and repair requirements. The Contractor shall take particular care to minimize wear through appropriate selection of materials and finishes.

#### The Contractor shall guarantee a subsystem design lending itself to replacement of rapid-wear parts during operation between planned revisions without system shutdown.

### Completeness Warranty

### The Contractor shall provide the Purchaser with warranty for the completeness and correctness of documentation and sources prepared for and submitted to the Purchaser in the execution of the Work. Deliveries of Goods and performance of Works are part of the Contractor’s obligations even if not explicitly listed in the Contract but demonstrably required for the manufacture, flawless operation, monitoring, and maintenance, and operational and personnel safety of the system in question (regulations, official requirements, etc.).

### Functionality Warranty

#### The Contractor shall provide the Purchaser with a Warranty Period for the correct functioning of the Work in the duration of sixty (60) months.

#### In the event that, during the Warranty Period, it becomes apparent that the Work or a part thereof is incapable of performing its particular function despite professional repair, performed by the Purchaser once materials warranty runs out, then the Contractor shall, at its own expense, take such measures as may be required to restore correct functioning and ensure guaranteed parameters are met. Such measures shall be taken by the Contractor upon consultation with the Purchaser at a suitable time.

### Performance Warranty

### The Contractor shall provide the Purchaser with warranty for the Work’s fulfillment of the guaranteed parameters given in Supplement 2 to the Contract during a twenty-four (24) month Warranty Period.

The Contractor shall not be held liable for duly made claims of warranty during the Warranty Period if it can demonstrate that the defect in question arose in direct result of the Purchaser’s operation of the Work or a part thereof during the Warranty Period in a manner non-compliant with operational guidelines and the technical conditions agreed in the Contract. Until such time as the Purchaser is demonstrated to have been at fault, it shall be assumed that the Contractor is. Without regard for who is at fault for a defect being claimed under warranty, the Contractor shall commence and carry on such Works as are required to remedy the defect, so as to remedy the defect without undue delay. In the event that the Contractor can demonstrate its lack of fault in relation to the defect, the Purchaser shall reimburse the Contractor for all reasonable and demonstrable expenses related to that defect’s remedy.

The Purchaser shall provide the Contractor with all required cooperation, particularly with information on the system’s operation, power states, etc.

Upon request, the Purchaser shall provide the Contractor with access to the Work for purposes of investigating the cause of a defect.

In the event that, during the Warranty Period, it becomes apparent that the Work has defects, the Purchaser may, without limiting its other rights under the Contract:

#### Require defect removal by repair of the Work, if, in the Purchaser’s opinion, the defect in question is repairable; and / or

#### Require defect removal by replacement of the defective parts of the Work, if, in the Purchaser’s opinion, the defect in question is not repairable per (a) above; and / or

#### Require the remedy of any legal defects.

If a defect cannot be removed in any of the ways given in (a) through (c) above, the Purchaser may, at its own discretion and with regard to the nature of the defect:

(i)		Require a reasonable discount of the Contract Price for the Work; or

(ii)	Withdraw from the Contract, in the case of non-removable defects impeding the operation of the Work; or

(iii)	Have defects removed by a third party at the Contractor’s expense.

The Purchaser may change its choice of any of the claim types given above or combine claim types at any time.

Before commencing works to remedy a defect, the Contractor shall report the cause of the defect and have the time and manner of removal (and any counterclaims) approved b the Purchaser.

In the case given in Section 43.4-a and /or 43.4-b of the Contract, the Contractor shall present itself at the site of the defect and commence works to remedy the defect:

- Within twenty-four (24) hours from the defect being reported, for major defects impeding the safe and reliable operation of the Work;

- Within forty-eight (48) hours from the defect being reported, for defects not impeding the safe and reliable operation of the Work, unless agreed otherwise with regard to the nature of the defect.

In the event of defect removal pursuant to Section 43.4 of the Contract, the Contractor shall remedy the defect without delay, but no later than within 30 Days, unless agreed otherwise with regard to the nature of the defect.

In the event that the same defect occurs on the same system three times during the Warranty Period, the Contractor shall, without undue delay, make design changes to the defective system and update the actual-state documentation.

In the event that the Contractor fails to remedy duly claimed defects of the Work within the timeframe given in Section 43.5 through 43.7 of the Contract, or that the Contractor refuses to remedy such defects within that timeframe, the Purchaser may, with prior notice to the Contractor, remedy the defect on its own or have it remedied, at the Contractor’s expense, without limiting any of the Purchaser’s rights under the Contract. The Contractor shall then reimburse the Purchaser for all demonstrable and reasonable costs related to the defect and its removal by or on behalf of the Purchaser, within forty-five (45) days of receipt of the Purchaser’s invoice for the amount. In the event of non-payment of such an invoice, the Purchaser may satisfy its claims by drawing down against the bank guarantee for the Work.

In the event of repair or replacement of defective parts of the Work during the Warranty Period, the Warranty Period for the Work or the relevant part thereof shall be extended by the amount of time for which the Work or its relevant part could not be operated as a result of the defect, provided warranty for the defect was claimed in a proper and timely manner. The Contractor shall, at its own expense, extend the term of the bank guarantee for the Work by a corresponding period – in the event of failure to do so, the Purchaser may, fourteen (14) days before the expiry of the existing bank guarantee for the Work, draw down against that guarantee in full or in part, without limiting its other rights under the Contract. All amounts withdrawn from the bank guarantee in this manner shall be returned to the Contractor without delay once the Contractor submits to the Purchaser a duly extended bank guarantee.

Replaced or newly-installed parts of the Work shall be covered by a Warranty Period of twenty-four (24) months, beginning on the day of replacement / installation.

The acceptance of new deliveries made as part of defect removal and defect warranties relating to such deliveries shall be governed by the relevant Contractor provisions governing the place and manner in which warranty claims may be made and fulfilled.

The removal of any defect shall not affect the Purchaser’s right to be paid contractual penalties and reimbursed for damages.

The periods specified in Section 43.5 and 43.6 of the Contract shall commence on the Day the notice of defect is delivered to the Contractor, where notices sent by e-mail shall be considered delivered on the Day and hour that the e-mail in question was sent, while notices sent by registered post shall be considered delivered on the third business day from the date given on the post office stamp on the sender’s receipt.

None of the provisions of this Section 43 relieve the Contractor of any of its other obligations under the Contract or general legislation.

# REIMBURSEMENT FOR DAMAGES, LIMITATION OF LIABILITY

The Purchaser may require the Contractor to reimburse the Purchaser, and the Contractor shall then be required to pay, for any damages caused to the Purchaser by the Contractor and / or its Subcontractors through a breach of their obligations under the Contract or in relation to the performance of the Contract, including cases of breach under the Contract covered by contractual penalty provisions, and then even in amounts exceeding such contractual penalties. Reimbursement for damages (indemnity) shall be governed by the provisions of Section 2894 et seq. of the Czech Civil Code.

Without regard for the provisions of Section 44.1 of the Contract, the Parties hereby declare (pursuant to Section 2898 (on Limits on Contractual Limitations of Indemnity) of the Czech Civil Code) that the Contractor’s total liability for damages and other costs that may arise in relation to a breach of any one (1) or several contractual or legal obligations by the Contractor in relation to the performance of the Contract, shall not exceed one hundred per cent (100%) of the total Contract Price. The Parties therefore declare the maximum obligation of the Contractor to reimburse for damages and other costs, including the payment of contractual penalties, to be limited by the amount equivalent to one hundred per cent (100%) of the total Contract Price. The Parties further declare that reimbursement for indirect and subsequent damages, lost profits, lost production, lost markets, and / or lost goodwill shall be limited to a maximum of twenty-five per cent (25%) of the total Contract Price.

# REIMBURSEMENT FOR PATENT CLAIMS

Provided that the Purchaser adheres to the provisions of Section 45.2 of the Contract, the Contractor shall reimburse the Purchaser for any and all damages, claims of warranty or other claims, losses, and expenses that may arise to the Purchaser as a result of any breach or claimed breach of any rights, trademarks, copyrights, or other intellectual property rights in relation to the equipment, works, and goods used in the Work or in relation to the same, that may be registered or otherwise valid in the Czech Republic as of the date of signing of the Contract.

In the event any proceedings or claims are brought against the Purchaser as a result of the matters listed in Section 45.1 of the Contract, the Purchaser shall notify the Contractor, in writing, to that effect, and the Contractor shall, at its own expense but the Purchaser’s name, participate in such proceedings and handle such claims and take steps to resolve such proceedings and claims. The Purchaser shall, upon request, provide the Contractor with all reasonable cooperation in handling such claims and proceedings. The Contractor shall reimburse the Purchaser for any and all demonstrable expenses related to such cooperation.

In the event that the Contractor fails to notify the Purchaser, within ten (10) days of receipt of notice per the preceding paragraph, that it has commenced participation in the relevant proceedings or handling of the relevant claims, the Purchaser may enter such proceedings in its own name and require the Contractor to reimburse all demonstrable and reasonable expenses incurred in relation thereto. In the event that the Contractor does notify the Purchaser, within ten (10) days of receipt of notice per the preceding paragraph, that it has commenced participation in the relevant proceedings or handling of the relevant claims, the Purchaser may not subsequently make any statements that might prejudice the defense against such claims or proceedings.

The Party entitled to claims under this Section 45 of the Contract shall use all reasonable means to mitigate any losses or damage that might arise. In the event of failure to do so, the other Party’s responsibility shall be proportionally reduced.

The Contractor’s obligations under this Section of the Contract shall remain in effect vis-à-vis any potential future successors to ownership of the Work, provided that such future successors honor the Purchaser’s obligations under Section 45.2 of the Contract.

# RISK ALLOCATION

# TRANSFER OF OWNERSHIP

The ownership rights for Goods (including documentation) that are part of the Work, unless already held by the Purchaser, shall transfer from the Contractor to the Purchaser upon their documented delivery to the Site at the Purchaser’s premises; for Services and Works, upon their documented acceptance by the Purchaser; for Rights of Use, upon their provision pursuant to the Contract, or upon payment, whichever occurs earlier. Where the Contractor works with or otherwise handles Purchaser property, the Contractor may only do so insofar as it is required to duly execute the Work.

Ownership rights to Contractor Construction Equipment used by the Contractor and /or Subcontractors in the execution of the Work shall remain with the Contractor or the relevant Subcontractor.

Any ownership rights that have not been transferred in accordance with the above shall transfer from the Contractor to the Purchaser upon the signing of the Work Provisional Acceptance Protocol pursuant to Section 30 of the Contract.

# DUE CARE OF THE WORK, TRANSFER OF LIABILITY FOR DAMAGE TO THE WORK

Regardless of ownership rights transfers pursuant to Section 46.1 of the Contract, the risk of damage to the Work, including relevant Purchaser systems, as well as the risks of loss, damage, or any other devaluation, shall transfer from the Contractor to the Purchaser upon the Parties’ signing of the Work Provisional Acceptance Protocol. This does not affect the Contractor’s obligations with regard to warranty.

In the event of damage, loss, or any other devaluation of the Work or any part thereof occurring before risks transfer to the Purchaser, excepting cases specified in Section 50.4 of the Contract, the Contractor shall, at its own expense, remedy the loss, damage, or other devaluation and shall ensure the Work and all parts thereof, including Goods, are returned in all respects to a flawless condition compliant with the terms of the Contract. Without regard for the above, if the damage, loss, or devaluation of the Work or a part thereof is attributable to the Purchaser, the Purchaser shall reimburse the Contractor for all demonstrable, reasonable expenses that may arise to the Contractor in relation with the remedy of the damage in question; in the event that the damage affects other obligations under the Contract, the Parties shall proceed pursuant to Section 51 of the Contract.

The Contractor shall also be liable for all losses and damage to the Work and the Purchaser’s or third parties’ property caused by the Contractor or its Subcontractors during the execution of Works and Services or in relation to the fulfillment of their obligations under the Contract, including obligations pursuant to Section 43 of the Contract.

# PROPERTY LOSS AND DAMAGE, PERSONNEL ACCIDENT AND INJURY, CLAIM SETTLEMENT

The Contractor shall indemnify and hold harmless the Purchaser and its employees for any claims, proceedings, sanctions, or activities ordered in administrative proceedings, as well as for all claims of warranty, damage, or other claims, losses, costs, and expenses of any kind, including costs of legal representation in matters of loss of life or limb or of loss or damage to any property, arising in relation to the execution of the Work for reasons attributable to the Contractor.

The Purchaser shall indemnify and hold harmless the Contractor and its employees for any claims, proceedings, sanctions, or activities ordered in administrative proceedings, as well as for all claims of warranty, damage, or other claims, losses, costs, and expenses of any kind, including costs of legal representation in matters of loss of life or limb or of loss or damage to any property, arising in relation to the execution of the Work for reasons attributable to the Purchaser.

In the event of any proceedings or claims, of warranty or otherwise, against the Purchaser arising for reasons attributable to the Contractor pursuant to Section 48.1 of the Contract, the Purchaser shall notify the Contractor of the matter, in writing, and the Contractor shall, at its own expense but in the Purchaser’s name, take all steps and participate in all negotiations that may be required for the proceedings against the Purchaser to be discontinued (if applicable), or, failing that, for the impact upon the Purchaser to be minimized.

In the event of any proceedings or claims, of warranty or otherwise, against the Contractor arising for reasons attributable to the Purchaser pursuant to Section 48.1 of the Contract, the Contractor shall notify the Purchaser of the matter, in writing, and the Purchaser shall, at its own expense but in the Contractor’s name, take all steps and participate in all negotiations that may be required for the proceedings against the Contractor to be discontinued (if applicable), or, failing that, for the impact upon the Contractor to be minimized.

In the event that the Contractor fails to notify the Purchaser, within seven (7) days of receipt of notification as per the above, to the effect that the Contractor shall proceed pursuant to Section 48.3 of the Contract, then the Purchaser may, at its own discretion, decide to enter such proceedings in its own name but at the Contractor’s expense. In the event that the Contractor does so notify the Purchaser, within seven (7) days of receipt of notice per the above, the Purchaser may not subsequently make any statements that might compromise the Contractor’s position in such proceedings or claims procedures. Depending on the particular situation, the seven (7) day period may be shortened.

In the event that the Purchaser fails to notify the Contractor, within seven (7) days of receipt of notification as per the above, to the effect that the Purchaser shall proceed pursuant to Section 48.3 of the Contract, then the Contractor may, at its own discretion, decide to enter such proceedings in its own name but at the Purchaser’s expense. In the event that the Purchaser does so notify the Contractor, within seven (7) days of receipt of notice per the above, the Contractor may not subsequently make any statements that might compromise the Purchaser’s position in such proceedings or claims procedures. Depending on the particular situation, the seven (7) day period may be shortened.

The Purchaser shall, upon request, provide the Contractor with all reasonable cooperation in proceedings under Section 48.3 of the Contract. The Contractor shall reimburse the Purchaser for any and all demonstrable expenses related to such cooperation.

The Contractor shall, upon request, provide the Purchaser with all reasonable cooperation in proceedings under Section 48.3 of the Contract. The Purchaser shall reimburse the Contractor for any and all demonstrable expenses related to such cooperation.

The Party entitled to claims under this Section 48 of the Contract shall use all reasonable means to mitigate any losses or damage that might arise. In the event of failure to do so, the other Party’s responsibility shall be proportionally reduced.

Before commencing any works, the Parties shall inform each other of relevant risks. The Contractor, through its authorized representative, shall submit a written or electronic risk assessment document to the Purchaser’s Department of Work and Environmental Safety, and shall receive the Purchaser’s risk assessment document on that occasion. This obligation applies equally to the Contractor’s Subcontractors.

The Contractor shall notify the Purchaser, without undue delay, of any injuries that may occur at the workplace. The Contractor shall request the Purchaser’s representative’s cooperation in investigating any workplace injuries that may occur in the execution of the Work.

# INSURANCE

The Contractor shall, at its own expense, enter into and maintain, or cause to be entered into and maintained, a construction and assembly insurance policy (CAR / EAR) in the scope specified below, throughout the construction and / or assembly of the Work, up until Final Acceptance of the technology section of the Work pursuant to Section 32.3 of the Contract.

#### Insurance of Contract subject

#### This insurance shall cover physical losses and damage to the Work and all parts thereof arising before the Purchaser’s Provisional Acceptance of the Work. Between the date of signing of the Provisional Acceptance Protocol and the date of signing of the Final Acceptance Protocol, this insurance shall cover physical losses and damage to the Work and all parts thereof arising from activities of the Contractor and / or its Subcontractors. Such insurance shall not cover physical losses or damage to Site Facilities, Construction Equipment and tools, or construction and other machinery owned by the Contractor or its Subcontractors.

#### Insurance of third-party liability, including cross-liability

#### This insurance shall cover all loss of life or limb suffered by third parties (including Purchaser employees) and losses and damage to third-party property (including Purchaser property and any and all parts of the Work already accepted by the Purchaser) that may arise in relation to the execution of the Work.

The coverage limit for insurance of Purchaser, Contractor, and Subcontractor third-party liability shall be no less than two hundred (200) million Czech koruna, with policyholder participation of no more than ten (10) per cent. The coverage limit for insurance of Contract subject shall be equal to the Contract Price for the Work. In the event the Contract Price changes during the performance of the Contract, in a manner consistent with the Contract, then the Contractor shall change its coverage limit to match the new total Contract Price amount.

All above specified policies shall be entered into with an insurer acceptable to and approved by the Purchaser, on terms acceptable to and approved by the Purchaser; the Purchaser shall not refuse such approval without reason. The Contractor shall submit the full insurance terms, including any contractual terms, for the Purchaser’s approval no later than twenty-one (21) days before the planned date of insurance contract signing. The Purchaser shall adhere to all insurance terms applicable to it and approved by it pursuant to the present paragraph, particularly with regard to work and fire safety provisions.

Construction and assembly insurance shall be entered into with an insurer or insurers of good standing authorized to offer such policies under Act No. 277/2009, the Act on Insurance and Amendment of Certain Other Acts (the Insurance Act), as amended.

The Purchaser and the Contractor’s Subcontractors shall be listed as co-policyholders / co-beneficiaries in all insurance contracts entered into by the Contractor pursuant to Section 49.1 of the Contract.

The Contractor shall, at its own expense, enter into and maintain a professional liability insurance policy throughout the construction and / or assembly of the Work, up until the construction Site has been fully disposed of pursuant to Section 30.4 of the Contract. This policy shall cover all loss of life or limb of third parties (including Purchaser employees) and losses and damage to property (including Purchaser property, including any parts of the Work already accepted by the Purchaser), including net financial losses that may arise in relation to the execution of the Work due to faults with the Contractor’s design or with other professional activities of the Contractor related to the execution of the Work. The coverage limit of the Contractor’s professional liability insurance shall not be less than fifty (50) million Czech koruna.

Before commencing relevant activities, the Contractor shall submit to the Purchaser documentation of its insurance – an insurance certificate (or attestation of insurance, or copy of insurance contract), to demonstrate that it has valid and effective insurance as required. All insurance policies shall provide that the Purhcaser is notified, no later than twenty-one (21) days in advance, of any impending cancellation or changes, by all involved insurers. In the event of the Contractor’s failure to comply with the requirements of this Section 49.7 of the Contract, the Purchaser may, without limiting its other rights under the Contract, enter into the insurance policies required by the Contract, at the Contractor’s expense.

Shipping Insurance

- This insurance shall cover losses and damage to Goods that may arise during transport from the Contractor, its Subcontractors, or manufacturers (including warehousing for periods common in shipping insurance) to the Site. Shipping insurance shall cover one hundred (100) per cent of the value of the Goods being shipped as priced in the Contract.

The Contractor and its Subcontractors are free to enter into any additional insurance related to the Work, over and above the scope of the mandatory insurance required by this Section 49 of the Contract; however, the price for such insurance are the Contractor's expense and cannot increase the Contract price.

None of the provisions of the Section 49 of the Contract relieve the Contractor of its obligations and responsibilities under the Contract.

# FORCE MAJEURE

The Parties shall not be liable for any full or partial failure to meet their respective obligations under the Contract in the event (and to the extent) that such failure is the result of an exceptional, unforeseeable, insurmountable event or circumstance arising independently of the will of the Parties, as defined in Section 2913, Subs. 2 of the Czech Civil Code. Responsibility shall not, however, be excluded in the event that the circumstance arises only when the Party in question is already delayed in meeting its obligations, or that the circumstance arises from the personal circumstances of the Party.

For the purposes of this Section, “force majeure” shall be defined to mean an exceptional, unpreventable event or circumstance that is outside the control of the Party invoking force majeure provisions, that the Party could not reasonably have foreseen when entering into the Contract, and that prevents the Party from fulfilling its obligations under the Contract. Events and circumstances classifiable as force majeure shall include, but not be limited to, war, revolution, wildfire, flood, transport embargo, general strike, and industry-wide strike.

A Party claiming force majeure shall notify the other Party to that effect, including causes, without delay but no later than five (5) Days from the Day the notifying Party became aware of the force majeure situation, via e-mail, with subsequent confirmation by registered post. The same procedure shall be used to notify the other Party when the force majeure situation is no longer in effect. Upon request, the Party claiming force majeure shall suitably document the claim to the other Party.

Without regard for the Contract’s other provisions, the Contractor shall not be held liable for loss or damage to the Work or the Purchaser’s property due to war, civil unrest, or military or paramilitary operations, invasion, civil war, revolution, martial law or military dictatorship, terrorist actions, confiscation, nationalization, and eminent domain, nuclear criticality events, radiation of manmade nuclear origin, irradiation, or shockwave, insofar as such events might impede the execution of the Work in Czech Republic territory, such events being outside the Contractor’s ability to influence and no insurance being normally available against them.

Unless agreed otherwise between the Parties, the execution of Contract obligations shall continue insofar and as long as that is reasonably possible, and the Parties shall further seek alternative means to perform the Contract free of force majeure influence. In the event that force majeure impacts the Contract Price, the Work timetable, or other Contract provisions, the Parties shall commence negotiations to amend the Contract Price, Work timetable, and / or other affected Contract provisions, pursuant to Section 51 of the Contract.

# CHANGES TO THE WORK (CONTRACT)

# CHANGE PROCEEDINGS

Change Requests

### The Purchaser may propose and subsequently require the Contractor to carry out any Changes, provided the terms of this Section 51 of the Contract are observed.

### The Contractor may, during the performance of the Contract, propose to the Purchaser any Changes that the Contractor may consider essential or beneficial to improving the quality and / or economic efficiency of the Work. The Purchaser may, at its discretion, either approve or refuse any such Changes proposed by the Contractor.

### Changes may also arise for other reasons specified in the Contract, particularly those given in Section 3 – Legal Interpretation of the Contract; Section 50 – Force Majeure; and Section 52 – Interruption of Works.

### Without regard to the provisions of Sections 51.1.1 and 51.1.2 of the Contract, no changes or modifications to the Work made essential through a failure of the Contractor to meet its obligations or required to ensure Work compliance with the Contract, but not covered by the types of Changes specified in Section 51.1.3 of the Contract, shall be considered Changes, and shall therefore not affect the Contract Price, the Work timetable, nor any other Contract provisions.

Purchaser-Initiated Changes

### In the event that the Purchaser proposes a Change under Section 51.1.1 of the Contract, the Purchaser shall send a Change Request to the Contractor. The Contractor shall then prepare and, without undue delay but, unless agreed otherwise, no later than within ten (10) days of Change Request receipt, submit to the Purchaser a preliminary calculation of the costs of making the Change and processing the Change Proposal. This Preliminary Calculation shall further contain the Contractor’s proposed timetable for the completion of the Change Proposal and of the Change itself, including preliminary estimates of the impact on the remainder of the Work’s timetable pursuant to the Contract. Once the Purchaser has received the Preliminary Calculation and received any clarification or explanation it may require from the Contractor, the Purchaser shall either:

- Non-bindingly accept the Contractor’s Preliminary Calculation, upon which the Parties shall proceed pursuant to Section 51.2.2 of the Contract; or

- Dispute the Contractor’s Preliminary Calculation and request the Contractor to reassess its proposal within the timeframe specified by the Purchaser. If the Contractor’s revised calculation is acceptable to the Purchaser, the Parties shall then proceed pursuant to Section 51.2.2 of the Contract; otherwise

- The Purchaser shall notify the Contractor of its intention to discontinue Change proceedings.

### Upon receipt of the Purchaser’s decision pursuant to Section 51.2.1-a or 51.2.1-b of the Contract, the Contractor shall, within the period agreed, prepare the Change Proposal. The Contractor shall also prepare a Change Proposal for Changes proposed under Sections 51.3.1 and 51.4.1 of the Contract. The Change Proposal shall contain:

- Detailed description of Change

- Impact of Change on Contract timetable

- Impact of Change on other Purchaser systems

- Impact of Change on Work Contract Price and / or terms of payment under the Contract

- Impact of Change on Work technical guarantees

- Impact of Change on other Contract provisions

- Calculation of costs of making the Change

- Proposed method of Purchaser’s payment for Change costs.

### Upon receipt of the Change Proposal, the Purchaser and the Contractor shall, without delay, reach an agreement on whether or not the proposed Change is to be made. If the Purchaser decides to carry through with the Change, it shall issue a Change Order to the Contractor within seven (7) days of its decision.

### In the event that the Purchaser is unable to decide within seven (7) days, it shall notify the Contractor to that effect, including information on when the Contractor can expect a decision.

### In the event that the Purchaser decides, for whatever reason, not to carry through with the Change, it shall notify the Contractor to that effect. In that event, the Contractor shall be entitled to be reimbursed for any demonstrable costs that may have arisen to it in the preparation of the Change Proposal, such reimbursement not to exceed the amount given by the Contractor in its Preliminary Calculation for the Change Proposal pursuant to Section 51.2.1 of the Contract.

### In the event that the Purchaser and the Contractor fail to reach consensus on a final price for the Change, or on any other matters discussed in the Change Proposal, within the seven (7) day period specified above, then the Purchaser may, regardless, order the Contractor to make the Change via a Preliminary Change Order, which can contain any of or all Changes to the execution of the Work requested by the Purchaser in relation to the Change proceedings at hand. Upon receipt of the Preliminary Change Order, the Contractor shall, without delay and on a technologically reasonable timetable, perform all Changes ordered in the Preliminary Change Order. The Parties shall then attempt to resolve any open issues that may remain in the Change Proposal.

### In the event that the Parties fail to reach agreement within sixty (60) days of the issue of a Preliminary Change Order pursuant to Section 51.2.6 of the Contract, the matter may be further handled pursuant to Section 6 of the Contract. Until such time as the Parties either reach an agreement or an enforceable decision is made pursuant to Section 6 of the Contract on the final price of the Change, and / or on any other matters discussed in the Change Proposal, the Preliminary Change Order shall be considered to constitute a full and accurate definition of the Change.

## Contractor-Initiated Changes

### In the event that the Contractor is proposing a Change pursuant to Section 51.1.2 of the Contract, it shall submit to the Purchaser a written Change Proposal, including the rationale for the proposed Change and the information required by Section 51.2.3 of the Contract.

### Upon the Purchaser’s receipt of the Change Proposal, the Parties shall proceed as described in Section 51.2.4 of the Contract. If, however, the Purchaser decides not to accept the Contractor’s Change Proposal pursuant to this Section 51.3 of the Contract, and therefore to not carry through with the Change, the Contractor shall have no right to claim reimbursement for costs related to the preparation of the Change Proposal.

## General Provisions for Changes

### Changes arising from other changes, particularly from changes in general legislation, due to force majeure, and Works interruptions, shall be carried out, within reason, pursuant to Section 51.2.1 et seq. of the Contract.

### Without regard to any other provisions of the Contract, all Contractor claims of increase in the Contract Price, reimbursement of additional costs, change of timetable, or any other changes to the Contract, whether resulting from Contract provisions or from legislation, shall be made to the Purchaser, in writing, no later than thirty (30) days from the moment that the Contractor becomes aware, or should have become aware if exercising due professional care, of the existence of the particular reason for the increase in the Contract Price, additional costs, timetable changes, or other changes to the Contract. In the event that the Contractor fails to make its claim to the Purchaser within the period given above, all such claims shall be considered null and void and unenforceable against the Purchaser. If the Contractor makes its claims within the period provided, the Parties shall further proceed pursuant to Section 51.3 of the Contract.

### All Changes made to the Contract once signed must comply with Section 222 of Act No. 134/2006, on Public Procurement, as amended.

# INTERRUPTION OF WORKS

The Contractor shall, upon the Purchaser’s written request, interrupt Works for such a period of time (not exceeding six (6) months) and in such a manner as the Purchaser may consider necessary; the Contractor shall duly secure and protect the Work during such Works interruptions.

In the event that an interruption of Works pursuant to this Section 52 of the Contract affects the execution of the Work on the timetable agreed in the Contract, or affects other areas of the Contract, further procedure shall be governed by Section 51 of the Contract. In that event, both Parties shall take reasonable measures to minimize any delay in the Work’s completion. The Purchaser shall reimburse the Contractor for any and all related demonstrable, reasonable costs that may arise to the latter in relation to a Works interruption, particularly costs of warehousing over two (2) months, conservation, refurbishment, capacity shifting, extension of bank guarantees, extension of Contractor personnel presence, insurance, etc.; this unless the Works interruption is due to reasons attributable to the Contractor.

While Works are interrupted, the Contractor may not remove from the Site any Goods, Construction Equipment, or Work components without the Purchaser’s prior written approval.

# WITHDRAWAL FROM THE CONTRACT

DISCRETIONARY PURCHASER WITHDRAWAL FROM THE CONTRACT

### The Purchaser may, at any time and at its own discretion, withdraw from the Contract. Withdrawal under this Section 53.1.1 of the Contract shall be effected via a written notice of withdrawal, which shall be effective upon receipt by the Contractor, unless a later date is specified therein.

### Upon receipt of a Notice of Withdrawal pursuant to Section 53.1.1 of the Contract, the Contractor shall, either immediately or as of the date given in the Notice:

#### Cease all further Works, excepting any the Purchaser may have specified in the Notice of Withdrawal for the sole purpose of protecting the already-completed portions of the Work

#### Terminate all subcontracts

#### Within a mutually-agreed, technologically reasonable timeframe, remove from the Site all Construction Equipment and recall all Contractor and Subcontractor personnel, clear the Site of all surplus materials, detritus, and waste of any kind, then return the Site to the Purchaser in a clean and safe condition

#### Once payments pursuant to Section 53.1.3 of the Contract have been made, then:

##### Hand over to the Purchaser those parts of the Work that have been completed before the withdrawal date

##### Transfer to the Purchaser all rights to completed parts of the Work, particularly to any Goods in place as of the date of withdrawal pursuant to Section 53.1.1 of the Contract such as to which the Contractor may be obligated under other provisions of the Contract to transfer rights to the Purchaser, and, upon the Purchaser’s request, make all reasonable effort to transfer the Contractor’s subcontracts relating to the Work to the Purchaser

##### Submit to the Purchaser all documentation created by the Contractor and its Subcontractors in relation to the Work as of the effective date of the Notice of Withdrawal pursuant to Section 53.1.1 of the Contract such as the Contractor may be obligated under other provisions of the Contract to submit to the Purchaser for a Work in progress.

### In the event of Purchaser withdrawal from the Contract under Section 53.1.1 of the Contract, the Purchaser shall pay to the Contractor:

#### The portion of the Contract Price corresponding to duly completed parts of the Work, including partially-complete parts in proportion to their degree of completion, as of the effective date of the Notice of Withdrawal. Where a portion of the Contract Price cannot be confidently allocated to partially-complete parts of the Work, the Purchaser shall reimburse the Contractor for demonstrable, reasonable expenses instead; and

#### All demonstrable and reasonable expenses that the Contractor may have incurred in the protection of the Work pursuant to Section 53.1.2-a of the Contract; and

#### All demonstrable and reasonable expenses that the Contractor may have incurred from Works pursuant to Section 53.1.2-c of the Contract.

WITHDRAWAL FROM THE CONTRACT FOR CAUSE OF CONTRACTOR MATERIAL BREACH OF CONTRACT

### Without limiting or excluding any of its other rights under the Contract, the Purchaser may, via a written Notice of Withdrawal delivered to the Contractor, withdraw from the Contract for cause in the event of the following material breaches of Contract by the Contractor:

#### In the event that, during the performance of the Contract, the Contractor is liquidated, or that insolvency proceedings are brought against the Contractor in relation to actual or impending Contractor insolvency, or that the Contractor otherwise becomes insolvent; or

#### In the event that the Purchaser (within its rights under the Contract) refuses to approve the Contractor’s Documentation for Execution of the Project prepared pursuant to Section 2.5 of Supplement 3 to the Contract, provided the three revisions (amendments) permitted to the Contractor under the Contract have already been refused; or

#### In the event that the Contractor, in breach of Section 54 of the Contract, assigns or transfers the Contract or any part thereof, or any of its rights or obligations under the Contract or interests in the Contract, to another party; or

#### In the event that the total contractual penalties duly charged to the Contractor reach any of the limits specified in Sections 42.1.4, 42.2.18, and 42.4.5 of the Contract, or that the completion of any of the part-payment milestones given in Supplement 10 to the Contract is delayed by more than ninety (90) days; or

#### In the event that, for reasons attributable to the Contractor, the limit values of guaranteed parameters specified in Supplement 2 to the Contract for the Guarantee Measurements during Tests “A” and “B” remain unachieved despite required changes and modifications having been made by the Contractor pursuant to the Contract; or

#### In the event that the Contractor has its own overdue financial obligations to any of its Subcontractors on the Work in excess of ten (10) per cent of any individual subcontract’s value; or

#### In the event that, despite written notices from the Purchaser to that effect, the Contractor is not proceeding with the Work in accordance with the Contract, or is repeatedly neglecting its obligations under the Contract; or

#### In the event that the Contractor fails to submit to the Purchaser bank guarantees on the terms specified in Section 16 of the Contract; or

#### In the event that the Contractor fails to secure insurance pursuant to Section 49 of the Contract; or

#### In the event of any breaches of Contract originally deemed immaterial, if such breaches are not remedied during an additional, reasonable period provided by the Purchaser for that purpose; or

#### In the event that force majeure conditions pursuant to Section 50 of the Contract persist longer than 180 days.

#### Purchaser withdrawal from the Contract under this Section 53.2.1 of the Contract is effective on the day of delivery of the Notice of Withdrawal to the Contractor, unless the Notice specifies a later date.

### Upon receipt of a Notice of Withdrawal pursuant to Section 53.2.1 of the Contract, the Contractor shall, either immediately or as of the date given in the Notice:

#### Cease all further Works, excepting any the Purchaser may have specified in the Notice of Withdrawal for the sole purpose of protecting the already-completed portions of the Work

#### Terminate all subcontracts, or, if requested by the Purchaser, assign to the Purchaser or to a third party (a replacement contractor) all subcontracts relating to the execution of the Work that the Purchaser may consider essential to the completion of the Work

#### Within a mutually-agreed, technologically reasonable timeframe, remove from the Site all Construction Equipment and recall all Contractor and Subcontractor personnel, clear the Site of all surplus materials, detritus, and waste of any kind, then return the Site to the Purchaser in a clean and safe condition

#### Transfer to the Purchaser all rights to completed parts of the Work, particularly to any Goods in place as of the date of withdrawal pursuant to Section 53.2.1 of the Contract such as to which the Contractor may be obligated under other provisions of the Contract to transfer rights to the Purchaser

#### Submit to the Purchaser all documentation created by the Contractor and its Subcontractors in relation to the Work as of the effective date of the Notice of Withdrawal pursuant to Section 53.2.1 of the Contract such as the Contractor may be obligated under other provisions of the Contract to submit to the Purchaser for a Work in progress.

### In the event of Purchaser withdrawal under Section 53.2 of the Contract, the Purchaser may access the Site and bar the Contractor from further access. Furthermore, the Purchaser may finish relevant works on its own or via a third party. The Purchaser may seize and, in return for payment to the Contractor, use any Construction Equipment that may remain at the Site to complete the Work, for such a period as the Purchaser may consider essential to complete the Work; for the avoidance of doubt, failure to reach agreement on related payments does not affect the Purchaser’s right to use the Construction Equipment in this manner. Once the Work has been completed, or earlier if the state of Works permits, the Purchaser shall return the Construction Equipment to the Contractor, by means of notice to the Contractor to the effect that the Construction Equipment in question is available for pick-up at the Site.

### In the event of Purchaser withdrawal from the Contract under Section 53.2.1 of the Contract, the Purchaser shall pay to the Contractor:

#### The portion of the Contract Price corresponding to duly completed parts of the Work, including partially-complete parts in proportion to their degree of completion, as of the effective date of the Notice of Withdrawal; and

#### Fair-value compensation for any unused or partially-used Goods that may remain at the Site in relation to the Work; and

#### All demonstrable and reasonable expenses that the Contractor may have incurred from Works pursuant to Section 53.2.2-a of the Contract.

#### Any and all Contractor debts vis-à-vis the Purchaser older than the withdrawal date shall be set off against Contractor claims under this Section. Once the Contractor has duly completed its activities pursuant to Section 53.2.2 of the Contract, and once all other claims the Purchaser and the Contractor may have on one another have been duly settled in accordance with the Contract, the Purchaser shall return to the Contractor the bank guarantees provided by the Contractor pursuant to the Contract.

### In the event of Purchaser completion of the Work pursuant to Section 53.2.3 of the Contract, the costs of such Purchaser works shall be calculated. If the sum of the Contractor’s claim under Section 53.2.4 of the Contract and demonstrated, reasonable expenses of the Purchaser on completing the Work exceeds the Contract Price, the Contractor shall be liable to cover the shortfall. If the shortfall exceeds the Contractor’s claim under Section 53.2.4 of the Contract, the Contractor shall compensate the Purchaser for the difference; if the shortfall is less than the Contractor’s claim under Section 53.2.4 of the Contract, the Purchaser shall compensate the Contractor for the difference. The Purchaser and the Contractor shall negotiate, in writing, the manner of calculation of the above, as well as the terms and means of payment.

CONTRACTOR WITHDRAWAL FROM THE CONTRACT

### Without limiting or excluding any of its other rights or means of redress under the Contract, the Contractor may, via a written Notice of Withdrawal delivered to the Purchaser, only withdraw from the Contract for cause in the event of those material breaches of Contract by the Purchaser specified below. The Notice of Withdrawal pursuant to this Section 53.3.1 of the Contract shall be effective upon delivery to the Purchaser, unless a later date is given in the Notice. The Contractor may withdraw:

- In the event that, during the performance of the Contract, the Purchaser is liquidated or bankruptcy proceedings are initiated against the Purchaser; or

- In the event that the Purchaser fails to pay to the Contractor any amount due under the Contract within three (3) months of the due date, despite having been notified in writing of its delay in payment and no fewer than fourteen (14) additional days have passed since the Purchaser’s receipt of such Contractor notice; or

- In the event that force majeure conditions pursuant to Section 50 of the Contract are impeding the execution of the Work, and that the situation persists for more than three hundred sixty (360) Days.

The Parties hereby expressly declare that the Contractor may not withdraw from the Contract for any reasons other than those explicitly stated in the Contract. For the avoidance of doubt, the Parties have agreed to exclude from applicability to the Contract the provisions of Sections 2002 through 2005 of the Czech Civil Code.

### In the event of Contractor withdrawal under Section 53.3.1 of the Contract, the Contractor shall, either immediately or at the date given in the Notice of Withdrawal, proceed in accordance with Section 53.1.2 of the Contract.

### In the event of Contractor withdrawal under Section 53.3.1 of the Contract, the Contractor shall make all payments to the Purchaser specified in Section 53.1.3 of the Contract.

Any and all payments made by the Purchaser to the Contractor under the Contract, including any advance payments, may be set off against any and all amounts owed by the Purchaser to the Contractor under this Section 53 of the Contract.

Termination of the Contract by withdrawal does not terminate (i) any Purchaser claims to payment of contractual fines, reimbursement of damages and other costs and expenses, and other Contractor payments under the Contract; (ii) any claims under warranty for the Work or for hidden defects; (iii) the Contract’s provisions on confidentiality, applicable law, and dispute resolution; or (iv) any other rights and obligations under the Contract obviously intended to survive termination.

In the event of withdrawal from the Contract under this Section 53 of the Contract, the Purchaser shall, once both Parties’ claims under the Contract have been settled, return to the Contractor the Contractor’s bank guarantees submitted pursuant to the Contract.

# CONCLUDING PROVISIONS

# ASSIGNMENT OF CONTRACT AND PROHIBITION OF RETENTION

The Parties have excluded the right of the Contractor to, without prior written permission of the Purchaser, assign the Contract or any part thereof, or any rights or obligations thereunder or any interests therein, to a third party. Likewise, the Parties have excluded the right of the Contractor to, without prior written permission of the Purchaser, offer as collateral to a third party any rights or obligations under the Contract or any interests therein.

The Parties have agreed that the Contractor shall not be entitled to retain, i.e., to exercise its right to retention of, any Goods or future parts of the Work under the Contract, including any documentation.

# ETHICAL CONDUCT BETWEEN THE PARTIES

## Throughout the performance of the Contract, the Parties agree to adhere to the highest ethical and anti-corruption standards.

## To that end, the Purchaser defines “Corrupt Behavior” to mean: The offer, promise, or giving, or the requesting or acceptance of, any undue advantages or benefits, as well as the giving or acceptance of remuneration, unreasonable gifts, acts of hospitality, or direct or indirect reimbursement for expenses to or from any person employed by or acting as a director of any private or public entity (including all persons making decisions on behalf of or acting in any capacity for any private or public entities or organizations), for the purpose of facilitating negotiations, receiving, retaining, or manipulating the course of business, or to gain any other advantage in the award and / or performance of the Contract.

## The Contractor shall ensure that itself and all entities controlled by it (defined as in Sections 74 through 77 of Act No. 90/2012, on Trading Corporations and Associations, as amended) adhere to these anti-corruption provisions.

## The Contractor shall also request that its controlling entity, as defined in Sections 74 through 77 of Act No. 90/2012, on Trading Corporations and Associations, as amended, adhere to these provisions vis-à-vis the Purchaser.

## The Purchaser reserves the right to terminate the Contract in the event that it becomes aware that the Contractor, or an entity controlled by or controlling the Contractor, engaged in Corrupt Behavior in relation to the performance of the Contract, directly or indirectly through a representative, and took no timely and adequate measures to remedy the situation.

# FINAL PROVISIONS

This Contract may only be amended by agreement of the Parties, in the form of numbered, written amendments executed pursuant to Section 222 of Act No. 134/2016, duly signed by the authorized signatories of both Parties, which shall then become an integral part of the Contract. For an amendment to the Contract to be valid, full consensus must be reached on its contents. Therefore, the Parties exclude the applicability of the provisions of Section 1726 (on Lack of Consensus) of the Czech Civil Code, whereby an amendment could otherwise be executed without full consensus.

Validity and Effect

### The Contract shall become valid on the day of signing by both Parties.

### The Contract as a whole enters into effect on the day all of the following conditions are met (hereinafter, the “Effective Date”):

#### A Resolution of Grant of Support is received from the Czech Ministry of the Environment (with approval from the Czech Ministry of Finance) in relation to such a grant from the EU Cohesion Fund under the Operational Programme Environment, Priority Axis 2, and / or on the day of the Purchaser’s issue of a unilateral written declaration pursuant to Section 56.2.3 of the Contract;

#### An enforceable Construction Permit is issued.

### Based on available information, the Purchaser expects the Contract to enter into effect within 30 Days of signing.

### The requirement of Section 56.2.2-a of the Contract on the receipt of a Resolution of Grant of Support from the Czech Ministry of the Environment in relation to a grant from the EU Cohesion Fund under the Operational Programme Environment, Priority Axis 2 may be waived via a written statement of waiver by the Purchaser.

### Without regard for the above, the following provisions become effective upon Contract signing: 1 [Parties to the Contract], 2 [Terms and Definitions], 3 [Legal Interpretation of the Contract], 4 [Contract Documents], 5 [Applicable Law], 6 [Resolution of Disputes], 7 [Notices], 8 [Purpose of the Work], Subsections 9.1 (a), (b), (c) in [Subject of the Contract – the Work], Subsections 10.1 (m), (n), (o), (p) in [Work Timetable], 11 [Contractor’s Obligations in Execution of the Work] to the extent that it applies to the Works and / or Services to be performed before the Effective Date, 12 [Purchaser’s Cooperation] to the extent that it applies to the Works and / or Services to be performed before the Effective Date, 15 [Taxes, Customs, and Fees], 17 [Licenses and Rights of Use to Technical Information], 18 [Information and Contract Documents Security], 19 [Parties‘ Representatives], Subsections 20.1 and 20.2, in [Information Submitted to Purchaser], 21 [Subcontracting], 22 [Standards and Legislation], 23 [Engineering Work, Documentation], 24 [Execution of the Work] to the extent that it applies to the Works and / or Services to be performed before the Effective Date, 38 [Administration Rules, Occupational Health and Safety], 42 [Contractual Penalties], 43 [Liability for Defects, Quality Guarantee], 44 [Reimbursement for Damages, Limitation of Liability], 45 [Reimbursement for Patent Claims], 46 [Transfer of Ownership], 49 [Insurance], 50 [Force Majeure], 51 [Change Proceedings], 52 [Interruption of Works], 53 [Withdrawal from the Contract], 54 [Assignment of Contract and Prohibition of Retention], 55 [Ethical Conduct Between the Parties], 56 [Final Provisions].

With regard to the provisions of Section 56.2 of the Contract, and in the interest of timely completion of the Work pursuant to the Contract, the Parties have agreed that the Contractor shall be allowed to perform, between Contract signing and the Effective Date, those activities listed in Table 2 of Supplement 9 to the Contract. In the event that the Effective Date does not occur within 30 Days of Contract signing, or within some other longer period such as the Parties may agree to, the Purchaser shall pay to the Contractor a portion of the Contract Price corresponding to those of the activities listed in Table 2 of Supplement 9 to the Contract that have been duly performed. Such a payment shall be made by the Purchaser against a Contractor invoice for the amount accompanied by a Purchaser-signed protocol documenting the Purchaser’s acceptance of the works in question, invoice due date to be forty-five (45) days from issue date. The payment of this Invoice shall represent the settlement of all claims, costs, expenses, and damages the Contractor may have thus far incurred in the performance of the Contract.

In the event that the Effective Date of the Contract does not occur within 30 Days of signing, but information available at the time indicates that the Contract will enter into effect at a later date, then the Purchaser shall call a meeting with the Contractor to discuss further procedure, particularly as regards the Work timetable, and while maintaining compliance with Act No. 134/2016, on Public Procurement, as amended, and with the Public Tender Guidelines of the Operational Programme Environment 2014 – 2020. In the event that the Effective Date does not occur within 30 Days of Contract signing, or within some other longer period such as the Parties may agree to, the Purchaser may withdraw from the Contract.

In the event that the Contract becomes effective later than 30 Days after Contract signing, as provided for in Section 56.4 of the Contract, but the payment pursuant to Section 56.3 of the Contract has already been made, then the Deposit and / or a relevant milestone payment as per Supplement 10 of the Contract shall be lowered by the corresponding amount.

Unless incorporated into the Contract, all agreements and understandings between the Parties, oral and written, prior to the Contract and related to the subject of the Contract, shall terminate upon the signing of the Contract.

The Parties have agreed that the following shall survive the signing of the Final Acceptance Protocol for the Work and / or the termination of the Contract: (i) any Purchaser claims to payment of contractual fines, reimbursement of damages and other costs and expenses, and other Contractor payments under the Contract; (ii) any claims under warranty for the Work or for hidden defects; (iii) the Contract’s provisions on confidentiality, applicable law, and dispute resolution; and (iv) any other rights and obligations under the Contract obviously intended to survive Final Acceptance Protocol signing and / or termination.

In the event that any provision of the Contract is found to be or to have become invalid, ineffective, and / or unenforceable, such a provision shall be considered separable from the remainder of the Contract and, as such, shall not affect the validity, effectiveness, and / or enforceability of the Contract as a whole. In such an event, the Parties shall replace the invalid, ineffective, and / or unenforceable provision with an alternative provision that is in line with the purpose of the Contract and the will of the Parties as expressed in the Contract.

The Contractor hereby assumes the risk of change of circumstances in the sense of Section 1765, Subs. 2 (on Right to Resume Negotiations) of the Czech Civil Code. Therefore, the provisions of Section 1765, Subs. 1 (on Right to Resume Negotiations) and Section 1766 (on Restoration of Balance of Rights and Obligations by a Court) of the Czech Civil Code shall be excluded from applicability to the Contract. The Contractor hereby further assumes the risk of change of circumstances in the sense of Section 2620 (on Absolute Amounts and References to Budget) of the Czech Civil Code.

This Contract is executed in four (4) identical counterparts in the Czech language, each of which shall have the legal force of an original. Upon signing, each Party shall receive two (2) counterparts.

The Contract shall be binding in full upon any potential legal successors to either Party.

The Contractor hereby acknowledges that the Purchaser, in the performance of the Contract, needs to process, in a certain necessary scope, the personal data of Contractor personnel including its Sub-contractors involved in the performance of the Contract. The rights of such Contractor personnel in relation to the processing of their personal data by the Purchaser are set forth in the Information Memorandum included in Supplement 13 to the Contract. The Contractor shall make acquainted its personnel including its Sub-contractors with this document.

The Parties declare to have familiarized themselves with the entirety of the Contract, including all Supplements and to have no doubts as to the Contract’s interpretation, and declare the Contract to be an expression of their free will; in attestation of this, the Parties adjoin their signatures.

In ..................... on ............				In ..................... on .............

For the Purchaser:					For the Contractor:

| ............................................................ Ing. Milan Boháček Deputy Chairman of the Board of Directors United Energy, a.s. | ............................................................ |
| --- | --- |
| ............................................................ Ing. Petr Mareš Director United Energy, a.s. | ............................................................ |