# supplement 10

# Roadmap of Key Work Milestones and Prices

The following Supplement 10 - Roadmap of Key Work Milestones and Prices shall be completed/finalized by the contractor/participant and submitted in Volume C10 of the indicative tender/tender (as a supplement to the CONTRACT FOR WORK) in accordance with the purchaser´s instructions for processing of Volume C10 contained in Part 4 of the Tender Documentation.

Roadmap of Key Work Milestones and Prices

Table 1

| SCHEDULE OF ADVANCE PAYMENTS |  |  |  |  |
| --- | --- | --- | --- | --- |
| Payment title | Anticipated term for advance payment invoice issuance | PERCENTAGE CONTRACT PRICE PAYMENT without VAT |  | Performance conditions for payment |
|  |  | % | (in thousand CZK) |  |
| 1st advanced payment | in accordance with Section 14.4 (a) of the CONTRACT | 15 | ................. | In accordance with Section 14.4 (a) of the CONTRACT |

Table 2

| SCHEDULE OF PARTIAL PAYMENTS FOR CONTRACT PRICE |  |  |  |  |
| --- | --- | --- | --- | --- |
| Payment title | Anticipated term for invoice issuance for partial project performance | Percentage CONTRACT PRICE payment without VAT |  | Performance conditions for payment |
|  |  | % | (in thousand CZK) |  |
| 1st Partial payment (based on progress and material WORK implementation) | 8 / 2019 | 2 | ................. | milestone I Handing over approved DOCUMENTATION FOR THE EXECUTION OF THE PROJECT (DESIGN) of the civil part of the WORK (in order of the last finished SO/IO design) and confirmation of milestone performance by the PURCHASER in accordance with the CONTRACT. |
| 2nd Partial payment (based on progress and material WORK implementation) | 11 / 2019 | 3 | ................. | milestone II Handing over approved DOCUMENTATION FOR THE EXECUTION OF THE PROJECT (DESIGN) of the process technology part of the WORK (in order of the last finished PS/DPS) and confirmation of milestone performance by the PURCHASER in accordance with the CONTRACT. |
| 3rd Partial payment (based on progress and material WORK implementation) | 5 / 2020 | 40 | ................. | milestone III Building readiness for process equipment installation (payment after completion of the last implemented SO 01 to 09 and SO 11 to SO 12 and confirmation of milestone performance by the PURCHASER in accordance with the CONTRACT. |
| 4th Partial payment (based on progress and material WORK implementation) | 1 / 2021 | 30 | ................. | milestone IV Signing of protocol on WORK MECHANICAL COMPLETION according to the CONTRACT and confirmation of milestone performance by the PURCHASER in accordance with the CONTRACT. |
| 5th Partial payment (final invoice for WORK) | 7 / 2021 | 25 | ................. | milestone v Signing of protocol on WORK PROVISIONAL ACCEPTANCE according to the CONTRACT and confirmation of milestone performance by the PURCHASER in accordance with the CONTRACT. |
| total without VAT |  | 100% | ................... |  |