PROCUREMENT DOCUMENTS for Public Contract Ref.no. Z2018-033521

Environmental Improvements of TKY II Heating Plant - Wet Desulfurization

PART 4 FORMS AND DETAILED INSTRUCTIONS FOR REQUESTS TO PARTICIPATE AND TENDERS

CONTENTS:

Request to Participate	3

Volume A 	Tender Cover Letter	9

Volume B 	Draft Contract for Work	12

Volume C 	Supplements to the Draft Contract for Work	17

Volume C1 	Purchaser’s Technical Requirements of the Work	18

Volume C2 	Quaranteed Parameters	20

Volume C3 	Documentation	22

Volume C4 	Timetable and Execution Plan for the Work	24

Volume C5 	Purchaser‘s Cooperation	27

Volume C6 	Training	29

Volume C7 	List of Subcontractors	31

Volume C8 	Bank Quarantees for the Work and for the Deposit	33

Volume C9 	Price Specification	35

Volume C10 	Roadmap of Key Work Milestones and Prices	37

Volume C11 	Contractors' Code of Conduct	39

Volume C12 	Contractor’s Technical Specifications	41

Volume C13 	Information on processing of personal data obtained from data subject and from other sources	54

# request to participate

- Participants shall prepare and submit Requests to Participate in accordance with the Procurement Documents, particularly Sections 13 through 16 of Part 1 of the Procurement Documents.

- As part of their Requests to Participate, Participants shall submit documents demonstrating their qualifications according to the Purchaser’s requirements given in Section 14 of Part 1 of the Procurement Documents.

- Qualifications pursuant to Section 14.1.4-a shall be demonstrated using the template of the List of Construction Projects Executed by the Participant over the Past 12 years, which is included below in Addendum 1.

- Requests to Participate shall further specify the Participant’s representative authorized to negotiate with the Purchaser in matters of the Request to Participate, i.e.:

| First and last name: |  |
| --- | --- |
| Address: |  |
| Telephone: | ................................... / mobile: .............................. |
| Fax: |  |
| E-mail: |  |
| Participant Data Box ID |  |

Addendum 1
Template: List of Construction Projects Executed by the Participant over the Past 12 years

- list of construction projects executed by the participant over the past 12 years

Public Contract: Environmental Improvements of TKY II Heating Plant - Wet Desulfurization

The Participant:

……………………… registered address .............................. Business Registration no. ..................,

in compliance with the Purchaser’s request of Section 14, Subs. 14.1.4-a of Part 1 of the Procurement Documents, hereby presents the following construction projects (contracts), duly executed and completed in the past 12 years:

| i) Manufacture and execution as principal supplier of a flue-gas desulfurization project using the wet lime scrubbing method, with a minimum volume of desulfurized gas of 400,000 Nm³/h |  |  |
| --- | --- | --- |
| 1. | Contract name: |  |
|  | Contractor trading name: |  |
|  | Contract location: |  |
|  | Subject of contract: |  |
|  | Monetary value: |  |
|  | Period of execution: |  |
|  | Date of project acceptance by client: |  |
|  | Client trading name: |  |
|  | Client reference (first and last name of client representative able to confirm reference, incl. phone and e-mail): |  |
|  | Brief description of project scope and basic parameters: |  |
| n. | Contract name: |  |
|  | Contractor trading name: |  |
|  | Contract location: |  |
|  | Subject of contract: |  |
|  | Monetary value: |  |
|  | Period of execution: |  |
|  | Date of project acceptance by client: |  |
|  | Client trading name: |  |
|  | Client reference (first and last name of client representative able to confirm reference, incl. phone and e-mail): |  |
|  | Brief description of project scope and basic parameters: |  |
| ii) Manufacture and execution through a third party of a flue-gas desulfurization project using the wet lime scrubbing method, with a minimum volume of desulfurized gas of 400,000 Nm³/h |  |  |
| 1. | Contract name: |  |
|  | Contractor trading name: |  |
|  | Contract location: |  |
|  | Subject of contract: |  |
|  | Monetary value: |  |
|  | Period of execution: |  |
|  | Date of project acceptance by client: |  |
|  | Client trading name: |  |
|  | Client reference (first and last name of client representative able to confirm reference, incl. phone and e-mail): |  |
|  | Brief description of project scope and basic parameters: |  |
| n. | Contract name: |  |
|  | Contractor trading name: |  |
|  | Contract location: |  |
|  | Subject of contract: |  |
|  | Monetary value: |  |
|  | Period of execution: |  |
|  | Date of project acceptance by client: |  |
|  | Client trading name: |  |
|  | Client reference (first and last name of client representative able to confirm reference, incl. phone and e-mail): |  |
|  | Brief description of project scope and basic parameters: |  |
| iii) Execution as principal supplier of a flue-gas desulfurization project using the wet lime scrubbing method, with a minimum volume of desulfurized gas of 400,000 Nm³/h |  |  |
| 1. | Contract name: |  |
|  | Contractor trading name: |  |
|  | Contract location: |  |
|  | Subject of contract: |  |
|  | Monetary value: |  |
|  | Period of execution: |  |
|  | Date of project acceptance by client: |  |
|  | Client trading name: |  |
|  | Client reference (first and last name of client representative able to confirm reference, incl. phone and e-mail): |  |
|  | Brief description of project scope and basic parameters: |  |
| n. | Contract name: |  |
|  | Contractor trading name: |  |
|  | Contract location: |  |
|  | Subject of contract: |  |
|  | Monetary value: |  |
|  | Period of execution: |  |
|  | Date of project acceptance by client: |  |
|  | Client trading name: |  |
|  | Client reference (first and last name of client representative able to confirm reference, incl. phone and e-mail): |  |
|  | Brief description of project scope and basic parameters: |  |
| iv) Execution as subcontractor of complete main system delivery for a flue-gas desulfurization project using the wet lime scrubbing method, with a minimum volume of desulfurized gas of 400,000 Nm³/h |  |  |
| 1. | Contract name: |  |
|  | Contractor trading name: |  |
|  | Contract location: |  |
|  | Subject of contract: |  |
|  | Monetary value: |  |
|  | Period of execution: |  |
|  | Date of project acceptance by client: |  |
|  | Client trading name: |  |
|  | Client reference (first and last name of client representative able to confirm reference, incl. phone and e-mail): |  |
|  | Brief description of project scope and basic parameters: |  |
| n. | Contract name: |  |
|  | Contractor trading name: |  |
|  | Contract location: |  |
|  | Subject of contract: |  |
|  | Monetary value: |  |
|  | Period of execution: |  |
|  | Date of project acceptance by client: |  |
|  | Client trading name: |  |
|  | Client reference (first and last name of client representative able to confirm reference, incl. phone and e-mail): |  |
|  | Brief description of project scope and basic parameters: |  |

The projects listed above meet in full the criteria of the qualification required by Section 14.1.4-a of Part 1 of the Procurement Documents.

In ......……….......... on ....................

.....................................................................

Participant authorized representative full name and signature

# volume A tender cover letter

- As part of Volume A of the Indicative Tender / Tender, the Participant / Contractor shall submit a Tender Cover Letter drafted on the cover letter template given below, dated and signed as required by Section 21.5 / Section 27.3 of Part 1 of the Procurement Documents. If the signatory is a Power of Attorney or authorization holder on behalf of the Participant’s / Contractor’s regular authorized signatory, this Volume A shall further include the Power of Attorney or authorization in question.

Cover Letter Template:

Contractor / procurement process Participant:

| Contractor / Participant trading name: |  |
| --- | --- |
| Contractor / Participant registered address: |  |
| Business Registration no.: |  |
| VAT no.: |  |
| a company registered | in Section ......, File ........ of the Business Registry of the [court name] |
| First and last names of all authorized signatories: |  |
| Signatories‘ manner of representation of the company, as listed in the Business Registry: |  |
| Data Box ID: |  |

To: 	United Energy, a.s. 
2 Teplárenská St., 434 03 Most-Komořany, Czech Republic

On: 	.....................................

Re:	Indicative Tender / Tender for Public Contract 
“Environmental Improvements of TKY II Heating Plant - Wet Desulfurization“
contract no. Z2018-033521

Dear Sirs,

in response to your invitation to submit Indicative Tenders / Tenders of [date of invitation], we undersigned and duly authorized hereby offer to execute the Public Contract “Environmental Improvements of TKY II Heating Plant - Wet Desulfurization“ in the scope and on the terms specified in your Procurement Documents.

The total offered price for the Work (without VAT applicable in CR), as given in our Indicative Tender / Tender no. [no. of tender], is CZK [insert price in CZK].

We hereby declare that, before submitting our Indicative Tender / Tender, we have obtained and familiarized ourselves with all information required to clearly specify the quantities and types of goods, works, and services that are to be delivered in the execution of this Public Contract, as well as with your terms as given in the Procurement Documents, and that these are clear and understood by us.

Our Representative authorized to negotiate with you, the Purchaser, in matters of our Indicative Tender / Tender, shall be:

| First and last name: |  |
| --- | --- |
| Address: |  |
| Telephone: | ................................... / mobile: .............................. |
| Fax: |  |
| E-mail: |  |
| Data Box ID |  |

Our Representative authorized to bid on our behalf in the electronic auction shall be:

| First and last name: |  |
| --- | --- |
| Telephone: | ................................... / mobile: .............................. |
| E-mail: |  |

.........................................................................................

(Participant authorized signatory signature)

Note: text highlighted in turquoise will be adapted by the Purchaser depending on the phase of the procurement process

- Volume A of the Tender shall also include the Security pursuant to Section 28 of Part 1 of the Procurement Documents.

# volume B draft contract for work

- Volume B of the Indicative Tender / Tender shall contain the Participant’s Draft Contract for Work (i.e., the text of the Contract itself, without its Supplements), which has been drafted by the Purchaser and forms the first section of Part 2 of the Procurement Documents.

- The Participant’s changes to the Draft Contract for Work (the Contract text, without Supplements) shall be limited to adding the information required by the Purchaser in Section / Paragraph 1, 7.1-e, 13.1 Draft Contract for Work as Submitted with Tenders, and to signing pursuant to Section 27.3 of Part 1 of the Contract Documents.

- Participants may, as part of their Indicative Tenders, propose minor adjustments to the Draft Contract text, insofar as such may improve clarity and/or transparency (remove ambiguities or errors), and provided that no such adjustment materially impacts the Purchaser / Contracting Authority’s rights or the Participant / Contractor’s obligations.

- The Participant’s potential adjustments as described in the preceding paragraph shall also be submitted in this Volume B of the Indicative Tender as a separate document based on the template given in Addendum 1 to this Volume B.

- Any adjustments the Participant may make to the Draft Contract text shall be interpreted as comments by the Purchaser. On the basis of such comments, the Purchaser may decide to change the Procurement Documents during the Indicative Tender Negotiations phase pursuant to Section 25 of Part 1 of the Procurement Documents. That is, Participants will not be able to stipulate their own changes and amendments to the Contract. In no event shall the Purchaser be bound to accept Participant changes proposed pursuant to Point 2 above.

- In the event the Participant has no adjustments to the Draft Contract to propose, this Volume B shall, in addition to the Draft Contract, contain the Participant’s statement to the effect that the Participant accepts without reservation the text of the Draft Contract for Work proper in the form drafted by the Purchaser and presented as the introduction to Part 2 of the Procurement Documents.

- The Purchaser reserves the right to change the text of the Draft Contract by amending the Procurement Documents during Indicative Tender negotiations pursuant to Section 25 of Part 1 of the Procurement Documents; this includes unilateral changes, if such are deemed necessary on the basis of tender negotiations. The Purchaser explicitly states that such changes may be made in contractual penalty provisions, as well as any other parts of the Draft Contract text affected, if required as a result of a change in the tender evaluation criteria arising from tender negotiations pursuant to Section 34.2 of Part 1 of the Procurement Documents, or as a result of changes, reductions, or expansions of the guaranteed parameters listed in Supplement 2 to the Draft Contract for Work, or of other changes to the award criteria, with the exception of minimum technical requirements, always so as to keep the Contract text in line with the changes in question.

Addendum 1
Template for Draft Contract for Work adjustment proposals

| Participant: ..................................... |  |
| --- | --- |
| Section | Title |
|  | PARTIES TO THE CONTRACT |
|  | TERMS AND DEFINITIONS |
|  | LEGAL INTERPRETATION OF THE CONTRACT |
|  | CONTRACT DOCUMENTS |
|  | APPLICABLE LAW |
|  | RESOLUTION OF DISPUTES |
|  | NOTICES |
| (Example) | Original text: |
| 7.1 (a) | Notices sent via e-mail containing digitized or scanned text to also be hand-delivered, mailed, or delivered by courier no later than three (3) Days after the e-mail in question has been sent, shall be considered delivered on the Day the e-mail is sent; |
|  | Proposed change: |
| 7.1 (a) | Notices sent via e-mail containing digitized or scanned text to also be hand-delivered, mailed, or delivered by courier no later than two (2) Days after the e-mail in question has been sent, shall be considered delivered on the Day the e-mail is sent; |
|  | PURPOSE OF THE WORK |
|  | SUBJECT OF THE CONTRACT – THE WORK |
|  | WORK TIMETABLE |
|  | CONTRACTOR’S OBLIGATIONS IN EXECUTION OF THE WORK |
|  | PURCHASER’S COOPERATION |
|  | CONTRACT PRICE |
|  | TERMS OF PAYMENT |
|  | TAXES, CUSTOMS AND FEES |
|  | BANK GUARANTEES FOR THE WORK AND FOR THE DEPOSIT |
|  | LICENSES AND RIGHTS OF USE TO TECHNICAL INFORMATION |
|  | INFORMATION AND CONTRACT DOCUMENTS SECURITY |
|  | PARTIES‘ REPRESENTATIVES |
|  | INFORMATION SUBMITTED TO PURCHASER |
|  | SUBCONTRACTING |
|  | STANDARDS AND LEGISLATION |
|  | ENGINEERING WORK, DOCUMENTATION |
|  | EXECUTION OF THE WORK |
|  | DELIVERY AND DOCUMENTATION |
|  | SHIPPING, PACKAGING INSTRUCTIONS |
|  | WORK QUALITY ASSURANCE |
|  | ASSEMBLY AND MECHANICAL COMPLETION |
|  | COMMISSIONING |
|  | PROVISIONAL ACCEPTANCE OF THE WORK |
|  | TRIAL OPERATION |
|  | GUARANTEE MEASUREMENT DURING TEST “B“, FINAL ACCEPTANCE OF THE WORK |
|  | EMERGENCY WORKS |
|  | PURCHASER OPERATIONS AND MAINTENANCE STAFF TRAINING |
|  | REPLACEMENT PARTS AND RAPID-WEAR PARTS |
|  | POST-WARRANTY SERVICING |
|  | SITE AND ASSEMBLY SITES |
|  | ADMINISTRATION RULES, OCCUPATIONAL HEALTH AND SAFETY |
|  | WASTE MANAGEMENT, ENVIRONMENTAL PROTECTION |
|  | WORK SECURITY |
|  | GUARANTEED PARAMETERS |
|  | CONTRACTUAL PENALTIES |
|  | LIABILITY FOR DEFECTS, QUALITY GUARANTEE |
|  | COMPENSATION FOR DAMAGE, LIMITATION OF LIABILITY |
|  | REIMBURSEMENT FOR PATENT CLAIMS |
|  | TRANSFER OF OWNERSHIP |
|  | DUE CARE OF THE WORK, TRANSFER OF LIABILITY FOR DAMAGE TO THE WORK |
|  | PROPERTY LOSS AND DAMAGE, PERSONNEL ACCIDENT AND INJURY, CLAIM SETTLEMENT |
|  | INSURANCE |
|  | FORCE MAJEURE |
|  | CHANGE PROCEEDINGS |
|  | INTERRUPTION OF WORKS |
|  | WITHDRAWAL FROM THE CONTRACT |
|  | ASSIGNMENT OF CONTRACT AND PROHIBITION OF RETENTION |
|  | ETHICAL CONDUCT BETWEEN THE PARTIES |
|  | FINAL PROVISIONS |

# Volume C supplements to the draft contract for work

This Volume C – Supplements to the Draft Contract for Work shall be, for the purposes of Indicative Tenders / Tenders, further divided into Volumes C1 through C13, as specified below.

# volume C1 PURCHASER’S TECHNICAL REQUIREMENTS OF THE WORK

- Volume C1 of the Indicative Tender / Tender shall contain the Participant’s draft Supplement 1 – Purchaser’s Technical Requirements on the Work, which has been drafted by the Purchaser and is included in Part 2 of the Procurement Documents.

- Considering that the technical specifications given in Supplement 1 consist of functional and performance requirements in the meaning of Section 89 (1a) of Act No. 134/2016, as amended, the Contractor / Participant may, as part of its Indicative Tender, propose minor adjustments to the text of Supplement 1, insofar as it may improve the clarity and / or transparency of the text, and / or bring Supplement 1 in line with Supplement 12 where the Contractor / Participant offers, on the basis of his know-how and engineering experience, to use Best Available Techniques which technical and economic parameters exceed the requirements of Supplement 1.

- The Participant’s potential adjustments as described in the preceding Point 2 shall also be submitted in this Volume C1 of the Indicative Tender as a separate document in a format equivalent to that used for adjustment proposals in Addendum 1 to Volume B.

- Any adjustments the Participant may make to Supplement 1 shall be discussed during the Indicative Tender Negotiations phase pursuant to Section 25 of Part 1 of the Procurement Documents. In no event shall the Purchaser be bound to accept such Participant changes.

- No Addenda to Supplement 1 shall be submitted with Indicative Tenders / Tenders.

# volume C2 guaranteed parameters

- Volume C2 of the Indicative Tender / Tender shall contain the Participant’s draft Supplement 2 – Guaranteed Parameters, which has been drafted by the Purchaser and is included in Part 2 of the Procurement Documents.

- As part of their Indicative Tenders / Tenders, Participants shall only amend Supplement 2 by adding the information required by the Purchaser in the following sections of Supplement 2:

- Lime consumption, Section 2.2, Subsections 2.2.1 through 2.2.6.

- Dry hydrate route, Section 2.3 b), Subsection 2.3.2

- Electrical energy consumption (power requirement), Section 2.4, Subsections 2.4.1 through 2.4.6

- Compressed air consumption sourced from purchaser, Section 2.5, Subsections 2.5.1 through 2.5.14

- Total water consumption, Section 2.7, Subsections 2.7.1 through 2.7.3.

- Work availability, Section 2.8, Subsections 2.8.1 and 2.8.2.

- Guarantee correction curves (Section 3) to be applied during the Guarantee Measurement. These correction curves define changes in guaranteed parameters (e.g. reagent and electricity consumption, SO2 scrubbing efficiency) at different input condition combinations.

The guarantee correction curves will cover input conditions from 0 to 110% of maximum, further specifying operating range.

Furthermore, balance diagrams for all Guaranteed parameters shall be submitted and balances shall be specified for the production of stabilizate and energo-gypsum (FGD gypsum) - see D3 – Supplement 01 Subsection 5.3.1.

# volume C3 documentation

- Volume C3 of the Indicative Tender / Tender shall contain the Participant’s submission of Supplement 3 – Documentation, which has been drafted by the Purchaser and is included in Part 2 of the Procurement Documents.

- The Participant / Contractor may not make any changes to Supplement 3.

# volume C4 timetable and execution plan for the work

- Volume C4 of the Indicative Tender / Tender shall contain the Participant’s draft Supplement 4 – Timetable and Execution Plan for the Work, which shall be drafted by the Participant pursuant to the Procurement Documents, and shall in particular reflect all of the following Purchaser requirements:

  - The Timetable and Execution Plan for the Work shall describe all activities of the Participant / Contractor and any Subcontractors it may engage in the execution of the Work

  - The Timetable and Execution Plan for the Work shall cover the period from the signing of the Contract for Work until the signing of the Provisional Acceptance protocol for the Work, including the subsequent Trial Operation of the Work, and shall comply with the Purchaser-specified timetable given in Section 10.1 of the Draft Contract for Work included in Part 2 of the Procurement Documents, as well as with the documentation submission timetable given in Section 7 of Supplement 3 to the Contract.

  - The Timetable and Execution Plan for the Work shall contain specific dates particularly for the following:

    - Signing of the Contract for Work (being the starting point of the Timetable and Execution Plan); planned signing date is May 31, 2019

    - Effective date of the contract; planned within 30 calendar days from signing

    - Dates for the fulfillment of the part-payment milestones specified in Section 10 of the Contract

    - Submission of Documentation for Execution of the Project, as prepared by Contractor and approved by Purchaser, pursuant to Supplement 3 to Part 2 of the Procurement Documents

    - Submission of other Work documentation, as prepared by Contractor and approved by Purchaser, pursuant to Supplement 3 to Part 2 of the Procurement Documents

    - Acceptance of custody of the Work construction site

    - Provision of materials, manufacturing, deliveries

    - Progress of construction on and completion of individual structural systems (SO) and technical systems (IO)

    - Progress of assembly on individual functional systems (PS) and functional subsystems (DPS)

    - Expected dates of heating plant shutdown as specified in Sections 24.3 of Part 2 of the Procurement Documents – the Draft Contract for Work

    - Mechanical Completion of individual functional systems / subsystems (PS / DPS), incl. individual system and subsystem (PS / DPS) tests

    - Mechanical Completion of the Work

    - Start and end of preparations for Work Complex Tests

    - Purchaser personnel training on the Work

    - Start and end of Work Complex Tests, including Test “A”

    - Star and end of Work Performance Test

    - Provisional Acceptance of the Work

    - Trial Operation of the Work

  - Individual activities shall be clearly defined as to their specifics, time allotment, beginning and end, and shall include logical linkages with related activities.

  - The Timetable and Execution Plan for the Work shall demonstrate that the Work can be executed according to the Purchaser’s timetable as given in Part 2 of the Procurement Documents.

  - The Timetable and Execution Plan for the Work shall, in particular, respect all procedures specified in the Procurement Documents, e.g. for consultation and Purchaser approval of documentation, etc., as well as the initial and limit conditions for the Work’s execution specified in the Procurement Documents.

  - The Timetable and Execution Plan for the Work shall use days as its unit of resolution.

# volume C5 purchaser‘s cooperation

- Volume C5 of the Indicative Tender / Tender shall contain the Participant’s draft Supplement 5 – Purchaser’s Cooperation, which has been drafted by the Purchaser and is included in Part 2 of the Procurement Documents.

- The Participant / Contractor shall, when preparing its Indicative Tender / Tender, fill in the fields labeled “Required by Contractor” to list its requirements on the Purchaser’s cooperation pursuant to Section 12.8 of the Draft Contract for Work in Part 2 of the Procurement Documents.

# volume C6 training

- Volume C6 of the Indicative Tender / Tender shall contain the Participant’s draft Supplement 6 – Training, which has been drafted by the Purchaser and is included in Part 2 of the Procurement Documents.

- The Participant / Contractor may not make any changes to Supplement 6.

# volume C7 list of subcontractors

- Volume C7 of the Indicative Tender / Tender shall contain the Participant’s draft Supplement 7 – List of Subcontractors, which shall be drafted by the Participant pursuant to the Procurement Documents, and shall in particular reflect all of the following Purchaser requirements:

  - The Participant / Contractor shall provide a list of the subcontractors who shall take part in executing the Work, on the following table template, all fields of which are to be filled:

List of Subcontractors for Goods deliveries related to the Work

| Item | Subcontractor trading name, registered address, and Business Registration no. | Goods to be delivered | Expected volume of subcontracting in CZK without VAT |
| --- | --- | --- | --- |
| 1. |  |  |  |
| 2. |  |  |  |
| n. |  |  |  |

List of Subcontractors for Works and Services deliveries related to the Work

| Item | Subcontractor trading name, registered address, and Business Registration no. | Works / Services to be delivered | Expected volume of subcontracting in CZK without VAT |
| --- | --- | --- | --- |
| 1. |  |  |  |
| 2. |  |  |  |
| n. |  |  |  |

  - The Purchaser / Contracting Authority recommends that no more than 5 subcontractors are proposed by the Participant / Contractor for each individual delivery of Goods, Works, and Services related to the Work.

# volume C8 bank guarantees for the work and for the deposit

- Volume C8 of the Indicative Tender / Tender shall contain the Participant’s draft Supplement 8 – Template Bank Guarantee for the Work and for the Deposit, which has been drafted by the Purchaser and is included in Part 2 of the Procurement Documents.

- In preparing its Indicative Tender, the Participant / Contractor may propose minor changes to Supplement 8 to conform with bank requirements, provided that no such change materially impacts the Purchaser / Contracting Authority’s rights or the Participant / Contractor’s obligations.

- The Participant / Contractor’s proposed changes shall be marked as revisions (visible, in colour, in both the electronic and printed versions of the Indicative Tender, but without markup of formatting changes) or otherwise suitably highlighted relative to the existing text, so as to allow rapid lookup.

- Instead of change proposals pursuant to Points 2 and 3 above, Participants may include in Supplement 8 the proposed bank’s preferred forms specifying the Purchaser / Contracting Authority’s rights and the Participant / Contractor’s obligations, provided these conform with the bank guarantee templates provided in Supplement 8 of the Procurement Documents.

- Any form proposals from the proposed bank or adjustments the Participant may make to Supplement 8 shall be discussed during the Indicative Tender Negotiations phase pursuant to Section 25 of Part 1 of the Procurement Documents. In no event shall the Purchaser be bound to accept such Participant changes or bank forms.

# volume C9 price specification

- Volume C9 of the Indicative Tender / Tender shall contain the Participant’s draft Supplement 9 – Price Specification, which has been drafted by the Purchaser and is included in Part 2 of the Procurement Documents.

- In preparing its Indicative Tender / Tender, the Participant / Contractor shall give its price specifications in the provided Tables 1 and 2 of Supplement 9 to Part 2 of the Procurement Documents.

- The price specification (tables) shall be provided by the Participant / Contractor for all table fields, i.e.:

Table 1
Price Specification of the Work

In this section, the Participant / Contractor shall provide:

- Prices, in CZK exclusive of VAT, for the individual items as listed; these ex-VAT CZK item prices shall correspond to the deliveries covered by that item. Furthermore, the item prices shall include all additional costs related to the execution of the Work in accordance with the Contract; e.g., transport of Goods to the Site, Site Facilities, Trial Operation, etc., attributed on the basis of the individual items’ share on total price.

- Total Contract Price for the Work, in CZK exclusive of VAT.

Table 2
Specification of Contractor Activities
from the date of Contract singing to Contract effective date as given in Section 56.2 of the Contract

Pursuant to Section 56.2 of the Contract, the Contract shall take effect on the day a Resolution of Grant of Support is received from the Czech Ministry of the Environment in relation to such a grant from the EU Cohesion Fund under the Operational Programme Environment, Priority Axis 2 (or on the day of the Purchaser’s issue of a unilateral written declaration pursuant to Section 56.2.3 of the Contract), or on the effective date of the Resolution to Grant a Construction Permit, whichever occurs later.

Pursuant to Section 56.3 of the Contract, the Participant / Contractor shall specify prices for the activities it is required to take between the Contract’s date of signing and effective date so as to remain on the timetable given for Provisional Acceptance of the Work in the Procurement Documents.

# volume C10 roadmap of key work milestones and prices

- Volume C10 of the Indicative Tender / Tender shall contain the Participant’s draft Supplement 10 – Roadmap of Key Work Milestones and Prices, which has been drafted by the Purchaser and is included in Part 2 of the Procurement Documents.

- In preparing its Indicative Tender / Tender, the Participant / Contractor shall specify its proposed timetable in the provided Tables 1 and 2 of Supplement 10 to Part 2 of the Procurement Documents, in accordance with the Purchaser’s requirements given below:

  - The Participant / Contractor shall specify its timetable (advance payment schedule) in the form of the provided Table 1. The only field to be filled in is the Deposit amount, which shall be 15% of the proposed Contract Price for the Work, in CZK and in accordance with Section 13.1 of the Draft Contract for Work in Part 2 of the Procurement Documents.

  - The Participant / Contractor shall specify its timetable (Contract Price part-payment schedule) in the form of the provided Table 2. All fields should be filled in, i.e., the individual 100% prices, in CZK exclusive of VAT, proposed for the completion of the milestone in question, while maintaining the required percentage share of the payment on total price.

# volume C11 Contractors' Code of Conduct

- Volume C11 of the Indicative Tender / Tender shall contain the Participant’s draft Supplement 11 – Contractors' Code of Conduct (being the text of the Purchaser’s internal guideline SM-UE-1805 “United Energy, a.s. Contractor Rules of Conduct”), which has been drafted by the Purchaser and is included in Part 2 of the Procurement Documents in Czech only.

- The Participant / Contractor shall further include in Volume C11 a statement confirming that he accepts the guidline SM-UE-1805 without reservation.

# volume C12 Contractor’s technical specifications

- Volume C12 of the Indicative Tender / Tender shall contain the Participant’s draft Supplement 12 – Contractor’s Technical Specifications, which shall be drafted by the Participant / Contractor pursuant to the Procurement Documents, and shall in particular reflect all of the following Purchaser requirements:

- Supplement 12 – Contractor’s Technical Specifications must allow detailed understanding of the system’s functions and an objective assessment of the technological quality of the Indicative Tender / Tender, as well as an assessment of the degree to which the requirements specified in Supplement 1 – Purchaser’s Technical Requirements on the Work have been met.

- The Contractor’s Technical Specifications shall cover the entire scope of the Work, and shall contain detailed specifications for all deliveries of Goods, Works, and Services, including the quantities of individual components, and across all professional areas.

- In terms of the technological and functional design and construction, provided that the technical requirements on the Work given in Part 3 of the Procurement documents – Technical Requirements are met, the Participant / Contractor shall have complete freedom to apply its best knowledge and engineering experience so as to offer to the Purchaser the best available techniques. Where, in Part 3 of the Procurement Documents (Supplement 1 – Purchaser’s Technical Requirements on the Work), the Purchaser specifies a preference for a particular method of execution or type of equipment, the Participant / Contractor may use a different solution or method that is equivalent in terms of quality and technology. The Participant / Contractor should, as part of Supplement 12, provide its reasons for departing from Purchaser preferences; the Purchaser, however, shall not be required to accept them.

- In the event that the Participant / Contractor’s proposal as given in the Indicative Tender differs from the Purchaser’s technical requirements as given in Part 3 of the Procurement Documents – Technical Requirements (Supplement 1 – Purchaser’s Technical Requirements on the Work), or elsewhere in the Procurement Documents, the Participant / Contractor shall append to Volume C12 a List of Departures from Procurement Documents Requirements.

- If required, the Participant / Contractor shall, at the end of this Volume C12 of the Indicative Tender, further append a list of any comments on the present Supplement (i.e., on the Purchaser’s requirements concerning the preparation of the present Supplement).

- Any Work departures from Procurement Documents requirements and comments the Participant /Contractor may make in the present Supplement shall be discussed during the Indicative Tender Negotiations phase pursuant to Section 25 of Part 1 of the Procurement Documents. In no event shall the Purchaser be bound to accept such departures or comments, unless agreed otherwise during Indicative Tender Negotiations.

- If the Participant / Contractor has no comments, he shall provide a statement to that effect.

- Supplement 12 – Contractor’s Technical Specifications shall be drafted in the following way and shall contain in particular the following:

    - Introduction

- Basic information on:

Structure and contents of Contractor’s Technical Specifications document, including information on any supplements and potential drawings contained therein

Acronyms and abbreviations used

- Basic characteristics of the technical solution proposed for the Work, including the scope in which Purchaser’s existing systems would be utilized and / or adapted

    - Scope of Delivery

- Specification of principal physical deliveries (i.e., of Goods), including special and maintenance equipment, included in the proposed Work price, including identification data and quantities (bill of materials) for individual items, while respecting the requirements and information given below.

The Specifications shall be organized by functional system and by structural system.

For the technology section, including the control systems and electrical technology, Specifications shall consist of a list of machinery and devices. For each machine or device, the minimum specifications required are:

Item number

Name

Number of units (operating and backup)

Type

Manufacturer

The same applies to structure fittings.

A separate list shall be provided of the existing Purchaser systems which the Contractor proposes to use, whether modified or not, as part of the Work, and which shall thereby become a part of the Work.

- Specification of all Works and Services included in the Work price

The specification of Works and Services shall include sufficient information and quantitative data on the services the Participant / Contractor proposes to render in his fulfillment of the requirements for the scope of the Work as given in Section 2.1 through 2.6 of Supplement 1 – Purchaser’s Technical Requirements on the Work.

- Specification of Rights of Use provided as part of the Work

The specification of Rights of Use shall include sufficient information and quantitative data on the usage rights the Participant / Contractor proposes to provide to the Purchaser to fulfill the requirements for the scope of the Work as given in Section 2.7 of Supplement 1 – Purchaser’s Technical Requirements for the Work.

    - Scope of Delivery

A precise delineation of the scope of the Work as proposed by the Participant / Contractor. The basic scope shall be based on that given in Section 3 of Supplement 1 – Purchaser’s Technical Requirements for the Work, but shall further include the Participant / Contractor’s proposed changes such as may be required to integrate certain existing Purchaser systems into the Work, to provide for necessary changes to existing structural or functional systems, or to meet the Contractor’s obligation to provide a Work compatible with its existing surroundings.

    - Description and Documentation of the Technical Concept (Design) of the Work as a Whole

Including design drawings, schematics, and information documenting the technical concept (design) of the Work as a whole and its functional and dynamic properties, particularly information on how the key project requirements and principles, as given in Part 3 of the Procurement Documents – Technical Requirements, are to be met. This shall particularly include:

- Detailed description of the desulfurization process, including the machinery technology used, providing:

Rationale for the choice of concept being proposed

Data on selected levels of reserves and redundancies in machinery and devices essential to the operability and reliability of the system as a whole, incl. manufacturer-quoted reliability data for individual machines

Technical schematics providing volumes of input chemicals, water, gas, and energy and output compounds and their composition (solids, flue gas, energy). Schematics must comply with the Purchaser’s required performance criteria in all guaranteed parameters.

Technical schematics providing volumes of input chemicals, water, gas, and energy and output compounds and their composition (solids, flue gas, energy) for the maximum-power state of the boiler room (PS Max, with lime V1 and V2) and for boiler room Power State 4 (PS 4, with lime V1 and V2), for 75%, 50%, 25%, and 15% flue-gas levels.

All the technical schematics and balances (mass – flue gas – energy) shall be prepared and submitted always for two operating conditions defined as:

- Operation with 0% production of the energo gypsum

- Operation with 100% production of the dewatered energo gypsum in the quality according to chapter 5.3.1 of D3 – Supplement 01

intermittency/batch processing of the stabilizate production and its formula according to the conditions of Supplement 1 – Purchaser’s Technical Requirements on the Work.The Purchaser / Contracting Authority reserves the right to specify (amend specification of) the humidity and the composition of the mixture during the negotiation procedure depending on the ongoing research.

Statement of the limit (extreme) values of the limestone purity in relation to the flue gas composition and quantity, required for the quality of the produced dewatered energo gypsum to comply with chapter 5.3.1 D3 – Supplement 01.

P&I diagrams showing main regulation circuits, systems, balance and measurement devices, key pipe diameters, links to existing systems.

- Description of basic Work construction and spatial disposition, including general plan and overview sketches showing the spatial configuration and space demand of technological devices.

- Work links to existing systems – description, including connection points

- Description of changes and modifications proposed to existing systems and structural systems

- Concept for transition from existing desulfurization system – description of transition procedure incl. required temporary measures and timetable of the individual transition steps. In particular, the following must be clearly defined:

Period of time from loss of operability of existing desulfurization system (if inoperability cannot be avoided to execute or connect the Work) to full operability of the Work

Period of time of the full shutdown of the heating plant (boilers K6 through K10)

- Functional and structural systems making up the Work

- Work performance characteristics as a whole, incl. energy and media consumption (for guaranteed parameters, can be given by reference to Supplement 3 – Guaranteed Parameters). The characteristics shall be always stated for 0% production of energo gypsum and for 100% production of energo gypsum.

- List of waste products, including quantity and quality of media produced

- Data on process flexibility – system output regulation range and achievable dynamics of change

- Description of operation, staffing, and control procedures for the Work, incl. data on:

Numbers and expertise of required operations and maintenance staff for round-the-clock operation in 3 shifts, separately for each normal-operation shift

Operator interface points

Degree of automation

Necessary local manipulation (by operating mode)

- Description of power-up and power-down process, normal and emergency

- Description of measures to ensure operability in winter

- Measures taken to ensure required service life, incl. protection of interior and exterior surfaces from erosion and corrosion for all key machinery, devices, pipes, flues, tanks, magazines, etc.

Further, which components would need replacement during expected service life, at which points in time, expected time and costs of such repair.

- Description of maintenance procedures

Including:

Special repair and maintenance procedures

Recommended maintenance model (annual revisions, cycles, etc.) and proposed procedures in repair work

Any special devices and systems required for repair and maintenance that would be supplied with the Work

- Environmental care

Description of Work environmental impact

- Fire safety

Work technical design with regard to fire safety

Structural system fire safety characteristics

- Occupational Health and Safety

OHS characteristics of technology, control system, electrical systems

Sources of hazards to personnel health and safety

Manner of risk mitigation to meet requirements

Personnel and work environment protection from hazardous substances

    - Detailed Information, Descriptions, Calculations, and Drawings

Machinery and Related Equipment

Detailed information on machine technology and related equipment shall contain, in particular:

NOTE: May be provided by reference to the Questionnaires if the data required below is also included there.

- Basic data on key machinery and devices, e.g. nominal parameters and operational ranges, design characteristics and power curves, efficiencies and power consumption at nominal output and over operating range, cooling, other consumption, rpm, regulation type, drive specification, nominal drive output

- Materials (for the various parts), including CSN or other standards applied, for each device, pipe system, etc. For pipes and flues, also corrosion reserves, thickness, etc.

- Also required are material quality tables, including material composition, their key properties, or their Czech equivalents.

- Reasons for material selection shall be provided (by comparison of suitable alternatives) particularly for:

Flue protection or lining materials

Absorber protection or lining materials

Unlined metals inside flues and absorbers

Flue liquid drainage system

Suspension pumps

Suspension pipes and armatures

- List of thermal insulation and protective paint used, presented in a concise table including scope, material, insulation thickness, etc.

- Internal corrosion protection, wherever used.

Information shall be provided concerning use, reliability, and suitability of proposed corrosion protection solution, with reference to a system successfully in long-term operation, including identification of manufacturer and his experience. It is also necessary to provide information on need for repairs, including frequency, time requirements, and service lives.

- Operating fluid quantities and technical data.

    - Control System

Technical specifications for the control system shall contain, in particular:

Drawings of complete control system configuration, denoting locations of key components and connections to existing control system

Description of proposed control system configuration, including description and technical data for main components, field instrumentation

List of measurement points

Description of linkages to existing Purchaser systems and electrical systems

Layout of all systems

Description of proposed field instrumentation and auxiliary devices

Drawings and description of power supply

    - Electrical Systems

Technical specifications for electrical systems shall contain, in particular:

Description of overall electrical system concept, including wiring and description of functional links to existing Purchaser systems

Single-pole schematic of Work proper consumption, including power supply and control system power supply proposed

Description of key system components (transformers, switchboards, protection elements, frequency modulators, accumulators, diesel generator, etc.)

Frequency modulator dimension drawings

Dimension drawings for other key system components

List and description of all connection points to Purchaser systems

Layout of electrical devices

Overall design of grounding and electrocution protection

List of electrical devices, including nominal output, voltage, load time coefficient, etc.

List of electrical devices powered through frequency modulators, including engine power output and rpm adjustment range

All other data that may be useful in assessing the technological properties of the electrical system.

    - Structural Systems

Shall contain, in particular, descriptions, drawings, calculations, and other materials, organized by individual SO and IO, documenting the structural and technological design of structures, incl. details on:

Foundation and load-bearing frames

Partition frames

Wall lining – materials, type, thickness, composition

Roof lining – materials, type, thickness, composition

Windows – finish, materials, type, opening mechanism

Doors and gates – finish, materials, type, opening mechanism

Floors

Ceilings

Finishing

Paint (specification of paint systems)

Final adjustments

Lifter frames – crane rails and grooves (maximum load), elevators (type, maximum load)

Foundations and frames for technological devices.

Further included shall be:

Layout plans of structural systems (floor plan, elevation plan, longitudinal and transversal sections)

Construction site limits for individual SO and IO

Specification and description of structure technological equipment (TZB) – healthcare technology, low-current and high-current construction equipment (incl. grounding and lightning rods), pressurized air systems, HVAC, incl. related I&C systems

Any other data that may be relevant to the assessment of structural system properties

Descriptions of individual engineering systems – technological and material solutions.

    - Questionnaires

The Participant / Contractor shall fill in the Purchaser’s questionnaires found below and submit them as a separate Addendum 1 to Supplement 12.

Note:

The data and information listed in the Questionnaires need not be repeated elsewhere in Supplement 12 – a reference to the Questionnaires will suffice.

    - List of Replacement and Rapid-Wear Parts

Pursuant to Section 35 of the Draft Contract for Work, the Participant shall submit, as a separate Addendum 2 to Supplement 12, the List of Replacement and Rapid-Wear Parts required for two years of post-warranty operation.

- ADDENDUM 1 - QUESTIONNAIRES

Absorber

| Number | pc |  |
| --- | --- | --- |
| Absorber type |  |  |
| Diameter | mm |  |
| Height | mm |  |
| Magazine diameter | mm |  |
| Magazine height | mm |  |
| Number of shower tiers | pc |  |
| L/G ratio |  |  |
| Liquid vol./tier | m3/ h |  |
| pH of absorber liquid |  |  |
| Sump material |  |  |
| Entry zone material |  |  |
| Shower section material |  |  |
| No. of stirring blades |  |  |
| Stirring blade material |  |  |
| Absorber weight | kg |  |
| Insulation |  |  |
| Bottom incline | % |  |

Drop separator

| Type | - |  |
| --- | --- | --- |
| Manufacturer | - |  |
| No. of tiers | pc |  |
| Material | - |  |
| Rinse water consumption (nominal) | l/h |  |

Boost ventilator

| Type | - |  |
| --- | --- | --- |
| Manufacturer | - |  |
| Flue-gas throughput – nominal | Nm3/h |  |
| Flue-gas operating temperature – nominal | °C |  |
| Flue-gas throughput – actual | m3/h |  |
| Nominal input overpressure | mbar |  |
| Rotation speed | 1/min |  |
| Ventilator efficiency | % |  |
| Input power, total | kW |  |
| Stator blade tilting regulation | Yes / No |  |
| Rotor blade tilting regulation | Yes / No |  |

Particulate filter

| Type |  |  |
| --- | --- | --- |
| Manufacturer |  |  |
| Design flue-gas temperature at filter input | °C |  |
| Design flue-gas volume | Nm3/h |  |
| Number of filtering chambers | ks |  |
| Total filtering area | m2 |  |
| Design filter throughput | m3/m2*min |  |
| Mean pressurized air consumption of regeneration | m3/ h |  |
| Filter hose – material |  |  |
| Mean time to hose replacement | h |  |
| Maximum overload temperature and time | °C/min |  |

Smoke flues

Raw gas flue

| Material |  |  |
| --- | --- | --- |
| Diameter | mm |  |
| Insulation |  |  |

Scrubbed gas flue

| Material |  |  |
| --- | --- | --- |
| Diameter | mm |  |
| Interior protective finish |  |  |

Flue closing armatures

| Type |  |  |
| --- | --- | --- |
| Number | pc |  |
| Drive |  |  |

Pumps (TBA by Participant for each pump type)

| Type | - |  |
| --- | --- | --- |
| Manufacturer | - |  |
| Number | pc |  |
| Water / suspension output | m3/ h// kg/ h suspension |  |
| Water discharge head | m |  |
| Suspension discharge head | m |  |
| Rotation speed | 1/min |  |
| Drive power consumption | kW |  |
| Pump material | - |  |
| Impeller material | - |  |
| Plug type | - |  |
| Plug material | - |  |

Blowers and compressors (TBA by Participant for each type)

| Type | - |  |
| --- | --- | --- |
| Manufacturer | - |  |
| Number | pc |  |
| Output | m3/ h |  |
| Input overpressure | bar |  |
| Rotation speed | 1/min |  |
| Drive power consumption | kW |  |

Stirrers (TBA by Participant for each type)

| Type | - |  |
| --- | --- | --- |
| Manufacturer | - |  |
| Stirrer material | - |  |
| Throughput | m3/ h |  |

Elevator

| Maximum load | kg |  |
| --- | --- | --- |
| Number of stops |  |  |

Lifters (TBA by Participant for each lifter type)

| Maximum load | kg |  |
| --- | --- | --- |
| Drive |  |  |

DCS

| Manufacturer | - |  |
| --- | --- | --- |
| Type | - |  |
| Galvanic isolation of individual AI card inputs | ano / ne |  |
| Input optocouplers at individual BI card inputs | ano / ne |  |
| Time resolution of BI card inputs | ms |  |
| Time resolution of event sequences (incl. internal system events such as e.g. limits of analog signals, operator input, etc.) | ms |  |

PLCs

| Auxiliary PLCs used | ano / ne |  |
| --- | --- | --- |
| PLC manufacturer / type | -/- |  |
| PLC purpose | - |  |

6 / 0.4 kV transformers

| - Manufacturer | - |  |
| --- | --- | --- |
| - Output | kVA |  |
| - Short-circuit voltage Uk | % |  |
| - Output voltage range (branches) | V |  |
| - Nominal current | A |  |
| - Ingress protection | IP |  |
| - Cooling | - |  |

6 kV substations

| - Manufacturer | - |  |
| --- | --- | --- |
| - Number of fields | - |  |
| - Nominal voltage | V |  |
| - Short-circuit resistance (incl. equipment) | kA |  |
| - Ingress protection | IP |  |
| - Dimensions ( W x D x H ) | mm |  |

0.4 kV switchboards

| - Manufacturer | - |  |
| --- | --- | --- |
| - Number of fields | - |  |
| - Nominal voltage | V |  |
| - Short-circuit resistance (incl. equipment) | kA |  |
| - Ingress protection | IP |  |
| - Dimensions ( W x D x H ) | mm |  |
| - Manufacturer |  |  |

Frequency converters (over 40kW) – list separately for each FC

| - Manufacturer | - |  |
| --- | --- | --- |
| - Type | - |  |
| - Output | kW |  |
| - Nominal input voltage | V AC |  |
| - Output voltage range | V AC |  |
| - Nominal efficiency | % |  |
| - Ambient temperature | °C |  |
| - Ingress protection | IP |  |
| - Output dU/dt filter | YES / NO |  |
| - Communications card | YES / NO |  |

Diesel generator

| - Manufacturer |  |  |
| --- | --- | --- |
| - Nominal output | - |  |
| - Fuel economy at nominal output | l/h |  |

# volume C13 Information on processing of personal data obtained from data subject and from other sources

- Volume C13 of the Indicative Tender / Tender shall contain the Participant’s draft Supplement 13 – Information on processing of personal data obtained from data subject and from other sources, which has been drafted by the Purchaser and is included in Part 2 of the Procurement Documents.

- In preparing its Indicative Tender / Tender, the Participant / Contractor shall only fill in the name of the company (of the Participant) in paragraphs 1 C), 2 A) and 2 E).

- The Participant / Contractor shall further include in Volume C13 a statement confirming that he accepts this Supplement 13 containing Information on processing of personal data obtained from data subject and from other sources without reservation.