{"text_format":"1","workbook":"xlsx","n_sheets":26,"sheets":["návrh milníků","kopie K80","PS109","PS113","PS201","PS202","PS203","PS204","PS205","PS206","PS207","PS208","PS210","PS209","PS211","SO201_OB2","SO203_OB2","K20","K80","K90","Total","K20 - time schedule","K80 - time schedule","K90 - time schedule","time schedule","consideration - time schedule"],"not_rendered":{"charts":0,"images":1,"macros":1,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"návrh milníků","index":0,"n_rows":44,"n_cols":2,"rows_kept":44,"cut":false,"hidden":true,"merged":[]}
["Činnost ","Měsíců od zahájení prací "]
["Podpis Smlouvy ",0]
["Pokyn k zahájení Prací + Předání  a převzetí Staveniště Zhotovitelem  ",2]
["Zahájení přípravy Staveniště (demolice, demontáže,….) "," "]
["Předání a převzetí dokumentace Fáze 1 Basic Designu ",3]
["Předání a převzetí dokumentace Fáze 1 Detail Design ",7]
["Zahájení výroby KOTLE "," "]
["Objednání ventilátorů vzduchu "," "]
["Objednání napájecích čerpadel "," "]
["Objednání ventilátorů spalin "," "]
["Objednání odlučovače úletového popílku "," "]
["Expedice KOTLE z výroby "," "]
["Expedice ventilátorů vzduchu z výroby "," "]
["Expedice napájecích čerpadel z výroby "," "]
["Expedice ventilátorů spalin z výroby "," "]
["Expedice odlučovače úletového popílku z výroby "," "]
["Dokončení montáže KOTLE "," "]
["Dokončení montáže ventilátorů vzduchu "," "]
["Dokončení montáže napájecích čerpadel "," "]
["Dokončení montáže ventilátorů spalin "," "]
["Dokončení montáže úletového popílku "," "]
["Zahájení výroby ocelové konstrukce "," "]
["Stavební připravenost pro montáž ocelové konstrukce "," "]
["Zahájení montáže ocelové konstrukce "," "]
["Stavební připravenost pro montáž technologie "," "]
["Dokončení nového velína KOTELNY  "," "]
["Dokončení stavby + Dokončení jednotlivých Systémů  ",22]
["Nástup pracovníků Objednatele na vyškolení  ",22]
["Zkoušky Systémů  ",23]
["Mechanické dokončení ",24]
["Zahájení Zkušebního provozu  ",24]
["Najetí ",24]
["Jednotné přezkoušení ",24]
["Zkoušky Zaručovaných hodnot ",25]
["Vyhotovení Seznamu závad ",25]
["Plánovaný termín Předběžného převzetí ",26]
["Zahájení Zkoušek Disponibility ",26]
["Dokončení Zkušebního provozu ",26]
["Odstranění závad ",27]
["Dokončení Zkoušek Disponibility ",37]
["Vydání Kolaudačního souhlasu     ",38]
["Plánovaný termín Převzetí ",38]
["Finální přezkoušení ",86]
["Finálního dokončení  ",86]

{"sheet":"kopie K80","index":1,"n_rows":97,"n_cols":293,"rows_kept":97,"cut":false,"hidden":true,"merged":[[63,285,63,288],[63,289,63,292],[64,0,64,4],[64,5,64,292],[63,261,63,264],[63,265,63,268],[63,269,63,272],[63,273,63,276],[63,277,63,280],[63,281,63,284],[63,237,63,240],[63,241,63,244],[63,245,63,248],[63,249,63,252],[63,253,63,256],[63,257,63,260],[63,213,63,216],[63,217,63,220],[63,221,63,224],[63,225,63,228],[63,229,63,232],[63,233,63,236],[63,189,63,192],[63,193,63,196],[63,197,63,200],[63,201,63,204],[63,205,63,208],[63,209,63,212],[63,165,63,168],[63,169,63,172],[63,173,63,176],[63,177,63,180],[63,181,63,184],[63,185,63,188],[63,141,63,144],[63,145,63,148],[63,149,63,152],[63,153,63,156],[63,157,63,160],[63,161,63,164],[63,117,63,120],[63,121,63,124],[63,125,63,128],[63,129,63,132],[63,133,63,136],[63,137,63,140],[63,93,63,96],[63,97,63,100],[63,101,63,104],[63,105,63,108],[63,109,63,112],[63,113,63,116],[63,69,63,72],[63,73,63,76],[63,77,63,80],[63,81,63,84],[63,85,63,88],[63,89,63,92],[63,45,63,48],[63,49,63,52],[63,53,63,56],[63,57,63,60],[63,61,63,64],[63,65,63,68],[63,21,63,24],[63,25,63,28],[63,29,63,32],[63,33,63,36],[63,37,63,40],[63,41,63,44],[62,0,62,4],[63,0,63,4],[63,5,63,8],[63,9,63,12],[63,13,63,16],[63,17,63,20],[55,0,56,0],[55,1,56,1],[57,0,58,0],[57,1,58,1],[59,0,60,0],[59,1,60,1],[49,0,50,0],[49,1,50,1],[51,0,52,0],[51,1,52,1],[53,0,54,0],[53,1,54,1],[40,0,41,0],[40,1,41,1],[42,0,43,0],[42,1,43,1],[42,2,43,2],[46,0,47,0],[46,1,47,1],[34,0,35,0],[34,1,35,1],[36,0,37,0],[36,1,37,1],[36,2,37,2],[38,0,39,0],[38,1,39,1],[28,0,29,0],[28,1,29,1],[30,0,31,0],[30,1,31,1],[32,0,33,0],[32,1,33,1],[22,0,23,0],[22,1,23,1],[24,0,25,0],[24,1,25,1],[26,0,27,0],[26,1,27,1],[16,2,17,2],[18,0,19,0],[18,1,19,1],[18,2,19,2],[20,0,21,0],[20,1,21,1],[10,0,11,0],[10,1,11,1],[12,0,13,0],[12,1,13,1],[16,0,17,0],[16,1,17,1],[1,285,1,288],[1,289,1,292],[6,0,7,0],[6,1,7,1],[6,2,7,2],[8,0,9,0],[8,1,9,1],[8,2,9,2],[1,261,1,264],[1,265,1,268],[1,269,1,272],[1,273,1,276],[1,277,1,280],[1,281,1,284],[1,237,1,240],[1,241,1,244],[1,245,1,248],[1,249,1,252],[1,253,1,256],[1,257,1,260],[1,213,1,216],[1,217,1,220],[1,221,1,224],[1,225,1,228],[1,229,1,232],[1,233,1,236],[1,189,1,192],[1,193,1,196],[1,197,1,200],[1,201,1,204],[1,205,1,208],[1,209,1,212],[1,165,1,168],[1,169,1,172],[1,173,1,176],[1,177,1,180],[1,181,1,184],[1,185,1,188],[1,141,1,144],[1,145,1,148],[1,149,1,152],[1,153,1,156],[1,157,1,160],[1,161,1,164],[1,117,1,120],[1,121,1,124],[1,125,1,128],[1,129,1,132],[1,133,1,136],[1,137,1,140],[1,101,1,104],[1,105,1,108],[1,109,1,112],[1,113,1,116],[1,69,1,72],[1,73,1,76],[1,77,1,80],[1,81,1,84],[1,85,1,88],[1,89,1,92],[0,0,2,0],[0,1,2,1],[0,2,2,2],[0,3,2,3],[0,4,2,4],[0,5,0,292],[1,5,1,8],[1,9,1,12],[1,13,1,16],[1,17,1,20],[1,45,1,48],[1,49,1,52],[1,53,1,56],[1,57,1,60],[1,61,1,64],[1,65,1,68],[1,21,1,24],[1,25,1,28],[1,29,1,32],[1,33,1,36],[1,37,1,40],[1,41,1,44],[1,93,1,96],[1,97,1,100]]}
["položka","související oblast","komentář",null,"termín / cena bez DPH (EUR)","Období"]
[null,null,null,null,null,"měsíc 1",null,null,null,"měsíc 2",null,null,null,"měsíc 3",null,null,null,"měsíc 4",null,null,null,"měsíc 5",null,null,null,"měsíc 6",null,null,null,"měsíc 7",null,null,null,"měsíc 8",null,null,null,"měsíc 9",null,null,null,"měsíc 10",null,null,null,"měsíc 11",null,null,null,"měsíc 12",null,null,null,"měsíc 13",null,null,null,"měsíc 14",null,null,null,"měsíc 15",null,null,null,"měsíc 16",null,null,null,"měsíc 17",null,null,null,"měsíc 18",null,null,null,"měsíc 19",null,null,null,"měsíc 20",null,null,null,"měsíc 21",null,null,null,"měsíc 22",null,null,null,"měsíc 23",null,null,null,"měsíc 24",null,null,null,"měsíc 25",null,null,null,"měsíc 26",null,null,null,"měsíc 27",null,null,null,"měsíc 28",null,null,null,"měsíc 29",null,null,null,"měsíc 30",null,null,null,"měsíc 31",null,null,null,"měsíc 32",null,null,null,"měsíc 33",null,null,null,"měsíc 34",null,null,null,"měsíc 35",null,null,null,"měsíc 36",null,null,null,"měsíc 37",null,null,null,"měsíc 38",null,null,null,"měsíc 39",null,null,null,"měsíc 40",null,null,null,"měsíc 41",null,null,null,"měsíc 42",null,null,null,"měsíc 43",null,null,null,"měsíc 44",null,null,null,"měsíc 45",null,null,null,"měsíc 46",null,null,null,"měsíc 47",null,null,null,"měsíc 48",null,null,null,"měsíc 49",null,null,null,"měsíc 50",null,null,null,"měsíc 51",null,null,null,"měsíc 52",null,null,null,"měsíc 53",null,null,null,"měsíc 54",null,null,null,"měsíc 55",null,null,null,"měsíc 56",null,null,null,"měsíc 57",null,null,null,"měsíc 58",null,null,null,"měsíc 59",null,null,null,"měsíc 60",null,null,null,"měsíc 61",null,null,null,"měsíc 62",null,null,null,"měsíc 63",null,null,null,"měsíc 64",null,null,null,"měsíc 65",null,null,null,"měsíc 66",null,null,null,"měsíc 67",null,null,null,"měsíc 68",null,null,null,"měsíc 69",null,null,null,"měsíc 70",null,null,null,"měsíc 71",null,null,null,"měsíc 72"]
[null,null,null,null,null,"týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4","týden 1","týden 2","týden 3","týden 4"]
[1,5]
["Podpis smlouvy","K20/K80/K90",null,null,"termín"]
["Vstupní technická jednání ","K80",null,null,"termín"]
["Závazné technické parametry pro OB 6 (Stavba) ","K80","Např. základy pro nový kotel K20",null,"termín"]
[null,null,null,null,"cena"]
["Závazné technické parametry pro OB 1 (Palivové hospodářství) ","K80","Např. místo vstupu dřevní štěpky na retrofit K80/K90",null,"termín"]
[null,null,null,null,"cena"]
["Závazné technické parametry pro ostatní OB, pro ostatní dodavatele technologických celků","K80",null,null,"termín"]
[null,null,null,null,"cena"]
["Odsouhlasená prováděcí dokumentace pro retrofit K80","K80",null,null,"termín"]
[null,null,null,null,"cena"]
["Předání a převzetí staveniště pro K80","K80",null,null,"termín"]
["Kotelna K80 - odstavení kotle K80","K80",null,null,"termín"]
["Kotelna K80 - demontáž","K80","Např. původní technologie, části nevyužitých ocel. konstrukcí atd.",null,"termín"]
[null,null,null,null,"cena"]
["Kotelna K80 - vlastní retrofit kotle K80 včetně všech komponentů a nosných konstrukcí","K80","Zahájení dodávky nových technologií pro kotel",null,"termín"]
[null,null,null,null,"cena"]
["Kotelna K80 - palivová sila včetně dopravy paliva do kotle","K80",null,null,"termín"]
[null,null,null,null,"cena"]
["Kotelna K80 - ohřívák vzduch","K80",null,null,"termín"]
[null,null,null,null,"cena"]
["Kotelna K80 - přehříváky","K80",null,null,"termín"]
[null,null,null,null,"cena"]
["Kotelna K80 - ekonomizér","K80",null,null,"termín"]
[null,null,null,null,"cena"]
["Kotelna K80 - vyzdívky","K80",null,null,"termín"]
[null,null,null,null,"cena"]
["Kotelna K80 - dno spalovací komory včetně systému chlazení a třídění popelu","K80",null,null,"termín"]
[null,null,null,null,"cena"]
["Kotelna K80 - spalinovody včetně tkaninového filtru","K80",null,null,"termín"]
[null,null,null,null,"cena"]
["Kotelna K80 - úprava rozvoden VN a NN","K80",null,null,"termín"]
[null,null,null,null,"cena"]
["Kotelna K80 - úprava ASŘ","K80","HW i SW aktualizace, SW provázanost s ŘS palivového hospodářství",null,"termín"]
[null,null,null,null,"cena"]
["Kotelna K80 - stavební konstrukce","K80",null,null,"termín"]
[null,null,null,null,"cena"]
["Kotelna K80 - popelové hospodářství (dopravní rozvody, sila)","K80",null,null,"termín"]
[null,null,null,null,"cena"]
["Kotelna K80 - další výše nevyjmenované položky","K80","Specifikace min. termínu - důležité položky z pohledu zhotovitele",null,"termín"]
[null,null,null,null,"cena"]
["Kotelna K80 - dokončení stavebních prací","K80","Včetně vrácení zařízení staveniště",null,"termín"]
["Kotelna K80 - ukončení montážních prací","K80","Včetně vrácení zařízení staveniště",null,"termín"]
["Kotelna K80 - školení zaměstnanců provozu","K80",null,null,"termín"]
[null,null,null,null,"cena"]
["Kotelna K80 - příprava ke kompexnímu vyzkoušení","K80","Zajištěna doprava paliva atd.",null,"termín"]
["Kotelna K80 - komplexní vyzkoušení","K80",null,null,"termín"]
[null,null,null,null,"cena"]
["Kotelna K80 - zkušební provoz","K80",null,null,"termín"]
[null,null,null,null,"cena"]
["Kotelna K80 - garanční test A","K80",null,null,"termín"]
[null,null,null,null,"cena"]
["Kotelna K80 - předběžné převzetí díla PAC","K80",null,null,"termín"]
[null,null,null,null,"cena"]
["Kotelna K80 - garanční test B","K80",null,null,"termín"]
[null,null,null,null,"cena"]
["Kotelna K80 - finální převzetí díla FAC","K80",null,null,"termín"]
[null,null,null,null,"cena"]
[]
["Dílčí ceny po týdnech",null,null,null,null,{"$f":"SUM(F5:F61)","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"SUM(BR5:BR61)","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"SUM(ED5:ED61)","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"SUM(GP5:GP61)","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"SUM(JB5:JB61)","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
["Dílčí ceny po měsících  ",null,null,null,null,{"$f":"SUM(F63:I63)","v":0},null,null,null,{"$f":"SUM(J63:M63)","v":0},null,null,null,{"$f":"SUM(N63:Q63)","v":0},null,null,null,{"$f":"SUM(R63:U63)","v":0},null,null,null,{"$f":"SUM(V63:Y63)","v":0},null,null,null,{"$f":"SUM(Z63:AC63)","v":0},null,null,null,{"$f":"SUM(AD63:AG63)","v":0},null,null,null,{"$f":"SUM(AH63:AK63)","v":0},null,null,null,{"$f":"SUM(AL63:AO63)","v":0},null,null,null,{"$f":"SUM(AP63:AS63)","v":0},null,null,null,{"$f":"SUM(AT63:AW63)","v":0},null,null,null,{"$f":"SUM(AX63:BA63)","v":0},null,null,null,{"$f":"SUM(BB63:BE63)","v":0},null,null,null,{"$f":"SUM(BF63:BI63)","v":0},null,null,null,{"$f":"SUM(BJ63:BM63)","v":0},null,null,null,{"$f":"SUM(BN63:BQ63)","v":0},null,null,null,{"$f":"SUM(BR63:BU63)","v":0},null,null,null,{"$f":"SUM(BV63:BY63)","v":0},null,null,null,{"$f":"SUM(BZ63:CC63)","v":0},null,null,null,{"$f":"SUM(CD63:CG63)","v":0},null,null,null,{"$f":"SUM(CH63:CK63)","v":0},null,null,null,{"$f":"SUM(CL63:CO63)","v":0},null,null,null,{"$f":"SUM(CP63:CS63)","v":0},null,null,null,{"$f":"SUM(CT63:CW63)","v":0},null,null,null,{"$f":"SUM(CX63:DA63)","v":0},null,null,null,{"$f":"SUM(DB63:DE63)","v":0},null,null,null,{"$f":"SUM(DF63:DI63)","v":0},null,null,null,{"$f":"SUM(DJ63:DM63)","v":0},null,null,null,{"$f":"SUM(DN63:DQ63)","v":0},null,null,null,{"$f":"SUM(DR63:DU63)","v":0},null,null,null,{"$f":"SUM(DV63:DY63)","v":0},null,null,null,{"$f":"SUM(DZ63:EC63)","v":0},null,null,null,{"$f":"SUM(ED63:EG63)","v":0},null,null,null,{"$f":"SUM(EH63:EK63)","v":0},null,null,null,{"$f":"SUM(EL63:EO63)","v":0},null,null,null,{"$f":"SUM(EP63:ES63)","v":0},null,null,null,{"$f":"SUM(ET63:EW63)","v":0},null,null,null,{"$f":"SUM(EX63:FA63)","v":0},null,null,null,{"$f":"SUM(FB63:FE63)","v":0},null,null,null,{"$f":"SUM(FF63:FI63)","v":0},null,null,null,{"$f":"SUM(FJ63:FM63)","v":0},null,null,null,{"$f":"SUM(FN63:FQ63)","v":0},null,null,null,{"$f":"SUM(FR63:FU63)","v":0},null,null,null,{"$f":"SUM(FV63:FY63)","v":0},null,null,null,{"$f":"SUM(FZ63:GC63)","v":0},null,null,null,{"$f":"SUM(GD63:GG63)","v":0},null,null,null,{"$f":"SUM(GH63:GK63)","v":0},null,null,null,{"$f":"SUM(GL63:GO63)","v":0},null,null,null,{"$f":"SUM(GP63:GS63)","v":0},null,null,null,{"$f":"SUM(GT63:GW63)","v":0},null,null,null,{"$f":"SUM(GX63:HA63)","v":0},null,null,null,{"$f":"SUM(HB63:HE63)","v":0},null,null,null,{"$f":"SUM(HF63:HI63)","v":0},null,null,null,{"$f":"SUM(HJ63:HM63)","v":0},null,null,null,{"$f":"SUM(HN63:HQ63)","v":0},null,null,null,{"$f":"SUM(HR63:HU63)","v":0},null,null,null,{"$f":"SUM(HV63:HY63)","v":0},null,null,null,{"$f":"SUM(HZ63:IC63)","v":0},null,null,null,{"$f":"SUM(ID63:IG63)","v":0},null,null,null,{"$f":"SUM(IH63:IK63)","v":0},null,null,null,{"$f":"SUM(IL63:IO63)","v":0},null,null,null,{"$f":"SUM(IP63:IS63)","v":0},null,null,null,{"$f":"SUM(IT63:IW63)","v":0},null,null,null,{"$f":"SUM(IX63:JA63)","v":0},null,null,null,{"$f":"SUM(JB63:JE63)","v":0},null,null,null,{"$f":"SUM(JF63:JI63)","v":0},null,null,null,{"$f":"SUM(JJ63:JM63)","v":0},null,null,null,{"$f":"SUM(JN63:JQ63)","v":0},null,null,null,{"$f":"SUM(JR63:JU63)","v":0},null,null,null,{"$f":"SUM(JV63:JY63)","v":0},null,null,null,{"$f":"SUM(JZ63:KC63)","v":0},null,null,null,{"$f":"SUM(KD63:KG63)","v":0}]
["Cena celkem",null,null,null,null,{"$f":"SUM(F64:KG64)","v":0}]
["Podpis smlouvy"]
["Vstupní technická jednání "]
["Závazné technické parametry pro OB 6 (Stavba) "]
["Závazné technické parametry pro OB 1 (Palivové hospodářství) "]
["Závazné technické parametry pro ostatní OB, pro ostatní dodavatele technologických celků"]
["Odsouhlasená prováděcí dokumentace pro retrofit K80"]
["Předání a převzetí staveniště pro K80"]
["Kotelna K80 - odstavení kotle K80"]
["Kotelna K80 - demontáž"]
["Kotelna K80 - vlastní retrofit kotle K80 včetně všech komponentů a nosných konstrukcí"]
["Kotelna K80 - palivová sila včetně dopravy paliva do kotle"]
["Kotelna K80 - ohřívák vzduch"]
["Kotelna K80 - přehříváky"]
["Kotelna K80 - ekonomizér"]
["Kotelna K80 - vyzdívky"]
["Kotelna K80 - dno spalovací komory včetně systému chlazení a třídění popelu"]
["Kotelna K80 - spalinovody včetně tkaninového filtru"]
["Kotelna K80 - úprava rozvoden VN a NN"]
["Kotelna K80 - úprava ASŘ"]
["Kotelna K80 - stavební konstrukce"]
["Kotelna K80 - popelové hospodářství (dopravní rozvody, sila)"]
["Kotelna K80 - další výše nevyjmenované položky"]
["Kotelna K80 - dokončení stavebních prací"]
["Kotelna K80 - ukončení montážních prací"]
["Kotelna K80 - školení zaměstnanců provozu"]
["Kotelna K80 - příprava ke kompexnímu vyzkoušení"]
["Kotelna K80 - komplexní vyzkoušení"]
["Kotelna K80 - zkušební provoz"]
["Kotelna K80 - garanční test A"]
["Kotelna K80 - předběžné převzetí díla PAC"]
["Kotelna K80 - garanční test B"]
["Kotelna K80 - finální převzetí díla FAC"]

{"sheet":"PS109","index":2,"n_rows":10,"n_cols":8,"rows_kept":10,"cut":false,"hidden":true,"merged":[[0,7,1,7],[1,0,1,1],[5,1,8,6],[9,1,12,6]]}
["Č. položky","Název položky ","Množství","Jednotková cena","Cena dodávka ","Cena montáž ","Cena celkem ****","Poznámka"]
["PS109 Rozvod zemního plynu ",null,"(KS)","(Kč / KS bez DPH)","(Kč bez DPH)","(Kč bez DPH)","(Kč bez DPH)"]
["109-01","Rozvod zemního plynu*",null,null,{"$f":"C3*D3","v":0},null,{"$f":"E3+F3","v":0}]
[null,"Celkem **** ",null,null,{"$f":"SUM(E3:E3)","v":0},{"$f":"SUM(F3:F3)","v":0},{"$f":"SUM(G3:G3)","v":0}]
[]
[null,"*pod kolonkou se může rozumět např. odbočka z areálového rozvodu DN150 s HUP, havarijním rychlouzávěrem a odvětráním, plynový filtr, bezpečnostní rychlouzávěr, regulační ventil, ruční uzavírací armatury, pojistné armatury, měření a regulace, plynové potrubí, instalace redukční stanice a plynového potrubí vč. nátěrů atd."]
[]
[]
[]
[null,"**** Položka \"Celkem\" za uvedený PS je vždy uvažována jako kompletní za funční celek a zahrnuje ceny veškerých plnění poskytnutých zhotovitelem na základě smlouvy, popřípadě těch, které mají být podle smlouvy poskytnuty k dosažení účelu smlouvy, aniž by taková plnění byla výslovně zde nebo ve smlouvě uvedena. Položky neuvedené, ale potřebné pro funkční celek musí být součástí položky \"Ostatní\", případně uvedeny jako nové položky."]

{"sheet":"PS113","index":3,"n_rows":12,"n_cols":8,"rows_kept":12,"cut":false,"hidden":true,"merged":[[0,7,1,7],[1,0,1,1],[8,1,9,6],[11,1,14,6]]}
["č. položky","název položky ","množství","jednotková cena","cena dodávka ","cena montáž ","cena celkem ****","poznámka"]
["PS 113 Kompresorová stanice vzduchu ",null,"(KS)","(Kč / KS bez DPH)","(Kč bez DPH)","(Kč bez DPH)","(Kč bez DPH)"]
["113-01","Kompresor dopravního vzduchu",null,null,{"$f":"C3*D3","v":0},null,{"$f":"E3+F3","v":0}]
["113-02","Kompresor řídícího vzduchu",null,null,{"$f":"C4*D4","v":0},null,{"$f":"E4+F4","v":0}]
["113-03","Suška vzduchu pro venkovní objekty",null,null,0,null,0]
["113-04","Ostatní *",null,null,0,null,{"$f":"E6+F6","v":0}]
[null,"Celkem **** ",null,null,{"$f":"SUM(E3:E6)","v":0},{"$f":"SUM(F3:F6)","v":0},0]
[]
[null,"*pod kolonkou ostatní může být zahrnuto např. adsorpční sušička vč. filtrace, stojatý vzdušník s povinnou výbavou, uzavírací armatury, odlučovač oleje z kondenzátu, instrumentace, potrubí stlačeného vzduchu, potrubí kondenzátu atd."]
[]
[]
[null,"**** Položka \"Celkem\" za uvedený PS je vždy uvažována jako kompletní za funční celek a zahrnuje ceny veškerých plnění poskytnutých zhotovitelem na základě smlouvy, popřípadě těch, které mají být podle smlouvy poskytnuty k dosažení účelu smlouvy, aniž by taková plnění byla výslovně zde nebo ve smlouvě uvedena. Položky neuvedené, ale potřebné pro funkční celek musí být součástí položky \"Ostatní\", případně uvedeny jako nové položky."]

{"sheet":"PS201","index":4,"n_rows":11,"n_cols":8,"rows_kept":11,"cut":false,"hidden":true,"merged":[[0,7,1,7],[1,0,1,1],[10,1,13,6]]}
["č. položky","název položky ","množství","jednotková cena","cena dodávka ","cena montáž ","cena celkem ****","poznámka"]
["PS201- Kotelna K20",null,"(KS)","(Kč / KS bez DPH)","(Kč bez DPH)","(Kč bez DPH)","(Kč bez DPH)"]
["201-01","Parní vysokotlaký fluidní kotel",null,null,{"$f":"C3*D3","v":0},null,{"$f":"E3+F3","v":0}]
["201-02","Primární vzduchový ventilátor",null,null,0,null,0]
["201-03","Sekundární vzduchový ventilátor",null,null,0,null,0]
["201-04","Systém sekundárních opatření snížení NOx",null,null,0,null,0]
["201-05","Ostatní*",null,null,0,null,0]
[null,"Celkem **** ",null,null,{"$f":"SUM(E3:E7)","v":0},{"$f":"SUM(F3:F7)","v":0},0]
[]
[]
[null,"**** Položka \"Celkem\" za uvedený PS je vždy uvažována jako kompletní za funční celek a zahrnuje ceny veškerých plnění poskytnutých zhotovitelem na základě smlouvy, popřípadě těch, které mají být podle smlouvy poskytnuty k dosažení účelu smlouvy, aniž by taková plnění byla výslovně zde nebo ve smlouvě uvedena. Položky neuvedené, ale potřebné pro funkční celek musí být součástí položky \"Ostatní\", případně uvedeny jako nové položky."]

{"sheet":"PS202","index":5,"n_rows":14,"n_cols":8,"rows_kept":14,"cut":false,"hidden":true,"merged":[[0,7,1,7],[1,0,1,1],[13,1,16,6]]}
["č. položky","název položky ","množství","jednotková cena","cena dodávka ","cena montáž ","cena celkem ****","poznámka"]
["PS202 Vnitřní palivové hospodářství ",null,"(KS)","(Kč / KS bez DPH)","(Kč bez DPH)","(Kč bez DPH)","(Kč bez DPH)"]
["202-01","Najížděcí a stabilizační plynové hořáky vč. potrubí*",null,null,{"$f":"C3*D3","v":0},null,{"$f":"E3+F3","v":0}]
["202-02","Provozní zásobníky štěpky",null,null,{"$f":"C4*D4","v":0},null,{"$f":"E4+F4","v":0}]
["202-03","Doprava paliva ze zásobníků",null,null,0,null,0]
["202-04","Systém dopravy MFV v rámci kotleny K20",null,null,0,null,0]
["202-05","Palivové váhy",null,null,{"$f":"C7*D7","v":0},null,{"$f":"E7+F7","v":0}]
["202-06","Provozní zásobník MFV",null,null,0,null,0]
["202-07","Ostatní**",null,null,0,null,0]
[null,"Celkem ****",null,null,{"$f":"SUM(E3:E9)","v":0},{"$f":"SUM(F3:F9)","v":0},{"$f":"SUM(G3:G9)","v":0}]
[]
[null,"*zahrnuje systém stáčení, systémy dopravy z kotle do zásobníku, ze zásobníku do kotle a z kotelny K20 do exp. sil"]
[null,"**pod kolonkou ostatní může být zahrnuto např. zařízení ochrany proti výbuchu "]
[null,"**** Položka \"Celkem\" za uvedený PS je vždy uvažována jako kompletní za funční celek a zahrnuje ceny veškerých plnění poskytnutých zhotovitelem na základě smlouvy, popřípadě těch, které mají být podle smlouvy poskytnuty k dosažení účelu smlouvy, aniž by taková plnění byla výslovně zde nebo ve smlouvě uvedena. Položky neuvedené, ale potřebné pro funkční celek musí být součástí položky \"Ostatní\", případně uvedeny jako nové položky."]

{"sheet":"PS203","index":6,"n_rows":13,"n_cols":8,"rows_kept":13,"cut":false,"hidden":true,"merged":[[0,7,1,7],[1,0,1,1],[12,1,15,6]]}
["č. položky","název položky ","množství","jednotková cena","cena dodávka ","cena montáž ","cena celkem ****","poznámka"]
["PS 203 Partie za kotlem K20 a čištění spalin",null,"(KS)","(Kč / KS bez DPH)","(Kč bez DPH)","(Kč bez DPH)","(Kč bez DPH)"]
["203-01","Spalinovody",null,null,{"$f":"C3*D3","v":0},null,{"$f":"E3+F3","v":0}]
["203-02","Tkaninový filtr K20",null,null,{"$f":"C4*D4","v":0},null,{"$f":"E4+F4","v":0}]
["203-03","Spalinový ventilátor",null,null,0,null,0]
["203-04","Recirkulační ventilátor spalin",null,null,0,null,0]
["203-05","Systém zajištění emisních limitů*",null,null,0,null,0]
["203-06","Ostatní**",null,null,0,null,0]
[null,"Celkem ****",null,null,{"$f":"SUM(E3:E8)","v":0},{"$f":"SUM(F3:F8)","v":0},{"$f":"SUM(G3:G8)","v":0}]
[]
[null,"*např. systém DSI (Dry sorbent injection)"]
[null,"**pod kolonkou ostatní může být zahrnuto např. ocelové konstrukce kouřovodu z K20"]
[null,"**** Položka \"Celkem\" za uvedený PS je vždy uvažována jako kompletní za funční celek a zahrnuje ceny veškerých plnění poskytnutých zhotovitelem na základě smlouvy, popřípadě těch, které mají být podle smlouvy poskytnuty k dosažení účelu smlouvy, aniž by taková plnění byla výslovně zde nebo ve smlouvě uvedena. Položky neuvedené, ale potřebné pro funkční celek musí být součástí položky \"Ostatní\", případně uvedeny jako nové položky."]

{"sheet":"PS204","index":7,"n_rows":9,"n_cols":8,"rows_kept":9,"cut":false,"hidden":true,"merged":[[0,7,1,7],[1,0,1,1],[5,1,7,6],[8,1,11,6]]}
["č. položky","název položky ","množství","jednotková cena","cena dodávka ","cena montáž ","cena celkem ****","poznámka"]
["PS 204 Systém dopravy popele",null,"(KS)","(Kč / KS bez DPH)","(Kč bez DPH)","(Kč bez DPH)","(Kč bez DPH)"]
["204-01","Systém dopravy popele*",null,null,{"$f":"C3*D3","v":0},null,{"$f":"E3+F3","v":0}]
[null,"Celkem ****",null,null,{"$f":"SUM(E3:E3)","v":0},{"$f":"SUM(F3:F3)","v":0},{"$f":"SUM(G3:G3)","v":0}]
[]
[null,"*pod tímto bodem může být zahrnuto např. třidič popele, úpravy stávajících expedičních sil, ocelové konstrukce pneudopravy popele do expedičních sil, případné úpravy potrubí okruhu chladicí vody, systém dopravy popílku a ložového popele do stávajících expedičních sil, doprava hrubé frakce popele"]
[]
[]
[null,"**** Položka \"Celkem\" za uvedený PS je vždy uvažována jako kompletní za funční celek a zahrnuje ceny veškerých plnění poskytnutých zhotovitelem na základě smlouvy, popřípadě těch, které mají být podle smlouvy poskytnuty k dosažení účelu smlouvy, aniž by taková plnění byla výslovně zde nebo ve smlouvě uvedena. Položky neuvedené, ale potřebné pro funkční celek musí být součástí položky \"Ostatní\", případně uvedeny jako nové položky."]

{"sheet":"PS205","index":8,"n_rows":25,"n_cols":8,"rows_kept":25,"cut":false,"hidden":true,"merged":[[0,7,1,7],[1,0,1,1],[21,1,23,6],[24,1,27,6]]}
["č. položky","název položky ","množství","jednotková cena","cena dodávka ","cena montáž ","cena celkem ****","poznámka"]
["PS 205 Rekonstrukce kotlů K80 a K90",null,"(KS)","(Kč / KS bez DPH)","(Kč bez DPH)","(Kč bez DPH)","(Kč bez DPH)"]
["205-01","Posouzení současného stavu technologie kotelny K80/90",null,null,{"$f":"C3*D3","v":0},null,{"$f":"E3+F3","v":0}]
["205-02","Úprava dna spalovací komory",null,null,{"$f":"C4*D4","v":0},null,{"$f":"E4+F4","v":0}]
["205-03","Výměna vortexu cyklónu",null,null,0,null,0]
["205-04","Úprava/výměna prvního přehříváku",null,null,0,null,0]
["205-05","Úprava druhého přehříváku",null,null,0,null,0]
["205-06","Úprava/výměna třetího přehříváku",null,null,0,null,0]
["205-07","Úprava/výměna EKO",null,null,0,null,0]
["205-08","Úprava/výměna LUVO",null,null,0,null,0]
["205-09","Hořáky",null,null,0,null,0]
["205-10","Úprava systému spalovacího vzduchu",null,null,0,null,0]
["205-11","Úpravy spalinovodů",null,null,0,null,0]
["205-12","Úpravy tkaninového filtru",null,null,0,null,0]
["205-13","Úprava systému SNCR",null,null,0,null,0]
["205-14","Systém DSI",null,null,0,null,0]
["205-15","Úpravy systému čištění výhřevných ploch",null,null,0,null,0]
["205-16","Úprava vyzdívek ",null,null,0,null,0]
["205-17","Ostatní*",null,null,0,null,0]
[null,"Celkem ****",null,null,{"$f":"SUM(E3:E19)","v":0},{"$f":"SUM(F3:F19)","v":0},{"$f":"SUM(G3:G19)","v":0}]
[]
[null,"*pod touto kolonkou může být zahrnut např. úpravy odvodu z kotle a dopravy popele a popílku do expedičních sil, úpravy systému napájení kotlů, úpravy v chladicím okruhu drobného chlazení, úpravy rozvodů stávajícho průmyslového vysavače, provizoria, další nejmenované úpravy kotlů"]
[]
[]
[null,"**** Položka \"Celkem\" za uvedený PS je vždy uvažována jako kompletní za funční celek a zahrnuje ceny veškerých plnění poskytnutých zhotovitelem na základě smlouvy, popřípadě těch, které mají být podle smlouvy poskytnuty k dosažení účelu smlouvy, aniž by taková plnění byla výslovně zde nebo ve smlouvě uvedena. Položky neuvedené, ale potřebné pro funkční celek musí být součástí položky \"Ostatní\", případně uvedeny jako nové položky."]

{"sheet":"PS206","index":9,"n_rows":10,"n_cols":8,"rows_kept":10,"cut":false,"hidden":true,"merged":[[0,7,1,7],[1,0,1,1],[9,1,12,6]]}
["č. položky","název položky ","množství","jednotková cena","cena dodávka ","cena montáž ","cena celkem ****","poznámka"]
["PS 206 Rekontrukce vnitřního palivového hodpodářství K80 a K90",null,"(KS)","(Kč / KS bez DPH)","(Kč bez DPH)","(Kč bez DPH)","(Kč bez DPH)"]
["206-01","Nové provozní zásobníky paliva ",null,null,{"$f":"C3*D3","v":0},null,{"$f":"E3+F3","v":0}]
["206-02","Nové dopravní cesty paliva ze zásobníků do kotlů ",null,null,{"$f":"C4*D4","v":0},null,{"$f":"E4+F4","v":0}]
["206-03","Ostatní*",null,null,0,null,0]
[null,"Celkem ****",null,null,{"$f":"SUM(E3:E5)","v":0},{"$f":"SUM(F3:F5)","v":0},{"$f":"SUM(G3:G5)","v":0}]
[]
[null,"*pod touto kolonkou mohou být zahrnuty např. výtahy a zdvihací zařízení "]
[]
[null,"**** Položka \"Celkem\" za uvedený PS je vždy uvažována jako kompletní za funční celek a zahrnuje ceny veškerých plnění poskytnutých zhotovitelem na základě smlouvy, popřípadě těch, které mají být podle smlouvy poskytnuty k dosažení účelu smlouvy, aniž by taková plnění byla výslovně zde nebo ve smlouvě uvedena. Položky neuvedené, ale potřebné pro funkční celek musí být součástí položky \"Ostatní\", případně uvedeny jako nové položky."]

{"sheet":"PS207","index":10,"n_rows":14,"n_cols":8,"rows_kept":14,"cut":false,"hidden":true,"merged":[[0,7,1,7],[1,0,1,1],[13,1,16,6]]}
["č. položky","název položky ","množství","jednotková cena","cena dodávka ","cena montáž ","cena celkem ****","poznámka"]
["PS 207 Demontáže ",null,"(KS)","(Kč / KS bez DPH)","(Kč bez DPH)","(Kč bez DPH)","(Kč bez DPH)"]
["207-01","Stavebně technický průzkum kotelny a technologicky souvisejících objektů ",null,null,{"$f":"C3*D3","v":0},null,{"$f":"E3+F3","v":0}]
["207-02","Demontáž stávajících uhelných bunkrů K80 a K90",null,null,{"$f":"C4*D4","v":0},null,{"$f":"E4+F4","v":0}]
["207-03","Demontáž stávající dopravy paliva do kotlů K80 a K90",null,null,0,null,0]
["207-04","Úpravy vápencového hospodářství",null,null,0,null,0]
["207-05","Demontáže kompresorů a přesun jednoho stávajícho kompresoru do kotelny K20",null,null,0,null,0]
["207-06","Odstranění odpadu ",null,null,0,null,0]
["207-07","Ostatní*",null,null,0,null,0]
[null,"Celkem ****",null,null,{"$f":"SUM(E3:E9)","v":0},{"$f":"SUM(F3:F9)","v":0},0]
[]
[null,"*pod touto kolonkou může být zahrnuto např. demontáže potrubních a technologických systémů v rámci kotelny a strojovny, demontáže stavebnch ocelových konstrukcí vyvolané umístěným nových provozních zásobníků vč. nových OK, demontáže opláštění, střechy, stavebních vnitřních stavebních a technologických  konstrukcí kotelny, demontáže systému elektro a MaR vč. slaboproudé techniky"]
[]
[null,"**** Položka \"Celkem\" za uvedený PS je vždy uvažována jako kompletní za funční celek a zahrnuje ceny veškerých plnění poskytnutých zhotovitelem na základě smlouvy, popřípadě těch, které mají být podle smlouvy poskytnuty k dosažení účelu smlouvy, aniž by taková plnění byla výslovně zde nebo ve smlouvě uvedena. Položky neuvedené, ale potřebné pro funkční celek musí být součástí položky \"Ostatní\", případně uvedeny jako nové položky."]

{"sheet":"PS208","index":11,"n_rows":11,"n_cols":8,"rows_kept":11,"cut":false,"hidden":true,"merged":[[0,7,1,7],[1,0,1,1],[8,1,8,6],[10,1,13,6]]}
["č. položky","název položky ","množství","jednotková cena","cena dodávka ","cena montáž ","cena celkem ****","poznámka"]
["PS 208 ASŘ K80/90/20",null,"(KS)","(Kč / KS bez DPH)","(Kč bez DPH)","(Kč bez DPH)","(Kč bez DPH)"]
["208-01","Úprava / rozšíření stávajících procesních stanic Procontrol P14 pro K80/90",null,null,{"$f":"C3*D3","v":0},null,{"$f":"E3+F3","v":0}]
["208-02","Systém řízení kotle K20",null,null,{"$f":"C4*D4","v":0},null,{"$f":"E4+F4","v":0}]
["208-03","Úpravy systému řízení kotlů K80/90 a strojovny",null,null,0,null,0]
["208-04","Ostatní*",null,null,0,null,0]
[null,"Celkem **** ",null,null,{"$f":"SUM(E3:E6)","v":0},{"$f":"SUM(F3:F6)","v":0},{"$f":"SUM(G3:G6)","v":0}]
[]
[null,"*pod touto konlonkou může být zahrnuto např. napájecí a komunikační kabeláž, polní instrumentace, sdružovací skříně, kabelové trasy a kabeláž"]
[]
[null,"**** Položka \"Celkem\" za uvedený PS je vždy uvažována jako kompletní za funční celek a zahrnuje ceny veškerých plnění poskytnutých zhotovitelem na základě smlouvy, popřípadě těch, které mají být podle smlouvy poskytnuty k dosažení účelu smlouvy, aniž by taková plnění byla výslovně zde nebo ve smlouvě uvedena. Položky neuvedené, ale potřebné pro funkční celek musí být součástí položky \"Ostatní\", případně uvedeny jako nové položky."]

{"sheet":"PS210","index":12,"n_rows":14,"n_cols":8,"rows_kept":14,"cut":false,"hidden":true,"merged":[[0,7,1,7],[1,0,1,1],[13,1,16,6]]}
["č. položky","název položky ","množství","jednotková cena","cena dodávka ","cena montáž ","cena celkem ****","poznámka"]
["PS 210 Elektro část K20/80/90",null,"(KS)","(Kč / KS bez DPH)","(Kč bez DPH)","(Kč bez DPH)","(Kč bez DPH)"]
["210-01","Rozváděče NN ",null,null,{"$f":"C3*D3","v":0},null,{"$f":"E3+F3","v":0}]
["210-02","Rozváděče VN",null,null,{"$f":"C4*D4","v":0},null,{"$f":"E4+F4","v":0}]
["210-03","Frekvenční měniče NN",null,null,0,null,0]
["210-04","Frekvenční měniče VN",null,null,0,null,0]
["210-05","Nosný kabelový systém",null,null,0,null,0]
["210-06","Kabeláž",null,null,0,null,0]
["210-07","Zásuvkové skříně",null,null,0,null,0]
["210-08","Ostatní",null,null,0,null,0]
[null,"Celkem **** ",null,null,{"$f":"SUM(E3:E10)","v":0},{"$f":"SUM(F3:F10)","v":0},{"$f":"SUM(G3:G10)","v":0}]
[]
[]
[null,"**** Položka \"Celkem\" za uvedený PS je vždy uvažována jako kompletní za funční celek a zahrnuje ceny veškerých plnění poskytnutých zhotovitelem na základě smlouvy, popřípadě těch, které mají být podle smlouvy poskytnuty k dosažení účelu smlouvy, aniž by taková plnění byla výslovně zde nebo ve smlouvě uvedena. Položky neuvedené, ale potřebné pro funkční celek musí být součástí položky \"Ostatní\", případně uvedeny jako nové položky."]

{"sheet":"PS209","index":13,"n_rows":11,"n_cols":8,"rows_kept":11,"cut":false,"hidden":true,"merged":[[0,7,1,7],[1,0,1,1],[10,1,13,6]]}
["č. položky","název položky ","množství","jednotková cena","cena dodávka ","cena montáž ","cena celkem ****","poznámka"]
["PS 209 CEMS ",null,"(KS)","(Kč / KS bez DPH)","(Kč bez DPH)","(Kč bez DPH)","(Kč bez DPH)"]
["209-01","Emisní monitoring vč. odběrových míst pro K20*",null,null,{"$f":"C3*D3","v":0},null,{"$f":"E3+F3","v":0}]
["209-02","Úpravy a doplnění emisního monitoringu K80*",null,null,0,null,0]
["209-03","Úpravy a doplnění emisního monitoringu K90*",null,null,0,null,0]
["209-04","Ostatní ",null,null,0,null,0]
[null,"Celkem **** ",null,null,{"$f":"SUM(E3:E6)","v":0},{"$f":"SUM(F3:F6)","v":0},{"$f":"SUM(G3:G6)","v":0}]
[]
[null,"*v rozsahu požadavků na monitorované veličiny dle přílohy A 6"]
[]
[null,"**** Položka \"Celkem\" za uvedený PS je vždy uvažována jako kompletní za funční celek a zahrnuje ceny veškerých plnění poskytnutých zhotovitelem na základě smlouvy, popřípadě těch, které mají být podle smlouvy poskytnuty k dosažení účelu smlouvy, aniž by taková plnění byla výslovně zde nebo ve smlouvě uvedena. Položky neuvedené, ale potřebné pro funkční celek musí být součástí položky \"Ostatní\", případně uvedeny jako nové položky."]

{"sheet":"PS211","index":14,"n_rows":11,"n_cols":8,"rows_kept":11,"cut":false,"hidden":true,"merged":[[0,7,1,7],[1,0,1,1],[10,1,13,6]]}
["č. položky","název položky ","množství","jednotková cena","cena dodávka ","cena montáž ","cena celkem ****","poznámka"]
["PS 211 Spojovací potrubí ",null,"(KS)","(Kč / KS bez DPH)","(Kč bez DPH)","(Kč bez DPH)","(Kč bez DPH)"]
["211-01","Připojení potrubí ostré páry z kotle K20 ve strojovně*",null,null,{"$f":"C3*D3","v":0},null,{"$f":"E3+F3","v":0}]
["211-02","Úpravy potrubí napájecí vody pro kotle vč. připojení nového kotle K20*",null,null,{"$f":"C4*D4","v":0},null,0]
["211-03","Čerpadlo a potrubí odpadní vody z vychlazovací jímky K20",null,null,0,null,0]
["211-04","Ostatní**",null,null,0,null,0]
[null,"Celkem **** ",null,null,{"$f":"SUM(E3:E6)","v":0},{"$f":"SUM(F3:F6)","v":0},{"$f":"SUM(G3:G6)","v":0}]
[]
[null,"*včetně potřebných stavebních úprav"]
[]
[null,"**** Položka \"Celkem\" za uvedený PS je vždy uvažována jako kompletní za funční celek a zahrnuje ceny veškerých plnění poskytnutých zhotovitelem na základě smlouvy, popřípadě těch, které mají být podle smlouvy poskytnuty k dosažení účelu smlouvy, aniž by taková plnění byla výslovně zde nebo ve smlouvě uvedena. Položky neuvedené, ale potřebné pro funkční celek musí být součástí položky \"Ostatní\", případně uvedeny jako nové položky."]

{"sheet":"SO201_OB2","index":15,"n_rows":23,"n_cols":8,"rows_kept":23,"cut":false,"hidden":true,"merged":[[0,7,1,7],[1,0,1,1],[19,1,21,6],[22,1,25,6]]}
["č. položky","název položky ","množství","jednotková cena","cena dodávka ","cena montáž ","cena celkem ****","poznámka"]
["SO201_OB2 Kotelna K20",null,"(KS)","(Kč / KS bez DPH)","(Kč bez DPH)","(Kč bez DPH)","(Kč bez DPH)"]
["SO201_OB2-01","Ocelová konstrukce kotle a kotelny",null,null,{"$f":"C3*D3","v":0},null,{"$f":"E3+F3","v":0}]
["SO201_OB2-02","Přístupové plošiny",null,null,{"$f":"C4*D4","v":0},null,{"$f":"E4+F4","v":0}]
["SO201_OB2-03","Podlahy",null,null,0,null,0]
["SO201_OB2-04","Schodiště",null,null,0,null,0]
["SO201_OB2-05","Obvodové stěny",null,null,0,null,0]
["SO201_OB2-06","Střecha",null,null,0,null,0]
["SO201_OB2-07","Svislé dělící a výplňové konstrukce",null,null,0,null,0]
["SO201_OB2-08","Nepoužito",null,null,0,null,0]
["SO201_OB2-09","Zdravotně technické instalace",null,null,0,null,0]
["SO201_OB2-10","Stavební elektroinstalace",null,null,0,null,0]
["SO201_OB2-11","Technologické ocelové konstrukce, přístupy, lávky, schodiště",null,null,0,null,0]
["SO201_OB2-12","Ocelové konstrukce pro provozní zásobníky paliva a technologie dopravy paliva*",null,null,0,null,0]
["SO201_OB2-13","Zdvihací zařízení, výtah",null,null,0,null,0]
["SO201_OB2-14","Ostatní**",null,null,0,null,0]
[null,"Celkem **** ",null,null,{"$f":"SUM(E3:E16)","v":0},{"$f":"SUM(F3:F16)","v":0},{"$f":"SUM(G3:G16)","v":0}]
[]
[null,"*samotná technologie je předmětem OB 1"]
[null,"**pod touto kolonkou může být zahrnuto např. klempířské konstrukce, chemické izolace, akustické izolace, omítky, hydroizolace, výplně otvorů, povrchové úpravy, speciální nátěry stavebních konstrukcí"]
[]
[]
[null,"**** Položka \"Celkem\" za uvedený SO je vždy uvažována jako kompletní za funční celek a zahrnuje ceny veškerých plnění poskytnutých zhotovitelem na základě smlouvy, popřípadě těch, které mají být podle smlouvy poskytnuty k dosažení účelu smlouvy, aniž by taková plnění byla výslovně zde nebo ve smlouvě uvedena. Položky neuvedené, ale potřebné pro funkční celek musí být součástí položky \"Ostatní\", případně uvedeny jako nové položky."]

{"sheet":"SO203_OB2","index":16,"n_rows":15,"n_cols":8,"rows_kept":15,"cut":false,"hidden":true,"merged":[[0,7,1,7],[1,0,1,1],[14,1,17,6]]}
["č. položky","název položky ","množství","jednotková cena","cena dodávka ","cena montáž ","cena celkem ****","poznámka"]
["SO203_OB2  Úpravy kotelny K80 a K90",null,"(KS)","(Kč / KS bez DPH)","(Kč bez DPH)","(Kč bez DPH)","(Kč bez DPH)"]
["SO203_OB2-01","Nové opláštění budovy kotelny K80 a K90 v místech, kde bude rekonstrukcí opláštění porušeno",null,null,{"$f":"C3*D3","v":0},null,{"$f":"E3+F3","v":0}]
["SO203_OB2-02","Nová případná střešní kontrukce kotelny K80/90",null,null,{"$f":"C4*D4","v":0},null,{"$f":"E4+F4","v":0}]
["SO203_OB2-03","Svislé a vodorovné konstrukce*",null,null,0,null,0]
["SO203_OB2-04","Technologické ocelové konstrukce, přístupy, lávky, schodiště",null,null,0,null,0]
["SO203_OB2-05","Ocelové konstrukce pro provozní zásobníky paliva a technologie dopravy paliva**",null,null,0,null,0]
["SO203_OB2-06","Celkové statické zajištění kotelny K80/90 pro úpravy ",null,null,0,null,0]
["SO203_OB2-07","Ostatní***",null,null,0,null,0]
[null,"Celkem **** ",null,null,{"$f":"SUM(E3:E9)","v":0},{"$f":"SUM(F3:F9)","v":0},{"$f":"SUM(G3:G9)","v":0}]
[]
[null,"*nové i upravované"]
[null,"**samotná technologie je předmětem OB 1"]
[null,"***pod touto kolonkou může být zahrnuto např. zdvihací zařízení"]
[null,"**** Položka \"Celkem\" za uvedený SO je vždy uvažována jako kompletní za funční celek a zahrnuje ceny veškerých plnění poskytnutých zhotovitelem na základě smlouvy, popřípadě těch, které mají být podle smlouvy poskytnuty k dosažení účelu smlouvy, aniž by taková plnění byla výslovně zde nebo ve smlouvě uvedena. Položky neuvedené, ale potřebné pro funkční celek musí být součástí položky \"Ostatní\", případně uvedeny jako nové položky."]

{"sheet":"K20","index":17,"n_rows":90,"n_cols":8,"rows_kept":90,"cut":false,"hidden":false,"merged":[[84,0,87,7],[3,7,4,7],[3,0,3,1],[1,0,1,7],[9,0,12,0],[13,0,16,0],[17,0,23,0],[25,0,27,0],[28,0,30,0],[31,0,39,0],[41,0,46,0],[47,0,51,0],[52,0,55,0],[56,0,59,0],[60,0,72,0],[81,0,81,1]]}
[]
["Annex K to the Tender Documentation - price table and time schedule"]
[]
["Tender price for boiler K20",null,"Amount","Unit price","Supply price","Installation price","Item price","Notes"]
["Milestone","Item","(pcs, m, m2)","(EUR / pc excl. VAT)","(EUR excl. VAT)","(EUR excl. VAT)","(EUR excl. VAT)"]
["Binding technical specification of OB 6",null,"-","-",null,"-",{"$f":"E6","v":0}]
["Binding technical specification of OB 1",null,"-","-",null,"-",0]
["Binding technical specification of other Obs",null,"-","-",null,"-",0]
["Implementing documentation for boiler K20",null,"-","-",null,"-",{"$f":"E9","v":0}]
["Boiler itself","Subtotal","-","-",{"$f":"E11+E12+E13","v":0},{"$f":"F11+F12+F13","v":0},0]
[null,"Steam jet fluidized bed boiler","-","-",null,null,{"$f":"E11+F11","v":0}]
[null,"NOx reducting secondary measures system","-","-",null,null,0]
[null,"Roll-on and stabilizing gas burners",null,null,{"$f":"C13*D13","v":0},null,0]
["Operating storage tanks","Subtotal","-","-",{"$f":"E15+E17+E16","v":0},{"$f":"F15+F17+F16","v":0},0]
[null,"Operating storage tanks - chips",null,null,0,null,0]
[null,"Transport of fuel from storage tanks",null,null,0,null,0]
[null,"Fuel weight",null,null,0,null,0]
["Ventilators","Subtotal","-","-",{"$f":"E19+E20+E21+E22+E23+E24","v":0},{"$f":"F19+F20+F21+F22+F23+F24","v":0},0]
[null,"Flue lines",null,null,0,null,0]
[null,"Flue vent",null,null,0,null,0]
[null,"Recirculation flue vent",null,null,0,null,0]
[null,"Emission limit measuring system","-","-",null,null,0]
[null,"Air vents",null,null,0,null,0]
[null,"Supply line of combustion air",null,null,0,null,0]
["Fabric filter",null,"-","-",null,null,0]
["Dry sorbent injection System","Subtotal","-","-",{"$f":"E27+E28","v":0},{"$f":"F27+F28","v":0},0]
[null,"Storage silo",null,null,0,null,0]
[null,"Other distribution systems, incl. dosing",null,null,0,null,0]
["Ash management","Subtotal","-","-",{"$f":"E30+E31","v":0},{"$f":"F30+F31","v":0},0]
[null,"Fluidized bed material storage tank",null,null,0,null,0]
[null,"Piping",null,null,0,null,0]
["Electrical installation","Subtotal","-","-",{"$f":"E33+E34+E35+E36+E37+E38+E39+E40","v":0},{"$f":"F33+F34+F35+F36+F37+F38+F39+F40","v":0},0]
[null,"Transformer station",null,null,0,null,0]
[null,"Low-voltage switchgear",null,null,0,null,0]
[null,"High-voltage switchgear",null,null,0,null,0]
[null,"Low-voltage frequency converter",null,null,0,null,0]
[null,"High-voltage frequency converter",null,null,0,null,0]
[null,"Central cabling system",null,null,0,null,0]
[null,"Cabling",null,null,0,null,0]
[null,"Plug cupboards",null,null,0,null,0]
["Automatic control system",null,"-","-",null,null,0]
["Compressor station","Subtotal","-","-",{"$f":"E43+E44+E45+E46+E47","v":0},{"$f":"F43+F44+F45+F46+F47","v":0},0]
[null,"Transport air compressor",null,null,0,null,0]
[null,"Control air compressor",null,null,0,null,0]
[null,"Support technologies (driers, reservoirs, filtration)",null,null,0,null,0]
[null,"Air drier for outside installations",null,null,0,null,0]
[null,"Lines",null,null,0,null,0]
["Media connection","Subtotal","-","-",{"$f":"E49+E50+E51+E52","v":0},{"$f":"F49+F50+F51+F52","v":0},0]
[null,"Feedwater connection",null,null,0,null,0]
[null,"Steam connection",null,null,0,null,0]
[null,"Natural gas connection",null,null,0,null,0]
[null,"Compressed air connection",null,null,0,null,0]
["Outdoor flue distribution","Subtotal","-","-",{"$f":"E54+E55+E56","v":0},{"$f":"F54+F55+F56","v":0},0]
[null,"Bridge construction",null,null,0,null,0]
[null,"Flue lines",null,null,0,null,0]
[null,"Chimney connection","-","-",null,null,0]
["Pipeline bridge","Subtotal","-","-",{"$f":"E58+E59+E60","v":0},{"$f":"F58+F59+F60","v":0},0]
[null,"Bridge construction",null,null,0,null,0]
[null,"Ash management lines",null,null,0,null,0]
[null,"SNCR lines",null,null,0,null,0]
["Construction structure","Subtotal","-","-",{"$f":"E62+E63+E64+E65+E66+E67+E68+E69+E70+E71+E72+E73","v":0},{"$f":"F62+F63+F64+F65+F66+F67+F68+F69+F70+F71+F72+F73","v":0},0]
[null,"Boiler and boiler room steel structure",null,null,0,null,0]
[null,"Access platforms",null,null,0,null,0]
[null,"Floors",null,null,0,null,0]
[null,"Stairway",null,null,0,null,0]
[null,"Exterior walls",null,null,0,null,0]
[null,"Roof",null,null,0,null,0]
[null,"Vertical dividing and filling structures",null,null,0,null,0]
[null,"Sanitary installation",null,null,0,null,0]
[null,"Construction electrical installation",null,null,0,null,0]
[null,"Technological steel structures, accesses, bridges, stairways",null,null,{"$f":"C71*D71","v":0},null,{"$f":"E71+F71","v":0}]
[null,"Steel structures for operating storage tanks and fuel transport technology",null,null,0,null,0]
[null,"Lifting equipment, elevator",null,null,0,null,0]
["Other",null,null,null,0,null,0]
["Operating staff training",null,"-","-",null,"-",{"$f":"E75","v":0}]
["Comprehensive testing",null,"-","-",null,"-",{"$f":"E76","v":0}]
["Trial operation",null,"-","-",null,"-",0]
["Guarantee test A",null,"-","-",null,"-",0]
["Preliminary acceptance of the Work PAC",null,"-","-",null,"-",0]
["Guarantee test B",null,"-","-",null,"-",0]
["Final acceptance of the Work FAC",null,"-","-",null,"-",0]
["Total *",null,null,null,{"$f":"E6+E7+E8+E9+E10+E14+E18+E25+E26+E29+E32+E41+E42+E48+E53+E57+E61+E74+E75+E76+E77+E78+E79+E80+E81","v":0},{"$f":"F10+F14+F18+F25+F26+F29+F32+F41+F42+F48+F53+F57+F61+F74","v":0},{"$f":"G6+G7+G8+G9+G10+G14+G18+G25+G26+G29+G32+G41+G42+G48+G53+G57+G61+G74+G75+G76+G77+G78+G79+G80+G81","v":0}]
[]
["Notes:"]
["* The item \"Total\" is always meant as for a complete and working unit and includes prices of all performance of the Contractor under the contract, or, as the case may be, of such that shall be performed under the Contract in order to fulfil its  purpose without such performance being expressly here or elsewhere stipulated. Non-stipulated items needed for the functional unit must be a part of the item \"Other\"."]
[]
[]
[]
["Value of cells \"E82\", \"F82\" and \"G82\" is transfered to the \"Total\" list"]
["The Contractor only fills in non-coloured cells in columns \"C\", \"D\", \"E\" and \"F\""]

{"sheet":"K80","index":18,"n_rows":68,"n_cols":8,"rows_kept":68,"cut":false,"hidden":false,"merged":[[3,0,3,1],[3,7,4,7],[62,0,65,7],[1,0,1,7],[10,0,12,0],[13,0,16,0],[18,0,21,0],[23,0,25,0],[27,0,30,0],[31,0,38,0],[40,0,46,0],[47,0,50,0],[59,0,59,1]]}
[]
["Annex K to the Tender Documentation - price table and time schedule"]
[]
["Tender price for boiler K80",null,"Amount","Unit price","Supply price","Installation price","Item price","Notes"]
["Milestone","Item","(pcs, m, m2)","(EUR / ks bez DPH)","(EUR excl. VAT)","(EUR excl. VAT)","(EUR excl. VAT)"]
["Binding technical specification of OB 6",null,"-","-",null,"-",{"$f":"E6","v":0}]
["Binding technical specification of OB 1",null,"-","-",null,"-",0]
["Binding technical specification of other OBs",null,"-","-",null,"-",0]
["Implementing documentation for K80",null,"-","-",null,"-",{"$f":"E9","v":0}]
["Dismantling",null,"-","-",null,"-",{"$f":"E10","v":0}]
["Supply of combustion air","Subtotal","-","-",{"$f":"SUM(E12:E13)","v":0},{"$f":"SUM(F12:F13)","v":0},{"$f":"G12+G13","v":0}]
[null,"Piping",null,null,{"$f":"C12*D12","v":0},null,{"$f":"E12+F12","v":0}]
[null,"Air vents",null,null,0,null,0]
["Operating storage tanks","Subtotal","-","-",{"$f":"E15+E16+E17","v":0},{"$f":"F15+F16+F17","v":0},0]
[null,"Operating storage tanks - chips",null,null,0,null,0]
[null,"Transport of fuel from storage tanks",null,null,0,null,0]
[null,"Fuel weight",null,null,0,null,0]
["Air heating",null,"-","-",null,null,{"$f":"E18+F18","v":0}]
["Overheating","Subtotal","-","-",{"$f":"E20+E21+E22","v":0},{"$f":"F20+F21+F22","v":0},0]
[null,"1.","-","-",null,null,{"$f":"E20+F20","v":0}]
[null,"2.","-","-",null,null,0]
[null,"3.","-","-",null,null,0]
["Economizer",null,"-","-",null,null,0]
["Lining","Subtotal","-","-",{"$f":"E25+E26","v":0},{"$f":"F25+F26","v":0},0]
[null,"Bottom of combustion chamber",null,null,0,null,0]
[null,"Cyclone",null,null,0,null,0]
["Bottom of combustion chamber",null,"-","-",null,null,0]
["Flue lines","Subtotal","-","-",{"$f":"E29+E30+E31","v":0},{"$f":"F29+F30+F31","v":0},0]
[null,"Flue lines",null,null,0,null,0]
[null,"Fabric filter",null,null,0,null,0]
[null,"Emission monitoring",null,null,0,null,0]
["Electrical installation","Subtotal","-","-",{"$f":"E33+E34+E35+E36+E37+E38+E39","v":0},{"$f":"F33+F34+F35+F36+F37+F38+F39","v":0},0]
[null,"Low-voltage switchgear",null,null,0,null,0]
[null,"High-voltage switchgear",null,null,0,null,0]
[null,"Low-voltage frequency converter",null,null,0,null,0]
[null,"High-voltage frequency converter",null,null,0,null,0]
[null,"Central cabling systém",null,null,0,null,0]
[null,"Cabling",null,null,0,null,0]
[null,"Plug cupboards",null,null,0,null,0]
["Automatic control system",null,"-","-",null,null,0]
["Construction structure","Subtotal","-","-",{"$f":"E42+E43+E44+E45+E46+E47","v":0},{"$f":"F42+F43+F44+F45+F46+F47","v":0},0]
[null,"New cladding of the K80 boiler building where the cladding will be damaged by the reconstruction",null,null,0,null,0]
[null,"Possible new roof structure of boiler room K80 ",null,null,0,null,0]
[null,"Vertical and horizontal structures",null,null,0,null,0]
[null,"Technological steel structures, accesses, bridges, stairways",null,null,0,null,0]
[null,"Steel structures for operating storage tanks and fuel transport technology",null,null,0,null,0]
[null,"Overall static securing of boiler room K80 for modifications ",null,null,0,null,0]
["Ash management","Subtotal","-","-",{"$f":"E49+E50+E51","v":0},{"$f":"F49+F50+F51","v":0},0]
[null,"Ash cooler",null,null,0,null,0]
[null,"Ash sorter",null,null,0,null,0]
[null,"Piping",null,null,0,null,0]
["Other",null,null,null,0,null,0]
["Operating staff training",null,"-","-",null,"-",{"$f":"E53","v":0}]
["Comprehensive testing",null,"-","-",null,"-",{"$f":"E54","v":0}]
["Trial operation",null,"-","-",null,"-",0]
["Guarantee test A",null,"-","-",null,"-",0]
["Preliminary acceptance of the Work PAC",null,"-","-",null,"-",0]
["Guarantee test B",null,"-","-",null,"-",0]
["Final acceptance of the Work FAC",null,"-","-",null,"-",0]
["Total *",null,null,null,{"$f":"E6+E7+E8+E9+E10+E11+E14+E18+E19+E23+E24+E27+E28+E32+E40+E41+E48+E52+E53+E54+E55+E56+E57+E58+E59","v":0},{"$f":"F11+F14+F18+F19+F23+F24+F27+F28+F32+F40+F41+F48+F52","v":0},{"$f":"G6+G7+G8+G9+G10+G11+G14+G18+G19+G23+G24+G27+G28+G32+G40+G41+G48+G52+G53+G54+G55+G56+G57+G58+G59","v":0}]
[]
["Notes:"]
["* The item \"Total\" is always meant as for a complete and working unit and includes prices of all performance of the Contractor under the contract, or, as the case may be, of such that shall be performed under the Contract in order to fulfil its  purpose without such performance being expressly here or elsewhere stipulated. Non-stipulated items needed for the functional unit must be a part of the item \"Other\"."]
[]
[]
[]
["Value of cells \"E60\", \"F60\" and \"G60\" is transfered to the \"Total\" list"]
["The Contractor only fills in non-coloured cells in columns \"C\", \"D\", \"E\" and \"F\""]

{"sheet":"K90","index":19,"n_rows":68,"n_cols":8,"rows_kept":68,"cut":false,"hidden":false,"merged":[[1,0,1,7],[3,0,3,1],[3,7,4,7],[62,0,65,7],[10,0,12,0],[13,0,16,0],[18,0,21,0],[23,0,25,0],[27,0,30,0],[31,0,38,0],[40,0,46,0],[47,0,50,0],[59,0,59,1]]}
[]
["Annex K to the Tender Documentation - price table and time schedule"]
[]
["Tender price for boiler K90",null,"Amount","Unit price","Supply price","Installation price","Item price","Notes"]
["Milestone","Item","(pcs, m, m2)","(EUR / pc excl. VAT)","(EUR excl. VAT)","(EUR excl. VAT)","(EUR excl. VAT)"]
["Binding technical specification of OB 6",null,"-","-",null,"-",{"$f":"E6","v":0}]
["Binding technical specification of OB 1",null,"-","-",null,"-",0]
["Binding technical specification of other OBs",null,"-","-",null,"-",0]
["Implementing documentation for boiler K90",null,"-","-",null,"-",{"$f":"E9","v":0}]
["Dismantling",null,"-","-",null,"-",{"$f":"E10","v":0}]
["Supply of combustion air","Subtotal","-","-",{"$f":"E12+E13","v":0},{"$f":"F12+F13","v":0},0]
[null,"Piping",null,null,{"$f":"C12*D12","v":0},null,{"$f":"E12+F12","v":0}]
[null,"Air vents",null,null,0,null,0]
["Operating storage tanks","Subtotal","-","-",{"$f":"E15+E16+E17","v":0},{"$f":"F15+F16+F17","v":0},0]
[null,"Operating storage tanks - chips",null,null,0,null,0]
[null,"Transport of fuel from storage tanks",null,null,0,null,0]
[null,"Fuel weight",null,null,0,null,0]
["Air heating",null,"-","-",null,null,{"$f":"E18+F18","v":0}]
["Overheating","Subtotal","-","-",{"$f":"E20+E21+E22","v":0},{"$f":"F20+F21+F22","v":0},0]
[null,"1.","-","-",null,null,{"$f":"E20+F20","v":0}]
[null,"2.","-","-",null,null,0]
[null,"3.","-","-",null,null,0]
["Economizer",null,"-","-",null,null,0]
["Lining","Subtotal","-","-",{"$f":"E25+E26","v":0},{"$f":"F25+F26","v":0},0]
[null,"Bottom of combustion chamber",null,null,0,null,0]
[null,"Cyclone",null,null,0,null,0]
["Bottom of combustion chamber",null,"-","-",null,null,0]
["Flue lines","Subtotal","-","-",{"$f":"E29+E30+E31","v":0},{"$f":"F29+F30+F31","v":0},0]
[null,"Flue lines",null,null,0,null,0]
[null,"Fabric filter",null,null,0,null,0]
[null,"Emission monitoring",null,null,0,null,0]
["Electrical installation","Subtotal","-","-",{"$f":"E33+E34+E35+E36+E37+E38+E39","v":0},{"$f":"F33+F34+F35+F36+F37+F38+F39","v":0},0]
[null,"Low-voltage switchgear",null,null,0,null,0]
[null,"High-voltage switchgear",null,null,0,null,0]
[null,"Low-voltage frequency converter",null,null,0,null,0]
[null,"High-voltage frequency converter",null,null,0,null,0]
[null,"Central cabling systém",null,null,0,null,0]
[null,"Cabling",null,null,0,null,0]
[null,"Plug cupboards",null,null,0,null,0]
["Automatic control system",null,"-","-",null,null,0]
["Construction structure","Subtotal","-","-",{"$f":"E42+E43+E44+E45+E46+E47","v":0},{"$f":"F42+F43+F44+F45+F46+F47","v":0},0]
[null,"New cladding of the K90 boiler building where the cladding will be damaged by the reconstruction",null,null,0,null,0]
[null,"Possible new roof structure of boiler room K90 ",null,null,0,null,0]
[null,"Vertical and horizontal structures",null,null,0,null,0]
[null,"Technological steel structures, accesses, bridges, stairways",null,null,0,null,0]
[null,"Steel structures for operating storage tanks and fuel transport technology",null,null,0,null,0]
[null,"Overall static securing of boiler room K90 for modifications ",null,null,0,null,0]
["Ash management","Subtotal","-","-",{"$f":"E49+E50+E51","v":0},{"$f":"F49+F50+F51","v":0},0]
[null,"Ash cooler",null,null,0,null,0]
[null,"Ash sorter",null,null,0,null,0]
[null,"Piping",null,null,0,null,0]
["Other",null,null,null,0,null,0]
["Operating staff training",null,"-","-",null,"-",{"$f":"E53","v":0}]
["Comprehensive testing",null,"-","-",null,"-",{"$f":"E54","v":0}]
["Trial operation",null,"-","-",null,"-",0]
["Guarantee test A",null,"-","-",null,"-",0]
["Preliminary acceptance of the Work PAC",null,"-","-",null,"-",0]
["Guarantee test B",null,"-","-",null,"-",0]
["Final acceptance of the Work FAC",null,"-","-",null,"-",0]
["Total *",null,null,null,{"$f":"E6+E7+E8+E9+E10+E11+E14+E18+E19+E23+E24+E27+E28+E32+E40+E41+E48+E52+E53+E54+E55+E56+E57+E58+E59","v":0},{"$f":"F11+F14+F18+F19+F23+F24+F27+F28+F32+F40+F41+F48+F52","v":0},{"$f":"G6+G7+G8+G9+G10+G11+G14+G18+G19+G23+G24+G27+G28+G32+G40+G41+G48+G52+G53+G54+G55+G56+G57+G58+G59","v":0}]
[]
["Notes:"]
["* The item \"Total\" is always meant as for a complete and working unit and includes prices of all performance of the Contractor under the contract, or, as the case may be, of such that shall be performed under the Contract in order to fulfil its  purpose without such performance being expressly here or elsewhere stipulated. Non-stipulated items needed for the functional unit must be a part of the item \"Other\"."]
[]
[]
[]
["Value of cells \"E60\", \"F60\" and \"G60\" is transfered to the \"Total\" list"]
["The Contractor only fills in non-coloured cells in columns \"C\", \"D\", \"E\" and \"F\""]

{"sheet":"Total","index":20,"n_rows":13,"n_cols":4,"rows_kept":13,"cut":false,"hidden":false,"merged":[[3,0,3,3],[1,0,1,7]]}
[]
["Annex K to the Tender Documentation - price table and time schedule"]
[]
["Summary - Total tender price"]
["Stage","Supply price (EUR)","Installation price (EUR)","Total item price (EUR)"]
["K20",{"$f":"'K20'!E82","v":0},{"$f":"'K20'!F82","v":0},{"$f":"'K20'!G82","v":0}]
["K80",{"$f":"'K80'!E60","v":0},{"$f":"'K80'!F60","v":0},{"$f":"'K80'!G60","v":0}]
["K90",{"$f":"'K90'!E60","v":0},{"$f":"'K90'!F60","v":0},{"$f":"'K90'!G60","v":0}]
["Total price (excl. VAT)",{"$f":"SUM(B6:B8)","v":0},{"$f":"SUM(C6:C8)","v":0},{"$f":"SUM(D6:D8)","v":0}]
[]
["Notes:"]
[" - no values are to be filled on this sheet"]
[" - all values are transfered to the above table from sheets \"K20\", \"K80\" and \"K90\""]

{"sheet":"K20 - time schedule","index":21,"n_rows":102,"n_cols":306,"rows_kept":102,"cut":false,"hidden":false,"merged":[[66,270,66,273],[66,274,66,277],[66,278,66,281],[66,282,66,285],[66,286,66,289],[4,290,4,293],[4,294,4,297],[4,262,4,265],[4,266,4,269],[4,270,4,273],[4,274,4,277],[4,278,4,281],[4,282,4,285],[4,286,4,289],[67,6,67,305],[3,6,3,305],[66,190,66,193],[66,194,66,197],[66,198,66,201],[66,222,66,225],[66,226,66,229],[66,230,66,233],[66,234,66,237],[66,238,66,241],[66,242,66,245],[66,246,66,249],[66,250,66,253],[66,254,66,257],[66,258,66,261],[66,262,66,265],[66,266,66,269],[66,290,66,293],[66,294,66,297],[66,298,66,301],[66,302,66,305],[4,190,4,193],[4,218,4,221],[4,222,4,225],[4,226,4,229],[4,230,4,233],[4,234,4,237],[4,242,4,245],[4,246,4,249],[4,250,4,253],[4,238,4,241],[4,194,4,197],[4,198,4,201],[4,202,4,205],[4,206,4,209],[4,210,4,213],[4,214,4,217],[4,298,4,301],[4,302,4,305],[4,254,4,257],[4,258,4,261],[60,2,61,2],[62,2,63,2],[65,0,65,5],[66,0,66,5],[67,0,67,5],[35,2,36,2],[37,2,38,2],[39,2,40,2],[41,2,42,2],[43,2,44,2],[49,2,50,2],[52,2,53,2],[54,2,55,2],[56,2,57,2],[45,3,46,3],[49,3,50,3],[52,3,53,3],[54,3,55,3],[56,3,57,3],[58,3,59,3],[60,3,61,3],[62,3,63,3],[58,0,59,0],[58,1,59,1],[66,186,66,189],[66,202,66,205],[66,206,66,209],[66,210,66,213],[66,214,66,217],[66,62,66,65],[66,66,66,69],[66,70,66,73],[66,74,66,77],[66,146,66,149],[66,78,66,81],[66,82,66,85],[66,86,66,89],[66,90,66,93],[66,94,66,97],[66,98,66,101],[66,102,66,105],[66,106,66,109],[66,110,66,113],[66,114,66,117],[66,218,66,221],[66,150,66,153],[66,154,66,157],[66,158,66,161],[66,162,66,165],[66,166,66,169],[66,170,66,173],[66,174,66,177],[66,178,66,181],[66,182,66,185],[66,118,66,121],[66,122,66,125],[66,126,66,129],[66,130,66,133],[66,134,66,137],[66,138,66,141],[66,142,66,145],[66,26,66,29],[66,30,66,33],[66,34,66,37],[66,38,66,41],[66,42,66,45],[66,46,66,49],[66,50,66,53],[66,54,66,57],[66,58,66,61],[3,2,5,2],[3,5,5,5],[4,6,4,9],[4,10,4,13],[4,14,4,17],[4,18,4,21],[4,22,4,25],[3,3,5,3],[66,6,66,9],[66,10,66,13],[66,14,66,17],[66,18,66,21],[66,22,66,25],[3,4,5,4],[13,2,14,2],[15,2,16,2],[19,2,20,2],[21,2,22,2],[23,2,24,2],[25,2,26,2],[27,2,28,2],[29,2,30,2],[31,2,32,2],[58,2,59,2],[4,186,4,189],[4,146,4,149],[4,150,4,153],[4,154,4,157],[4,158,4,161],[4,166,4,169],[4,58,4,61],[4,62,4,65],[4,66,4,69],[4,70,4,73],[4,122,4,125],[4,126,4,129],[4,130,4,133],[4,134,4,137],[4,138,4,141],[4,142,4,145],[4,98,4,101],[4,102,4,105],[4,106,4,109],[4,110,4,113],[4,114,4,117],[4,118,4,121],[4,74,4,77],[4,78,4,81],[9,2,10,2],[9,0,10,0],[9,1,10,1],[11,0,12,0],[11,1,12,1],[4,170,4,173],[4,174,4,177],[4,178,4,181],[4,182,4,185],[4,82,4,85],[4,86,4,89],[4,90,4,93],[4,94,4,97],[4,50,4,53],[4,54,4,57],[4,162,4,165],[4,26,4,29],[4,30,4,33],[4,34,4,37],[4,38,4,41],[4,42,4,45],[4,46,4,49],[3,0,5,0],[3,1,5,1],[60,0,61,0],[60,1,61,1],[62,0,63,0],[62,1,63,1],[52,0,53,0],[52,1,53,1],[54,0,55,0],[54,1,55,1],[56,0,57,0],[56,1,57,1],[19,0,20,0],[19,1,20,1],[11,2,12,2],[13,0,14,0],[13,1,14,1],[15,0,16,0],[15,1,16,1],[45,2,46,2],[31,0,32,0],[31,1,32,1],[21,0,22,0],[21,1,22,1],[23,0,24,0],[23,1,24,1],[25,0,26,0],[25,1,26,1],[27,0,28,0],[27,1,28,1],[29,0,30,0],[29,1,30,1],[49,0,50,0],[49,1,50,1],[37,0,38,0],[37,1,38,1],[39,0,40,0],[39,1,40,1],[41,0,42,0],[41,1,42,1],[33,2,34,2],[35,0,36,0],[35,1,36,1],[45,0,46,0],[45,1,46,1],[43,0,44,0],[43,1,44,1],[33,0,34,0],[33,1,34,1],[9,3,10,3],[11,3,12,3],[13,3,14,3],[15,3,16,3],[19,3,20,3],[21,3,22,3],[23,3,24,3],[25,3,26,3],[17,3,18,3],[27,3,28,3],[29,3,30,3],[31,3,32,3],[33,3,34,3],[35,3,36,3],[37,3,38,3],[39,3,40,3],[41,3,42,3],[43,3,44,3]]}
[]
["Annex K to the Tender Documentation - price table and time schedule"]
[]
["Milestones","Stage","Comment","Price for item excl. VAT (EUR)",null,"Deadline / price excl. VAT (EUR)","Period"]
[null,null,null,null,null,null,"month 1",null,null,null,"month 2",null,null,null,"month 3",null,null,null,"month 4",null,null,null,"month 5",null,null,null,"month 6",null,null,null,"month 7",null,null,null,"month 8",null,null,null,"month 9",null,null,null,"month 10",null,null,null,"month 11",null,null,null,"month 12",null,null,null,"month 13",null,null,null,"month 14",null,null,null,"month 15",null,null,null,"month 16",null,null,null,"month 17",null,null,null,"month 18",null,null,null,"month 19",null,null,null,"month 20",null,null,null,"month 21",null,null,null,"month 22",null,null,null,"month 23",null,null,null,"month 24",null,null,null,"month 25",null,null,null,"month 26",null,null,null,"month 27",null,null,null,"month 28",null,null,null,"month 29",null,null,null,"month 30",null,null,null,"month 31",null,null,null,"month 32",null,null,null,"month 33",null,null,null,"month 34",null,null,null,"month 35",null,null,null,"month 36",null,null,null,"month 37",null,null,null,"month 38",null,null,null,"month 39",null,null,null,"month 40",null,null,null,"month 41",null,null,null,"month 42",null,null,null,"month 43",null,null,null,"month 44",null,null,null,"month 45",null,null,null,"month 46",null,null,null,"month 47",null,null,null,"month 48",null,null,null,"month 49",null,null,null,"month 50",null,null,null,"month 51",null,null,null,"month 52",null,null,null,"month 53",null,null,null,"month 54",null,null,null,"month 55",null,null,null,"month 56",null,null,null,"month 57",null,null,null,"month 58",null,null,null,"month 59",null,null,null,"month 60",null,null,null,"month 61",null,null,null,"month 62",null,null,null,"month 63",null,null,null,"month 64",null,null,null,"month 65",null,null,null,"month 66",null,null,null,"month 67",null,null,null,"month 68",null,null,null,"month 69",null,null,null,"month 70",null,null,null,"month 71",null,null,null,"month 72",null,null,null,"month 73",null,null,null,"month 74",null,null,null,"month 75"]
[null,null,null,null,null,null,"week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4"]
[0,0,20,null,null,null,1,2,3,4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,39,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61,62,63,64,65,66,67,68,69,70,71,72,73,74,75,76,77,78,79,80,81,82,83,84,85,86,87,88,89,90,91,92,93,94,95,96,97,98,99,100,101,102,103,104,105,106,107,108,109,110,111,112,113,114,115,116,117,118,119,120,121,122,123,124,125,126,127,128,129,130,131,132,133,134,135,136,137,138,139,140,141,142,143,144,145,146,147,148,149,150,151,152,153,154,155,156,157,158,159,160,161,162,163,164,165,166,167,168,169,170,171,172,173,174,175,176,177,178,179,180,181,182,183,184,185,186,187,188,189,190,191,192,193,194,195,196,197,198,199,200,201,202,203,204,205,206,207,208,209,210,211,212,213,214,215,216,217,218,219,220,221,222,223,224,225,226,227,228,229,230,231,232,233,234,235,236,237,238,239,240,241,242,243,244,245,246,247,248,249,250,251,252,253,254,255,256,257,258,259,260,261,262,263,264,265,266,267,268,269,270,271,272,273,274,275,276,277,278,279,280,281,282,283,284,285,286,287,288,289,290,291,292,293,294,295,296,297,298,299,300]
["Contract signing","K20/K80/K90",null,{"$f":"SUM(G8:GH8)","v":0},null,"deadline"]
["Initial technical meetings","K20",null,{"$f":"SUM(G9:GH9)","v":0},null,"deadline"]
["Binding technical specification for OB 6 (Construction)","K20","eg., foundations for new boiler K20",{"$f":"SUM(G11:GH11)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Binding technical specification for OB 1 (Fuel management) ","K20","eg., point of entry for wooden chips in boiler K20",{"$f":"SUM(G13:GH13)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Binding technical specification for other OBs, for other suppliers of technological units ","K20",null,{"$f":"SUM(G15:GH15)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Approved implementation documentation for new boiler K20","K20",null,{"$f":"SUM(G17:GH17)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Handover and acceptance of construction site for K20","K20",null,{"$f":"SUM(G18:GH18)","v":0},null,"deadline"]
[null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Kotelna K20 - tkaninový filtr"]
["Boiler room K20 - the boiler itself including all components","K20",null,{"$f":"SUM(G21:GH21)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K20 - operating fuel storage tanks including transport of chips into boiler","K20",null,{"$f":"SUM(G23:GH23)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K20 - vents (air, flue, recirculation) including inner flue lines","K20",null,{"$f":"SUM(G25:GH25)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K20 - fabric filter","K20",null,{"$f":"SUM(G27:GH27)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K20 - DSI technology","K20",null,{"$f":"SUM(G29:GH29)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K20 - cooler and sorter of ash","K20",null,{"$f":"SUM(G31:GH31)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K20 - electrical installation","K20",null,{"$f":"SUM(G33:GH33)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K20 - automatic control system","K20","HW and SW",{"$f":"SUM(G35:GH35)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K20 - compressor station","K20",null,{"$f":"SUM(G37:GH37)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K20 - media connection","K20",null,{"$f":"SUM(G39:GH39)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K20 - outdoor flue lines including chimney connection","K20",null,{"$f":"SUM(G41:GH41)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K20 - outdoor pipeline bridge construction (connection of ash management and SNCR)","K20",null,{"$f":"SUM(G43:GH43)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K20 - cladding and roofing, completion of all construction activities","K20",null,{"$f":"SUM(G45:GH45)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K20 - other above not specified items","K20","specification of the minimum deadline - important items from the contractor's point of view",{"$f":"SUM(G47:GH47)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K20 - completion of construction works","K20","including the return of construction site equipment",{"$f":"SUM(G48:GH48)","v":0},null,"deadline"]
["Boiler room K20 - completion of installation works","K20","including the return of construction site equipment",{"$f":"SUM(G49:GH49)","v":0},null,"deadline"]
["Boiler room K20 - operating staff training","K20",null,{"$f":"SUM(G51:GH51)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K20 - preparation for comprehensive testing","K20","fuel transport provided etc.",{"$f":"SUM(G52:GH52)","v":0},null,"deadline"]
["Boiler room K20 - comprehensive testing","K20",null,{"$f":"SUM(G54:GH54)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K20 - trial operation","K20",null,{"$f":"SUM(G56:GH56)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K20 - guarantee test A","K20",null,{"$f":"SUM(G58:GH58)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K20 - preliminary acceptance of the Work PAC","K20",null,{"$f":"SUM(G60:GH60)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K20 - guarantee test B","K20",null,{"$f":"SUM(G62:GH62)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K20 - final acceptance of the Work FAC","K20",null,{"$f":"SUM(G64:GH64)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
[]
["Partial prices by week",null,null,null,null,null,{"$f":"SUM(G8:G64)","v":0},{"$f":"SUM(H8:H64)","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"SUM(BS8:BS64)","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"SUM(EE8:EE64)","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"SUM(GI8:GI64)","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"SUM(IM8:IM64)","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
["Partial prices by month",null,null,null,null,null,{"$f":"SUM(G66:J66)","v":0},null,null,null,{"$f":"SUM(K66:N66)","v":0},null,null,null,{"$f":"SUM(O66:R66)","v":0},null,null,null,{"$f":"SUM(S66:V66)","v":0},null,null,null,{"$f":"SUM(W66:Z66)","v":0},null,null,null,{"$f":"SUM(AA66:AD66)","v":0},null,null,null,{"$f":"SUM(AE66:AH66)","v":0},null,null,null,{"$f":"SUM(AI66:AL66)","v":0},null,null,null,{"$f":"SUM(AM66:AP66)","v":0},null,null,null,{"$f":"SUM(AQ66:AT66)","v":0},null,null,null,{"$f":"SUM(AU66:AX66)","v":0},null,null,null,{"$f":"SUM(AY66:BB66)","v":0},null,null,null,{"$f":"SUM(BC66:BF66)","v":0},null,null,null,{"$f":"SUM(BG66:BJ66)","v":0},null,null,null,{"$f":"SUM(BK66:BN66)","v":0},null,null,null,{"$f":"SUM(BO66:BR66)","v":0},null,null,null,{"$f":"SUM(BS66:BV66)","v":0},null,null,null,{"$f":"SUM(BW66:BZ66)","v":0},null,null,null,{"$f":"SUM(CA66:CD66)","v":0},null,null,null,{"$f":"SUM(CE66:CH66)","v":0},null,null,null,{"$f":"SUM(CI66:CL66)","v":0},null,null,null,{"$f":"SUM(CM66:CP66)","v":0},null,null,null,{"$f":"SUM(CQ66:CT66)","v":0},null,null,null,{"$f":"SUM(CU66:CX66)","v":0},null,null,null,{"$f":"SUM(CY66:DB66)","v":0},null,null,null,{"$f":"SUM(DC66:DF66)","v":0},null,null,null,{"$f":"SUM(DG66:DJ66)","v":0},null,null,null,{"$f":"SUM(DK66:DN66)","v":0},null,null,null,{"$f":"SUM(DO66:DR66)","v":0},null,null,null,{"$f":"SUM(DS66:DV66)","v":0},null,null,null,{"$f":"SUM(DW66:DZ66)","v":0},null,null,null,{"$f":"SUM(EA66:ED66)","v":0},null,null,null,{"$f":"SUM(EE66:EH66)","v":0},null,null,null,{"$f":"SUM(EI66:EL66)","v":0},null,null,null,{"$f":"SUM(EM66:EP66)","v":0},null,null,null,{"$f":"SUM(EQ66:ET66)","v":0},null,null,null,{"$f":"SUM(EU66:EX66)","v":0},null,null,null,{"$f":"SUM(EY66:FB66)","v":0},null,null,null,{"$f":"SUM(FC66:FF66)","v":0},null,null,null,{"$f":"SUM(FG66:FJ66)","v":0},null,null,null,{"$f":"SUM(FK66:FN66)","v":0},null,null,null,{"$f":"SUM(FO66:FR66)","v":0},null,null,null,{"$f":"SUM(FS66:FV66)","v":0},null,null,null,{"$f":"SUM(FW66:FZ66)","v":0},null,null,null,{"$f":"SUM(GA66:GD66)","v":0},null,null,null,{"$f":"SUM(GE66:GH66)","v":0},null,null,null,{"$f":"SUM(GI66:GL66)","v":0},null,null,null,{"$f":"SUM(GM66:GP66)","v":0},null,null,null,{"$f":"SUM(GQ66:GT66)","v":0},null,null,null,{"$f":"SUM(GU66:GX66)","v":0},null,null,null,{"$f":"SUM(GY66:HB66)","v":0},null,null,null,{"$f":"SUM(HC66:HF66)","v":0},null,null,null,{"$f":"SUM(HG66:HJ66)","v":0},null,null,null,{"$f":"SUM(HK66:HN66)","v":0},null,null,null,{"$f":"SUM(HO66:HR66)","v":0},null,null,null,{"$f":"SUM(HS66:HV66)","v":0},null,null,null,{"$f":"SUM(HW66:HZ66)","v":0},null,null,null,{"$f":"SUM(IA66:ID66)","v":0},null,null,null,{"$f":"SUM(IE66:IH66)","v":0},null,null,null,{"$f":"SUM(II66:IL66)","v":0},null,null,null,{"$f":"SUM(IM66:IP66)","v":0},null,null,null,{"$f":"SUM(IQ66:IT66)","v":0},null,null,null,{"$f":"SUM(IU66:IX66)","v":0},null,null,null,{"$f":"SUM(IY66:JB66)","v":0},null,null,null,{"$f":"SUM(JC66:JF66)","v":0},null,null,null,{"$f":"SUM(JG66:JJ66)","v":0},null,null,null,{"$f":"SUM(JK66:JN66)","v":0},null,null,null,{"$f":"SUM(JO66:JR66)","v":0},null,null,null,{"$f":"SUM(JS66:JV66)","v":0},null,null,null,{"$f":"SUM(JW66:JZ66)","v":0},null,null,null,{"$f":"SUM(KA66:KD66)","v":0},null,null,null,{"$f":"SUM(KE66:KH66)","v":0},null,null,null,{"$f":"SUM(KI66:KL66)","v":0},null,null,null,{"$f":"SUM(KM66:KP66)","v":0},null,null,null,{"$f":"SUM(KQ66:KT66)","v":0}]
["Price total",null,null,null,null,null,{"$f":"SUM(G66:KT66)","v":0}]
[]
["Notes:"]
["The Contractor fills in only the numerical values \"expected start (week)\" and \"expected end (week)\" in the windows that open after clicking \"fill in\"",null,null,null,null,null,null,"Contract signing"]
[null,null,null,null,null,null,null,"Initial technical meetings"]
[null,null,null,null,null,null,null,"Binding technical specification for OB 6 (Construction)"]
[null,null,null,null,null,null,null,"Binding technical specification for OB 1 (Fuel management) "]
[null,null,null,null,null,null,null,"Binding technical specification for other OBs, for other suppliers of technological units "]
[null,null,null,null,null,null,null,"Approved implementation documentation for new boiler K20"]
[null,null,null,null,null,null,null,"Handover and acceptance of construction site for K20"]
[null,null,null,null,null,null,null,"unoccupied"]
[null,null,null,null,null,null,null,"Boiler room K20 - the boiler itself including all components"]
[null,null,null,null,null,null,null,"Boiler room K20 - operating fuel storage tanks including transport of chips into boiler"]
[null,null,null,null,null,null,null,"Boiler room K20 - vents (air, flue, recirculation) including inner flue lines"]
[null,null,null,null,null,null,null,"Boiler room K20 - fabric filter"]
[null,null,null,null,null,null,null,"Boiler room K20 - DSI technology"]
["The price data is transferred to the table from the previous sheets",null,null,null,null,null,null,"Boiler room K20 - cooler and sorter of ash"]
[null,null,null,null,null,null,null,"Boiler room K20 - electrical installation"]
[null,null,null,null,null,null,null,"Boiler room K20 - automatic control system"]
[null,null,null,null,null,null,null,"Boiler room K20 - compressor station"]
[null,null,null,null,null,null,null,"Boiler room K20 - media connection"]
[null,null,null,null,null,null,null,"Boiler room K20 - outdoor flue lines including chimney connection"]
[null,null,null,null,null,null,null,"Boiler room K20 - outdoor pipeline bridge construction (connection of ash management and SNCR)"]
[null,null,null,null,null,null,null,"Boiler room K20 - cladding and roofing, completion of all construction activities"]
[null,null,null,null,null,null,null,"Boiler room K20 - other above not specified items"]
[null,null,null,null,null,null,null,"Boiler room K20 - completion of construction works"]
[null,null,null,null,null,null,null,"Boiler room K20 - completion of installation works"]
[null,null,null,null,null,null,null,"Boiler room K20 - operating staff training"]
[null,null,null,null,null,null,null,"Boiler room K20 - preparation for comprehensive testing"]
[null,null,null,null,null,null,null,"Boiler room K20 - comprehensive testing"]
[null,null,null,null,null,null,null,"Boiler room K20 - trial operation"]
[null,null,null,null,null,null,null,"Boiler room K20 - guarantee test A"]
[null,null,null,null,null,null,null,"Boiler room K20 - preliminary acceptance of the Work PAC"]
[null,null,null,null,null,null,null,"Boiler room K20 - guarantee test B"]
[null,null,null,null,null,null,null,"Boiler room K20 - final acceptance of the Work FAC"]

{"sheet":"K80 - time schedule","index":22,"n_rows":102,"n_cols":306,"rows_kept":102,"cut":false,"hidden":false,"merged":[[4,302,4,305],[3,6,3,305],[66,302,66,305],[67,6,67,305],[4,298,4,301],[66,190,66,193],[66,206,66,209],[66,210,66,213],[66,286,66,289],[66,294,66,297],[66,298,66,301],[4,190,4,193],[4,294,4,297],[4,78,4,81],[4,82,4,85],[4,86,4,89],[4,90,4,93],[4,94,4,97],[4,50,4,53],[4,146,4,149],[4,150,4,153],[4,54,4,57],[4,58,4,61],[4,62,4,65],[31,2,32,2],[33,2,34,2],[35,2,36,2],[37,2,38,2],[41,2,42,2],[43,2,44,2],[49,2,50,2],[52,2,53,2],[54,2,55,2],[67,0,67,5],[4,26,4,29],[4,30,4,33],[4,34,4,37],[4,38,4,41],[4,42,4,45],[13,0,14,0],[13,1,14,1],[15,0,16,0],[15,1,16,1],[23,0,24,0],[23,1,24,1],[25,0,26,0],[25,1,26,1],[27,0,28,0],[27,1,28,1],[19,0,20,0],[19,1,20,1],[19,2,20,2],[21,0,22,0],[21,1,22,1],[4,18,4,21],[4,22,4,25],[21,2,22,2],[3,4,5,4],[65,0,65,5],[66,0,66,5],[4,98,4,101],[4,102,4,105],[4,106,4,109],[4,110,4,113],[4,114,4,117],[4,118,4,121],[4,46,4,49],[3,0,5,0],[3,1,5,1],[3,2,5,2],[3,5,5,5],[4,6,4,9],[4,10,4,13],[4,14,4,17],[13,2,14,2],[15,2,16,2],[23,2,24,2],[25,2,26,2],[27,2,28,2],[29,2,30,2],[4,74,4,77],[4,66,4,69],[4,70,4,73],[4,122,4,125],[4,154,4,157],[4,158,4,161],[4,162,4,165],[4,166,4,169],[4,126,4,129],[4,130,4,133],[4,134,4,137],[4,138,4,141],[4,142,4,145],[4,238,4,241],[4,194,4,197],[4,198,4,201],[4,202,4,205],[4,206,4,209],[4,210,4,213],[4,214,4,217],[4,170,4,173],[4,174,4,177],[4,178,4,181],[4,182,4,185],[4,186,4,189],[4,290,4,293],[9,0,10,0],[9,1,10,1],[9,2,10,2],[11,0,12,0],[11,1,12,1],[11,2,12,2],[4,266,4,269],[4,270,4,273],[4,274,4,277],[4,278,4,281],[4,282,4,285],[4,286,4,289],[4,242,4,245],[4,246,4,249],[4,250,4,253],[4,254,4,257],[4,258,4,261],[4,262,4,265],[4,218,4,221],[4,222,4,225],[4,226,4,229],[4,230,4,233],[4,234,4,237],[35,0,36,0],[35,1,36,1],[37,0,38,0],[37,1,38,1],[39,0,40,0],[39,1,40,1],[29,0,30,0],[29,1,30,1],[31,0,32,0],[31,1,32,1],[33,0,34,0],[33,1,34,1],[49,0,50,0],[49,1,50,1],[52,0,53,0],[52,1,53,1],[54,0,55,0],[54,1,55,1],[39,2,40,2],[41,0,42,0],[41,1,42,1],[43,0,44,0],[43,1,44,1],[45,0,46,0],[45,1,46,1],[45,2,46,2],[62,0,63,0],[62,1,63,1],[56,0,57,0],[56,1,57,1],[58,0,59,0],[58,1,59,1],[60,0,61,0],[60,1,61,1],[56,2,57,2],[58,2,59,2],[60,2,61,2],[62,2,63,2],[66,22,66,25],[66,26,66,29],[66,30,66,33],[66,34,66,37],[66,38,66,41],[66,42,66,45],[66,6,66,9],[66,10,66,13],[66,14,66,17],[66,18,66,21],[66,110,66,113],[66,114,66,117],[66,70,66,73],[66,74,66,77],[66,78,66,81],[66,82,66,85],[66,86,66,89],[66,90,66,93],[66,46,66,49],[66,50,66,53],[66,54,66,57],[66,58,66,61],[66,62,66,65],[66,66,66,69],[66,290,66,293],[66,262,66,265],[66,266,66,269],[66,270,66,273],[66,274,66,277],[66,278,66,281],[66,282,66,285],[66,238,66,241],[66,242,66,245],[66,246,66,249],[66,250,66,253],[66,254,66,257],[66,258,66,261],[66,214,66,217],[66,218,66,221],[66,222,66,225],[66,226,66,229],[66,230,66,233],[66,234,66,237],[66,194,66,197],[66,198,66,201],[66,202,66,205],[3,3,5,3],[9,3,10,3],[11,3,12,3],[13,3,14,3],[15,3,16,3],[19,3,20,3],[21,3,22,3],[23,3,24,3],[66,166,66,169],[66,118,66,121],[25,3,26,3],[27,3,28,3],[29,3,30,3],[31,3,32,3],[33,3,34,3],[35,3,36,3],[37,3,38,3],[39,3,40,3],[41,3,42,3],[43,3,44,3],[45,3,46,3],[49,3,50,3],[52,3,53,3],[54,3,55,3],[56,3,57,3],[58,3,59,3],[60,3,61,3],[62,3,63,3],[66,170,66,173],[66,174,66,177],[66,178,66,181],[66,182,66,185],[66,186,66,189],[66,142,66,145],[66,146,66,149],[66,150,66,153],[66,154,66,157],[66,158,66,161],[66,162,66,165],[66,122,66,125],[66,126,66,129],[66,130,66,133],[66,134,66,137],[66,138,66,141],[66,94,66,97],[66,98,66,101],[66,102,66,105],[66,106,66,109]]}
[]
["Annex K to the Tender Documentation - price table and time schedule"]
[]
["Milestones","Stage","Comment","Price for item excl. VAT (EUR)",null,"Deadline / price excl. VAT (EUR)","Period"]
[null,null,null,null,null,null,"month 1",null,null,null,"month 2",null,null,null,"month 3",null,null,null,"month 4",null,null,null,"month 5",null,null,null,"month 6",null,null,null,"month 7",null,null,null,"month 8",null,null,null,"month 9",null,null,null,"month 10",null,null,null,"month 11",null,null,null,"month 12",null,null,null,"month 13",null,null,null,"month 14",null,null,null,"month 15",null,null,null,"month 16",null,null,null,"month 17",null,null,null,"month 18",null,null,null,"month 19",null,null,null,"month 20",null,null,null,"month 21",null,null,null,"month 22",null,null,null,"month 23",null,null,null,"month 24",null,null,null,"month 25",null,null,null,"month 26",null,null,null,"month 27",null,null,null,"month 28",null,null,null,"month 29",null,null,null,"month 30",null,null,null,"month 31",null,null,null,"month 32",null,null,null,"month 33",null,null,null,"month 34",null,null,null,"month 35",null,null,null,"month 36",null,null,null,"month 37",null,null,null,"month 38",null,null,null,"month 39",null,null,null,"month 40",null,null,null,"month 41",null,null,null,"month 42",null,null,null,"month 43",null,null,null,"month 44",null,null,null,"month 45",null,null,null,"month 46",null,null,null,"month 47",null,null,null,"month 48",null,null,null,"month 49",null,null,null,"month 50",null,null,null,"month 51",null,null,null,"month 52",null,null,null,"month 53",null,null,null,"month 54",null,null,null,"month 55",null,null,null,"month 56",null,null,null,"month 57",null,null,null,"month 58",null,null,null,"month 59",null,null,null,"month 60",null,null,null,"month 61",null,null,null,"month 62",null,null,null,"month 63",null,null,null,"month 64",null,null,null,"month 65",null,null,null,"month 66",null,null,null,"month 67",null,null,null,"month 68",null,null,null,"month 69",null,null,null,"month 70",null,null,null,"month 71",null,null,null,"month 72",null,null,null,"month 73",null,null,null,"month 74",null,null,null,"month 75"]
[null,null,null,null,null,null,"week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4"]
[0,0,80,null,null,null,1,2,3,4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,39,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61,62,63,64,65,66,67,68,69,70,71,72,73,74,75,76,77,78,79,80,81,82,83,84,85,86,87,88,89,90,91,92,93,94,95,96,97,98,99,100,101,102,103,104,105,106,107,108,109,110,111,112,113,114,115,116,117,118,119,120,121,122,123,124,125,126,127,128,129,130,131,132,133,134,135,136,137,138,139,140,141,142,143,144,145,146,147,148,149,150,151,152,153,154,155,156,157,158,159,160,161,162,163,164,165,166,167,168,169,170,171,172,173,174,175,176,177,178,179,180,181,182,183,184,185,186,187,188,189,190,191,192,193,194,195,196,197,198,199,200,201,202,203,204,205,206,207,208,209,210,211,212,213,214,215,216,217,218,219,220,221,222,223,224,225,226,227,228,229,230,231,232,233,234,235,236,237,238,239,240,241,242,243,244,245,246,247,248,249,250,251,252,253,254,255,256,257,258,259,260,261,262,263,264,265,266,267,268,269,270,271,272,273,274,275,276,277,278,279,280,281,282,283,284,285,286,287,288,289,290,291,292,293,294,295,296,297,298,299,300]
["Contract signing","K20/K80/K90",null,{"$f":"SUM(G8:GJ8)","v":0},null,"deadline"]
["Initial technical meetings","K80",null,{"$f":"SUM(G9:GJ9)","v":0},null,"deadline"]
["Binding technical specification for OB 6 (Construction)","K80",null,{"$f":"SUM(G11:GJ11)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Binding technical specification for OB 1 (Fuel management) ","K80","eg., point of entry for wooden chips on retrofit K80/K90",{"$f":"SUM(G13:GJ13)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Binding technical specification for other OBs, for other suppliers of technological units ","K80",null,{"$f":"SUM(G15:GJ15)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Approved implementation documentation for retrofit K80","K80",null,{"$f":"SUM(G17:GJ17)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Handover and acceptance of construction site for K80","K80",null,{"$f":"SUM(G18:GJ18)","v":0},null,"deadline"]
["Boiler room K80 - shutdown of boiler K80","K80",null,{"$f":"SUM(G19:GJ19)","v":0},null,"deadline"]
["Boiler room K80 - dismantling","K80","eg., original technologies, parts of unused steel structures etc.",{"$f":"SUM(G21:GJ21)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K80 - supply of combustion air","K80","start of delivery of new technologies for the boiler",{"$f":"SUM(G23:GJ23)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K80 - fuel silos, including transport of fuel to the boiler","K80",null,{"$f":"SUM(G25:GJ25)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K80 - air heating","K80",null,{"$f":"SUM(G27:GJ27)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K80 - overheating","K80",null,{"$f":"SUM(G29:GJ29)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K80 - economizer","K80",null,{"$f":"SUM(G31:GJ31)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K80 - lining","K80",null,{"$f":"SUM(G33:GJ33)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K80 - bottom of combustion chamber","K80",null,{"$f":"SUM(G35:GJ35)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K80 - flue lines, including fabric filter","K80",null,{"$f":"SUM(G37:GJ37)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K80 - electrical installation","K80",null,{"$f":"SUM(G39:GJ39)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K80 - management of automatic control system","K80","both HW and SW updates, SW connected with fuel management control station",{"$f":"SUM(G41:GJ41)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K80 - construction structures","K80",null,{"$f":"SUM(G43:GJ43)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K80 - ash management (transport piping, silos)","K80",null,{"$f":"SUM(G45:GJ45)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K80 - other above not specified items","K80","specification of the minimum deadline - important items from the contractor's point of view",{"$f":"SUM(G47:GJ47)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K80 - completion of construction works","K80","including the return of construction site equipment",{"$f":"SUM(G48:GJ48)","v":0},null,"deadline"]
["Boiler room K80 - completion of installation works","K80","including the return of construction site equipment",{"$f":"SUM(G49:GJ49)","v":0},null,"deadline"]
["Boiler room K80 - operating staff training","K80",null,{"$f":"SUM(G51:GJ51)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K80 - preparation for comprehensive testing","K80","fuel transport provided etc.",{"$f":"SUM(G52:GJ52)","v":0},null,"deadline"]
["Boiler room K80 - comprehensive testing","K80",null,{"$f":"SUM(G54:GJ54)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K80 - trial operation","K80",null,{"$f":"SUM(G56:GJ56)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K80 - guarantee test A","K80",null,{"$f":"SUM(G58:GJ58)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K80 - preliminary acceptance of the Work PAC","K80",null,{"$f":"SUM(G60:GJ60)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K80 - guarantee test B","K80",null,{"$f":"SUM(G62:GJ62)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K80 - final acceptance of the Work FAC","K80",null,{"$f":"SUM(G64:GJ64)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
[]
["Partial prices by week",null,null,null,null,null,{"$f":"SUM(G8:G64)","v":0},{"$f":"SUM(H8:H64)","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"SUM(BS8:BS64)","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"SUM(EE8:EE64)","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"SUM(GQ8:GQ64)","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"SUM(JC8:JC64)","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
["Partial prices by month",null,null,null,null,null,{"$f":"SUM(G66:J66)","v":0},null,null,null,{"$f":"SUM(K66:N66)","v":0},null,null,null,{"$f":"SUM(O66:R66)","v":0},null,null,null,{"$f":"SUM(S66:V66)","v":0},null,null,null,{"$f":"SUM(W66:Z66)","v":0},null,null,null,{"$f":"SUM(AA66:AD66)","v":0},null,null,null,{"$f":"SUM(AE66:AH66)","v":0},null,null,null,{"$f":"SUM(AI66:AL66)","v":0},null,null,null,{"$f":"SUM(AM66:AP66)","v":0},null,null,null,{"$f":"SUM(AQ66:AT66)","v":0},null,null,null,{"$f":"SUM(AU66:AX66)","v":0},null,null,null,{"$f":"SUM(AY66:BB66)","v":0},null,null,null,{"$f":"SUM(BC66:BF66)","v":0},null,null,null,{"$f":"SUM(BG66:BJ66)","v":0},null,null,null,{"$f":"SUM(BK66:BN66)","v":0},null,null,null,{"$f":"SUM(BO66:BR66)","v":0},null,null,null,{"$f":"SUM(BS66:BV66)","v":0},null,null,null,{"$f":"SUM(BW66:BZ66)","v":0},null,null,null,{"$f":"SUM(CA66:CD66)","v":0},null,null,null,{"$f":"SUM(CE66:CH66)","v":0},null,null,null,{"$f":"SUM(CI66:CL66)","v":0},null,null,null,{"$f":"SUM(CM66:CP66)","v":0},null,null,null,{"$f":"SUM(CQ66:CT66)","v":0},null,null,null,{"$f":"SUM(CU66:CX66)","v":0},null,null,null,{"$f":"SUM(CY66:DB66)","v":0},null,null,null,{"$f":"SUM(DC66:DF66)","v":0},null,null,null,{"$f":"SUM(DG66:DJ66)","v":0},null,null,null,{"$f":"SUM(DK66:DN66)","v":0},null,null,null,{"$f":"SUM(DO66:DR66)","v":0},null,null,null,{"$f":"SUM(DS66:DV66)","v":0},null,null,null,{"$f":"SUM(DW66:DZ66)","v":0},null,null,null,{"$f":"SUM(EA66:ED66)","v":0},null,null,null,{"$f":"SUM(EE66:EH66)","v":0},null,null,null,{"$f":"SUM(EI66:EL66)","v":0},null,null,null,{"$f":"SUM(EM66:EP66)","v":0},null,null,null,{"$f":"SUM(EQ66:ET66)","v":0},null,null,null,{"$f":"SUM(EU66:EX66)","v":0},null,null,null,{"$f":"SUM(EY66:FB66)","v":0},null,null,null,{"$f":"SUM(FC66:FF66)","v":0},null,null,null,{"$f":"SUM(FG66:FJ66)","v":0},null,null,null,{"$f":"SUM(FK66:FN66)","v":0},null,null,null,{"$f":"SUM(FO66:FR66)","v":0},null,null,null,{"$f":"SUM(FS66:FV66)","v":0},null,null,null,{"$f":"SUM(FW66:FZ66)","v":0},null,null,null,{"$f":"SUM(GA66:GD66)","v":0},null,null,null,{"$f":"SUM(GE66:GH66)","v":0},null,null,null,{"$f":"SUM(GI66:GL66)","v":0},null,null,null,{"$f":"SUM(GM66:GP66)","v":0},null,null,null,{"$f":"SUM(GQ66:GT66)","v":0},null,null,null,{"$f":"SUM(GU66:GX66)","v":0},null,null,null,{"$f":"SUM(GY66:HB66)","v":0},null,null,null,{"$f":"SUM(HC66:HF66)","v":0},null,null,null,{"$f":"SUM(HG66:HJ66)","v":0},null,null,null,{"$f":"SUM(HK66:HN66)","v":0},null,null,null,{"$f":"SUM(HO66:HR66)","v":0},null,null,null,{"$f":"SUM(HS66:HV66)","v":0},null,null,null,{"$f":"SUM(HW66:HZ66)","v":0},null,null,null,{"$f":"SUM(IA66:ID66)","v":0},null,null,null,{"$f":"SUM(IE66:IH66)","v":0},null,null,null,{"$f":"SUM(II66:IL66)","v":0},null,null,null,{"$f":"SUM(IM66:IP66)","v":0},null,null,null,{"$f":"SUM(IQ66:IT66)","v":0},null,null,null,{"$f":"SUM(IU66:IX66)","v":0},null,null,null,{"$f":"SUM(IY66:JB66)","v":0},null,null,null,{"$f":"SUM(JC66:JF66)","v":0},null,null,null,{"$f":"SUM(JG66:JJ66)","v":0},null,null,null,{"$f":"SUM(JK66:JN66)","v":0},null,null,null,{"$f":"SUM(JO66:JR66)","v":0},null,null,null,{"$f":"SUM(JS66:JV66)","v":0},null,null,null,{"$f":"SUM(JW66:JZ66)","v":0},null,null,null,{"$f":"SUM(KA66:KD66)","v":0},null,null,null,{"$f":"SUM(KE66:KH66)","v":0},null,null,null,{"$f":"SUM(KI66:KL66)","v":0},null,null,null,{"$f":"SUM(KM66:KP66)","v":0},null,null,null,{"$f":"SUM(KQ66:KT66)","v":0}]
["Total price",null,null,null,null,null,{"$f":"SUM(G66:KT66)","v":0}]
[]
["Notes:"]
["The Contractor fills in only the numerical values \"expected start (week)\" and \"expected end (week)\" in the windows that open after clicking \"fill in\"",null,null,null,null,null,null,"Contract signing"]
[null,null,null,null,null,null,null,"Initial technical meetings"]
[null,null,null,null,null,null,null,"Binding technical specification for OB 6 (Construction)"]
[null,null,null,null,null,null,null,"Binding technical specification for OB 1 (Fuel management) "]
[null,null,null,null,null,null,null,"Binding technical specification for other OBs, for other suppliers of technological units "]
[null,null,null,null,null,null,null,"Approved implementation documentation for retrofit K90"]
[null,null,null,null,null,null,null,"Handover and acceptance of construction site for K90"]
[null,null,null,null,null,null,null,"Boiler room K80 - shutdown of boiler K90"]
[null,null,null,null,null,null,null,"Boiler room K80 - dismantling"]
[null,null,null,null,null,null,null,"Boiler room K80 - supply of combustion air"]
[null,null,null,null,null,null,null,"Boiler room K80 - fuel silos, including transport of fuel to the boiler"]
[null,null,null,null,null,null,null,"Boiler room K80 - air heating"]
[null,null,null,null,null,null,null,"Boiler room K80 - overheating"]
["The price data is transferred to the table from the previous sheets",null,null,null,null,null,null,"Boiler room K80 - economizer"]
[null,null,null,null,null,null,null,"Boiler room K80 - lining"]
[null,null,null,null,null,null,null,"Boiler room K80 - bottom of combustion chamber"]
[null,null,null,null,null,null,null,"Boiler room K80 - flue lines, including fabric filter"]
[null,null,null,null,null,null,null,"Boiler room K80 - electrical installation"]
[null,null,null,null,null,null,null,"Boiler room K80 - management of automatic control systém"]
[null,null,null,null,null,null,null,"Boiler room K80 - construction structures"]
[null,null,null,null,null,null,null,"Boiler room K80 - ash management (transport piping, silos)"]
[null,null,null,null,null,null,null,"Boiler room K80 - other above not specified items"]
[null,null,null,null,null,null,null,"Boiler room K80 - completion of construction works"]
[null,null,null,null,null,null,null,"Boiler room K80 - completion of installation works"]
[null,null,null,null,null,null,null,"Boiler room K80 - operating staff training"]
[null,null,null,null,null,null,null,"Boiler room K80 - preparation for comprehensive testing"]
[null,null,null,null,null,null,null,"Boiler room K80 - comprehensive testing"]
[null,null,null,null,null,null,null,"Boiler room K80 - trial operation"]
[null,null,null,null,null,null,null,"Boiler room K80 - guarantee test A"]
[null,null,null,null,null,null,null,"Boiler room K80 - preliminary acceptance of the Work PAC"]
[null,null,null,null,null,null,null,"Boiler room K80 - guarantee test B"]
[null,null,null,null,null,null,null,"Boiler room K80 - final acceptance of the Work FAC"]

{"sheet":"K90 - time schedule","index":23,"n_rows":102,"n_cols":306,"rows_kept":102,"cut":false,"hidden":false,"merged":[[4,294,4,297],[4,298,4,301],[66,190,66,193],[66,294,66,297],[66,298,66,301],[4,302,4,305],[3,6,3,305],[66,302,66,305],[67,6,67,305],[4,190,4,193],[4,74,4,77],[4,78,4,81],[4,82,4,85],[4,86,4,89],[4,90,4,93],[4,94,4,97],[4,50,4,53],[4,170,4,173],[4,54,4,57],[4,58,4,61],[4,62,4,65],[4,66,4,69],[4,70,4,73],[4,122,4,125],[67,0,67,5],[13,2,14,2],[15,2,16,2],[23,2,24,2],[25,2,26,2],[27,2,28,2],[29,2,30,2],[31,2,32,2],[33,2,34,2],[35,2,36,2],[37,2,38,2],[41,2,42,2],[43,2,44,2],[49,2,50,2],[52,2,53,2],[54,2,55,2],[56,2,57,2],[58,2,59,2],[60,2,61,2],[62,2,63,2],[15,0,16,0],[15,1,16,1],[13,0,14,0],[13,1,14,1],[3,0,5,0],[3,1,5,1],[3,2,5,2],[3,5,5,5],[4,6,4,9],[4,10,4,13],[4,14,4,17],[4,18,4,21],[4,22,4,25],[4,162,4,165],[4,166,4,169],[4,138,4,141],[4,142,4,145],[3,4,5,4],[4,26,4,29],[4,30,4,33],[4,34,4,37],[4,38,4,41],[4,42,4,45],[4,46,4,49],[4,98,4,101],[4,102,4,105],[4,106,4,109],[4,110,4,113],[4,114,4,117],[4,118,4,121],[4,126,4,129],[4,130,4,133],[4,134,4,137],[4,146,4,149],[4,150,4,153],[4,154,4,157],[4,158,4,161],[4,238,4,241],[4,194,4,197],[4,198,4,201],[4,202,4,205],[4,206,4,209],[4,210,4,213],[4,214,4,217],[4,174,4,177],[4,178,4,181],[4,182,4,185],[4,186,4,189],[4,290,4,293],[9,0,10,0],[9,1,10,1],[9,2,10,2],[11,0,12,0],[11,1,12,1],[11,2,12,2],[4,266,4,269],[4,270,4,273],[4,274,4,277],[4,278,4,281],[4,282,4,285],[4,286,4,289],[4,242,4,245],[4,246,4,249],[4,250,4,253],[4,254,4,257],[4,258,4,261],[4,262,4,265],[4,218,4,221],[4,222,4,225],[4,226,4,229],[4,230,4,233],[4,234,4,237],[23,0,24,0],[23,1,24,1],[25,0,26,0],[25,1,26,1],[27,0,28,0],[27,1,28,1],[19,0,20,0],[19,1,20,1],[19,2,20,2],[21,0,22,0],[21,1,22,1],[21,2,22,2],[35,0,36,0],[35,1,36,1],[37,0,38,0],[37,1,38,1],[39,0,40,0],[39,1,40,1],[29,0,30,0],[29,1,30,1],[31,0,32,0],[31,1,32,1],[33,0,34,0],[33,1,34,1],[49,0,50,0],[49,1,50,1],[52,0,53,0],[52,1,53,1],[54,0,55,0],[54,1,55,1],[39,2,40,2],[41,0,42,0],[41,1,42,1],[43,0,44,0],[43,1,44,1],[45,0,46,0],[45,1,46,1],[45,2,46,2],[62,0,63,0],[62,1,63,1],[66,6,66,9],[66,10,66,13],[66,14,66,17],[66,18,66,21],[56,0,57,0],[56,1,57,1],[58,0,59,0],[58,1,59,1],[60,0,61,0],[60,1,61,1],[65,0,65,5],[66,0,66,5],[62,3,63,3],[66,46,66,49],[66,50,66,53],[66,54,66,57],[66,58,66,61],[66,62,66,65],[66,66,66,69],[66,22,66,25],[66,26,66,29],[66,30,66,33],[66,34,66,37],[66,38,66,41],[66,42,66,45],[66,94,66,97],[66,98,66,101],[66,102,66,105],[66,106,66,109],[66,110,66,113],[66,114,66,117],[66,70,66,73],[66,74,66,77],[66,78,66,81],[66,82,66,85],[66,86,66,89],[66,90,66,93],[66,142,66,145],[66,146,66,149],[66,150,66,153],[66,154,66,157],[66,158,66,161],[66,162,66,165],[66,118,66,121],[66,122,66,125],[66,126,66,129],[66,130,66,133],[66,134,66,137],[66,138,66,141],[66,202,66,205],[66,206,66,209],[66,210,66,213],[66,166,66,169],[66,170,66,173],[66,174,66,177],[66,178,66,181],[66,182,66,185],[66,186,66,189],[66,286,66,289],[66,290,66,293],[66,262,66,265],[66,266,66,269],[66,270,66,273],[66,274,66,277],[66,278,66,281],[66,282,66,285],[66,238,66,241],[66,242,66,245],[66,246,66,249],[66,250,66,253],[66,254,66,257],[66,258,66,261],[66,214,66,217],[66,218,66,221],[66,222,66,225],[66,226,66,229],[66,230,66,233],[66,234,66,237],[66,194,66,197],[66,198,66,201],[3,3,5,3],[9,3,10,3],[11,3,12,3],[13,3,14,3],[15,3,16,3],[19,3,20,3],[21,3,22,3],[23,3,24,3],[25,3,26,3],[45,3,46,3],[49,3,50,3],[52,3,53,3],[54,3,55,3],[56,3,57,3],[58,3,59,3],[60,3,61,3],[27,3,28,3],[29,3,30,3],[31,3,32,3],[33,3,34,3],[35,3,36,3],[37,3,38,3],[39,3,40,3],[41,3,42,3],[43,3,44,3]]}
[]
["Annex K to the Tender Documentation - price table and time schedule"]
[]
["Milestones","Stage","Comment","Price for item excl. VAT (EUR)",null,"Deadline / price excl. VAT (EUR)","Period"]
[null,null,null,null,null,null,"month 1",null,null,null,"month 2",null,null,null,"month 3",null,null,null,"month 4",null,null,null,"month 5",null,null,null,"month 6",null,null,null,"month 7",null,null,null,"month 8",null,null,null,"month 9",null,null,null,"month 10",null,null,null,"month 11",null,null,null,"month 12",null,null,null,"month 13",null,null,null,"month 14",null,null,null,"month 15",null,null,null,"month 16",null,null,null,"month 17",null,null,null,"month 18",null,null,null,"month 19",null,null,null,"month 20",null,null,null,"month 21",null,null,null,"month 22",null,null,null,"month 23",null,null,null,"month 24",null,null,null,"month 25",null,null,null,"month 26",null,null,null,"month 27",null,null,null,"month 28",null,null,null,"month 29",null,null,null,"month 30",null,null,null,"month 31",null,null,null,"month 32",null,null,null,"month 33",null,null,null,"month 34",null,null,null,"month 35",null,null,null,"month 36",null,null,null,"month 37",null,null,null,"month 38",null,null,null,"month 39",null,null,null,"month 40",null,null,null,"month 41",null,null,null,"month 42",null,null,null,"month 43",null,null,null,"month 44",null,null,null,"month 45",null,null,null,"month 46",null,null,null,"month 47",null,null,null,"month 48",null,null,null,"month 49",null,null,null,"month 50",null,null,null,"month 51",null,null,null,"month 52",null,null,null,"month 53",null,null,null,"month 54",null,null,null,"month 55",null,null,null,"month 56",null,null,null,"month 57",null,null,null,"month 58",null,null,null,"month 59",null,null,null,"month 60",null,null,null,"month 61",null,null,null,"month 62",null,null,null,"month 63",null,null,null,"month 64",null,null,null,"month 65",null,null,null,"month 66",null,null,null,"month 67",null,null,null,"month 68",null,null,null,"month 69",null,null,null,"month 70",null,null,null,"month 71",null,null,null,"month 72",null,null,null,"month 73",null,null,null,"month 74",null,null,null,"month 75"]
[null,null,null,null,null,null,"week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4"]
[null,null,90,null,null,null,1,2,3,4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,39,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61,62,63,64,65,66,67,68,69,70,71,72,73,74,75,76,77,78,79,80,81,82,83,84,85,86,87,88,89,90,91,92,93,94,95,96,97,98,99,100,101,102,103,104,105,106,107,108,109,110,111,112,113,114,115,116,117,118,119,120,121,122,123,124,125,126,127,128,129,130,131,132,133,134,135,136,137,138,139,140,141,142,143,144,145,146,147,148,149,150,151,152,153,154,155,156,157,158,159,160,161,162,163,164,165,166,167,168,169,170,171,172,173,174,175,176,177,178,179,180,181,182,183,184,185,186,187,188,189,190,191,192,193,194,195,196,197,198,199,200,201,202,203,204,205,206,207,208,209,210,211,212,213,214,215,216,217,218,219,220,221,222,223,224,225,226,227,228,229,230,231,232,233,234,235,236,237,238,239,240,241,242,243,244,245,246,247,248,249,250,251,252,253,254,255,256,257,258,259,260,261,262,263,264,265,266,267,268,269,270,271,272,273,274,275,276,277,278,279,280,281,282,283,284,285,286,287,288,289,290,291,292,293,294,295,296,297,298,299,300]
["Contract signing","K20/K80/K90",null,{"$f":"SUM(G8:GJ8)","v":0},null,"deadline"]
["Initial technical meetings","K90",null,{"$f":"SUM(G9:GJ9)","v":0},null,"deadline"]
["Binding technical specification for OB 6 (Construction)","K90",null,{"$f":"SUM(G11:GJ11)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Binding technical specification for OB 1 (Fuel management) ","K90","eg., point of entry for wooden chips on retrofit K80/K90",{"$f":"SUM(G13:GJ13)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Binding technical specification for other OBs, for other suppliers of technological units ","K90",null,{"$f":"SUM(G15:GJ15)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Approved implementation documentation for retrofit K90","K90",null,{"$f":"SUM(G17:GJ17)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Handover and acceptance of construction site for K90","K90",null,{"$f":"SUM(G18:GJ18)","v":0},null,"deadline"]
["Boiler room K90 - shutdown of boiler K90","K90",null,{"$f":"SUM(G19:GJ19)","v":0},null,"deadline"]
["Boiler room K90 - dismantling","K90","eg., original technologies, parts of unused steel structures etc.",{"$f":"SUM(G21:GJ21)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K90 - supply of combustion air","K90","start of delivery of new technologies for the boiler",{"$f":"SUM(G23:GJ23)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K90 - fuel silos, including transport of fuel to the boiler","K90",null,{"$f":"SUM(G25:GJ25)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K90 - air heating","K90",null,{"$f":"SUM(G27:GJ27)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K90 - overheating","K90",null,{"$f":"SUM(G29:GJ29)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K90 - economizer","K90",null,{"$f":"SUM(G31:GJ31)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K90 - lining","K90",null,{"$f":"SUM(G33:GJ33)","v":0},null,"termín"]
[null,null,null,null,null,"price"]
["Boiler room K90 - bottom of combustion chamber","K90",null,{"$f":"SUM(G35:GJ35)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K90 - flue lines, including fabric filter","K90",null,{"$f":"SUM(G37:GJ37)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K90 - electrical installation","K90",null,{"$f":"SUM(G39:GJ39)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K90 - management of automatic control systém","K90","both HW and SW updates, SW connected with fuel management control station",{"$f":"SUM(G41:GJ41)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K90 - construction structures","K90",null,{"$f":"SUM(G43:GJ43)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K90 - ash management (transport piping, silos)","K90",null,{"$f":"SUM(G45:GJ45)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K90 - other above not specified items","K90","specification of the minimum deadline - important items from the contractor's point of view",{"$f":"SUM(G47:GJ47)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K90 - completion of construction works","K90","including the return of construction site equipment",{"$f":"SUM(G48:GJ48)","v":0},null,"deadline"]
["Boiler room K90 - completion of installation works","K90","including the return of construction site equipment",{"$f":"SUM(G49:GJ49)","v":0},null,"deadline"]
["Boiler room K90 - operating staff training","K90",null,{"$f":"SUM(G51:GJ51)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K90 - preparation for comprehensive testing","K90","fuel transport provided etc.",{"$f":"SUM(G52:GJ52)","v":0},null,"deadline"]
["Boiler room K90 - comprehensive testing","K90",null,{"$f":"SUM(G54:GJ54)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K90 - trial operation","K90",null,{"$f":"SUM(G56:GJ56)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K90 - guarantee test A","K90",null,{"$f":"SUM(G58:GJ58)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K90 - preliminary acceptance of the Work PAC","K90",null,{"$f":"SUM(G60:GJ60)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K90 - guarantee test B","K90",null,{"$f":"SUM(G62:GJ62)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
["Boiler room K90 - final acceptance of the Work FAC","K90",null,{"$f":"SUM(G64:GJ64)","v":0},null,"deadline"]
[null,null,null,null,null,"price"]
[]
["Partial prices by week",null,null,null,null,null,{"$f":"SUM(G8:G64)","v":0},{"$f":"SUM(H8:H64)","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"SUM(BS8:BS64)","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"SUM(EE8:EE64)","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"SUM(GQ8:GQ64)","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"SUM(JC8:JC64)","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
["Partial prices by month",null,null,null,null,null,{"$f":"SUM(G66:J66)","v":0},null,null,null,{"$f":"SUM(K66:N66)","v":0},null,null,null,{"$f":"SUM(O66:R66)","v":0},null,null,null,{"$f":"SUM(S66:V66)","v":0},null,null,null,{"$f":"SUM(W66:Z66)","v":0},null,null,null,{"$f":"SUM(AA66:AD66)","v":0},null,null,null,{"$f":"SUM(AE66:AH66)","v":0},null,null,null,{"$f":"SUM(AI66:AL66)","v":0},null,null,null,{"$f":"SUM(AM66:AP66)","v":0},null,null,null,{"$f":"SUM(AQ66:AT66)","v":0},null,null,null,{"$f":"SUM(AU66:AX66)","v":0},null,null,null,{"$f":"SUM(AY66:BB66)","v":0},null,null,null,{"$f":"SUM(BC66:BF66)","v":0},null,null,null,{"$f":"SUM(BG66:BJ66)","v":0},null,null,null,{"$f":"SUM(BK66:BN66)","v":0},null,null,null,{"$f":"SUM(BO66:BR66)","v":0},null,null,null,{"$f":"SUM(BS66:BV66)","v":0},null,null,null,{"$f":"SUM(BW66:BZ66)","v":0},null,null,null,{"$f":"SUM(CA66:CD66)","v":0},null,null,null,{"$f":"SUM(CE66:CH66)","v":0},null,null,null,{"$f":"SUM(CI66:CL66)","v":0},null,null,null,{"$f":"SUM(CM66:CP66)","v":0},null,null,null,{"$f":"SUM(CQ66:CT66)","v":0},null,null,null,{"$f":"SUM(CU66:CX66)","v":0},null,null,null,{"$f":"SUM(CY66:DB66)","v":0},null,null,null,{"$f":"SUM(DC66:DF66)","v":0},null,null,null,{"$f":"SUM(DG66:DJ66)","v":0},null,null,null,{"$f":"SUM(DK66:DN66)","v":0},null,null,null,{"$f":"SUM(DO66:DR66)","v":0},null,null,null,{"$f":"SUM(DS66:DV66)","v":0},null,null,null,{"$f":"SUM(DW66:DZ66)","v":0},null,null,null,{"$f":"SUM(EA66:ED66)","v":0},null,null,null,{"$f":"SUM(EE66:EH66)","v":0},null,null,null,{"$f":"SUM(EI66:EL66)","v":0},null,null,null,{"$f":"SUM(EM66:EP66)","v":0},null,null,null,{"$f":"SUM(EQ66:ET66)","v":0},null,null,null,{"$f":"SUM(EU66:EX66)","v":0},null,null,null,{"$f":"SUM(EY66:FB66)","v":0},null,null,null,{"$f":"SUM(FC66:FF66)","v":0},null,null,null,{"$f":"SUM(FG66:FJ66)","v":0},null,null,null,{"$f":"SUM(FK66:FN66)","v":0},null,null,null,{"$f":"SUM(FO66:FR66)","v":0},null,null,null,{"$f":"SUM(FS66:FV66)","v":0},null,null,null,{"$f":"SUM(FW66:FZ66)","v":0},null,null,null,{"$f":"SUM(GA66:GD66)","v":0},null,null,null,{"$f":"SUM(GE66:GH66)","v":0},null,null,null,{"$f":"SUM(GI66:GL66)","v":0},null,null,null,{"$f":"SUM(GM66:GP66)","v":0},null,null,null,{"$f":"SUM(GQ66:GT66)","v":0},null,null,null,{"$f":"SUM(GU66:GX66)","v":0},null,null,null,{"$f":"SUM(GY66:HB66)","v":0},null,null,null,{"$f":"SUM(HC66:HF66)","v":0},null,null,null,{"$f":"SUM(HG66:HJ66)","v":0},null,null,null,{"$f":"SUM(HK66:HN66)","v":0},null,null,null,{"$f":"SUM(HO66:HR66)","v":0},null,null,null,{"$f":"SUM(HS66:HV66)","v":0},null,null,null,{"$f":"SUM(HW66:HZ66)","v":0},null,null,null,{"$f":"SUM(IA66:ID66)","v":0},null,null,null,{"$f":"SUM(IE66:IH66)","v":0},null,null,null,{"$f":"SUM(II66:IL66)","v":0},null,null,null,{"$f":"SUM(IM66:IP66)","v":0},null,null,null,{"$f":"SUM(IQ66:IT66)","v":0},null,null,null,{"$f":"SUM(IU66:IX66)","v":0},null,null,null,{"$f":"SUM(IY66:JB66)","v":0},null,null,null,{"$f":"SUM(JC66:JF66)","v":0},null,null,null,{"$f":"SUM(JG66:JJ66)","v":0},null,null,null,{"$f":"SUM(JK66:JN66)","v":0},null,null,null,{"$f":"SUM(JO66:JR66)","v":0},null,null,null,{"$f":"SUM(JS66:JV66)","v":0},null,null,null,{"$f":"SUM(JW66:JZ66)","v":0},null,null,null,{"$f":"SUM(KA66:KD66)","v":0},null,null,null,{"$f":"SUM(KE66:KH66)","v":0},null,null,null,{"$f":"SUM(KI66:KL66)","v":0},null,null,null,{"$f":"SUM(KM66:KP66)","v":0},null,null,null,{"$f":"SUM(KQ66:KT66)","v":0}]
["Total price",null,null,null,null,null,{"$f":"SUM(G66:KT66)","v":0}]
[]
["Notes:"]
["The Contractor fills in only the numerical values \"expected start (week)\" and \"expected end (week)\" in the windows that open after clicking \"fill in\"",null,null,null,null,null,null,"Contract signing"]
[null,null,null,null,null,null,null,"Initial technical meetings"]
[null,null,null,null,null,null,null,"Binding technical specification for OB 6 (Construction)"]
[null,null,null,null,null,null,null,"Binding technical specification for OB 1 (Fuel management) "]
[null,null,null,null,null,null,null,"Binding technical specification for other OBs, for other suppliers of technological units "]
[null,null,null,null,null,null,null,"Approved implementation documentation for retrofit K90"]
[null,null,null,null,null,null,null,"Handover and acceptance of construction site for K90"]
[null,null,null,null,null,null,null,"Boiler room K90 - shutdown of boiler K90"]
[null,null,null,null,null,null,null,"Boiler room K90 - dismantling"]
[null,null,null,null,null,null,null,"Boiler room K90 - supply of combustion air"]
[null,null,null,null,null,null,null,"Boiler room K90 - fuel silos, including transport of fuel to the boiler"]
[null,null,null,null,null,null,null,"Boiler room K90 - air heating"]
[null,null,null,null,null,null,null,"Boiler room K90 - overheating"]
["Údaje o cenách se do tabulky přenášejí z předcházejících listů",null,null,null,null,null,null,"Boiler room K90 - economizer"]
[null,null,null,null,null,null,null,"Boiler room K90 - lining"]
[null,null,null,null,null,null,null,"Boiler room K90 - bottom of combustion chamber"]
[null,null,null,null,null,null,null,"Boiler room K90 - flue lines, including fabric filter"]
[null,null,null,null,null,null,null,"Boiler room K90 - electrical installation"]
[null,null,null,null,null,null,null,"Boiler room K90 - management of automatic control systém"]
[null,null,null,null,null,null,null,"Boiler room K90 - construction structures"]
[null,null,null,null,null,null,null,"Boiler room K90 - ash management (transport piping, silos)"]
[null,null,null,null,null,null,null,"Boiler room K90 - other above not specified items"]
[null,null,null,null,null,null,null,"Boiler room K90 - completion of construction works"]
[null,null,null,null,null,null,null,"Boiler room K90 - completion of installation works"]
[null,null,null,null,null,null,null,"Boiler room K90 - operating staff training"]
[null,null,null,null,null,null,null,"Boiler room K90 - preparation for comprehensive testing"]
[null,null,null,null,null,null,null,"Boiler room K90 - comprehensive testing"]
[null,null,null,null,null,null,null,"Boiler room K90 - trial operation"]
[null,null,null,null,null,null,null,"Boiler room K90 - guarantee test A"]
[null,null,null,null,null,null,null,"Boiler room K90 - preliminary acceptance of the Work PAC"]
[null,null,null,null,null,null,null,"Boiler room K90 - guarantee test B"]
[null,null,null,null,null,null,null,"Boiler room K90 - final acceptance of the Work FAC"]

{"sheet":"time schedule","index":24,"n_rows":129,"n_cols":302,"rows_kept":129,"cut":false,"hidden":false,"merged":[[4,290,4,293],[4,294,4,297],[4,298,4,301],[3,2,3,301],[4,46,4,49],[4,14,4,17],[4,18,4,21],[4,22,4,25],[4,26,4,29],[4,30,4,33],[4,34,4,37],[4,38,4,41],[4,42,4,45],[4,94,4,97],[4,50,4,53],[4,54,4,57],[3,0,5,0],[3,1,5,1],[4,2,4,5],[4,6,4,9],[4,10,4,13],[4,58,4,61],[4,62,4,65],[4,66,4,69],[4,70,4,73],[4,74,4,77],[4,78,4,81],[4,82,4,85],[4,86,4,89],[4,90,4,93],[4,142,4,145],[4,98,4,101],[4,102,4,105],[4,106,4,109],[4,110,4,113],[4,114,4,117],[4,118,4,121],[4,122,4,125],[4,126,4,129],[4,130,4,133],[4,134,4,137],[4,138,4,141],[4,190,4,193],[4,146,4,149],[4,150,4,153],[4,154,4,157],[4,158,4,161],[4,162,4,165],[4,166,4,169],[4,170,4,173],[4,174,4,177],[4,178,4,181],[4,182,4,185],[4,186,4,189],[4,238,4,241],[4,194,4,197],[4,198,4,201],[4,202,4,205],[4,206,4,209],[4,210,4,213],[4,214,4,217],[4,218,4,221],[4,222,4,225],[4,226,4,229],[4,230,4,233],[4,234,4,237],[4,286,4,289],[4,242,4,245],[4,246,4,249],[4,250,4,253],[4,254,4,257],[4,258,4,261],[4,262,4,265],[4,266,4,269],[4,270,4,273],[4,274,4,277],[4,278,4,281],[4,282,4,285]]}
[]
["Annex K to the Tender Documentation - price table and time schedule"]
[]
["Milestones","Stage","Period"]
[null,null,"month 1",null,null,null,"month 2",null,null,null,"month 3",null,null,null,"month 4",null,null,null,"month 5",null,null,null,"month 6",null,null,null,"month 7",null,null,null,"month 8",null,null,null,"month 9",null,null,null,"month 10",null,null,null,"month 11",null,null,null,"month 12",null,null,null,"month 13",null,null,null,"month 14",null,null,null,"month 15",null,null,null,"month 16",null,null,null,"month 17",null,null,null,"month 18",null,null,null,"month 19",null,null,null,"month 20",null,null,null,"month 21",null,null,null,"month 22",null,null,null,"month 23",null,null,null,"month 24",null,null,null,"month 25",null,null,null,"month 26",null,null,null,"month 27",null,null,null,"month 28",null,null,null,"month 29",null,null,null,"month 30",null,null,null,"month 31",null,null,null,"month 32",null,null,null,"month 33",null,null,null,"month 34",null,null,null,"month 35",null,null,null,"month 36",null,null,null,"month 37",null,null,null,"month 38",null,null,null,"month 39",null,null,null,"month 40",null,null,null,"month 41",null,null,null,"month 42",null,null,null,"month 43",null,null,null,"month 44",null,null,null,"month 45",null,null,null,"month 46",null,null,null,"month 47",null,null,null,"month 48",null,null,null,"month 49",null,null,null,"month 50",null,null,null,"month 51",null,null,null,"month 52",null,null,null,"month 53",null,null,null,"month 54",null,null,null,"month 55",null,null,null,"month 56",null,null,null,"month 57",null,null,null,"month 58",null,null,null,"month 59",null,null,null,"month 60",null,null,null,"month 61",null,null,null,"month 62",null,null,null,"month 63",null,null,null,"month 64",null,null,null,"month 65",null,null,null,"month 66",null,null,null,"month 67",null,null,null,"month 68",null,null,null,"month 69",null,null,null,"month 70",null,null,null,"month 71",null,null,null,"month 72",null,null,null,"month 73",null,null,null,"month 74",null,null,null,"month 75"]
[null,null,"week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4"]
[1,1,1,2,3,4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,39,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61,62,63,64,65,66,67,68,69,70,71,72,73,74,75,76,77,78,79,80,81,82,83,84,85,86,87,88,89,90,91,92,93,94,95,96,97,98,99,100,101,102,103,104,105,106,107,108,109,110,111,112,113,114,115,116,117,118,119,120,121,122,123,124,125,126,127,128,129,130,131,132,133,134,135,136,137,138,139,140,141,142,143,144,145,146,147,148,149,150,151,152,153,154,155,156,157,158,159,160,161,162,163,164,165,166,167,168,169,170,171,172,173,174,175,176,177,178,179,180,181,182,183,184,185,186,187,188,189,190,191,192,193,194,195,196,197,198,199,200,201,202,203,204,205,206,207,208,209,210,211,212,213,214,215,216,217,218,219,220,221,222,223,224,225,226,227,228,229,230,231,232,233,234,235,236,237,238,239,240,241,242,243,244,245,246,247,248,249,250,251,252,253,254,255,256,257,258,259,260,261,262,263,264,265,266,267,268,269,270,271,272,273,274,275,276,277,278,279,280,281,282,283,284,285,286,287,288,289,290,291,292,293,294,295,296,297,298,299,300]
["Contract signing","K20/K80/K90",{"$f":"'K20 - time schedule'!G8","v":0},{"$f":"'K20 - time schedule'!H8","v":0},{"$f":"'K20 - time schedule'!I8","v":0},{"$f":"'K20 - time schedule'!J8","v":0},{"$f":"'K20 - time schedule'!K8","v":0},{"$f":"'K20 - time schedule'!L8","v":0},{"$f":"'K20 - time schedule'!M8","v":0},{"$f":"'K20 - time schedule'!N8","v":0},{"$f":"'K20 - time schedule'!O8","v":0},{"$f":"'K20 - time schedule'!P8","v":0},{"$f":"'K20 - time schedule'!Q8","v":0},{"$f":"'K20 - time schedule'!R8","v":0},{"$f":"'K20 - time schedule'!S8","v":0},{"$f":"'K20 - time schedule'!T8","v":0},{"$f":"'K20 - time schedule'!U8","v":0},{"$f":"'K20 - time schedule'!V8","v":0},{"$f":"'K20 - time schedule'!W8","v":0},{"$f":"'K20 - time schedule'!X8","v":0},{"$f":"'K20 - time schedule'!Y8","v":0},{"$f":"'K20 - time schedule'!Z8","v":0},{"$f":"'K20 - time schedule'!AA8","v":0},{"$f":"'K20 - time schedule'!AB8","v":0},{"$f":"'K20 - time schedule'!AC8","v":0},{"$f":"'K20 - time schedule'!AD8","v":0},{"$f":"'K20 - time schedule'!AE8","v":0},{"$f":"'K20 - time schedule'!AF8","v":0},{"$f":"'K20 - time schedule'!AG8","v":0},{"$f":"'K20 - time schedule'!AH8","v":0},{"$f":"'K20 - time schedule'!AI8","v":0},{"$f":"'K20 - time schedule'!AJ8","v":0},{"$f":"'K20 - time schedule'!AK8","v":0},{"$f":"'K20 - time schedule'!AL8","v":0},{"$f":"'K20 - time schedule'!AM8","v":0},{"$f":"'K20 - time schedule'!AN8","v":0},{"$f":"'K20 - time schedule'!AO8","v":0},{"$f":"'K20 - time schedule'!AP8","v":0},{"$f":"'K20 - time schedule'!AQ8","v":0},{"$f":"'K20 - time schedule'!AR8","v":0},{"$f":"'K20 - time schedule'!AS8","v":0},{"$f":"'K20 - time schedule'!AT8","v":0},{"$f":"'K20 - time schedule'!AU8","v":0},{"$f":"'K20 - time schedule'!AV8","v":0},{"$f":"'K20 - time schedule'!AW8","v":0},{"$f":"'K20 - time schedule'!AX8","v":0},{"$f":"'K20 - time schedule'!AY8","v":0},{"$f":"'K20 - time schedule'!AZ8","v":0},{"$f":"'K20 - time schedule'!BA8","v":0},{"$f":"'K20 - time schedule'!BB8","v":0},{"$f":"'K20 - time schedule'!BC8","v":0},{"$f":"'K20 - time schedule'!BD8","v":0},{"$f":"'K20 - time schedule'!BE8","v":0},{"$f":"'K20 - time schedule'!BF8","v":0},{"$f":"'K20 - time schedule'!BG8","v":0},{"$f":"'K20 - time schedule'!BH8","v":0},{"$f":"'K20 - time schedule'!BI8","v":0},{"$f":"'K20 - time schedule'!BJ8","v":0},{"$f":"'K20 - time schedule'!BK8","v":0},{"$f":"'K20 - time schedule'!BL8","v":0},{"$f":"'K20 - time schedule'!BM8","v":0},{"$f":"'K20 - time schedule'!BN8","v":0},{"$f":"'K20 - time schedule'!BO8","v":0},{"$f":"'K20 - time schedule'!BP8","v":0},{"$f":"'K20 - time schedule'!BQ8","v":0},{"$f":"'K20 - time schedule'!BR8","v":0},{"$f":"'K20 - time schedule'!BS8","v":0},{"$f":"'K20 - time schedule'!BT8","v":0},{"$f":"'K20 - time schedule'!BU8","v":0},{"$f":"'K20 - time schedule'!BV8","v":0},{"$f":"'K20 - time schedule'!BW8","v":0},{"$f":"'K20 - time schedule'!BX8","v":0},{"$f":"'K20 - time schedule'!BY8","v":0},{"$f":"'K20 - time schedule'!BZ8","v":0},{"$f":"'K20 - time schedule'!CA8","v":0},{"$f":"'K20 - time schedule'!CB8","v":0},{"$f":"'K20 - time schedule'!CC8","v":0},{"$f":"'K20 - time schedule'!CD8","v":0},{"$f":"'K20 - time schedule'!CE8","v":0},{"$f":"'K20 - time schedule'!CF8","v":0},{"$f":"'K20 - time schedule'!CG8","v":0},{"$f":"'K20 - time schedule'!CH8","v":0},{"$f":"'K20 - time schedule'!CI8","v":0},{"$f":"'K20 - time schedule'!CJ8","v":0},{"$f":"'K20 - time schedule'!CK8","v":0},{"$f":"'K20 - time schedule'!CL8","v":0},{"$f":"'K20 - time schedule'!CM8","v":0},{"$f":"'K20 - time schedule'!CN8","v":0},{"$f":"'K20 - time schedule'!CO8","v":0},{"$f":"'K20 - time schedule'!CP8","v":0},{"$f":"'K20 - time schedule'!CQ8","v":0},{"$f":"'K20 - time schedule'!CR8","v":0},{"$f":"'K20 - time schedule'!CS8","v":0},{"$f":"'K20 - time schedule'!CT8","v":0},{"$f":"'K20 - time schedule'!CU8","v":0},{"$f":"'K20 - time schedule'!CV8","v":0},{"$f":"'K20 - time schedule'!CW8","v":0},{"$f":"'K20 - time schedule'!CX8","v":0},{"$f":"'K20 - time schedule'!CY8","v":0},{"$f":"'K20 - time schedule'!CZ8","v":0},{"$f":"'K20 - time schedule'!DA8","v":0},{"$f":"'K20 - time schedule'!DB8","v":0},{"$f":"'K20 - time schedule'!DC8","v":0},{"$f":"'K20 - time schedule'!DD8","v":0},{"$f":"'K20 - time schedule'!DE8","v":0},{"$f":"'K20 - time schedule'!DF8","v":0},{"$f":"'K20 - time schedule'!DG8","v":0},{"$f":"'K20 - time schedule'!DH8","v":0},{"$f":"'K20 - time schedule'!DI8","v":0},{"$f":"'K20 - time schedule'!DJ8","v":0},{"$f":"'K20 - time schedule'!DK8","v":0},{"$f":"'K20 - time schedule'!DL8","v":0},{"$f":"'K20 - time schedule'!DM8","v":0},{"$f":"'K20 - time schedule'!DN8","v":0},{"$f":"'K20 - time schedule'!DO8","v":0},{"$f":"'K20 - time schedule'!DP8","v":0},{"$f":"'K20 - time schedule'!DQ8","v":0},{"$f":"'K20 - time schedule'!DR8","v":0},{"$f":"'K20 - time schedule'!DS8","v":0},{"$f":"'K20 - time schedule'!DT8","v":0},{"$f":"'K20 - time schedule'!DU8","v":0},{"$f":"'K20 - time schedule'!DV8","v":0},{"$f":"'K20 - time schedule'!DW8","v":0},{"$f":"'K20 - time schedule'!DX8","v":0},{"$f":"'K20 - time schedule'!DY8","v":0},{"$f":"'K20 - time schedule'!DZ8","v":0},{"$f":"'K20 - time schedule'!EA8","v":0},{"$f":"'K20 - time schedule'!EB8","v":0},{"$f":"'K20 - time schedule'!EC8","v":0},{"$f":"'K20 - time schedule'!ED8","v":0},{"$f":"'K20 - time schedule'!EE8","v":0},{"$f":"'K20 - time schedule'!EF8","v":0},{"$f":"'K20 - time schedule'!EG8","v":0},{"$f":"'K20 - time schedule'!EH8","v":0},{"$f":"'K20 - time schedule'!EI8","v":0},{"$f":"'K20 - time schedule'!EJ8","v":0},{"$f":"'K20 - time schedule'!EK8","v":0},{"$f":"'K20 - time schedule'!EL8","v":0},{"$f":"'K20 - time schedule'!EM8","v":0},{"$f":"'K20 - time schedule'!EN8","v":0},{"$f":"'K20 - time schedule'!EO8","v":0},{"$f":"'K20 - time schedule'!EP8","v":0},{"$f":"'K20 - time schedule'!EQ8","v":0},{"$f":"'K20 - time schedule'!ER8","v":0},{"$f":"'K20 - time schedule'!ES8","v":0},{"$f":"'K20 - time schedule'!ET8","v":0},{"$f":"'K20 - time schedule'!EU8","v":0},{"$f":"'K20 - time schedule'!EV8","v":0},{"$f":"'K20 - time schedule'!EW8","v":0},{"$f":"'K20 - time schedule'!EX8","v":0},{"$f":"'K20 - time schedule'!EY8","v":0},{"$f":"'K20 - time schedule'!EZ8","v":0},{"$f":"'K20 - time schedule'!FA8","v":0},{"$f":"'K20 - time schedule'!FB8","v":0},{"$f":"'K20 - time schedule'!FC8","v":0},{"$f":"'K20 - time schedule'!FD8","v":0},{"$f":"'K20 - time schedule'!FE8","v":0},{"$f":"'K20 - time schedule'!FF8","v":0},{"$f":"'K20 - time schedule'!FG8","v":0},{"$f":"'K20 - time schedule'!FH8","v":0},{"$f":"'K20 - time schedule'!FI8","v":0},{"$f":"'K20 - time schedule'!FJ8","v":0},{"$f":"'K20 - time schedule'!FK8","v":0},{"$f":"'K20 - time schedule'!FL8","v":0},{"$f":"'K20 - time schedule'!FM8","v":0},{"$f":"'K20 - time schedule'!FN8","v":0},{"$f":"'K20 - time schedule'!FO8","v":0},{"$f":"'K20 - time schedule'!FP8","v":0},{"$f":"'K20 - time schedule'!FQ8","v":0},{"$f":"'K20 - time schedule'!FR8","v":0},{"$f":"'K20 - time schedule'!FS8","v":0},{"$f":"'K20 - time schedule'!FT8","v":0},{"$f":"'K20 - time schedule'!FU8","v":0},{"$f":"'K20 - time schedule'!FV8","v":0},{"$f":"'K20 - time schedule'!FW8","v":0},{"$f":"'K20 - time schedule'!FX8","v":0},{"$f":"'K20 - time schedule'!FY8","v":0},{"$f":"'K20 - time schedule'!FZ8","v":0},{"$f":"'K20 - time schedule'!GA8","v":0},{"$f":"'K20 - time schedule'!GB8","v":0},{"$f":"'K20 - time schedule'!GC8","v":0},{"$f":"'K20 - time schedule'!GD8","v":0},{"$f":"'K20 - time schedule'!GE8","v":0},{"$f":"'K20 - time schedule'!GF8","v":0},{"$f":"'K20 - time schedule'!GG8","v":0},{"$f":"'K20 - time schedule'!GH8","v":0},{"$f":"'K20 - time schedule'!GI8","v":0},{"$f":"'K20 - time schedule'!GJ8","v":0},{"$f":"'K20 - time schedule'!GK8","v":0},{"$f":"'K20 - time schedule'!GL8","v":0},{"$f":"'K20 - time schedule'!GM8","v":0},{"$f":"'K20 - time schedule'!GN8","v":0},{"$f":"'K20 - time schedule'!GO8","v":0},{"$f":"'K20 - time schedule'!GP8","v":0},{"$f":"'K20 - time schedule'!GQ8","v":0},{"$f":"'K20 - time schedule'!GR8","v":0},{"$f":"'K20 - time schedule'!GS8","v":0},{"$f":"'K20 - time schedule'!GT8","v":0},{"$f":"'K20 - time schedule'!GU8","v":0},{"$f":"'K20 - time schedule'!GV8","v":0},{"$f":"'K20 - time schedule'!GW8","v":0},{"$f":"'K20 - time schedule'!GX8","v":0},{"$f":"'K20 - time schedule'!GY8","v":0},{"$f":"'K20 - time schedule'!GZ8","v":0},{"$f":"'K20 - time schedule'!HA8","v":0},{"$f":"'K20 - time schedule'!HB8","v":0},{"$f":"'K20 - time schedule'!HC8","v":0},{"$f":"'K20 - time schedule'!HD8","v":0},{"$f":"'K20 - time schedule'!HE8","v":0},{"$f":"'K20 - time schedule'!HF8","v":0},{"$f":"'K20 - time schedule'!HG8","v":0},{"$f":"'K20 - time schedule'!HH8","v":0},{"$f":"'K20 - time schedule'!HI8","v":0},{"$f":"'K20 - time schedule'!HJ8","v":0},{"$f":"'K20 - time schedule'!HK8","v":0},{"$f":"'K20 - time schedule'!HL8","v":0},{"$f":"'K20 - time schedule'!HM8","v":0},{"$f":"'K20 - time schedule'!HN8","v":0},{"$f":"'K20 - time schedule'!HO8","v":0},{"$f":"'K20 - time schedule'!HP8","v":0},{"$f":"'K20 - time schedule'!HQ8","v":0},{"$f":"'K20 - time schedule'!HR8","v":0},{"$f":"'K20 - time schedule'!HS8","v":0},{"$f":"'K20 - time schedule'!HT8","v":0},{"$f":"'K20 - time schedule'!HU8","v":0},{"$f":"'K20 - time schedule'!HV8","v":0},{"$f":"'K20 - time schedule'!HW8","v":0},{"$f":"'K20 - time schedule'!HX8","v":0},{"$f":"'K20 - time schedule'!HY8","v":0},{"$f":"'K20 - time schedule'!HZ8","v":0},{"$f":"'K20 - time schedule'!IA8","v":0},{"$f":"'K20 - time schedule'!IB8","v":0},{"$f":"'K20 - time schedule'!IC8","v":0},{"$f":"'K20 - time schedule'!ID8","v":0},{"$f":"'K20 - time schedule'!IE8","v":0},{"$f":"'K20 - time schedule'!IF8","v":0},{"$f":"'K20 - time schedule'!IG8","v":0},{"$f":"'K20 - time schedule'!IH8","v":0},{"$f":"'K20 - time schedule'!II8","v":0},{"$f":"'K20 - time schedule'!IJ8","v":0},{"$f":"'K20 - time schedule'!IK8","v":0},{"$f":"'K20 - time schedule'!IL8","v":0},{"$f":"'K20 - time schedule'!IM8","v":0},{"$f":"'K20 - time schedule'!IN8","v":0},{"$f":"'K20 - time schedule'!IO8","v":0},{"$f":"'K20 - time schedule'!IP8","v":0},{"$f":"'K20 - time schedule'!IQ8","v":0},{"$f":"'K20 - time schedule'!IR8","v":0},{"$f":"'K20 - time schedule'!IS8","v":0},{"$f":"'K20 - time schedule'!IT8","v":0},{"$f":"'K20 - time schedule'!IU8","v":0},{"$f":"'K20 - time schedule'!IV8","v":0},{"$f":"'K20 - time schedule'!IW8","v":0},{"$f":"'K20 - time schedule'!IX8","v":0},{"$f":"'K20 - time schedule'!IY8","v":0},{"$f":"'K20 - time schedule'!IZ8","v":0},{"$f":"'K20 - time schedule'!JA8","v":0},{"$f":"'K20 - time schedule'!JB8","v":0},{"$f":"'K20 - time schedule'!JC8","v":0},{"$f":"'K20 - time schedule'!JD8","v":0},{"$f":"'K20 - time schedule'!JE8","v":0},{"$f":"'K20 - time schedule'!JF8","v":0},{"$f":"'K20 - time schedule'!JG8","v":0},{"$f":"'K20 - time schedule'!JH8","v":0},{"$f":"'K20 - time schedule'!JI8","v":0},{"$f":"'K20 - time schedule'!JJ8","v":0},{"$f":"'K20 - time schedule'!JK8","v":0},{"$f":"'K20 - time schedule'!JL8","v":0},{"$f":"'K20 - time schedule'!JM8","v":0},{"$f":"'K20 - time schedule'!JN8","v":0},{"$f":"'K20 - time schedule'!JO8","v":0},{"$f":"'K20 - time schedule'!JP8","v":0},{"$f":"'K20 - time schedule'!JQ8","v":0},{"$f":"'K20 - time schedule'!JR8","v":0},{"$f":"'K20 - time schedule'!JS8","v":0},{"$f":"'K20 - time schedule'!JT8","v":0},{"$f":"'K20 - time schedule'!JU8","v":0},{"$f":"'K20 - time schedule'!JV8","v":0},{"$f":"'K20 - time schedule'!JW8","v":0},{"$f":"'K20 - time schedule'!JX8","v":0},{"$f":"'K20 - time schedule'!JY8","v":0},{"$f":"'K20 - time schedule'!JZ8","v":0},{"$f":"'K20 - time schedule'!KA8","v":0},{"$f":"'K20 - time schedule'!KB8","v":0},{"$f":"'K20 - time schedule'!KC8","v":0},{"$f":"'K20 - time schedule'!KD8","v":0},{"$f":"'K20 - time schedule'!KE8","v":0},{"$f":"'K20 - time schedule'!KF8","v":0},{"$f":"'K20 - time schedule'!KG8","v":0},{"$f":"'K20 - time schedule'!KH8","v":0},{"$f":"'K20 - time schedule'!KI8","v":0},{"$f":"'K20 - time schedule'!KJ8","v":0},{"$f":"'K20 - time schedule'!KK8","v":0},{"$f":"'K20 - time schedule'!KL8","v":0},{"$f":"'K20 - time schedule'!KM8","v":0},{"$f":"'K20 - time schedule'!KN8","v":0},{"$f":"'K20 - time schedule'!KO8","v":0},{"$f":"'K20 - time schedule'!KP8","v":0},{"$f":"'K20 - time schedule'!KQ8","v":0},{"$f":"'K20 - time schedule'!KR8","v":0},{"$f":"'K20 - time schedule'!KS8","v":0},{"$f":"'K20 - time schedule'!KT8","v":0}]
["Boiler room K20 - initial technical meetings","K20",{"$f":"'K20 - time schedule'!G9","v":0},{"$f":"'K20 - time schedule'!H9","v":0},{"$f":"'K20 - time schedule'!I9","v":0},{"$f":"'K20 - time schedule'!J9","v":0},{"$f":"'K20 - time schedule'!K9","v":0},{"$f":"'K20 - time schedule'!L9","v":0},{"$f":"'K20 - time schedule'!M9","v":0},{"$f":"'K20 - time schedule'!N9","v":0},{"$f":"'K20 - time schedule'!O9","v":0},{"$f":"'K20 - time schedule'!P9","v":0},{"$f":"'K20 - time schedule'!Q9","v":0},{"$f":"'K20 - time schedule'!R9","v":0},{"$f":"'K20 - time schedule'!S9","v":0},{"$f":"'K20 - time schedule'!T9","v":0},{"$f":"'K20 - time schedule'!U9","v":0},{"$f":"'K20 - time schedule'!V9","v":0},{"$f":"'K20 - time schedule'!W9","v":0},{"$f":"'K20 - time schedule'!X9","v":0},{"$f":"'K20 - time schedule'!Y9","v":0},{"$f":"'K20 - time schedule'!Z9","v":0},{"$f":"'K20 - time schedule'!AA9","v":0},{"$f":"'K20 - time schedule'!AB9","v":0},{"$f":"'K20 - time schedule'!AC9","v":0},{"$f":"'K20 - time schedule'!AD9","v":0},{"$f":"'K20 - time schedule'!AE9","v":0},{"$f":"'K20 - time schedule'!AF9","v":0},{"$f":"'K20 - time schedule'!AG9","v":0},{"$f":"'K20 - time schedule'!AH9","v":0},{"$f":"'K20 - time schedule'!AI9","v":0},{"$f":"'K20 - time schedule'!AJ9","v":0},{"$f":"'K20 - time schedule'!AK9","v":0},{"$f":"'K20 - time schedule'!AL9","v":0},{"$f":"'K20 - time schedule'!AM9","v":0},{"$f":"'K20 - time schedule'!AN9","v":0},{"$f":"'K20 - time schedule'!AO9","v":0},{"$f":"'K20 - time schedule'!AP9","v":0},{"$f":"'K20 - time schedule'!AQ9","v":0},{"$f":"'K20 - time schedule'!AR9","v":0},{"$f":"'K20 - time schedule'!AS9","v":0},{"$f":"'K20 - time schedule'!AT9","v":0},{"$f":"'K20 - time schedule'!AU9","v":0},{"$f":"'K20 - time schedule'!AV9","v":0},{"$f":"'K20 - time schedule'!AW9","v":0},{"$f":"'K20 - time schedule'!AX9","v":0},{"$f":"'K20 - time schedule'!AY9","v":0},{"$f":"'K20 - time schedule'!AZ9","v":0},{"$f":"'K20 - time schedule'!BA9","v":0},{"$f":"'K20 - time schedule'!BB9","v":0},{"$f":"'K20 - time schedule'!BC9","v":0},{"$f":"'K20 - time schedule'!BD9","v":0},{"$f":"'K20 - time schedule'!BE9","v":0},{"$f":"'K20 - time schedule'!BF9","v":0},{"$f":"'K20 - time schedule'!BG9","v":0},{"$f":"'K20 - time schedule'!BH9","v":0},{"$f":"'K20 - time schedule'!BI9","v":0},{"$f":"'K20 - time schedule'!BJ9","v":0},{"$f":"'K20 - time schedule'!BK9","v":0},{"$f":"'K20 - time schedule'!BL9","v":0},{"$f":"'K20 - time schedule'!BM9","v":0},{"$f":"'K20 - time schedule'!BN9","v":0},{"$f":"'K20 - time schedule'!BO9","v":0},{"$f":"'K20 - time schedule'!BP9","v":0},{"$f":"'K20 - time schedule'!BQ9","v":0},{"$f":"'K20 - time schedule'!BR9","v":0},{"$f":"'K20 - time schedule'!BS9","v":0},{"$f":"'K20 - time schedule'!BT9","v":0},{"$f":"'K20 - time schedule'!BU9","v":0},{"$f":"'K20 - time schedule'!BV9","v":0},{"$f":"'K20 - time schedule'!BW9","v":0},{"$f":"'K20 - time schedule'!BX9","v":0},{"$f":"'K20 - time schedule'!BY9","v":0},{"$f":"'K20 - time schedule'!BZ9","v":0},{"$f":"'K20 - time schedule'!CA9","v":0},{"$f":"'K20 - time schedule'!CB9","v":0},{"$f":"'K20 - time schedule'!CC9","v":0},{"$f":"'K20 - time schedule'!CD9","v":0},{"$f":"'K20 - time schedule'!CE9","v":0},{"$f":"'K20 - time schedule'!CF9","v":0},{"$f":"'K20 - time schedule'!CG9","v":0},{"$f":"'K20 - time schedule'!CH9","v":0},{"$f":"'K20 - time schedule'!CI9","v":0},{"$f":"'K20 - time schedule'!CJ9","v":0},{"$f":"'K20 - time schedule'!CK9","v":0},{"$f":"'K20 - time schedule'!CL9","v":0},{"$f":"'K20 - time schedule'!CM9","v":0},{"$f":"'K20 - time schedule'!CN9","v":0},{"$f":"'K20 - time schedule'!CO9","v":0},{"$f":"'K20 - time schedule'!CP9","v":0},{"$f":"'K20 - time schedule'!CQ9","v":0},{"$f":"'K20 - time schedule'!CR9","v":0},{"$f":"'K20 - time schedule'!CS9","v":0},{"$f":"'K20 - time schedule'!CT9","v":0},{"$f":"'K20 - time schedule'!CU9","v":0},{"$f":"'K20 - time schedule'!CV9","v":0},{"$f":"'K20 - time schedule'!CW9","v":0},{"$f":"'K20 - time schedule'!CX9","v":0},{"$f":"'K20 - time schedule'!CY9","v":0},{"$f":"'K20 - time schedule'!CZ9","v":0},{"$f":"'K20 - time schedule'!DA9","v":0},{"$f":"'K20 - time schedule'!DB9","v":0},{"$f":"'K20 - time schedule'!DC9","v":0},{"$f":"'K20 - time schedule'!DD9","v":0},{"$f":"'K20 - time schedule'!DE9","v":0},{"$f":"'K20 - time schedule'!DF9","v":0},{"$f":"'K20 - time schedule'!DG9","v":0},{"$f":"'K20 - time schedule'!DH9","v":0},{"$f":"'K20 - time schedule'!DI9","v":0},{"$f":"'K20 - time schedule'!DJ9","v":0},{"$f":"'K20 - time schedule'!DK9","v":0},{"$f":"'K20 - time schedule'!DL9","v":0},{"$f":"'K20 - time schedule'!DM9","v":0},{"$f":"'K20 - time schedule'!DN9","v":0},{"$f":"'K20 - time schedule'!DO9","v":0},{"$f":"'K20 - time schedule'!DP9","v":0},{"$f":"'K20 - time schedule'!DQ9","v":0},{"$f":"'K20 - time schedule'!DR9","v":0},{"$f":"'K20 - time schedule'!DS9","v":0},{"$f":"'K20 - time schedule'!DT9","v":0},{"$f":"'K20 - time schedule'!DU9","v":0},{"$f":"'K20 - time schedule'!DV9","v":0},{"$f":"'K20 - time schedule'!DW9","v":0},{"$f":"'K20 - time schedule'!DX9","v":0},{"$f":"'K20 - time schedule'!DY9","v":0},{"$f":"'K20 - time schedule'!DZ9","v":0},{"$f":"'K20 - time schedule'!EA9","v":0},{"$f":"'K20 - time schedule'!EB9","v":0},{"$f":"'K20 - time schedule'!EC9","v":0},{"$f":"'K20 - time schedule'!ED9","v":0},{"$f":"'K20 - time schedule'!EE9","v":0},{"$f":"'K20 - time schedule'!EF9","v":0},{"$f":"'K20 - time schedule'!EG9","v":0},{"$f":"'K20 - time schedule'!EH9","v":0},{"$f":"'K20 - time schedule'!EI9","v":0},{"$f":"'K20 - time schedule'!EJ9","v":0},{"$f":"'K20 - time schedule'!EK9","v":0},{"$f":"'K20 - time schedule'!EL9","v":0},{"$f":"'K20 - time schedule'!EM9","v":0},{"$f":"'K20 - time schedule'!EN9","v":0},{"$f":"'K20 - time schedule'!EO9","v":0},{"$f":"'K20 - time schedule'!EP9","v":0},{"$f":"'K20 - time schedule'!EQ9","v":0},{"$f":"'K20 - time schedule'!ER9","v":0},{"$f":"'K20 - time schedule'!ES9","v":0},{"$f":"'K20 - time schedule'!ET9","v":0},{"$f":"'K20 - time schedule'!EU9","v":0},{"$f":"'K20 - time schedule'!EV9","v":0},{"$f":"'K20 - time schedule'!EW9","v":0},{"$f":"'K20 - time schedule'!EX9","v":0},{"$f":"'K20 - time schedule'!EY9","v":0},{"$f":"'K20 - time schedule'!EZ9","v":0},{"$f":"'K20 - time schedule'!FA9","v":0},{"$f":"'K20 - time schedule'!FB9","v":0},{"$f":"'K20 - time schedule'!FC9","v":0},{"$f":"'K20 - time schedule'!FD9","v":0},{"$f":"'K20 - time schedule'!FE9","v":0},{"$f":"'K20 - time schedule'!FF9","v":0},{"$f":"'K20 - time schedule'!FG9","v":0},{"$f":"'K20 - time schedule'!FH9","v":0},{"$f":"'K20 - time schedule'!FI9","v":0},{"$f":"'K20 - time schedule'!FJ9","v":0},{"$f":"'K20 - time schedule'!FK9","v":0},{"$f":"'K20 - time schedule'!FL9","v":0},{"$f":"'K20 - time schedule'!FM9","v":0},{"$f":"'K20 - time schedule'!FN9","v":0},{"$f":"'K20 - time schedule'!FO9","v":0},{"$f":"'K20 - time schedule'!FP9","v":0},{"$f":"'K20 - time schedule'!FQ9","v":0},{"$f":"'K20 - time schedule'!FR9","v":0},{"$f":"'K20 - time schedule'!FS9","v":0},{"$f":"'K20 - time schedule'!FT9","v":0},{"$f":"'K20 - time schedule'!FU9","v":0},{"$f":"'K20 - time schedule'!FV9","v":0},{"$f":"'K20 - time schedule'!FW9","v":0},{"$f":"'K20 - time schedule'!FX9","v":0},{"$f":"'K20 - time schedule'!FY9","v":0},{"$f":"'K20 - time schedule'!FZ9","v":0},{"$f":"'K20 - time schedule'!GA9","v":0},{"$f":"'K20 - time schedule'!GB9","v":0},{"$f":"'K20 - time schedule'!GC9","v":0},{"$f":"'K20 - time schedule'!GD9","v":0},{"$f":"'K20 - time schedule'!GE9","v":0},{"$f":"'K20 - time schedule'!GF9","v":0},{"$f":"'K20 - time schedule'!GG9","v":0},{"$f":"'K20 - time schedule'!GH9","v":0},{"$f":"'K20 - time schedule'!GI9","v":0},{"$f":"'K20 - time schedule'!GJ9","v":0},{"$f":"'K20 - time schedule'!GK9","v":0},{"$f":"'K20 - time schedule'!GL9","v":0},{"$f":"'K20 - time schedule'!GM9","v":0},{"$f":"'K20 - time schedule'!GN9","v":0},{"$f":"'K20 - time schedule'!GO9","v":0},{"$f":"'K20 - time schedule'!GP9","v":0},{"$f":"'K20 - time schedule'!GQ9","v":0},{"$f":"'K20 - time schedule'!GR9","v":0},{"$f":"'K20 - time schedule'!GS9","v":0},{"$f":"'K20 - time schedule'!GT9","v":0},{"$f":"'K20 - time schedule'!GU9","v":0},{"$f":"'K20 - time schedule'!GV9","v":0},{"$f":"'K20 - time schedule'!GW9","v":0},{"$f":"'K20 - time schedule'!GX9","v":0},{"$f":"'K20 - time schedule'!GY9","v":0},{"$f":"'K20 - time schedule'!GZ9","v":0},{"$f":"'K20 - time schedule'!HA9","v":0},{"$f":"'K20 - time schedule'!HB9","v":0},{"$f":"'K20 - time schedule'!HC9","v":0},{"$f":"'K20 - time schedule'!HD9","v":0},{"$f":"'K20 - time schedule'!HE9","v":0},{"$f":"'K20 - time schedule'!HF9","v":0},{"$f":"'K20 - time schedule'!HG9","v":0},{"$f":"'K20 - time schedule'!HH9","v":0},{"$f":"'K20 - time schedule'!HI9","v":0},{"$f":"'K20 - time schedule'!HJ9","v":0},{"$f":"'K20 - time schedule'!HK9","v":0},{"$f":"'K20 - time schedule'!HL9","v":0},{"$f":"'K20 - time schedule'!HM9","v":0},{"$f":"'K20 - time schedule'!HN9","v":0},{"$f":"'K20 - time schedule'!HO9","v":0},{"$f":"'K20 - time schedule'!HP9","v":0},{"$f":"'K20 - time schedule'!HQ9","v":0},{"$f":"'K20 - time schedule'!HR9","v":0},{"$f":"'K20 - time schedule'!HS9","v":0},{"$f":"'K20 - time schedule'!HT9","v":0},{"$f":"'K20 - time schedule'!HU9","v":0},{"$f":"'K20 - time schedule'!HV9","v":0},{"$f":"'K20 - time schedule'!HW9","v":0},{"$f":"'K20 - time schedule'!HX9","v":0},{"$f":"'K20 - time schedule'!HY9","v":0},{"$f":"'K20 - time schedule'!HZ9","v":0},{"$f":"'K20 - time schedule'!IA9","v":0},{"$f":"'K20 - time schedule'!IB9","v":0},{"$f":"'K20 - time schedule'!IC9","v":0},{"$f":"'K20 - time schedule'!ID9","v":0},{"$f":"'K20 - time schedule'!IE9","v":0},{"$f":"'K20 - time schedule'!IF9","v":0},{"$f":"'K20 - time schedule'!IG9","v":0},{"$f":"'K20 - time schedule'!IH9","v":0},{"$f":"'K20 - time schedule'!II9","v":0},{"$f":"'K20 - time schedule'!IJ9","v":0},{"$f":"'K20 - time schedule'!IK9","v":0},{"$f":"'K20 - time schedule'!IL9","v":0},{"$f":"'K20 - time schedule'!IM9","v":0},{"$f":"'K20 - time schedule'!IN9","v":0},{"$f":"'K20 - time schedule'!IO9","v":0},{"$f":"'K20 - time schedule'!IP9","v":0},{"$f":"'K20 - time schedule'!IQ9","v":0},{"$f":"'K20 - time schedule'!IR9","v":0},{"$f":"'K20 - time schedule'!IS9","v":0},{"$f":"'K20 - time schedule'!IT9","v":0},{"$f":"'K20 - time schedule'!IU9","v":0},{"$f":"'K20 - time schedule'!IV9","v":0},{"$f":"'K20 - time schedule'!IW9","v":0},{"$f":"'K20 - time schedule'!IX9","v":0},{"$f":"'K20 - time schedule'!IY9","v":0},{"$f":"'K20 - time schedule'!IZ9","v":0},{"$f":"'K20 - time schedule'!JA9","v":0},{"$f":"'K20 - time schedule'!JB9","v":0},{"$f":"'K20 - time schedule'!JC9","v":0},{"$f":"'K20 - time schedule'!JD9","v":0},{"$f":"'K20 - time schedule'!JE9","v":0},{"$f":"'K20 - time schedule'!JF9","v":0},{"$f":"'K20 - time schedule'!JG9","v":0},{"$f":"'K20 - time schedule'!JH9","v":0},{"$f":"'K20 - time schedule'!JI9","v":0},{"$f":"'K20 - time schedule'!JJ9","v":0},{"$f":"'K20 - time schedule'!JK9","v":0},{"$f":"'K20 - time schedule'!JL9","v":0},{"$f":"'K20 - time schedule'!JM9","v":0},{"$f":"'K20 - time schedule'!JN9","v":0},{"$f":"'K20 - time schedule'!JO9","v":0},{"$f":"'K20 - time schedule'!JP9","v":0},{"$f":"'K20 - time schedule'!JQ9","v":0},{"$f":"'K20 - time schedule'!JR9","v":0},{"$f":"'K20 - time schedule'!JS9","v":0},{"$f":"'K20 - time schedule'!JT9","v":0},{"$f":"'K20 - time schedule'!JU9","v":0},{"$f":"'K20 - time schedule'!JV9","v":0},{"$f":"'K20 - time schedule'!JW9","v":0},{"$f":"'K20 - time schedule'!JX9","v":0},{"$f":"'K20 - time schedule'!JY9","v":0},{"$f":"'K20 - time schedule'!JZ9","v":0},{"$f":"'K20 - time schedule'!KA9","v":0},{"$f":"'K20 - time schedule'!KB9","v":0},{"$f":"'K20 - time schedule'!KC9","v":0},{"$f":"'K20 - time schedule'!KD9","v":0},{"$f":"'K20 - time schedule'!KE9","v":0},{"$f":"'K20 - time schedule'!KF9","v":0},{"$f":"'K20 - time schedule'!KG9","v":0},{"$f":"'K20 - time schedule'!KH9","v":0},{"$f":"'K20 - time schedule'!KI9","v":0},{"$f":"'K20 - time schedule'!KJ9","v":0},{"$f":"'K20 - time schedule'!KK9","v":0},{"$f":"'K20 - time schedule'!KL9","v":0},{"$f":"'K20 - time schedule'!KM9","v":0},{"$f":"'K20 - time schedule'!KN9","v":0},{"$f":"'K20 - time schedule'!KO9","v":0},{"$f":"'K20 - time schedule'!KP9","v":0},{"$f":"'K20 - time schedule'!KQ9","v":0},{"$f":"'K20 - time schedule'!KR9","v":0},{"$f":"'K20 - time schedule'!KS9","v":0},{"$f":"'K20 - time schedule'!KT9","v":0}]
["Boiler room K20 - binding technical specification for OB 6 (Construction)","K20",{"$f":"'K20 - time schedule'!G10","v":0},{"$f":"'K20 - time schedule'!H10","v":0},{"$f":"'K20 - time schedule'!I10","v":0},{"$f":"'K20 - time schedule'!J10","v":0},{"$f":"'K20 - time schedule'!K10","v":0},{"$f":"'K20 - time schedule'!L10","v":0},{"$f":"'K20 - time schedule'!M10","v":0},{"$f":"'K20 - time schedule'!N10","v":0},{"$f":"'K20 - time schedule'!O10","v":0},{"$f":"'K20 - time schedule'!P10","v":0},{"$f":"'K20 - time schedule'!Q10","v":0},{"$f":"'K20 - time schedule'!R10","v":0},{"$f":"'K20 - time schedule'!S10","v":0},{"$f":"'K20 - time schedule'!T10","v":0},{"$f":"'K20 - time schedule'!U10","v":0},{"$f":"'K20 - time schedule'!V10","v":0},{"$f":"'K20 - time schedule'!W10","v":0},{"$f":"'K20 - time schedule'!X10","v":0},{"$f":"'K20 - time schedule'!Y10","v":0},{"$f":"'K20 - time schedule'!Z10","v":0},{"$f":"'K20 - time schedule'!AA10","v":0},{"$f":"'K20 - time schedule'!AB10","v":0},{"$f":"'K20 - time schedule'!AC10","v":0},{"$f":"'K20 - time schedule'!AD10","v":0},{"$f":"'K20 - time schedule'!AE10","v":0},{"$f":"'K20 - time schedule'!AF10","v":0},{"$f":"'K20 - time schedule'!AG10","v":0},{"$f":"'K20 - time schedule'!AH10","v":0},{"$f":"'K20 - time schedule'!AI10","v":0},{"$f":"'K20 - time schedule'!AJ10","v":0},{"$f":"'K20 - time schedule'!AK10","v":0},{"$f":"'K20 - time schedule'!AL10","v":0},{"$f":"'K20 - time schedule'!AM10","v":0},{"$f":"'K20 - time schedule'!AN10","v":0},{"$f":"'K20 - time schedule'!AO10","v":0},{"$f":"'K20 - time schedule'!AP10","v":0},{"$f":"'K20 - time schedule'!AQ10","v":0},{"$f":"'K20 - time schedule'!AR10","v":0},{"$f":"'K20 - time schedule'!AS10","v":0},{"$f":"'K20 - time schedule'!AT10","v":0},{"$f":"'K20 - time schedule'!AU10","v":0},{"$f":"'K20 - time schedule'!AV10","v":0},{"$f":"'K20 - time schedule'!AW10","v":0},{"$f":"'K20 - time schedule'!AX10","v":0},{"$f":"'K20 - time schedule'!AY10","v":0},{"$f":"'K20 - time schedule'!AZ10","v":0},{"$f":"'K20 - time schedule'!BA10","v":0},{"$f":"'K20 - time schedule'!BB10","v":0},{"$f":"'K20 - time schedule'!BC10","v":0},{"$f":"'K20 - time schedule'!BD10","v":0},{"$f":"'K20 - time schedule'!BE10","v":0},{"$f":"'K20 - time schedule'!BF10","v":0},{"$f":"'K20 - time schedule'!BG10","v":0},{"$f":"'K20 - time schedule'!BH10","v":0},{"$f":"'K20 - time schedule'!BI10","v":0},{"$f":"'K20 - time schedule'!BJ10","v":0},{"$f":"'K20 - time schedule'!BK10","v":0},{"$f":"'K20 - time schedule'!BL10","v":0},{"$f":"'K20 - time schedule'!BM10","v":0},{"$f":"'K20 - time schedule'!BN10","v":0},{"$f":"'K20 - time schedule'!BO10","v":0},{"$f":"'K20 - time schedule'!BP10","v":0},{"$f":"'K20 - time schedule'!BQ10","v":0},{"$f":"'K20 - time schedule'!BR10","v":0},{"$f":"'K20 - time schedule'!BS10","v":0},{"$f":"'K20 - time schedule'!BT10","v":0},{"$f":"'K20 - time schedule'!BU10","v":0},{"$f":"'K20 - time schedule'!BV10","v":0},{"$f":"'K20 - time schedule'!BW10","v":0},{"$f":"'K20 - time schedule'!BX10","v":0},{"$f":"'K20 - time schedule'!BY10","v":0},{"$f":"'K20 - time schedule'!BZ10","v":0},{"$f":"'K20 - time schedule'!CA10","v":0},{"$f":"'K20 - time schedule'!CB10","v":0},{"$f":"'K20 - time schedule'!CC10","v":0},{"$f":"'K20 - time schedule'!CD10","v":0},{"$f":"'K20 - time schedule'!CE10","v":0},{"$f":"'K20 - time schedule'!CF10","v":0},{"$f":"'K20 - time schedule'!CG10","v":0},{"$f":"'K20 - time schedule'!CH10","v":0},{"$f":"'K20 - time schedule'!CI10","v":0},{"$f":"'K20 - time schedule'!CJ10","v":0},{"$f":"'K20 - time schedule'!CK10","v":0},{"$f":"'K20 - time schedule'!CL10","v":0},{"$f":"'K20 - time schedule'!CM10","v":0},{"$f":"'K20 - time schedule'!CN10","v":0},{"$f":"'K20 - time schedule'!CO10","v":0},{"$f":"'K20 - time schedule'!CP10","v":0},{"$f":"'K20 - time schedule'!CQ10","v":0},{"$f":"'K20 - time schedule'!CR10","v":0},{"$f":"'K20 - time schedule'!CS10","v":0},{"$f":"'K20 - time schedule'!CT10","v":0},{"$f":"'K20 - time schedule'!CU10","v":0},{"$f":"'K20 - time schedule'!CV10","v":0},{"$f":"'K20 - time schedule'!CW10","v":0},{"$f":"'K20 - time schedule'!CX10","v":0},{"$f":"'K20 - time schedule'!CY10","v":0},{"$f":"'K20 - time schedule'!CZ10","v":0},{"$f":"'K20 - time schedule'!DA10","v":0},{"$f":"'K20 - time schedule'!DB10","v":0},{"$f":"'K20 - time schedule'!DC10","v":0},{"$f":"'K20 - time schedule'!DD10","v":0},{"$f":"'K20 - time schedule'!DE10","v":0},{"$f":"'K20 - time schedule'!DF10","v":0},{"$f":"'K20 - time schedule'!DG10","v":0},{"$f":"'K20 - time schedule'!DH10","v":0},{"$f":"'K20 - time schedule'!DI10","v":0},{"$f":"'K20 - time schedule'!DJ10","v":0},{"$f":"'K20 - time schedule'!DK10","v":0},{"$f":"'K20 - time schedule'!DL10","v":0},{"$f":"'K20 - time schedule'!DM10","v":0},{"$f":"'K20 - time schedule'!DN10","v":0},{"$f":"'K20 - time schedule'!DO10","v":0},{"$f":"'K20 - time schedule'!DP10","v":0},{"$f":"'K20 - time schedule'!DQ10","v":0},{"$f":"'K20 - time schedule'!DR10","v":0},{"$f":"'K20 - time schedule'!DS10","v":0},{"$f":"'K20 - time schedule'!DT10","v":0},{"$f":"'K20 - time schedule'!DU10","v":0},{"$f":"'K20 - time schedule'!DV10","v":0},{"$f":"'K20 - time schedule'!DW10","v":0},{"$f":"'K20 - time schedule'!DX10","v":0},{"$f":"'K20 - time schedule'!DY10","v":0},{"$f":"'K20 - time schedule'!DZ10","v":0},{"$f":"'K20 - time schedule'!EA10","v":0},{"$f":"'K20 - time schedule'!EB10","v":0},{"$f":"'K20 - time schedule'!EC10","v":0},{"$f":"'K20 - time schedule'!ED10","v":0},{"$f":"'K20 - time schedule'!EE10","v":0},{"$f":"'K20 - time schedule'!EF10","v":0},{"$f":"'K20 - time schedule'!EG10","v":0},{"$f":"'K20 - time schedule'!EH10","v":0},{"$f":"'K20 - time schedule'!EI10","v":0},{"$f":"'K20 - time schedule'!EJ10","v":0},{"$f":"'K20 - time schedule'!EK10","v":0},{"$f":"'K20 - time schedule'!EL10","v":0},{"$f":"'K20 - time schedule'!EM10","v":0},{"$f":"'K20 - time schedule'!EN10","v":0},{"$f":"'K20 - time schedule'!EO10","v":0},{"$f":"'K20 - time schedule'!EP10","v":0},{"$f":"'K20 - time schedule'!EQ10","v":0},{"$f":"'K20 - time schedule'!ER10","v":0},{"$f":"'K20 - time schedule'!ES10","v":0},{"$f":"'K20 - time schedule'!ET10","v":0},{"$f":"'K20 - time schedule'!EU10","v":0},{"$f":"'K20 - time schedule'!EV10","v":0},{"$f":"'K20 - time schedule'!EW10","v":0},{"$f":"'K20 - time schedule'!EX10","v":0},{"$f":"'K20 - time schedule'!EY10","v":0},{"$f":"'K20 - time schedule'!EZ10","v":0},{"$f":"'K20 - time schedule'!FA10","v":0},{"$f":"'K20 - time schedule'!FB10","v":0},{"$f":"'K20 - time schedule'!FC10","v":0},{"$f":"'K20 - time schedule'!FD10","v":0},{"$f":"'K20 - time schedule'!FE10","v":0},{"$f":"'K20 - time schedule'!FF10","v":0},{"$f":"'K20 - time schedule'!FG10","v":0},{"$f":"'K20 - time schedule'!FH10","v":0},{"$f":"'K20 - time schedule'!FI10","v":0},{"$f":"'K20 - time schedule'!FJ10","v":0},{"$f":"'K20 - time schedule'!FK10","v":0},{"$f":"'K20 - time schedule'!FL10","v":0},{"$f":"'K20 - time schedule'!FM10","v":0},{"$f":"'K20 - time schedule'!FN10","v":0},{"$f":"'K20 - time schedule'!FO10","v":0},{"$f":"'K20 - time schedule'!FP10","v":0},{"$f":"'K20 - time schedule'!FQ10","v":0},{"$f":"'K20 - time schedule'!FR10","v":0},{"$f":"'K20 - time schedule'!FS10","v":0},{"$f":"'K20 - time schedule'!FT10","v":0},{"$f":"'K20 - time schedule'!FU10","v":0},{"$f":"'K20 - time schedule'!FV10","v":0},{"$f":"'K20 - time schedule'!FW10","v":0},{"$f":"'K20 - time schedule'!FX10","v":0},{"$f":"'K20 - time schedule'!FY10","v":0},{"$f":"'K20 - time schedule'!FZ10","v":0},{"$f":"'K20 - time schedule'!GA10","v":0},{"$f":"'K20 - time schedule'!GB10","v":0},{"$f":"'K20 - time schedule'!GC10","v":0},{"$f":"'K20 - time schedule'!GD10","v":0},{"$f":"'K20 - time schedule'!GE10","v":0},{"$f":"'K20 - time schedule'!GF10","v":0},{"$f":"'K20 - time schedule'!GG10","v":0},{"$f":"'K20 - time schedule'!GH10","v":0},{"$f":"'K20 - time schedule'!GI10","v":0},{"$f":"'K20 - time schedule'!GJ10","v":0},{"$f":"'K20 - time schedule'!GK10","v":0},{"$f":"'K20 - time schedule'!GL10","v":0},{"$f":"'K20 - time schedule'!GM10","v":0},{"$f":"'K20 - time schedule'!GN10","v":0},{"$f":"'K20 - time schedule'!GO10","v":0},{"$f":"'K20 - time schedule'!GP10","v":0},{"$f":"'K20 - time schedule'!GQ10","v":0},{"$f":"'K20 - time schedule'!GR10","v":0},{"$f":"'K20 - time schedule'!GS10","v":0},{"$f":"'K20 - time schedule'!GT10","v":0},{"$f":"'K20 - time schedule'!GU10","v":0},{"$f":"'K20 - time schedule'!GV10","v":0},{"$f":"'K20 - time schedule'!GW10","v":0},{"$f":"'K20 - time schedule'!GX10","v":0},{"$f":"'K20 - time schedule'!GY10","v":0},{"$f":"'K20 - time schedule'!GZ10","v":0},{"$f":"'K20 - time schedule'!HA10","v":0},{"$f":"'K20 - time schedule'!HB10","v":0},{"$f":"'K20 - time schedule'!HC10","v":0},{"$f":"'K20 - time schedule'!HD10","v":0},{"$f":"'K20 - time schedule'!HE10","v":0},{"$f":"'K20 - time schedule'!HF10","v":0},{"$f":"'K20 - time schedule'!HG10","v":0},{"$f":"'K20 - time schedule'!HH10","v":0},{"$f":"'K20 - time schedule'!HI10","v":0},{"$f":"'K20 - time schedule'!HJ10","v":0},{"$f":"'K20 - time schedule'!HK10","v":0},{"$f":"'K20 - time schedule'!HL10","v":0},{"$f":"'K20 - time schedule'!HM10","v":0},{"$f":"'K20 - time schedule'!HN10","v":0},{"$f":"'K20 - time schedule'!HO10","v":0},{"$f":"'K20 - time schedule'!HP10","v":0},{"$f":"'K20 - time schedule'!HQ10","v":0},{"$f":"'K20 - time schedule'!HR10","v":0},{"$f":"'K20 - time schedule'!HS10","v":0},{"$f":"'K20 - time schedule'!HT10","v":0},{"$f":"'K20 - time schedule'!HU10","v":0},{"$f":"'K20 - time schedule'!HV10","v":0},{"$f":"'K20 - time schedule'!HW10","v":0},{"$f":"'K20 - time schedule'!HX10","v":0},{"$f":"'K20 - time schedule'!HY10","v":0},{"$f":"'K20 - time schedule'!HZ10","v":0},{"$f":"'K20 - time schedule'!IA10","v":0},{"$f":"'K20 - time schedule'!IB10","v":0},{"$f":"'K20 - time schedule'!IC10","v":0},{"$f":"'K20 - time schedule'!ID10","v":0},{"$f":"'K20 - time schedule'!IE10","v":0},{"$f":"'K20 - time schedule'!IF10","v":0},{"$f":"'K20 - time schedule'!IG10","v":0},{"$f":"'K20 - time schedule'!IH10","v":0},{"$f":"'K20 - time schedule'!II10","v":0},{"$f":"'K20 - time schedule'!IJ10","v":0},{"$f":"'K20 - time schedule'!IK10","v":0},{"$f":"'K20 - time schedule'!IL10","v":0},{"$f":"'K20 - time schedule'!IM10","v":0},{"$f":"'K20 - time schedule'!IN10","v":0},{"$f":"'K20 - time schedule'!IO10","v":0},{"$f":"'K20 - time schedule'!IP10","v":0},{"$f":"'K20 - time schedule'!IQ10","v":0},{"$f":"'K20 - time schedule'!IR10","v":0},{"$f":"'K20 - time schedule'!IS10","v":0},{"$f":"'K20 - time schedule'!IT10","v":0},{"$f":"'K20 - time schedule'!IU10","v":0},{"$f":"'K20 - time schedule'!IV10","v":0},{"$f":"'K20 - time schedule'!IW10","v":0},{"$f":"'K20 - time schedule'!IX10","v":0},{"$f":"'K20 - time schedule'!IY10","v":0},{"$f":"'K20 - time schedule'!IZ10","v":0},{"$f":"'K20 - time schedule'!JA10","v":0},{"$f":"'K20 - time schedule'!JB10","v":0},{"$f":"'K20 - time schedule'!JC10","v":0},{"$f":"'K20 - time schedule'!JD10","v":0},{"$f":"'K20 - time schedule'!JE10","v":0},{"$f":"'K20 - time schedule'!JF10","v":0},{"$f":"'K20 - time schedule'!JG10","v":0},{"$f":"'K20 - time schedule'!JH10","v":0},{"$f":"'K20 - time schedule'!JI10","v":0},{"$f":"'K20 - time schedule'!JJ10","v":0},{"$f":"'K20 - time schedule'!JK10","v":0},{"$f":"'K20 - time schedule'!JL10","v":0},{"$f":"'K20 - time schedule'!JM10","v":0},{"$f":"'K20 - time schedule'!JN10","v":0},{"$f":"'K20 - time schedule'!JO10","v":0},{"$f":"'K20 - time schedule'!JP10","v":0},{"$f":"'K20 - time schedule'!JQ10","v":0},{"$f":"'K20 - time schedule'!JR10","v":0},{"$f":"'K20 - time schedule'!JS10","v":0},{"$f":"'K20 - time schedule'!JT10","v":0},{"$f":"'K20 - time schedule'!JU10","v":0},{"$f":"'K20 - time schedule'!JV10","v":0},{"$f":"'K20 - time schedule'!JW10","v":0},{"$f":"'K20 - time schedule'!JX10","v":0},{"$f":"'K20 - time schedule'!JY10","v":0},{"$f":"'K20 - time schedule'!JZ10","v":0},{"$f":"'K20 - time schedule'!KA10","v":0},{"$f":"'K20 - time schedule'!KB10","v":0},{"$f":"'K20 - time schedule'!KC10","v":0},{"$f":"'K20 - time schedule'!KD10","v":0},{"$f":"'K20 - time schedule'!KE10","v":0},{"$f":"'K20 - time schedule'!KF10","v":0},{"$f":"'K20 - time schedule'!KG10","v":0},{"$f":"'K20 - time schedule'!KH10","v":0},{"$f":"'K20 - time schedule'!KI10","v":0},{"$f":"'K20 - time schedule'!KJ10","v":0},{"$f":"'K20 - time schedule'!KK10","v":0},{"$f":"'K20 - time schedule'!KL10","v":0},{"$f":"'K20 - time schedule'!KM10","v":0},{"$f":"'K20 - time schedule'!KN10","v":0},{"$f":"'K20 - time schedule'!KO10","v":0},{"$f":"'K20 - time schedule'!KP10","v":0},{"$f":"'K20 - time schedule'!KQ10","v":0},{"$f":"'K20 - time schedule'!KR10","v":0},{"$f":"'K20 - time schedule'!KS10","v":0},{"$f":"'K20 - time schedule'!KT10","v":0}]
["Boiler room K20 - binding technical specification for OB 1 (Fuel management) ","K20",{"$f":"'K20 - time schedule'!G12","v":0},{"$f":"'K20 - time schedule'!H12","v":0},{"$f":"'K20 - time schedule'!I12","v":0},{"$f":"'K20 - time schedule'!J12","v":0},{"$f":"'K20 - time schedule'!K12","v":0},{"$f":"'K20 - time schedule'!L12","v":0},{"$f":"'K20 - time schedule'!M12","v":0},{"$f":"'K20 - time schedule'!N12","v":0},{"$f":"'K20 - time schedule'!O12","v":0},{"$f":"'K20 - time schedule'!P12","v":0},{"$f":"'K20 - time schedule'!Q12","v":0},{"$f":"'K20 - time schedule'!R12","v":0},{"$f":"'K20 - time schedule'!S12","v":0},{"$f":"'K20 - time schedule'!T12","v":0},{"$f":"'K20 - time schedule'!U12","v":0},{"$f":"'K20 - time schedule'!V12","v":0},{"$f":"'K20 - time schedule'!W12","v":0},{"$f":"'K20 - time schedule'!X12","v":0},{"$f":"'K20 - time schedule'!Y12","v":0},{"$f":"'K20 - time schedule'!Z12","v":0},{"$f":"'K20 - time schedule'!AA12","v":0},{"$f":"'K20 - time schedule'!AB12","v":0},{"$f":"'K20 - time schedule'!AC12","v":0},{"$f":"'K20 - time schedule'!AD12","v":0},{"$f":"'K20 - time schedule'!AE12","v":0},{"$f":"'K20 - time schedule'!AF12","v":0},{"$f":"'K20 - time schedule'!AG12","v":0},{"$f":"'K20 - time schedule'!AH12","v":0},{"$f":"'K20 - time schedule'!AI12","v":0},{"$f":"'K20 - time schedule'!AJ12","v":0},{"$f":"'K20 - time schedule'!AK12","v":0},{"$f":"'K20 - time schedule'!AL12","v":0},{"$f":"'K20 - time schedule'!AM12","v":0},{"$f":"'K20 - time schedule'!AN12","v":0},{"$f":"'K20 - time schedule'!AO12","v":0},{"$f":"'K20 - time schedule'!AP12","v":0},{"$f":"'K20 - time schedule'!AQ12","v":0},{"$f":"'K20 - time schedule'!AR12","v":0},{"$f":"'K20 - time schedule'!AS12","v":0},{"$f":"'K20 - time schedule'!AT12","v":0},{"$f":"'K20 - time schedule'!AU12","v":0},{"$f":"'K20 - time schedule'!AV12","v":0},{"$f":"'K20 - time schedule'!AW12","v":0},{"$f":"'K20 - time schedule'!AX12","v":0},{"$f":"'K20 - time schedule'!AY12","v":0},{"$f":"'K20 - time schedule'!AZ12","v":0},{"$f":"'K20 - time schedule'!BA12","v":0},{"$f":"'K20 - time schedule'!BB12","v":0},{"$f":"'K20 - time schedule'!BC12","v":0},{"$f":"'K20 - time schedule'!BD12","v":0},{"$f":"'K20 - time schedule'!BE12","v":0},{"$f":"'K20 - time schedule'!BF12","v":0},{"$f":"'K20 - time schedule'!BG12","v":0},{"$f":"'K20 - time schedule'!BH12","v":0},{"$f":"'K20 - time schedule'!BI12","v":0},{"$f":"'K20 - time schedule'!BJ12","v":0},{"$f":"'K20 - time schedule'!BK12","v":0},{"$f":"'K20 - time schedule'!BL12","v":0},{"$f":"'K20 - time schedule'!BM12","v":0},{"$f":"'K20 - time schedule'!BN12","v":0},{"$f":"'K20 - time schedule'!BO12","v":0},{"$f":"'K20 - time schedule'!BP12","v":0},{"$f":"'K20 - time schedule'!BQ12","v":0},{"$f":"'K20 - time schedule'!BR12","v":0},{"$f":"'K20 - time schedule'!BS12","v":0},{"$f":"'K20 - time schedule'!BT12","v":0},{"$f":"'K20 - time schedule'!BU12","v":0},{"$f":"'K20 - time schedule'!BV12","v":0},{"$f":"'K20 - time schedule'!BW12","v":0},{"$f":"'K20 - time schedule'!BX12","v":0},{"$f":"'K20 - time schedule'!BY12","v":0},{"$f":"'K20 - time schedule'!BZ12","v":0},{"$f":"'K20 - time schedule'!CA12","v":0},{"$f":"'K20 - time schedule'!CB12","v":0},{"$f":"'K20 - time schedule'!CC12","v":0},{"$f":"'K20 - time schedule'!CD12","v":0},{"$f":"'K20 - time schedule'!CE12","v":0},{"$f":"'K20 - time schedule'!CF12","v":0},{"$f":"'K20 - time schedule'!CG12","v":0},{"$f":"'K20 - time schedule'!CH12","v":0},{"$f":"'K20 - time schedule'!CI12","v":0},{"$f":"'K20 - time schedule'!CJ12","v":0},{"$f":"'K20 - time schedule'!CK12","v":0},{"$f":"'K20 - time schedule'!CL12","v":0},{"$f":"'K20 - time schedule'!CM12","v":0},{"$f":"'K20 - time schedule'!CN12","v":0},{"$f":"'K20 - time schedule'!CO12","v":0},{"$f":"'K20 - time schedule'!CP12","v":0},{"$f":"'K20 - time schedule'!CQ12","v":0},{"$f":"'K20 - time schedule'!CR12","v":0},{"$f":"'K20 - time schedule'!CS12","v":0},{"$f":"'K20 - time schedule'!CT12","v":0},{"$f":"'K20 - time schedule'!CU12","v":0},{"$f":"'K20 - time schedule'!CV12","v":0},{"$f":"'K20 - time schedule'!CW12","v":0},{"$f":"'K20 - time schedule'!CX12","v":0},{"$f":"'K20 - time schedule'!CY12","v":0},{"$f":"'K20 - time schedule'!CZ12","v":0},{"$f":"'K20 - time schedule'!DA12","v":0},{"$f":"'K20 - time schedule'!DB12","v":0},{"$f":"'K20 - time schedule'!DC12","v":0},{"$f":"'K20 - time schedule'!DD12","v":0},{"$f":"'K20 - time schedule'!DE12","v":0},{"$f":"'K20 - time schedule'!DF12","v":0},{"$f":"'K20 - time schedule'!DG12","v":0},{"$f":"'K20 - time schedule'!DH12","v":0},{"$f":"'K20 - time schedule'!DI12","v":0},{"$f":"'K20 - time schedule'!DJ12","v":0},{"$f":"'K20 - time schedule'!DK12","v":0},{"$f":"'K20 - time schedule'!DL12","v":0},{"$f":"'K20 - time schedule'!DM12","v":0},{"$f":"'K20 - time schedule'!DN12","v":0},{"$f":"'K20 - time schedule'!DO12","v":0},{"$f":"'K20 - time schedule'!DP12","v":0},{"$f":"'K20 - time schedule'!DQ12","v":0},{"$f":"'K20 - time schedule'!DR12","v":0},{"$f":"'K20 - time schedule'!DS12","v":0},{"$f":"'K20 - time schedule'!DT12","v":0},{"$f":"'K20 - time schedule'!DU12","v":0},{"$f":"'K20 - time schedule'!DV12","v":0},{"$f":"'K20 - time schedule'!DW12","v":0},{"$f":"'K20 - time schedule'!DX12","v":0},{"$f":"'K20 - time schedule'!DY12","v":0},{"$f":"'K20 - time schedule'!DZ12","v":0},{"$f":"'K20 - time schedule'!EA12","v":0},{"$f":"'K20 - time schedule'!EB12","v":0},{"$f":"'K20 - time schedule'!EC12","v":0},{"$f":"'K20 - time schedule'!ED12","v":0},{"$f":"'K20 - time schedule'!EE12","v":0},{"$f":"'K20 - time schedule'!EF12","v":0},{"$f":"'K20 - time schedule'!EG12","v":0},{"$f":"'K20 - time schedule'!EH12","v":0},{"$f":"'K20 - time schedule'!EI12","v":0},{"$f":"'K20 - time schedule'!EJ12","v":0},{"$f":"'K20 - time schedule'!EK12","v":0},{"$f":"'K20 - time schedule'!EL12","v":0},{"$f":"'K20 - time schedule'!EM12","v":0},{"$f":"'K20 - time schedule'!EN12","v":0},{"$f":"'K20 - time schedule'!EO12","v":0},{"$f":"'K20 - time schedule'!EP12","v":0},{"$f":"'K20 - time schedule'!EQ12","v":0},{"$f":"'K20 - time schedule'!ER12","v":0},{"$f":"'K20 - time schedule'!ES12","v":0},{"$f":"'K20 - time schedule'!ET12","v":0},{"$f":"'K20 - time schedule'!EU12","v":0},{"$f":"'K20 - time schedule'!EV12","v":0},{"$f":"'K20 - time schedule'!EW12","v":0},{"$f":"'K20 - time schedule'!EX12","v":0},{"$f":"'K20 - time schedule'!EY12","v":0},{"$f":"'K20 - time schedule'!EZ12","v":0},{"$f":"'K20 - time schedule'!FA12","v":0},{"$f":"'K20 - time schedule'!FB12","v":0},{"$f":"'K20 - time schedule'!FC12","v":0},{"$f":"'K20 - time schedule'!FD12","v":0},{"$f":"'K20 - time schedule'!FE12","v":0},{"$f":"'K20 - time schedule'!FF12","v":0},{"$f":"'K20 - time schedule'!FG12","v":0},{"$f":"'K20 - time schedule'!FH12","v":0},{"$f":"'K20 - time schedule'!FI12","v":0},{"$f":"'K20 - time schedule'!FJ12","v":0},{"$f":"'K20 - time schedule'!FK12","v":0},{"$f":"'K20 - time schedule'!FL12","v":0},{"$f":"'K20 - time schedule'!FM12","v":0},{"$f":"'K20 - time schedule'!FN12","v":0},{"$f":"'K20 - time schedule'!FO12","v":0},{"$f":"'K20 - time schedule'!FP12","v":0},{"$f":"'K20 - time schedule'!FQ12","v":0},{"$f":"'K20 - time schedule'!FR12","v":0},{"$f":"'K20 - time schedule'!FS12","v":0},{"$f":"'K20 - time schedule'!FT12","v":0},{"$f":"'K20 - time schedule'!FU12","v":0},{"$f":"'K20 - time schedule'!FV12","v":0},{"$f":"'K20 - time schedule'!FW12","v":0},{"$f":"'K20 - time schedule'!FX12","v":0},{"$f":"'K20 - time schedule'!FY12","v":0},{"$f":"'K20 - time schedule'!FZ12","v":0},{"$f":"'K20 - time schedule'!GA12","v":0},{"$f":"'K20 - time schedule'!GB12","v":0},{"$f":"'K20 - time schedule'!GC12","v":0},{"$f":"'K20 - time schedule'!GD12","v":0},{"$f":"'K20 - time schedule'!GE12","v":0},{"$f":"'K20 - time schedule'!GF12","v":0},{"$f":"'K20 - time schedule'!GG12","v":0},{"$f":"'K20 - time schedule'!GH11","v":0},{"$f":"'K20 - time schedule'!GI11","v":0},{"$f":"'K20 - time schedule'!GJ11","v":0},{"$f":"'K20 - time schedule'!GK11","v":0},{"$f":"'K20 - time schedule'!GL11","v":0},{"$f":"'K20 - time schedule'!GM11","v":0},{"$f":"'K20 - time schedule'!GN11","v":0},{"$f":"'K20 - time schedule'!GO11","v":0},{"$f":"'K20 - time schedule'!GP11","v":0},{"$f":"'K20 - time schedule'!GQ11","v":0},{"$f":"'K20 - time schedule'!GR11","v":0},{"$f":"'K20 - time schedule'!GS11","v":0},{"$f":"'K20 - time schedule'!GT11","v":0},{"$f":"'K20 - time schedule'!GU11","v":0},{"$f":"'K20 - time schedule'!GV11","v":0},{"$f":"'K20 - time schedule'!GW11","v":0},{"$f":"'K20 - time schedule'!GX11","v":0},{"$f":"'K20 - time schedule'!GY11","v":0},{"$f":"'K20 - time schedule'!GZ11","v":0},{"$f":"'K20 - time schedule'!HA11","v":0},{"$f":"'K20 - time schedule'!HB11","v":0},{"$f":"'K20 - time schedule'!HC11","v":0},{"$f":"'K20 - time schedule'!HD11","v":0},{"$f":"'K20 - time schedule'!HE11","v":0},{"$f":"'K20 - time schedule'!HF11","v":0},{"$f":"'K20 - time schedule'!HG11","v":0},{"$f":"'K20 - time schedule'!HH11","v":0},{"$f":"'K20 - time schedule'!HI11","v":0},{"$f":"'K20 - time schedule'!HJ11","v":0},{"$f":"'K20 - time schedule'!HK11","v":0},{"$f":"'K20 - time schedule'!HL11","v":0},{"$f":"'K20 - time schedule'!HM11","v":0},{"$f":"'K20 - time schedule'!HN11","v":0},{"$f":"'K20 - time schedule'!HO11","v":0},{"$f":"'K20 - time schedule'!HP11","v":0},{"$f":"'K20 - time schedule'!HQ11","v":0},{"$f":"'K20 - time schedule'!HR11","v":0},{"$f":"'K20 - time schedule'!HS11","v":0},{"$f":"'K20 - time schedule'!HT11","v":0},{"$f":"'K20 - time schedule'!HU11","v":0},{"$f":"'K20 - time schedule'!HV11","v":0},{"$f":"'K20 - time schedule'!HW11","v":0},{"$f":"'K20 - time schedule'!HX11","v":0},{"$f":"'K20 - time schedule'!HY11","v":0},{"$f":"'K20 - time schedule'!HZ11","v":0},{"$f":"'K20 - time schedule'!IA11","v":0},{"$f":"'K20 - time schedule'!IB11","v":0},{"$f":"'K20 - time schedule'!IC11","v":0},{"$f":"'K20 - time schedule'!ID11","v":0},{"$f":"'K20 - time schedule'!IE11","v":0},{"$f":"'K20 - time schedule'!IF11","v":0},{"$f":"'K20 - time schedule'!IG11","v":0},{"$f":"'K20 - time schedule'!IH11","v":0},{"$f":"'K20 - time schedule'!II11","v":0},{"$f":"'K20 - time schedule'!IJ11","v":0},{"$f":"'K20 - time schedule'!IK11","v":0},{"$f":"'K20 - time schedule'!IL11","v":0},{"$f":"'K20 - time schedule'!IM11","v":0},{"$f":"'K20 - time schedule'!IN11","v":0},{"$f":"'K20 - time schedule'!IO11","v":0},{"$f":"'K20 - time schedule'!IP11","v":0},{"$f":"'K20 - time schedule'!IQ11","v":0},{"$f":"'K20 - time schedule'!IR11","v":0},{"$f":"'K20 - time schedule'!IS11","v":0},{"$f":"'K20 - time schedule'!IT11","v":0},{"$f":"'K20 - time schedule'!IU11","v":0},{"$f":"'K20 - time schedule'!IV11","v":0},{"$f":"'K20 - time schedule'!IW11","v":0},{"$f":"'K20 - time schedule'!IX11","v":0},{"$f":"'K20 - time schedule'!IY11","v":0},{"$f":"'K20 - time schedule'!IZ11","v":0},{"$f":"'K20 - time schedule'!JA11","v":0},{"$f":"'K20 - time schedule'!JB11","v":0},{"$f":"'K20 - time schedule'!JC11","v":0},{"$f":"'K20 - time schedule'!JD11","v":0},{"$f":"'K20 - time schedule'!JE11","v":0},{"$f":"'K20 - time schedule'!JF11","v":0},{"$f":"'K20 - time schedule'!JG11","v":0},{"$f":"'K20 - time schedule'!JH11","v":0},{"$f":"'K20 - time schedule'!JI11","v":0},{"$f":"'K20 - time schedule'!JJ11","v":0},{"$f":"'K20 - time schedule'!JK11","v":0},{"$f":"'K20 - time schedule'!JL11","v":0},{"$f":"'K20 - time schedule'!JM11","v":0},{"$f":"'K20 - time schedule'!JN11","v":0},{"$f":"'K20 - time schedule'!JO11","v":0},{"$f":"'K20 - time schedule'!JP11","v":0},{"$f":"'K20 - time schedule'!JQ11","v":0},{"$f":"'K20 - time schedule'!JR11","v":0},{"$f":"'K20 - time schedule'!JS11","v":0},{"$f":"'K20 - time schedule'!JT11","v":0},{"$f":"'K20 - time schedule'!JU11","v":0},{"$f":"'K20 - time schedule'!JV11","v":0},{"$f":"'K20 - time schedule'!JW11","v":0},{"$f":"'K20 - time schedule'!JX11","v":0},{"$f":"'K20 - time schedule'!JY11","v":0},{"$f":"'K20 - time schedule'!JZ11","v":0},{"$f":"'K20 - time schedule'!KA11","v":0},{"$f":"'K20 - time schedule'!KB11","v":0},{"$f":"'K20 - time schedule'!KC11","v":0},{"$f":"'K20 - time schedule'!KD11","v":0},{"$f":"'K20 - time schedule'!KE11","v":0},{"$f":"'K20 - time schedule'!KF11","v":0},{"$f":"'K20 - time schedule'!KG11","v":0},{"$f":"'K20 - time schedule'!KH11","v":0},{"$f":"'K20 - time schedule'!KI11","v":0},{"$f":"'K20 - time schedule'!KJ11","v":0},{"$f":"'K20 - time schedule'!KK11","v":0},{"$f":"'K20 - time schedule'!KL11","v":0},{"$f":"'K20 - time schedule'!KM11","v":0},{"$f":"'K20 - time schedule'!KN11","v":0},{"$f":"'K20 - time schedule'!KO11","v":0},{"$f":"'K20 - time schedule'!KP11","v":0},{"$f":"'K20 - time schedule'!KQ11","v":0},{"$f":"'K20 - time schedule'!KR11","v":0},{"$f":"'K20 - time schedule'!KS11","v":0},{"$f":"'K20 - time schedule'!KT11","v":0}]
["Boiler room K20 - binding technical specification for other OBs, for other suppliers of technological units ","K20",{"$f":"'K20 - time schedule'!G14","v":0},{"$f":"'K20 - time schedule'!H14","v":0},{"$f":"'K20 - time schedule'!I14","v":0},{"$f":"'K20 - time schedule'!J14","v":0},{"$f":"'K20 - time schedule'!K14","v":0},{"$f":"'K20 - time schedule'!L14","v":0},{"$f":"'K20 - time schedule'!M14","v":0},{"$f":"'K20 - time schedule'!N14","v":0},{"$f":"'K20 - time schedule'!O14","v":0},{"$f":"'K20 - time schedule'!P14","v":0},{"$f":"'K20 - time schedule'!Q14","v":0},{"$f":"'K20 - time schedule'!R14","v":0},{"$f":"'K20 - time schedule'!S14","v":0},{"$f":"'K20 - time schedule'!T14","v":0},{"$f":"'K20 - time schedule'!U14","v":0},{"$f":"'K20 - time schedule'!V14","v":0},{"$f":"'K20 - time schedule'!W14","v":0},{"$f":"'K20 - time schedule'!X14","v":0},{"$f":"'K20 - time schedule'!Y14","v":0},{"$f":"'K20 - time schedule'!Z14","v":0},{"$f":"'K20 - time schedule'!AA14","v":0},{"$f":"'K20 - time schedule'!AB14","v":0},{"$f":"'K20 - time schedule'!AC14","v":0},{"$f":"'K20 - time schedule'!AD14","v":0},{"$f":"'K20 - time schedule'!AE14","v":0},{"$f":"'K20 - time schedule'!AF14","v":0},{"$f":"'K20 - time schedule'!AG14","v":0},{"$f":"'K20 - time schedule'!AH14","v":0},{"$f":"'K20 - time schedule'!AI14","v":0},{"$f":"'K20 - time schedule'!AJ14","v":0},{"$f":"'K20 - time schedule'!AK14","v":0},{"$f":"'K20 - time schedule'!AL14","v":0},{"$f":"'K20 - time schedule'!AM14","v":0},{"$f":"'K20 - time schedule'!AN14","v":0},{"$f":"'K20 - time schedule'!AO14","v":0},{"$f":"'K20 - time schedule'!AP14","v":0},{"$f":"'K20 - time schedule'!AQ14","v":0},{"$f":"'K20 - time schedule'!AR14","v":0},{"$f":"'K20 - time schedule'!AS14","v":0},{"$f":"'K20 - time schedule'!AT14","v":0},{"$f":"'K20 - time schedule'!AU14","v":0},{"$f":"'K20 - time schedule'!AV14","v":0},{"$f":"'K20 - time schedule'!AW14","v":0},{"$f":"'K20 - time schedule'!AX14","v":0},{"$f":"'K20 - time schedule'!AY14","v":0},{"$f":"'K20 - time schedule'!AZ14","v":0},{"$f":"'K20 - time schedule'!BA14","v":0},{"$f":"'K20 - time schedule'!BB14","v":0},{"$f":"'K20 - time schedule'!BC14","v":0},{"$f":"'K20 - time schedule'!BD14","v":0},{"$f":"'K20 - time schedule'!BE14","v":0},{"$f":"'K20 - time schedule'!BF14","v":0},{"$f":"'K20 - time schedule'!BG14","v":0},{"$f":"'K20 - time schedule'!BH14","v":0},{"$f":"'K20 - time schedule'!BI14","v":0},{"$f":"'K20 - time schedule'!BJ14","v":0},{"$f":"'K20 - time schedule'!BK14","v":0},{"$f":"'K20 - time schedule'!BL14","v":0},{"$f":"'K20 - time schedule'!BM14","v":0},{"$f":"'K20 - time schedule'!BN14","v":0},{"$f":"'K20 - time schedule'!BO14","v":0},{"$f":"'K20 - time schedule'!BP14","v":0},{"$f":"'K20 - time schedule'!BQ14","v":0},{"$f":"'K20 - time schedule'!BR14","v":0},{"$f":"'K20 - time schedule'!BS14","v":0},{"$f":"'K20 - time schedule'!BT14","v":0},{"$f":"'K20 - time schedule'!BU14","v":0},{"$f":"'K20 - time schedule'!BV14","v":0},{"$f":"'K20 - time schedule'!BW14","v":0},{"$f":"'K20 - time schedule'!BX14","v":0},{"$f":"'K20 - time schedule'!BY14","v":0},{"$f":"'K20 - time schedule'!BZ14","v":0},{"$f":"'K20 - time schedule'!CA14","v":0},{"$f":"'K20 - time schedule'!CB14","v":0},{"$f":"'K20 - time schedule'!CC14","v":0},{"$f":"'K20 - time schedule'!CD14","v":0},{"$f":"'K20 - time schedule'!CE14","v":0},{"$f":"'K20 - time schedule'!CF14","v":0},{"$f":"'K20 - time schedule'!CG14","v":0},{"$f":"'K20 - time schedule'!CH14","v":0},{"$f":"'K20 - time schedule'!CI14","v":0},{"$f":"'K20 - time schedule'!CJ14","v":0},{"$f":"'K20 - time schedule'!CK14","v":0},{"$f":"'K20 - time schedule'!CL14","v":0},{"$f":"'K20 - time schedule'!CM14","v":0},{"$f":"'K20 - time schedule'!CN14","v":0},{"$f":"'K20 - time schedule'!CO14","v":0},{"$f":"'K20 - time schedule'!CP14","v":0},{"$f":"'K20 - time schedule'!CQ14","v":0},{"$f":"'K20 - time schedule'!CR14","v":0},{"$f":"'K20 - time schedule'!CS14","v":0},{"$f":"'K20 - time schedule'!CT14","v":0},{"$f":"'K20 - time schedule'!CU14","v":0},{"$f":"'K20 - time schedule'!CV14","v":0},{"$f":"'K20 - time schedule'!CW14","v":0},{"$f":"'K20 - time schedule'!CX14","v":0},{"$f":"'K20 - time schedule'!CY14","v":0},{"$f":"'K20 - time schedule'!CZ14","v":0},{"$f":"'K20 - time schedule'!DA14","v":0},{"$f":"'K20 - time schedule'!DB14","v":0},{"$f":"'K20 - time schedule'!DC14","v":0},{"$f":"'K20 - time schedule'!DD14","v":0},{"$f":"'K20 - time schedule'!DE14","v":0},{"$f":"'K20 - time schedule'!DF14","v":0},{"$f":"'K20 - time schedule'!DG14","v":0},{"$f":"'K20 - time schedule'!DH14","v":0},{"$f":"'K20 - time schedule'!DI14","v":0},{"$f":"'K20 - time schedule'!DJ14","v":0},{"$f":"'K20 - time schedule'!DK14","v":0},{"$f":"'K20 - time schedule'!DL14","v":0},{"$f":"'K20 - time schedule'!DM14","v":0},{"$f":"'K20 - time schedule'!DN14","v":0},{"$f":"'K20 - time schedule'!DO14","v":0},{"$f":"'K20 - time schedule'!DP14","v":0},{"$f":"'K20 - time schedule'!DQ14","v":0},{"$f":"'K20 - time schedule'!DR14","v":0},{"$f":"'K20 - time schedule'!DS14","v":0},{"$f":"'K20 - time schedule'!DT14","v":0},{"$f":"'K20 - time schedule'!DU14","v":0},{"$f":"'K20 - time schedule'!DV14","v":0},{"$f":"'K20 - time schedule'!DW14","v":0},{"$f":"'K20 - time schedule'!DX14","v":0},{"$f":"'K20 - time schedule'!DY14","v":0},{"$f":"'K20 - time schedule'!DZ14","v":0},{"$f":"'K20 - time schedule'!EA14","v":0},{"$f":"'K20 - time schedule'!EB14","v":0},{"$f":"'K20 - time schedule'!EC14","v":0},{"$f":"'K20 - time schedule'!ED14","v":0},{"$f":"'K20 - time schedule'!EE14","v":0},{"$f":"'K20 - time schedule'!EF14","v":0},{"$f":"'K20 - time schedule'!EG14","v":0},{"$f":"'K20 - time schedule'!EH14","v":0},{"$f":"'K20 - time schedule'!EI14","v":0},{"$f":"'K20 - time schedule'!EJ14","v":0},{"$f":"'K20 - time schedule'!EK14","v":0},{"$f":"'K20 - time schedule'!EL14","v":0},{"$f":"'K20 - time schedule'!EM14","v":0},{"$f":"'K20 - time schedule'!EN14","v":0},{"$f":"'K20 - time schedule'!EO14","v":0},{"$f":"'K20 - time schedule'!EP14","v":0},{"$f":"'K20 - time schedule'!EQ14","v":0},{"$f":"'K20 - time schedule'!ER14","v":0},{"$f":"'K20 - time schedule'!ES14","v":0},{"$f":"'K20 - time schedule'!ET14","v":0},{"$f":"'K20 - time schedule'!EU14","v":0},{"$f":"'K20 - time schedule'!EV14","v":0},{"$f":"'K20 - time schedule'!EW14","v":0},{"$f":"'K20 - time schedule'!EX14","v":0},{"$f":"'K20 - time schedule'!EY14","v":0},{"$f":"'K20 - time schedule'!EZ14","v":0},{"$f":"'K20 - time schedule'!FA14","v":0},{"$f":"'K20 - time schedule'!FB14","v":0},{"$f":"'K20 - time schedule'!FC14","v":0},{"$f":"'K20 - time schedule'!FD14","v":0},{"$f":"'K20 - time schedule'!FE14","v":0},{"$f":"'K20 - time schedule'!FF14","v":0},{"$f":"'K20 - time schedule'!FG14","v":0},{"$f":"'K20 - time schedule'!FH14","v":0},{"$f":"'K20 - time schedule'!FI14","v":0},{"$f":"'K20 - time schedule'!FJ14","v":0},{"$f":"'K20 - time schedule'!FK14","v":0},{"$f":"'K20 - time schedule'!FL14","v":0},{"$f":"'K20 - time schedule'!FM14","v":0},{"$f":"'K20 - time schedule'!FN14","v":0},{"$f":"'K20 - time schedule'!FO14","v":0},{"$f":"'K20 - time schedule'!FP14","v":0},{"$f":"'K20 - time schedule'!FQ14","v":0},{"$f":"'K20 - time schedule'!FR14","v":0},{"$f":"'K20 - time schedule'!FS14","v":0},{"$f":"'K20 - time schedule'!FT14","v":0},{"$f":"'K20 - time schedule'!FU14","v":0},{"$f":"'K20 - time schedule'!FV14","v":0},{"$f":"'K20 - time schedule'!FW14","v":0},{"$f":"'K20 - time schedule'!FX14","v":0},{"$f":"'K20 - time schedule'!FY14","v":0},{"$f":"'K20 - time schedule'!FZ14","v":0},{"$f":"'K20 - time schedule'!GA14","v":0},{"$f":"'K20 - time schedule'!GB14","v":0},{"$f":"'K20 - time schedule'!GC14","v":0},{"$f":"'K20 - time schedule'!GD14","v":0},{"$f":"'K20 - time schedule'!GE14","v":0},{"$f":"'K20 - time schedule'!GF14","v":0},{"$f":"'K20 - time schedule'!GG14","v":0},{"$f":"'K20 - time schedule'!GH12","v":0},{"$f":"'K20 - time schedule'!GI12","v":0},{"$f":"'K20 - time schedule'!GJ12","v":0},{"$f":"'K20 - time schedule'!GK12","v":0},{"$f":"'K20 - time schedule'!GL12","v":0},{"$f":"'K20 - time schedule'!GM12","v":0},{"$f":"'K20 - time schedule'!GN12","v":0},{"$f":"'K20 - time schedule'!GO12","v":0},{"$f":"'K20 - time schedule'!GP12","v":0},{"$f":"'K20 - time schedule'!GQ12","v":0},{"$f":"'K20 - time schedule'!GR12","v":0},{"$f":"'K20 - time schedule'!GS12","v":0},{"$f":"'K20 - time schedule'!GT12","v":0},{"$f":"'K20 - time schedule'!GU12","v":0},{"$f":"'K20 - time schedule'!GV12","v":0},{"$f":"'K20 - time schedule'!GW12","v":0},{"$f":"'K20 - time schedule'!GX12","v":0},{"$f":"'K20 - time schedule'!GY12","v":0},{"$f":"'K20 - time schedule'!GZ12","v":0},{"$f":"'K20 - time schedule'!HA12","v":0},{"$f":"'K20 - time schedule'!HB12","v":0},{"$f":"'K20 - time schedule'!HC12","v":0},{"$f":"'K20 - time schedule'!HD12","v":0},{"$f":"'K20 - time schedule'!HE12","v":0},{"$f":"'K20 - time schedule'!HF12","v":0},{"$f":"'K20 - time schedule'!HG12","v":0},{"$f":"'K20 - time schedule'!HH12","v":0},{"$f":"'K20 - time schedule'!HI12","v":0},{"$f":"'K20 - time schedule'!HJ12","v":0},{"$f":"'K20 - time schedule'!HK12","v":0},{"$f":"'K20 - time schedule'!HL12","v":0},{"$f":"'K20 - time schedule'!HM12","v":0},{"$f":"'K20 - time schedule'!HN12","v":0},{"$f":"'K20 - time schedule'!HO12","v":0},{"$f":"'K20 - time schedule'!HP12","v":0},{"$f":"'K20 - time schedule'!HQ12","v":0},{"$f":"'K20 - time schedule'!HR12","v":0},{"$f":"'K20 - time schedule'!HS12","v":0},{"$f":"'K20 - time schedule'!HT12","v":0},{"$f":"'K20 - time schedule'!HU12","v":0},{"$f":"'K20 - time schedule'!HV12","v":0},{"$f":"'K20 - time schedule'!HW12","v":0},{"$f":"'K20 - time schedule'!HX12","v":0},{"$f":"'K20 - time schedule'!HY12","v":0},{"$f":"'K20 - time schedule'!HZ12","v":0},{"$f":"'K20 - time schedule'!IA12","v":0},{"$f":"'K20 - time schedule'!IB12","v":0},{"$f":"'K20 - time schedule'!IC12","v":0},{"$f":"'K20 - time schedule'!ID12","v":0},{"$f":"'K20 - time schedule'!IE12","v":0},{"$f":"'K20 - time schedule'!IF12","v":0},{"$f":"'K20 - time schedule'!IG12","v":0},{"$f":"'K20 - time schedule'!IH12","v":0},{"$f":"'K20 - time schedule'!II12","v":0},{"$f":"'K20 - time schedule'!IJ12","v":0},{"$f":"'K20 - time schedule'!IK12","v":0},{"$f":"'K20 - time schedule'!IL12","v":0},{"$f":"'K20 - time schedule'!IM12","v":0},{"$f":"'K20 - time schedule'!IN12","v":0},{"$f":"'K20 - time schedule'!IO12","v":0},{"$f":"'K20 - time schedule'!IP12","v":0},{"$f":"'K20 - time schedule'!IQ12","v":0},{"$f":"'K20 - time schedule'!IR12","v":0},{"$f":"'K20 - time schedule'!IS12","v":0},{"$f":"'K20 - time schedule'!IT12","v":0},{"$f":"'K20 - time schedule'!IU12","v":0},{"$f":"'K20 - time schedule'!IV12","v":0},{"$f":"'K20 - time schedule'!IW12","v":0},{"$f":"'K20 - time schedule'!IX12","v":0},{"$f":"'K20 - time schedule'!IY12","v":0},{"$f":"'K20 - time schedule'!IZ12","v":0},{"$f":"'K20 - time schedule'!JA12","v":0},{"$f":"'K20 - time schedule'!JB12","v":0},{"$f":"'K20 - time schedule'!JC12","v":0},{"$f":"'K20 - time schedule'!JD12","v":0},{"$f":"'K20 - time schedule'!JE12","v":0},{"$f":"'K20 - time schedule'!JF12","v":0},{"$f":"'K20 - time schedule'!JG12","v":0},{"$f":"'K20 - time schedule'!JH12","v":0},{"$f":"'K20 - time schedule'!JI12","v":0},{"$f":"'K20 - time schedule'!JJ12","v":0},{"$f":"'K20 - time schedule'!JK12","v":0},{"$f":"'K20 - time schedule'!JL12","v":0},{"$f":"'K20 - time schedule'!JM12","v":0},{"$f":"'K20 - time schedule'!JN12","v":0},{"$f":"'K20 - time schedule'!JO12","v":0},{"$f":"'K20 - time schedule'!JP12","v":0},{"$f":"'K20 - time schedule'!JQ12","v":0},{"$f":"'K20 - time schedule'!JR12","v":0},{"$f":"'K20 - time schedule'!JS12","v":0},{"$f":"'K20 - time schedule'!JT12","v":0},{"$f":"'K20 - time schedule'!JU12","v":0},{"$f":"'K20 - time schedule'!JV12","v":0},{"$f":"'K20 - time schedule'!JW12","v":0},{"$f":"'K20 - time schedule'!JX12","v":0},{"$f":"'K20 - time schedule'!JY12","v":0},{"$f":"'K20 - time schedule'!JZ12","v":0},{"$f":"'K20 - time schedule'!KA12","v":0},{"$f":"'K20 - time schedule'!KB12","v":0},{"$f":"'K20 - time schedule'!KC12","v":0},{"$f":"'K20 - time schedule'!KD12","v":0},{"$f":"'K20 - time schedule'!KE12","v":0},{"$f":"'K20 - time schedule'!KF12","v":0},{"$f":"'K20 - time schedule'!KG12","v":0},{"$f":"'K20 - time schedule'!KH12","v":0},{"$f":"'K20 - time schedule'!KI12","v":0},{"$f":"'K20 - time schedule'!KJ12","v":0},{"$f":"'K20 - time schedule'!KK12","v":0},{"$f":"'K20 - time schedule'!KL12","v":0},{"$f":"'K20 - time schedule'!KM12","v":0},{"$f":"'K20 - time schedule'!KN12","v":0},{"$f":"'K20 - time schedule'!KO12","v":0},{"$f":"'K20 - time schedule'!KP12","v":0},{"$f":"'K20 - time schedule'!KQ12","v":0},{"$f":"'K20 - time schedule'!KR12","v":0},{"$f":"'K20 - time schedule'!KS12","v":0},{"$f":"'K20 - time schedule'!KT12","v":0}]
["Boiler room K20 - approved implementation documentation","K20",{"$f":"'K20 - time schedule'!G16","v":0},{"$f":"'K20 - time schedule'!H16","v":0},{"$f":"'K20 - time schedule'!I16","v":0},{"$f":"'K20 - time schedule'!J16","v":0},{"$f":"'K20 - time schedule'!K16","v":0},{"$f":"'K20 - time schedule'!L16","v":0},{"$f":"'K20 - time schedule'!M16","v":0},{"$f":"'K20 - time schedule'!N16","v":0},{"$f":"'K20 - time schedule'!O16","v":0},{"$f":"'K20 - time schedule'!P16","v":0},{"$f":"'K20 - time schedule'!Q16","v":0},{"$f":"'K20 - time schedule'!R16","v":0},{"$f":"'K20 - time schedule'!S16","v":0},{"$f":"'K20 - time schedule'!T16","v":0},{"$f":"'K20 - time schedule'!U16","v":0},{"$f":"'K20 - time schedule'!V16","v":0},{"$f":"'K20 - time schedule'!W16","v":0},{"$f":"'K20 - time schedule'!X16","v":0},{"$f":"'K20 - time schedule'!Y16","v":0},{"$f":"'K20 - time schedule'!Z16","v":0},{"$f":"'K20 - time schedule'!AA16","v":0},{"$f":"'K20 - time schedule'!AB16","v":0},{"$f":"'K20 - time schedule'!AC16","v":0},{"$f":"'K20 - time schedule'!AD16","v":0},{"$f":"'K20 - time schedule'!AE16","v":0},{"$f":"'K20 - time schedule'!AF16","v":0},{"$f":"'K20 - time schedule'!AG16","v":0},{"$f":"'K20 - time schedule'!AH16","v":0},{"$f":"'K20 - time schedule'!AI16","v":0},{"$f":"'K20 - time schedule'!AJ16","v":0},{"$f":"'K20 - time schedule'!AK16","v":0},{"$f":"'K20 - time schedule'!AL16","v":0},{"$f":"'K20 - time schedule'!AM16","v":0},{"$f":"'K20 - time schedule'!AN16","v":0},{"$f":"'K20 - time schedule'!AO16","v":0},{"$f":"'K20 - time schedule'!AP16","v":0},{"$f":"'K20 - time schedule'!AQ16","v":0},{"$f":"'K20 - time schedule'!AR16","v":0},{"$f":"'K20 - time schedule'!AS16","v":0},{"$f":"'K20 - time schedule'!AT16","v":0},{"$f":"'K20 - time schedule'!AU16","v":0},{"$f":"'K20 - time schedule'!AV16","v":0},{"$f":"'K20 - time schedule'!AW16","v":0},{"$f":"'K20 - time schedule'!AX16","v":0},{"$f":"'K20 - time schedule'!AY16","v":0},{"$f":"'K20 - time schedule'!AZ16","v":0},{"$f":"'K20 - time schedule'!BA16","v":0},{"$f":"'K20 - time schedule'!BB16","v":0},{"$f":"'K20 - time schedule'!BC16","v":0},{"$f":"'K20 - time schedule'!BD16","v":0},{"$f":"'K20 - time schedule'!BE16","v":0},{"$f":"'K20 - time schedule'!BF16","v":0},{"$f":"'K20 - time schedule'!BG16","v":0},{"$f":"'K20 - time schedule'!BH16","v":0},{"$f":"'K20 - time schedule'!BI16","v":0},{"$f":"'K20 - time schedule'!BJ16","v":0},{"$f":"'K20 - time schedule'!BK16","v":0},{"$f":"'K20 - time schedule'!BL16","v":0},{"$f":"'K20 - time schedule'!BM16","v":0},{"$f":"'K20 - time schedule'!BN16","v":0},{"$f":"'K20 - time schedule'!BO16","v":0},{"$f":"'K20 - time schedule'!BP16","v":0},{"$f":"'K20 - time schedule'!BQ16","v":0},{"$f":"'K20 - time schedule'!BR16","v":0},{"$f":"'K20 - time schedule'!BS16","v":0},{"$f":"'K20 - time schedule'!BT16","v":0},{"$f":"'K20 - time schedule'!BU16","v":0},{"$f":"'K20 - time schedule'!BV16","v":0},{"$f":"'K20 - time schedule'!BW16","v":0},{"$f":"'K20 - time schedule'!BX16","v":0},{"$f":"'K20 - time schedule'!BY16","v":0},{"$f":"'K20 - time schedule'!BZ16","v":0},{"$f":"'K20 - time schedule'!CA16","v":0},{"$f":"'K20 - time schedule'!CB16","v":0},{"$f":"'K20 - time schedule'!CC16","v":0},{"$f":"'K20 - time schedule'!CD16","v":0},{"$f":"'K20 - time schedule'!CE16","v":0},{"$f":"'K20 - time schedule'!CF16","v":0},{"$f":"'K20 - time schedule'!CG16","v":0},{"$f":"'K20 - time schedule'!CH16","v":0},{"$f":"'K20 - time schedule'!CI16","v":0},{"$f":"'K20 - time schedule'!CJ16","v":0},{"$f":"'K20 - time schedule'!CK16","v":0},{"$f":"'K20 - time schedule'!CL16","v":0},{"$f":"'K20 - time schedule'!CM16","v":0},{"$f":"'K20 - time schedule'!CN16","v":0},{"$f":"'K20 - time schedule'!CO16","v":0},{"$f":"'K20 - time schedule'!CP16","v":0},{"$f":"'K20 - time schedule'!CQ16","v":0},{"$f":"'K20 - time schedule'!CR16","v":0},{"$f":"'K20 - time schedule'!CS16","v":0},{"$f":"'K20 - time schedule'!CT16","v":0},{"$f":"'K20 - time schedule'!CU16","v":0},{"$f":"'K20 - time schedule'!CV16","v":0},{"$f":"'K20 - time schedule'!CW16","v":0},{"$f":"'K20 - time schedule'!CX16","v":0},{"$f":"'K20 - time schedule'!CY16","v":0},{"$f":"'K20 - time schedule'!CZ16","v":0},{"$f":"'K20 - time schedule'!DA16","v":0},{"$f":"'K20 - time schedule'!DB16","v":0},{"$f":"'K20 - time schedule'!DC16","v":0},{"$f":"'K20 - time schedule'!DD16","v":0},{"$f":"'K20 - time schedule'!DE16","v":0},{"$f":"'K20 - time schedule'!DF16","v":0},{"$f":"'K20 - time schedule'!DG16","v":0},{"$f":"'K20 - time schedule'!DH16","v":0},{"$f":"'K20 - time schedule'!DI16","v":0},{"$f":"'K20 - time schedule'!DJ16","v":0},{"$f":"'K20 - time schedule'!DK16","v":0},{"$f":"'K20 - time schedule'!DL16","v":0},{"$f":"'K20 - time schedule'!DM16","v":0},{"$f":"'K20 - time schedule'!DN16","v":0},{"$f":"'K20 - time schedule'!DO16","v":0},{"$f":"'K20 - time schedule'!DP16","v":0},{"$f":"'K20 - time schedule'!DQ16","v":0},{"$f":"'K20 - time schedule'!DR16","v":0},{"$f":"'K20 - time schedule'!DS16","v":0},{"$f":"'K20 - time schedule'!DT16","v":0},{"$f":"'K20 - time schedule'!DU16","v":0},{"$f":"'K20 - time schedule'!DV16","v":0},{"$f":"'K20 - time schedule'!DW16","v":0},{"$f":"'K20 - time schedule'!DX16","v":0},{"$f":"'K20 - time schedule'!DY16","v":0},{"$f":"'K20 - time schedule'!DZ16","v":0},{"$f":"'K20 - time schedule'!EA16","v":0},{"$f":"'K20 - time schedule'!EB16","v":0},{"$f":"'K20 - time schedule'!EC16","v":0},{"$f":"'K20 - time schedule'!ED16","v":0},{"$f":"'K20 - time schedule'!EE16","v":0},{"$f":"'K20 - time schedule'!EF16","v":0},{"$f":"'K20 - time schedule'!EG16","v":0},{"$f":"'K20 - time schedule'!EH16","v":0},{"$f":"'K20 - time schedule'!EI16","v":0},{"$f":"'K20 - time schedule'!EJ16","v":0},{"$f":"'K20 - time schedule'!EK16","v":0},{"$f":"'K20 - time schedule'!EL16","v":0},{"$f":"'K20 - time schedule'!EM16","v":0},{"$f":"'K20 - time schedule'!EN16","v":0},{"$f":"'K20 - time schedule'!EO16","v":0},{"$f":"'K20 - time schedule'!EP16","v":0},{"$f":"'K20 - time schedule'!EQ16","v":0},{"$f":"'K20 - time schedule'!ER16","v":0},{"$f":"'K20 - time schedule'!ES16","v":0},{"$f":"'K20 - time schedule'!ET16","v":0},{"$f":"'K20 - time schedule'!EU16","v":0},{"$f":"'K20 - time schedule'!EV16","v":0},{"$f":"'K20 - time schedule'!EW16","v":0},{"$f":"'K20 - time schedule'!EX16","v":0},{"$f":"'K20 - time schedule'!EY16","v":0},{"$f":"'K20 - time schedule'!EZ16","v":0},{"$f":"'K20 - time schedule'!FA16","v":0},{"$f":"'K20 - time schedule'!FB16","v":0},{"$f":"'K20 - time schedule'!FC16","v":0},{"$f":"'K20 - time schedule'!FD16","v":0},{"$f":"'K20 - time schedule'!FE16","v":0},{"$f":"'K20 - time schedule'!FF16","v":0},{"$f":"'K20 - time schedule'!FG16","v":0},{"$f":"'K20 - time schedule'!FH16","v":0},{"$f":"'K20 - time schedule'!FI16","v":0},{"$f":"'K20 - time schedule'!FJ16","v":0},{"$f":"'K20 - time schedule'!FK16","v":0},{"$f":"'K20 - time schedule'!FL16","v":0},{"$f":"'K20 - time schedule'!FM16","v":0},{"$f":"'K20 - time schedule'!FN16","v":0},{"$f":"'K20 - time schedule'!FO16","v":0},{"$f":"'K20 - time schedule'!FP16","v":0},{"$f":"'K20 - time schedule'!FQ16","v":0},{"$f":"'K20 - time schedule'!FR16","v":0},{"$f":"'K20 - time schedule'!FS16","v":0},{"$f":"'K20 - time schedule'!FT16","v":0},{"$f":"'K20 - time schedule'!FU16","v":0},{"$f":"'K20 - time schedule'!FV16","v":0},{"$f":"'K20 - time schedule'!FW16","v":0},{"$f":"'K20 - time schedule'!FX16","v":0},{"$f":"'K20 - time schedule'!FY16","v":0},{"$f":"'K20 - time schedule'!FZ16","v":0},{"$f":"'K20 - time schedule'!GA16","v":0},{"$f":"'K20 - time schedule'!GB16","v":0},{"$f":"'K20 - time schedule'!GC16","v":0},{"$f":"'K20 - time schedule'!GD16","v":0},{"$f":"'K20 - time schedule'!GE16","v":0},{"$f":"'K20 - time schedule'!GF16","v":0},{"$f":"'K20 - time schedule'!GG16","v":0},{"$f":"'K20 - time schedule'!GH13","v":0},{"$f":"'K20 - time schedule'!GI13","v":0},{"$f":"'K20 - time schedule'!GJ13","v":0},{"$f":"'K20 - time schedule'!GK13","v":0},{"$f":"'K20 - time schedule'!GL13","v":0},{"$f":"'K20 - time schedule'!GM13","v":0},{"$f":"'K20 - time schedule'!GN13","v":0},{"$f":"'K20 - time schedule'!GO13","v":0},{"$f":"'K20 - time schedule'!GP13","v":0},{"$f":"'K20 - time schedule'!GQ13","v":0},{"$f":"'K20 - time schedule'!GR13","v":0},{"$f":"'K20 - time schedule'!GS13","v":0},{"$f":"'K20 - time schedule'!GT13","v":0},{"$f":"'K20 - time schedule'!GU13","v":0},{"$f":"'K20 - time schedule'!GV13","v":0},{"$f":"'K20 - time schedule'!GW13","v":0},{"$f":"'K20 - time schedule'!GX13","v":0},{"$f":"'K20 - time schedule'!GY13","v":0},{"$f":"'K20 - time schedule'!GZ13","v":0},{"$f":"'K20 - time schedule'!HA13","v":0},{"$f":"'K20 - time schedule'!HB13","v":0},{"$f":"'K20 - time schedule'!HC13","v":0},{"$f":"'K20 - time schedule'!HD13","v":0},{"$f":"'K20 - time schedule'!HE13","v":0},{"$f":"'K20 - time schedule'!HF13","v":0},{"$f":"'K20 - time schedule'!HG13","v":0},{"$f":"'K20 - time schedule'!HH13","v":0},{"$f":"'K20 - time schedule'!HI13","v":0},{"$f":"'K20 - time schedule'!HJ13","v":0},{"$f":"'K20 - time schedule'!HK13","v":0},{"$f":"'K20 - time schedule'!HL13","v":0},{"$f":"'K20 - time schedule'!HM13","v":0},{"$f":"'K20 - time schedule'!HN13","v":0},{"$f":"'K20 - time schedule'!HO13","v":0},{"$f":"'K20 - time schedule'!HP13","v":0},{"$f":"'K20 - time schedule'!HQ13","v":0},{"$f":"'K20 - time schedule'!HR13","v":0},{"$f":"'K20 - time schedule'!HS13","v":0},{"$f":"'K20 - time schedule'!HT13","v":0},{"$f":"'K20 - time schedule'!HU13","v":0},{"$f":"'K20 - time schedule'!HV13","v":0},{"$f":"'K20 - time schedule'!HW13","v":0},{"$f":"'K20 - time schedule'!HX13","v":0},{"$f":"'K20 - time schedule'!HY13","v":0},{"$f":"'K20 - time schedule'!HZ13","v":0},{"$f":"'K20 - time schedule'!IA13","v":0},{"$f":"'K20 - time schedule'!IB13","v":0},{"$f":"'K20 - time schedule'!IC13","v":0},{"$f":"'K20 - time schedule'!ID13","v":0},{"$f":"'K20 - time schedule'!IE13","v":0},{"$f":"'K20 - time schedule'!IF13","v":0},{"$f":"'K20 - time schedule'!IG13","v":0},{"$f":"'K20 - time schedule'!IH13","v":0},{"$f":"'K20 - time schedule'!II13","v":0},{"$f":"'K20 - time schedule'!IJ13","v":0},{"$f":"'K20 - time schedule'!IK13","v":0},{"$f":"'K20 - time schedule'!IL13","v":0},{"$f":"'K20 - time schedule'!IM13","v":0},{"$f":"'K20 - time schedule'!IN13","v":0},{"$f":"'K20 - time schedule'!IO13","v":0},{"$f":"'K20 - time schedule'!IP13","v":0},{"$f":"'K20 - time schedule'!IQ13","v":0},{"$f":"'K20 - time schedule'!IR13","v":0},{"$f":"'K20 - time schedule'!IS13","v":0},{"$f":"'K20 - time schedule'!IT13","v":0},{"$f":"'K20 - time schedule'!IU13","v":0},{"$f":"'K20 - time schedule'!IV13","v":0},{"$f":"'K20 - time schedule'!IW13","v":0},{"$f":"'K20 - time schedule'!IX13","v":0},{"$f":"'K20 - time schedule'!IY13","v":0},{"$f":"'K20 - time schedule'!IZ13","v":0},{"$f":"'K20 - time schedule'!JA13","v":0},{"$f":"'K20 - time schedule'!JB13","v":0},{"$f":"'K20 - time schedule'!JC13","v":0},{"$f":"'K20 - time schedule'!JD13","v":0},{"$f":"'K20 - time schedule'!JE13","v":0},{"$f":"'K20 - time schedule'!JF13","v":0},{"$f":"'K20 - time schedule'!JG13","v":0},{"$f":"'K20 - time schedule'!JH13","v":0},{"$f":"'K20 - time schedule'!JI13","v":0},{"$f":"'K20 - time schedule'!JJ13","v":0},{"$f":"'K20 - time schedule'!JK13","v":0},{"$f":"'K20 - time schedule'!JL13","v":0},{"$f":"'K20 - time schedule'!JM13","v":0},{"$f":"'K20 - time schedule'!JN13","v":0},{"$f":"'K20 - time schedule'!JO13","v":0},{"$f":"'K20 - time schedule'!JP13","v":0},{"$f":"'K20 - time schedule'!JQ13","v":0},{"$f":"'K20 - time schedule'!JR13","v":0},{"$f":"'K20 - time schedule'!JS13","v":0},{"$f":"'K20 - time schedule'!JT13","v":0},{"$f":"'K20 - time schedule'!JU13","v":0},{"$f":"'K20 - time schedule'!JV13","v":0},{"$f":"'K20 - time schedule'!JW13","v":0},{"$f":"'K20 - time schedule'!JX13","v":0},{"$f":"'K20 - time schedule'!JY13","v":0},{"$f":"'K20 - time schedule'!JZ13","v":0},{"$f":"'K20 - time schedule'!KA13","v":0},{"$f":"'K20 - time schedule'!KB13","v":0},{"$f":"'K20 - time schedule'!KC13","v":0},{"$f":"'K20 - time schedule'!KD13","v":0},{"$f":"'K20 - time schedule'!KE13","v":0},{"$f":"'K20 - time schedule'!KF13","v":0},{"$f":"'K20 - time schedule'!KG13","v":0},{"$f":"'K20 - time schedule'!KH13","v":0},{"$f":"'K20 - time schedule'!KI13","v":0},{"$f":"'K20 - time schedule'!KJ13","v":0},{"$f":"'K20 - time schedule'!KK13","v":0},{"$f":"'K20 - time schedule'!KL13","v":0},{"$f":"'K20 - time schedule'!KM13","v":0},{"$f":"'K20 - time schedule'!KN13","v":0},{"$f":"'K20 - time schedule'!KO13","v":0},{"$f":"'K20 - time schedule'!KP13","v":0},{"$f":"'K20 - time schedule'!KQ13","v":0},{"$f":"'K20 - time schedule'!KR13","v":0},{"$f":"'K20 - time schedule'!KS13","v":0},{"$f":"'K20 - time schedule'!KT13","v":0}]
["Boiler room K20 - handover and acceptance of construction site","K20",{"$f":"'K20 - time schedule'!G18","v":0},{"$f":"'K20 - time schedule'!H18","v":0},{"$f":"'K20 - time schedule'!I18","v":0},{"$f":"'K20 - time schedule'!J18","v":0},{"$f":"'K20 - time schedule'!K18","v":0},{"$f":"'K20 - time schedule'!L18","v":0},{"$f":"'K20 - time schedule'!M18","v":0},{"$f":"'K20 - time schedule'!N18","v":0},{"$f":"'K20 - time schedule'!O18","v":0},{"$f":"'K20 - time schedule'!P18","v":0},{"$f":"'K20 - time schedule'!Q18","v":0},{"$f":"'K20 - time schedule'!R18","v":0},{"$f":"'K20 - time schedule'!S18","v":0},{"$f":"'K20 - time schedule'!T18","v":0},{"$f":"'K20 - time schedule'!U18","v":0},{"$f":"'K20 - time schedule'!V18","v":0},{"$f":"'K20 - time schedule'!W18","v":0},{"$f":"'K20 - time schedule'!X18","v":0},{"$f":"'K20 - time schedule'!Y18","v":0},{"$f":"'K20 - time schedule'!Z18","v":0},{"$f":"'K20 - time schedule'!AA18","v":0},{"$f":"'K20 - time schedule'!AB18","v":0},{"$f":"'K20 - time schedule'!AC18","v":0},{"$f":"'K20 - time schedule'!AD18","v":0},{"$f":"'K20 - time schedule'!AE18","v":0},{"$f":"'K20 - time schedule'!AF18","v":0},{"$f":"'K20 - time schedule'!AG18","v":0},{"$f":"'K20 - time schedule'!AH18","v":0},{"$f":"'K20 - time schedule'!AI18","v":0},{"$f":"'K20 - time schedule'!AJ18","v":0},{"$f":"'K20 - time schedule'!AK18","v":0},{"$f":"'K20 - time schedule'!AL18","v":0},{"$f":"'K20 - time schedule'!AM18","v":0},{"$f":"'K20 - time schedule'!AN18","v":0},{"$f":"'K20 - time schedule'!AO18","v":0},{"$f":"'K20 - time schedule'!AP18","v":0},{"$f":"'K20 - time schedule'!AQ18","v":0},{"$f":"'K20 - time schedule'!AR18","v":0},{"$f":"'K20 - time schedule'!AS18","v":0},{"$f":"'K20 - time schedule'!AT18","v":0},{"$f":"'K20 - time schedule'!AU18","v":0},{"$f":"'K20 - time schedule'!AV18","v":0},{"$f":"'K20 - time schedule'!AW18","v":0},{"$f":"'K20 - time schedule'!AX18","v":0},{"$f":"'K20 - time schedule'!AY18","v":0},{"$f":"'K20 - time schedule'!AZ18","v":0},{"$f":"'K20 - time schedule'!BA18","v":0},{"$f":"'K20 - time schedule'!BB18","v":0},{"$f":"'K20 - time schedule'!BC18","v":0},{"$f":"'K20 - time schedule'!BD18","v":0},{"$f":"'K20 - time schedule'!BE18","v":0},{"$f":"'K20 - time schedule'!BF18","v":0},{"$f":"'K20 - time schedule'!BG18","v":0},{"$f":"'K20 - time schedule'!BH18","v":0},{"$f":"'K20 - time schedule'!BI18","v":0},{"$f":"'K20 - time schedule'!BJ18","v":0},{"$f":"'K20 - time schedule'!BK18","v":0},{"$f":"'K20 - time schedule'!BL18","v":0},{"$f":"'K20 - time schedule'!BM18","v":0},{"$f":"'K20 - time schedule'!BN18","v":0},{"$f":"'K20 - time schedule'!BO18","v":0},{"$f":"'K20 - time schedule'!BP18","v":0},{"$f":"'K20 - time schedule'!BQ18","v":0},{"$f":"'K20 - time schedule'!BR18","v":0},{"$f":"'K20 - time schedule'!BS18","v":0},{"$f":"'K20 - time schedule'!BT18","v":0},{"$f":"'K20 - time schedule'!BU18","v":0},{"$f":"'K20 - time schedule'!BV18","v":0},{"$f":"'K20 - time schedule'!BW18","v":0},{"$f":"'K20 - time schedule'!BX18","v":0},{"$f":"'K20 - time schedule'!BY18","v":0},{"$f":"'K20 - time schedule'!BZ18","v":0},{"$f":"'K20 - time schedule'!CA18","v":0},{"$f":"'K20 - time schedule'!CB18","v":0},{"$f":"'K20 - time schedule'!CC18","v":0},{"$f":"'K20 - time schedule'!CD18","v":0},{"$f":"'K20 - time schedule'!CE18","v":0},{"$f":"'K20 - time schedule'!CF18","v":0},{"$f":"'K20 - time schedule'!CG18","v":0},{"$f":"'K20 - time schedule'!CH18","v":0},{"$f":"'K20 - time schedule'!CI18","v":0},{"$f":"'K20 - time schedule'!CJ18","v":0},{"$f":"'K20 - time schedule'!CK18","v":0},{"$f":"'K20 - time schedule'!CL18","v":0},{"$f":"'K20 - time schedule'!CM18","v":0},{"$f":"'K20 - time schedule'!CN18","v":0},{"$f":"'K20 - time schedule'!CO18","v":0},{"$f":"'K20 - time schedule'!CP18","v":0},{"$f":"'K20 - time schedule'!CQ18","v":0},{"$f":"'K20 - time schedule'!CR18","v":0},{"$f":"'K20 - time schedule'!CS18","v":0},{"$f":"'K20 - time schedule'!CT18","v":0},{"$f":"'K20 - time schedule'!CU18","v":0},{"$f":"'K20 - time schedule'!CV18","v":0},{"$f":"'K20 - time schedule'!CW18","v":0},{"$f":"'K20 - time schedule'!CX18","v":0},{"$f":"'K20 - time schedule'!CY18","v":0},{"$f":"'K20 - time schedule'!CZ18","v":0},{"$f":"'K20 - time schedule'!DA18","v":0},{"$f":"'K20 - time schedule'!DB18","v":0},{"$f":"'K20 - time schedule'!DC18","v":0},{"$f":"'K20 - time schedule'!DD18","v":0},{"$f":"'K20 - time schedule'!DE18","v":0},{"$f":"'K20 - time schedule'!DF18","v":0},{"$f":"'K20 - time schedule'!DG18","v":0},{"$f":"'K20 - time schedule'!DH18","v":0},{"$f":"'K20 - time schedule'!DI18","v":0},{"$f":"'K20 - time schedule'!DJ18","v":0},{"$f":"'K20 - time schedule'!DK18","v":0},{"$f":"'K20 - time schedule'!DL18","v":0},{"$f":"'K20 - time schedule'!DM18","v":0},{"$f":"'K20 - time schedule'!DN18","v":0},{"$f":"'K20 - time schedule'!DO18","v":0},{"$f":"'K20 - time schedule'!DP18","v":0},{"$f":"'K20 - time schedule'!DQ18","v":0},{"$f":"'K20 - time schedule'!DR18","v":0},{"$f":"'K20 - time schedule'!DS18","v":0},{"$f":"'K20 - time schedule'!DT18","v":0},{"$f":"'K20 - time schedule'!DU18","v":0},{"$f":"'K20 - time schedule'!DV18","v":0},{"$f":"'K20 - time schedule'!DW18","v":0},{"$f":"'K20 - time schedule'!DX18","v":0},{"$f":"'K20 - time schedule'!DY18","v":0},{"$f":"'K20 - time schedule'!DZ18","v":0},{"$f":"'K20 - time schedule'!EA18","v":0},{"$f":"'K20 - time schedule'!EB18","v":0},{"$f":"'K20 - time schedule'!EC18","v":0},{"$f":"'K20 - time schedule'!ED18","v":0},{"$f":"'K20 - time schedule'!EE18","v":0},{"$f":"'K20 - time schedule'!EF18","v":0},{"$f":"'K20 - time schedule'!EG18","v":0},{"$f":"'K20 - time schedule'!EH18","v":0},{"$f":"'K20 - time schedule'!EI18","v":0},{"$f":"'K20 - time schedule'!EJ18","v":0},{"$f":"'K20 - time schedule'!EK18","v":0},{"$f":"'K20 - time schedule'!EL18","v":0},{"$f":"'K20 - time schedule'!EM18","v":0},{"$f":"'K20 - time schedule'!EN18","v":0},{"$f":"'K20 - time schedule'!EO18","v":0},{"$f":"'K20 - time schedule'!EP18","v":0},{"$f":"'K20 - time schedule'!EQ18","v":0},{"$f":"'K20 - time schedule'!ER18","v":0},{"$f":"'K20 - time schedule'!ES18","v":0},{"$f":"'K20 - time schedule'!ET18","v":0},{"$f":"'K20 - time schedule'!EU18","v":0},{"$f":"'K20 - time schedule'!EV18","v":0},{"$f":"'K20 - time schedule'!EW18","v":0},{"$f":"'K20 - time schedule'!EX18","v":0},{"$f":"'K20 - time schedule'!EY18","v":0},{"$f":"'K20 - time schedule'!EZ18","v":0},{"$f":"'K20 - time schedule'!FA18","v":0},{"$f":"'K20 - time schedule'!FB18","v":0},{"$f":"'K20 - time schedule'!FC18","v":0},{"$f":"'K20 - time schedule'!FD18","v":0},{"$f":"'K20 - time schedule'!FE18","v":0},{"$f":"'K20 - time schedule'!FF18","v":0},{"$f":"'K20 - time schedule'!FG18","v":0},{"$f":"'K20 - time schedule'!FH18","v":0},{"$f":"'K20 - time schedule'!FI18","v":0},{"$f":"'K20 - time schedule'!FJ18","v":0},{"$f":"'K20 - time schedule'!FK18","v":0},{"$f":"'K20 - time schedule'!FL18","v":0},{"$f":"'K20 - time schedule'!FM18","v":0},{"$f":"'K20 - time schedule'!FN18","v":0},{"$f":"'K20 - time schedule'!FO18","v":0},{"$f":"'K20 - time schedule'!FP18","v":0},{"$f":"'K20 - time schedule'!FQ18","v":0},{"$f":"'K20 - time schedule'!FR18","v":0},{"$f":"'K20 - time schedule'!FS18","v":0},{"$f":"'K20 - time schedule'!FT18","v":0},{"$f":"'K20 - time schedule'!FU18","v":0},{"$f":"'K20 - time schedule'!FV18","v":0},{"$f":"'K20 - time schedule'!FW18","v":0},{"$f":"'K20 - time schedule'!FX18","v":0},{"$f":"'K20 - time schedule'!FY18","v":0},{"$f":"'K20 - time schedule'!FZ18","v":0},{"$f":"'K20 - time schedule'!GA18","v":0},{"$f":"'K20 - time schedule'!GB18","v":0},{"$f":"'K20 - time schedule'!GC18","v":0},{"$f":"'K20 - time schedule'!GD18","v":0},{"$f":"'K20 - time schedule'!GE18","v":0},{"$f":"'K20 - time schedule'!GF18","v":0},{"$f":"'K20 - time schedule'!GG18","v":0},{"$f":"'K20 - time schedule'!GH14","v":0},{"$f":"'K20 - time schedule'!GI14","v":0},{"$f":"'K20 - time schedule'!GJ14","v":0},{"$f":"'K20 - time schedule'!GK14","v":0},{"$f":"'K20 - time schedule'!GL14","v":0},{"$f":"'K20 - time schedule'!GM14","v":0},{"$f":"'K20 - time schedule'!GN14","v":0},{"$f":"'K20 - time schedule'!GO14","v":0},{"$f":"'K20 - time schedule'!GP14","v":0},{"$f":"'K20 - time schedule'!GQ14","v":0},{"$f":"'K20 - time schedule'!GR14","v":0},{"$f":"'K20 - time schedule'!GS14","v":0},{"$f":"'K20 - time schedule'!GT14","v":0},{"$f":"'K20 - time schedule'!GU14","v":0},{"$f":"'K20 - time schedule'!GV14","v":0},{"$f":"'K20 - time schedule'!GW14","v":0},{"$f":"'K20 - time schedule'!GX14","v":0},{"$f":"'K20 - time schedule'!GY14","v":0},{"$f":"'K20 - time schedule'!GZ14","v":0},{"$f":"'K20 - time schedule'!HA14","v":0},{"$f":"'K20 - time schedule'!HB14","v":0},{"$f":"'K20 - time schedule'!HC14","v":0},{"$f":"'K20 - time schedule'!HD14","v":0},{"$f":"'K20 - time schedule'!HE14","v":0},{"$f":"'K20 - time schedule'!HF14","v":0},{"$f":"'K20 - time schedule'!HG14","v":0},{"$f":"'K20 - time schedule'!HH14","v":0},{"$f":"'K20 - time schedule'!HI14","v":0},{"$f":"'K20 - time schedule'!HJ14","v":0},{"$f":"'K20 - time schedule'!HK14","v":0},{"$f":"'K20 - time schedule'!HL14","v":0},{"$f":"'K20 - time schedule'!HM14","v":0},{"$f":"'K20 - time schedule'!HN14","v":0},{"$f":"'K20 - time schedule'!HO14","v":0},{"$f":"'K20 - time schedule'!HP14","v":0},{"$f":"'K20 - time schedule'!HQ14","v":0},{"$f":"'K20 - time schedule'!HR14","v":0},{"$f":"'K20 - time schedule'!HS14","v":0},{"$f":"'K20 - time schedule'!HT14","v":0},{"$f":"'K20 - time schedule'!HU14","v":0},{"$f":"'K20 - time schedule'!HV14","v":0},{"$f":"'K20 - time schedule'!HW14","v":0},{"$f":"'K20 - time schedule'!HX14","v":0},{"$f":"'K20 - time schedule'!HY14","v":0},{"$f":"'K20 - time schedule'!HZ14","v":0},{"$f":"'K20 - time schedule'!IA14","v":0},{"$f":"'K20 - time schedule'!IB14","v":0},{"$f":"'K20 - time schedule'!IC14","v":0},{"$f":"'K20 - time schedule'!ID14","v":0},{"$f":"'K20 - time schedule'!IE14","v":0},{"$f":"'K20 - time schedule'!IF14","v":0},{"$f":"'K20 - time schedule'!IG14","v":0},{"$f":"'K20 - time schedule'!IH14","v":0},{"$f":"'K20 - time schedule'!II14","v":0},{"$f":"'K20 - time schedule'!IJ14","v":0},{"$f":"'K20 - time schedule'!IK14","v":0},{"$f":"'K20 - time schedule'!IL14","v":0},{"$f":"'K20 - time schedule'!IM14","v":0},{"$f":"'K20 - time schedule'!IN14","v":0},{"$f":"'K20 - time schedule'!IO14","v":0},{"$f":"'K20 - time schedule'!IP14","v":0},{"$f":"'K20 - time schedule'!IQ14","v":0},{"$f":"'K20 - time schedule'!IR14","v":0},{"$f":"'K20 - time schedule'!IS14","v":0},{"$f":"'K20 - time schedule'!IT14","v":0},{"$f":"'K20 - time schedule'!IU14","v":0},{"$f":"'K20 - time schedule'!IV14","v":0},{"$f":"'K20 - time schedule'!IW14","v":0},{"$f":"'K20 - time schedule'!IX14","v":0},{"$f":"'K20 - time schedule'!IY14","v":0},{"$f":"'K20 - time schedule'!IZ14","v":0},{"$f":"'K20 - time schedule'!JA14","v":0},{"$f":"'K20 - time schedule'!JB14","v":0},{"$f":"'K20 - time schedule'!JC14","v":0},{"$f":"'K20 - time schedule'!JD14","v":0},{"$f":"'K20 - time schedule'!JE14","v":0},{"$f":"'K20 - time schedule'!JF14","v":0},{"$f":"'K20 - time schedule'!JG14","v":0},{"$f":"'K20 - time schedule'!JH14","v":0},{"$f":"'K20 - time schedule'!JI14","v":0},{"$f":"'K20 - time schedule'!JJ14","v":0},{"$f":"'K20 - time schedule'!JK14","v":0},{"$f":"'K20 - time schedule'!JL14","v":0},{"$f":"'K20 - time schedule'!JM14","v":0},{"$f":"'K20 - time schedule'!JN14","v":0},{"$f":"'K20 - time schedule'!JO14","v":0},{"$f":"'K20 - time schedule'!JP14","v":0},{"$f":"'K20 - time schedule'!JQ14","v":0},{"$f":"'K20 - time schedule'!JR14","v":0},{"$f":"'K20 - time schedule'!JS14","v":0},{"$f":"'K20 - time schedule'!JT14","v":0},{"$f":"'K20 - time schedule'!JU14","v":0},{"$f":"'K20 - time schedule'!JV14","v":0},{"$f":"'K20 - time schedule'!JW14","v":0},{"$f":"'K20 - time schedule'!JX14","v":0},{"$f":"'K20 - time schedule'!JY14","v":0},{"$f":"'K20 - time schedule'!JZ14","v":0},{"$f":"'K20 - time schedule'!KA14","v":0},{"$f":"'K20 - time schedule'!KB14","v":0},{"$f":"'K20 - time schedule'!KC14","v":0},{"$f":"'K20 - time schedule'!KD14","v":0},{"$f":"'K20 - time schedule'!KE14","v":0},{"$f":"'K20 - time schedule'!KF14","v":0},{"$f":"'K20 - time schedule'!KG14","v":0},{"$f":"'K20 - time schedule'!KH14","v":0},{"$f":"'K20 - time schedule'!KI14","v":0},{"$f":"'K20 - time schedule'!KJ14","v":0},{"$f":"'K20 - time schedule'!KK14","v":0},{"$f":"'K20 - time schedule'!KL14","v":0},{"$f":"'K20 - time schedule'!KM14","v":0},{"$f":"'K20 - time schedule'!KN14","v":0},{"$f":"'K20 - time schedule'!KO14","v":0},{"$f":"'K20 - time schedule'!KP14","v":0},{"$f":"'K20 - time schedule'!KQ14","v":0},{"$f":"'K20 - time schedule'!KR14","v":0},{"$f":"'K20 - time schedule'!KS14","v":0},{"$f":"'K20 - time schedule'!KT14","v":0}]
["Boiler room K20 - the boiler itself including all components","K20",{"$f":"'K20 - time schedule'!G20","v":0},{"$f":"'K20 - time schedule'!H20","v":0},{"$f":"'K20 - time schedule'!I20","v":0},{"$f":"'K20 - time schedule'!J20","v":0},{"$f":"'K20 - time schedule'!K20","v":0},{"$f":"'K20 - time schedule'!L20","v":0},{"$f":"'K20 - time schedule'!M20","v":0},{"$f":"'K20 - time schedule'!N20","v":0},{"$f":"'K20 - time schedule'!O20","v":0},{"$f":"'K20 - time schedule'!P20","v":0},{"$f":"'K20 - time schedule'!Q20","v":0},{"$f":"'K20 - time schedule'!R20","v":0},{"$f":"'K20 - time schedule'!S20","v":0},{"$f":"'K20 - time schedule'!T20","v":0},{"$f":"'K20 - time schedule'!U20","v":0},{"$f":"'K20 - time schedule'!V20","v":0},{"$f":"'K20 - time schedule'!W20","v":0},{"$f":"'K20 - time schedule'!X20","v":0},{"$f":"'K20 - time schedule'!Y20","v":0},{"$f":"'K20 - time schedule'!Z20","v":0},{"$f":"'K20 - time schedule'!AA20","v":0},{"$f":"'K20 - time schedule'!AB20","v":0},{"$f":"'K20 - time schedule'!AC20","v":0},{"$f":"'K20 - time schedule'!AD20","v":0},{"$f":"'K20 - time schedule'!AE20","v":0},{"$f":"'K20 - time schedule'!AF20","v":0},{"$f":"'K20 - time schedule'!AG20","v":0},{"$f":"'K20 - time schedule'!AH20","v":0},{"$f":"'K20 - time schedule'!AI20","v":0},{"$f":"'K20 - time schedule'!AJ20","v":0},{"$f":"'K20 - time schedule'!AK20","v":0},{"$f":"'K20 - time schedule'!AL20","v":0},{"$f":"'K20 - time schedule'!AM20","v":0},{"$f":"'K20 - time schedule'!AN20","v":0},{"$f":"'K20 - time schedule'!AO20","v":0},{"$f":"'K20 - time schedule'!AP20","v":0},{"$f":"'K20 - time schedule'!AQ20","v":0},{"$f":"'K20 - time schedule'!AR20","v":0},{"$f":"'K20 - time schedule'!AS20","v":0},{"$f":"'K20 - time schedule'!AT20","v":0},{"$f":"'K20 - time schedule'!AU20","v":0},{"$f":"'K20 - time schedule'!AV20","v":0},{"$f":"'K20 - time schedule'!AW20","v":0},{"$f":"'K20 - time schedule'!AX20","v":0},{"$f":"'K20 - time schedule'!AY20","v":0},{"$f":"'K20 - time schedule'!AZ20","v":0},{"$f":"'K20 - time schedule'!BA20","v":0},{"$f":"'K20 - time schedule'!BB20","v":0},{"$f":"'K20 - time schedule'!BC20","v":0},{"$f":"'K20 - time schedule'!BD20","v":0},{"$f":"'K20 - time schedule'!BE20","v":0},{"$f":"'K20 - time schedule'!BF20","v":0},{"$f":"'K20 - time schedule'!BG20","v":0},{"$f":"'K20 - time schedule'!BH20","v":0},{"$f":"'K20 - time schedule'!BI20","v":0},{"$f":"'K20 - time schedule'!BJ20","v":0},{"$f":"'K20 - time schedule'!BK20","v":0},{"$f":"'K20 - time schedule'!BL20","v":0},{"$f":"'K20 - time schedule'!BM20","v":0},{"$f":"'K20 - time schedule'!BN20","v":0},{"$f":"'K20 - time schedule'!BO20","v":0},{"$f":"'K20 - time schedule'!BP20","v":0},{"$f":"'K20 - time schedule'!BQ20","v":0},{"$f":"'K20 - time schedule'!BR20","v":0},{"$f":"'K20 - time schedule'!BS20","v":0},{"$f":"'K20 - time schedule'!BT20","v":0},{"$f":"'K20 - time schedule'!BU20","v":0},{"$f":"'K20 - time schedule'!BV20","v":0},{"$f":"'K20 - time schedule'!BW20","v":0},{"$f":"'K20 - time schedule'!BX20","v":0},{"$f":"'K20 - time schedule'!BY20","v":0},{"$f":"'K20 - time schedule'!BZ20","v":0},{"$f":"'K20 - time schedule'!CA20","v":0},{"$f":"'K20 - time schedule'!CB20","v":0},{"$f":"'K20 - time schedule'!CC20","v":0},{"$f":"'K20 - time schedule'!CD20","v":0},{"$f":"'K20 - time schedule'!CE20","v":0},{"$f":"'K20 - time schedule'!CF20","v":0},{"$f":"'K20 - time schedule'!CG20","v":0},{"$f":"'K20 - time schedule'!CH20","v":0},{"$f":"'K20 - time schedule'!CI20","v":0},{"$f":"'K20 - time schedule'!CJ20","v":0},{"$f":"'K20 - time schedule'!CK20","v":0},{"$f":"'K20 - time schedule'!CL20","v":0},{"$f":"'K20 - time schedule'!CM20","v":0},{"$f":"'K20 - time schedule'!CN20","v":0},{"$f":"'K20 - time schedule'!CO20","v":0},{"$f":"'K20 - time schedule'!CP20","v":0},{"$f":"'K20 - time schedule'!CQ20","v":0},{"$f":"'K20 - time schedule'!CR20","v":0},{"$f":"'K20 - time schedule'!CS20","v":0},{"$f":"'K20 - time schedule'!CT20","v":0},{"$f":"'K20 - time schedule'!CU20","v":0},{"$f":"'K20 - time schedule'!CV20","v":0},{"$f":"'K20 - time schedule'!CW20","v":0},{"$f":"'K20 - time schedule'!CX20","v":0},{"$f":"'K20 - time schedule'!CY20","v":0},{"$f":"'K20 - time schedule'!CZ20","v":0},{"$f":"'K20 - time schedule'!DA20","v":0},{"$f":"'K20 - time schedule'!DB20","v":0},{"$f":"'K20 - time schedule'!DC20","v":0},{"$f":"'K20 - time schedule'!DD20","v":0},{"$f":"'K20 - time schedule'!DE20","v":0},{"$f":"'K20 - time schedule'!DF20","v":0},{"$f":"'K20 - time schedule'!DG20","v":0},{"$f":"'K20 - time schedule'!DH20","v":0},{"$f":"'K20 - time schedule'!DI20","v":0},{"$f":"'K20 - time schedule'!DJ20","v":0},{"$f":"'K20 - time schedule'!DK20","v":0},{"$f":"'K20 - time schedule'!DL20","v":0},{"$f":"'K20 - time schedule'!DM20","v":0},{"$f":"'K20 - time schedule'!DN20","v":0},{"$f":"'K20 - time schedule'!DO20","v":0},{"$f":"'K20 - time schedule'!DP20","v":0},{"$f":"'K20 - time schedule'!DQ20","v":0},{"$f":"'K20 - time schedule'!DR20","v":0},{"$f":"'K20 - time schedule'!DS20","v":0},{"$f":"'K20 - time schedule'!DT20","v":0},{"$f":"'K20 - time schedule'!DU20","v":0},{"$f":"'K20 - time schedule'!DV20","v":0},{"$f":"'K20 - time schedule'!DW20","v":0},{"$f":"'K20 - time schedule'!DX20","v":0},{"$f":"'K20 - time schedule'!DY20","v":0},{"$f":"'K20 - time schedule'!DZ20","v":0},{"$f":"'K20 - time schedule'!EA20","v":0},{"$f":"'K20 - time schedule'!EB20","v":0},{"$f":"'K20 - time schedule'!EC20","v":0},{"$f":"'K20 - time schedule'!ED20","v":0},{"$f":"'K20 - time schedule'!EE20","v":0},{"$f":"'K20 - time schedule'!EF20","v":0},{"$f":"'K20 - time schedule'!EG20","v":0},{"$f":"'K20 - time schedule'!EH20","v":0},{"$f":"'K20 - time schedule'!EI20","v":0},{"$f":"'K20 - time schedule'!EJ20","v":0},{"$f":"'K20 - time schedule'!EK20","v":0},{"$f":"'K20 - time schedule'!EL20","v":0},{"$f":"'K20 - time schedule'!EM20","v":0},{"$f":"'K20 - time schedule'!EN20","v":0},{"$f":"'K20 - time schedule'!EO20","v":0},{"$f":"'K20 - time schedule'!EP20","v":0},{"$f":"'K20 - time schedule'!EQ20","v":0},{"$f":"'K20 - time schedule'!ER20","v":0},{"$f":"'K20 - time schedule'!ES20","v":0},{"$f":"'K20 - time schedule'!ET20","v":0},{"$f":"'K20 - time schedule'!EU20","v":0},{"$f":"'K20 - time schedule'!EV20","v":0},{"$f":"'K20 - time schedule'!EW20","v":0},{"$f":"'K20 - time schedule'!EX20","v":0},{"$f":"'K20 - time schedule'!EY20","v":0},{"$f":"'K20 - time schedule'!EZ20","v":0},{"$f":"'K20 - time schedule'!FA20","v":0},{"$f":"'K20 - time schedule'!FB20","v":0},{"$f":"'K20 - time schedule'!FC20","v":0},{"$f":"'K20 - time schedule'!FD20","v":0},{"$f":"'K20 - time schedule'!FE20","v":0},{"$f":"'K20 - time schedule'!FF20","v":0},{"$f":"'K20 - time schedule'!FG20","v":0},{"$f":"'K20 - time schedule'!FH20","v":0},{"$f":"'K20 - time schedule'!FI20","v":0},{"$f":"'K20 - time schedule'!FJ20","v":0},{"$f":"'K20 - time schedule'!FK20","v":0},{"$f":"'K20 - time schedule'!FL20","v":0},{"$f":"'K20 - time schedule'!FM20","v":0},{"$f":"'K20 - time schedule'!FN20","v":0},{"$f":"'K20 - time schedule'!FO20","v":0},{"$f":"'K20 - time schedule'!FP20","v":0},{"$f":"'K20 - time schedule'!FQ20","v":0},{"$f":"'K20 - time schedule'!FR20","v":0},{"$f":"'K20 - time schedule'!FS20","v":0},{"$f":"'K20 - time schedule'!FT20","v":0},{"$f":"'K20 - time schedule'!FU20","v":0},{"$f":"'K20 - time schedule'!FV20","v":0},{"$f":"'K20 - time schedule'!FW20","v":0},{"$f":"'K20 - time schedule'!FX20","v":0},{"$f":"'K20 - time schedule'!FY20","v":0},{"$f":"'K20 - time schedule'!FZ20","v":0},{"$f":"'K20 - time schedule'!GA20","v":0},{"$f":"'K20 - time schedule'!GB20","v":0},{"$f":"'K20 - time schedule'!GC20","v":0},{"$f":"'K20 - time schedule'!GD20","v":0},{"$f":"'K20 - time schedule'!GE20","v":0},{"$f":"'K20 - time schedule'!GF20","v":0},{"$f":"'K20 - time schedule'!GG20","v":0},{"$f":"'K20 - time schedule'!GH15","v":0},{"$f":"'K20 - time schedule'!GI15","v":0},{"$f":"'K20 - time schedule'!GJ15","v":0},{"$f":"'K20 - time schedule'!GK15","v":0},{"$f":"'K20 - time schedule'!GL15","v":0},{"$f":"'K20 - time schedule'!GM15","v":0},{"$f":"'K20 - time schedule'!GN15","v":0},{"$f":"'K20 - time schedule'!GO15","v":0},{"$f":"'K20 - time schedule'!GP15","v":0},{"$f":"'K20 - time schedule'!GQ15","v":0},{"$f":"'K20 - time schedule'!GR15","v":0},{"$f":"'K20 - time schedule'!GS15","v":0},{"$f":"'K20 - time schedule'!GT15","v":0},{"$f":"'K20 - time schedule'!GU15","v":0},{"$f":"'K20 - time schedule'!GV15","v":0},{"$f":"'K20 - time schedule'!GW15","v":0},{"$f":"'K20 - time schedule'!GX15","v":0},{"$f":"'K20 - time schedule'!GY15","v":0},{"$f":"'K20 - time schedule'!GZ15","v":0},{"$f":"'K20 - time schedule'!HA15","v":0},{"$f":"'K20 - time schedule'!HB15","v":0},{"$f":"'K20 - time schedule'!HC15","v":0},{"$f":"'K20 - time schedule'!HD15","v":0},{"$f":"'K20 - time schedule'!HE15","v":0},{"$f":"'K20 - time schedule'!HF15","v":0},{"$f":"'K20 - time schedule'!HG15","v":0},{"$f":"'K20 - time schedule'!HH15","v":0},{"$f":"'K20 - time schedule'!HI15","v":0},{"$f":"'K20 - time schedule'!HJ15","v":0},{"$f":"'K20 - time schedule'!HK15","v":0},{"$f":"'K20 - time schedule'!HL15","v":0},{"$f":"'K20 - time schedule'!HM15","v":0},{"$f":"'K20 - time schedule'!HN15","v":0},{"$f":"'K20 - time schedule'!HO15","v":0},{"$f":"'K20 - time schedule'!HP15","v":0},{"$f":"'K20 - time schedule'!HQ15","v":0},{"$f":"'K20 - time schedule'!HR15","v":0},{"$f":"'K20 - time schedule'!HS15","v":0},{"$f":"'K20 - time schedule'!HT15","v":0},{"$f":"'K20 - time schedule'!HU15","v":0},{"$f":"'K20 - time schedule'!HV15","v":0},{"$f":"'K20 - time schedule'!HW15","v":0},{"$f":"'K20 - time schedule'!HX15","v":0},{"$f":"'K20 - time schedule'!HY15","v":0},{"$f":"'K20 - time schedule'!HZ15","v":0},{"$f":"'K20 - time schedule'!IA15","v":0},{"$f":"'K20 - time schedule'!IB15","v":0},{"$f":"'K20 - time schedule'!IC15","v":0},{"$f":"'K20 - time schedule'!ID15","v":0},{"$f":"'K20 - time schedule'!IE15","v":0},{"$f":"'K20 - time schedule'!IF15","v":0},{"$f":"'K20 - time schedule'!IG15","v":0},{"$f":"'K20 - time schedule'!IH15","v":0},{"$f":"'K20 - time schedule'!II15","v":0},{"$f":"'K20 - time schedule'!IJ15","v":0},{"$f":"'K20 - time schedule'!IK15","v":0},{"$f":"'K20 - time schedule'!IL15","v":0},{"$f":"'K20 - time schedule'!IM15","v":0},{"$f":"'K20 - time schedule'!IN15","v":0},{"$f":"'K20 - time schedule'!IO15","v":0},{"$f":"'K20 - time schedule'!IP15","v":0},{"$f":"'K20 - time schedule'!IQ15","v":0},{"$f":"'K20 - time schedule'!IR15","v":0},{"$f":"'K20 - time schedule'!IS15","v":0},{"$f":"'K20 - time schedule'!IT15","v":0},{"$f":"'K20 - time schedule'!IU15","v":0},{"$f":"'K20 - time schedule'!IV15","v":0},{"$f":"'K20 - time schedule'!IW15","v":0},{"$f":"'K20 - time schedule'!IX15","v":0},{"$f":"'K20 - time schedule'!IY15","v":0},{"$f":"'K20 - time schedule'!IZ15","v":0},{"$f":"'K20 - time schedule'!JA15","v":0},{"$f":"'K20 - time schedule'!JB15","v":0},{"$f":"'K20 - time schedule'!JC15","v":0},{"$f":"'K20 - time schedule'!JD15","v":0},{"$f":"'K20 - time schedule'!JE15","v":0},{"$f":"'K20 - time schedule'!JF15","v":0},{"$f":"'K20 - time schedule'!JG15","v":0},{"$f":"'K20 - time schedule'!JH15","v":0},{"$f":"'K20 - time schedule'!JI15","v":0},{"$f":"'K20 - time schedule'!JJ15","v":0},{"$f":"'K20 - time schedule'!JK15","v":0},{"$f":"'K20 - time schedule'!JL15","v":0},{"$f":"'K20 - time schedule'!JM15","v":0},{"$f":"'K20 - time schedule'!JN15","v":0},{"$f":"'K20 - time schedule'!JO15","v":0},{"$f":"'K20 - time schedule'!JP15","v":0},{"$f":"'K20 - time schedule'!JQ15","v":0},{"$f":"'K20 - time schedule'!JR15","v":0},{"$f":"'K20 - time schedule'!JS15","v":0},{"$f":"'K20 - time schedule'!JT15","v":0},{"$f":"'K20 - time schedule'!JU15","v":0},{"$f":"'K20 - time schedule'!JV15","v":0},{"$f":"'K20 - time schedule'!JW15","v":0},{"$f":"'K20 - time schedule'!JX15","v":0},{"$f":"'K20 - time schedule'!JY15","v":0},{"$f":"'K20 - time schedule'!JZ15","v":0},{"$f":"'K20 - time schedule'!KA15","v":0},{"$f":"'K20 - time schedule'!KB15","v":0},{"$f":"'K20 - time schedule'!KC15","v":0},{"$f":"'K20 - time schedule'!KD15","v":0},{"$f":"'K20 - time schedule'!KE15","v":0},{"$f":"'K20 - time schedule'!KF15","v":0},{"$f":"'K20 - time schedule'!KG15","v":0},{"$f":"'K20 - time schedule'!KH15","v":0},{"$f":"'K20 - time schedule'!KI15","v":0},{"$f":"'K20 - time schedule'!KJ15","v":0},{"$f":"'K20 - time schedule'!KK15","v":0},{"$f":"'K20 - time schedule'!KL15","v":0},{"$f":"'K20 - time schedule'!KM15","v":0},{"$f":"'K20 - time schedule'!KN15","v":0},{"$f":"'K20 - time schedule'!KO15","v":0},{"$f":"'K20 - time schedule'!KP15","v":0},{"$f":"'K20 - time schedule'!KQ15","v":0},{"$f":"'K20 - time schedule'!KR15","v":0},{"$f":"'K20 - time schedule'!KS15","v":0},{"$f":"'K20 - time schedule'!KT15","v":0}]
["Boiler room K20 - operating fuel storage tanks including transport of chips into boiler","K20",{"$f":"'K20 - time schedule'!G22","v":0},{"$f":"'K20 - time schedule'!H22","v":0},{"$f":"'K20 - time schedule'!I22","v":0},{"$f":"'K20 - time schedule'!J22","v":0},{"$f":"'K20 - time schedule'!K22","v":0},{"$f":"'K20 - time schedule'!L22","v":0},{"$f":"'K20 - time schedule'!M22","v":0},{"$f":"'K20 - time schedule'!N22","v":0},{"$f":"'K20 - time schedule'!O22","v":0},{"$f":"'K20 - time schedule'!P22","v":0},{"$f":"'K20 - time schedule'!Q22","v":0},{"$f":"'K20 - time schedule'!R22","v":0},{"$f":"'K20 - time schedule'!S22","v":0},{"$f":"'K20 - time schedule'!T22","v":0},{"$f":"'K20 - time schedule'!U22","v":0},{"$f":"'K20 - time schedule'!V22","v":0},{"$f":"'K20 - time schedule'!W22","v":0},{"$f":"'K20 - time schedule'!X22","v":0},{"$f":"'K20 - time schedule'!Y22","v":0},{"$f":"'K20 - time schedule'!Z22","v":0},{"$f":"'K20 - time schedule'!AA22","v":0},{"$f":"'K20 - time schedule'!AB22","v":0},{"$f":"'K20 - time schedule'!AC22","v":0},{"$f":"'K20 - time schedule'!AD22","v":0},{"$f":"'K20 - time schedule'!AE22","v":0},{"$f":"'K20 - time schedule'!AF22","v":0},{"$f":"'K20 - time schedule'!AG22","v":0},{"$f":"'K20 - time schedule'!AH22","v":0},{"$f":"'K20 - time schedule'!AI22","v":0},{"$f":"'K20 - time schedule'!AJ22","v":0},{"$f":"'K20 - time schedule'!AK22","v":0},{"$f":"'K20 - time schedule'!AL22","v":0},{"$f":"'K20 - time schedule'!AM22","v":0},{"$f":"'K20 - time schedule'!AN22","v":0},{"$f":"'K20 - time schedule'!AO22","v":0},{"$f":"'K20 - time schedule'!AP22","v":0},{"$f":"'K20 - time schedule'!AQ22","v":0},{"$f":"'K20 - time schedule'!AR22","v":0},{"$f":"'K20 - time schedule'!AS22","v":0},{"$f":"'K20 - time schedule'!AT22","v":0},{"$f":"'K20 - time schedule'!AU22","v":0},{"$f":"'K20 - time schedule'!AV22","v":0},{"$f":"'K20 - time schedule'!AW22","v":0},{"$f":"'K20 - time schedule'!AX22","v":0},{"$f":"'K20 - time schedule'!AY22","v":0},{"$f":"'K20 - time schedule'!AZ22","v":0},{"$f":"'K20 - time schedule'!BA22","v":0},{"$f":"'K20 - time schedule'!BB22","v":0},{"$f":"'K20 - time schedule'!BC22","v":0},{"$f":"'K20 - time schedule'!BD22","v":0},{"$f":"'K20 - time schedule'!BE22","v":0},{"$f":"'K20 - time schedule'!BF22","v":0},{"$f":"'K20 - time schedule'!BG22","v":0},{"$f":"'K20 - time schedule'!BH22","v":0},{"$f":"'K20 - time schedule'!BI22","v":0},{"$f":"'K20 - time schedule'!BJ22","v":0},{"$f":"'K20 - time schedule'!BK22","v":0},{"$f":"'K20 - time schedule'!BL22","v":0},{"$f":"'K20 - time schedule'!BM22","v":0},{"$f":"'K20 - time schedule'!BN22","v":0},{"$f":"'K20 - time schedule'!BO22","v":0},{"$f":"'K20 - time schedule'!BP22","v":0},{"$f":"'K20 - time schedule'!BQ22","v":0},{"$f":"'K20 - time schedule'!BR22","v":0},{"$f":"'K20 - time schedule'!BS22","v":0},{"$f":"'K20 - time schedule'!BT22","v":0},{"$f":"'K20 - time schedule'!BU22","v":0},{"$f":"'K20 - time schedule'!BV22","v":0},{"$f":"'K20 - time schedule'!BW22","v":0},{"$f":"'K20 - time schedule'!BX22","v":0},{"$f":"'K20 - time schedule'!BY22","v":0},{"$f":"'K20 - time schedule'!BZ22","v":0},{"$f":"'K20 - time schedule'!CA22","v":0},{"$f":"'K20 - time schedule'!CB22","v":0},{"$f":"'K20 - time schedule'!CC22","v":0},{"$f":"'K20 - time schedule'!CD22","v":0},{"$f":"'K20 - time schedule'!CE22","v":0},{"$f":"'K20 - time schedule'!CF22","v":0},{"$f":"'K20 - time schedule'!CG22","v":0},{"$f":"'K20 - time schedule'!CH22","v":0},{"$f":"'K20 - time schedule'!CI22","v":0},{"$f":"'K20 - time schedule'!CJ22","v":0},{"$f":"'K20 - time schedule'!CK22","v":0},{"$f":"'K20 - time schedule'!CL22","v":0},{"$f":"'K20 - time schedule'!CM22","v":0},{"$f":"'K20 - time schedule'!CN22","v":0},{"$f":"'K20 - time schedule'!CO22","v":0},{"$f":"'K20 - time schedule'!CP22","v":0},{"$f":"'K20 - time schedule'!CQ22","v":0},{"$f":"'K20 - time schedule'!CR22","v":0},{"$f":"'K20 - time schedule'!CS22","v":0},{"$f":"'K20 - time schedule'!CT22","v":0},{"$f":"'K20 - time schedule'!CU22","v":0},{"$f":"'K20 - time schedule'!CV22","v":0},{"$f":"'K20 - time schedule'!CW22","v":0},{"$f":"'K20 - time schedule'!CX22","v":0},{"$f":"'K20 - time schedule'!CY22","v":0},{"$f":"'K20 - time schedule'!CZ22","v":0},{"$f":"'K20 - time schedule'!DA22","v":0},{"$f":"'K20 - time schedule'!DB22","v":0},{"$f":"'K20 - time schedule'!DC22","v":0},{"$f":"'K20 - time schedule'!DD22","v":0},{"$f":"'K20 - time schedule'!DE22","v":0},{"$f":"'K20 - time schedule'!DF22","v":0},{"$f":"'K20 - time schedule'!DG22","v":0},{"$f":"'K20 - time schedule'!DH22","v":0},{"$f":"'K20 - time schedule'!DI22","v":0},{"$f":"'K20 - time schedule'!DJ22","v":0},{"$f":"'K20 - time schedule'!DK22","v":0},{"$f":"'K20 - time schedule'!DL22","v":0},{"$f":"'K20 - time schedule'!DM22","v":0},{"$f":"'K20 - time schedule'!DN22","v":0},{"$f":"'K20 - time schedule'!DO22","v":0},{"$f":"'K20 - time schedule'!DP22","v":0},{"$f":"'K20 - time schedule'!DQ22","v":0},{"$f":"'K20 - time schedule'!DR22","v":0},{"$f":"'K20 - time schedule'!DS22","v":0},{"$f":"'K20 - time schedule'!DT22","v":0},{"$f":"'K20 - time schedule'!DU22","v":0},{"$f":"'K20 - time schedule'!DV22","v":0},{"$f":"'K20 - time schedule'!DW22","v":0},{"$f":"'K20 - time schedule'!DX22","v":0},{"$f":"'K20 - time schedule'!DY22","v":0},{"$f":"'K20 - time schedule'!DZ22","v":0},{"$f":"'K20 - time schedule'!EA22","v":0},{"$f":"'K20 - time schedule'!EB22","v":0},{"$f":"'K20 - time schedule'!EC22","v":0},{"$f":"'K20 - time schedule'!ED22","v":0},{"$f":"'K20 - time schedule'!EE22","v":0},{"$f":"'K20 - time schedule'!EF22","v":0},{"$f":"'K20 - time schedule'!EG22","v":0},{"$f":"'K20 - time schedule'!EH22","v":0},{"$f":"'K20 - time schedule'!EI22","v":0},{"$f":"'K20 - time schedule'!EJ22","v":0},{"$f":"'K20 - time schedule'!EK22","v":0},{"$f":"'K20 - time schedule'!EL22","v":0},{"$f":"'K20 - time schedule'!EM22","v":0},{"$f":"'K20 - time schedule'!EN22","v":0},{"$f":"'K20 - time schedule'!EO22","v":0},{"$f":"'K20 - time schedule'!EP22","v":0},{"$f":"'K20 - time schedule'!EQ22","v":0},{"$f":"'K20 - time schedule'!ER22","v":0},{"$f":"'K20 - time schedule'!ES22","v":0},{"$f":"'K20 - time schedule'!ET22","v":0},{"$f":"'K20 - time schedule'!EU22","v":0},{"$f":"'K20 - time schedule'!EV22","v":0},{"$f":"'K20 - time schedule'!EW22","v":0},{"$f":"'K20 - time schedule'!EX22","v":0},{"$f":"'K20 - time schedule'!EY22","v":0},{"$f":"'K20 - time schedule'!EZ22","v":0},{"$f":"'K20 - time schedule'!FA22","v":0},{"$f":"'K20 - time schedule'!FB22","v":0},{"$f":"'K20 - time schedule'!FC22","v":0},{"$f":"'K20 - time schedule'!FD22","v":0},{"$f":"'K20 - time schedule'!FE22","v":0},{"$f":"'K20 - time schedule'!FF22","v":0},{"$f":"'K20 - time schedule'!FG22","v":0},{"$f":"'K20 - time schedule'!FH22","v":0},{"$f":"'K20 - time schedule'!FI22","v":0},{"$f":"'K20 - time schedule'!FJ22","v":0},{"$f":"'K20 - time schedule'!FK22","v":0},{"$f":"'K20 - time schedule'!FL22","v":0},{"$f":"'K20 - time schedule'!FM22","v":0},{"$f":"'K20 - time schedule'!FN22","v":0},{"$f":"'K20 - time schedule'!FO22","v":0},{"$f":"'K20 - time schedule'!FP22","v":0},{"$f":"'K20 - time schedule'!FQ22","v":0},{"$f":"'K20 - time schedule'!FR22","v":0},{"$f":"'K20 - time schedule'!FS22","v":0},{"$f":"'K20 - time schedule'!FT22","v":0},{"$f":"'K20 - time schedule'!FU22","v":0},{"$f":"'K20 - time schedule'!FV22","v":0},{"$f":"'K20 - time schedule'!FW22","v":0},{"$f":"'K20 - time schedule'!FX22","v":0},{"$f":"'K20 - time schedule'!FY22","v":0},{"$f":"'K20 - time schedule'!FZ22","v":0},{"$f":"'K20 - time schedule'!GA22","v":0},{"$f":"'K20 - time schedule'!GB22","v":0},{"$f":"'K20 - time schedule'!GC22","v":0},{"$f":"'K20 - time schedule'!GD22","v":0},{"$f":"'K20 - time schedule'!GE22","v":0},{"$f":"'K20 - time schedule'!GF22","v":0},{"$f":"'K20 - time schedule'!GG22","v":0},{"$f":"'K20 - time schedule'!GH16","v":0},{"$f":"'K20 - time schedule'!GI16","v":0},{"$f":"'K20 - time schedule'!GJ16","v":0},{"$f":"'K20 - time schedule'!GK16","v":0},{"$f":"'K20 - time schedule'!GL16","v":0},{"$f":"'K20 - time schedule'!GM16","v":0},{"$f":"'K20 - time schedule'!GN16","v":0},{"$f":"'K20 - time schedule'!GO16","v":0},{"$f":"'K20 - time schedule'!GP16","v":0},{"$f":"'K20 - time schedule'!GQ16","v":0},{"$f":"'K20 - time schedule'!GR16","v":0},{"$f":"'K20 - time schedule'!GS16","v":0},{"$f":"'K20 - time schedule'!GT16","v":0},{"$f":"'K20 - time schedule'!GU16","v":0},{"$f":"'K20 - time schedule'!GV16","v":0},{"$f":"'K20 - time schedule'!GW16","v":0},{"$f":"'K20 - time schedule'!GX16","v":0},{"$f":"'K20 - time schedule'!GY16","v":0},{"$f":"'K20 - time schedule'!GZ16","v":0},{"$f":"'K20 - time schedule'!HA16","v":0},{"$f":"'K20 - time schedule'!HB16","v":0},{"$f":"'K20 - time schedule'!HC16","v":0},{"$f":"'K20 - time schedule'!HD16","v":0},{"$f":"'K20 - time schedule'!HE16","v":0},{"$f":"'K20 - time schedule'!HF16","v":0},{"$f":"'K20 - time schedule'!HG16","v":0},{"$f":"'K20 - time schedule'!HH16","v":0},{"$f":"'K20 - time schedule'!HI16","v":0},{"$f":"'K20 - time schedule'!HJ16","v":0},{"$f":"'K20 - time schedule'!HK16","v":0},{"$f":"'K20 - time schedule'!HL16","v":0},{"$f":"'K20 - time schedule'!HM16","v":0},{"$f":"'K20 - time schedule'!HN16","v":0},{"$f":"'K20 - time schedule'!HO16","v":0},{"$f":"'K20 - time schedule'!HP16","v":0},{"$f":"'K20 - time schedule'!HQ16","v":0},{"$f":"'K20 - time schedule'!HR16","v":0},{"$f":"'K20 - time schedule'!HS16","v":0},{"$f":"'K20 - time schedule'!HT16","v":0},{"$f":"'K20 - time schedule'!HU16","v":0},{"$f":"'K20 - time schedule'!HV16","v":0},{"$f":"'K20 - time schedule'!HW16","v":0},{"$f":"'K20 - time schedule'!HX16","v":0},{"$f":"'K20 - time schedule'!HY16","v":0},{"$f":"'K20 - time schedule'!HZ16","v":0},{"$f":"'K20 - time schedule'!IA16","v":0},{"$f":"'K20 - time schedule'!IB16","v":0},{"$f":"'K20 - time schedule'!IC16","v":0},{"$f":"'K20 - time schedule'!ID16","v":0},{"$f":"'K20 - time schedule'!IE16","v":0},{"$f":"'K20 - time schedule'!IF16","v":0},{"$f":"'K20 - time schedule'!IG16","v":0},{"$f":"'K20 - time schedule'!IH16","v":0},{"$f":"'K20 - time schedule'!II16","v":0},{"$f":"'K20 - time schedule'!IJ16","v":0},{"$f":"'K20 - time schedule'!IK16","v":0},{"$f":"'K20 - time schedule'!IL16","v":0},{"$f":"'K20 - time schedule'!IM16","v":0},{"$f":"'K20 - time schedule'!IN16","v":0},{"$f":"'K20 - time schedule'!IO16","v":0},{"$f":"'K20 - time schedule'!IP16","v":0},{"$f":"'K20 - time schedule'!IQ16","v":0},{"$f":"'K20 - time schedule'!IR16","v":0},{"$f":"'K20 - time schedule'!IS16","v":0},{"$f":"'K20 - time schedule'!IT16","v":0},{"$f":"'K20 - time schedule'!IU16","v":0},{"$f":"'K20 - time schedule'!IV16","v":0},{"$f":"'K20 - time schedule'!IW16","v":0},{"$f":"'K20 - time schedule'!IX16","v":0},{"$f":"'K20 - time schedule'!IY16","v":0},{"$f":"'K20 - time schedule'!IZ16","v":0},{"$f":"'K20 - time schedule'!JA16","v":0},{"$f":"'K20 - time schedule'!JB16","v":0},{"$f":"'K20 - time schedule'!JC16","v":0},{"$f":"'K20 - time schedule'!JD16","v":0},{"$f":"'K20 - time schedule'!JE16","v":0},{"$f":"'K20 - time schedule'!JF16","v":0},{"$f":"'K20 - time schedule'!JG16","v":0},{"$f":"'K20 - time schedule'!JH16","v":0},{"$f":"'K20 - time schedule'!JI16","v":0},{"$f":"'K20 - time schedule'!JJ16","v":0},{"$f":"'K20 - time schedule'!JK16","v":0},{"$f":"'K20 - time schedule'!JL16","v":0},{"$f":"'K20 - time schedule'!JM16","v":0},{"$f":"'K20 - time schedule'!JN16","v":0},{"$f":"'K20 - time schedule'!JO16","v":0},{"$f":"'K20 - time schedule'!JP16","v":0},{"$f":"'K20 - time schedule'!JQ16","v":0},{"$f":"'K20 - time schedule'!JR16","v":0},{"$f":"'K20 - time schedule'!JS16","v":0},{"$f":"'K20 - time schedule'!JT16","v":0},{"$f":"'K20 - time schedule'!JU16","v":0},{"$f":"'K20 - time schedule'!JV16","v":0},{"$f":"'K20 - time schedule'!JW16","v":0},{"$f":"'K20 - time schedule'!JX16","v":0},{"$f":"'K20 - time schedule'!JY16","v":0},{"$f":"'K20 - time schedule'!JZ16","v":0},{"$f":"'K20 - time schedule'!KA16","v":0},{"$f":"'K20 - time schedule'!KB16","v":0},{"$f":"'K20 - time schedule'!KC16","v":0},{"$f":"'K20 - time schedule'!KD16","v":0},{"$f":"'K20 - time schedule'!KE16","v":0},{"$f":"'K20 - time schedule'!KF16","v":0},{"$f":"'K20 - time schedule'!KG16","v":0},{"$f":"'K20 - time schedule'!KH16","v":0},{"$f":"'K20 - time schedule'!KI16","v":0},{"$f":"'K20 - time schedule'!KJ16","v":0},{"$f":"'K20 - time schedule'!KK16","v":0},{"$f":"'K20 - time schedule'!KL16","v":0},{"$f":"'K20 - time schedule'!KM16","v":0},{"$f":"'K20 - time schedule'!KN16","v":0},{"$f":"'K20 - time schedule'!KO16","v":0},{"$f":"'K20 - time schedule'!KP16","v":0},{"$f":"'K20 - time schedule'!KQ16","v":0},{"$f":"'K20 - time schedule'!KR16","v":0},{"$f":"'K20 - time schedule'!KS16","v":0},{"$f":"'K20 - time schedule'!KT16","v":0}]
["Boiler room K20 - vents (air, flue, recirculation) including inner flue lines","K20",{"$f":"'K20 - time schedule'!G24","v":0},{"$f":"'K20 - time schedule'!H24","v":0},{"$f":"'K20 - time schedule'!I24","v":0},{"$f":"'K20 - time schedule'!J24","v":0},{"$f":"'K20 - time schedule'!K24","v":0},{"$f":"'K20 - time schedule'!L24","v":0},{"$f":"'K20 - time schedule'!M24","v":0},{"$f":"'K20 - time schedule'!N24","v":0},{"$f":"'K20 - time schedule'!O24","v":0},{"$f":"'K20 - time schedule'!P24","v":0},{"$f":"'K20 - time schedule'!Q24","v":0},{"$f":"'K20 - time schedule'!R24","v":0},{"$f":"'K20 - time schedule'!S24","v":0},{"$f":"'K20 - time schedule'!T24","v":0},{"$f":"'K20 - time schedule'!U24","v":0},{"$f":"'K20 - time schedule'!V24","v":0},{"$f":"'K20 - time schedule'!W24","v":0},{"$f":"'K20 - time schedule'!X24","v":0},{"$f":"'K20 - time schedule'!Y24","v":0},{"$f":"'K20 - time schedule'!Z24","v":0},{"$f":"'K20 - time schedule'!AA24","v":0},{"$f":"'K20 - time schedule'!AB24","v":0},{"$f":"'K20 - time schedule'!AC24","v":0},{"$f":"'K20 - time schedule'!AD24","v":0},{"$f":"'K20 - time schedule'!AE24","v":0},{"$f":"'K20 - time schedule'!AF24","v":0},{"$f":"'K20 - time schedule'!AG24","v":0},{"$f":"'K20 - time schedule'!AH24","v":0},{"$f":"'K20 - time schedule'!AI24","v":0},{"$f":"'K20 - time schedule'!AJ24","v":0},{"$f":"'K20 - time schedule'!AK24","v":0},{"$f":"'K20 - time schedule'!AL24","v":0},{"$f":"'K20 - time schedule'!AM24","v":0},{"$f":"'K20 - time schedule'!AN24","v":0},{"$f":"'K20 - time schedule'!AO24","v":0},{"$f":"'K20 - time schedule'!AP24","v":0},{"$f":"'K20 - time schedule'!AQ24","v":0},{"$f":"'K20 - time schedule'!AR24","v":0},{"$f":"'K20 - time schedule'!AS24","v":0},{"$f":"'K20 - time schedule'!AT24","v":0},{"$f":"'K20 - time schedule'!AU24","v":0},{"$f":"'K20 - time schedule'!AV24","v":0},{"$f":"'K20 - time schedule'!AW24","v":0},{"$f":"'K20 - time schedule'!AX24","v":0},{"$f":"'K20 - time schedule'!AY24","v":0},{"$f":"'K20 - time schedule'!AZ24","v":0},{"$f":"'K20 - time schedule'!BA24","v":0},{"$f":"'K20 - time schedule'!BB24","v":0},{"$f":"'K20 - time schedule'!BC24","v":0},{"$f":"'K20 - time schedule'!BD24","v":0},{"$f":"'K20 - time schedule'!BE24","v":0},{"$f":"'K20 - time schedule'!BF24","v":0},{"$f":"'K20 - time schedule'!BG24","v":0},{"$f":"'K20 - time schedule'!BH24","v":0},{"$f":"'K20 - time schedule'!BI24","v":0},{"$f":"'K20 - time schedule'!BJ24","v":0},{"$f":"'K20 - time schedule'!BK24","v":0},{"$f":"'K20 - time schedule'!BL24","v":0},{"$f":"'K20 - time schedule'!BM24","v":0},{"$f":"'K20 - time schedule'!BN24","v":0},{"$f":"'K20 - time schedule'!BO24","v":0},{"$f":"'K20 - time schedule'!BP24","v":0},{"$f":"'K20 - time schedule'!BQ24","v":0},{"$f":"'K20 - time schedule'!BR24","v":0},{"$f":"'K20 - time schedule'!BS24","v":0},{"$f":"'K20 - time schedule'!BT24","v":0},{"$f":"'K20 - time schedule'!BU24","v":0},{"$f":"'K20 - time schedule'!BV24","v":0},{"$f":"'K20 - time schedule'!BW24","v":0},{"$f":"'K20 - time schedule'!BX24","v":0},{"$f":"'K20 - time schedule'!BY24","v":0},{"$f":"'K20 - time schedule'!BZ24","v":0},{"$f":"'K20 - time schedule'!CA24","v":0},{"$f":"'K20 - time schedule'!CB24","v":0},{"$f":"'K20 - time schedule'!CC24","v":0},{"$f":"'K20 - time schedule'!CD24","v":0},{"$f":"'K20 - time schedule'!CE24","v":0},{"$f":"'K20 - time schedule'!CF24","v":0},{"$f":"'K20 - time schedule'!CG24","v":0},{"$f":"'K20 - time schedule'!CH24","v":0},{"$f":"'K20 - time schedule'!CI24","v":0},{"$f":"'K20 - time schedule'!CJ24","v":0},{"$f":"'K20 - time schedule'!CK24","v":0},{"$f":"'K20 - time schedule'!CL24","v":0},{"$f":"'K20 - time schedule'!CM24","v":0},{"$f":"'K20 - time schedule'!CN24","v":0},{"$f":"'K20 - time schedule'!CO24","v":0},{"$f":"'K20 - time schedule'!CP24","v":0},{"$f":"'K20 - time schedule'!CQ24","v":0},{"$f":"'K20 - time schedule'!CR24","v":0},{"$f":"'K20 - time schedule'!CS24","v":0},{"$f":"'K20 - time schedule'!CT24","v":0},{"$f":"'K20 - time schedule'!CU24","v":0},{"$f":"'K20 - time schedule'!CV24","v":0},{"$f":"'K20 - time schedule'!CW24","v":0},{"$f":"'K20 - time schedule'!CX24","v":0},{"$f":"'K20 - time schedule'!CY24","v":0},{"$f":"'K20 - time schedule'!CZ24","v":0},{"$f":"'K20 - time schedule'!DA24","v":0},{"$f":"'K20 - time schedule'!DB24","v":0},{"$f":"'K20 - time schedule'!DC24","v":0},{"$f":"'K20 - time schedule'!DD24","v":0},{"$f":"'K20 - time schedule'!DE24","v":0},{"$f":"'K20 - time schedule'!DF24","v":0},{"$f":"'K20 - time schedule'!DG24","v":0},{"$f":"'K20 - time schedule'!DH24","v":0},{"$f":"'K20 - time schedule'!DI24","v":0},{"$f":"'K20 - time schedule'!DJ24","v":0},{"$f":"'K20 - time schedule'!DK24","v":0},{"$f":"'K20 - time schedule'!DL24","v":0},{"$f":"'K20 - time schedule'!DM24","v":0},{"$f":"'K20 - time schedule'!DN24","v":0},{"$f":"'K20 - time schedule'!DO24","v":0},{"$f":"'K20 - time schedule'!DP24","v":0},{"$f":"'K20 - time schedule'!DQ24","v":0},{"$f":"'K20 - time schedule'!DR24","v":0},{"$f":"'K20 - time schedule'!DS24","v":0},{"$f":"'K20 - time schedule'!DT24","v":0},{"$f":"'K20 - time schedule'!DU24","v":0},{"$f":"'K20 - time schedule'!DV24","v":0},{"$f":"'K20 - time schedule'!DW24","v":0},{"$f":"'K20 - time schedule'!DX24","v":0},{"$f":"'K20 - time schedule'!DY24","v":0},{"$f":"'K20 - time schedule'!DZ24","v":0},{"$f":"'K20 - time schedule'!EA24","v":0},{"$f":"'K20 - time schedule'!EB24","v":0},{"$f":"'K20 - time schedule'!EC24","v":0},{"$f":"'K20 - time schedule'!ED24","v":0},{"$f":"'K20 - time schedule'!EE24","v":0},{"$f":"'K20 - time schedule'!EF24","v":0},{"$f":"'K20 - time schedule'!EG24","v":0},{"$f":"'K20 - time schedule'!EH24","v":0},{"$f":"'K20 - time schedule'!EI24","v":0},{"$f":"'K20 - time schedule'!EJ24","v":0},{"$f":"'K20 - time schedule'!EK24","v":0},{"$f":"'K20 - time schedule'!EL24","v":0},{"$f":"'K20 - time schedule'!EM24","v":0},{"$f":"'K20 - time schedule'!EN24","v":0},{"$f":"'K20 - time schedule'!EO24","v":0},{"$f":"'K20 - time schedule'!EP24","v":0},{"$f":"'K20 - time schedule'!EQ24","v":0},{"$f":"'K20 - time schedule'!ER24","v":0},{"$f":"'K20 - time schedule'!ES24","v":0},{"$f":"'K20 - time schedule'!ET24","v":0},{"$f":"'K20 - time schedule'!EU24","v":0},{"$f":"'K20 - time schedule'!EV24","v":0},{"$f":"'K20 - time schedule'!EW24","v":0},{"$f":"'K20 - time schedule'!EX24","v":0},{"$f":"'K20 - time schedule'!EY24","v":0},{"$f":"'K20 - time schedule'!EZ24","v":0},{"$f":"'K20 - time schedule'!FA24","v":0},{"$f":"'K20 - time schedule'!FB24","v":0},{"$f":"'K20 - time schedule'!FC24","v":0},{"$f":"'K20 - time schedule'!FD24","v":0},{"$f":"'K20 - time schedule'!FE24","v":0},{"$f":"'K20 - time schedule'!FF24","v":0},{"$f":"'K20 - time schedule'!FG24","v":0},{"$f":"'K20 - time schedule'!FH24","v":0},{"$f":"'K20 - time schedule'!FI24","v":0},{"$f":"'K20 - time schedule'!FJ24","v":0},{"$f":"'K20 - time schedule'!FK24","v":0},{"$f":"'K20 - time schedule'!FL24","v":0},{"$f":"'K20 - time schedule'!FM24","v":0},{"$f":"'K20 - time schedule'!FN24","v":0},{"$f":"'K20 - time schedule'!FO24","v":0},{"$f":"'K20 - time schedule'!FP24","v":0},{"$f":"'K20 - time schedule'!FQ24","v":0},{"$f":"'K20 - time schedule'!FR24","v":0},{"$f":"'K20 - time schedule'!FS24","v":0},{"$f":"'K20 - time schedule'!FT24","v":0},{"$f":"'K20 - time schedule'!FU24","v":0},{"$f":"'K20 - time schedule'!FV24","v":0},{"$f":"'K20 - time schedule'!FW24","v":0},{"$f":"'K20 - time schedule'!FX24","v":0},{"$f":"'K20 - time schedule'!FY24","v":0},{"$f":"'K20 - time schedule'!FZ24","v":0},{"$f":"'K20 - time schedule'!GA24","v":0},{"$f":"'K20 - time schedule'!GB24","v":0},{"$f":"'K20 - time schedule'!GC24","v":0},{"$f":"'K20 - time schedule'!GD24","v":0},{"$f":"'K20 - time schedule'!GE24","v":0},{"$f":"'K20 - time schedule'!GF24","v":0},{"$f":"'K20 - time schedule'!GG24","v":0},{"$f":"'K20 - time schedule'!GH17","v":0},{"$f":"'K20 - time schedule'!GI17","v":0},{"$f":"'K20 - time schedule'!GJ17","v":0},{"$f":"'K20 - time schedule'!GK17","v":0},{"$f":"'K20 - time schedule'!GL17","v":0},{"$f":"'K20 - time schedule'!GM17","v":0},{"$f":"'K20 - time schedule'!GN17","v":0},{"$f":"'K20 - time schedule'!GO17","v":0},{"$f":"'K20 - time schedule'!GP17","v":0},{"$f":"'K20 - time schedule'!GQ17","v":0},{"$f":"'K20 - time schedule'!GR17","v":0},{"$f":"'K20 - time schedule'!GS17","v":0},{"$f":"'K20 - time schedule'!GT17","v":0},{"$f":"'K20 - time schedule'!GU17","v":0},{"$f":"'K20 - time schedule'!GV17","v":0},{"$f":"'K20 - time schedule'!GW17","v":0},{"$f":"'K20 - time schedule'!GX17","v":0},{"$f":"'K20 - time schedule'!GY17","v":0},{"$f":"'K20 - time schedule'!GZ17","v":0},{"$f":"'K20 - time schedule'!HA17","v":0},{"$f":"'K20 - time schedule'!HB17","v":0},{"$f":"'K20 - time schedule'!HC17","v":0},{"$f":"'K20 - time schedule'!HD17","v":0},{"$f":"'K20 - time schedule'!HE17","v":0},{"$f":"'K20 - time schedule'!HF17","v":0},{"$f":"'K20 - time schedule'!HG17","v":0},{"$f":"'K20 - time schedule'!HH17","v":0},{"$f":"'K20 - time schedule'!HI17","v":0},{"$f":"'K20 - time schedule'!HJ17","v":0},{"$f":"'K20 - time schedule'!HK17","v":0},{"$f":"'K20 - time schedule'!HL17","v":0},{"$f":"'K20 - time schedule'!HM17","v":0},{"$f":"'K20 - time schedule'!HN17","v":0},{"$f":"'K20 - time schedule'!HO17","v":0},{"$f":"'K20 - time schedule'!HP17","v":0},{"$f":"'K20 - time schedule'!HQ17","v":0},{"$f":"'K20 - time schedule'!HR17","v":0},{"$f":"'K20 - time schedule'!HS17","v":0},{"$f":"'K20 - time schedule'!HT17","v":0},{"$f":"'K20 - time schedule'!HU17","v":0},{"$f":"'K20 - time schedule'!HV17","v":0},{"$f":"'K20 - time schedule'!HW17","v":0},{"$f":"'K20 - time schedule'!HX17","v":0},{"$f":"'K20 - time schedule'!HY17","v":0},{"$f":"'K20 - time schedule'!HZ17","v":0},{"$f":"'K20 - time schedule'!IA17","v":0},{"$f":"'K20 - time schedule'!IB17","v":0},{"$f":"'K20 - time schedule'!IC17","v":0},{"$f":"'K20 - time schedule'!ID17","v":0},{"$f":"'K20 - time schedule'!IE17","v":0},{"$f":"'K20 - time schedule'!IF17","v":0},{"$f":"'K20 - time schedule'!IG17","v":0},{"$f":"'K20 - time schedule'!IH17","v":0},{"$f":"'K20 - time schedule'!II17","v":0},{"$f":"'K20 - time schedule'!IJ17","v":0},{"$f":"'K20 - time schedule'!IK17","v":0},{"$f":"'K20 - time schedule'!IL17","v":0},{"$f":"'K20 - time schedule'!IM17","v":0},{"$f":"'K20 - time schedule'!IN17","v":0},{"$f":"'K20 - time schedule'!IO17","v":0},{"$f":"'K20 - time schedule'!IP17","v":0},{"$f":"'K20 - time schedule'!IQ17","v":0},{"$f":"'K20 - time schedule'!IR17","v":0},{"$f":"'K20 - time schedule'!IS17","v":0},{"$f":"'K20 - time schedule'!IT17","v":0},{"$f":"'K20 - time schedule'!IU17","v":0},{"$f":"'K20 - time schedule'!IV17","v":0},{"$f":"'K20 - time schedule'!IW17","v":0},{"$f":"'K20 - time schedule'!IX17","v":0},{"$f":"'K20 - time schedule'!IY17","v":0},{"$f":"'K20 - time schedule'!IZ17","v":0},{"$f":"'K20 - time schedule'!JA17","v":0},{"$f":"'K20 - time schedule'!JB17","v":0},{"$f":"'K20 - time schedule'!JC17","v":0},{"$f":"'K20 - time schedule'!JD17","v":0},{"$f":"'K20 - time schedule'!JE17","v":0},{"$f":"'K20 - time schedule'!JF17","v":0},{"$f":"'K20 - time schedule'!JG17","v":0},{"$f":"'K20 - time schedule'!JH17","v":0},{"$f":"'K20 - time schedule'!JI17","v":0},{"$f":"'K20 - time schedule'!JJ17","v":0},{"$f":"'K20 - time schedule'!JK17","v":0},{"$f":"'K20 - time schedule'!JL17","v":0},{"$f":"'K20 - time schedule'!JM17","v":0},{"$f":"'K20 - time schedule'!JN17","v":0},{"$f":"'K20 - time schedule'!JO17","v":0},{"$f":"'K20 - time schedule'!JP17","v":0},{"$f":"'K20 - time schedule'!JQ17","v":0},{"$f":"'K20 - time schedule'!JR17","v":0},{"$f":"'K20 - time schedule'!JS17","v":0},{"$f":"'K20 - time schedule'!JT17","v":0},{"$f":"'K20 - time schedule'!JU17","v":0},{"$f":"'K20 - time schedule'!JV17","v":0},{"$f":"'K20 - time schedule'!JW17","v":0},{"$f":"'K20 - time schedule'!JX17","v":0},{"$f":"'K20 - time schedule'!JY17","v":0},{"$f":"'K20 - time schedule'!JZ17","v":0},{"$f":"'K20 - time schedule'!KA17","v":0},{"$f":"'K20 - time schedule'!KB17","v":0},{"$f":"'K20 - time schedule'!KC17","v":0},{"$f":"'K20 - time schedule'!KD17","v":0},{"$f":"'K20 - time schedule'!KE17","v":0},{"$f":"'K20 - time schedule'!KF17","v":0},{"$f":"'K20 - time schedule'!KG17","v":0},{"$f":"'K20 - time schedule'!KH17","v":0},{"$f":"'K20 - time schedule'!KI17","v":0},{"$f":"'K20 - time schedule'!KJ17","v":0},{"$f":"'K20 - time schedule'!KK17","v":0},{"$f":"'K20 - time schedule'!KL17","v":0},{"$f":"'K20 - time schedule'!KM17","v":0},{"$f":"'K20 - time schedule'!KN17","v":0},{"$f":"'K20 - time schedule'!KO17","v":0},{"$f":"'K20 - time schedule'!KP17","v":0},{"$f":"'K20 - time schedule'!KQ17","v":0},{"$f":"'K20 - time schedule'!KR17","v":0},{"$f":"'K20 - time schedule'!KS17","v":0},{"$f":"'K20 - time schedule'!KT17","v":0}]
["Boiler room K20 - fabric filter","K20",{"$f":"'K20 - time schedule'!G26","v":0},{"$f":"'K20 - time schedule'!H26","v":0},{"$f":"'K20 - time schedule'!I26","v":0},{"$f":"'K20 - time schedule'!J26","v":0},{"$f":"'K20 - time schedule'!K26","v":0},{"$f":"'K20 - time schedule'!L26","v":0},{"$f":"'K20 - time schedule'!M26","v":0},{"$f":"'K20 - time schedule'!N26","v":0},{"$f":"'K20 - time schedule'!O26","v":0},{"$f":"'K20 - time schedule'!P26","v":0},{"$f":"'K20 - time schedule'!Q26","v":0},{"$f":"'K20 - time schedule'!R26","v":0},{"$f":"'K20 - time schedule'!S26","v":0},{"$f":"'K20 - time schedule'!T26","v":0},{"$f":"'K20 - time schedule'!U26","v":0},{"$f":"'K20 - time schedule'!V26","v":0},{"$f":"'K20 - time schedule'!W26","v":0},{"$f":"'K20 - time schedule'!X26","v":0},{"$f":"'K20 - time schedule'!Y26","v":0},{"$f":"'K20 - time schedule'!Z26","v":0},{"$f":"'K20 - time schedule'!AA26","v":0},{"$f":"'K20 - time schedule'!AB26","v":0},{"$f":"'K20 - time schedule'!AC26","v":0},{"$f":"'K20 - time schedule'!AD26","v":0},{"$f":"'K20 - time schedule'!AE26","v":0},{"$f":"'K20 - time schedule'!AF26","v":0},{"$f":"'K20 - time schedule'!AG26","v":0},{"$f":"'K20 - time schedule'!AH26","v":0},{"$f":"'K20 - time schedule'!AI26","v":0},{"$f":"'K20 - time schedule'!AJ26","v":0},{"$f":"'K20 - time schedule'!AK26","v":0},{"$f":"'K20 - time schedule'!AL26","v":0},{"$f":"'K20 - time schedule'!AM26","v":0},{"$f":"'K20 - time schedule'!AN26","v":0},{"$f":"'K20 - time schedule'!AO26","v":0},{"$f":"'K20 - time schedule'!AP26","v":0},{"$f":"'K20 - time schedule'!AQ26","v":0},{"$f":"'K20 - time schedule'!AR26","v":0},{"$f":"'K20 - time schedule'!AS26","v":0},{"$f":"'K20 - time schedule'!AT26","v":0},{"$f":"'K20 - time schedule'!AU26","v":0},{"$f":"'K20 - time schedule'!AV26","v":0},{"$f":"'K20 - time schedule'!AW26","v":0},{"$f":"'K20 - time schedule'!AX26","v":0},{"$f":"'K20 - time schedule'!AY26","v":0},{"$f":"'K20 - time schedule'!AZ26","v":0},{"$f":"'K20 - time schedule'!BA26","v":0},{"$f":"'K20 - time schedule'!BB26","v":0},{"$f":"'K20 - time schedule'!BC26","v":0},{"$f":"'K20 - time schedule'!BD26","v":0},{"$f":"'K20 - time schedule'!BE26","v":0},{"$f":"'K20 - time schedule'!BF26","v":0},{"$f":"'K20 - time schedule'!BG26","v":0},{"$f":"'K20 - time schedule'!BH26","v":0},{"$f":"'K20 - time schedule'!BI26","v":0},{"$f":"'K20 - time schedule'!BJ26","v":0},{"$f":"'K20 - time schedule'!BK26","v":0},{"$f":"'K20 - time schedule'!BL26","v":0},{"$f":"'K20 - time schedule'!BM26","v":0},{"$f":"'K20 - time schedule'!BN26","v":0},{"$f":"'K20 - time schedule'!BO26","v":0},{"$f":"'K20 - time schedule'!BP26","v":0},{"$f":"'K20 - time schedule'!BQ26","v":0},{"$f":"'K20 - time schedule'!BR26","v":0},{"$f":"'K20 - time schedule'!BS26","v":0},{"$f":"'K20 - time schedule'!BT26","v":0},{"$f":"'K20 - time schedule'!BU26","v":0},{"$f":"'K20 - time schedule'!BV26","v":0},{"$f":"'K20 - time schedule'!BW26","v":0},{"$f":"'K20 - time schedule'!BX26","v":0},{"$f":"'K20 - time schedule'!BY26","v":0},{"$f":"'K20 - time schedule'!BZ26","v":0},{"$f":"'K20 - time schedule'!CA26","v":0},{"$f":"'K20 - time schedule'!CB26","v":0},{"$f":"'K20 - time schedule'!CC26","v":0},{"$f":"'K20 - time schedule'!CD26","v":0},{"$f":"'K20 - time schedule'!CE26","v":0},{"$f":"'K20 - time schedule'!CF26","v":0},{"$f":"'K20 - time schedule'!CG26","v":0},{"$f":"'K20 - time schedule'!CH26","v":0},{"$f":"'K20 - time schedule'!CI26","v":0},{"$f":"'K20 - time schedule'!CJ26","v":0},{"$f":"'K20 - time schedule'!CK26","v":0},{"$f":"'K20 - time schedule'!CL26","v":0},{"$f":"'K20 - time schedule'!CM26","v":0},{"$f":"'K20 - time schedule'!CN26","v":0},{"$f":"'K20 - time schedule'!CO26","v":0},{"$f":"'K20 - time schedule'!CP26","v":0},{"$f":"'K20 - time schedule'!CQ26","v":0},{"$f":"'K20 - time schedule'!CR26","v":0},{"$f":"'K20 - time schedule'!CS26","v":0},{"$f":"'K20 - time schedule'!CT26","v":0},{"$f":"'K20 - time schedule'!CU26","v":0},{"$f":"'K20 - time schedule'!CV26","v":0},{"$f":"'K20 - time schedule'!CW26","v":0},{"$f":"'K20 - time schedule'!CX26","v":0},{"$f":"'K20 - time schedule'!CY26","v":0},{"$f":"'K20 - time schedule'!CZ26","v":0},{"$f":"'K20 - time schedule'!DA26","v":0},{"$f":"'K20 - time schedule'!DB26","v":0},{"$f":"'K20 - time schedule'!DC26","v":0},{"$f":"'K20 - time schedule'!DD26","v":0},{"$f":"'K20 - time schedule'!DE26","v":0},{"$f":"'K20 - time schedule'!DF26","v":0},{"$f":"'K20 - time schedule'!DG26","v":0},{"$f":"'K20 - time schedule'!DH26","v":0},{"$f":"'K20 - time schedule'!DI26","v":0},{"$f":"'K20 - time schedule'!DJ26","v":0},{"$f":"'K20 - time schedule'!DK26","v":0},{"$f":"'K20 - time schedule'!DL26","v":0},{"$f":"'K20 - time schedule'!DM26","v":0},{"$f":"'K20 - time schedule'!DN26","v":0},{"$f":"'K20 - time schedule'!DO26","v":0},{"$f":"'K20 - time schedule'!DP26","v":0},{"$f":"'K20 - time schedule'!DQ26","v":0},{"$f":"'K20 - time schedule'!DR26","v":0},{"$f":"'K20 - time schedule'!DS26","v":0},{"$f":"'K20 - time schedule'!DT26","v":0},{"$f":"'K20 - time schedule'!DU26","v":0},{"$f":"'K20 - time schedule'!DV26","v":0},{"$f":"'K20 - time schedule'!DW26","v":0},{"$f":"'K20 - time schedule'!DX26","v":0},{"$f":"'K20 - time schedule'!DY26","v":0},{"$f":"'K20 - time schedule'!DZ26","v":0},{"$f":"'K20 - time schedule'!EA26","v":0},{"$f":"'K20 - time schedule'!EB26","v":0},{"$f":"'K20 - time schedule'!EC26","v":0},{"$f":"'K20 - time schedule'!ED26","v":0},{"$f":"'K20 - time schedule'!EE26","v":0},{"$f":"'K20 - time schedule'!EF26","v":0},{"$f":"'K20 - time schedule'!EG26","v":0},{"$f":"'K20 - time schedule'!EH26","v":0},{"$f":"'K20 - time schedule'!EI26","v":0},{"$f":"'K20 - time schedule'!EJ26","v":0},{"$f":"'K20 - time schedule'!EK26","v":0},{"$f":"'K20 - time schedule'!EL26","v":0},{"$f":"'K20 - time schedule'!EM26","v":0},{"$f":"'K20 - time schedule'!EN26","v":0},{"$f":"'K20 - time schedule'!EO26","v":0},{"$f":"'K20 - time schedule'!EP26","v":0},{"$f":"'K20 - time schedule'!EQ26","v":0},{"$f":"'K20 - time schedule'!ER26","v":0},{"$f":"'K20 - time schedule'!ES26","v":0},{"$f":"'K20 - time schedule'!ET26","v":0},{"$f":"'K20 - time schedule'!EU26","v":0},{"$f":"'K20 - time schedule'!EV26","v":0},{"$f":"'K20 - time schedule'!EW26","v":0},{"$f":"'K20 - time schedule'!EX26","v":0},{"$f":"'K20 - time schedule'!EY26","v":0},{"$f":"'K20 - time schedule'!EZ26","v":0},{"$f":"'K20 - time schedule'!FA26","v":0},{"$f":"'K20 - time schedule'!FB26","v":0},{"$f":"'K20 - time schedule'!FC26","v":0},{"$f":"'K20 - time schedule'!FD26","v":0},{"$f":"'K20 - time schedule'!FE26","v":0},{"$f":"'K20 - time schedule'!FF26","v":0},{"$f":"'K20 - time schedule'!FG26","v":0},{"$f":"'K20 - time schedule'!FH26","v":0},{"$f":"'K20 - time schedule'!FI26","v":0},{"$f":"'K20 - time schedule'!FJ26","v":0},{"$f":"'K20 - time schedule'!FK26","v":0},{"$f":"'K20 - time schedule'!FL26","v":0},{"$f":"'K20 - time schedule'!FM26","v":0},{"$f":"'K20 - time schedule'!FN26","v":0},{"$f":"'K20 - time schedule'!FO26","v":0},{"$f":"'K20 - time schedule'!FP26","v":0},{"$f":"'K20 - time schedule'!FQ26","v":0},{"$f":"'K20 - time schedule'!FR26","v":0},{"$f":"'K20 - time schedule'!FS26","v":0},{"$f":"'K20 - time schedule'!FT26","v":0},{"$f":"'K20 - time schedule'!FU26","v":0},{"$f":"'K20 - time schedule'!FV26","v":0},{"$f":"'K20 - time schedule'!FW26","v":0},{"$f":"'K20 - time schedule'!FX26","v":0},{"$f":"'K20 - time schedule'!FY26","v":0},{"$f":"'K20 - time schedule'!FZ26","v":0},{"$f":"'K20 - time schedule'!GA26","v":0},{"$f":"'K20 - time schedule'!GB26","v":0},{"$f":"'K20 - time schedule'!GC26","v":0},{"$f":"'K20 - time schedule'!GD26","v":0},{"$f":"'K20 - time schedule'!GE26","v":0},{"$f":"'K20 - time schedule'!GF26","v":0},{"$f":"'K20 - time schedule'!GG26","v":0},{"$f":"'K20 - time schedule'!GH18","v":0},{"$f":"'K20 - time schedule'!GI18","v":0},{"$f":"'K20 - time schedule'!GJ18","v":0},{"$f":"'K20 - time schedule'!GK18","v":0},{"$f":"'K20 - time schedule'!GL18","v":0},{"$f":"'K20 - time schedule'!GM18","v":0},{"$f":"'K20 - time schedule'!GN18","v":0},{"$f":"'K20 - time schedule'!GO18","v":0},{"$f":"'K20 - time schedule'!GP18","v":0},{"$f":"'K20 - time schedule'!GQ18","v":0},{"$f":"'K20 - time schedule'!GR18","v":0},{"$f":"'K20 - time schedule'!GS18","v":0},{"$f":"'K20 - time schedule'!GT18","v":0},{"$f":"'K20 - time schedule'!GU18","v":0},{"$f":"'K20 - time schedule'!GV18","v":0},{"$f":"'K20 - time schedule'!GW18","v":0},{"$f":"'K20 - time schedule'!GX18","v":0},{"$f":"'K20 - time schedule'!GY18","v":0},{"$f":"'K20 - time schedule'!GZ18","v":0},{"$f":"'K20 - time schedule'!HA18","v":0},{"$f":"'K20 - time schedule'!HB18","v":0},{"$f":"'K20 - time schedule'!HC18","v":0},{"$f":"'K20 - time schedule'!HD18","v":0},{"$f":"'K20 - time schedule'!HE18","v":0},{"$f":"'K20 - time schedule'!HF18","v":0},{"$f":"'K20 - time schedule'!HG18","v":0},{"$f":"'K20 - time schedule'!HH18","v":0},{"$f":"'K20 - time schedule'!HI18","v":0},{"$f":"'K20 - time schedule'!HJ18","v":0},{"$f":"'K20 - time schedule'!HK18","v":0},{"$f":"'K20 - time schedule'!HL18","v":0},{"$f":"'K20 - time schedule'!HM18","v":0},{"$f":"'K20 - time schedule'!HN18","v":0},{"$f":"'K20 - time schedule'!HO18","v":0},{"$f":"'K20 - time schedule'!HP18","v":0},{"$f":"'K20 - time schedule'!HQ18","v":0},{"$f":"'K20 - time schedule'!HR18","v":0},{"$f":"'K20 - time schedule'!HS18","v":0},{"$f":"'K20 - time schedule'!HT18","v":0},{"$f":"'K20 - time schedule'!HU18","v":0},{"$f":"'K20 - time schedule'!HV18","v":0},{"$f":"'K20 - time schedule'!HW18","v":0},{"$f":"'K20 - time schedule'!HX18","v":0},{"$f":"'K20 - time schedule'!HY18","v":0},{"$f":"'K20 - time schedule'!HZ18","v":0},{"$f":"'K20 - time schedule'!IA18","v":0},{"$f":"'K20 - time schedule'!IB18","v":0},{"$f":"'K20 - time schedule'!IC18","v":0},{"$f":"'K20 - time schedule'!ID18","v":0},{"$f":"'K20 - time schedule'!IE18","v":0},{"$f":"'K20 - time schedule'!IF18","v":0},{"$f":"'K20 - time schedule'!IG18","v":0},{"$f":"'K20 - time schedule'!IH18","v":0},{"$f":"'K20 - time schedule'!II18","v":0},{"$f":"'K20 - time schedule'!IJ18","v":0},{"$f":"'K20 - time schedule'!IK18","v":0},{"$f":"'K20 - time schedule'!IL18","v":0},{"$f":"'K20 - time schedule'!IM18","v":0},{"$f":"'K20 - time schedule'!IN18","v":0},{"$f":"'K20 - time schedule'!IO18","v":0},{"$f":"'K20 - time schedule'!IP18","v":0},{"$f":"'K20 - time schedule'!IQ18","v":0},{"$f":"'K20 - time schedule'!IR18","v":0},{"$f":"'K20 - time schedule'!IS18","v":0},{"$f":"'K20 - time schedule'!IT18","v":0},{"$f":"'K20 - time schedule'!IU18","v":0},{"$f":"'K20 - time schedule'!IV18","v":0},{"$f":"'K20 - time schedule'!IW18","v":0},{"$f":"'K20 - time schedule'!IX18","v":0},{"$f":"'K20 - time schedule'!IY18","v":0},{"$f":"'K20 - time schedule'!IZ18","v":0},{"$f":"'K20 - time schedule'!JA18","v":0},{"$f":"'K20 - time schedule'!JB18","v":0},{"$f":"'K20 - time schedule'!JC18","v":0},{"$f":"'K20 - time schedule'!JD18","v":0},{"$f":"'K20 - time schedule'!JE18","v":0},{"$f":"'K20 - time schedule'!JF18","v":0},{"$f":"'K20 - time schedule'!JG18","v":0},{"$f":"'K20 - time schedule'!JH18","v":0},{"$f":"'K20 - time schedule'!JI18","v":0},{"$f":"'K20 - time schedule'!JJ18","v":0},{"$f":"'K20 - time schedule'!JK18","v":0},{"$f":"'K20 - time schedule'!JL18","v":0},{"$f":"'K20 - time schedule'!JM18","v":0},{"$f":"'K20 - time schedule'!JN18","v":0},{"$f":"'K20 - time schedule'!JO18","v":0},{"$f":"'K20 - time schedule'!JP18","v":0},{"$f":"'K20 - time schedule'!JQ18","v":0},{"$f":"'K20 - time schedule'!JR18","v":0},{"$f":"'K20 - time schedule'!JS18","v":0},{"$f":"'K20 - time schedule'!JT18","v":0},{"$f":"'K20 - time schedule'!JU18","v":0},{"$f":"'K20 - time schedule'!JV18","v":0},{"$f":"'K20 - time schedule'!JW18","v":0},{"$f":"'K20 - time schedule'!JX18","v":0},{"$f":"'K20 - time schedule'!JY18","v":0},{"$f":"'K20 - time schedule'!JZ18","v":0},{"$f":"'K20 - time schedule'!KA18","v":0},{"$f":"'K20 - time schedule'!KB18","v":0},{"$f":"'K20 - time schedule'!KC18","v":0},{"$f":"'K20 - time schedule'!KD18","v":0},{"$f":"'K20 - time schedule'!KE18","v":0},{"$f":"'K20 - time schedule'!KF18","v":0},{"$f":"'K20 - time schedule'!KG18","v":0},{"$f":"'K20 - time schedule'!KH18","v":0},{"$f":"'K20 - time schedule'!KI18","v":0},{"$f":"'K20 - time schedule'!KJ18","v":0},{"$f":"'K20 - time schedule'!KK18","v":0},{"$f":"'K20 - time schedule'!KL18","v":0},{"$f":"'K20 - time schedule'!KM18","v":0},{"$f":"'K20 - time schedule'!KN18","v":0},{"$f":"'K20 - time schedule'!KO18","v":0},{"$f":"'K20 - time schedule'!KP18","v":0},{"$f":"'K20 - time schedule'!KQ18","v":0},{"$f":"'K20 - time schedule'!KR18","v":0},{"$f":"'K20 - time schedule'!KS18","v":0},{"$f":"'K20 - time schedule'!KT18","v":0}]
["Boiler room K20 - DSI technology","K20",{"$f":"'K20 - time schedule'!G28","v":0},{"$f":"'K20 - time schedule'!H28","v":0},{"$f":"'K20 - time schedule'!I28","v":0},{"$f":"'K20 - time schedule'!J28","v":0},{"$f":"'K20 - time schedule'!K28","v":0},{"$f":"'K20 - time schedule'!L28","v":0},{"$f":"'K20 - time schedule'!M28","v":0},{"$f":"'K20 - time schedule'!N28","v":0},{"$f":"'K20 - time schedule'!O28","v":0},{"$f":"'K20 - time schedule'!P28","v":0},{"$f":"'K20 - time schedule'!Q28","v":0},{"$f":"'K20 - time schedule'!R28","v":0},{"$f":"'K20 - time schedule'!S28","v":0},{"$f":"'K20 - time schedule'!T28","v":0},{"$f":"'K20 - time schedule'!U28","v":0},{"$f":"'K20 - time schedule'!V28","v":0},{"$f":"'K20 - time schedule'!W28","v":0},{"$f":"'K20 - time schedule'!X28","v":0},{"$f":"'K20 - time schedule'!Y28","v":0},{"$f":"'K20 - time schedule'!Z28","v":0},{"$f":"'K20 - time schedule'!AA28","v":0},{"$f":"'K20 - time schedule'!AB28","v":0},{"$f":"'K20 - time schedule'!AC28","v":0},{"$f":"'K20 - time schedule'!AD28","v":0},{"$f":"'K20 - time schedule'!AE28","v":0},{"$f":"'K20 - time schedule'!AF28","v":0},{"$f":"'K20 - time schedule'!AG28","v":0},{"$f":"'K20 - time schedule'!AH28","v":0},{"$f":"'K20 - time schedule'!AI28","v":0},{"$f":"'K20 - time schedule'!AJ28","v":0},{"$f":"'K20 - time schedule'!AK28","v":0},{"$f":"'K20 - time schedule'!AL28","v":0},{"$f":"'K20 - time schedule'!AM28","v":0},{"$f":"'K20 - time schedule'!AN28","v":0},{"$f":"'K20 - time schedule'!AO28","v":0},{"$f":"'K20 - time schedule'!AP28","v":0},{"$f":"'K20 - time schedule'!AQ28","v":0},{"$f":"'K20 - time schedule'!AR28","v":0},{"$f":"'K20 - time schedule'!AS28","v":0},{"$f":"'K20 - time schedule'!AT28","v":0},{"$f":"'K20 - time schedule'!AU28","v":0},{"$f":"'K20 - time schedule'!AV28","v":0},{"$f":"'K20 - time schedule'!AW28","v":0},{"$f":"'K20 - time schedule'!AX28","v":0},{"$f":"'K20 - time schedule'!AY28","v":0},{"$f":"'K20 - time schedule'!AZ28","v":0},{"$f":"'K20 - time schedule'!BA28","v":0},{"$f":"'K20 - time schedule'!BB28","v":0},{"$f":"'K20 - time schedule'!BC28","v":0},{"$f":"'K20 - time schedule'!BD28","v":0},{"$f":"'K20 - time schedule'!BE28","v":0},{"$f":"'K20 - time schedule'!BF28","v":0},{"$f":"'K20 - time schedule'!BG28","v":0},{"$f":"'K20 - time schedule'!BH28","v":0},{"$f":"'K20 - time schedule'!BI28","v":0},{"$f":"'K20 - time schedule'!BJ28","v":0},{"$f":"'K20 - time schedule'!BK28","v":0},{"$f":"'K20 - time schedule'!BL28","v":0},{"$f":"'K20 - time schedule'!BM28","v":0},{"$f":"'K20 - time schedule'!BN28","v":0},{"$f":"'K20 - time schedule'!BO28","v":0},{"$f":"'K20 - time schedule'!BP28","v":0},{"$f":"'K20 - time schedule'!BQ28","v":0},{"$f":"'K20 - time schedule'!BR28","v":0},{"$f":"'K20 - time schedule'!BS28","v":0},{"$f":"'K20 - time schedule'!BT28","v":0},{"$f":"'K20 - time schedule'!BU28","v":0},{"$f":"'K20 - time schedule'!BV28","v":0},{"$f":"'K20 - time schedule'!BW28","v":0},{"$f":"'K20 - time schedule'!BX28","v":0},{"$f":"'K20 - time schedule'!BY28","v":0},{"$f":"'K20 - time schedule'!BZ28","v":0},{"$f":"'K20 - time schedule'!CA28","v":0},{"$f":"'K20 - time schedule'!CB28","v":0},{"$f":"'K20 - time schedule'!CC28","v":0},{"$f":"'K20 - time schedule'!CD28","v":0},{"$f":"'K20 - time schedule'!CE28","v":0},{"$f":"'K20 - time schedule'!CF28","v":0},{"$f":"'K20 - time schedule'!CG28","v":0},{"$f":"'K20 - time schedule'!CH28","v":0},{"$f":"'K20 - time schedule'!CI28","v":0},{"$f":"'K20 - time schedule'!CJ28","v":0},{"$f":"'K20 - time schedule'!CK28","v":0},{"$f":"'K20 - time schedule'!CL28","v":0},{"$f":"'K20 - time schedule'!CM28","v":0},{"$f":"'K20 - time schedule'!CN28","v":0},{"$f":"'K20 - time schedule'!CO28","v":0},{"$f":"'K20 - time schedule'!CP28","v":0},{"$f":"'K20 - time schedule'!CQ28","v":0},{"$f":"'K20 - time schedule'!CR28","v":0},{"$f":"'K20 - time schedule'!CS28","v":0},{"$f":"'K20 - time schedule'!CT28","v":0},{"$f":"'K20 - time schedule'!CU28","v":0},{"$f":"'K20 - time schedule'!CV28","v":0},{"$f":"'K20 - time schedule'!CW28","v":0},{"$f":"'K20 - time schedule'!CX28","v":0},{"$f":"'K20 - time schedule'!CY28","v":0},{"$f":"'K20 - time schedule'!CZ28","v":0},{"$f":"'K20 - time schedule'!DA28","v":0},{"$f":"'K20 - time schedule'!DB28","v":0},{"$f":"'K20 - time schedule'!DC28","v":0},{"$f":"'K20 - time schedule'!DD28","v":0},{"$f":"'K20 - time schedule'!DE28","v":0},{"$f":"'K20 - time schedule'!DF28","v":0},{"$f":"'K20 - time schedule'!DG28","v":0},{"$f":"'K20 - time schedule'!DH28","v":0},{"$f":"'K20 - time schedule'!DI28","v":0},{"$f":"'K20 - time schedule'!DJ28","v":0},{"$f":"'K20 - time schedule'!DK28","v":0},{"$f":"'K20 - time schedule'!DL28","v":0},{"$f":"'K20 - time schedule'!DM28","v":0},{"$f":"'K20 - time schedule'!DN28","v":0},{"$f":"'K20 - time schedule'!DO28","v":0},{"$f":"'K20 - time schedule'!DP28","v":0},{"$f":"'K20 - time schedule'!DQ28","v":0},{"$f":"'K20 - time schedule'!DR28","v":0},{"$f":"'K20 - time schedule'!DS28","v":0},{"$f":"'K20 - time schedule'!DT28","v":0},{"$f":"'K20 - time schedule'!DU28","v":0},{"$f":"'K20 - time schedule'!DV28","v":0},{"$f":"'K20 - time schedule'!DW28","v":0},{"$f":"'K20 - time schedule'!DX28","v":0},{"$f":"'K20 - time schedule'!DY28","v":0},{"$f":"'K20 - time schedule'!DZ28","v":0},{"$f":"'K20 - time schedule'!EA28","v":0},{"$f":"'K20 - time schedule'!EB28","v":0},{"$f":"'K20 - time schedule'!EC28","v":0},{"$f":"'K20 - time schedule'!ED28","v":0},{"$f":"'K20 - time schedule'!EE28","v":0},{"$f":"'K20 - time schedule'!EF28","v":0},{"$f":"'K20 - time schedule'!EG28","v":0},{"$f":"'K20 - time schedule'!EH28","v":0},{"$f":"'K20 - time schedule'!EI28","v":0},{"$f":"'K20 - time schedule'!EJ28","v":0},{"$f":"'K20 - time schedule'!EK28","v":0},{"$f":"'K20 - time schedule'!EL28","v":0},{"$f":"'K20 - time schedule'!EM28","v":0},{"$f":"'K20 - time schedule'!EN28","v":0},{"$f":"'K20 - time schedule'!EO28","v":0},{"$f":"'K20 - time schedule'!EP28","v":0},{"$f":"'K20 - time schedule'!EQ28","v":0},{"$f":"'K20 - time schedule'!ER28","v":0},{"$f":"'K20 - time schedule'!ES28","v":0},{"$f":"'K20 - time schedule'!ET28","v":0},{"$f":"'K20 - time schedule'!EU28","v":0},{"$f":"'K20 - time schedule'!EV28","v":0},{"$f":"'K20 - time schedule'!EW28","v":0},{"$f":"'K20 - time schedule'!EX28","v":0},{"$f":"'K20 - time schedule'!EY28","v":0},{"$f":"'K20 - time schedule'!EZ28","v":0},{"$f":"'K20 - time schedule'!FA28","v":0},{"$f":"'K20 - time schedule'!FB28","v":0},{"$f":"'K20 - time schedule'!FC28","v":0},{"$f":"'K20 - time schedule'!FD28","v":0},{"$f":"'K20 - time schedule'!FE28","v":0},{"$f":"'K20 - time schedule'!FF28","v":0},{"$f":"'K20 - time schedule'!FG28","v":0},{"$f":"'K20 - time schedule'!FH28","v":0},{"$f":"'K20 - time schedule'!FI28","v":0},{"$f":"'K20 - time schedule'!FJ28","v":0},{"$f":"'K20 - time schedule'!FK28","v":0},{"$f":"'K20 - time schedule'!FL28","v":0},{"$f":"'K20 - time schedule'!FM28","v":0},{"$f":"'K20 - time schedule'!FN28","v":0},{"$f":"'K20 - time schedule'!FO28","v":0},{"$f":"'K20 - time schedule'!FP28","v":0},{"$f":"'K20 - time schedule'!FQ28","v":0},{"$f":"'K20 - time schedule'!FR28","v":0},{"$f":"'K20 - time schedule'!FS28","v":0},{"$f":"'K20 - time schedule'!FT28","v":0},{"$f":"'K20 - time schedule'!FU28","v":0},{"$f":"'K20 - time schedule'!FV28","v":0},{"$f":"'K20 - time schedule'!FW28","v":0},{"$f":"'K20 - time schedule'!FX28","v":0},{"$f":"'K20 - time schedule'!FY28","v":0},{"$f":"'K20 - time schedule'!FZ28","v":0},{"$f":"'K20 - time schedule'!GA28","v":0},{"$f":"'K20 - time schedule'!GB28","v":0},{"$f":"'K20 - time schedule'!GC28","v":0},{"$f":"'K20 - time schedule'!GD28","v":0},{"$f":"'K20 - time schedule'!GE28","v":0},{"$f":"'K20 - time schedule'!GF28","v":0},{"$f":"'K20 - time schedule'!GG28","v":0},{"$f":"'K20 - time schedule'!GH19","v":0},{"$f":"'K20 - time schedule'!GI19","v":0},{"$f":"'K20 - time schedule'!GJ19","v":"Kotelna K20 - tkaninový filtr"},{"$f":"'K20 - time schedule'!GK19","v":0},{"$f":"'K20 - time schedule'!GL19","v":0},{"$f":"'K20 - time schedule'!GM19","v":0},{"$f":"'K20 - time schedule'!GN19","v":0},{"$f":"'K20 - time schedule'!GO19","v":0},{"$f":"'K20 - time schedule'!GP19","v":0},{"$f":"'K20 - time schedule'!GQ19","v":0},{"$f":"'K20 - time schedule'!GR19","v":0},{"$f":"'K20 - time schedule'!GS19","v":0},{"$f":"'K20 - time schedule'!GT19","v":0},{"$f":"'K20 - time schedule'!GU19","v":0},{"$f":"'K20 - time schedule'!GV19","v":0},{"$f":"'K20 - time schedule'!GW19","v":0},{"$f":"'K20 - time schedule'!GX19","v":0},{"$f":"'K20 - time schedule'!GY19","v":0},{"$f":"'K20 - time schedule'!GZ19","v":0},{"$f":"'K20 - time schedule'!HA19","v":0},{"$f":"'K20 - time schedule'!HB19","v":0},{"$f":"'K20 - time schedule'!HC19","v":0},{"$f":"'K20 - time schedule'!HD19","v":0},{"$f":"'K20 - time schedule'!HE19","v":0},{"$f":"'K20 - time schedule'!HF19","v":0},{"$f":"'K20 - time schedule'!HG19","v":0},{"$f":"'K20 - time schedule'!HH19","v":0},{"$f":"'K20 - time schedule'!HI19","v":0},{"$f":"'K20 - time schedule'!HJ19","v":0},{"$f":"'K20 - time schedule'!HK19","v":0},{"$f":"'K20 - time schedule'!HL19","v":0},{"$f":"'K20 - time schedule'!HM19","v":0},{"$f":"'K20 - time schedule'!HN19","v":0},{"$f":"'K20 - time schedule'!HO19","v":0},{"$f":"'K20 - time schedule'!HP19","v":0},{"$f":"'K20 - time schedule'!HQ19","v":0},{"$f":"'K20 - time schedule'!HR19","v":0},{"$f":"'K20 - time schedule'!HS19","v":0},{"$f":"'K20 - time schedule'!HT19","v":0},{"$f":"'K20 - time schedule'!HU19","v":0},{"$f":"'K20 - time schedule'!HV19","v":0},{"$f":"'K20 - time schedule'!HW19","v":0},{"$f":"'K20 - time schedule'!HX19","v":0},{"$f":"'K20 - time schedule'!HY19","v":0},{"$f":"'K20 - time schedule'!HZ19","v":0},{"$f":"'K20 - time schedule'!IA19","v":0},{"$f":"'K20 - time schedule'!IB19","v":0},{"$f":"'K20 - time schedule'!IC19","v":0},{"$f":"'K20 - time schedule'!ID19","v":0},{"$f":"'K20 - time schedule'!IE19","v":0},{"$f":"'K20 - time schedule'!IF19","v":0},{"$f":"'K20 - time schedule'!IG19","v":0},{"$f":"'K20 - time schedule'!IH19","v":0},{"$f":"'K20 - time schedule'!II19","v":0},{"$f":"'K20 - time schedule'!IJ19","v":0},{"$f":"'K20 - time schedule'!IK19","v":0},{"$f":"'K20 - time schedule'!IL19","v":0},{"$f":"'K20 - time schedule'!IM19","v":0},{"$f":"'K20 - time schedule'!IN19","v":0},{"$f":"'K20 - time schedule'!IO19","v":0},{"$f":"'K20 - time schedule'!IP19","v":0},{"$f":"'K20 - time schedule'!IQ19","v":0},{"$f":"'K20 - time schedule'!IR19","v":0},{"$f":"'K20 - time schedule'!IS19","v":0},{"$f":"'K20 - time schedule'!IT19","v":0},{"$f":"'K20 - time schedule'!IU19","v":0},{"$f":"'K20 - time schedule'!IV19","v":0},{"$f":"'K20 - time schedule'!IW19","v":0},{"$f":"'K20 - time schedule'!IX19","v":0},{"$f":"'K20 - time schedule'!IY19","v":0},{"$f":"'K20 - time schedule'!IZ19","v":0},{"$f":"'K20 - time schedule'!JA19","v":0},{"$f":"'K20 - time schedule'!JB19","v":0},{"$f":"'K20 - time schedule'!JC19","v":0},{"$f":"'K20 - time schedule'!JD19","v":0},{"$f":"'K20 - time schedule'!JE19","v":0},{"$f":"'K20 - time schedule'!JF19","v":0},{"$f":"'K20 - time schedule'!JG19","v":0},{"$f":"'K20 - time schedule'!JH19","v":0},{"$f":"'K20 - time schedule'!JI19","v":0},{"$f":"'K20 - time schedule'!JJ19","v":0},{"$f":"'K20 - time schedule'!JK19","v":0},{"$f":"'K20 - time schedule'!JL19","v":0},{"$f":"'K20 - time schedule'!JM19","v":0},{"$f":"'K20 - time schedule'!JN19","v":0},{"$f":"'K20 - time schedule'!JO19","v":0},{"$f":"'K20 - time schedule'!JP19","v":0},{"$f":"'K20 - time schedule'!JQ19","v":0},{"$f":"'K20 - time schedule'!JR19","v":0},{"$f":"'K20 - time schedule'!JS19","v":0},{"$f":"'K20 - time schedule'!JT19","v":0},{"$f":"'K20 - time schedule'!JU19","v":0},{"$f":"'K20 - time schedule'!JV19","v":0},{"$f":"'K20 - time schedule'!JW19","v":0},{"$f":"'K20 - time schedule'!JX19","v":0},{"$f":"'K20 - time schedule'!JY19","v":0},{"$f":"'K20 - time schedule'!JZ19","v":0},{"$f":"'K20 - time schedule'!KA19","v":0},{"$f":"'K20 - time schedule'!KB19","v":0},{"$f":"'K20 - time schedule'!KC19","v":0},{"$f":"'K20 - time schedule'!KD19","v":0},{"$f":"'K20 - time schedule'!KE19","v":0},{"$f":"'K20 - time schedule'!KF19","v":0},{"$f":"'K20 - time schedule'!KG19","v":0},{"$f":"'K20 - time schedule'!KH19","v":0},{"$f":"'K20 - time schedule'!KI19","v":0},{"$f":"'K20 - time schedule'!KJ19","v":0},{"$f":"'K20 - time schedule'!KK19","v":0},{"$f":"'K20 - time schedule'!KL19","v":0},{"$f":"'K20 - time schedule'!KM19","v":0},{"$f":"'K20 - time schedule'!KN19","v":0},{"$f":"'K20 - time schedule'!KO19","v":0},{"$f":"'K20 - time schedule'!KP19","v":0},{"$f":"'K20 - time schedule'!KQ19","v":0},{"$f":"'K20 - time schedule'!KR19","v":0},{"$f":"'K20 - time schedule'!KS19","v":0},{"$f":"'K20 - time schedule'!KT19","v":0}]
["Boiler room K20 - cooler and sorter of ash","K20",{"$f":"'K20 - time schedule'!G30","v":0},{"$f":"'K20 - time schedule'!H30","v":0},{"$f":"'K20 - time schedule'!I30","v":0},{"$f":"'K20 - time schedule'!J30","v":0},{"$f":"'K20 - time schedule'!K30","v":0},{"$f":"'K20 - time schedule'!L30","v":0},{"$f":"'K20 - time schedule'!M30","v":0},{"$f":"'K20 - time schedule'!N30","v":0},{"$f":"'K20 - time schedule'!O30","v":0},{"$f":"'K20 - time schedule'!P30","v":0},{"$f":"'K20 - time schedule'!Q30","v":0},{"$f":"'K20 - time schedule'!R30","v":0},{"$f":"'K20 - time schedule'!S30","v":0},{"$f":"'K20 - time schedule'!T30","v":0},{"$f":"'K20 - time schedule'!U30","v":0},{"$f":"'K20 - time schedule'!V30","v":0},{"$f":"'K20 - time schedule'!W30","v":0},{"$f":"'K20 - time schedule'!X30","v":0},{"$f":"'K20 - time schedule'!Y30","v":0},{"$f":"'K20 - time schedule'!Z30","v":0},{"$f":"'K20 - time schedule'!AA30","v":0},{"$f":"'K20 - time schedule'!AB30","v":0},{"$f":"'K20 - time schedule'!AC30","v":0},{"$f":"'K20 - time schedule'!AD30","v":0},{"$f":"'K20 - time schedule'!AE30","v":0},{"$f":"'K20 - time schedule'!AF30","v":0},{"$f":"'K20 - time schedule'!AG30","v":0},{"$f":"'K20 - time schedule'!AH30","v":0},{"$f":"'K20 - time schedule'!AI30","v":0},{"$f":"'K20 - time schedule'!AJ30","v":0},{"$f":"'K20 - time schedule'!AK30","v":0},{"$f":"'K20 - time schedule'!AL30","v":0},{"$f":"'K20 - time schedule'!AM30","v":0},{"$f":"'K20 - time schedule'!AN30","v":0},{"$f":"'K20 - time schedule'!AO30","v":0},{"$f":"'K20 - time schedule'!AP30","v":0},{"$f":"'K20 - time schedule'!AQ30","v":0},{"$f":"'K20 - time schedule'!AR30","v":0},{"$f":"'K20 - time schedule'!AS30","v":0},{"$f":"'K20 - time schedule'!AT30","v":0},{"$f":"'K20 - time schedule'!AU30","v":0},{"$f":"'K20 - time schedule'!AV30","v":0},{"$f":"'K20 - time schedule'!AW30","v":0},{"$f":"'K20 - time schedule'!AX30","v":0},{"$f":"'K20 - time schedule'!AY30","v":0},{"$f":"'K20 - time schedule'!AZ30","v":0},{"$f":"'K20 - time schedule'!BA30","v":0},{"$f":"'K20 - time schedule'!BB30","v":0},{"$f":"'K20 - time schedule'!BC30","v":0},{"$f":"'K20 - time schedule'!BD30","v":0},{"$f":"'K20 - time schedule'!BE30","v":0},{"$f":"'K20 - time schedule'!BF30","v":0},{"$f":"'K20 - time schedule'!BG30","v":0},{"$f":"'K20 - time schedule'!BH30","v":0},{"$f":"'K20 - time schedule'!BI30","v":0},{"$f":"'K20 - time schedule'!BJ30","v":0},{"$f":"'K20 - time schedule'!BK30","v":0},{"$f":"'K20 - time schedule'!BL30","v":0},{"$f":"'K20 - time schedule'!BM30","v":0},{"$f":"'K20 - time schedule'!BN30","v":0},{"$f":"'K20 - time schedule'!BO30","v":0},{"$f":"'K20 - time schedule'!BP30","v":0},{"$f":"'K20 - time schedule'!BQ30","v":0},{"$f":"'K20 - time schedule'!BR30","v":0},{"$f":"'K20 - time schedule'!BS30","v":0},{"$f":"'K20 - time schedule'!BT30","v":0},{"$f":"'K20 - time schedule'!BU30","v":0},{"$f":"'K20 - time schedule'!BV30","v":0},{"$f":"'K20 - time schedule'!BW30","v":0},{"$f":"'K20 - time schedule'!BX30","v":0},{"$f":"'K20 - time schedule'!BY30","v":0},{"$f":"'K20 - time schedule'!BZ30","v":0},{"$f":"'K20 - time schedule'!CA30","v":0},{"$f":"'K20 - time schedule'!CB30","v":0},{"$f":"'K20 - time schedule'!CC30","v":0},{"$f":"'K20 - time schedule'!CD30","v":0},{"$f":"'K20 - time schedule'!CE30","v":0},{"$f":"'K20 - time schedule'!CF30","v":0},{"$f":"'K20 - time schedule'!CG30","v":0},{"$f":"'K20 - time schedule'!CH30","v":0},{"$f":"'K20 - time schedule'!CI30","v":0},{"$f":"'K20 - time schedule'!CJ30","v":0},{"$f":"'K20 - time schedule'!CK30","v":0},{"$f":"'K20 - time schedule'!CL30","v":0},{"$f":"'K20 - time schedule'!CM30","v":0},{"$f":"'K20 - time schedule'!CN30","v":0},{"$f":"'K20 - time schedule'!CO30","v":0},{"$f":"'K20 - time schedule'!CP30","v":0},{"$f":"'K20 - time schedule'!CQ30","v":0},{"$f":"'K20 - time schedule'!CR30","v":0},{"$f":"'K20 - time schedule'!CS30","v":0},{"$f":"'K20 - time schedule'!CT30","v":0},{"$f":"'K20 - time schedule'!CU30","v":0},{"$f":"'K20 - time schedule'!CV30","v":0},{"$f":"'K20 - time schedule'!CW30","v":0},{"$f":"'K20 - time schedule'!CX30","v":0},{"$f":"'K20 - time schedule'!CY30","v":0},{"$f":"'K20 - time schedule'!CZ30","v":0},{"$f":"'K20 - time schedule'!DA30","v":0},{"$f":"'K20 - time schedule'!DB30","v":0},{"$f":"'K20 - time schedule'!DC30","v":0},{"$f":"'K20 - time schedule'!DD30","v":0},{"$f":"'K20 - time schedule'!DE30","v":0},{"$f":"'K20 - time schedule'!DF30","v":0},{"$f":"'K20 - time schedule'!DG30","v":0},{"$f":"'K20 - time schedule'!DH30","v":0},{"$f":"'K20 - time schedule'!DI30","v":0},{"$f":"'K20 - time schedule'!DJ30","v":0},{"$f":"'K20 - time schedule'!DK30","v":0},{"$f":"'K20 - time schedule'!DL30","v":0},{"$f":"'K20 - time schedule'!DM30","v":0},{"$f":"'K20 - time schedule'!DN30","v":0},{"$f":"'K20 - time schedule'!DO30","v":0},{"$f":"'K20 - time schedule'!DP30","v":0},{"$f":"'K20 - time schedule'!DQ30","v":0},{"$f":"'K20 - time schedule'!DR30","v":0},{"$f":"'K20 - time schedule'!DS30","v":0},{"$f":"'K20 - time schedule'!DT30","v":0},{"$f":"'K20 - time schedule'!DU30","v":0},{"$f":"'K20 - time schedule'!DV30","v":0},{"$f":"'K20 - time schedule'!DW30","v":0},{"$f":"'K20 - time schedule'!DX30","v":0},{"$f":"'K20 - time schedule'!DY30","v":0},{"$f":"'K20 - time schedule'!DZ30","v":0},{"$f":"'K20 - time schedule'!EA30","v":0},{"$f":"'K20 - time schedule'!EB30","v":0},{"$f":"'K20 - time schedule'!EC30","v":0},{"$f":"'K20 - time schedule'!ED30","v":0},{"$f":"'K20 - time schedule'!EE30","v":0},{"$f":"'K20 - time schedule'!EF30","v":0},{"$f":"'K20 - time schedule'!EG30","v":0},{"$f":"'K20 - time schedule'!EH30","v":0},{"$f":"'K20 - time schedule'!EI30","v":0},{"$f":"'K20 - time schedule'!EJ30","v":0},{"$f":"'K20 - time schedule'!EK30","v":0},{"$f":"'K20 - time schedule'!EL30","v":0},{"$f":"'K20 - time schedule'!EM30","v":0},{"$f":"'K20 - time schedule'!EN30","v":0},{"$f":"'K20 - time schedule'!EO30","v":0},{"$f":"'K20 - time schedule'!EP30","v":0},{"$f":"'K20 - time schedule'!EQ30","v":0},{"$f":"'K20 - time schedule'!ER30","v":0},{"$f":"'K20 - time schedule'!ES30","v":0},{"$f":"'K20 - time schedule'!ET30","v":0},{"$f":"'K20 - time schedule'!EU30","v":0},{"$f":"'K20 - time schedule'!EV30","v":0},{"$f":"'K20 - time schedule'!EW30","v":0},{"$f":"'K20 - time schedule'!EX30","v":0},{"$f":"'K20 - time schedule'!EY30","v":0},{"$f":"'K20 - time schedule'!EZ30","v":0},{"$f":"'K20 - time schedule'!FA30","v":0},{"$f":"'K20 - time schedule'!FB30","v":0},{"$f":"'K20 - time schedule'!FC30","v":0},{"$f":"'K20 - time schedule'!FD30","v":0},{"$f":"'K20 - time schedule'!FE30","v":0},{"$f":"'K20 - time schedule'!FF30","v":0},{"$f":"'K20 - time schedule'!FG30","v":0},{"$f":"'K20 - time schedule'!FH30","v":0},{"$f":"'K20 - time schedule'!FI30","v":0},{"$f":"'K20 - time schedule'!FJ30","v":0},{"$f":"'K20 - time schedule'!FK30","v":0},{"$f":"'K20 - time schedule'!FL30","v":0},{"$f":"'K20 - time schedule'!FM30","v":0},{"$f":"'K20 - time schedule'!FN30","v":0},{"$f":"'K20 - time schedule'!FO30","v":0},{"$f":"'K20 - time schedule'!FP30","v":0},{"$f":"'K20 - time schedule'!FQ30","v":0},{"$f":"'K20 - time schedule'!FR30","v":0},{"$f":"'K20 - time schedule'!FS30","v":0},{"$f":"'K20 - time schedule'!FT30","v":0},{"$f":"'K20 - time schedule'!FU30","v":0},{"$f":"'K20 - time schedule'!FV30","v":0},{"$f":"'K20 - time schedule'!FW30","v":0},{"$f":"'K20 - time schedule'!FX30","v":0},{"$f":"'K20 - time schedule'!FY30","v":0},{"$f":"'K20 - time schedule'!FZ30","v":0},{"$f":"'K20 - time schedule'!GA30","v":0},{"$f":"'K20 - time schedule'!GB30","v":0},{"$f":"'K20 - time schedule'!GC30","v":0},{"$f":"'K20 - time schedule'!GD30","v":0},{"$f":"'K20 - time schedule'!GE30","v":0},{"$f":"'K20 - time schedule'!GF30","v":0},{"$f":"'K20 - time schedule'!GG30","v":0},{"$f":"'K20 - time schedule'!GH20","v":0},{"$f":"'K20 - time schedule'!GI20","v":0},{"$f":"'K20 - time schedule'!GJ20","v":0},{"$f":"'K20 - time schedule'!GK20","v":0},{"$f":"'K20 - time schedule'!GL20","v":0},{"$f":"'K20 - time schedule'!GM20","v":0},{"$f":"'K20 - time schedule'!GN20","v":0},{"$f":"'K20 - time schedule'!GO20","v":0},{"$f":"'K20 - time schedule'!GP20","v":0},{"$f":"'K20 - time schedule'!GQ20","v":0},{"$f":"'K20 - time schedule'!GR20","v":0},{"$f":"'K20 - time schedule'!GS20","v":0},{"$f":"'K20 - time schedule'!GT20","v":0},{"$f":"'K20 - time schedule'!GU20","v":0},{"$f":"'K20 - time schedule'!GV20","v":0},{"$f":"'K20 - time schedule'!GW20","v":0},{"$f":"'K20 - time schedule'!GX20","v":0},{"$f":"'K20 - time schedule'!GY20","v":0},{"$f":"'K20 - time schedule'!GZ20","v":0},{"$f":"'K20 - time schedule'!HA20","v":0},{"$f":"'K20 - time schedule'!HB20","v":0},{"$f":"'K20 - time schedule'!HC20","v":0},{"$f":"'K20 - time schedule'!HD20","v":0},{"$f":"'K20 - time schedule'!HE20","v":0},{"$f":"'K20 - time schedule'!HF20","v":0},{"$f":"'K20 - time schedule'!HG20","v":0},{"$f":"'K20 - time schedule'!HH20","v":0},{"$f":"'K20 - time schedule'!HI20","v":0},{"$f":"'K20 - time schedule'!HJ20","v":0},{"$f":"'K20 - time schedule'!HK20","v":0},{"$f":"'K20 - time schedule'!HL20","v":0},{"$f":"'K20 - time schedule'!HM20","v":0},{"$f":"'K20 - time schedule'!HN20","v":0},{"$f":"'K20 - time schedule'!HO20","v":0},{"$f":"'K20 - time schedule'!HP20","v":0},{"$f":"'K20 - time schedule'!HQ20","v":0},{"$f":"'K20 - time schedule'!HR20","v":0},{"$f":"'K20 - time schedule'!HS20","v":0},{"$f":"'K20 - time schedule'!HT20","v":0},{"$f":"'K20 - time schedule'!HU20","v":0},{"$f":"'K20 - time schedule'!HV20","v":0},{"$f":"'K20 - time schedule'!HW20","v":0},{"$f":"'K20 - time schedule'!HX20","v":0},{"$f":"'K20 - time schedule'!HY20","v":0},{"$f":"'K20 - time schedule'!HZ20","v":0},{"$f":"'K20 - time schedule'!IA20","v":0},{"$f":"'K20 - time schedule'!IB20","v":0},{"$f":"'K20 - time schedule'!IC20","v":0},{"$f":"'K20 - time schedule'!ID20","v":0},{"$f":"'K20 - time schedule'!IE20","v":0},{"$f":"'K20 - time schedule'!IF20","v":0},{"$f":"'K20 - time schedule'!IG20","v":0},{"$f":"'K20 - time schedule'!IH20","v":0},{"$f":"'K20 - time schedule'!II20","v":0},{"$f":"'K20 - time schedule'!IJ20","v":0},{"$f":"'K20 - time schedule'!IK20","v":0},{"$f":"'K20 - time schedule'!IL20","v":0},{"$f":"'K20 - time schedule'!IM20","v":0},{"$f":"'K20 - time schedule'!IN20","v":0},{"$f":"'K20 - time schedule'!IO20","v":0},{"$f":"'K20 - time schedule'!IP20","v":0},{"$f":"'K20 - time schedule'!IQ20","v":0},{"$f":"'K20 - time schedule'!IR20","v":0},{"$f":"'K20 - time schedule'!IS20","v":0},{"$f":"'K20 - time schedule'!IT20","v":0},{"$f":"'K20 - time schedule'!IU20","v":0},{"$f":"'K20 - time schedule'!IV20","v":0},{"$f":"'K20 - time schedule'!IW20","v":0},{"$f":"'K20 - time schedule'!IX20","v":0},{"$f":"'K20 - time schedule'!IY20","v":0},{"$f":"'K20 - time schedule'!IZ20","v":0},{"$f":"'K20 - time schedule'!JA20","v":0},{"$f":"'K20 - time schedule'!JB20","v":0},{"$f":"'K20 - time schedule'!JC20","v":0},{"$f":"'K20 - time schedule'!JD20","v":0},{"$f":"'K20 - time schedule'!JE20","v":0},{"$f":"'K20 - time schedule'!JF20","v":0},{"$f":"'K20 - time schedule'!JG20","v":0},{"$f":"'K20 - time schedule'!JH20","v":0},{"$f":"'K20 - time schedule'!JI20","v":0},{"$f":"'K20 - time schedule'!JJ20","v":0},{"$f":"'K20 - time schedule'!JK20","v":0},{"$f":"'K20 - time schedule'!JL20","v":0},{"$f":"'K20 - time schedule'!JM20","v":0},{"$f":"'K20 - time schedule'!JN20","v":0},{"$f":"'K20 - time schedule'!JO20","v":0},{"$f":"'K20 - time schedule'!JP20","v":0},{"$f":"'K20 - time schedule'!JQ20","v":0},{"$f":"'K20 - time schedule'!JR20","v":0},{"$f":"'K20 - time schedule'!JS20","v":0},{"$f":"'K20 - time schedule'!JT20","v":0},{"$f":"'K20 - time schedule'!JU20","v":0},{"$f":"'K20 - time schedule'!JV20","v":0},{"$f":"'K20 - time schedule'!JW20","v":0},{"$f":"'K20 - time schedule'!JX20","v":0},{"$f":"'K20 - time schedule'!JY20","v":0},{"$f":"'K20 - time schedule'!JZ20","v":0},{"$f":"'K20 - time schedule'!KA20","v":0},{"$f":"'K20 - time schedule'!KB20","v":0},{"$f":"'K20 - time schedule'!KC20","v":0},{"$f":"'K20 - time schedule'!KD20","v":0},{"$f":"'K20 - time schedule'!KE20","v":0},{"$f":"'K20 - time schedule'!KF20","v":0},{"$f":"'K20 - time schedule'!KG20","v":0},{"$f":"'K20 - time schedule'!KH20","v":0},{"$f":"'K20 - time schedule'!KI20","v":0},{"$f":"'K20 - time schedule'!KJ20","v":0},{"$f":"'K20 - time schedule'!KK20","v":0},{"$f":"'K20 - time schedule'!KL20","v":0},{"$f":"'K20 - time schedule'!KM20","v":0},{"$f":"'K20 - time schedule'!KN20","v":0},{"$f":"'K20 - time schedule'!KO20","v":0},{"$f":"'K20 - time schedule'!KP20","v":0},{"$f":"'K20 - time schedule'!KQ20","v":0},{"$f":"'K20 - time schedule'!KR20","v":0},{"$f":"'K20 - time schedule'!KS20","v":0},{"$f":"'K20 - time schedule'!KT20","v":0}]
["Boiler room K20 - electrical installation","K20",{"$f":"'K20 - time schedule'!G32","v":0},{"$f":"'K20 - time schedule'!H32","v":0},{"$f":"'K20 - time schedule'!I32","v":0},{"$f":"'K20 - time schedule'!J32","v":0},{"$f":"'K20 - time schedule'!K32","v":0},{"$f":"'K20 - time schedule'!L32","v":0},{"$f":"'K20 - time schedule'!M32","v":0},{"$f":"'K20 - time schedule'!N32","v":0},{"$f":"'K20 - time schedule'!O32","v":0},{"$f":"'K20 - time schedule'!P32","v":0},{"$f":"'K20 - time schedule'!Q32","v":0},{"$f":"'K20 - time schedule'!R32","v":0},{"$f":"'K20 - time schedule'!S32","v":0},{"$f":"'K20 - time schedule'!T32","v":0},{"$f":"'K20 - time schedule'!U32","v":0},{"$f":"'K20 - time schedule'!V32","v":0},{"$f":"'K20 - time schedule'!W32","v":0},{"$f":"'K20 - time schedule'!X32","v":0},{"$f":"'K20 - time schedule'!Y32","v":0},{"$f":"'K20 - time schedule'!Z32","v":0},{"$f":"'K20 - time schedule'!AA32","v":0},{"$f":"'K20 - time schedule'!AB32","v":0},{"$f":"'K20 - time schedule'!AC32","v":0},{"$f":"'K20 - time schedule'!AD32","v":0},{"$f":"'K20 - time schedule'!AE32","v":0},{"$f":"'K20 - time schedule'!AF32","v":0},{"$f":"'K20 - time schedule'!AG32","v":0},{"$f":"'K20 - time schedule'!AH32","v":0},{"$f":"'K20 - time schedule'!AI32","v":0},{"$f":"'K20 - time schedule'!AJ32","v":0},{"$f":"'K20 - time schedule'!AK32","v":0},{"$f":"'K20 - time schedule'!AL32","v":0},{"$f":"'K20 - time schedule'!AM32","v":0},{"$f":"'K20 - time schedule'!AN32","v":0},{"$f":"'K20 - time schedule'!AO32","v":0},{"$f":"'K20 - time schedule'!AP32","v":0},{"$f":"'K20 - time schedule'!AQ32","v":0},{"$f":"'K20 - time schedule'!AR32","v":0},{"$f":"'K20 - time schedule'!AS32","v":0},{"$f":"'K20 - time schedule'!AT32","v":0},{"$f":"'K20 - time schedule'!AU32","v":0},{"$f":"'K20 - time schedule'!AV32","v":0},{"$f":"'K20 - time schedule'!AW32","v":0},{"$f":"'K20 - time schedule'!AX32","v":0},{"$f":"'K20 - time schedule'!AY32","v":0},{"$f":"'K20 - time schedule'!AZ32","v":0},{"$f":"'K20 - time schedule'!BA32","v":0},{"$f":"'K20 - time schedule'!BB32","v":0},{"$f":"'K20 - time schedule'!BC32","v":0},{"$f":"'K20 - time schedule'!BD32","v":0},{"$f":"'K20 - time schedule'!BE32","v":0},{"$f":"'K20 - time schedule'!BF32","v":0},{"$f":"'K20 - time schedule'!BG32","v":0},{"$f":"'K20 - time schedule'!BH32","v":0},{"$f":"'K20 - time schedule'!BI32","v":0},{"$f":"'K20 - time schedule'!BJ32","v":0},{"$f":"'K20 - time schedule'!BK32","v":0},{"$f":"'K20 - time schedule'!BL32","v":0},{"$f":"'K20 - time schedule'!BM32","v":0},{"$f":"'K20 - time schedule'!BN32","v":0},{"$f":"'K20 - time schedule'!BO32","v":0},{"$f":"'K20 - time schedule'!BP32","v":0},{"$f":"'K20 - time schedule'!BQ32","v":0},{"$f":"'K20 - time schedule'!BR32","v":0},{"$f":"'K20 - time schedule'!BS32","v":0},{"$f":"'K20 - time schedule'!BT32","v":0},{"$f":"'K20 - time schedule'!BU32","v":0},{"$f":"'K20 - time schedule'!BV32","v":0},{"$f":"'K20 - time schedule'!BW32","v":0},{"$f":"'K20 - time schedule'!BX32","v":0},{"$f":"'K20 - time schedule'!BY32","v":0},{"$f":"'K20 - time schedule'!BZ32","v":0},{"$f":"'K20 - time schedule'!CA32","v":0},{"$f":"'K20 - time schedule'!CB32","v":0},{"$f":"'K20 - time schedule'!CC32","v":0},{"$f":"'K20 - time schedule'!CD32","v":0},{"$f":"'K20 - time schedule'!CE32","v":0},{"$f":"'K20 - time schedule'!CF32","v":0},{"$f":"'K20 - time schedule'!CG32","v":0},{"$f":"'K20 - time schedule'!CH32","v":0},{"$f":"'K20 - time schedule'!CI32","v":0},{"$f":"'K20 - time schedule'!CJ32","v":0},{"$f":"'K20 - time schedule'!CK32","v":0},{"$f":"'K20 - time schedule'!CL32","v":0},{"$f":"'K20 - time schedule'!CM32","v":0},{"$f":"'K20 - time schedule'!CN32","v":0},{"$f":"'K20 - time schedule'!CO32","v":0},{"$f":"'K20 - time schedule'!CP32","v":0},{"$f":"'K20 - time schedule'!CQ32","v":0},{"$f":"'K20 - time schedule'!CR32","v":0},{"$f":"'K20 - time schedule'!CS32","v":0},{"$f":"'K20 - time schedule'!CT32","v":0},{"$f":"'K20 - time schedule'!CU32","v":0},{"$f":"'K20 - time schedule'!CV32","v":0},{"$f":"'K20 - time schedule'!CW32","v":0},{"$f":"'K20 - time schedule'!CX32","v":0},{"$f":"'K20 - time schedule'!CY32","v":0},{"$f":"'K20 - time schedule'!CZ32","v":0},{"$f":"'K20 - time schedule'!DA32","v":0},{"$f":"'K20 - time schedule'!DB32","v":0},{"$f":"'K20 - time schedule'!DC32","v":0},{"$f":"'K20 - time schedule'!DD32","v":0},{"$f":"'K20 - time schedule'!DE32","v":0},{"$f":"'K20 - time schedule'!DF32","v":0},{"$f":"'K20 - time schedule'!DG32","v":0},{"$f":"'K20 - time schedule'!DH32","v":0},{"$f":"'K20 - time schedule'!DI32","v":0},{"$f":"'K20 - time schedule'!DJ32","v":0},{"$f":"'K20 - time schedule'!DK32","v":0},{"$f":"'K20 - time schedule'!DL32","v":0},{"$f":"'K20 - time schedule'!DM32","v":0},{"$f":"'K20 - time schedule'!DN32","v":0},{"$f":"'K20 - time schedule'!DO32","v":0},{"$f":"'K20 - time schedule'!DP32","v":0},{"$f":"'K20 - time schedule'!DQ32","v":0},{"$f":"'K20 - time schedule'!DR32","v":0},{"$f":"'K20 - time schedule'!DS32","v":0},{"$f":"'K20 - time schedule'!DT32","v":0},{"$f":"'K20 - time schedule'!DU32","v":0},{"$f":"'K20 - time schedule'!DV32","v":0},{"$f":"'K20 - time schedule'!DW32","v":0},{"$f":"'K20 - time schedule'!DX32","v":0},{"$f":"'K20 - time schedule'!DY32","v":0},{"$f":"'K20 - time schedule'!DZ32","v":0},{"$f":"'K20 - time schedule'!EA32","v":0},{"$f":"'K20 - time schedule'!EB32","v":0},{"$f":"'K20 - time schedule'!EC32","v":0},{"$f":"'K20 - time schedule'!ED32","v":0},{"$f":"'K20 - time schedule'!EE32","v":0},{"$f":"'K20 - time schedule'!EF32","v":0},{"$f":"'K20 - time schedule'!EG32","v":0},{"$f":"'K20 - time schedule'!EH32","v":0},{"$f":"'K20 - time schedule'!EI32","v":0},{"$f":"'K20 - time schedule'!EJ32","v":0},{"$f":"'K20 - time schedule'!EK32","v":0},{"$f":"'K20 - time schedule'!EL32","v":0},{"$f":"'K20 - time schedule'!EM32","v":0},{"$f":"'K20 - time schedule'!EN32","v":0},{"$f":"'K20 - time schedule'!EO32","v":0},{"$f":"'K20 - time schedule'!EP32","v":0},{"$f":"'K20 - time schedule'!EQ32","v":0},{"$f":"'K20 - time schedule'!ER32","v":0},{"$f":"'K20 - time schedule'!ES32","v":0},{"$f":"'K20 - time schedule'!ET32","v":0},{"$f":"'K20 - time schedule'!EU32","v":0},{"$f":"'K20 - time schedule'!EV32","v":0},{"$f":"'K20 - time schedule'!EW32","v":0},{"$f":"'K20 - time schedule'!EX32","v":0},{"$f":"'K20 - time schedule'!EY32","v":0},{"$f":"'K20 - time schedule'!EZ32","v":0},{"$f":"'K20 - time schedule'!FA32","v":0},{"$f":"'K20 - time schedule'!FB32","v":0},{"$f":"'K20 - time schedule'!FC32","v":0},{"$f":"'K20 - time schedule'!FD32","v":0},{"$f":"'K20 - time schedule'!FE32","v":0},{"$f":"'K20 - time schedule'!FF32","v":0},{"$f":"'K20 - time schedule'!FG32","v":0},{"$f":"'K20 - time schedule'!FH32","v":0},{"$f":"'K20 - time schedule'!FI32","v":0},{"$f":"'K20 - time schedule'!FJ32","v":0},{"$f":"'K20 - time schedule'!FK32","v":0},{"$f":"'K20 - time schedule'!FL32","v":0},{"$f":"'K20 - time schedule'!FM32","v":0},{"$f":"'K20 - time schedule'!FN32","v":0},{"$f":"'K20 - time schedule'!FO32","v":0},{"$f":"'K20 - time schedule'!FP32","v":0},{"$f":"'K20 - time schedule'!FQ32","v":0},{"$f":"'K20 - time schedule'!FR32","v":0},{"$f":"'K20 - time schedule'!FS32","v":0},{"$f":"'K20 - time schedule'!FT32","v":0},{"$f":"'K20 - time schedule'!FU32","v":0},{"$f":"'K20 - time schedule'!FV32","v":0},{"$f":"'K20 - time schedule'!FW32","v":0},{"$f":"'K20 - time schedule'!FX32","v":0},{"$f":"'K20 - time schedule'!FY32","v":0},{"$f":"'K20 - time schedule'!FZ32","v":0},{"$f":"'K20 - time schedule'!GA32","v":0},{"$f":"'K20 - time schedule'!GB32","v":0},{"$f":"'K20 - time schedule'!GC32","v":0},{"$f":"'K20 - time schedule'!GD32","v":0},{"$f":"'K20 - time schedule'!GE32","v":0},{"$f":"'K20 - time schedule'!GF32","v":0},{"$f":"'K20 - time schedule'!GG32","v":0},{"$f":"'K20 - time schedule'!GH21","v":0},{"$f":"'K20 - time schedule'!GI21","v":0},{"$f":"'K20 - time schedule'!GJ21","v":0},{"$f":"'K20 - time schedule'!GK21","v":0},{"$f":"'K20 - time schedule'!GL21","v":0},{"$f":"'K20 - time schedule'!GM21","v":0},{"$f":"'K20 - time schedule'!GN21","v":0},{"$f":"'K20 - time schedule'!GO21","v":0},{"$f":"'K20 - time schedule'!GP21","v":0},{"$f":"'K20 - time schedule'!GQ21","v":0},{"$f":"'K20 - time schedule'!GR21","v":0},{"$f":"'K20 - time schedule'!GS21","v":0},{"$f":"'K20 - time schedule'!GT21","v":0},{"$f":"'K20 - time schedule'!GU21","v":0},{"$f":"'K20 - time schedule'!GV21","v":0},{"$f":"'K20 - time schedule'!GW21","v":0},{"$f":"'K20 - time schedule'!GX21","v":0},{"$f":"'K20 - time schedule'!GY21","v":0},{"$f":"'K20 - time schedule'!GZ21","v":0},{"$f":"'K20 - time schedule'!HA21","v":0},{"$f":"'K20 - time schedule'!HB21","v":0},{"$f":"'K20 - time schedule'!HC21","v":0},{"$f":"'K20 - time schedule'!HD21","v":0},{"$f":"'K20 - time schedule'!HE21","v":0},{"$f":"'K20 - time schedule'!HF21","v":0},{"$f":"'K20 - time schedule'!HG21","v":0},{"$f":"'K20 - time schedule'!HH21","v":0},{"$f":"'K20 - time schedule'!HI21","v":0},{"$f":"'K20 - time schedule'!HJ21","v":0},{"$f":"'K20 - time schedule'!HK21","v":0},{"$f":"'K20 - time schedule'!HL21","v":0},{"$f":"'K20 - time schedule'!HM21","v":0},{"$f":"'K20 - time schedule'!HN21","v":0},{"$f":"'K20 - time schedule'!HO21","v":0},{"$f":"'K20 - time schedule'!HP21","v":0},{"$f":"'K20 - time schedule'!HQ21","v":0},{"$f":"'K20 - time schedule'!HR21","v":0},{"$f":"'K20 - time schedule'!HS21","v":0},{"$f":"'K20 - time schedule'!HT21","v":0},{"$f":"'K20 - time schedule'!HU21","v":0},{"$f":"'K20 - time schedule'!HV21","v":0},{"$f":"'K20 - time schedule'!HW21","v":0},{"$f":"'K20 - time schedule'!HX21","v":0},{"$f":"'K20 - time schedule'!HY21","v":0},{"$f":"'K20 - time schedule'!HZ21","v":0},{"$f":"'K20 - time schedule'!IA21","v":0},{"$f":"'K20 - time schedule'!IB21","v":0},{"$f":"'K20 - time schedule'!IC21","v":0},{"$f":"'K20 - time schedule'!ID21","v":0},{"$f":"'K20 - time schedule'!IE21","v":0},{"$f":"'K20 - time schedule'!IF21","v":0},{"$f":"'K20 - time schedule'!IG21","v":0},{"$f":"'K20 - time schedule'!IH21","v":0},{"$f":"'K20 - time schedule'!II21","v":0},{"$f":"'K20 - time schedule'!IJ21","v":0},{"$f":"'K20 - time schedule'!IK21","v":0},{"$f":"'K20 - time schedule'!IL21","v":0},{"$f":"'K20 - time schedule'!IM21","v":0},{"$f":"'K20 - time schedule'!IN21","v":0},{"$f":"'K20 - time schedule'!IO21","v":0},{"$f":"'K20 - time schedule'!IP21","v":0},{"$f":"'K20 - time schedule'!IQ21","v":0},{"$f":"'K20 - time schedule'!IR21","v":0},{"$f":"'K20 - time schedule'!IS21","v":0},{"$f":"'K20 - time schedule'!IT21","v":0},{"$f":"'K20 - time schedule'!IU21","v":0},{"$f":"'K20 - time schedule'!IV21","v":0},{"$f":"'K20 - time schedule'!IW21","v":0},{"$f":"'K20 - time schedule'!IX21","v":0},{"$f":"'K20 - time schedule'!IY21","v":0},{"$f":"'K20 - time schedule'!IZ21","v":0},{"$f":"'K20 - time schedule'!JA21","v":0},{"$f":"'K20 - time schedule'!JB21","v":0},{"$f":"'K20 - time schedule'!JC21","v":0},{"$f":"'K20 - time schedule'!JD21","v":0},{"$f":"'K20 - time schedule'!JE21","v":0},{"$f":"'K20 - time schedule'!JF21","v":0},{"$f":"'K20 - time schedule'!JG21","v":0},{"$f":"'K20 - time schedule'!JH21","v":0},{"$f":"'K20 - time schedule'!JI21","v":0},{"$f":"'K20 - time schedule'!JJ21","v":0},{"$f":"'K20 - time schedule'!JK21","v":0},{"$f":"'K20 - time schedule'!JL21","v":0},{"$f":"'K20 - time schedule'!JM21","v":0},{"$f":"'K20 - time schedule'!JN21","v":0},{"$f":"'K20 - time schedule'!JO21","v":0},{"$f":"'K20 - time schedule'!JP21","v":0},{"$f":"'K20 - time schedule'!JQ21","v":0},{"$f":"'K20 - time schedule'!JR21","v":0},{"$f":"'K20 - time schedule'!JS21","v":0},{"$f":"'K20 - time schedule'!JT21","v":0},{"$f":"'K20 - time schedule'!JU21","v":0},{"$f":"'K20 - time schedule'!JV21","v":0},{"$f":"'K20 - time schedule'!JW21","v":0},{"$f":"'K20 - time schedule'!JX21","v":0},{"$f":"'K20 - time schedule'!JY21","v":0},{"$f":"'K20 - time schedule'!JZ21","v":0},{"$f":"'K20 - time schedule'!KA21","v":0},{"$f":"'K20 - time schedule'!KB21","v":0},{"$f":"'K20 - time schedule'!KC21","v":0},{"$f":"'K20 - time schedule'!KD21","v":0},{"$f":"'K20 - time schedule'!KE21","v":0},{"$f":"'K20 - time schedule'!KF21","v":0},{"$f":"'K20 - time schedule'!KG21","v":0},{"$f":"'K20 - time schedule'!KH21","v":0},{"$f":"'K20 - time schedule'!KI21","v":0},{"$f":"'K20 - time schedule'!KJ21","v":0},{"$f":"'K20 - time schedule'!KK21","v":0},{"$f":"'K20 - time schedule'!KL21","v":0},{"$f":"'K20 - time schedule'!KM21","v":0},{"$f":"'K20 - time schedule'!KN21","v":0},{"$f":"'K20 - time schedule'!KO21","v":0},{"$f":"'K20 - time schedule'!KP21","v":0},{"$f":"'K20 - time schedule'!KQ21","v":0},{"$f":"'K20 - time schedule'!KR21","v":0},{"$f":"'K20 - time schedule'!KS21","v":0},{"$f":"'K20 - time schedule'!KT21","v":0}]
["Boiler room K20 - automatic control system","K20",{"$f":"'K20 - time schedule'!G34","v":0},{"$f":"'K20 - time schedule'!H34","v":0},{"$f":"'K20 - time schedule'!I34","v":0},{"$f":"'K20 - time schedule'!J34","v":0},{"$f":"'K20 - time schedule'!K34","v":0},{"$f":"'K20 - time schedule'!L34","v":0},{"$f":"'K20 - time schedule'!M34","v":0},{"$f":"'K20 - time schedule'!N34","v":0},{"$f":"'K20 - time schedule'!O34","v":0},{"$f":"'K20 - time schedule'!P34","v":0},{"$f":"'K20 - time schedule'!Q34","v":0},{"$f":"'K20 - time schedule'!R34","v":0},{"$f":"'K20 - time schedule'!S34","v":0},{"$f":"'K20 - time schedule'!T34","v":0},{"$f":"'K20 - time schedule'!U34","v":0},{"$f":"'K20 - time schedule'!V34","v":0},{"$f":"'K20 - time schedule'!W34","v":0},{"$f":"'K20 - time schedule'!X34","v":0},{"$f":"'K20 - time schedule'!Y34","v":0},{"$f":"'K20 - time schedule'!Z34","v":0},{"$f":"'K20 - time schedule'!AA34","v":0},{"$f":"'K20 - time schedule'!AB34","v":0},{"$f":"'K20 - time schedule'!AC34","v":0},{"$f":"'K20 - time schedule'!AD34","v":0},{"$f":"'K20 - time schedule'!AE34","v":0},{"$f":"'K20 - time schedule'!AF34","v":0},{"$f":"'K20 - time schedule'!AG34","v":0},{"$f":"'K20 - time schedule'!AH34","v":0},{"$f":"'K20 - time schedule'!AI34","v":0},{"$f":"'K20 - time schedule'!AJ34","v":0},{"$f":"'K20 - time schedule'!AK34","v":0},{"$f":"'K20 - time schedule'!AL34","v":0},{"$f":"'K20 - time schedule'!AM34","v":0},{"$f":"'K20 - time schedule'!AN34","v":0},{"$f":"'K20 - time schedule'!AO34","v":0},{"$f":"'K20 - time schedule'!AP34","v":0},{"$f":"'K20 - time schedule'!AQ34","v":0},{"$f":"'K20 - time schedule'!AR34","v":0},{"$f":"'K20 - time schedule'!AS34","v":0},{"$f":"'K20 - time schedule'!AT34","v":0},{"$f":"'K20 - time schedule'!AU34","v":0},{"$f":"'K20 - time schedule'!AV34","v":0},{"$f":"'K20 - time schedule'!AW34","v":0},{"$f":"'K20 - time schedule'!AX34","v":0},{"$f":"'K20 - time schedule'!AY34","v":0},{"$f":"'K20 - time schedule'!AZ34","v":0},{"$f":"'K20 - time schedule'!BA34","v":0},{"$f":"'K20 - time schedule'!BB34","v":0},{"$f":"'K20 - time schedule'!BC34","v":0},{"$f":"'K20 - time schedule'!BD34","v":0},{"$f":"'K20 - time schedule'!BE34","v":0},{"$f":"'K20 - time schedule'!BF34","v":0},{"$f":"'K20 - time schedule'!BG34","v":0},{"$f":"'K20 - time schedule'!BH34","v":0},{"$f":"'K20 - time schedule'!BI34","v":0},{"$f":"'K20 - time schedule'!BJ34","v":0},{"$f":"'K20 - time schedule'!BK34","v":0},{"$f":"'K20 - time schedule'!BL34","v":0},{"$f":"'K20 - time schedule'!BM34","v":0},{"$f":"'K20 - time schedule'!BN34","v":0},{"$f":"'K20 - time schedule'!BO34","v":0},{"$f":"'K20 - time schedule'!BP34","v":0},{"$f":"'K20 - time schedule'!BQ34","v":0},{"$f":"'K20 - time schedule'!BR34","v":0},{"$f":"'K20 - time schedule'!BS34","v":0},{"$f":"'K20 - time schedule'!BT34","v":0},{"$f":"'K20 - time schedule'!BU34","v":0},{"$f":"'K20 - time schedule'!BV34","v":0},{"$f":"'K20 - time schedule'!BW34","v":0},{"$f":"'K20 - time schedule'!BX34","v":0},{"$f":"'K20 - time schedule'!BY34","v":0},{"$f":"'K20 - time schedule'!BZ34","v":0},{"$f":"'K20 - time schedule'!CA34","v":0},{"$f":"'K20 - time schedule'!CB34","v":0},{"$f":"'K20 - time schedule'!CC34","v":0},{"$f":"'K20 - time schedule'!CD34","v":0},{"$f":"'K20 - time schedule'!CE34","v":0},{"$f":"'K20 - time schedule'!CF34","v":0},{"$f":"'K20 - time schedule'!CG34","v":0},{"$f":"'K20 - time schedule'!CH34","v":0},{"$f":"'K20 - time schedule'!CI34","v":0},{"$f":"'K20 - time schedule'!CJ34","v":0},{"$f":"'K20 - time schedule'!CK34","v":0},{"$f":"'K20 - time schedule'!CL34","v":0},{"$f":"'K20 - time schedule'!CM34","v":0},{"$f":"'K20 - time schedule'!CN34","v":0},{"$f":"'K20 - time schedule'!CO34","v":0},{"$f":"'K20 - time schedule'!CP34","v":0},{"$f":"'K20 - time schedule'!CQ34","v":0},{"$f":"'K20 - time schedule'!CR34","v":0},{"$f":"'K20 - time schedule'!CS34","v":0},{"$f":"'K20 - time schedule'!CT34","v":0},{"$f":"'K20 - time schedule'!CU34","v":0},{"$f":"'K20 - time schedule'!CV34","v":0},{"$f":"'K20 - time schedule'!CW34","v":0},{"$f":"'K20 - time schedule'!CX34","v":0},{"$f":"'K20 - time schedule'!CY34","v":0},{"$f":"'K20 - time schedule'!CZ34","v":0},{"$f":"'K20 - time schedule'!DA34","v":0},{"$f":"'K20 - time schedule'!DB34","v":0},{"$f":"'K20 - time schedule'!DC34","v":0},{"$f":"'K20 - time schedule'!DD34","v":0},{"$f":"'K20 - time schedule'!DE34","v":0},{"$f":"'K20 - time schedule'!DF34","v":0},{"$f":"'K20 - time schedule'!DG34","v":0},{"$f":"'K20 - time schedule'!DH34","v":0},{"$f":"'K20 - time schedule'!DI34","v":0},{"$f":"'K20 - time schedule'!DJ34","v":0},{"$f":"'K20 - time schedule'!DK34","v":0},{"$f":"'K20 - time schedule'!DL34","v":0},{"$f":"'K20 - time schedule'!DM34","v":0},{"$f":"'K20 - time schedule'!DN34","v":0},{"$f":"'K20 - time schedule'!DO34","v":0},{"$f":"'K20 - time schedule'!DP34","v":0},{"$f":"'K20 - time schedule'!DQ34","v":0},{"$f":"'K20 - time schedule'!DR34","v":0},{"$f":"'K20 - time schedule'!DS34","v":0},{"$f":"'K20 - time schedule'!DT34","v":0},{"$f":"'K20 - time schedule'!DU34","v":0},{"$f":"'K20 - time schedule'!DV34","v":0},{"$f":"'K20 - time schedule'!DW34","v":0},{"$f":"'K20 - time schedule'!DX34","v":0},{"$f":"'K20 - time schedule'!DY34","v":0},{"$f":"'K20 - time schedule'!DZ34","v":0},{"$f":"'K20 - time schedule'!EA34","v":0},{"$f":"'K20 - time schedule'!EB34","v":0},{"$f":"'K20 - time schedule'!EC34","v":0},{"$f":"'K20 - time schedule'!ED34","v":0},{"$f":"'K20 - time schedule'!EE34","v":0},{"$f":"'K20 - time schedule'!EF34","v":0},{"$f":"'K20 - time schedule'!EG34","v":0},{"$f":"'K20 - time schedule'!EH34","v":0},{"$f":"'K20 - time schedule'!EI34","v":0},{"$f":"'K20 - time schedule'!EJ34","v":0},{"$f":"'K20 - time schedule'!EK34","v":0},{"$f":"'K20 - time schedule'!EL34","v":0},{"$f":"'K20 - time schedule'!EM34","v":0},{"$f":"'K20 - time schedule'!EN34","v":0},{"$f":"'K20 - time schedule'!EO34","v":0},{"$f":"'K20 - time schedule'!EP34","v":0},{"$f":"'K20 - time schedule'!EQ34","v":0},{"$f":"'K20 - time schedule'!ER34","v":0},{"$f":"'K20 - time schedule'!ES34","v":0},{"$f":"'K20 - time schedule'!ET34","v":0},{"$f":"'K20 - time schedule'!EU34","v":0},{"$f":"'K20 - time schedule'!EV34","v":0},{"$f":"'K20 - time schedule'!EW34","v":0},{"$f":"'K20 - time schedule'!EX34","v":0},{"$f":"'K20 - time schedule'!EY34","v":0},{"$f":"'K20 - time schedule'!EZ34","v":0},{"$f":"'K20 - time schedule'!FA34","v":0},{"$f":"'K20 - time schedule'!FB34","v":0},{"$f":"'K20 - time schedule'!FC34","v":0},{"$f":"'K20 - time schedule'!FD34","v":0},{"$f":"'K20 - time schedule'!FE34","v":0},{"$f":"'K20 - time schedule'!FF34","v":0},{"$f":"'K20 - time schedule'!FG34","v":0},{"$f":"'K20 - time schedule'!FH34","v":0},{"$f":"'K20 - time schedule'!FI34","v":0},{"$f":"'K20 - time schedule'!FJ34","v":0},{"$f":"'K20 - time schedule'!FK34","v":0},{"$f":"'K20 - time schedule'!FL34","v":0},{"$f":"'K20 - time schedule'!FM34","v":0},{"$f":"'K20 - time schedule'!FN34","v":0},{"$f":"'K20 - time schedule'!FO34","v":0},{"$f":"'K20 - time schedule'!FP34","v":0},{"$f":"'K20 - time schedule'!FQ34","v":0},{"$f":"'K20 - time schedule'!FR34","v":0},{"$f":"'K20 - time schedule'!FS34","v":0},{"$f":"'K20 - time schedule'!FT34","v":0},{"$f":"'K20 - time schedule'!FU34","v":0},{"$f":"'K20 - time schedule'!FV34","v":0},{"$f":"'K20 - time schedule'!FW34","v":0},{"$f":"'K20 - time schedule'!FX34","v":0},{"$f":"'K20 - time schedule'!FY34","v":0},{"$f":"'K20 - time schedule'!FZ34","v":0},{"$f":"'K20 - time schedule'!GA34","v":0},{"$f":"'K20 - time schedule'!GB34","v":0},{"$f":"'K20 - time schedule'!GC34","v":0},{"$f":"'K20 - time schedule'!GD34","v":0},{"$f":"'K20 - time schedule'!GE34","v":0},{"$f":"'K20 - time schedule'!GF34","v":0},{"$f":"'K20 - time schedule'!GG34","v":0},{"$f":"'K20 - time schedule'!GH22","v":0},{"$f":"'K20 - time schedule'!GI22","v":0},{"$f":"'K20 - time schedule'!GJ22","v":0},{"$f":"'K20 - time schedule'!GK22","v":0},{"$f":"'K20 - time schedule'!GL22","v":0},{"$f":"'K20 - time schedule'!GM22","v":0},{"$f":"'K20 - time schedule'!GN22","v":0},{"$f":"'K20 - time schedule'!GO22","v":0},{"$f":"'K20 - time schedule'!GP22","v":0},{"$f":"'K20 - time schedule'!GQ22","v":0},{"$f":"'K20 - time schedule'!GR22","v":0},{"$f":"'K20 - time schedule'!GS22","v":0},{"$f":"'K20 - time schedule'!GT22","v":0},{"$f":"'K20 - time schedule'!GU22","v":0},{"$f":"'K20 - time schedule'!GV22","v":0},{"$f":"'K20 - time schedule'!GW22","v":0},{"$f":"'K20 - time schedule'!GX22","v":0},{"$f":"'K20 - time schedule'!GY22","v":0},{"$f":"'K20 - time schedule'!GZ22","v":0},{"$f":"'K20 - time schedule'!HA22","v":0},{"$f":"'K20 - time schedule'!HB22","v":0},{"$f":"'K20 - time schedule'!HC22","v":0},{"$f":"'K20 - time schedule'!HD22","v":0},{"$f":"'K20 - time schedule'!HE22","v":0},{"$f":"'K20 - time schedule'!HF22","v":0},{"$f":"'K20 - time schedule'!HG22","v":0},{"$f":"'K20 - time schedule'!HH22","v":0},{"$f":"'K20 - time schedule'!HI22","v":0},{"$f":"'K20 - time schedule'!HJ22","v":0},{"$f":"'K20 - time schedule'!HK22","v":0},{"$f":"'K20 - time schedule'!HL22","v":0},{"$f":"'K20 - time schedule'!HM22","v":0},{"$f":"'K20 - time schedule'!HN22","v":0},{"$f":"'K20 - time schedule'!HO22","v":0},{"$f":"'K20 - time schedule'!HP22","v":0},{"$f":"'K20 - time schedule'!HQ22","v":0},{"$f":"'K20 - time schedule'!HR22","v":0},{"$f":"'K20 - time schedule'!HS22","v":0},{"$f":"'K20 - time schedule'!HT22","v":0},{"$f":"'K20 - time schedule'!HU22","v":0},{"$f":"'K20 - time schedule'!HV22","v":0},{"$f":"'K20 - time schedule'!HW22","v":0},{"$f":"'K20 - time schedule'!HX22","v":0},{"$f":"'K20 - time schedule'!HY22","v":0},{"$f":"'K20 - time schedule'!HZ22","v":0},{"$f":"'K20 - time schedule'!IA22","v":0},{"$f":"'K20 - time schedule'!IB22","v":0},{"$f":"'K20 - time schedule'!IC22","v":0},{"$f":"'K20 - time schedule'!ID22","v":0},{"$f":"'K20 - time schedule'!IE22","v":0},{"$f":"'K20 - time schedule'!IF22","v":0},{"$f":"'K20 - time schedule'!IG22","v":0},{"$f":"'K20 - time schedule'!IH22","v":0},{"$f":"'K20 - time schedule'!II22","v":0},{"$f":"'K20 - time schedule'!IJ22","v":0},{"$f":"'K20 - time schedule'!IK22","v":0},{"$f":"'K20 - time schedule'!IL22","v":0},{"$f":"'K20 - time schedule'!IM22","v":0},{"$f":"'K20 - time schedule'!IN22","v":0},{"$f":"'K20 - time schedule'!IO22","v":0},{"$f":"'K20 - time schedule'!IP22","v":0},{"$f":"'K20 - time schedule'!IQ22","v":0},{"$f":"'K20 - time schedule'!IR22","v":0},{"$f":"'K20 - time schedule'!IS22","v":0},{"$f":"'K20 - time schedule'!IT22","v":0},{"$f":"'K20 - time schedule'!IU22","v":0},{"$f":"'K20 - time schedule'!IV22","v":0},{"$f":"'K20 - time schedule'!IW22","v":0},{"$f":"'K20 - time schedule'!IX22","v":0},{"$f":"'K20 - time schedule'!IY22","v":0},{"$f":"'K20 - time schedule'!IZ22","v":0},{"$f":"'K20 - time schedule'!JA22","v":0},{"$f":"'K20 - time schedule'!JB22","v":0},{"$f":"'K20 - time schedule'!JC22","v":0},{"$f":"'K20 - time schedule'!JD22","v":0},{"$f":"'K20 - time schedule'!JE22","v":0},{"$f":"'K20 - time schedule'!JF22","v":0},{"$f":"'K20 - time schedule'!JG22","v":0},{"$f":"'K20 - time schedule'!JH22","v":0},{"$f":"'K20 - time schedule'!JI22","v":0},{"$f":"'K20 - time schedule'!JJ22","v":0},{"$f":"'K20 - time schedule'!JK22","v":0},{"$f":"'K20 - time schedule'!JL22","v":0},{"$f":"'K20 - time schedule'!JM22","v":0},{"$f":"'K20 - time schedule'!JN22","v":0},{"$f":"'K20 - time schedule'!JO22","v":0},{"$f":"'K20 - time schedule'!JP22","v":0},{"$f":"'K20 - time schedule'!JQ22","v":0},{"$f":"'K20 - time schedule'!JR22","v":0},{"$f":"'K20 - time schedule'!JS22","v":0},{"$f":"'K20 - time schedule'!JT22","v":0},{"$f":"'K20 - time schedule'!JU22","v":0},{"$f":"'K20 - time schedule'!JV22","v":0},{"$f":"'K20 - time schedule'!JW22","v":0},{"$f":"'K20 - time schedule'!JX22","v":0},{"$f":"'K20 - time schedule'!JY22","v":0},{"$f":"'K20 - time schedule'!JZ22","v":0},{"$f":"'K20 - time schedule'!KA22","v":0},{"$f":"'K20 - time schedule'!KB22","v":0},{"$f":"'K20 - time schedule'!KC22","v":0},{"$f":"'K20 - time schedule'!KD22","v":0},{"$f":"'K20 - time schedule'!KE22","v":0},{"$f":"'K20 - time schedule'!KF22","v":0},{"$f":"'K20 - time schedule'!KG22","v":0},{"$f":"'K20 - time schedule'!KH22","v":0},{"$f":"'K20 - time schedule'!KI22","v":0},{"$f":"'K20 - time schedule'!KJ22","v":0},{"$f":"'K20 - time schedule'!KK22","v":0},{"$f":"'K20 - time schedule'!KL22","v":0},{"$f":"'K20 - time schedule'!KM22","v":0},{"$f":"'K20 - time schedule'!KN22","v":0},{"$f":"'K20 - time schedule'!KO22","v":0},{"$f":"'K20 - time schedule'!KP22","v":0},{"$f":"'K20 - time schedule'!KQ22","v":0},{"$f":"'K20 - time schedule'!KR22","v":0},{"$f":"'K20 - time schedule'!KS22","v":0},{"$f":"'K20 - time schedule'!KT22","v":0}]
["Boiler room K20 - compressor station","K20",{"$f":"'K20 - time schedule'!G36","v":0},{"$f":"'K20 - time schedule'!H36","v":0},{"$f":"'K20 - time schedule'!I36","v":0},{"$f":"'K20 - time schedule'!J36","v":0},{"$f":"'K20 - time schedule'!K36","v":0},{"$f":"'K20 - time schedule'!L36","v":0},{"$f":"'K20 - time schedule'!M36","v":0},{"$f":"'K20 - time schedule'!N36","v":0},{"$f":"'K20 - time schedule'!O36","v":0},{"$f":"'K20 - time schedule'!P36","v":0},{"$f":"'K20 - time schedule'!Q36","v":0},{"$f":"'K20 - time schedule'!R36","v":0},{"$f":"'K20 - time schedule'!S36","v":0},{"$f":"'K20 - time schedule'!T36","v":0},{"$f":"'K20 - time schedule'!U36","v":0},{"$f":"'K20 - time schedule'!V36","v":0},{"$f":"'K20 - time schedule'!W36","v":0},{"$f":"'K20 - time schedule'!X36","v":0},{"$f":"'K20 - time schedule'!Y36","v":0},{"$f":"'K20 - time schedule'!Z36","v":0},{"$f":"'K20 - time schedule'!AA36","v":0},{"$f":"'K20 - time schedule'!AB36","v":0},{"$f":"'K20 - time schedule'!AC36","v":0},{"$f":"'K20 - time schedule'!AD36","v":0},{"$f":"'K20 - time schedule'!AE36","v":0},{"$f":"'K20 - time schedule'!AF36","v":0},{"$f":"'K20 - time schedule'!AG36","v":0},{"$f":"'K20 - time schedule'!AH36","v":0},{"$f":"'K20 - time schedule'!AI36","v":0},{"$f":"'K20 - time schedule'!AJ36","v":0},{"$f":"'K20 - time schedule'!AK36","v":0},{"$f":"'K20 - time schedule'!AL36","v":0},{"$f":"'K20 - time schedule'!AM36","v":0},{"$f":"'K20 - time schedule'!AN36","v":0},{"$f":"'K20 - time schedule'!AO36","v":0},{"$f":"'K20 - time schedule'!AP36","v":0},{"$f":"'K20 - time schedule'!AQ36","v":0},{"$f":"'K20 - time schedule'!AR36","v":0},{"$f":"'K20 - time schedule'!AS36","v":0},{"$f":"'K20 - time schedule'!AT36","v":0},{"$f":"'K20 - time schedule'!AU36","v":0},{"$f":"'K20 - time schedule'!AV36","v":0},{"$f":"'K20 - time schedule'!AW36","v":0},{"$f":"'K20 - time schedule'!AX36","v":0},{"$f":"'K20 - time schedule'!AY36","v":0},{"$f":"'K20 - time schedule'!AZ36","v":0},{"$f":"'K20 - time schedule'!BA36","v":0},{"$f":"'K20 - time schedule'!BB36","v":0},{"$f":"'K20 - time schedule'!BC36","v":0},{"$f":"'K20 - time schedule'!BD36","v":0},{"$f":"'K20 - time schedule'!BE36","v":0},{"$f":"'K20 - time schedule'!BF36","v":0},{"$f":"'K20 - time schedule'!BG36","v":0},{"$f":"'K20 - time schedule'!BH36","v":0},{"$f":"'K20 - time schedule'!BI36","v":0},{"$f":"'K20 - time schedule'!BJ36","v":0},{"$f":"'K20 - time schedule'!BK36","v":0},{"$f":"'K20 - time schedule'!BL36","v":0},{"$f":"'K20 - time schedule'!BM36","v":0},{"$f":"'K20 - time schedule'!BN36","v":0},{"$f":"'K20 - time schedule'!BO36","v":0},{"$f":"'K20 - time schedule'!BP36","v":0},{"$f":"'K20 - time schedule'!BQ36","v":0},{"$f":"'K20 - time schedule'!BR36","v":0},{"$f":"'K20 - time schedule'!BS36","v":0},{"$f":"'K20 - time schedule'!BT36","v":0},{"$f":"'K20 - time schedule'!BU36","v":0},{"$f":"'K20 - time schedule'!BV36","v":0},{"$f":"'K20 - time schedule'!BW36","v":0},{"$f":"'K20 - time schedule'!BX36","v":0},{"$f":"'K20 - time schedule'!BY36","v":0},{"$f":"'K20 - time schedule'!BZ36","v":0},{"$f":"'K20 - time schedule'!CA36","v":0},{"$f":"'K20 - time schedule'!CB36","v":0},{"$f":"'K20 - time schedule'!CC36","v":0},{"$f":"'K20 - time schedule'!CD36","v":0},{"$f":"'K20 - time schedule'!CE36","v":0},{"$f":"'K20 - time schedule'!CF36","v":0},{"$f":"'K20 - time schedule'!CG36","v":0},{"$f":"'K20 - time schedule'!CH36","v":0},{"$f":"'K20 - time schedule'!CI36","v":0},{"$f":"'K20 - time schedule'!CJ36","v":0},{"$f":"'K20 - time schedule'!CK36","v":0},{"$f":"'K20 - time schedule'!CL36","v":0},{"$f":"'K20 - time schedule'!CM36","v":0},{"$f":"'K20 - time schedule'!CN36","v":0},{"$f":"'K20 - time schedule'!CO36","v":0},{"$f":"'K20 - time schedule'!CP36","v":0},{"$f":"'K20 - time schedule'!CQ36","v":0},{"$f":"'K20 - time schedule'!CR36","v":0},{"$f":"'K20 - time schedule'!CS36","v":0},{"$f":"'K20 - time schedule'!CT36","v":0},{"$f":"'K20 - time schedule'!CU36","v":0},{"$f":"'K20 - time schedule'!CV36","v":0},{"$f":"'K20 - time schedule'!CW36","v":0},{"$f":"'K20 - time schedule'!CX36","v":0},{"$f":"'K20 - time schedule'!CY36","v":0},{"$f":"'K20 - time schedule'!CZ36","v":0},{"$f":"'K20 - time schedule'!DA36","v":0},{"$f":"'K20 - time schedule'!DB36","v":0},{"$f":"'K20 - time schedule'!DC36","v":0},{"$f":"'K20 - time schedule'!DD36","v":0},{"$f":"'K20 - time schedule'!DE36","v":0},{"$f":"'K20 - time schedule'!DF36","v":0},{"$f":"'K20 - time schedule'!DG36","v":0},{"$f":"'K20 - time schedule'!DH36","v":0},{"$f":"'K20 - time schedule'!DI36","v":0},{"$f":"'K20 - time schedule'!DJ36","v":0},{"$f":"'K20 - time schedule'!DK36","v":0},{"$f":"'K20 - time schedule'!DL36","v":0},{"$f":"'K20 - time schedule'!DM36","v":0},{"$f":"'K20 - time schedule'!DN36","v":0},{"$f":"'K20 - time schedule'!DO36","v":0},{"$f":"'K20 - time schedule'!DP36","v":0},{"$f":"'K20 - time schedule'!DQ36","v":0},{"$f":"'K20 - time schedule'!DR36","v":0},{"$f":"'K20 - time schedule'!DS36","v":0},{"$f":"'K20 - time schedule'!DT36","v":0},{"$f":"'K20 - time schedule'!DU36","v":0},{"$f":"'K20 - time schedule'!DV36","v":0},{"$f":"'K20 - time schedule'!DW36","v":0},{"$f":"'K20 - time schedule'!DX36","v":0},{"$f":"'K20 - time schedule'!DY36","v":0},{"$f":"'K20 - time schedule'!DZ36","v":0},{"$f":"'K20 - time schedule'!EA36","v":0},{"$f":"'K20 - time schedule'!EB36","v":0},{"$f":"'K20 - time schedule'!EC36","v":0},{"$f":"'K20 - time schedule'!ED36","v":0},{"$f":"'K20 - time schedule'!EE36","v":0},{"$f":"'K20 - time schedule'!EF36","v":0},{"$f":"'K20 - time schedule'!EG36","v":0},{"$f":"'K20 - time schedule'!EH36","v":0},{"$f":"'K20 - time schedule'!EI36","v":0},{"$f":"'K20 - time schedule'!EJ36","v":0},{"$f":"'K20 - time schedule'!EK36","v":0},{"$f":"'K20 - time schedule'!EL36","v":0},{"$f":"'K20 - time schedule'!EM36","v":0},{"$f":"'K20 - time schedule'!EN36","v":0},{"$f":"'K20 - time schedule'!EO36","v":0},{"$f":"'K20 - time schedule'!EP36","v":0},{"$f":"'K20 - time schedule'!EQ36","v":0},{"$f":"'K20 - time schedule'!ER36","v":0},{"$f":"'K20 - time schedule'!ES36","v":0},{"$f":"'K20 - time schedule'!ET36","v":0},{"$f":"'K20 - time schedule'!EU36","v":0},{"$f":"'K20 - time schedule'!EV36","v":0},{"$f":"'K20 - time schedule'!EW36","v":0},{"$f":"'K20 - time schedule'!EX36","v":0},{"$f":"'K20 - time schedule'!EY36","v":0},{"$f":"'K20 - time schedule'!EZ36","v":0},{"$f":"'K20 - time schedule'!FA36","v":0},{"$f":"'K20 - time schedule'!FB36","v":0},{"$f":"'K20 - time schedule'!FC36","v":0},{"$f":"'K20 - time schedule'!FD36","v":0},{"$f":"'K20 - time schedule'!FE36","v":0},{"$f":"'K20 - time schedule'!FF36","v":0},{"$f":"'K20 - time schedule'!FG36","v":0},{"$f":"'K20 - time schedule'!FH36","v":0},{"$f":"'K20 - time schedule'!FI36","v":0},{"$f":"'K20 - time schedule'!FJ36","v":0},{"$f":"'K20 - time schedule'!FK36","v":0},{"$f":"'K20 - time schedule'!FL36","v":0},{"$f":"'K20 - time schedule'!FM36","v":0},{"$f":"'K20 - time schedule'!FN36","v":0},{"$f":"'K20 - time schedule'!FO36","v":0},{"$f":"'K20 - time schedule'!FP36","v":0},{"$f":"'K20 - time schedule'!FQ36","v":0},{"$f":"'K20 - time schedule'!FR36","v":0},{"$f":"'K20 - time schedule'!FS36","v":0},{"$f":"'K20 - time schedule'!FT36","v":0},{"$f":"'K20 - time schedule'!FU36","v":0},{"$f":"'K20 - time schedule'!FV36","v":0},{"$f":"'K20 - time schedule'!FW36","v":0},{"$f":"'K20 - time schedule'!FX36","v":0},{"$f":"'K20 - time schedule'!FY36","v":0},{"$f":"'K20 - time schedule'!FZ36","v":0},{"$f":"'K20 - time schedule'!GA36","v":0},{"$f":"'K20 - time schedule'!GB36","v":0},{"$f":"'K20 - time schedule'!GC36","v":0},{"$f":"'K20 - time schedule'!GD36","v":0},{"$f":"'K20 - time schedule'!GE36","v":0},{"$f":"'K20 - time schedule'!GF36","v":0},{"$f":"'K20 - time schedule'!GG36","v":0},{"$f":"'K20 - time schedule'!GH23","v":0},{"$f":"'K20 - time schedule'!GI23","v":0},{"$f":"'K20 - time schedule'!GJ23","v":0},{"$f":"'K20 - time schedule'!GK23","v":0},{"$f":"'K20 - time schedule'!GL23","v":0},{"$f":"'K20 - time schedule'!GM23","v":0},{"$f":"'K20 - time schedule'!GN23","v":0},{"$f":"'K20 - time schedule'!GO23","v":0},{"$f":"'K20 - time schedule'!GP23","v":0},{"$f":"'K20 - time schedule'!GQ23","v":0},{"$f":"'K20 - time schedule'!GR23","v":0},{"$f":"'K20 - time schedule'!GS23","v":0},{"$f":"'K20 - time schedule'!GT23","v":0},{"$f":"'K20 - time schedule'!GU23","v":0},{"$f":"'K20 - time schedule'!GV23","v":0},{"$f":"'K20 - time schedule'!GW23","v":0},{"$f":"'K20 - time schedule'!GX23","v":0},{"$f":"'K20 - time schedule'!GY23","v":0},{"$f":"'K20 - time schedule'!GZ23","v":0},{"$f":"'K20 - time schedule'!HA23","v":0},{"$f":"'K20 - time schedule'!HB23","v":0},{"$f":"'K20 - time schedule'!HC23","v":0},{"$f":"'K20 - time schedule'!HD23","v":0},{"$f":"'K20 - time schedule'!HE23","v":0},{"$f":"'K20 - time schedule'!HF23","v":0},{"$f":"'K20 - time schedule'!HG23","v":0},{"$f":"'K20 - time schedule'!HH23","v":0},{"$f":"'K20 - time schedule'!HI23","v":0},{"$f":"'K20 - time schedule'!HJ23","v":0},{"$f":"'K20 - time schedule'!HK23","v":0},{"$f":"'K20 - time schedule'!HL23","v":0},{"$f":"'K20 - time schedule'!HM23","v":0},{"$f":"'K20 - time schedule'!HN23","v":0},{"$f":"'K20 - time schedule'!HO23","v":0},{"$f":"'K20 - time schedule'!HP23","v":0},{"$f":"'K20 - time schedule'!HQ23","v":0},{"$f":"'K20 - time schedule'!HR23","v":0},{"$f":"'K20 - time schedule'!HS23","v":0},{"$f":"'K20 - time schedule'!HT23","v":0},{"$f":"'K20 - time schedule'!HU23","v":0},{"$f":"'K20 - time schedule'!HV23","v":0},{"$f":"'K20 - time schedule'!HW23","v":0},{"$f":"'K20 - time schedule'!HX23","v":0},{"$f":"'K20 - time schedule'!HY23","v":0},{"$f":"'K20 - time schedule'!HZ23","v":0},{"$f":"'K20 - time schedule'!IA23","v":0},{"$f":"'K20 - time schedule'!IB23","v":0},{"$f":"'K20 - time schedule'!IC23","v":0},{"$f":"'K20 - time schedule'!ID23","v":0},{"$f":"'K20 - time schedule'!IE23","v":0},{"$f":"'K20 - time schedule'!IF23","v":0},{"$f":"'K20 - time schedule'!IG23","v":0},{"$f":"'K20 - time schedule'!IH23","v":0},{"$f":"'K20 - time schedule'!II23","v":0},{"$f":"'K20 - time schedule'!IJ23","v":0},{"$f":"'K20 - time schedule'!IK23","v":0},{"$f":"'K20 - time schedule'!IL23","v":0},{"$f":"'K20 - time schedule'!IM23","v":0},{"$f":"'K20 - time schedule'!IN23","v":0},{"$f":"'K20 - time schedule'!IO23","v":0},{"$f":"'K20 - time schedule'!IP23","v":0},{"$f":"'K20 - time schedule'!IQ23","v":0},{"$f":"'K20 - time schedule'!IR23","v":0},{"$f":"'K20 - time schedule'!IS23","v":0},{"$f":"'K20 - time schedule'!IT23","v":0},{"$f":"'K20 - time schedule'!IU23","v":0},{"$f":"'K20 - time schedule'!IV23","v":0},{"$f":"'K20 - time schedule'!IW23","v":0},{"$f":"'K20 - time schedule'!IX23","v":0},{"$f":"'K20 - time schedule'!IY23","v":0},{"$f":"'K20 - time schedule'!IZ23","v":0},{"$f":"'K20 - time schedule'!JA23","v":0},{"$f":"'K20 - time schedule'!JB23","v":0},{"$f":"'K20 - time schedule'!JC23","v":0},{"$f":"'K20 - time schedule'!JD23","v":0},{"$f":"'K20 - time schedule'!JE23","v":0},{"$f":"'K20 - time schedule'!JF23","v":0},{"$f":"'K20 - time schedule'!JG23","v":0},{"$f":"'K20 - time schedule'!JH23","v":0},{"$f":"'K20 - time schedule'!JI23","v":0},{"$f":"'K20 - time schedule'!JJ23","v":0},{"$f":"'K20 - time schedule'!JK23","v":0},{"$f":"'K20 - time schedule'!JL23","v":0},{"$f":"'K20 - time schedule'!JM23","v":0},{"$f":"'K20 - time schedule'!JN23","v":0},{"$f":"'K20 - time schedule'!JO23","v":0},{"$f":"'K20 - time schedule'!JP23","v":0},{"$f":"'K20 - time schedule'!JQ23","v":0},{"$f":"'K20 - time schedule'!JR23","v":0},{"$f":"'K20 - time schedule'!JS23","v":0},{"$f":"'K20 - time schedule'!JT23","v":0},{"$f":"'K20 - time schedule'!JU23","v":0},{"$f":"'K20 - time schedule'!JV23","v":0},{"$f":"'K20 - time schedule'!JW23","v":0},{"$f":"'K20 - time schedule'!JX23","v":0},{"$f":"'K20 - time schedule'!JY23","v":0},{"$f":"'K20 - time schedule'!JZ23","v":0},{"$f":"'K20 - time schedule'!KA23","v":0},{"$f":"'K20 - time schedule'!KB23","v":0},{"$f":"'K20 - time schedule'!KC23","v":0},{"$f":"'K20 - time schedule'!KD23","v":0},{"$f":"'K20 - time schedule'!KE23","v":0},{"$f":"'K20 - time schedule'!KF23","v":0},{"$f":"'K20 - time schedule'!KG23","v":0},{"$f":"'K20 - time schedule'!KH23","v":0},{"$f":"'K20 - time schedule'!KI23","v":0},{"$f":"'K20 - time schedule'!KJ23","v":0},{"$f":"'K20 - time schedule'!KK23","v":0},{"$f":"'K20 - time schedule'!KL23","v":0},{"$f":"'K20 - time schedule'!KM23","v":0},{"$f":"'K20 - time schedule'!KN23","v":0},{"$f":"'K20 - time schedule'!KO23","v":0},{"$f":"'K20 - time schedule'!KP23","v":0},{"$f":"'K20 - time schedule'!KQ23","v":0},{"$f":"'K20 - time schedule'!KR23","v":0},{"$f":"'K20 - time schedule'!KS23","v":0},{"$f":"'K20 - time schedule'!KT23","v":0}]
["Boiler room K20 - media connection","K20",{"$f":"'K20 - time schedule'!G38","v":0},{"$f":"'K20 - time schedule'!H38","v":0},{"$f":"'K20 - time schedule'!I38","v":0},{"$f":"'K20 - time schedule'!J38","v":0},{"$f":"'K20 - time schedule'!K38","v":0},{"$f":"'K20 - time schedule'!L38","v":0},{"$f":"'K20 - time schedule'!M38","v":0},{"$f":"'K20 - time schedule'!N38","v":0},{"$f":"'K20 - time schedule'!O38","v":0},{"$f":"'K20 - time schedule'!P38","v":0},{"$f":"'K20 - time schedule'!Q38","v":0},{"$f":"'K20 - time schedule'!R38","v":0},{"$f":"'K20 - time schedule'!S38","v":0},{"$f":"'K20 - time schedule'!T38","v":0},{"$f":"'K20 - time schedule'!U38","v":0},{"$f":"'K20 - time schedule'!V38","v":0},{"$f":"'K20 - time schedule'!W38","v":0},{"$f":"'K20 - time schedule'!X38","v":0},{"$f":"'K20 - time schedule'!Y38","v":0},{"$f":"'K20 - time schedule'!Z38","v":0},{"$f":"'K20 - time schedule'!AA38","v":0},{"$f":"'K20 - time schedule'!AB38","v":0},{"$f":"'K20 - time schedule'!AC38","v":0},{"$f":"'K20 - time schedule'!AD38","v":0},{"$f":"'K20 - time schedule'!AE38","v":0},{"$f":"'K20 - time schedule'!AF38","v":0},{"$f":"'K20 - time schedule'!AG38","v":0},{"$f":"'K20 - time schedule'!AH38","v":0},{"$f":"'K20 - time schedule'!AI38","v":0},{"$f":"'K20 - time schedule'!AJ38","v":0},{"$f":"'K20 - time schedule'!AK38","v":0},{"$f":"'K20 - time schedule'!AL38","v":0},{"$f":"'K20 - time schedule'!AM38","v":0},{"$f":"'K20 - time schedule'!AN38","v":0},{"$f":"'K20 - time schedule'!AO38","v":0},{"$f":"'K20 - time schedule'!AP38","v":0},{"$f":"'K20 - time schedule'!AQ38","v":0},{"$f":"'K20 - time schedule'!AR38","v":0},{"$f":"'K20 - time schedule'!AS38","v":0},{"$f":"'K20 - time schedule'!AT38","v":0},{"$f":"'K20 - time schedule'!AU38","v":0},{"$f":"'K20 - time schedule'!AV38","v":0},{"$f":"'K20 - time schedule'!AW38","v":0},{"$f":"'K20 - time schedule'!AX38","v":0},{"$f":"'K20 - time schedule'!AY38","v":0},{"$f":"'K20 - time schedule'!AZ38","v":0},{"$f":"'K20 - time schedule'!BA38","v":0},{"$f":"'K20 - time schedule'!BB38","v":0},{"$f":"'K20 - time schedule'!BC38","v":0},{"$f":"'K20 - time schedule'!BD38","v":0},{"$f":"'K20 - time schedule'!BE38","v":0},{"$f":"'K20 - time schedule'!BF38","v":0},{"$f":"'K20 - time schedule'!BG38","v":0},{"$f":"'K20 - time schedule'!BH38","v":0},{"$f":"'K20 - time schedule'!BI38","v":0},{"$f":"'K20 - time schedule'!BJ38","v":0},{"$f":"'K20 - time schedule'!BK38","v":0},{"$f":"'K20 - time schedule'!BL38","v":0},{"$f":"'K20 - time schedule'!BM38","v":0},{"$f":"'K20 - time schedule'!BN38","v":0},{"$f":"'K20 - time schedule'!BO38","v":0},{"$f":"'K20 - time schedule'!BP38","v":0},{"$f":"'K20 - time schedule'!BQ38","v":0},{"$f":"'K20 - time schedule'!BR38","v":0},{"$f":"'K20 - time schedule'!BS38","v":0},{"$f":"'K20 - time schedule'!BT38","v":0},{"$f":"'K20 - time schedule'!BU38","v":0},{"$f":"'K20 - time schedule'!BV38","v":0},{"$f":"'K20 - time schedule'!BW38","v":0},{"$f":"'K20 - time schedule'!BX38","v":0},{"$f":"'K20 - time schedule'!BY38","v":0},{"$f":"'K20 - time schedule'!BZ38","v":0},{"$f":"'K20 - time schedule'!CA38","v":0},{"$f":"'K20 - time schedule'!CB38","v":0},{"$f":"'K20 - time schedule'!CC38","v":0},{"$f":"'K20 - time schedule'!CD38","v":0},{"$f":"'K20 - time schedule'!CE38","v":0},{"$f":"'K20 - time schedule'!CF38","v":0},{"$f":"'K20 - time schedule'!CG38","v":0},{"$f":"'K20 - time schedule'!CH38","v":0},{"$f":"'K20 - time schedule'!CI38","v":0},{"$f":"'K20 - time schedule'!CJ38","v":0},{"$f":"'K20 - time schedule'!CK38","v":0},{"$f":"'K20 - time schedule'!CL38","v":0},{"$f":"'K20 - time schedule'!CM38","v":0},{"$f":"'K20 - time schedule'!CN38","v":0},{"$f":"'K20 - time schedule'!CO38","v":0},{"$f":"'K20 - time schedule'!CP38","v":0},{"$f":"'K20 - time schedule'!CQ38","v":0},{"$f":"'K20 - time schedule'!CR38","v":0},{"$f":"'K20 - time schedule'!CS38","v":0},{"$f":"'K20 - time schedule'!CT38","v":0},{"$f":"'K20 - time schedule'!CU38","v":0},{"$f":"'K20 - time schedule'!CV38","v":0},{"$f":"'K20 - time schedule'!CW38","v":0},{"$f":"'K20 - time schedule'!CX38","v":0},{"$f":"'K20 - time schedule'!CY38","v":0},{"$f":"'K20 - time schedule'!CZ38","v":0},{"$f":"'K20 - time schedule'!DA38","v":0},{"$f":"'K20 - time schedule'!DB38","v":0},{"$f":"'K20 - time schedule'!DC38","v":0},{"$f":"'K20 - time schedule'!DD38","v":0},{"$f":"'K20 - time schedule'!DE38","v":0},{"$f":"'K20 - time schedule'!DF38","v":0},{"$f":"'K20 - time schedule'!DG38","v":0},{"$f":"'K20 - time schedule'!DH38","v":0},{"$f":"'K20 - time schedule'!DI38","v":0},{"$f":"'K20 - time schedule'!DJ38","v":0},{"$f":"'K20 - time schedule'!DK38","v":0},{"$f":"'K20 - time schedule'!DL38","v":0},{"$f":"'K20 - time schedule'!DM38","v":0},{"$f":"'K20 - time schedule'!DN38","v":0},{"$f":"'K20 - time schedule'!DO38","v":0},{"$f":"'K20 - time schedule'!DP38","v":0},{"$f":"'K20 - time schedule'!DQ38","v":0},{"$f":"'K20 - time schedule'!DR38","v":0},{"$f":"'K20 - time schedule'!DS38","v":0},{"$f":"'K20 - time schedule'!DT38","v":0},{"$f":"'K20 - time schedule'!DU38","v":0},{"$f":"'K20 - time schedule'!DV38","v":0},{"$f":"'K20 - time schedule'!DW38","v":0},{"$f":"'K20 - time schedule'!DX38","v":0},{"$f":"'K20 - time schedule'!DY38","v":0},{"$f":"'K20 - time schedule'!DZ38","v":0},{"$f":"'K20 - time schedule'!EA38","v":0},{"$f":"'K20 - time schedule'!EB38","v":0},{"$f":"'K20 - time schedule'!EC38","v":0},{"$f":"'K20 - time schedule'!ED38","v":0},{"$f":"'K20 - time schedule'!EE38","v":0},{"$f":"'K20 - time schedule'!EF38","v":0},{"$f":"'K20 - time schedule'!EG38","v":0},{"$f":"'K20 - time schedule'!EH38","v":0},{"$f":"'K20 - time schedule'!EI38","v":0},{"$f":"'K20 - time schedule'!EJ38","v":0},{"$f":"'K20 - time schedule'!EK38","v":0},{"$f":"'K20 - time schedule'!EL38","v":0},{"$f":"'K20 - time schedule'!EM38","v":0},{"$f":"'K20 - time schedule'!EN38","v":0},{"$f":"'K20 - time schedule'!EO38","v":0},{"$f":"'K20 - time schedule'!EP38","v":0},{"$f":"'K20 - time schedule'!EQ38","v":0},{"$f":"'K20 - time schedule'!ER38","v":0},{"$f":"'K20 - time schedule'!ES38","v":0},{"$f":"'K20 - time schedule'!ET38","v":0},{"$f":"'K20 - time schedule'!EU38","v":0},{"$f":"'K20 - time schedule'!EV38","v":0},{"$f":"'K20 - time schedule'!EW38","v":0},{"$f":"'K20 - time schedule'!EX38","v":0},{"$f":"'K20 - time schedule'!EY38","v":0},{"$f":"'K20 - time schedule'!EZ38","v":0},{"$f":"'K20 - time schedule'!FA38","v":0},{"$f":"'K20 - time schedule'!FB38","v":0},{"$f":"'K20 - time schedule'!FC38","v":0},{"$f":"'K20 - time schedule'!FD38","v":0},{"$f":"'K20 - time schedule'!FE38","v":0},{"$f":"'K20 - time schedule'!FF38","v":0},{"$f":"'K20 - time schedule'!FG38","v":0},{"$f":"'K20 - time schedule'!FH38","v":0},{"$f":"'K20 - time schedule'!FI38","v":0},{"$f":"'K20 - time schedule'!FJ38","v":0},{"$f":"'K20 - time schedule'!FK38","v":0},{"$f":"'K20 - time schedule'!FL38","v":0},{"$f":"'K20 - time schedule'!FM38","v":0},{"$f":"'K20 - time schedule'!FN38","v":0},{"$f":"'K20 - time schedule'!FO38","v":0},{"$f":"'K20 - time schedule'!FP38","v":0},{"$f":"'K20 - time schedule'!FQ38","v":0},{"$f":"'K20 - time schedule'!FR38","v":0},{"$f":"'K20 - time schedule'!FS38","v":0},{"$f":"'K20 - time schedule'!FT38","v":0},{"$f":"'K20 - time schedule'!FU38","v":0},{"$f":"'K20 - time schedule'!FV38","v":0},{"$f":"'K20 - time schedule'!FW38","v":0},{"$f":"'K20 - time schedule'!FX38","v":0},{"$f":"'K20 - time schedule'!FY38","v":0},{"$f":"'K20 - time schedule'!FZ38","v":0},{"$f":"'K20 - time schedule'!GA38","v":0},{"$f":"'K20 - time schedule'!GB38","v":0},{"$f":"'K20 - time schedule'!GC38","v":0},{"$f":"'K20 - time schedule'!GD38","v":0},{"$f":"'K20 - time schedule'!GE38","v":0},{"$f":"'K20 - time schedule'!GF38","v":0},{"$f":"'K20 - time schedule'!GG38","v":0},{"$f":"'K20 - time schedule'!GH24","v":0},{"$f":"'K20 - time schedule'!GI24","v":0},{"$f":"'K20 - time schedule'!GJ24","v":0},{"$f":"'K20 - time schedule'!GK24","v":0},{"$f":"'K20 - time schedule'!GL24","v":0},{"$f":"'K20 - time schedule'!GM24","v":0},{"$f":"'K20 - time schedule'!GN24","v":0},{"$f":"'K20 - time schedule'!GO24","v":0},{"$f":"'K20 - time schedule'!GP24","v":0},{"$f":"'K20 - time schedule'!GQ24","v":0},{"$f":"'K20 - time schedule'!GR24","v":0},{"$f":"'K20 - time schedule'!GS24","v":0},{"$f":"'K20 - time schedule'!GT24","v":0},{"$f":"'K20 - time schedule'!GU24","v":0},{"$f":"'K20 - time schedule'!GV24","v":0},{"$f":"'K20 - time schedule'!GW24","v":0},{"$f":"'K20 - time schedule'!GX24","v":0},{"$f":"'K20 - time schedule'!GY24","v":0},{"$f":"'K20 - time schedule'!GZ24","v":0},{"$f":"'K20 - time schedule'!HA24","v":0},{"$f":"'K20 - time schedule'!HB24","v":0},{"$f":"'K20 - time schedule'!HC24","v":0},{"$f":"'K20 - time schedule'!HD24","v":0},{"$f":"'K20 - time schedule'!HE24","v":0},{"$f":"'K20 - time schedule'!HF24","v":0},{"$f":"'K20 - time schedule'!HG24","v":0},{"$f":"'K20 - time schedule'!HH24","v":0},{"$f":"'K20 - time schedule'!HI24","v":0},{"$f":"'K20 - time schedule'!HJ24","v":0},{"$f":"'K20 - time schedule'!HK24","v":0},{"$f":"'K20 - time schedule'!HL24","v":0},{"$f":"'K20 - time schedule'!HM24","v":0},{"$f":"'K20 - time schedule'!HN24","v":0},{"$f":"'K20 - time schedule'!HO24","v":0},{"$f":"'K20 - time schedule'!HP24","v":0},{"$f":"'K20 - time schedule'!HQ24","v":0},{"$f":"'K20 - time schedule'!HR24","v":0},{"$f":"'K20 - time schedule'!HS24","v":0},{"$f":"'K20 - time schedule'!HT24","v":0},{"$f":"'K20 - time schedule'!HU24","v":0},{"$f":"'K20 - time schedule'!HV24","v":0},{"$f":"'K20 - time schedule'!HW24","v":0},{"$f":"'K20 - time schedule'!HX24","v":0},{"$f":"'K20 - time schedule'!HY24","v":0},{"$f":"'K20 - time schedule'!HZ24","v":0},{"$f":"'K20 - time schedule'!IA24","v":0},{"$f":"'K20 - time schedule'!IB24","v":0},{"$f":"'K20 - time schedule'!IC24","v":0},{"$f":"'K20 - time schedule'!ID24","v":0},{"$f":"'K20 - time schedule'!IE24","v":0},{"$f":"'K20 - time schedule'!IF24","v":0},{"$f":"'K20 - time schedule'!IG24","v":0},{"$f":"'K20 - time schedule'!IH24","v":0},{"$f":"'K20 - time schedule'!II24","v":0},{"$f":"'K20 - time schedule'!IJ24","v":0},{"$f":"'K20 - time schedule'!IK24","v":0},{"$f":"'K20 - time schedule'!IL24","v":0},{"$f":"'K20 - time schedule'!IM24","v":0},{"$f":"'K20 - time schedule'!IN24","v":0},{"$f":"'K20 - time schedule'!IO24","v":0},{"$f":"'K20 - time schedule'!IP24","v":0},{"$f":"'K20 - time schedule'!IQ24","v":0},{"$f":"'K20 - time schedule'!IR24","v":0},{"$f":"'K20 - time schedule'!IS24","v":0},{"$f":"'K20 - time schedule'!IT24","v":0},{"$f":"'K20 - time schedule'!IU24","v":0},{"$f":"'K20 - time schedule'!IV24","v":0},{"$f":"'K20 - time schedule'!IW24","v":0},{"$f":"'K20 - time schedule'!IX24","v":0},{"$f":"'K20 - time schedule'!IY24","v":0},{"$f":"'K20 - time schedule'!IZ24","v":0},{"$f":"'K20 - time schedule'!JA24","v":0},{"$f":"'K20 - time schedule'!JB24","v":0},{"$f":"'K20 - time schedule'!JC24","v":0},{"$f":"'K20 - time schedule'!JD24","v":0},{"$f":"'K20 - time schedule'!JE24","v":0},{"$f":"'K20 - time schedule'!JF24","v":0},{"$f":"'K20 - time schedule'!JG24","v":0},{"$f":"'K20 - time schedule'!JH24","v":0},{"$f":"'K20 - time schedule'!JI24","v":0},{"$f":"'K20 - time schedule'!JJ24","v":0},{"$f":"'K20 - time schedule'!JK24","v":0},{"$f":"'K20 - time schedule'!JL24","v":0},{"$f":"'K20 - time schedule'!JM24","v":0},{"$f":"'K20 - time schedule'!JN24","v":0},{"$f":"'K20 - time schedule'!JO24","v":0},{"$f":"'K20 - time schedule'!JP24","v":0},{"$f":"'K20 - time schedule'!JQ24","v":0},{"$f":"'K20 - time schedule'!JR24","v":0},{"$f":"'K20 - time schedule'!JS24","v":0},{"$f":"'K20 - time schedule'!JT24","v":0},{"$f":"'K20 - time schedule'!JU24","v":0},{"$f":"'K20 - time schedule'!JV24","v":0},{"$f":"'K20 - time schedule'!JW24","v":0},{"$f":"'K20 - time schedule'!JX24","v":0},{"$f":"'K20 - time schedule'!JY24","v":0},{"$f":"'K20 - time schedule'!JZ24","v":0},{"$f":"'K20 - time schedule'!KA24","v":0},{"$f":"'K20 - time schedule'!KB24","v":0},{"$f":"'K20 - time schedule'!KC24","v":0},{"$f":"'K20 - time schedule'!KD24","v":0},{"$f":"'K20 - time schedule'!KE24","v":0},{"$f":"'K20 - time schedule'!KF24","v":0},{"$f":"'K20 - time schedule'!KG24","v":0},{"$f":"'K20 - time schedule'!KH24","v":0},{"$f":"'K20 - time schedule'!KI24","v":0},{"$f":"'K20 - time schedule'!KJ24","v":0},{"$f":"'K20 - time schedule'!KK24","v":0},{"$f":"'K20 - time schedule'!KL24","v":0},{"$f":"'K20 - time schedule'!KM24","v":0},{"$f":"'K20 - time schedule'!KN24","v":0},{"$f":"'K20 - time schedule'!KO24","v":0},{"$f":"'K20 - time schedule'!KP24","v":0},{"$f":"'K20 - time schedule'!KQ24","v":0},{"$f":"'K20 - time schedule'!KR24","v":0},{"$f":"'K20 - time schedule'!KS24","v":0},{"$f":"'K20 - time schedule'!KT24","v":0}]
["Boiler room K20 - outdoor flue lines including chimney connection","K20",{"$f":"'K20 - time schedule'!G40","v":0},{"$f":"'K20 - time schedule'!H40","v":0},{"$f":"'K20 - time schedule'!I40","v":0},{"$f":"'K20 - time schedule'!J40","v":0},{"$f":"'K20 - time schedule'!K40","v":0},{"$f":"'K20 - time schedule'!L40","v":0},{"$f":"'K20 - time schedule'!M40","v":0},{"$f":"'K20 - time schedule'!N40","v":0},{"$f":"'K20 - time schedule'!O40","v":0},{"$f":"'K20 - time schedule'!P40","v":0},{"$f":"'K20 - time schedule'!Q40","v":0},{"$f":"'K20 - time schedule'!R40","v":0},{"$f":"'K20 - time schedule'!S40","v":0},{"$f":"'K20 - time schedule'!T40","v":0},{"$f":"'K20 - time schedule'!U40","v":0},{"$f":"'K20 - time schedule'!V40","v":0},{"$f":"'K20 - time schedule'!W40","v":0},{"$f":"'K20 - time schedule'!X40","v":0},{"$f":"'K20 - time schedule'!Y40","v":0},{"$f":"'K20 - time schedule'!Z40","v":0},{"$f":"'K20 - time schedule'!AA40","v":0},{"$f":"'K20 - time schedule'!AB40","v":0},{"$f":"'K20 - time schedule'!AC40","v":0},{"$f":"'K20 - time schedule'!AD40","v":0},{"$f":"'K20 - time schedule'!AE40","v":0},{"$f":"'K20 - time schedule'!AF40","v":0},{"$f":"'K20 - time schedule'!AG40","v":0},{"$f":"'K20 - time schedule'!AH40","v":0},{"$f":"'K20 - time schedule'!AI40","v":0},{"$f":"'K20 - time schedule'!AJ40","v":0},{"$f":"'K20 - time schedule'!AK40","v":0},{"$f":"'K20 - time schedule'!AL40","v":0},{"$f":"'K20 - time schedule'!AM40","v":0},{"$f":"'K20 - time schedule'!AN40","v":0},{"$f":"'K20 - time schedule'!AO40","v":0},{"$f":"'K20 - time schedule'!AP40","v":0},{"$f":"'K20 - time schedule'!AQ40","v":0},{"$f":"'K20 - time schedule'!AR40","v":0},{"$f":"'K20 - time schedule'!AS40","v":0},{"$f":"'K20 - time schedule'!AT40","v":0},{"$f":"'K20 - time schedule'!AU40","v":0},{"$f":"'K20 - time schedule'!AV40","v":0},{"$f":"'K20 - time schedule'!AW40","v":0},{"$f":"'K20 - time schedule'!AX40","v":0},{"$f":"'K20 - time schedule'!AY40","v":0},{"$f":"'K20 - time schedule'!AZ40","v":0},{"$f":"'K20 - time schedule'!BA40","v":0},{"$f":"'K20 - time schedule'!BB40","v":0},{"$f":"'K20 - time schedule'!BC40","v":0},{"$f":"'K20 - time schedule'!BD40","v":0},{"$f":"'K20 - time schedule'!BE40","v":0},{"$f":"'K20 - time schedule'!BF40","v":0},{"$f":"'K20 - time schedule'!BG40","v":0},{"$f":"'K20 - time schedule'!BH40","v":0},{"$f":"'K20 - time schedule'!BI40","v":0},{"$f":"'K20 - time schedule'!BJ40","v":0},{"$f":"'K20 - time schedule'!BK40","v":0},{"$f":"'K20 - time schedule'!BL40","v":0},{"$f":"'K20 - time schedule'!BM40","v":0},{"$f":"'K20 - time schedule'!BN40","v":0},{"$f":"'K20 - time schedule'!BO40","v":0},{"$f":"'K20 - time schedule'!BP40","v":0},{"$f":"'K20 - time schedule'!BQ40","v":0},{"$f":"'K20 - time schedule'!BR40","v":0},{"$f":"'K20 - time schedule'!BS40","v":0},{"$f":"'K20 - time schedule'!BT40","v":0},{"$f":"'K20 - time schedule'!BU40","v":0},{"$f":"'K20 - time schedule'!BV40","v":0},{"$f":"'K20 - time schedule'!BW40","v":0},{"$f":"'K20 - time schedule'!BX40","v":0},{"$f":"'K20 - time schedule'!BY40","v":0},{"$f":"'K20 - time schedule'!BZ40","v":0},{"$f":"'K20 - time schedule'!CA40","v":0},{"$f":"'K20 - time schedule'!CB40","v":0},{"$f":"'K20 - time schedule'!CC40","v":0},{"$f":"'K20 - time schedule'!CD40","v":0},{"$f":"'K20 - time schedule'!CE40","v":0},{"$f":"'K20 - time schedule'!CF40","v":0},{"$f":"'K20 - time schedule'!CG40","v":0},{"$f":"'K20 - time schedule'!CH40","v":0},{"$f":"'K20 - time schedule'!CI40","v":0},{"$f":"'K20 - time schedule'!CJ40","v":0},{"$f":"'K20 - time schedule'!CK40","v":0},{"$f":"'K20 - time schedule'!CL40","v":0},{"$f":"'K20 - time schedule'!CM40","v":0},{"$f":"'K20 - time schedule'!CN40","v":0},{"$f":"'K20 - time schedule'!CO40","v":0},{"$f":"'K20 - time schedule'!CP40","v":0},{"$f":"'K20 - time schedule'!CQ40","v":0},{"$f":"'K20 - time schedule'!CR40","v":0},{"$f":"'K20 - time schedule'!CS40","v":0},{"$f":"'K20 - time schedule'!CT40","v":0},{"$f":"'K20 - time schedule'!CU40","v":0},{"$f":"'K20 - time schedule'!CV40","v":0},{"$f":"'K20 - time schedule'!CW40","v":0},{"$f":"'K20 - time schedule'!CX40","v":0},{"$f":"'K20 - time schedule'!CY40","v":0},{"$f":"'K20 - time schedule'!CZ40","v":0},{"$f":"'K20 - time schedule'!DA40","v":0},{"$f":"'K20 - time schedule'!DB40","v":0},{"$f":"'K20 - time schedule'!DC40","v":0},{"$f":"'K20 - time schedule'!DD40","v":0},{"$f":"'K20 - time schedule'!DE40","v":0},{"$f":"'K20 - time schedule'!DF40","v":0},{"$f":"'K20 - time schedule'!DG40","v":0},{"$f":"'K20 - time schedule'!DH40","v":0},{"$f":"'K20 - time schedule'!DI40","v":0},{"$f":"'K20 - time schedule'!DJ40","v":0},{"$f":"'K20 - time schedule'!DK40","v":0},{"$f":"'K20 - time schedule'!DL40","v":0},{"$f":"'K20 - time schedule'!DM40","v":0},{"$f":"'K20 - time schedule'!DN40","v":0},{"$f":"'K20 - time schedule'!DO40","v":0},{"$f":"'K20 - time schedule'!DP40","v":0},{"$f":"'K20 - time schedule'!DQ40","v":0},{"$f":"'K20 - time schedule'!DR40","v":0},{"$f":"'K20 - time schedule'!DS40","v":0},{"$f":"'K20 - time schedule'!DT40","v":0},{"$f":"'K20 - time schedule'!DU40","v":0},{"$f":"'K20 - time schedule'!DV40","v":0},{"$f":"'K20 - time schedule'!DW40","v":0},{"$f":"'K20 - time schedule'!DX40","v":0},{"$f":"'K20 - time schedule'!DY40","v":0},{"$f":"'K20 - time schedule'!DZ40","v":0},{"$f":"'K20 - time schedule'!EA40","v":0},{"$f":"'K20 - time schedule'!EB40","v":0},{"$f":"'K20 - time schedule'!EC40","v":0},{"$f":"'K20 - time schedule'!ED40","v":0},{"$f":"'K20 - time schedule'!EE40","v":0},{"$f":"'K20 - time schedule'!EF40","v":0},{"$f":"'K20 - time schedule'!EG40","v":0},{"$f":"'K20 - time schedule'!EH40","v":0},{"$f":"'K20 - time schedule'!EI40","v":0},{"$f":"'K20 - time schedule'!EJ40","v":0},{"$f":"'K20 - time schedule'!EK40","v":0},{"$f":"'K20 - time schedule'!EL40","v":0},{"$f":"'K20 - time schedule'!EM40","v":0},{"$f":"'K20 - time schedule'!EN40","v":0},{"$f":"'K20 - time schedule'!EO40","v":0},{"$f":"'K20 - time schedule'!EP40","v":0},{"$f":"'K20 - time schedule'!EQ40","v":0},{"$f":"'K20 - time schedule'!ER40","v":0},{"$f":"'K20 - time schedule'!ES40","v":0},{"$f":"'K20 - time schedule'!ET40","v":0},{"$f":"'K20 - time schedule'!EU40","v":0},{"$f":"'K20 - time schedule'!EV40","v":0},{"$f":"'K20 - time schedule'!EW40","v":0},{"$f":"'K20 - time schedule'!EX40","v":0},{"$f":"'K20 - time schedule'!EY40","v":0},{"$f":"'K20 - time schedule'!EZ40","v":0},{"$f":"'K20 - time schedule'!FA40","v":0},{"$f":"'K20 - time schedule'!FB40","v":0},{"$f":"'K20 - time schedule'!FC40","v":0},{"$f":"'K20 - time schedule'!FD40","v":0},{"$f":"'K20 - time schedule'!FE40","v":0},{"$f":"'K20 - time schedule'!FF40","v":0},{"$f":"'K20 - time schedule'!FG40","v":0},{"$f":"'K20 - time schedule'!FH40","v":0},{"$f":"'K20 - time schedule'!FI40","v":0},{"$f":"'K20 - time schedule'!FJ40","v":0},{"$f":"'K20 - time schedule'!FK40","v":0},{"$f":"'K20 - time schedule'!FL40","v":0},{"$f":"'K20 - time schedule'!FM40","v":0},{"$f":"'K20 - time schedule'!FN40","v":0},{"$f":"'K20 - time schedule'!FO40","v":0},{"$f":"'K20 - time schedule'!FP40","v":0},{"$f":"'K20 - time schedule'!FQ40","v":0},{"$f":"'K20 - time schedule'!FR40","v":0},{"$f":"'K20 - time schedule'!FS40","v":0},{"$f":"'K20 - time schedule'!FT40","v":0},{"$f":"'K20 - time schedule'!FU40","v":0},{"$f":"'K20 - time schedule'!FV40","v":0},{"$f":"'K20 - time schedule'!FW40","v":0},{"$f":"'K20 - time schedule'!FX40","v":0},{"$f":"'K20 - time schedule'!FY40","v":0},{"$f":"'K20 - time schedule'!FZ40","v":0},{"$f":"'K20 - time schedule'!GA40","v":0},{"$f":"'K20 - time schedule'!GB40","v":0},{"$f":"'K20 - time schedule'!GC40","v":0},{"$f":"'K20 - time schedule'!GD40","v":0},{"$f":"'K20 - time schedule'!GE40","v":0},{"$f":"'K20 - time schedule'!GF40","v":0},{"$f":"'K20 - time schedule'!GG40","v":0},{"$f":"'K20 - time schedule'!GH25","v":0},{"$f":"'K20 - time schedule'!GI25","v":0},{"$f":"'K20 - time schedule'!GJ25","v":0},{"$f":"'K20 - time schedule'!GK25","v":0},{"$f":"'K20 - time schedule'!GL25","v":0},{"$f":"'K20 - time schedule'!GM25","v":0},{"$f":"'K20 - time schedule'!GN25","v":0},{"$f":"'K20 - time schedule'!GO25","v":0},{"$f":"'K20 - time schedule'!GP25","v":0},{"$f":"'K20 - time schedule'!GQ25","v":0},{"$f":"'K20 - time schedule'!GR25","v":0},{"$f":"'K20 - time schedule'!GS25","v":0},{"$f":"'K20 - time schedule'!GT25","v":0},{"$f":"'K20 - time schedule'!GU25","v":0},{"$f":"'K20 - time schedule'!GV25","v":0},{"$f":"'K20 - time schedule'!GW25","v":0},{"$f":"'K20 - time schedule'!GX25","v":0},{"$f":"'K20 - time schedule'!GY25","v":0},{"$f":"'K20 - time schedule'!GZ25","v":0},{"$f":"'K20 - time schedule'!HA25","v":0},{"$f":"'K20 - time schedule'!HB25","v":0},{"$f":"'K20 - time schedule'!HC25","v":0},{"$f":"'K20 - time schedule'!HD25","v":0},{"$f":"'K20 - time schedule'!HE25","v":0},{"$f":"'K20 - time schedule'!HF25","v":0},{"$f":"'K20 - time schedule'!HG25","v":0},{"$f":"'K20 - time schedule'!HH25","v":0},{"$f":"'K20 - time schedule'!HI25","v":0},{"$f":"'K20 - time schedule'!HJ25","v":0},{"$f":"'K20 - time schedule'!HK25","v":0},{"$f":"'K20 - time schedule'!HL25","v":0},{"$f":"'K20 - time schedule'!HM25","v":0},{"$f":"'K20 - time schedule'!HN25","v":0},{"$f":"'K20 - time schedule'!HO25","v":0},{"$f":"'K20 - time schedule'!HP25","v":0},{"$f":"'K20 - time schedule'!HQ25","v":0},{"$f":"'K20 - time schedule'!HR25","v":0},{"$f":"'K20 - time schedule'!HS25","v":0},{"$f":"'K20 - time schedule'!HT25","v":0},{"$f":"'K20 - time schedule'!HU25","v":0},{"$f":"'K20 - time schedule'!HV25","v":0},{"$f":"'K20 - time schedule'!HW25","v":0},{"$f":"'K20 - time schedule'!HX25","v":0},{"$f":"'K20 - time schedule'!HY25","v":0},{"$f":"'K20 - time schedule'!HZ25","v":0},{"$f":"'K20 - time schedule'!IA25","v":0},{"$f":"'K20 - time schedule'!IB25","v":0},{"$f":"'K20 - time schedule'!IC25","v":0},{"$f":"'K20 - time schedule'!ID25","v":0},{"$f":"'K20 - time schedule'!IE25","v":0},{"$f":"'K20 - time schedule'!IF25","v":0},{"$f":"'K20 - time schedule'!IG25","v":0},{"$f":"'K20 - time schedule'!IH25","v":0},{"$f":"'K20 - time schedule'!II25","v":0},{"$f":"'K20 - time schedule'!IJ25","v":0},{"$f":"'K20 - time schedule'!IK25","v":0},{"$f":"'K20 - time schedule'!IL25","v":0},{"$f":"'K20 - time schedule'!IM25","v":0},{"$f":"'K20 - time schedule'!IN25","v":0},{"$f":"'K20 - time schedule'!IO25","v":0},{"$f":"'K20 - time schedule'!IP25","v":0},{"$f":"'K20 - time schedule'!IQ25","v":0},{"$f":"'K20 - time schedule'!IR25","v":0},{"$f":"'K20 - time schedule'!IS25","v":0},{"$f":"'K20 - time schedule'!IT25","v":0},{"$f":"'K20 - time schedule'!IU25","v":0},{"$f":"'K20 - time schedule'!IV25","v":0},{"$f":"'K20 - time schedule'!IW25","v":0},{"$f":"'K20 - time schedule'!IX25","v":0},{"$f":"'K20 - time schedule'!IY25","v":0},{"$f":"'K20 - time schedule'!IZ25","v":0},{"$f":"'K20 - time schedule'!JA25","v":0},{"$f":"'K20 - time schedule'!JB25","v":0},{"$f":"'K20 - time schedule'!JC25","v":0},{"$f":"'K20 - time schedule'!JD25","v":0},{"$f":"'K20 - time schedule'!JE25","v":0},{"$f":"'K20 - time schedule'!JF25","v":0},{"$f":"'K20 - time schedule'!JG25","v":0},{"$f":"'K20 - time schedule'!JH25","v":0},{"$f":"'K20 - time schedule'!JI25","v":0},{"$f":"'K20 - time schedule'!JJ25","v":0},{"$f":"'K20 - time schedule'!JK25","v":0},{"$f":"'K20 - time schedule'!JL25","v":0},{"$f":"'K20 - time schedule'!JM25","v":0},{"$f":"'K20 - time schedule'!JN25","v":0},{"$f":"'K20 - time schedule'!JO25","v":0},{"$f":"'K20 - time schedule'!JP25","v":0},{"$f":"'K20 - time schedule'!JQ25","v":0},{"$f":"'K20 - time schedule'!JR25","v":0},{"$f":"'K20 - time schedule'!JS25","v":0},{"$f":"'K20 - time schedule'!JT25","v":0},{"$f":"'K20 - time schedule'!JU25","v":0},{"$f":"'K20 - time schedule'!JV25","v":0},{"$f":"'K20 - time schedule'!JW25","v":0},{"$f":"'K20 - time schedule'!JX25","v":0},{"$f":"'K20 - time schedule'!JY25","v":0},{"$f":"'K20 - time schedule'!JZ25","v":0},{"$f":"'K20 - time schedule'!KA25","v":0},{"$f":"'K20 - time schedule'!KB25","v":0},{"$f":"'K20 - time schedule'!KC25","v":0},{"$f":"'K20 - time schedule'!KD25","v":0},{"$f":"'K20 - time schedule'!KE25","v":0},{"$f":"'K20 - time schedule'!KF25","v":0},{"$f":"'K20 - time schedule'!KG25","v":0},{"$f":"'K20 - time schedule'!KH25","v":0},{"$f":"'K20 - time schedule'!KI25","v":0},{"$f":"'K20 - time schedule'!KJ25","v":0},{"$f":"'K20 - time schedule'!KK25","v":0},{"$f":"'K20 - time schedule'!KL25","v":0},{"$f":"'K20 - time schedule'!KM25","v":0},{"$f":"'K20 - time schedule'!KN25","v":0},{"$f":"'K20 - time schedule'!KO25","v":0},{"$f":"'K20 - time schedule'!KP25","v":0},{"$f":"'K20 - time schedule'!KQ25","v":0},{"$f":"'K20 - time schedule'!KR25","v":0},{"$f":"'K20 - time schedule'!KS25","v":0},{"$f":"'K20 - time schedule'!KT25","v":0}]
["Boiler room K20 - outdoor pipeline bridge construction (connection of ash management and SNCR)","K20",{"$f":"'K20 - time schedule'!G42","v":0},{"$f":"'K20 - time schedule'!H42","v":0},{"$f":"'K20 - time schedule'!I42","v":0},{"$f":"'K20 - time schedule'!J42","v":0},{"$f":"'K20 - time schedule'!K42","v":0},{"$f":"'K20 - time schedule'!L42","v":0},{"$f":"'K20 - time schedule'!M42","v":0},{"$f":"'K20 - time schedule'!N42","v":0},{"$f":"'K20 - time schedule'!O42","v":0},{"$f":"'K20 - time schedule'!P42","v":0},{"$f":"'K20 - time schedule'!Q42","v":0},{"$f":"'K20 - time schedule'!R42","v":0},{"$f":"'K20 - time schedule'!S42","v":0},{"$f":"'K20 - time schedule'!T42","v":0},{"$f":"'K20 - time schedule'!U42","v":0},{"$f":"'K20 - time schedule'!V42","v":0},{"$f":"'K20 - time schedule'!W42","v":0},{"$f":"'K20 - time schedule'!X42","v":0},{"$f":"'K20 - time schedule'!Y42","v":0},{"$f":"'K20 - time schedule'!Z42","v":0},{"$f":"'K20 - time schedule'!AA42","v":0},{"$f":"'K20 - time schedule'!AB42","v":0},{"$f":"'K20 - time schedule'!AC42","v":0},{"$f":"'K20 - time schedule'!AD42","v":0},{"$f":"'K20 - time schedule'!AE42","v":0},{"$f":"'K20 - time schedule'!AF42","v":0},{"$f":"'K20 - time schedule'!AG42","v":0},{"$f":"'K20 - time schedule'!AH42","v":0},{"$f":"'K20 - time schedule'!AI42","v":0},{"$f":"'K20 - time schedule'!AJ42","v":0},{"$f":"'K20 - time schedule'!AK42","v":0},{"$f":"'K20 - time schedule'!AL42","v":0},{"$f":"'K20 - time schedule'!AM42","v":0},{"$f":"'K20 - time schedule'!AN42","v":0},{"$f":"'K20 - time schedule'!AO42","v":0},{"$f":"'K20 - time schedule'!AP42","v":0},{"$f":"'K20 - time schedule'!AQ42","v":0},{"$f":"'K20 - time schedule'!AR42","v":0},{"$f":"'K20 - time schedule'!AS42","v":0},{"$f":"'K20 - time schedule'!AT42","v":0},{"$f":"'K20 - time schedule'!AU42","v":0},{"$f":"'K20 - time schedule'!AV42","v":0},{"$f":"'K20 - time schedule'!AW42","v":0},{"$f":"'K20 - time schedule'!AX42","v":0},{"$f":"'K20 - time schedule'!AY42","v":0},{"$f":"'K20 - time schedule'!AZ42","v":0},{"$f":"'K20 - time schedule'!BA42","v":0},{"$f":"'K20 - time schedule'!BB42","v":0},{"$f":"'K20 - time schedule'!BC42","v":0},{"$f":"'K20 - time schedule'!BD42","v":0},{"$f":"'K20 - time schedule'!BE42","v":0},{"$f":"'K20 - time schedule'!BF42","v":0},{"$f":"'K20 - time schedule'!BG42","v":0},{"$f":"'K20 - time schedule'!BH42","v":0},{"$f":"'K20 - time schedule'!BI42","v":0},{"$f":"'K20 - time schedule'!BJ42","v":0},{"$f":"'K20 - time schedule'!BK42","v":0},{"$f":"'K20 - time schedule'!BL42","v":0},{"$f":"'K20 - time schedule'!BM42","v":0},{"$f":"'K20 - time schedule'!BN42","v":0},{"$f":"'K20 - time schedule'!BO42","v":0},{"$f":"'K20 - time schedule'!BP42","v":0},{"$f":"'K20 - time schedule'!BQ42","v":0},{"$f":"'K20 - time schedule'!BR42","v":0},{"$f":"'K20 - time schedule'!BS42","v":0},{"$f":"'K20 - time schedule'!BT42","v":0},{"$f":"'K20 - time schedule'!BU42","v":0},{"$f":"'K20 - time schedule'!BV42","v":0},{"$f":"'K20 - time schedule'!BW42","v":0},{"$f":"'K20 - time schedule'!BX42","v":0},{"$f":"'K20 - time schedule'!BY42","v":0},{"$f":"'K20 - time schedule'!BZ42","v":0},{"$f":"'K20 - time schedule'!CA42","v":0},{"$f":"'K20 - time schedule'!CB42","v":0},{"$f":"'K20 - time schedule'!CC42","v":0},{"$f":"'K20 - time schedule'!CD42","v":0},{"$f":"'K20 - time schedule'!CE42","v":0},{"$f":"'K20 - time schedule'!CF42","v":0},{"$f":"'K20 - time schedule'!CG42","v":0},{"$f":"'K20 - time schedule'!CH42","v":0},{"$f":"'K20 - time schedule'!CI42","v":0},{"$f":"'K20 - time schedule'!CJ42","v":0},{"$f":"'K20 - time schedule'!CK42","v":0},{"$f":"'K20 - time schedule'!CL42","v":0},{"$f":"'K20 - time schedule'!CM42","v":0},{"$f":"'K20 - time schedule'!CN42","v":0},{"$f":"'K20 - time schedule'!CO42","v":0},{"$f":"'K20 - time schedule'!CP42","v":0},{"$f":"'K20 - time schedule'!CQ42","v":0},{"$f":"'K20 - time schedule'!CR42","v":0},{"$f":"'K20 - time schedule'!CS42","v":0},{"$f":"'K20 - time schedule'!CT42","v":0},{"$f":"'K20 - time schedule'!CU42","v":0},{"$f":"'K20 - time schedule'!CV42","v":0},{"$f":"'K20 - time schedule'!CW42","v":0},{"$f":"'K20 - time schedule'!CX42","v":0},{"$f":"'K20 - time schedule'!CY42","v":0},{"$f":"'K20 - time schedule'!CZ42","v":0},{"$f":"'K20 - time schedule'!DA42","v":0},{"$f":"'K20 - time schedule'!DB42","v":0},{"$f":"'K20 - time schedule'!DC42","v":0},{"$f":"'K20 - time schedule'!DD42","v":0},{"$f":"'K20 - time schedule'!DE42","v":0},{"$f":"'K20 - time schedule'!DF42","v":0},{"$f":"'K20 - time schedule'!DG42","v":0},{"$f":"'K20 - time schedule'!DH42","v":0},{"$f":"'K20 - time schedule'!DI42","v":0},{"$f":"'K20 - time schedule'!DJ42","v":0},{"$f":"'K20 - time schedule'!DK42","v":0},{"$f":"'K20 - time schedule'!DL42","v":0},{"$f":"'K20 - time schedule'!DM42","v":0},{"$f":"'K20 - time schedule'!DN42","v":0},{"$f":"'K20 - time schedule'!DO42","v":0},{"$f":"'K20 - time schedule'!DP42","v":0},{"$f":"'K20 - time schedule'!DQ42","v":0},{"$f":"'K20 - time schedule'!DR42","v":0},{"$f":"'K20 - time schedule'!DS42","v":0},{"$f":"'K20 - time schedule'!DT42","v":0},{"$f":"'K20 - time schedule'!DU42","v":0},{"$f":"'K20 - time schedule'!DV42","v":0},{"$f":"'K20 - time schedule'!DW42","v":0},{"$f":"'K20 - time schedule'!DX42","v":0},{"$f":"'K20 - time schedule'!DY42","v":0},{"$f":"'K20 - time schedule'!DZ42","v":0},{"$f":"'K20 - time schedule'!EA42","v":0},{"$f":"'K20 - time schedule'!EB42","v":0},{"$f":"'K20 - time schedule'!EC42","v":0},{"$f":"'K20 - time schedule'!ED42","v":0},{"$f":"'K20 - time schedule'!EE42","v":0},{"$f":"'K20 - time schedule'!EF42","v":0},{"$f":"'K20 - time schedule'!EG42","v":0},{"$f":"'K20 - time schedule'!EH42","v":0},{"$f":"'K20 - time schedule'!EI42","v":0},{"$f":"'K20 - time schedule'!EJ42","v":0},{"$f":"'K20 - time schedule'!EK42","v":0},{"$f":"'K20 - time schedule'!EL42","v":0},{"$f":"'K20 - time schedule'!EM42","v":0},{"$f":"'K20 - time schedule'!EN42","v":0},{"$f":"'K20 - time schedule'!EO42","v":0},{"$f":"'K20 - time schedule'!EP42","v":0},{"$f":"'K20 - time schedule'!EQ42","v":0},{"$f":"'K20 - time schedule'!ER42","v":0},{"$f":"'K20 - time schedule'!ES42","v":0},{"$f":"'K20 - time schedule'!ET42","v":0},{"$f":"'K20 - time schedule'!EU42","v":0},{"$f":"'K20 - time schedule'!EV42","v":0},{"$f":"'K20 - time schedule'!EW42","v":0},{"$f":"'K20 - time schedule'!EX42","v":0},{"$f":"'K20 - time schedule'!EY42","v":0},{"$f":"'K20 - time schedule'!EZ42","v":0},{"$f":"'K20 - time schedule'!FA42","v":0},{"$f":"'K20 - time schedule'!FB42","v":0},{"$f":"'K20 - time schedule'!FC42","v":0},{"$f":"'K20 - time schedule'!FD42","v":0},{"$f":"'K20 - time schedule'!FE42","v":0},{"$f":"'K20 - time schedule'!FF42","v":0},{"$f":"'K20 - time schedule'!FG42","v":0},{"$f":"'K20 - time schedule'!FH42","v":0},{"$f":"'K20 - time schedule'!FI42","v":0},{"$f":"'K20 - time schedule'!FJ42","v":0},{"$f":"'K20 - time schedule'!FK42","v":0},{"$f":"'K20 - time schedule'!FL42","v":0},{"$f":"'K20 - time schedule'!FM42","v":0},{"$f":"'K20 - time schedule'!FN42","v":0},{"$f":"'K20 - time schedule'!FO42","v":0},{"$f":"'K20 - time schedule'!FP42","v":0},{"$f":"'K20 - time schedule'!FQ42","v":0},{"$f":"'K20 - time schedule'!FR42","v":0},{"$f":"'K20 - time schedule'!FS42","v":0},{"$f":"'K20 - time schedule'!FT42","v":0},{"$f":"'K20 - time schedule'!FU42","v":0},{"$f":"'K20 - time schedule'!FV42","v":0},{"$f":"'K20 - time schedule'!FW42","v":0},{"$f":"'K20 - time schedule'!FX42","v":0},{"$f":"'K20 - time schedule'!FY42","v":0},{"$f":"'K20 - time schedule'!FZ42","v":0},{"$f":"'K20 - time schedule'!GA42","v":0},{"$f":"'K20 - time schedule'!GB42","v":0},{"$f":"'K20 - time schedule'!GC42","v":0},{"$f":"'K20 - time schedule'!GD42","v":0},{"$f":"'K20 - time schedule'!GE42","v":0},{"$f":"'K20 - time schedule'!GF42","v":0},{"$f":"'K20 - time schedule'!GG42","v":0},{"$f":"'K20 - time schedule'!GH26","v":0},{"$f":"'K20 - time schedule'!GI26","v":0},{"$f":"'K20 - time schedule'!GJ26","v":0},{"$f":"'K20 - time schedule'!GK26","v":0},{"$f":"'K20 - time schedule'!GL26","v":0},{"$f":"'K20 - time schedule'!GM26","v":0},{"$f":"'K20 - time schedule'!GN26","v":0},{"$f":"'K20 - time schedule'!GO26","v":0},{"$f":"'K20 - time schedule'!GP26","v":0},{"$f":"'K20 - time schedule'!GQ26","v":0},{"$f":"'K20 - time schedule'!GR26","v":0},{"$f":"'K20 - time schedule'!GS26","v":0},{"$f":"'K20 - time schedule'!GT26","v":0},{"$f":"'K20 - time schedule'!GU26","v":0},{"$f":"'K20 - time schedule'!GV26","v":0},{"$f":"'K20 - time schedule'!GW26","v":0},{"$f":"'K20 - time schedule'!GX26","v":0},{"$f":"'K20 - time schedule'!GY26","v":0},{"$f":"'K20 - time schedule'!GZ26","v":0},{"$f":"'K20 - time schedule'!HA26","v":0},{"$f":"'K20 - time schedule'!HB26","v":0},{"$f":"'K20 - time schedule'!HC26","v":0},{"$f":"'K20 - time schedule'!HD26","v":0},{"$f":"'K20 - time schedule'!HE26","v":0},{"$f":"'K20 - time schedule'!HF26","v":0},{"$f":"'K20 - time schedule'!HG26","v":0},{"$f":"'K20 - time schedule'!HH26","v":0},{"$f":"'K20 - time schedule'!HI26","v":0},{"$f":"'K20 - time schedule'!HJ26","v":0},{"$f":"'K20 - time schedule'!HK26","v":0},{"$f":"'K20 - time schedule'!HL26","v":0},{"$f":"'K20 - time schedule'!HM26","v":0},{"$f":"'K20 - time schedule'!HN26","v":0},{"$f":"'K20 - time schedule'!HO26","v":0},{"$f":"'K20 - time schedule'!HP26","v":0},{"$f":"'K20 - time schedule'!HQ26","v":0},{"$f":"'K20 - time schedule'!HR26","v":0},{"$f":"'K20 - time schedule'!HS26","v":0},{"$f":"'K20 - time schedule'!HT26","v":0},{"$f":"'K20 - time schedule'!HU26","v":0},{"$f":"'K20 - time schedule'!HV26","v":0},{"$f":"'K20 - time schedule'!HW26","v":0},{"$f":"'K20 - time schedule'!HX26","v":0},{"$f":"'K20 - time schedule'!HY26","v":0},{"$f":"'K20 - time schedule'!HZ26","v":0},{"$f":"'K20 - time schedule'!IA26","v":0},{"$f":"'K20 - time schedule'!IB26","v":0},{"$f":"'K20 - time schedule'!IC26","v":0},{"$f":"'K20 - time schedule'!ID26","v":0},{"$f":"'K20 - time schedule'!IE26","v":0},{"$f":"'K20 - time schedule'!IF26","v":0},{"$f":"'K20 - time schedule'!IG26","v":0},{"$f":"'K20 - time schedule'!IH26","v":0},{"$f":"'K20 - time schedule'!II26","v":0},{"$f":"'K20 - time schedule'!IJ26","v":0},{"$f":"'K20 - time schedule'!IK26","v":0},{"$f":"'K20 - time schedule'!IL26","v":0},{"$f":"'K20 - time schedule'!IM26","v":0},{"$f":"'K20 - time schedule'!IN26","v":0},{"$f":"'K20 - time schedule'!IO26","v":0},{"$f":"'K20 - time schedule'!IP26","v":0},{"$f":"'K20 - time schedule'!IQ26","v":0},{"$f":"'K20 - time schedule'!IR26","v":0},{"$f":"'K20 - time schedule'!IS26","v":0},{"$f":"'K20 - time schedule'!IT26","v":0},{"$f":"'K20 - time schedule'!IU26","v":0},{"$f":"'K20 - time schedule'!IV26","v":0},{"$f":"'K20 - time schedule'!IW26","v":0},{"$f":"'K20 - time schedule'!IX26","v":0},{"$f":"'K20 - time schedule'!IY26","v":0},{"$f":"'K20 - time schedule'!IZ26","v":0},{"$f":"'K20 - time schedule'!JA26","v":0},{"$f":"'K20 - time schedule'!JB26","v":0},{"$f":"'K20 - time schedule'!JC26","v":0},{"$f":"'K20 - time schedule'!JD26","v":0},{"$f":"'K20 - time schedule'!JE26","v":0},{"$f":"'K20 - time schedule'!JF26","v":0},{"$f":"'K20 - time schedule'!JG26","v":0},{"$f":"'K20 - time schedule'!JH26","v":0},{"$f":"'K20 - time schedule'!JI26","v":0},{"$f":"'K20 - time schedule'!JJ26","v":0},{"$f":"'K20 - time schedule'!JK26","v":0},{"$f":"'K20 - time schedule'!JL26","v":0},{"$f":"'K20 - time schedule'!JM26","v":0},{"$f":"'K20 - time schedule'!JN26","v":0},{"$f":"'K20 - time schedule'!JO26","v":0},{"$f":"'K20 - time schedule'!JP26","v":0},{"$f":"'K20 - time schedule'!JQ26","v":0},{"$f":"'K20 - time schedule'!JR26","v":0},{"$f":"'K20 - time schedule'!JS26","v":0},{"$f":"'K20 - time schedule'!JT26","v":0},{"$f":"'K20 - time schedule'!JU26","v":0},{"$f":"'K20 - time schedule'!JV26","v":0},{"$f":"'K20 - time schedule'!JW26","v":0},{"$f":"'K20 - time schedule'!JX26","v":0},{"$f":"'K20 - time schedule'!JY26","v":0},{"$f":"'K20 - time schedule'!JZ26","v":0},{"$f":"'K20 - time schedule'!KA26","v":0},{"$f":"'K20 - time schedule'!KB26","v":0},{"$f":"'K20 - time schedule'!KC26","v":0},{"$f":"'K20 - time schedule'!KD26","v":0},{"$f":"'K20 - time schedule'!KE26","v":0},{"$f":"'K20 - time schedule'!KF26","v":0},{"$f":"'K20 - time schedule'!KG26","v":0},{"$f":"'K20 - time schedule'!KH26","v":0},{"$f":"'K20 - time schedule'!KI26","v":0},{"$f":"'K20 - time schedule'!KJ26","v":0},{"$f":"'K20 - time schedule'!KK26","v":0},{"$f":"'K20 - time schedule'!KL26","v":0},{"$f":"'K20 - time schedule'!KM26","v":0},{"$f":"'K20 - time schedule'!KN26","v":0},{"$f":"'K20 - time schedule'!KO26","v":0},{"$f":"'K20 - time schedule'!KP26","v":0},{"$f":"'K20 - time schedule'!KQ26","v":0},{"$f":"'K20 - time schedule'!KR26","v":0},{"$f":"'K20 - time schedule'!KS26","v":0},{"$f":"'K20 - time schedule'!KT26","v":0}]
["Boiler room K20 - cladding and roofing, completion of all construction activities","K20",{"$f":"'K20 - time schedule'!G44","v":0},{"$f":"'K20 - time schedule'!H44","v":0},{"$f":"'K20 - time schedule'!I44","v":0},{"$f":"'K20 - time schedule'!J44","v":0},{"$f":"'K20 - time schedule'!K44","v":0},{"$f":"'K20 - time schedule'!L44","v":0},{"$f":"'K20 - time schedule'!M44","v":0},{"$f":"'K20 - time schedule'!N44","v":0},{"$f":"'K20 - time schedule'!O44","v":0},{"$f":"'K20 - time schedule'!P44","v":0},{"$f":"'K20 - time schedule'!Q44","v":0},{"$f":"'K20 - time schedule'!R44","v":0},{"$f":"'K20 - time schedule'!S44","v":0},{"$f":"'K20 - time schedule'!T44","v":0},{"$f":"'K20 - time schedule'!U44","v":0},{"$f":"'K20 - time schedule'!V44","v":0},{"$f":"'K20 - time schedule'!W44","v":0},{"$f":"'K20 - time schedule'!X44","v":0},{"$f":"'K20 - time schedule'!Y44","v":0},{"$f":"'K20 - time schedule'!Z44","v":0},{"$f":"'K20 - time schedule'!AA44","v":0},{"$f":"'K20 - time schedule'!AB44","v":0},{"$f":"'K20 - time schedule'!AC44","v":0},{"$f":"'K20 - time schedule'!AD44","v":0},{"$f":"'K20 - time schedule'!AE44","v":0},{"$f":"'K20 - time schedule'!AF44","v":0},{"$f":"'K20 - time schedule'!AG44","v":0},{"$f":"'K20 - time schedule'!AH44","v":0},{"$f":"'K20 - time schedule'!AI44","v":0},{"$f":"'K20 - time schedule'!AJ44","v":0},{"$f":"'K20 - time schedule'!AK44","v":0},{"$f":"'K20 - time schedule'!AL44","v":0},{"$f":"'K20 - time schedule'!AM44","v":0},{"$f":"'K20 - time schedule'!AN44","v":0},{"$f":"'K20 - time schedule'!AO44","v":0},{"$f":"'K20 - time schedule'!AP44","v":0},{"$f":"'K20 - time schedule'!AQ44","v":0},{"$f":"'K20 - time schedule'!AR44","v":0},{"$f":"'K20 - time schedule'!AS44","v":0},{"$f":"'K20 - time schedule'!AT44","v":0},{"$f":"'K20 - time schedule'!AU44","v":0},{"$f":"'K20 - time schedule'!AV44","v":0},{"$f":"'K20 - time schedule'!AW44","v":0},{"$f":"'K20 - time schedule'!AX44","v":0},{"$f":"'K20 - time schedule'!AY44","v":0},{"$f":"'K20 - time schedule'!AZ44","v":0},{"$f":"'K20 - time schedule'!BA44","v":0},{"$f":"'K20 - time schedule'!BB44","v":0},{"$f":"'K20 - time schedule'!BC44","v":0},{"$f":"'K20 - time schedule'!BD44","v":0},{"$f":"'K20 - time schedule'!BE44","v":0},{"$f":"'K20 - time schedule'!BF44","v":0},{"$f":"'K20 - time schedule'!BG44","v":0},{"$f":"'K20 - time schedule'!BH44","v":0},{"$f":"'K20 - time schedule'!BI44","v":0},{"$f":"'K20 - time schedule'!BJ44","v":0},{"$f":"'K20 - time schedule'!BK44","v":0},{"$f":"'K20 - time schedule'!BL44","v":0},{"$f":"'K20 - time schedule'!BM44","v":0},{"$f":"'K20 - time schedule'!BN44","v":0},{"$f":"'K20 - time schedule'!BO44","v":0},{"$f":"'K20 - time schedule'!BP44","v":0},{"$f":"'K20 - time schedule'!BQ44","v":0},{"$f":"'K20 - time schedule'!BR44","v":0},{"$f":"'K20 - time schedule'!BS44","v":0},{"$f":"'K20 - time schedule'!BT44","v":0},{"$f":"'K20 - time schedule'!BU44","v":0},{"$f":"'K20 - time schedule'!BV44","v":0},{"$f":"'K20 - time schedule'!BW44","v":0},{"$f":"'K20 - time schedule'!BX44","v":0},{"$f":"'K20 - time schedule'!BY44","v":0},{"$f":"'K20 - time schedule'!BZ44","v":0},{"$f":"'K20 - time schedule'!CA44","v":0},{"$f":"'K20 - time schedule'!CB44","v":0},{"$f":"'K20 - time schedule'!CC44","v":0},{"$f":"'K20 - time schedule'!CD44","v":0},{"$f":"'K20 - time schedule'!CE44","v":0},{"$f":"'K20 - time schedule'!CF44","v":0},{"$f":"'K20 - time schedule'!CG44","v":0},{"$f":"'K20 - time schedule'!CH44","v":0},{"$f":"'K20 - time schedule'!CI44","v":0},{"$f":"'K20 - time schedule'!CJ44","v":0},{"$f":"'K20 - time schedule'!CK44","v":0},{"$f":"'K20 - time schedule'!CL44","v":0},{"$f":"'K20 - time schedule'!CM44","v":0},{"$f":"'K20 - time schedule'!CN44","v":0},{"$f":"'K20 - time schedule'!CO44","v":0},{"$f":"'K20 - time schedule'!CP44","v":0},{"$f":"'K20 - time schedule'!CQ44","v":0},{"$f":"'K20 - time schedule'!CR44","v":0},{"$f":"'K20 - time schedule'!CS44","v":0},{"$f":"'K20 - time schedule'!CT44","v":0},{"$f":"'K20 - time schedule'!CU44","v":0},{"$f":"'K20 - time schedule'!CV44","v":0},{"$f":"'K20 - time schedule'!CW44","v":0},{"$f":"'K20 - time schedule'!CX44","v":0},{"$f":"'K20 - time schedule'!CY44","v":0},{"$f":"'K20 - time schedule'!CZ44","v":0},{"$f":"'K20 - time schedule'!DA44","v":0},{"$f":"'K20 - time schedule'!DB44","v":0},{"$f":"'K20 - time schedule'!DC44","v":0},{"$f":"'K20 - time schedule'!DD44","v":0},{"$f":"'K20 - time schedule'!DE44","v":0},{"$f":"'K20 - time schedule'!DF44","v":0},{"$f":"'K20 - time schedule'!DG44","v":0},{"$f":"'K20 - time schedule'!DH44","v":0},{"$f":"'K20 - time schedule'!DI44","v":0},{"$f":"'K20 - time schedule'!DJ44","v":0},{"$f":"'K20 - time schedule'!DK44","v":0},{"$f":"'K20 - time schedule'!DL44","v":0},{"$f":"'K20 - time schedule'!DM44","v":0},{"$f":"'K20 - time schedule'!DN44","v":0},{"$f":"'K20 - time schedule'!DO44","v":0},{"$f":"'K20 - time schedule'!DP44","v":0},{"$f":"'K20 - time schedule'!DQ44","v":0},{"$f":"'K20 - time schedule'!DR44","v":0},{"$f":"'K20 - time schedule'!DS44","v":0},{"$f":"'K20 - time schedule'!DT44","v":0},{"$f":"'K20 - time schedule'!DU44","v":0},{"$f":"'K20 - time schedule'!DV44","v":0},{"$f":"'K20 - time schedule'!DW44","v":0},{"$f":"'K20 - time schedule'!DX44","v":0},{"$f":"'K20 - time schedule'!DY44","v":0},{"$f":"'K20 - time schedule'!DZ44","v":0},{"$f":"'K20 - time schedule'!EA44","v":0},{"$f":"'K20 - time schedule'!EB44","v":0},{"$f":"'K20 - time schedule'!EC44","v":0},{"$f":"'K20 - time schedule'!ED44","v":0},{"$f":"'K20 - time schedule'!EE44","v":0},{"$f":"'K20 - time schedule'!EF44","v":0},{"$f":"'K20 - time schedule'!EG44","v":0},{"$f":"'K20 - time schedule'!EH44","v":0},{"$f":"'K20 - time schedule'!EI44","v":0},{"$f":"'K20 - time schedule'!EJ44","v":0},{"$f":"'K20 - time schedule'!EK44","v":0},{"$f":"'K20 - time schedule'!EL44","v":0},{"$f":"'K20 - time schedule'!EM44","v":0},{"$f":"'K20 - time schedule'!EN44","v":0},{"$f":"'K20 - time schedule'!EO44","v":0},{"$f":"'K20 - time schedule'!EP44","v":0},{"$f":"'K20 - time schedule'!EQ44","v":0},{"$f":"'K20 - time schedule'!ER44","v":0},{"$f":"'K20 - time schedule'!ES44","v":0},{"$f":"'K20 - time schedule'!ET44","v":0},{"$f":"'K20 - time schedule'!EU44","v":0},{"$f":"'K20 - time schedule'!EV44","v":0},{"$f":"'K20 - time schedule'!EW44","v":0},{"$f":"'K20 - time schedule'!EX44","v":0},{"$f":"'K20 - time schedule'!EY44","v":0},{"$f":"'K20 - time schedule'!EZ44","v":0},{"$f":"'K20 - time schedule'!FA44","v":0},{"$f":"'K20 - time schedule'!FB44","v":0},{"$f":"'K20 - time schedule'!FC44","v":0},{"$f":"'K20 - time schedule'!FD44","v":0},{"$f":"'K20 - time schedule'!FE44","v":0},{"$f":"'K20 - time schedule'!FF44","v":0},{"$f":"'K20 - time schedule'!FG44","v":0},{"$f":"'K20 - time schedule'!FH44","v":0},{"$f":"'K20 - time schedule'!FI44","v":0},{"$f":"'K20 - time schedule'!FJ44","v":0},{"$f":"'K20 - time schedule'!FK44","v":0},{"$f":"'K20 - time schedule'!FL44","v":0},{"$f":"'K20 - time schedule'!FM44","v":0},{"$f":"'K20 - time schedule'!FN44","v":0},{"$f":"'K20 - time schedule'!FO44","v":0},{"$f":"'K20 - time schedule'!FP44","v":0},{"$f":"'K20 - time schedule'!FQ44","v":0},{"$f":"'K20 - time schedule'!FR44","v":0},{"$f":"'K20 - time schedule'!FS44","v":0},{"$f":"'K20 - time schedule'!FT44","v":0},{"$f":"'K20 - time schedule'!FU44","v":0},{"$f":"'K20 - time schedule'!FV44","v":0},{"$f":"'K20 - time schedule'!FW44","v":0},{"$f":"'K20 - time schedule'!FX44","v":0},{"$f":"'K20 - time schedule'!FY44","v":0},{"$f":"'K20 - time schedule'!FZ44","v":0},{"$f":"'K20 - time schedule'!GA44","v":0},{"$f":"'K20 - time schedule'!GB44","v":0},{"$f":"'K20 - time schedule'!GC44","v":0},{"$f":"'K20 - time schedule'!GD44","v":0},{"$f":"'K20 - time schedule'!GE44","v":0},{"$f":"'K20 - time schedule'!GF44","v":0},{"$f":"'K20 - time schedule'!GG44","v":0},{"$f":"'K20 - time schedule'!GH27","v":0},{"$f":"'K20 - time schedule'!GI27","v":0},{"$f":"'K20 - time schedule'!GJ27","v":0},{"$f":"'K20 - time schedule'!GK27","v":0},{"$f":"'K20 - time schedule'!GL27","v":0},{"$f":"'K20 - time schedule'!GM27","v":0},{"$f":"'K20 - time schedule'!GN27","v":0},{"$f":"'K20 - time schedule'!GO27","v":0},{"$f":"'K20 - time schedule'!GP27","v":0},{"$f":"'K20 - time schedule'!GQ27","v":0},{"$f":"'K20 - time schedule'!GR27","v":0},{"$f":"'K20 - time schedule'!GS27","v":0},{"$f":"'K20 - time schedule'!GT27","v":0},{"$f":"'K20 - time schedule'!GU27","v":0},{"$f":"'K20 - time schedule'!GV27","v":0},{"$f":"'K20 - time schedule'!GW27","v":0},{"$f":"'K20 - time schedule'!GX27","v":0},{"$f":"'K20 - time schedule'!GY27","v":0},{"$f":"'K20 - time schedule'!GZ27","v":0},{"$f":"'K20 - time schedule'!HA27","v":0},{"$f":"'K20 - time schedule'!HB27","v":0},{"$f":"'K20 - time schedule'!HC27","v":0},{"$f":"'K20 - time schedule'!HD27","v":0},{"$f":"'K20 - time schedule'!HE27","v":0},{"$f":"'K20 - time schedule'!HF27","v":0},{"$f":"'K20 - time schedule'!HG27","v":0},{"$f":"'K20 - time schedule'!HH27","v":0},{"$f":"'K20 - time schedule'!HI27","v":0},{"$f":"'K20 - time schedule'!HJ27","v":0},{"$f":"'K20 - time schedule'!HK27","v":0},{"$f":"'K20 - time schedule'!HL27","v":0},{"$f":"'K20 - time schedule'!HM27","v":0},{"$f":"'K20 - time schedule'!HN27","v":0},{"$f":"'K20 - time schedule'!HO27","v":0},{"$f":"'K20 - time schedule'!HP27","v":0},{"$f":"'K20 - time schedule'!HQ27","v":0},{"$f":"'K20 - time schedule'!HR27","v":0},{"$f":"'K20 - time schedule'!HS27","v":0},{"$f":"'K20 - time schedule'!HT27","v":0},{"$f":"'K20 - time schedule'!HU27","v":0},{"$f":"'K20 - time schedule'!HV27","v":0},{"$f":"'K20 - time schedule'!HW27","v":0},{"$f":"'K20 - time schedule'!HX27","v":0},{"$f":"'K20 - time schedule'!HY27","v":0},{"$f":"'K20 - time schedule'!HZ27","v":0},{"$f":"'K20 - time schedule'!IA27","v":0},{"$f":"'K20 - time schedule'!IB27","v":0},{"$f":"'K20 - time schedule'!IC27","v":0},{"$f":"'K20 - time schedule'!ID27","v":0},{"$f":"'K20 - time schedule'!IE27","v":0},{"$f":"'K20 - time schedule'!IF27","v":0},{"$f":"'K20 - time schedule'!IG27","v":0},{"$f":"'K20 - time schedule'!IH27","v":0},{"$f":"'K20 - time schedule'!II27","v":0},{"$f":"'K20 - time schedule'!IJ27","v":0},{"$f":"'K20 - time schedule'!IK27","v":0},{"$f":"'K20 - time schedule'!IL27","v":0},{"$f":"'K20 - time schedule'!IM27","v":0},{"$f":"'K20 - time schedule'!IN27","v":0},{"$f":"'K20 - time schedule'!IO27","v":0},{"$f":"'K20 - time schedule'!IP27","v":0},{"$f":"'K20 - time schedule'!IQ27","v":0},{"$f":"'K20 - time schedule'!IR27","v":0},{"$f":"'K20 - time schedule'!IS27","v":0},{"$f":"'K20 - time schedule'!IT27","v":0},{"$f":"'K20 - time schedule'!IU27","v":0},{"$f":"'K20 - time schedule'!IV27","v":0},{"$f":"'K20 - time schedule'!IW27","v":0},{"$f":"'K20 - time schedule'!IX27","v":0},{"$f":"'K20 - time schedule'!IY27","v":0},{"$f":"'K20 - time schedule'!IZ27","v":0},{"$f":"'K20 - time schedule'!JA27","v":0},{"$f":"'K20 - time schedule'!JB27","v":0},{"$f":"'K20 - time schedule'!JC27","v":0},{"$f":"'K20 - time schedule'!JD27","v":0},{"$f":"'K20 - time schedule'!JE27","v":0},{"$f":"'K20 - time schedule'!JF27","v":0},{"$f":"'K20 - time schedule'!JG27","v":0},{"$f":"'K20 - time schedule'!JH27","v":0},{"$f":"'K20 - time schedule'!JI27","v":0},{"$f":"'K20 - time schedule'!JJ27","v":0},{"$f":"'K20 - time schedule'!JK27","v":0},{"$f":"'K20 - time schedule'!JL27","v":0},{"$f":"'K20 - time schedule'!JM27","v":0},{"$f":"'K20 - time schedule'!JN27","v":0},{"$f":"'K20 - time schedule'!JO27","v":0},{"$f":"'K20 - time schedule'!JP27","v":0},{"$f":"'K20 - time schedule'!JQ27","v":0},{"$f":"'K20 - time schedule'!JR27","v":0},{"$f":"'K20 - time schedule'!JS27","v":0},{"$f":"'K20 - time schedule'!JT27","v":0},{"$f":"'K20 - time schedule'!JU27","v":0},{"$f":"'K20 - time schedule'!JV27","v":0},{"$f":"'K20 - time schedule'!JW27","v":0},{"$f":"'K20 - time schedule'!JX27","v":0},{"$f":"'K20 - time schedule'!JY27","v":0},{"$f":"'K20 - time schedule'!JZ27","v":0},{"$f":"'K20 - time schedule'!KA27","v":0},{"$f":"'K20 - time schedule'!KB27","v":0},{"$f":"'K20 - time schedule'!KC27","v":0},{"$f":"'K20 - time schedule'!KD27","v":0},{"$f":"'K20 - time schedule'!KE27","v":0},{"$f":"'K20 - time schedule'!KF27","v":0},{"$f":"'K20 - time schedule'!KG27","v":0},{"$f":"'K20 - time schedule'!KH27","v":0},{"$f":"'K20 - time schedule'!KI27","v":0},{"$f":"'K20 - time schedule'!KJ27","v":0},{"$f":"'K20 - time schedule'!KK27","v":0},{"$f":"'K20 - time schedule'!KL27","v":0},{"$f":"'K20 - time schedule'!KM27","v":0},{"$f":"'K20 - time schedule'!KN27","v":0},{"$f":"'K20 - time schedule'!KO27","v":0},{"$f":"'K20 - time schedule'!KP27","v":0},{"$f":"'K20 - time schedule'!KQ27","v":0},{"$f":"'K20 - time schedule'!KR27","v":0},{"$f":"'K20 - time schedule'!KS27","v":0},{"$f":"'K20 - time schedule'!KT27","v":0}]
["Boiler room K20 - other above not specified items","K20",{"$f":"'K20 - time schedule'!G46","v":0},{"$f":"'K20 - time schedule'!H46","v":0},{"$f":"'K20 - time schedule'!I46","v":0},{"$f":"'K20 - time schedule'!J46","v":0},{"$f":"'K20 - time schedule'!K46","v":0},{"$f":"'K20 - time schedule'!L46","v":0},{"$f":"'K20 - time schedule'!M46","v":0},{"$f":"'K20 - time schedule'!N46","v":0},{"$f":"'K20 - time schedule'!O46","v":0},{"$f":"'K20 - time schedule'!P46","v":0},{"$f":"'K20 - time schedule'!Q46","v":0},{"$f":"'K20 - time schedule'!R46","v":0},{"$f":"'K20 - time schedule'!S46","v":0},{"$f":"'K20 - time schedule'!T46","v":0},{"$f":"'K20 - time schedule'!U46","v":0},{"$f":"'K20 - time schedule'!V46","v":0},{"$f":"'K20 - time schedule'!W46","v":0},{"$f":"'K20 - time schedule'!X46","v":0},{"$f":"'K20 - time schedule'!Y46","v":0},{"$f":"'K20 - time schedule'!Z46","v":0},{"$f":"'K20 - time schedule'!AA46","v":0},{"$f":"'K20 - time schedule'!AB46","v":0},{"$f":"'K20 - time schedule'!AC46","v":0},{"$f":"'K20 - time schedule'!AD46","v":0},{"$f":"'K20 - time schedule'!AE46","v":0},{"$f":"'K20 - time schedule'!AF46","v":0},{"$f":"'K20 - time schedule'!AG46","v":0},{"$f":"'K20 - time schedule'!AH46","v":0},{"$f":"'K20 - time schedule'!AI46","v":0},{"$f":"'K20 - time schedule'!AJ46","v":0},{"$f":"'K20 - time schedule'!AK46","v":0},{"$f":"'K20 - time schedule'!AL46","v":0},{"$f":"'K20 - time schedule'!AM46","v":0},{"$f":"'K20 - time schedule'!AN46","v":0},{"$f":"'K20 - time schedule'!AO46","v":0},{"$f":"'K20 - time schedule'!AP46","v":0},{"$f":"'K20 - time schedule'!AQ46","v":0},{"$f":"'K20 - time schedule'!AR46","v":0},{"$f":"'K20 - time schedule'!AS46","v":0},{"$f":"'K20 - time schedule'!AT46","v":0},{"$f":"'K20 - time schedule'!AU46","v":0},{"$f":"'K20 - time schedule'!AV46","v":0},{"$f":"'K20 - time schedule'!AW46","v":0},{"$f":"'K20 - time schedule'!AX46","v":0},{"$f":"'K20 - time schedule'!AY46","v":0},{"$f":"'K20 - time schedule'!AZ46","v":0},{"$f":"'K20 - time schedule'!BA46","v":0},{"$f":"'K20 - time schedule'!BB46","v":0},{"$f":"'K20 - time schedule'!BC46","v":0},{"$f":"'K20 - time schedule'!BD46","v":0},{"$f":"'K20 - time schedule'!BE46","v":0},{"$f":"'K20 - time schedule'!BF46","v":0},{"$f":"'K20 - time schedule'!BG46","v":0},{"$f":"'K20 - time schedule'!BH46","v":0},{"$f":"'K20 - time schedule'!BI46","v":0},{"$f":"'K20 - time schedule'!BJ46","v":0},{"$f":"'K20 - time schedule'!BK46","v":0},{"$f":"'K20 - time schedule'!BL46","v":0},{"$f":"'K20 - time schedule'!BM46","v":0},{"$f":"'K20 - time schedule'!BN46","v":0},{"$f":"'K20 - time schedule'!BO46","v":0},{"$f":"'K20 - time schedule'!BP46","v":0},{"$f":"'K20 - time schedule'!BQ46","v":0},{"$f":"'K20 - time schedule'!BR46","v":0},{"$f":"'K20 - time schedule'!BS46","v":0},{"$f":"'K20 - time schedule'!BT46","v":0},{"$f":"'K20 - time schedule'!BU46","v":0},{"$f":"'K20 - time schedule'!BV46","v":0},{"$f":"'K20 - time schedule'!BW46","v":0},{"$f":"'K20 - time schedule'!BX46","v":0},{"$f":"'K20 - time schedule'!BY46","v":0},{"$f":"'K20 - time schedule'!BZ46","v":0},{"$f":"'K20 - time schedule'!CA46","v":0},{"$f":"'K20 - time schedule'!CB46","v":0},{"$f":"'K20 - time schedule'!CC46","v":0},{"$f":"'K20 - time schedule'!CD46","v":0},{"$f":"'K20 - time schedule'!CE46","v":0},{"$f":"'K20 - time schedule'!CF46","v":0},{"$f":"'K20 - time schedule'!CG46","v":0},{"$f":"'K20 - time schedule'!CH46","v":0},{"$f":"'K20 - time schedule'!CI46","v":0},{"$f":"'K20 - time schedule'!CJ46","v":0},{"$f":"'K20 - time schedule'!CK46","v":0},{"$f":"'K20 - time schedule'!CL46","v":0},{"$f":"'K20 - time schedule'!CM46","v":0},{"$f":"'K20 - time schedule'!CN46","v":0},{"$f":"'K20 - time schedule'!CO46","v":0},{"$f":"'K20 - time schedule'!CP46","v":0},{"$f":"'K20 - time schedule'!CQ46","v":0},{"$f":"'K20 - time schedule'!CR46","v":0},{"$f":"'K20 - time schedule'!CS46","v":0},{"$f":"'K20 - time schedule'!CT46","v":0},{"$f":"'K20 - time schedule'!CU46","v":0},{"$f":"'K20 - time schedule'!CV46","v":0},{"$f":"'K20 - time schedule'!CW46","v":0},{"$f":"'K20 - time schedule'!CX46","v":0},{"$f":"'K20 - time schedule'!CY46","v":0},{"$f":"'K20 - time schedule'!CZ46","v":0},{"$f":"'K20 - time schedule'!DA46","v":0},{"$f":"'K20 - time schedule'!DB46","v":0},{"$f":"'K20 - time schedule'!DC46","v":0},{"$f":"'K20 - time schedule'!DD46","v":0},{"$f":"'K20 - time schedule'!DE46","v":0},{"$f":"'K20 - time schedule'!DF46","v":0},{"$f":"'K20 - time schedule'!DG46","v":0},{"$f":"'K20 - time schedule'!DH46","v":0},{"$f":"'K20 - time schedule'!DI46","v":0},{"$f":"'K20 - time schedule'!DJ46","v":0},{"$f":"'K20 - time schedule'!DK46","v":0},{"$f":"'K20 - time schedule'!DL46","v":0},{"$f":"'K20 - time schedule'!DM46","v":0},{"$f":"'K20 - time schedule'!DN46","v":0},{"$f":"'K20 - time schedule'!DO46","v":0},{"$f":"'K20 - time schedule'!DP46","v":0},{"$f":"'K20 - time schedule'!DQ46","v":0},{"$f":"'K20 - time schedule'!DR46","v":0},{"$f":"'K20 - time schedule'!DS46","v":0},{"$f":"'K20 - time schedule'!DT46","v":0},{"$f":"'K20 - time schedule'!DU46","v":0},{"$f":"'K20 - time schedule'!DV46","v":0},{"$f":"'K20 - time schedule'!DW46","v":0},{"$f":"'K20 - time schedule'!DX46","v":0},{"$f":"'K20 - time schedule'!DY46","v":0},{"$f":"'K20 - time schedule'!DZ46","v":0},{"$f":"'K20 - time schedule'!EA46","v":0},{"$f":"'K20 - time schedule'!EB46","v":0},{"$f":"'K20 - time schedule'!EC46","v":0},{"$f":"'K20 - time schedule'!ED46","v":0},{"$f":"'K20 - time schedule'!EE46","v":0},{"$f":"'K20 - time schedule'!EF46","v":0},{"$f":"'K20 - time schedule'!EG46","v":0},{"$f":"'K20 - time schedule'!EH46","v":0},{"$f":"'K20 - time schedule'!EI46","v":0},{"$f":"'K20 - time schedule'!EJ46","v":0},{"$f":"'K20 - time schedule'!EK46","v":0},{"$f":"'K20 - time schedule'!EL46","v":0},{"$f":"'K20 - time schedule'!EM46","v":0},{"$f":"'K20 - time schedule'!EN46","v":0},{"$f":"'K20 - time schedule'!EO46","v":0},{"$f":"'K20 - time schedule'!EP46","v":0},{"$f":"'K20 - time schedule'!EQ46","v":0},{"$f":"'K20 - time schedule'!ER46","v":0},{"$f":"'K20 - time schedule'!ES46","v":0},{"$f":"'K20 - time schedule'!ET46","v":0},{"$f":"'K20 - time schedule'!EU46","v":0},{"$f":"'K20 - time schedule'!EV46","v":0},{"$f":"'K20 - time schedule'!EW46","v":0},{"$f":"'K20 - time schedule'!EX46","v":0},{"$f":"'K20 - time schedule'!EY46","v":0},{"$f":"'K20 - time schedule'!EZ46","v":0},{"$f":"'K20 - time schedule'!FA46","v":0},{"$f":"'K20 - time schedule'!FB46","v":0},{"$f":"'K20 - time schedule'!FC46","v":0},{"$f":"'K20 - time schedule'!FD46","v":0},{"$f":"'K20 - time schedule'!FE46","v":0},{"$f":"'K20 - time schedule'!FF46","v":0},{"$f":"'K20 - time schedule'!FG46","v":0},{"$f":"'K20 - time schedule'!FH46","v":0},{"$f":"'K20 - time schedule'!FI46","v":0},{"$f":"'K20 - time schedule'!FJ46","v":0},{"$f":"'K20 - time schedule'!FK46","v":0},{"$f":"'K20 - time schedule'!FL46","v":0},{"$f":"'K20 - time schedule'!FM46","v":0},{"$f":"'K20 - time schedule'!FN46","v":0},{"$f":"'K20 - time schedule'!FO46","v":0},{"$f":"'K20 - time schedule'!FP46","v":0},{"$f":"'K20 - time schedule'!FQ46","v":0},{"$f":"'K20 - time schedule'!FR46","v":0},{"$f":"'K20 - time schedule'!FS46","v":0},{"$f":"'K20 - time schedule'!FT46","v":0},{"$f":"'K20 - time schedule'!FU46","v":0},{"$f":"'K20 - time schedule'!FV46","v":0},{"$f":"'K20 - time schedule'!FW46","v":0},{"$f":"'K20 - time schedule'!FX46","v":0},{"$f":"'K20 - time schedule'!FY46","v":0},{"$f":"'K20 - time schedule'!FZ46","v":0},{"$f":"'K20 - time schedule'!GA46","v":0},{"$f":"'K20 - time schedule'!GB46","v":0},{"$f":"'K20 - time schedule'!GC46","v":0},{"$f":"'K20 - time schedule'!GD46","v":0},{"$f":"'K20 - time schedule'!GE46","v":0},{"$f":"'K20 - time schedule'!GF46","v":0},{"$f":"'K20 - time schedule'!GG46","v":0},{"$f":"'K20 - time schedule'!GH28","v":0},{"$f":"'K20 - time schedule'!GI28","v":0},{"$f":"'K20 - time schedule'!GJ28","v":0},{"$f":"'K20 - time schedule'!GK28","v":0},{"$f":"'K20 - time schedule'!GL28","v":0},{"$f":"'K20 - time schedule'!GM28","v":0},{"$f":"'K20 - time schedule'!GN28","v":0},{"$f":"'K20 - time schedule'!GO28","v":0},{"$f":"'K20 - time schedule'!GP28","v":0},{"$f":"'K20 - time schedule'!GQ28","v":0},{"$f":"'K20 - time schedule'!GR28","v":0},{"$f":"'K20 - time schedule'!GS28","v":0},{"$f":"'K20 - time schedule'!GT28","v":0},{"$f":"'K20 - time schedule'!GU28","v":0},{"$f":"'K20 - time schedule'!GV28","v":0},{"$f":"'K20 - time schedule'!GW28","v":0},{"$f":"'K20 - time schedule'!GX28","v":0},{"$f":"'K20 - time schedule'!GY28","v":0},{"$f":"'K20 - time schedule'!GZ28","v":0},{"$f":"'K20 - time schedule'!HA28","v":0},{"$f":"'K20 - time schedule'!HB28","v":0},{"$f":"'K20 - time schedule'!HC28","v":0},{"$f":"'K20 - time schedule'!HD28","v":0},{"$f":"'K20 - time schedule'!HE28","v":0},{"$f":"'K20 - time schedule'!HF28","v":0},{"$f":"'K20 - time schedule'!HG28","v":0},{"$f":"'K20 - time schedule'!HH28","v":0},{"$f":"'K20 - time schedule'!HI28","v":0},{"$f":"'K20 - time schedule'!HJ28","v":0},{"$f":"'K20 - time schedule'!HK28","v":0},{"$f":"'K20 - time schedule'!HL28","v":0},{"$f":"'K20 - time schedule'!HM28","v":0},{"$f":"'K20 - time schedule'!HN28","v":0},{"$f":"'K20 - time schedule'!HO28","v":0},{"$f":"'K20 - time schedule'!HP28","v":0},{"$f":"'K20 - time schedule'!HQ28","v":0},{"$f":"'K20 - time schedule'!HR28","v":0},{"$f":"'K20 - time schedule'!HS28","v":0},{"$f":"'K20 - time schedule'!HT28","v":0},{"$f":"'K20 - time schedule'!HU28","v":0},{"$f":"'K20 - time schedule'!HV28","v":0},{"$f":"'K20 - time schedule'!HW28","v":0},{"$f":"'K20 - time schedule'!HX28","v":0},{"$f":"'K20 - time schedule'!HY28","v":0},{"$f":"'K20 - time schedule'!HZ28","v":0},{"$f":"'K20 - time schedule'!IA28","v":0},{"$f":"'K20 - time schedule'!IB28","v":0},{"$f":"'K20 - time schedule'!IC28","v":0},{"$f":"'K20 - time schedule'!ID28","v":0},{"$f":"'K20 - time schedule'!IE28","v":0},{"$f":"'K20 - time schedule'!IF28","v":0},{"$f":"'K20 - time schedule'!IG28","v":0},{"$f":"'K20 - time schedule'!IH28","v":0},{"$f":"'K20 - time schedule'!II28","v":0},{"$f":"'K20 - time schedule'!IJ28","v":0},{"$f":"'K20 - time schedule'!IK28","v":0},{"$f":"'K20 - time schedule'!IL28","v":0},{"$f":"'K20 - time schedule'!IM28","v":0},{"$f":"'K20 - time schedule'!IN28","v":0},{"$f":"'K20 - time schedule'!IO28","v":0},{"$f":"'K20 - time schedule'!IP28","v":0},{"$f":"'K20 - time schedule'!IQ28","v":0},{"$f":"'K20 - time schedule'!IR28","v":0},{"$f":"'K20 - time schedule'!IS28","v":0},{"$f":"'K20 - time schedule'!IT28","v":0},{"$f":"'K20 - time schedule'!IU28","v":0},{"$f":"'K20 - time schedule'!IV28","v":0},{"$f":"'K20 - time schedule'!IW28","v":0},{"$f":"'K20 - time schedule'!IX28","v":0},{"$f":"'K20 - time schedule'!IY28","v":0},{"$f":"'K20 - time schedule'!IZ28","v":0},{"$f":"'K20 - time schedule'!JA28","v":0},{"$f":"'K20 - time schedule'!JB28","v":0},{"$f":"'K20 - time schedule'!JC28","v":0},{"$f":"'K20 - time schedule'!JD28","v":0},{"$f":"'K20 - time schedule'!JE28","v":0},{"$f":"'K20 - time schedule'!JF28","v":0},{"$f":"'K20 - time schedule'!JG28","v":0},{"$f":"'K20 - time schedule'!JH28","v":0},{"$f":"'K20 - time schedule'!JI28","v":0},{"$f":"'K20 - time schedule'!JJ28","v":0},{"$f":"'K20 - time schedule'!JK28","v":0},{"$f":"'K20 - time schedule'!JL28","v":0},{"$f":"'K20 - time schedule'!JM28","v":0},{"$f":"'K20 - time schedule'!JN28","v":0},{"$f":"'K20 - time schedule'!JO28","v":0},{"$f":"'K20 - time schedule'!JP28","v":0},{"$f":"'K20 - time schedule'!JQ28","v":0},{"$f":"'K20 - time schedule'!JR28","v":0},{"$f":"'K20 - time schedule'!JS28","v":0},{"$f":"'K20 - time schedule'!JT28","v":0},{"$f":"'K20 - time schedule'!JU28","v":0},{"$f":"'K20 - time schedule'!JV28","v":0},{"$f":"'K20 - time schedule'!JW28","v":0},{"$f":"'K20 - time schedule'!JX28","v":0},{"$f":"'K20 - time schedule'!JY28","v":0},{"$f":"'K20 - time schedule'!JZ28","v":0},{"$f":"'K20 - time schedule'!KA28","v":0},{"$f":"'K20 - time schedule'!KB28","v":0},{"$f":"'K20 - time schedule'!KC28","v":0},{"$f":"'K20 - time schedule'!KD28","v":0},{"$f":"'K20 - time schedule'!KE28","v":0},{"$f":"'K20 - time schedule'!KF28","v":0},{"$f":"'K20 - time schedule'!KG28","v":0},{"$f":"'K20 - time schedule'!KH28","v":0},{"$f":"'K20 - time schedule'!KI28","v":0},{"$f":"'K20 - time schedule'!KJ28","v":0},{"$f":"'K20 - time schedule'!KK28","v":0},{"$f":"'K20 - time schedule'!KL28","v":0},{"$f":"'K20 - time schedule'!KM28","v":0},{"$f":"'K20 - time schedule'!KN28","v":0},{"$f":"'K20 - time schedule'!KO28","v":0},{"$f":"'K20 - time schedule'!KP28","v":0},{"$f":"'K20 - time schedule'!KQ28","v":0},{"$f":"'K20 - time schedule'!KR28","v":0},{"$f":"'K20 - time schedule'!KS28","v":0},{"$f":"'K20 - time schedule'!KT28","v":0}]
["Boiler room K20 - completion of construction works","K20",{"$f":"'K20 - time schedule'!G48","v":0},{"$f":"'K20 - time schedule'!H48","v":0},{"$f":"'K20 - time schedule'!I48","v":0},{"$f":"'K20 - time schedule'!J48","v":0},{"$f":"'K20 - time schedule'!K48","v":0},{"$f":"'K20 - time schedule'!L48","v":0},{"$f":"'K20 - time schedule'!M48","v":0},{"$f":"'K20 - time schedule'!N48","v":0},{"$f":"'K20 - time schedule'!O48","v":0},{"$f":"'K20 - time schedule'!P48","v":0},{"$f":"'K20 - time schedule'!Q48","v":0},{"$f":"'K20 - time schedule'!R48","v":0},{"$f":"'K20 - time schedule'!S48","v":0},{"$f":"'K20 - time schedule'!T48","v":0},{"$f":"'K20 - time schedule'!U48","v":0},{"$f":"'K20 - time schedule'!V48","v":0},{"$f":"'K20 - time schedule'!W48","v":0},{"$f":"'K20 - time schedule'!X48","v":0},{"$f":"'K20 - time schedule'!Y48","v":0},{"$f":"'K20 - time schedule'!Z48","v":0},{"$f":"'K20 - time schedule'!AA48","v":0},{"$f":"'K20 - time schedule'!AB48","v":0},{"$f":"'K20 - time schedule'!AC48","v":0},{"$f":"'K20 - time schedule'!AD48","v":0},{"$f":"'K20 - time schedule'!AE48","v":0},{"$f":"'K20 - time schedule'!AF48","v":0},{"$f":"'K20 - time schedule'!AG48","v":0},{"$f":"'K20 - time schedule'!AH48","v":0},{"$f":"'K20 - time schedule'!AI48","v":0},{"$f":"'K20 - time schedule'!AJ48","v":0},{"$f":"'K20 - time schedule'!AK48","v":0},{"$f":"'K20 - time schedule'!AL48","v":0},{"$f":"'K20 - time schedule'!AM48","v":0},{"$f":"'K20 - time schedule'!AN48","v":0},{"$f":"'K20 - time schedule'!AO48","v":0},{"$f":"'K20 - time schedule'!AP48","v":0},{"$f":"'K20 - time schedule'!AQ48","v":0},{"$f":"'K20 - time schedule'!AR48","v":0},{"$f":"'K20 - time schedule'!AS48","v":0},{"$f":"'K20 - time schedule'!AT48","v":0},{"$f":"'K20 - time schedule'!AU48","v":0},{"$f":"'K20 - time schedule'!AV48","v":0},{"$f":"'K20 - time schedule'!AW48","v":0},{"$f":"'K20 - time schedule'!AX48","v":0},{"$f":"'K20 - time schedule'!AY48","v":0},{"$f":"'K20 - time schedule'!AZ48","v":0},{"$f":"'K20 - time schedule'!BA48","v":0},{"$f":"'K20 - time schedule'!BB48","v":0},{"$f":"'K20 - time schedule'!BC48","v":0},{"$f":"'K20 - time schedule'!BD48","v":0},{"$f":"'K20 - time schedule'!BE48","v":0},{"$f":"'K20 - time schedule'!BF48","v":0},{"$f":"'K20 - time schedule'!BG48","v":0},{"$f":"'K20 - time schedule'!BH48","v":0},{"$f":"'K20 - time schedule'!BI48","v":0},{"$f":"'K20 - time schedule'!BJ48","v":0},{"$f":"'K20 - time schedule'!BK48","v":0},{"$f":"'K20 - time schedule'!BL48","v":0},{"$f":"'K20 - time schedule'!BM48","v":0},{"$f":"'K20 - time schedule'!BN48","v":0},{"$f":"'K20 - time schedule'!BO48","v":0},{"$f":"'K20 - time schedule'!BP48","v":0},{"$f":"'K20 - time schedule'!BQ48","v":0},{"$f":"'K20 - time schedule'!BR48","v":0},{"$f":"'K20 - time schedule'!BS48","v":0},{"$f":"'K20 - time schedule'!BT48","v":0},{"$f":"'K20 - time schedule'!BU48","v":0},{"$f":"'K20 - time schedule'!BV48","v":0},{"$f":"'K20 - time schedule'!BW48","v":0},{"$f":"'K20 - time schedule'!BX48","v":0},{"$f":"'K20 - time schedule'!BY48","v":0},{"$f":"'K20 - time schedule'!BZ48","v":0},{"$f":"'K20 - time schedule'!CA48","v":0},{"$f":"'K20 - time schedule'!CB48","v":0},{"$f":"'K20 - time schedule'!CC48","v":0},{"$f":"'K20 - time schedule'!CD48","v":0},{"$f":"'K20 - time schedule'!CE48","v":0},{"$f":"'K20 - time schedule'!CF48","v":0},{"$f":"'K20 - time schedule'!CG48","v":0},{"$f":"'K20 - time schedule'!CH48","v":0},{"$f":"'K20 - time schedule'!CI48","v":0},{"$f":"'K20 - time schedule'!CJ48","v":0},{"$f":"'K20 - time schedule'!CK48","v":0},{"$f":"'K20 - time schedule'!CL48","v":0},{"$f":"'K20 - time schedule'!CM48","v":0},{"$f":"'K20 - time schedule'!CN48","v":0},{"$f":"'K20 - time schedule'!CO48","v":0},{"$f":"'K20 - time schedule'!CP48","v":0},{"$f":"'K20 - time schedule'!CQ48","v":0},{"$f":"'K20 - time schedule'!CR48","v":0},{"$f":"'K20 - time schedule'!CS48","v":0},{"$f":"'K20 - time schedule'!CT48","v":0},{"$f":"'K20 - time schedule'!CU48","v":0},{"$f":"'K20 - time schedule'!CV48","v":0},{"$f":"'K20 - time schedule'!CW48","v":0},{"$f":"'K20 - time schedule'!CX48","v":0},{"$f":"'K20 - time schedule'!CY48","v":0},{"$f":"'K20 - time schedule'!CZ48","v":0},{"$f":"'K20 - time schedule'!DA48","v":0},{"$f":"'K20 - time schedule'!DB48","v":0},{"$f":"'K20 - time schedule'!DC48","v":0},{"$f":"'K20 - time schedule'!DD48","v":0},{"$f":"'K20 - time schedule'!DE48","v":0},{"$f":"'K20 - time schedule'!DF48","v":0},{"$f":"'K20 - time schedule'!DG48","v":0},{"$f":"'K20 - time schedule'!DH48","v":0},{"$f":"'K20 - time schedule'!DI48","v":0},{"$f":"'K20 - time schedule'!DJ48","v":0},{"$f":"'K20 - time schedule'!DK48","v":0},{"$f":"'K20 - time schedule'!DL48","v":0},{"$f":"'K20 - time schedule'!DM48","v":0},{"$f":"'K20 - time schedule'!DN48","v":0},{"$f":"'K20 - time schedule'!DO48","v":0},{"$f":"'K20 - time schedule'!DP48","v":0},{"$f":"'K20 - time schedule'!DQ48","v":0},{"$f":"'K20 - time schedule'!DR48","v":0},{"$f":"'K20 - time schedule'!DS48","v":0},{"$f":"'K20 - time schedule'!DT48","v":0},{"$f":"'K20 - time schedule'!DU48","v":0},{"$f":"'K20 - time schedule'!DV48","v":0},{"$f":"'K20 - time schedule'!DW48","v":0},{"$f":"'K20 - time schedule'!DX48","v":0},{"$f":"'K20 - time schedule'!DY48","v":0},{"$f":"'K20 - time schedule'!DZ48","v":0},{"$f":"'K20 - time schedule'!EA48","v":0},{"$f":"'K20 - time schedule'!EB48","v":0},{"$f":"'K20 - time schedule'!EC48","v":0},{"$f":"'K20 - time schedule'!ED48","v":0},{"$f":"'K20 - time schedule'!EE48","v":0},{"$f":"'K20 - time schedule'!EF48","v":0},{"$f":"'K20 - time schedule'!EG48","v":0},{"$f":"'K20 - time schedule'!EH48","v":0},{"$f":"'K20 - time schedule'!EI48","v":0},{"$f":"'K20 - time schedule'!EJ48","v":0},{"$f":"'K20 - time schedule'!EK48","v":0},{"$f":"'K20 - time schedule'!EL48","v":0},{"$f":"'K20 - time schedule'!EM48","v":0},{"$f":"'K20 - time schedule'!EN48","v":0},{"$f":"'K20 - time schedule'!EO48","v":0},{"$f":"'K20 - time schedule'!EP48","v":0},{"$f":"'K20 - time schedule'!EQ48","v":0},{"$f":"'K20 - time schedule'!ER48","v":0},{"$f":"'K20 - time schedule'!ES48","v":0},{"$f":"'K20 - time schedule'!ET48","v":0},{"$f":"'K20 - time schedule'!EU48","v":0},{"$f":"'K20 - time schedule'!EV48","v":0},{"$f":"'K20 - time schedule'!EW48","v":0},{"$f":"'K20 - time schedule'!EX48","v":0},{"$f":"'K20 - time schedule'!EY48","v":0},{"$f":"'K20 - time schedule'!EZ48","v":0},{"$f":"'K20 - time schedule'!FA48","v":0},{"$f":"'K20 - time schedule'!FB48","v":0},{"$f":"'K20 - time schedule'!FC48","v":0},{"$f":"'K20 - time schedule'!FD48","v":0},{"$f":"'K20 - time schedule'!FE48","v":0},{"$f":"'K20 - time schedule'!FF48","v":0},{"$f":"'K20 - time schedule'!FG48","v":0},{"$f":"'K20 - time schedule'!FH48","v":0},{"$f":"'K20 - time schedule'!FI48","v":0},{"$f":"'K20 - time schedule'!FJ48","v":0},{"$f":"'K20 - time schedule'!FK48","v":0},{"$f":"'K20 - time schedule'!FL48","v":0},{"$f":"'K20 - time schedule'!FM48","v":0},{"$f":"'K20 - time schedule'!FN48","v":0},{"$f":"'K20 - time schedule'!FO48","v":0},{"$f":"'K20 - time schedule'!FP48","v":0},{"$f":"'K20 - time schedule'!FQ48","v":0},{"$f":"'K20 - time schedule'!FR48","v":0},{"$f":"'K20 - time schedule'!FS48","v":0},{"$f":"'K20 - time schedule'!FT48","v":0},{"$f":"'K20 - time schedule'!FU48","v":0},{"$f":"'K20 - time schedule'!FV48","v":0},{"$f":"'K20 - time schedule'!FW48","v":0},{"$f":"'K20 - time schedule'!FX48","v":0},{"$f":"'K20 - time schedule'!FY48","v":0},{"$f":"'K20 - time schedule'!FZ48","v":0},{"$f":"'K20 - time schedule'!GA48","v":0},{"$f":"'K20 - time schedule'!GB48","v":0},{"$f":"'K20 - time schedule'!GC48","v":0},{"$f":"'K20 - time schedule'!GD48","v":0},{"$f":"'K20 - time schedule'!GE48","v":0},{"$f":"'K20 - time schedule'!GF48","v":0},{"$f":"'K20 - time schedule'!GG48","v":0},{"$f":"'K20 - time schedule'!GH29","v":0},{"$f":"'K20 - time schedule'!GI29","v":0},{"$f":"'K20 - time schedule'!GJ29","v":0},{"$f":"'K20 - time schedule'!GK29","v":0},{"$f":"'K20 - time schedule'!GL29","v":0},{"$f":"'K20 - time schedule'!GM29","v":0},{"$f":"'K20 - time schedule'!GN29","v":0},{"$f":"'K20 - time schedule'!GO29","v":0},{"$f":"'K20 - time schedule'!GP29","v":0},{"$f":"'K20 - time schedule'!GQ29","v":0},{"$f":"'K20 - time schedule'!GR29","v":0},{"$f":"'K20 - time schedule'!GS29","v":0},{"$f":"'K20 - time schedule'!GT29","v":0},{"$f":"'K20 - time schedule'!GU29","v":0},{"$f":"'K20 - time schedule'!GV29","v":0},{"$f":"'K20 - time schedule'!GW29","v":0},{"$f":"'K20 - time schedule'!GX29","v":0},{"$f":"'K20 - time schedule'!GY29","v":0},{"$f":"'K20 - time schedule'!GZ29","v":0},{"$f":"'K20 - time schedule'!HA29","v":0},{"$f":"'K20 - time schedule'!HB29","v":0},{"$f":"'K20 - time schedule'!HC29","v":0},{"$f":"'K20 - time schedule'!HD29","v":0},{"$f":"'K20 - time schedule'!HE29","v":0},{"$f":"'K20 - time schedule'!HF29","v":0},{"$f":"'K20 - time schedule'!HG29","v":0},{"$f":"'K20 - time schedule'!HH29","v":0},{"$f":"'K20 - time schedule'!HI29","v":0},{"$f":"'K20 - time schedule'!HJ29","v":0},{"$f":"'K20 - time schedule'!HK29","v":0},{"$f":"'K20 - time schedule'!HL29","v":0},{"$f":"'K20 - time schedule'!HM29","v":0},{"$f":"'K20 - time schedule'!HN29","v":0},{"$f":"'K20 - time schedule'!HO29","v":0},{"$f":"'K20 - time schedule'!HP29","v":0},{"$f":"'K20 - time schedule'!HQ29","v":0},{"$f":"'K20 - time schedule'!HR29","v":0},{"$f":"'K20 - time schedule'!HS29","v":0},{"$f":"'K20 - time schedule'!HT29","v":0},{"$f":"'K20 - time schedule'!HU29","v":0},{"$f":"'K20 - time schedule'!HV29","v":0},{"$f":"'K20 - time schedule'!HW29","v":0},{"$f":"'K20 - time schedule'!HX29","v":0},{"$f":"'K20 - time schedule'!HY29","v":0},{"$f":"'K20 - time schedule'!HZ29","v":0},{"$f":"'K20 - time schedule'!IA29","v":0},{"$f":"'K20 - time schedule'!IB29","v":0},{"$f":"'K20 - time schedule'!IC29","v":0},{"$f":"'K20 - time schedule'!ID29","v":0},{"$f":"'K20 - time schedule'!IE29","v":0},{"$f":"'K20 - time schedule'!IF29","v":0},{"$f":"'K20 - time schedule'!IG29","v":0},{"$f":"'K20 - time schedule'!IH29","v":0},{"$f":"'K20 - time schedule'!II29","v":0},{"$f":"'K20 - time schedule'!IJ29","v":0},{"$f":"'K20 - time schedule'!IK29","v":0},{"$f":"'K20 - time schedule'!IL29","v":0},{"$f":"'K20 - time schedule'!IM29","v":0},{"$f":"'K20 - time schedule'!IN29","v":0},{"$f":"'K20 - time schedule'!IO29","v":0},{"$f":"'K20 - time schedule'!IP29","v":0},{"$f":"'K20 - time schedule'!IQ29","v":0},{"$f":"'K20 - time schedule'!IR29","v":0},{"$f":"'K20 - time schedule'!IS29","v":0},{"$f":"'K20 - time schedule'!IT29","v":0},{"$f":"'K20 - time schedule'!IU29","v":0},{"$f":"'K20 - time schedule'!IV29","v":0},{"$f":"'K20 - time schedule'!IW29","v":0},{"$f":"'K20 - time schedule'!IX29","v":0},{"$f":"'K20 - time schedule'!IY29","v":0},{"$f":"'K20 - time schedule'!IZ29","v":0},{"$f":"'K20 - time schedule'!JA29","v":0},{"$f":"'K20 - time schedule'!JB29","v":0},{"$f":"'K20 - time schedule'!JC29","v":0},{"$f":"'K20 - time schedule'!JD29","v":0},{"$f":"'K20 - time schedule'!JE29","v":0},{"$f":"'K20 - time schedule'!JF29","v":0},{"$f":"'K20 - time schedule'!JG29","v":0},{"$f":"'K20 - time schedule'!JH29","v":0},{"$f":"'K20 - time schedule'!JI29","v":0},{"$f":"'K20 - time schedule'!JJ29","v":0},{"$f":"'K20 - time schedule'!JK29","v":0},{"$f":"'K20 - time schedule'!JL29","v":0},{"$f":"'K20 - time schedule'!JM29","v":0},{"$f":"'K20 - time schedule'!JN29","v":0},{"$f":"'K20 - time schedule'!JO29","v":0},{"$f":"'K20 - time schedule'!JP29","v":0},{"$f":"'K20 - time schedule'!JQ29","v":0},{"$f":"'K20 - time schedule'!JR29","v":0},{"$f":"'K20 - time schedule'!JS29","v":0},{"$f":"'K20 - time schedule'!JT29","v":0},{"$f":"'K20 - time schedule'!JU29","v":0},{"$f":"'K20 - time schedule'!JV29","v":0},{"$f":"'K20 - time schedule'!JW29","v":0},{"$f":"'K20 - time schedule'!JX29","v":0},{"$f":"'K20 - time schedule'!JY29","v":0},{"$f":"'K20 - time schedule'!JZ29","v":0},{"$f":"'K20 - time schedule'!KA29","v":0},{"$f":"'K20 - time schedule'!KB29","v":0},{"$f":"'K20 - time schedule'!KC29","v":0},{"$f":"'K20 - time schedule'!KD29","v":0},{"$f":"'K20 - time schedule'!KE29","v":0},{"$f":"'K20 - time schedule'!KF29","v":0},{"$f":"'K20 - time schedule'!KG29","v":0},{"$f":"'K20 - time schedule'!KH29","v":0},{"$f":"'K20 - time schedule'!KI29","v":0},{"$f":"'K20 - time schedule'!KJ29","v":0},{"$f":"'K20 - time schedule'!KK29","v":0},{"$f":"'K20 - time schedule'!KL29","v":0},{"$f":"'K20 - time schedule'!KM29","v":0},{"$f":"'K20 - time schedule'!KN29","v":0},{"$f":"'K20 - time schedule'!KO29","v":0},{"$f":"'K20 - time schedule'!KP29","v":0},{"$f":"'K20 - time schedule'!KQ29","v":0},{"$f":"'K20 - time schedule'!KR29","v":0},{"$f":"'K20 - time schedule'!KS29","v":0},{"$f":"'K20 - time schedule'!KT29","v":0}]
["Boiler room K20 - completion of installation works","K20",{"$f":"'K20 - time schedule'!G49","v":0},{"$f":"'K20 - time schedule'!H49","v":0},{"$f":"'K20 - time schedule'!I49","v":0},{"$f":"'K20 - time schedule'!J49","v":0},{"$f":"'K20 - time schedule'!K49","v":0},{"$f":"'K20 - time schedule'!L49","v":0},{"$f":"'K20 - time schedule'!M49","v":0},{"$f":"'K20 - time schedule'!N49","v":0},{"$f":"'K20 - time schedule'!O49","v":0},{"$f":"'K20 - time schedule'!P49","v":0},{"$f":"'K20 - time schedule'!Q49","v":0},{"$f":"'K20 - time schedule'!R49","v":0},{"$f":"'K20 - time schedule'!S49","v":0},{"$f":"'K20 - time schedule'!T49","v":0},{"$f":"'K20 - time schedule'!U49","v":0},{"$f":"'K20 - time schedule'!V49","v":0},{"$f":"'K20 - time schedule'!W49","v":0},{"$f":"'K20 - time schedule'!X49","v":0},{"$f":"'K20 - time schedule'!Y49","v":0},{"$f":"'K20 - time schedule'!Z49","v":0},{"$f":"'K20 - time schedule'!AA49","v":0},{"$f":"'K20 - time schedule'!AB49","v":0},{"$f":"'K20 - time schedule'!AC49","v":0},{"$f":"'K20 - time schedule'!AD49","v":0},{"$f":"'K20 - time schedule'!AE49","v":0},{"$f":"'K20 - time schedule'!AF49","v":0},{"$f":"'K20 - time schedule'!AG49","v":0},{"$f":"'K20 - time schedule'!AH49","v":0},{"$f":"'K20 - time schedule'!AI49","v":0},{"$f":"'K20 - time schedule'!AJ49","v":0},{"$f":"'K20 - time schedule'!AK49","v":0},{"$f":"'K20 - time schedule'!AL49","v":0},{"$f":"'K20 - time schedule'!AM49","v":0},{"$f":"'K20 - time schedule'!AN49","v":0},{"$f":"'K20 - time schedule'!AO49","v":0},{"$f":"'K20 - time schedule'!AP49","v":0},{"$f":"'K20 - time schedule'!AQ49","v":0},{"$f":"'K20 - time schedule'!AR49","v":0},{"$f":"'K20 - time schedule'!AS49","v":0},{"$f":"'K20 - time schedule'!AT49","v":0},{"$f":"'K20 - time schedule'!AU49","v":0},{"$f":"'K20 - time schedule'!AV49","v":0},{"$f":"'K20 - time schedule'!AW49","v":0},{"$f":"'K20 - time schedule'!AX49","v":0},{"$f":"'K20 - time schedule'!AY49","v":0},{"$f":"'K20 - time schedule'!AZ49","v":0},{"$f":"'K20 - time schedule'!BA49","v":0},{"$f":"'K20 - time schedule'!BB49","v":0},{"$f":"'K20 - time schedule'!BC49","v":0},{"$f":"'K20 - time schedule'!BD49","v":0},{"$f":"'K20 - time schedule'!BE49","v":0},{"$f":"'K20 - time schedule'!BF49","v":0},{"$f":"'K20 - time schedule'!BG49","v":0},{"$f":"'K20 - time schedule'!BH49","v":0},{"$f":"'K20 - time schedule'!BI49","v":0},{"$f":"'K20 - time schedule'!BJ49","v":0},{"$f":"'K20 - time schedule'!BK49","v":0},{"$f":"'K20 - time schedule'!BL49","v":0},{"$f":"'K20 - time schedule'!BM49","v":0},{"$f":"'K20 - time schedule'!BN49","v":0},{"$f":"'K20 - time schedule'!BO49","v":0},{"$f":"'K20 - time schedule'!BP49","v":0},{"$f":"'K20 - time schedule'!BQ49","v":0},{"$f":"'K20 - time schedule'!BR49","v":0},{"$f":"'K20 - time schedule'!BS49","v":0},{"$f":"'K20 - time schedule'!BT49","v":0},{"$f":"'K20 - time schedule'!BU49","v":0},{"$f":"'K20 - time schedule'!BV49","v":0},{"$f":"'K20 - time schedule'!BW49","v":0},{"$f":"'K20 - time schedule'!BX49","v":0},{"$f":"'K20 - time schedule'!BY49","v":0},{"$f":"'K20 - time schedule'!BZ49","v":0},{"$f":"'K20 - time schedule'!CA49","v":0},{"$f":"'K20 - time schedule'!CB49","v":0},{"$f":"'K20 - time schedule'!CC49","v":0},{"$f":"'K20 - time schedule'!CD49","v":0},{"$f":"'K20 - time schedule'!CE49","v":0},{"$f":"'K20 - time schedule'!CF49","v":0},{"$f":"'K20 - time schedule'!CG49","v":0},{"$f":"'K20 - time schedule'!CH49","v":0},{"$f":"'K20 - time schedule'!CI49","v":0},{"$f":"'K20 - time schedule'!CJ49","v":0},{"$f":"'K20 - time schedule'!CK49","v":0},{"$f":"'K20 - time schedule'!CL49","v":0},{"$f":"'K20 - time schedule'!CM49","v":0},{"$f":"'K20 - time schedule'!CN49","v":0},{"$f":"'K20 - time schedule'!CO49","v":0},{"$f":"'K20 - time schedule'!CP49","v":0},{"$f":"'K20 - time schedule'!CQ49","v":0},{"$f":"'K20 - time schedule'!CR49","v":0},{"$f":"'K20 - time schedule'!CS49","v":0},{"$f":"'K20 - time schedule'!CT49","v":0},{"$f":"'K20 - time schedule'!CU49","v":0},{"$f":"'K20 - time schedule'!CV49","v":0},{"$f":"'K20 - time schedule'!CW49","v":0},{"$f":"'K20 - time schedule'!CX49","v":0},{"$f":"'K20 - time schedule'!CY49","v":0},{"$f":"'K20 - time schedule'!CZ49","v":0},{"$f":"'K20 - time schedule'!DA49","v":0},{"$f":"'K20 - time schedule'!DB49","v":0},{"$f":"'K20 - time schedule'!DC49","v":0},{"$f":"'K20 - time schedule'!DD49","v":0},{"$f":"'K20 - time schedule'!DE49","v":0},{"$f":"'K20 - time schedule'!DF49","v":0},{"$f":"'K20 - time schedule'!DG49","v":0},{"$f":"'K20 - time schedule'!DH49","v":0},{"$f":"'K20 - time schedule'!DI49","v":0},{"$f":"'K20 - time schedule'!DJ49","v":0},{"$f":"'K20 - time schedule'!DK49","v":0},{"$f":"'K20 - time schedule'!DL49","v":0},{"$f":"'K20 - time schedule'!DM49","v":0},{"$f":"'K20 - time schedule'!DN49","v":0},{"$f":"'K20 - time schedule'!DO49","v":0},{"$f":"'K20 - time schedule'!DP49","v":0},{"$f":"'K20 - time schedule'!DQ49","v":0},{"$f":"'K20 - time schedule'!DR49","v":0},{"$f":"'K20 - time schedule'!DS49","v":0},{"$f":"'K20 - time schedule'!DT49","v":0},{"$f":"'K20 - time schedule'!DU49","v":0},{"$f":"'K20 - time schedule'!DV49","v":0},{"$f":"'K20 - time schedule'!DW49","v":0},{"$f":"'K20 - time schedule'!DX49","v":0},{"$f":"'K20 - time schedule'!DY49","v":0},{"$f":"'K20 - time schedule'!DZ49","v":0},{"$f":"'K20 - time schedule'!EA49","v":0},{"$f":"'K20 - time schedule'!EB49","v":0},{"$f":"'K20 - time schedule'!EC49","v":0},{"$f":"'K20 - time schedule'!ED49","v":0},{"$f":"'K20 - time schedule'!EE49","v":0},{"$f":"'K20 - time schedule'!EF49","v":0},{"$f":"'K20 - time schedule'!EG49","v":0},{"$f":"'K20 - time schedule'!EH49","v":0},{"$f":"'K20 - time schedule'!EI49","v":0},{"$f":"'K20 - time schedule'!EJ49","v":0},{"$f":"'K20 - time schedule'!EK49","v":0},{"$f":"'K20 - time schedule'!EL49","v":0},{"$f":"'K20 - time schedule'!EM49","v":0},{"$f":"'K20 - time schedule'!EN49","v":0},{"$f":"'K20 - time schedule'!EO49","v":0},{"$f":"'K20 - time schedule'!EP49","v":0},{"$f":"'K20 - time schedule'!EQ49","v":0},{"$f":"'K20 - time schedule'!ER49","v":0},{"$f":"'K20 - time schedule'!ES49","v":0},{"$f":"'K20 - time schedule'!ET49","v":0},{"$f":"'K20 - time schedule'!EU49","v":0},{"$f":"'K20 - time schedule'!EV49","v":0},{"$f":"'K20 - time schedule'!EW49","v":0},{"$f":"'K20 - time schedule'!EX49","v":0},{"$f":"'K20 - time schedule'!EY49","v":0},{"$f":"'K20 - time schedule'!EZ49","v":0},{"$f":"'K20 - time schedule'!FA49","v":0},{"$f":"'K20 - time schedule'!FB49","v":0},{"$f":"'K20 - time schedule'!FC49","v":0},{"$f":"'K20 - time schedule'!FD49","v":0},{"$f":"'K20 - time schedule'!FE49","v":0},{"$f":"'K20 - time schedule'!FF49","v":0},{"$f":"'K20 - time schedule'!FG49","v":0},{"$f":"'K20 - time schedule'!FH49","v":0},{"$f":"'K20 - time schedule'!FI49","v":0},{"$f":"'K20 - time schedule'!FJ49","v":0},{"$f":"'K20 - time schedule'!FK49","v":0},{"$f":"'K20 - time schedule'!FL49","v":0},{"$f":"'K20 - time schedule'!FM49","v":0},{"$f":"'K20 - time schedule'!FN49","v":0},{"$f":"'K20 - time schedule'!FO49","v":0},{"$f":"'K20 - time schedule'!FP49","v":0},{"$f":"'K20 - time schedule'!FQ49","v":0},{"$f":"'K20 - time schedule'!FR49","v":0},{"$f":"'K20 - time schedule'!FS49","v":0},{"$f":"'K20 - time schedule'!FT49","v":0},{"$f":"'K20 - time schedule'!FU49","v":0},{"$f":"'K20 - time schedule'!FV49","v":0},{"$f":"'K20 - time schedule'!FW49","v":0},{"$f":"'K20 - time schedule'!FX49","v":0},{"$f":"'K20 - time schedule'!FY49","v":0},{"$f":"'K20 - time schedule'!FZ49","v":0},{"$f":"'K20 - time schedule'!GA49","v":0},{"$f":"'K20 - time schedule'!GB49","v":0},{"$f":"'K20 - time schedule'!GC49","v":0},{"$f":"'K20 - time schedule'!GD49","v":0},{"$f":"'K20 - time schedule'!GE49","v":0},{"$f":"'K20 - time schedule'!GF49","v":0},{"$f":"'K20 - time schedule'!GG49","v":0},{"$f":"'K20 - time schedule'!GH30","v":0},{"$f":"'K20 - time schedule'!GI30","v":0},{"$f":"'K20 - time schedule'!GJ30","v":0},{"$f":"'K20 - time schedule'!GK30","v":0},{"$f":"'K20 - time schedule'!GL30","v":0},{"$f":"'K20 - time schedule'!GM30","v":0},{"$f":"'K20 - time schedule'!GN30","v":0},{"$f":"'K20 - time schedule'!GO30","v":0},{"$f":"'K20 - time schedule'!GP30","v":0},{"$f":"'K20 - time schedule'!GQ30","v":0},{"$f":"'K20 - time schedule'!GR30","v":0},{"$f":"'K20 - time schedule'!GS30","v":0},{"$f":"'K20 - time schedule'!GT30","v":0},{"$f":"'K20 - time schedule'!GU30","v":0},{"$f":"'K20 - time schedule'!GV30","v":0},{"$f":"'K20 - time schedule'!GW30","v":0},{"$f":"'K20 - time schedule'!GX30","v":0},{"$f":"'K20 - time schedule'!GY30","v":0},{"$f":"'K20 - time schedule'!GZ30","v":0},{"$f":"'K20 - time schedule'!HA30","v":0},{"$f":"'K20 - time schedule'!HB30","v":0},{"$f":"'K20 - time schedule'!HC30","v":0},{"$f":"'K20 - time schedule'!HD30","v":0},{"$f":"'K20 - time schedule'!HE30","v":0},{"$f":"'K20 - time schedule'!HF30","v":0},{"$f":"'K20 - time schedule'!HG30","v":0},{"$f":"'K20 - time schedule'!HH30","v":0},{"$f":"'K20 - time schedule'!HI30","v":0},{"$f":"'K20 - time schedule'!HJ30","v":0},{"$f":"'K20 - time schedule'!HK30","v":0},{"$f":"'K20 - time schedule'!HL30","v":0},{"$f":"'K20 - time schedule'!HM30","v":0},{"$f":"'K20 - time schedule'!HN30","v":0},{"$f":"'K20 - time schedule'!HO30","v":0},{"$f":"'K20 - time schedule'!HP30","v":0},{"$f":"'K20 - time schedule'!HQ30","v":0},{"$f":"'K20 - time schedule'!HR30","v":0},{"$f":"'K20 - time schedule'!HS30","v":0},{"$f":"'K20 - time schedule'!HT30","v":0},{"$f":"'K20 - time schedule'!HU30","v":0},{"$f":"'K20 - time schedule'!HV30","v":0},{"$f":"'K20 - time schedule'!HW30","v":0},{"$f":"'K20 - time schedule'!HX30","v":0},{"$f":"'K20 - time schedule'!HY30","v":0},{"$f":"'K20 - time schedule'!HZ30","v":0},{"$f":"'K20 - time schedule'!IA30","v":0},{"$f":"'K20 - time schedule'!IB30","v":0},{"$f":"'K20 - time schedule'!IC30","v":0},{"$f":"'K20 - time schedule'!ID30","v":0},{"$f":"'K20 - time schedule'!IE30","v":0},{"$f":"'K20 - time schedule'!IF30","v":0},{"$f":"'K20 - time schedule'!IG30","v":0},{"$f":"'K20 - time schedule'!IH30","v":0},{"$f":"'K20 - time schedule'!II30","v":0},{"$f":"'K20 - time schedule'!IJ30","v":0},{"$f":"'K20 - time schedule'!IK30","v":0},{"$f":"'K20 - time schedule'!IL30","v":0},{"$f":"'K20 - time schedule'!IM30","v":0},{"$f":"'K20 - time schedule'!IN30","v":0},{"$f":"'K20 - time schedule'!IO30","v":0},{"$f":"'K20 - time schedule'!IP30","v":0},{"$f":"'K20 - time schedule'!IQ30","v":0},{"$f":"'K20 - time schedule'!IR30","v":0},{"$f":"'K20 - time schedule'!IS30","v":0},{"$f":"'K20 - time schedule'!IT30","v":0},{"$f":"'K20 - time schedule'!IU30","v":0},{"$f":"'K20 - time schedule'!IV30","v":0},{"$f":"'K20 - time schedule'!IW30","v":0},{"$f":"'K20 - time schedule'!IX30","v":0},{"$f":"'K20 - time schedule'!IY30","v":0},{"$f":"'K20 - time schedule'!IZ30","v":0},{"$f":"'K20 - time schedule'!JA30","v":0},{"$f":"'K20 - time schedule'!JB30","v":0},{"$f":"'K20 - time schedule'!JC30","v":0},{"$f":"'K20 - time schedule'!JD30","v":0},{"$f":"'K20 - time schedule'!JE30","v":0},{"$f":"'K20 - time schedule'!JF30","v":0},{"$f":"'K20 - time schedule'!JG30","v":0},{"$f":"'K20 - time schedule'!JH30","v":0},{"$f":"'K20 - time schedule'!JI30","v":0},{"$f":"'K20 - time schedule'!JJ30","v":0},{"$f":"'K20 - time schedule'!JK30","v":0},{"$f":"'K20 - time schedule'!JL30","v":0},{"$f":"'K20 - time schedule'!JM30","v":0},{"$f":"'K20 - time schedule'!JN30","v":0},{"$f":"'K20 - time schedule'!JO30","v":0},{"$f":"'K20 - time schedule'!JP30","v":0},{"$f":"'K20 - time schedule'!JQ30","v":0},{"$f":"'K20 - time schedule'!JR30","v":0},{"$f":"'K20 - time schedule'!JS30","v":0},{"$f":"'K20 - time schedule'!JT30","v":0},{"$f":"'K20 - time schedule'!JU30","v":0},{"$f":"'K20 - time schedule'!JV30","v":0},{"$f":"'K20 - time schedule'!JW30","v":0},{"$f":"'K20 - time schedule'!JX30","v":0},{"$f":"'K20 - time schedule'!JY30","v":0},{"$f":"'K20 - time schedule'!JZ30","v":0},{"$f":"'K20 - time schedule'!KA30","v":0},{"$f":"'K20 - time schedule'!KB30","v":0},{"$f":"'K20 - time schedule'!KC30","v":0},{"$f":"'K20 - time schedule'!KD30","v":0},{"$f":"'K20 - time schedule'!KE30","v":0},{"$f":"'K20 - time schedule'!KF30","v":0},{"$f":"'K20 - time schedule'!KG30","v":0},{"$f":"'K20 - time schedule'!KH30","v":0},{"$f":"'K20 - time schedule'!KI30","v":0},{"$f":"'K20 - time schedule'!KJ30","v":0},{"$f":"'K20 - time schedule'!KK30","v":0},{"$f":"'K20 - time schedule'!KL30","v":0},{"$f":"'K20 - time schedule'!KM30","v":0},{"$f":"'K20 - time schedule'!KN30","v":0},{"$f":"'K20 - time schedule'!KO30","v":0},{"$f":"'K20 - time schedule'!KP30","v":0},{"$f":"'K20 - time schedule'!KQ30","v":0},{"$f":"'K20 - time schedule'!KR30","v":0},{"$f":"'K20 - time schedule'!KS30","v":0},{"$f":"'K20 - time schedule'!KT30","v":0}]
["Boiler room K20 - operating staff training","K20",{"$f":"'K20 - time schedule'!G50","v":0},{"$f":"'K20 - time schedule'!H50","v":0},{"$f":"'K20 - time schedule'!I50","v":0},{"$f":"'K20 - time schedule'!J50","v":0},{"$f":"'K20 - time schedule'!K50","v":0},{"$f":"'K20 - time schedule'!L50","v":0},{"$f":"'K20 - time schedule'!M50","v":0},{"$f":"'K20 - time schedule'!N50","v":0},{"$f":"'K20 - time schedule'!O50","v":0},{"$f":"'K20 - time schedule'!P50","v":0},{"$f":"'K20 - time schedule'!Q50","v":0},{"$f":"'K20 - time schedule'!R50","v":0},{"$f":"'K20 - time schedule'!S50","v":0},{"$f":"'K20 - time schedule'!T50","v":0},{"$f":"'K20 - time schedule'!U50","v":0},{"$f":"'K20 - time schedule'!V50","v":0},{"$f":"'K20 - time schedule'!W50","v":0},{"$f":"'K20 - time schedule'!X50","v":0},{"$f":"'K20 - time schedule'!Y50","v":0},{"$f":"'K20 - time schedule'!Z50","v":0},{"$f":"'K20 - time schedule'!AA50","v":0},{"$f":"'K20 - time schedule'!AB50","v":0},{"$f":"'K20 - time schedule'!AC50","v":0},{"$f":"'K20 - time schedule'!AD50","v":0},{"$f":"'K20 - time schedule'!AE50","v":0},{"$f":"'K20 - time schedule'!AF50","v":0},{"$f":"'K20 - time schedule'!AG50","v":0},{"$f":"'K20 - time schedule'!AH50","v":0},{"$f":"'K20 - time schedule'!AI50","v":0},{"$f":"'K20 - time schedule'!AJ50","v":0},{"$f":"'K20 - time schedule'!AK50","v":0},{"$f":"'K20 - time schedule'!AL50","v":0},{"$f":"'K20 - time schedule'!AM50","v":0},{"$f":"'K20 - time schedule'!AN50","v":0},{"$f":"'K20 - time schedule'!AO50","v":0},{"$f":"'K20 - time schedule'!AP50","v":0},{"$f":"'K20 - time schedule'!AQ50","v":0},{"$f":"'K20 - time schedule'!AR50","v":0},{"$f":"'K20 - time schedule'!AS50","v":0},{"$f":"'K20 - time schedule'!AT50","v":0},{"$f":"'K20 - time schedule'!AU50","v":0},{"$f":"'K20 - time schedule'!AV50","v":0},{"$f":"'K20 - time schedule'!AW50","v":0},{"$f":"'K20 - time schedule'!AX50","v":0},{"$f":"'K20 - time schedule'!AY50","v":0},{"$f":"'K20 - time schedule'!AZ50","v":0},{"$f":"'K20 - time schedule'!BA50","v":0},{"$f":"'K20 - time schedule'!BB50","v":0},{"$f":"'K20 - time schedule'!BC50","v":0},{"$f":"'K20 - time schedule'!BD50","v":0},{"$f":"'K20 - time schedule'!BE50","v":0},{"$f":"'K20 - time schedule'!BF50","v":0},{"$f":"'K20 - time schedule'!BG50","v":0},{"$f":"'K20 - time schedule'!BH50","v":0},{"$f":"'K20 - time schedule'!BI50","v":0},{"$f":"'K20 - time schedule'!BJ50","v":0},{"$f":"'K20 - time schedule'!BK50","v":0},{"$f":"'K20 - time schedule'!BL50","v":0},{"$f":"'K20 - time schedule'!BM50","v":0},{"$f":"'K20 - time schedule'!BN50","v":0},{"$f":"'K20 - time schedule'!BO50","v":0},{"$f":"'K20 - time schedule'!BP50","v":0},{"$f":"'K20 - time schedule'!BQ50","v":0},{"$f":"'K20 - time schedule'!BR50","v":0},{"$f":"'K20 - time schedule'!BS50","v":0},{"$f":"'K20 - time schedule'!BT50","v":0},{"$f":"'K20 - time schedule'!BU50","v":0},{"$f":"'K20 - time schedule'!BV50","v":0},{"$f":"'K20 - time schedule'!BW50","v":0},{"$f":"'K20 - time schedule'!BX50","v":0},{"$f":"'K20 - time schedule'!BY50","v":0},{"$f":"'K20 - time schedule'!BZ50","v":0},{"$f":"'K20 - time schedule'!CA50","v":0},{"$f":"'K20 - time schedule'!CB50","v":0},{"$f":"'K20 - time schedule'!CC50","v":0},{"$f":"'K20 - time schedule'!CD50","v":0},{"$f":"'K20 - time schedule'!CE50","v":0},{"$f":"'K20 - time schedule'!CF50","v":0},{"$f":"'K20 - time schedule'!CG50","v":0},{"$f":"'K20 - time schedule'!CH50","v":0},{"$f":"'K20 - time schedule'!CI50","v":0},{"$f":"'K20 - time schedule'!CJ50","v":0},{"$f":"'K20 - time schedule'!CK50","v":0},{"$f":"'K20 - time schedule'!CL50","v":0},{"$f":"'K20 - time schedule'!CM50","v":0},{"$f":"'K20 - time schedule'!CN50","v":0},{"$f":"'K20 - time schedule'!CO50","v":0},{"$f":"'K20 - time schedule'!CP50","v":0},{"$f":"'K20 - time schedule'!CQ50","v":0},{"$f":"'K20 - time schedule'!CR50","v":0},{"$f":"'K20 - time schedule'!CS50","v":0},{"$f":"'K20 - time schedule'!CT50","v":0},{"$f":"'K20 - time schedule'!CU50","v":0},{"$f":"'K20 - time schedule'!CV50","v":0},{"$f":"'K20 - time schedule'!CW50","v":0},{"$f":"'K20 - time schedule'!CX50","v":0},{"$f":"'K20 - time schedule'!CY50","v":0},{"$f":"'K20 - time schedule'!CZ50","v":0},{"$f":"'K20 - time schedule'!DA50","v":0},{"$f":"'K20 - time schedule'!DB50","v":0},{"$f":"'K20 - time schedule'!DC50","v":0},{"$f":"'K20 - time schedule'!DD50","v":0},{"$f":"'K20 - time schedule'!DE50","v":0},{"$f":"'K20 - time schedule'!DF50","v":0},{"$f":"'K20 - time schedule'!DG50","v":0},{"$f":"'K20 - time schedule'!DH50","v":0},{"$f":"'K20 - time schedule'!DI50","v":0},{"$f":"'K20 - time schedule'!DJ50","v":0},{"$f":"'K20 - time schedule'!DK50","v":0},{"$f":"'K20 - time schedule'!DL50","v":0},{"$f":"'K20 - time schedule'!DM50","v":0},{"$f":"'K20 - time schedule'!DN50","v":0},{"$f":"'K20 - time schedule'!DO50","v":0},{"$f":"'K20 - time schedule'!DP50","v":0},{"$f":"'K20 - time schedule'!DQ50","v":0},{"$f":"'K20 - time schedule'!DR50","v":0},{"$f":"'K20 - time schedule'!DS50","v":0},{"$f":"'K20 - time schedule'!DT50","v":0},{"$f":"'K20 - time schedule'!DU50","v":0},{"$f":"'K20 - time schedule'!DV50","v":0},{"$f":"'K20 - time schedule'!DW50","v":0},{"$f":"'K20 - time schedule'!DX50","v":0},{"$f":"'K20 - time schedule'!DY50","v":0},{"$f":"'K20 - time schedule'!DZ50","v":0},{"$f":"'K20 - time schedule'!EA50","v":0},{"$f":"'K20 - time schedule'!EB50","v":0},{"$f":"'K20 - time schedule'!EC50","v":0},{"$f":"'K20 - time schedule'!ED50","v":0},{"$f":"'K20 - time schedule'!EE50","v":0},{"$f":"'K20 - time schedule'!EF50","v":0},{"$f":"'K20 - time schedule'!EG50","v":0},{"$f":"'K20 - time schedule'!EH50","v":0},{"$f":"'K20 - time schedule'!EI50","v":0},{"$f":"'K20 - time schedule'!EJ50","v":0},{"$f":"'K20 - time schedule'!EK50","v":0},{"$f":"'K20 - time schedule'!EL50","v":0},{"$f":"'K20 - time schedule'!EM50","v":0},{"$f":"'K20 - time schedule'!EN50","v":0},{"$f":"'K20 - time schedule'!EO50","v":0},{"$f":"'K20 - time schedule'!EP50","v":0},{"$f":"'K20 - time schedule'!EQ50","v":0},{"$f":"'K20 - time schedule'!ER50","v":0},{"$f":"'K20 - time schedule'!ES50","v":0},{"$f":"'K20 - time schedule'!ET50","v":0},{"$f":"'K20 - time schedule'!EU50","v":0},{"$f":"'K20 - time schedule'!EV50","v":0},{"$f":"'K20 - time schedule'!EW50","v":0},{"$f":"'K20 - time schedule'!EX50","v":0},{"$f":"'K20 - time schedule'!EY50","v":0},{"$f":"'K20 - time schedule'!EZ50","v":0},{"$f":"'K20 - time schedule'!FA50","v":0},{"$f":"'K20 - time schedule'!FB50","v":0},{"$f":"'K20 - time schedule'!FC50","v":0},{"$f":"'K20 - time schedule'!FD50","v":0},{"$f":"'K20 - time schedule'!FE50","v":0},{"$f":"'K20 - time schedule'!FF50","v":0},{"$f":"'K20 - time schedule'!FG50","v":0},{"$f":"'K20 - time schedule'!FH50","v":0},{"$f":"'K20 - time schedule'!FI50","v":0},{"$f":"'K20 - time schedule'!FJ50","v":0},{"$f":"'K20 - time schedule'!FK50","v":0},{"$f":"'K20 - time schedule'!FL50","v":0},{"$f":"'K20 - time schedule'!FM50","v":0},{"$f":"'K20 - time schedule'!FN50","v":0},{"$f":"'K20 - time schedule'!FO50","v":0},{"$f":"'K20 - time schedule'!FP50","v":0},{"$f":"'K20 - time schedule'!FQ50","v":0},{"$f":"'K20 - time schedule'!FR50","v":0},{"$f":"'K20 - time schedule'!FS50","v":0},{"$f":"'K20 - time schedule'!FT50","v":0},{"$f":"'K20 - time schedule'!FU50","v":0},{"$f":"'K20 - time schedule'!FV50","v":0},{"$f":"'K20 - time schedule'!FW50","v":0},{"$f":"'K20 - time schedule'!FX50","v":0},{"$f":"'K20 - time schedule'!FY50","v":0},{"$f":"'K20 - time schedule'!FZ50","v":0},{"$f":"'K20 - time schedule'!GA50","v":0},{"$f":"'K20 - time schedule'!GB50","v":0},{"$f":"'K20 - time schedule'!GC50","v":0},{"$f":"'K20 - time schedule'!GD50","v":0},{"$f":"'K20 - time schedule'!GE50","v":0},{"$f":"'K20 - time schedule'!GF50","v":0},{"$f":"'K20 - time schedule'!GG50","v":0},{"$f":"'K20 - time schedule'!GH31","v":0},{"$f":"'K20 - time schedule'!GI31","v":0},{"$f":"'K20 - time schedule'!GJ31","v":0},{"$f":"'K20 - time schedule'!GK31","v":0},{"$f":"'K20 - time schedule'!GL31","v":0},{"$f":"'K20 - time schedule'!GM31","v":0},{"$f":"'K20 - time schedule'!GN31","v":0},{"$f":"'K20 - time schedule'!GO31","v":0},{"$f":"'K20 - time schedule'!GP31","v":0},{"$f":"'K20 - time schedule'!GQ31","v":0},{"$f":"'K20 - time schedule'!GR31","v":0},{"$f":"'K20 - time schedule'!GS31","v":0},{"$f":"'K20 - time schedule'!GT31","v":0},{"$f":"'K20 - time schedule'!GU31","v":0},{"$f":"'K20 - time schedule'!GV31","v":0},{"$f":"'K20 - time schedule'!GW31","v":0},{"$f":"'K20 - time schedule'!GX31","v":0},{"$f":"'K20 - time schedule'!GY31","v":0},{"$f":"'K20 - time schedule'!GZ31","v":0},{"$f":"'K20 - time schedule'!HA31","v":0},{"$f":"'K20 - time schedule'!HB31","v":0},{"$f":"'K20 - time schedule'!HC31","v":0},{"$f":"'K20 - time schedule'!HD31","v":0},{"$f":"'K20 - time schedule'!HE31","v":0},{"$f":"'K20 - time schedule'!HF31","v":0},{"$f":"'K20 - time schedule'!HG31","v":0},{"$f":"'K20 - time schedule'!HH31","v":0},{"$f":"'K20 - time schedule'!HI31","v":0},{"$f":"'K20 - time schedule'!HJ31","v":0},{"$f":"'K20 - time schedule'!HK31","v":0},{"$f":"'K20 - time schedule'!HL31","v":0},{"$f":"'K20 - time schedule'!HM31","v":0},{"$f":"'K20 - time schedule'!HN31","v":0},{"$f":"'K20 - time schedule'!HO31","v":0},{"$f":"'K20 - time schedule'!HP31","v":0},{"$f":"'K20 - time schedule'!HQ31","v":0},{"$f":"'K20 - time schedule'!HR31","v":0},{"$f":"'K20 - time schedule'!HS31","v":0},{"$f":"'K20 - time schedule'!HT31","v":0},{"$f":"'K20 - time schedule'!HU31","v":0},{"$f":"'K20 - time schedule'!HV31","v":0},{"$f":"'K20 - time schedule'!HW31","v":0},{"$f":"'K20 - time schedule'!HX31","v":0},{"$f":"'K20 - time schedule'!HY31","v":0},{"$f":"'K20 - time schedule'!HZ31","v":0},{"$f":"'K20 - time schedule'!IA31","v":0},{"$f":"'K20 - time schedule'!IB31","v":0},{"$f":"'K20 - time schedule'!IC31","v":0},{"$f":"'K20 - time schedule'!ID31","v":0},{"$f":"'K20 - time schedule'!IE31","v":0},{"$f":"'K20 - time schedule'!IF31","v":0},{"$f":"'K20 - time schedule'!IG31","v":0},{"$f":"'K20 - time schedule'!IH31","v":0},{"$f":"'K20 - time schedule'!II31","v":0},{"$f":"'K20 - time schedule'!IJ31","v":0},{"$f":"'K20 - time schedule'!IK31","v":0},{"$f":"'K20 - time schedule'!IL31","v":0},{"$f":"'K20 - time schedule'!IM31","v":0},{"$f":"'K20 - time schedule'!IN31","v":0},{"$f":"'K20 - time schedule'!IO31","v":0},{"$f":"'K20 - time schedule'!IP31","v":0},{"$f":"'K20 - time schedule'!IQ31","v":0},{"$f":"'K20 - time schedule'!IR31","v":0},{"$f":"'K20 - time schedule'!IS31","v":0},{"$f":"'K20 - time schedule'!IT31","v":0},{"$f":"'K20 - time schedule'!IU31","v":0},{"$f":"'K20 - time schedule'!IV31","v":0},{"$f":"'K20 - time schedule'!IW31","v":0},{"$f":"'K20 - time schedule'!IX31","v":0},{"$f":"'K20 - time schedule'!IY31","v":0},{"$f":"'K20 - time schedule'!IZ31","v":0},{"$f":"'K20 - time schedule'!JA31","v":0},{"$f":"'K20 - time schedule'!JB31","v":0},{"$f":"'K20 - time schedule'!JC31","v":0},{"$f":"'K20 - time schedule'!JD31","v":0},{"$f":"'K20 - time schedule'!JE31","v":0},{"$f":"'K20 - time schedule'!JF31","v":0},{"$f":"'K20 - time schedule'!JG31","v":0},{"$f":"'K20 - time schedule'!JH31","v":0},{"$f":"'K20 - time schedule'!JI31","v":0},{"$f":"'K20 - time schedule'!JJ31","v":0},{"$f":"'K20 - time schedule'!JK31","v":0},{"$f":"'K20 - time schedule'!JL31","v":0},{"$f":"'K20 - time schedule'!JM31","v":0},{"$f":"'K20 - time schedule'!JN31","v":0},{"$f":"'K20 - time schedule'!JO31","v":0},{"$f":"'K20 - time schedule'!JP31","v":0},{"$f":"'K20 - time schedule'!JQ31","v":0},{"$f":"'K20 - time schedule'!JR31","v":0},{"$f":"'K20 - time schedule'!JS31","v":0},{"$f":"'K20 - time schedule'!JT31","v":0},{"$f":"'K20 - time schedule'!JU31","v":0},{"$f":"'K20 - time schedule'!JV31","v":0},{"$f":"'K20 - time schedule'!JW31","v":0},{"$f":"'K20 - time schedule'!JX31","v":0},{"$f":"'K20 - time schedule'!JY31","v":0},{"$f":"'K20 - time schedule'!JZ31","v":0},{"$f":"'K20 - time schedule'!KA31","v":0},{"$f":"'K20 - time schedule'!KB31","v":0},{"$f":"'K20 - time schedule'!KC31","v":0},{"$f":"'K20 - time schedule'!KD31","v":0},{"$f":"'K20 - time schedule'!KE31","v":0},{"$f":"'K20 - time schedule'!KF31","v":0},{"$f":"'K20 - time schedule'!KG31","v":0},{"$f":"'K20 - time schedule'!KH31","v":0},{"$f":"'K20 - time schedule'!KI31","v":0},{"$f":"'K20 - time schedule'!KJ31","v":0},{"$f":"'K20 - time schedule'!KK31","v":0},{"$f":"'K20 - time schedule'!KL31","v":0},{"$f":"'K20 - time schedule'!KM31","v":0},{"$f":"'K20 - time schedule'!KN31","v":0},{"$f":"'K20 - time schedule'!KO31","v":0},{"$f":"'K20 - time schedule'!KP31","v":0},{"$f":"'K20 - time schedule'!KQ31","v":0},{"$f":"'K20 - time schedule'!KR31","v":0},{"$f":"'K20 - time schedule'!KS31","v":0},{"$f":"'K20 - time schedule'!KT31","v":0}]
["Boiler room K20 - preparation for comprehensive testing","K20",{"$f":"'K20 - time schedule'!G52","v":0},{"$f":"'K20 - time schedule'!H52","v":0},{"$f":"'K20 - time schedule'!I52","v":0},{"$f":"'K20 - time schedule'!J52","v":0},{"$f":"'K20 - time schedule'!K52","v":0},{"$f":"'K20 - time schedule'!L52","v":0},{"$f":"'K20 - time schedule'!M52","v":0},{"$f":"'K20 - time schedule'!N52","v":0},{"$f":"'K20 - time schedule'!O52","v":0},{"$f":"'K20 - time schedule'!P52","v":0},{"$f":"'K20 - time schedule'!Q52","v":0},{"$f":"'K20 - time schedule'!R52","v":0},{"$f":"'K20 - time schedule'!S52","v":0},{"$f":"'K20 - time schedule'!T52","v":0},{"$f":"'K20 - time schedule'!U52","v":0},{"$f":"'K20 - time schedule'!V52","v":0},{"$f":"'K20 - time schedule'!W52","v":0},{"$f":"'K20 - time schedule'!X52","v":0},{"$f":"'K20 - time schedule'!Y52","v":0},{"$f":"'K20 - time schedule'!Z52","v":0},{"$f":"'K20 - time schedule'!AA52","v":0},{"$f":"'K20 - time schedule'!AB52","v":0},{"$f":"'K20 - time schedule'!AC52","v":0},{"$f":"'K20 - time schedule'!AD52","v":0},{"$f":"'K20 - time schedule'!AE52","v":0},{"$f":"'K20 - time schedule'!AF52","v":0},{"$f":"'K20 - time schedule'!AG52","v":0},{"$f":"'K20 - time schedule'!AH52","v":0},{"$f":"'K20 - time schedule'!AI52","v":0},{"$f":"'K20 - time schedule'!AJ52","v":0},{"$f":"'K20 - time schedule'!AK52","v":0},{"$f":"'K20 - time schedule'!AL52","v":0},{"$f":"'K20 - time schedule'!AM52","v":0},{"$f":"'K20 - time schedule'!AN52","v":0},{"$f":"'K20 - time schedule'!AO52","v":0},{"$f":"'K20 - time schedule'!AP52","v":0},{"$f":"'K20 - time schedule'!AQ52","v":0},{"$f":"'K20 - time schedule'!AR52","v":0},{"$f":"'K20 - time schedule'!AS52","v":0},{"$f":"'K20 - time schedule'!AT52","v":0},{"$f":"'K20 - time schedule'!AU52","v":0},{"$f":"'K20 - time schedule'!AV52","v":0},{"$f":"'K20 - time schedule'!AW52","v":0},{"$f":"'K20 - time schedule'!AX52","v":0},{"$f":"'K20 - time schedule'!AY52","v":0},{"$f":"'K20 - time schedule'!AZ52","v":0},{"$f":"'K20 - time schedule'!BA52","v":0},{"$f":"'K20 - time schedule'!BB52","v":0},{"$f":"'K20 - time schedule'!BC52","v":0},{"$f":"'K20 - time schedule'!BD52","v":0},{"$f":"'K20 - time schedule'!BE52","v":0},{"$f":"'K20 - time schedule'!BF52","v":0},{"$f":"'K20 - time schedule'!BG52","v":0},{"$f":"'K20 - time schedule'!BH52","v":0},{"$f":"'K20 - time schedule'!BI52","v":0},{"$f":"'K20 - time schedule'!BJ52","v":0},{"$f":"'K20 - time schedule'!BK52","v":0},{"$f":"'K20 - time schedule'!BL52","v":0},{"$f":"'K20 - time schedule'!BM52","v":0},{"$f":"'K20 - time schedule'!BN52","v":0},{"$f":"'K20 - time schedule'!BO52","v":0},{"$f":"'K20 - time schedule'!BP52","v":0},{"$f":"'K20 - time schedule'!BQ52","v":0},{"$f":"'K20 - time schedule'!BR52","v":0},{"$f":"'K20 - time schedule'!BS52","v":0},{"$f":"'K20 - time schedule'!BT52","v":0},{"$f":"'K20 - time schedule'!BU52","v":0},{"$f":"'K20 - time schedule'!BV52","v":0},{"$f":"'K20 - time schedule'!BW52","v":0},{"$f":"'K20 - time schedule'!BX52","v":0},{"$f":"'K20 - time schedule'!BY52","v":0},{"$f":"'K20 - time schedule'!BZ52","v":0},{"$f":"'K20 - time schedule'!CA52","v":0},{"$f":"'K20 - time schedule'!CB52","v":0},{"$f":"'K20 - time schedule'!CC52","v":0},{"$f":"'K20 - time schedule'!CD52","v":0},{"$f":"'K20 - time schedule'!CE52","v":0},{"$f":"'K20 - time schedule'!CF52","v":0},{"$f":"'K20 - time schedule'!CG52","v":0},{"$f":"'K20 - time schedule'!CH52","v":0},{"$f":"'K20 - time schedule'!CI52","v":0},{"$f":"'K20 - time schedule'!CJ52","v":0},{"$f":"'K20 - time schedule'!CK52","v":0},{"$f":"'K20 - time schedule'!CL52","v":0},{"$f":"'K20 - time schedule'!CM52","v":0},{"$f":"'K20 - time schedule'!CN52","v":0},{"$f":"'K20 - time schedule'!CO52","v":0},{"$f":"'K20 - time schedule'!CP52","v":0},{"$f":"'K20 - time schedule'!CQ52","v":0},{"$f":"'K20 - time schedule'!CR52","v":0},{"$f":"'K20 - time schedule'!CS52","v":0},{"$f":"'K20 - time schedule'!CT52","v":0},{"$f":"'K20 - time schedule'!CU52","v":0},{"$f":"'K20 - time schedule'!CV52","v":0},{"$f":"'K20 - time schedule'!CW52","v":0},{"$f":"'K20 - time schedule'!CX52","v":0},{"$f":"'K20 - time schedule'!CY52","v":0},{"$f":"'K20 - time schedule'!CZ52","v":0},{"$f":"'K20 - time schedule'!DA52","v":0},{"$f":"'K20 - time schedule'!DB52","v":0},{"$f":"'K20 - time schedule'!DC52","v":0},{"$f":"'K20 - time schedule'!DD52","v":0},{"$f":"'K20 - time schedule'!DE52","v":0},{"$f":"'K20 - time schedule'!DF52","v":0},{"$f":"'K20 - time schedule'!DG52","v":0},{"$f":"'K20 - time schedule'!DH52","v":0},{"$f":"'K20 - time schedule'!DI52","v":0},{"$f":"'K20 - time schedule'!DJ52","v":0},{"$f":"'K20 - time schedule'!DK52","v":0},{"$f":"'K20 - time schedule'!DL52","v":0},{"$f":"'K20 - time schedule'!DM52","v":0},{"$f":"'K20 - time schedule'!DN52","v":0},{"$f":"'K20 - time schedule'!DO52","v":0},{"$f":"'K20 - time schedule'!DP52","v":0},{"$f":"'K20 - time schedule'!DQ52","v":0},{"$f":"'K20 - time schedule'!DR52","v":0},{"$f":"'K20 - time schedule'!DS52","v":0},{"$f":"'K20 - time schedule'!DT52","v":0},{"$f":"'K20 - time schedule'!DU52","v":0},{"$f":"'K20 - time schedule'!DV52","v":0},{"$f":"'K20 - time schedule'!DW52","v":0},{"$f":"'K20 - time schedule'!DX52","v":0},{"$f":"'K20 - time schedule'!DY52","v":0},{"$f":"'K20 - time schedule'!DZ52","v":0},{"$f":"'K20 - time schedule'!EA52","v":0},{"$f":"'K20 - time schedule'!EB52","v":0},{"$f":"'K20 - time schedule'!EC52","v":0},{"$f":"'K20 - time schedule'!ED52","v":0},{"$f":"'K20 - time schedule'!EE52","v":0},{"$f":"'K20 - time schedule'!EF52","v":0},{"$f":"'K20 - time schedule'!EG52","v":0},{"$f":"'K20 - time schedule'!EH52","v":0},{"$f":"'K20 - time schedule'!EI52","v":0},{"$f":"'K20 - time schedule'!EJ52","v":0},{"$f":"'K20 - time schedule'!EK52","v":0},{"$f":"'K20 - time schedule'!EL52","v":0},{"$f":"'K20 - time schedule'!EM52","v":0},{"$f":"'K20 - time schedule'!EN52","v":0},{"$f":"'K20 - time schedule'!EO52","v":0},{"$f":"'K20 - time schedule'!EP52","v":0},{"$f":"'K20 - time schedule'!EQ52","v":0},{"$f":"'K20 - time schedule'!ER52","v":0},{"$f":"'K20 - time schedule'!ES52","v":0},{"$f":"'K20 - time schedule'!ET52","v":0},{"$f":"'K20 - time schedule'!EU52","v":0},{"$f":"'K20 - time schedule'!EV52","v":0},{"$f":"'K20 - time schedule'!EW52","v":0},{"$f":"'K20 - time schedule'!EX52","v":0},{"$f":"'K20 - time schedule'!EY52","v":0},{"$f":"'K20 - time schedule'!EZ52","v":0},{"$f":"'K20 - time schedule'!FA52","v":0},{"$f":"'K20 - time schedule'!FB52","v":0},{"$f":"'K20 - time schedule'!FC52","v":0},{"$f":"'K20 - time schedule'!FD52","v":0},{"$f":"'K20 - time schedule'!FE52","v":0},{"$f":"'K20 - time schedule'!FF52","v":0},{"$f":"'K20 - time schedule'!FG52","v":0},{"$f":"'K20 - time schedule'!FH52","v":0},{"$f":"'K20 - time schedule'!FI52","v":0},{"$f":"'K20 - time schedule'!FJ52","v":0},{"$f":"'K20 - time schedule'!FK52","v":0},{"$f":"'K20 - time schedule'!FL52","v":0},{"$f":"'K20 - time schedule'!FM52","v":0},{"$f":"'K20 - time schedule'!FN52","v":0},{"$f":"'K20 - time schedule'!FO52","v":0},{"$f":"'K20 - time schedule'!FP52","v":0},{"$f":"'K20 - time schedule'!FQ52","v":0},{"$f":"'K20 - time schedule'!FR52","v":0},{"$f":"'K20 - time schedule'!FS52","v":0},{"$f":"'K20 - time schedule'!FT52","v":0},{"$f":"'K20 - time schedule'!FU52","v":0},{"$f":"'K20 - time schedule'!FV52","v":0},{"$f":"'K20 - time schedule'!FW52","v":0},{"$f":"'K20 - time schedule'!FX52","v":0},{"$f":"'K20 - time schedule'!FY52","v":0},{"$f":"'K20 - time schedule'!FZ52","v":0},{"$f":"'K20 - time schedule'!GA52","v":0},{"$f":"'K20 - time schedule'!GB52","v":0},{"$f":"'K20 - time schedule'!GC52","v":0},{"$f":"'K20 - time schedule'!GD52","v":0},{"$f":"'K20 - time schedule'!GE52","v":0},{"$f":"'K20 - time schedule'!GF52","v":0},{"$f":"'K20 - time schedule'!GG52","v":0},{"$f":"'K20 - time schedule'!GH32","v":0},{"$f":"'K20 - time schedule'!GI32","v":0},{"$f":"'K20 - time schedule'!GJ32","v":0},{"$f":"'K20 - time schedule'!GK32","v":0},{"$f":"'K20 - time schedule'!GL32","v":0},{"$f":"'K20 - time schedule'!GM32","v":0},{"$f":"'K20 - time schedule'!GN32","v":0},{"$f":"'K20 - time schedule'!GO32","v":0},{"$f":"'K20 - time schedule'!GP32","v":0},{"$f":"'K20 - time schedule'!GQ32","v":0},{"$f":"'K20 - time schedule'!GR32","v":0},{"$f":"'K20 - time schedule'!GS32","v":0},{"$f":"'K20 - time schedule'!GT32","v":0},{"$f":"'K20 - time schedule'!GU32","v":0},{"$f":"'K20 - time schedule'!GV32","v":0},{"$f":"'K20 - time schedule'!GW32","v":0},{"$f":"'K20 - time schedule'!GX32","v":0},{"$f":"'K20 - time schedule'!GY32","v":0},{"$f":"'K20 - time schedule'!GZ32","v":0},{"$f":"'K20 - time schedule'!HA32","v":0},{"$f":"'K20 - time schedule'!HB32","v":0},{"$f":"'K20 - time schedule'!HC32","v":0},{"$f":"'K20 - time schedule'!HD32","v":0},{"$f":"'K20 - time schedule'!HE32","v":0},{"$f":"'K20 - time schedule'!HF32","v":0},{"$f":"'K20 - time schedule'!HG32","v":0},{"$f":"'K20 - time schedule'!HH32","v":0},{"$f":"'K20 - time schedule'!HI32","v":0},{"$f":"'K20 - time schedule'!HJ32","v":0},{"$f":"'K20 - time schedule'!HK32","v":0},{"$f":"'K20 - time schedule'!HL32","v":0},{"$f":"'K20 - time schedule'!HM32","v":0},{"$f":"'K20 - time schedule'!HN32","v":0},{"$f":"'K20 - time schedule'!HO32","v":0},{"$f":"'K20 - time schedule'!HP32","v":0},{"$f":"'K20 - time schedule'!HQ32","v":0},{"$f":"'K20 - time schedule'!HR32","v":0},{"$f":"'K20 - time schedule'!HS32","v":0},{"$f":"'K20 - time schedule'!HT32","v":0},{"$f":"'K20 - time schedule'!HU32","v":0},{"$f":"'K20 - time schedule'!HV32","v":0},{"$f":"'K20 - time schedule'!HW32","v":0},{"$f":"'K20 - time schedule'!HX32","v":0},{"$f":"'K20 - time schedule'!HY32","v":0},{"$f":"'K20 - time schedule'!HZ32","v":0},{"$f":"'K20 - time schedule'!IA32","v":0},{"$f":"'K20 - time schedule'!IB32","v":0},{"$f":"'K20 - time schedule'!IC32","v":0},{"$f":"'K20 - time schedule'!ID32","v":0},{"$f":"'K20 - time schedule'!IE32","v":0},{"$f":"'K20 - time schedule'!IF32","v":0},{"$f":"'K20 - time schedule'!IG32","v":0},{"$f":"'K20 - time schedule'!IH32","v":0},{"$f":"'K20 - time schedule'!II32","v":0},{"$f":"'K20 - time schedule'!IJ32","v":0},{"$f":"'K20 - time schedule'!IK32","v":0},{"$f":"'K20 - time schedule'!IL32","v":0},{"$f":"'K20 - time schedule'!IM32","v":0},{"$f":"'K20 - time schedule'!IN32","v":0},{"$f":"'K20 - time schedule'!IO32","v":0},{"$f":"'K20 - time schedule'!IP32","v":0},{"$f":"'K20 - time schedule'!IQ32","v":0},{"$f":"'K20 - time schedule'!IR32","v":0},{"$f":"'K20 - time schedule'!IS32","v":0},{"$f":"'K20 - time schedule'!IT32","v":0},{"$f":"'K20 - time schedule'!IU32","v":0},{"$f":"'K20 - time schedule'!IV32","v":0},{"$f":"'K20 - time schedule'!IW32","v":0},{"$f":"'K20 - time schedule'!IX32","v":0},{"$f":"'K20 - time schedule'!IY32","v":0},{"$f":"'K20 - time schedule'!IZ32","v":0},{"$f":"'K20 - time schedule'!JA32","v":0},{"$f":"'K20 - time schedule'!JB32","v":0},{"$f":"'K20 - time schedule'!JC32","v":0},{"$f":"'K20 - time schedule'!JD32","v":0},{"$f":"'K20 - time schedule'!JE32","v":0},{"$f":"'K20 - time schedule'!JF32","v":0},{"$f":"'K20 - time schedule'!JG32","v":0},{"$f":"'K20 - time schedule'!JH32","v":0},{"$f":"'K20 - time schedule'!JI32","v":0},{"$f":"'K20 - time schedule'!JJ32","v":0},{"$f":"'K20 - time schedule'!JK32","v":0},{"$f":"'K20 - time schedule'!JL32","v":0},{"$f":"'K20 - time schedule'!JM32","v":0},{"$f":"'K20 - time schedule'!JN32","v":0},{"$f":"'K20 - time schedule'!JO32","v":0},{"$f":"'K20 - time schedule'!JP32","v":0},{"$f":"'K20 - time schedule'!JQ32","v":0},{"$f":"'K20 - time schedule'!JR32","v":0},{"$f":"'K20 - time schedule'!JS32","v":0},{"$f":"'K20 - time schedule'!JT32","v":0},{"$f":"'K20 - time schedule'!JU32","v":0},{"$f":"'K20 - time schedule'!JV32","v":0},{"$f":"'K20 - time schedule'!JW32","v":0},{"$f":"'K20 - time schedule'!JX32","v":0},{"$f":"'K20 - time schedule'!JY32","v":0},{"$f":"'K20 - time schedule'!JZ32","v":0},{"$f":"'K20 - time schedule'!KA32","v":0},{"$f":"'K20 - time schedule'!KB32","v":0},{"$f":"'K20 - time schedule'!KC32","v":0},{"$f":"'K20 - time schedule'!KD32","v":0},{"$f":"'K20 - time schedule'!KE32","v":0},{"$f":"'K20 - time schedule'!KF32","v":0},{"$f":"'K20 - time schedule'!KG32","v":0},{"$f":"'K20 - time schedule'!KH32","v":0},{"$f":"'K20 - time schedule'!KI32","v":0},{"$f":"'K20 - time schedule'!KJ32","v":0},{"$f":"'K20 - time schedule'!KK32","v":0},{"$f":"'K20 - time schedule'!KL32","v":0},{"$f":"'K20 - time schedule'!KM32","v":0},{"$f":"'K20 - time schedule'!KN32","v":0},{"$f":"'K20 - time schedule'!KO32","v":0},{"$f":"'K20 - time schedule'!KP32","v":0},{"$f":"'K20 - time schedule'!KQ32","v":0},{"$f":"'K20 - time schedule'!KR32","v":0},{"$f":"'K20 - time schedule'!KS32","v":0},{"$f":"'K20 - time schedule'!KT32","v":0}]
["Boiler room K20 - comprehensive testing","K20",{"$f":"'K20 - time schedule'!G53","v":0},{"$f":"'K20 - time schedule'!H53","v":0},{"$f":"'K20 - time schedule'!I53","v":0},{"$f":"'K20 - time schedule'!J53","v":0},{"$f":"'K20 - time schedule'!K53","v":0},{"$f":"'K20 - time schedule'!L53","v":0},{"$f":"'K20 - time schedule'!M53","v":0},{"$f":"'K20 - time schedule'!N53","v":0},{"$f":"'K20 - time schedule'!O53","v":0},{"$f":"'K20 - time schedule'!P53","v":0},{"$f":"'K20 - time schedule'!Q53","v":0},{"$f":"'K20 - time schedule'!R53","v":0},{"$f":"'K20 - time schedule'!S53","v":0},{"$f":"'K20 - time schedule'!T53","v":0},{"$f":"'K20 - time schedule'!U53","v":0},{"$f":"'K20 - time schedule'!V53","v":0},{"$f":"'K20 - time schedule'!W53","v":0},{"$f":"'K20 - time schedule'!X53","v":0},{"$f":"'K20 - time schedule'!Y53","v":0},{"$f":"'K20 - time schedule'!Z53","v":0},{"$f":"'K20 - time schedule'!AA53","v":0},{"$f":"'K20 - time schedule'!AB53","v":0},{"$f":"'K20 - time schedule'!AC53","v":0},{"$f":"'K20 - time schedule'!AD53","v":0},{"$f":"'K20 - time schedule'!AE53","v":0},{"$f":"'K20 - time schedule'!AF53","v":0},{"$f":"'K20 - time schedule'!AG53","v":0},{"$f":"'K20 - time schedule'!AH53","v":0},{"$f":"'K20 - time schedule'!AI53","v":0},{"$f":"'K20 - time schedule'!AJ53","v":0},{"$f":"'K20 - time schedule'!AK53","v":0},{"$f":"'K20 - time schedule'!AL53","v":0},{"$f":"'K20 - time schedule'!AM53","v":0},{"$f":"'K20 - time schedule'!AN53","v":0},{"$f":"'K20 - time schedule'!AO53","v":0},{"$f":"'K20 - time schedule'!AP53","v":0},{"$f":"'K20 - time schedule'!AQ53","v":0},{"$f":"'K20 - time schedule'!AR53","v":0},{"$f":"'K20 - time schedule'!AS53","v":0},{"$f":"'K20 - time schedule'!AT53","v":0},{"$f":"'K20 - time schedule'!AU53","v":0},{"$f":"'K20 - time schedule'!AV53","v":0},{"$f":"'K20 - time schedule'!AW53","v":0},{"$f":"'K20 - time schedule'!AX53","v":0},{"$f":"'K20 - time schedule'!AY53","v":0},{"$f":"'K20 - time schedule'!AZ53","v":0},{"$f":"'K20 - time schedule'!BA53","v":0},{"$f":"'K20 - time schedule'!BB53","v":0},{"$f":"'K20 - time schedule'!BC53","v":0},{"$f":"'K20 - time schedule'!BD53","v":0},{"$f":"'K20 - time schedule'!BE53","v":0},{"$f":"'K20 - time schedule'!BF53","v":0},{"$f":"'K20 - time schedule'!BG53","v":0},{"$f":"'K20 - time schedule'!BH53","v":0},{"$f":"'K20 - time schedule'!BI53","v":0},{"$f":"'K20 - time schedule'!BJ53","v":0},{"$f":"'K20 - time schedule'!BK53","v":0},{"$f":"'K20 - time schedule'!BL53","v":0},{"$f":"'K20 - time schedule'!BM53","v":0},{"$f":"'K20 - time schedule'!BN53","v":0},{"$f":"'K20 - time schedule'!BO53","v":0},{"$f":"'K20 - time schedule'!BP53","v":0},{"$f":"'K20 - time schedule'!BQ53","v":0},{"$f":"'K20 - time schedule'!BR53","v":0},{"$f":"'K20 - time schedule'!BS53","v":0},{"$f":"'K20 - time schedule'!BT53","v":0},{"$f":"'K20 - time schedule'!BU53","v":0},{"$f":"'K20 - time schedule'!BV53","v":0},{"$f":"'K20 - time schedule'!BW53","v":0},{"$f":"'K20 - time schedule'!BX53","v":0},{"$f":"'K20 - time schedule'!BY53","v":0},{"$f":"'K20 - time schedule'!BZ53","v":0},{"$f":"'K20 - time schedule'!CA53","v":0},{"$f":"'K20 - time schedule'!CB53","v":0},{"$f":"'K20 - time schedule'!CC53","v":0},{"$f":"'K20 - time schedule'!CD53","v":0},{"$f":"'K20 - time schedule'!CE53","v":0},{"$f":"'K20 - time schedule'!CF53","v":0},{"$f":"'K20 - time schedule'!CG53","v":0},{"$f":"'K20 - time schedule'!CH53","v":0},{"$f":"'K20 - time schedule'!CI53","v":0},{"$f":"'K20 - time schedule'!CJ53","v":0},{"$f":"'K20 - time schedule'!CK53","v":0},{"$f":"'K20 - time schedule'!CL53","v":0},{"$f":"'K20 - time schedule'!CM53","v":0},{"$f":"'K20 - time schedule'!CN53","v":0},{"$f":"'K20 - time schedule'!CO53","v":0},{"$f":"'K20 - time schedule'!CP53","v":0},{"$f":"'K20 - time schedule'!CQ53","v":0},{"$f":"'K20 - time schedule'!CR53","v":0},{"$f":"'K20 - time schedule'!CS53","v":0},{"$f":"'K20 - time schedule'!CT53","v":0},{"$f":"'K20 - time schedule'!CU53","v":0},{"$f":"'K20 - time schedule'!CV53","v":0},{"$f":"'K20 - time schedule'!CW53","v":0},{"$f":"'K20 - time schedule'!CX53","v":0},{"$f":"'K20 - time schedule'!CY53","v":0},{"$f":"'K20 - time schedule'!CZ53","v":0},{"$f":"'K20 - time schedule'!DA53","v":0},{"$f":"'K20 - time schedule'!DB53","v":0},{"$f":"'K20 - time schedule'!DC53","v":0},{"$f":"'K20 - time schedule'!DD53","v":0},{"$f":"'K20 - time schedule'!DE53","v":0},{"$f":"'K20 - time schedule'!DF53","v":0},{"$f":"'K20 - time schedule'!DG53","v":0},{"$f":"'K20 - time schedule'!DH53","v":0},{"$f":"'K20 - time schedule'!DI53","v":0},{"$f":"'K20 - time schedule'!DJ53","v":0},{"$f":"'K20 - time schedule'!DK53","v":0},{"$f":"'K20 - time schedule'!DL53","v":0},{"$f":"'K20 - time schedule'!DM53","v":0},{"$f":"'K20 - time schedule'!DN53","v":0},{"$f":"'K20 - time schedule'!DO53","v":0},{"$f":"'K20 - time schedule'!DP53","v":0},{"$f":"'K20 - time schedule'!DQ53","v":0},{"$f":"'K20 - time schedule'!DR53","v":0},{"$f":"'K20 - time schedule'!DS53","v":0},{"$f":"'K20 - time schedule'!DT53","v":0},{"$f":"'K20 - time schedule'!DU53","v":0},{"$f":"'K20 - time schedule'!DV53","v":0},{"$f":"'K20 - time schedule'!DW53","v":0},{"$f":"'K20 - time schedule'!DX53","v":0},{"$f":"'K20 - time schedule'!DY53","v":0},{"$f":"'K20 - time schedule'!DZ53","v":0},{"$f":"'K20 - time schedule'!EA53","v":0},{"$f":"'K20 - time schedule'!EB53","v":0},{"$f":"'K20 - time schedule'!EC53","v":0},{"$f":"'K20 - time schedule'!ED53","v":0},{"$f":"'K20 - time schedule'!EE53","v":0},{"$f":"'K20 - time schedule'!EF53","v":0},{"$f":"'K20 - time schedule'!EG53","v":0},{"$f":"'K20 - time schedule'!EH53","v":0},{"$f":"'K20 - time schedule'!EI53","v":0},{"$f":"'K20 - time schedule'!EJ53","v":0},{"$f":"'K20 - time schedule'!EK53","v":0},{"$f":"'K20 - time schedule'!EL53","v":0},{"$f":"'K20 - time schedule'!EM53","v":0},{"$f":"'K20 - time schedule'!EN53","v":0},{"$f":"'K20 - time schedule'!EO53","v":0},{"$f":"'K20 - time schedule'!EP53","v":0},{"$f":"'K20 - time schedule'!EQ53","v":0},{"$f":"'K20 - time schedule'!ER53","v":0},{"$f":"'K20 - time schedule'!ES53","v":0},{"$f":"'K20 - time schedule'!ET53","v":0},{"$f":"'K20 - time schedule'!EU53","v":0},{"$f":"'K20 - time schedule'!EV53","v":0},{"$f":"'K20 - time schedule'!EW53","v":0},{"$f":"'K20 - time schedule'!EX53","v":0},{"$f":"'K20 - time schedule'!EY53","v":0},{"$f":"'K20 - time schedule'!EZ53","v":0},{"$f":"'K20 - time schedule'!FA53","v":0},{"$f":"'K20 - time schedule'!FB53","v":0},{"$f":"'K20 - time schedule'!FC53","v":0},{"$f":"'K20 - time schedule'!FD53","v":0},{"$f":"'K20 - time schedule'!FE53","v":0},{"$f":"'K20 - time schedule'!FF53","v":0},{"$f":"'K20 - time schedule'!FG53","v":0},{"$f":"'K20 - time schedule'!FH53","v":0},{"$f":"'K20 - time schedule'!FI53","v":0},{"$f":"'K20 - time schedule'!FJ53","v":0},{"$f":"'K20 - time schedule'!FK53","v":0},{"$f":"'K20 - time schedule'!FL53","v":0},{"$f":"'K20 - time schedule'!FM53","v":0},{"$f":"'K20 - time schedule'!FN53","v":0},{"$f":"'K20 - time schedule'!FO53","v":0},{"$f":"'K20 - time schedule'!FP53","v":0},{"$f":"'K20 - time schedule'!FQ53","v":0},{"$f":"'K20 - time schedule'!FR53","v":0},{"$f":"'K20 - time schedule'!FS53","v":0},{"$f":"'K20 - time schedule'!FT53","v":0},{"$f":"'K20 - time schedule'!FU53","v":0},{"$f":"'K20 - time schedule'!FV53","v":0},{"$f":"'K20 - time schedule'!FW53","v":0},{"$f":"'K20 - time schedule'!FX53","v":0},{"$f":"'K20 - time schedule'!FY53","v":0},{"$f":"'K20 - time schedule'!FZ53","v":0},{"$f":"'K20 - time schedule'!GA53","v":0},{"$f":"'K20 - time schedule'!GB53","v":0},{"$f":"'K20 - time schedule'!GC53","v":0},{"$f":"'K20 - time schedule'!GD53","v":0},{"$f":"'K20 - time schedule'!GE53","v":0},{"$f":"'K20 - time schedule'!GF53","v":0},{"$f":"'K20 - time schedule'!GG53","v":0},{"$f":"'K20 - time schedule'!GH33","v":0},{"$f":"'K20 - time schedule'!GI33","v":0},{"$f":"'K20 - time schedule'!GJ33","v":0},{"$f":"'K20 - time schedule'!GK33","v":0},{"$f":"'K20 - time schedule'!GL33","v":0},{"$f":"'K20 - time schedule'!GM33","v":0},{"$f":"'K20 - time schedule'!GN33","v":0},{"$f":"'K20 - time schedule'!GO33","v":0},{"$f":"'K20 - time schedule'!GP33","v":0},{"$f":"'K20 - time schedule'!GQ33","v":0},{"$f":"'K20 - time schedule'!GR33","v":0},{"$f":"'K20 - time schedule'!GS33","v":0},{"$f":"'K20 - time schedule'!GT33","v":0},{"$f":"'K20 - time schedule'!GU33","v":0},{"$f":"'K20 - time schedule'!GV33","v":0},{"$f":"'K20 - time schedule'!GW33","v":0},{"$f":"'K20 - time schedule'!GX33","v":0},{"$f":"'K20 - time schedule'!GY33","v":0},{"$f":"'K20 - time schedule'!GZ33","v":0},{"$f":"'K20 - time schedule'!HA33","v":0},{"$f":"'K20 - time schedule'!HB33","v":0},{"$f":"'K20 - time schedule'!HC33","v":0},{"$f":"'K20 - time schedule'!HD33","v":0},{"$f":"'K20 - time schedule'!HE33","v":0},{"$f":"'K20 - time schedule'!HF33","v":0},{"$f":"'K20 - time schedule'!HG33","v":0},{"$f":"'K20 - time schedule'!HH33","v":0},{"$f":"'K20 - time schedule'!HI33","v":0},{"$f":"'K20 - time schedule'!HJ33","v":0},{"$f":"'K20 - time schedule'!HK33","v":0},{"$f":"'K20 - time schedule'!HL33","v":0},{"$f":"'K20 - time schedule'!HM33","v":0},{"$f":"'K20 - time schedule'!HN33","v":0},{"$f":"'K20 - time schedule'!HO33","v":0},{"$f":"'K20 - time schedule'!HP33","v":0},{"$f":"'K20 - time schedule'!HQ33","v":0},{"$f":"'K20 - time schedule'!HR33","v":0},{"$f":"'K20 - time schedule'!HS33","v":0},{"$f":"'K20 - time schedule'!HT33","v":0},{"$f":"'K20 - time schedule'!HU33","v":0},{"$f":"'K20 - time schedule'!HV33","v":0},{"$f":"'K20 - time schedule'!HW33","v":0},{"$f":"'K20 - time schedule'!HX33","v":0},{"$f":"'K20 - time schedule'!HY33","v":0},{"$f":"'K20 - time schedule'!HZ33","v":0},{"$f":"'K20 - time schedule'!IA33","v":0},{"$f":"'K20 - time schedule'!IB33","v":0},{"$f":"'K20 - time schedule'!IC33","v":0},{"$f":"'K20 - time schedule'!ID33","v":0},{"$f":"'K20 - time schedule'!IE33","v":0},{"$f":"'K20 - time schedule'!IF33","v":0},{"$f":"'K20 - time schedule'!IG33","v":0},{"$f":"'K20 - time schedule'!IH33","v":0},{"$f":"'K20 - time schedule'!II33","v":0},{"$f":"'K20 - time schedule'!IJ33","v":0},{"$f":"'K20 - time schedule'!IK33","v":0},{"$f":"'K20 - time schedule'!IL33","v":0},{"$f":"'K20 - time schedule'!IM33","v":0},{"$f":"'K20 - time schedule'!IN33","v":0},{"$f":"'K20 - time schedule'!IO33","v":0},{"$f":"'K20 - time schedule'!IP33","v":0},{"$f":"'K20 - time schedule'!IQ33","v":0},{"$f":"'K20 - time schedule'!IR33","v":0},{"$f":"'K20 - time schedule'!IS33","v":0},{"$f":"'K20 - time schedule'!IT33","v":0},{"$f":"'K20 - time schedule'!IU33","v":0},{"$f":"'K20 - time schedule'!IV33","v":0},{"$f":"'K20 - time schedule'!IW33","v":0},{"$f":"'K20 - time schedule'!IX33","v":0},{"$f":"'K20 - time schedule'!IY33","v":0},{"$f":"'K20 - time schedule'!IZ33","v":0},{"$f":"'K20 - time schedule'!JA33","v":0},{"$f":"'K20 - time schedule'!JB33","v":0},{"$f":"'K20 - time schedule'!JC33","v":0},{"$f":"'K20 - time schedule'!JD33","v":0},{"$f":"'K20 - time schedule'!JE33","v":0},{"$f":"'K20 - time schedule'!JF33","v":0},{"$f":"'K20 - time schedule'!JG33","v":0},{"$f":"'K20 - time schedule'!JH33","v":0},{"$f":"'K20 - time schedule'!JI33","v":0},{"$f":"'K20 - time schedule'!JJ33","v":0},{"$f":"'K20 - time schedule'!JK33","v":0},{"$f":"'K20 - time schedule'!JL33","v":0},{"$f":"'K20 - time schedule'!JM33","v":0},{"$f":"'K20 - time schedule'!JN33","v":0},{"$f":"'K20 - time schedule'!JO33","v":0},{"$f":"'K20 - time schedule'!JP33","v":0},{"$f":"'K20 - time schedule'!JQ33","v":0},{"$f":"'K20 - time schedule'!JR33","v":0},{"$f":"'K20 - time schedule'!JS33","v":0},{"$f":"'K20 - time schedule'!JT33","v":0},{"$f":"'K20 - time schedule'!JU33","v":0},{"$f":"'K20 - time schedule'!JV33","v":0},{"$f":"'K20 - time schedule'!JW33","v":0},{"$f":"'K20 - time schedule'!JX33","v":0},{"$f":"'K20 - time schedule'!JY33","v":0},{"$f":"'K20 - time schedule'!JZ33","v":0},{"$f":"'K20 - time schedule'!KA33","v":0},{"$f":"'K20 - time schedule'!KB33","v":0},{"$f":"'K20 - time schedule'!KC33","v":0},{"$f":"'K20 - time schedule'!KD33","v":0},{"$f":"'K20 - time schedule'!KE33","v":0},{"$f":"'K20 - time schedule'!KF33","v":0},{"$f":"'K20 - time schedule'!KG33","v":0},{"$f":"'K20 - time schedule'!KH33","v":0},{"$f":"'K20 - time schedule'!KI33","v":0},{"$f":"'K20 - time schedule'!KJ33","v":0},{"$f":"'K20 - time schedule'!KK33","v":0},{"$f":"'K20 - time schedule'!KL33","v":0},{"$f":"'K20 - time schedule'!KM33","v":0},{"$f":"'K20 - time schedule'!KN33","v":0},{"$f":"'K20 - time schedule'!KO33","v":0},{"$f":"'K20 - time schedule'!KP33","v":0},{"$f":"'K20 - time schedule'!KQ33","v":0},{"$f":"'K20 - time schedule'!KR33","v":0},{"$f":"'K20 - time schedule'!KS33","v":0},{"$f":"'K20 - time schedule'!KT33","v":0}]
["Boiler room K20 - trial operation","K20",{"$f":"'K20 - time schedule'!G55","v":0},{"$f":"'K20 - time schedule'!H55","v":0},{"$f":"'K20 - time schedule'!I55","v":0},{"$f":"'K20 - time schedule'!J55","v":0},{"$f":"'K20 - time schedule'!K55","v":0},{"$f":"'K20 - time schedule'!L55","v":0},{"$f":"'K20 - time schedule'!M55","v":0},{"$f":"'K20 - time schedule'!N55","v":0},{"$f":"'K20 - time schedule'!O55","v":0},{"$f":"'K20 - time schedule'!P55","v":0},{"$f":"'K20 - time schedule'!Q55","v":0},{"$f":"'K20 - time schedule'!R55","v":0},{"$f":"'K20 - time schedule'!S55","v":0},{"$f":"'K20 - time schedule'!T55","v":0},{"$f":"'K20 - time schedule'!U55","v":0},{"$f":"'K20 - time schedule'!V55","v":0},{"$f":"'K20 - time schedule'!W55","v":0},{"$f":"'K20 - time schedule'!X55","v":0},{"$f":"'K20 - time schedule'!Y55","v":0},{"$f":"'K20 - time schedule'!Z55","v":0},{"$f":"'K20 - time schedule'!AA55","v":0},{"$f":"'K20 - time schedule'!AB55","v":0},{"$f":"'K20 - time schedule'!AC55","v":0},{"$f":"'K20 - time schedule'!AD55","v":0},{"$f":"'K20 - time schedule'!AE55","v":0},{"$f":"'K20 - time schedule'!AF55","v":0},{"$f":"'K20 - time schedule'!AG55","v":0},{"$f":"'K20 - time schedule'!AH55","v":0},{"$f":"'K20 - time schedule'!AI55","v":0},{"$f":"'K20 - time schedule'!AJ55","v":0},{"$f":"'K20 - time schedule'!AK55","v":0},{"$f":"'K20 - time schedule'!AL55","v":0},{"$f":"'K20 - time schedule'!AM55","v":0},{"$f":"'K20 - time schedule'!AN55","v":0},{"$f":"'K20 - time schedule'!AO55","v":0},{"$f":"'K20 - time schedule'!AP55","v":0},{"$f":"'K20 - time schedule'!AQ55","v":0},{"$f":"'K20 - time schedule'!AR55","v":0},{"$f":"'K20 - time schedule'!AS55","v":0},{"$f":"'K20 - time schedule'!AT55","v":0},{"$f":"'K20 - time schedule'!AU55","v":0},{"$f":"'K20 - time schedule'!AV55","v":0},{"$f":"'K20 - time schedule'!AW55","v":0},{"$f":"'K20 - time schedule'!AX55","v":0},{"$f":"'K20 - time schedule'!AY55","v":0},{"$f":"'K20 - time schedule'!AZ55","v":0},{"$f":"'K20 - time schedule'!BA55","v":0},{"$f":"'K20 - time schedule'!BB55","v":0},{"$f":"'K20 - time schedule'!BC55","v":0},{"$f":"'K20 - time schedule'!BD55","v":0},{"$f":"'K20 - time schedule'!BE55","v":0},{"$f":"'K20 - time schedule'!BF55","v":0},{"$f":"'K20 - time schedule'!BG55","v":0},{"$f":"'K20 - time schedule'!BH55","v":0},{"$f":"'K20 - time schedule'!BI55","v":0},{"$f":"'K20 - time schedule'!BJ55","v":0},{"$f":"'K20 - time schedule'!BK55","v":0},{"$f":"'K20 - time schedule'!BL55","v":0},{"$f":"'K20 - time schedule'!BM55","v":0},{"$f":"'K20 - time schedule'!BN55","v":0},{"$f":"'K20 - time schedule'!BO55","v":0},{"$f":"'K20 - time schedule'!BP55","v":0},{"$f":"'K20 - time schedule'!BQ55","v":0},{"$f":"'K20 - time schedule'!BR55","v":0},{"$f":"'K20 - time schedule'!BS55","v":0},{"$f":"'K20 - time schedule'!BT55","v":0},{"$f":"'K20 - time schedule'!BU55","v":0},{"$f":"'K20 - time schedule'!BV55","v":0},{"$f":"'K20 - time schedule'!BW55","v":0},{"$f":"'K20 - time schedule'!BX55","v":0},{"$f":"'K20 - time schedule'!BY55","v":0},{"$f":"'K20 - time schedule'!BZ55","v":0},{"$f":"'K20 - time schedule'!CA55","v":0},{"$f":"'K20 - time schedule'!CB55","v":0},{"$f":"'K20 - time schedule'!CC55","v":0},{"$f":"'K20 - time schedule'!CD55","v":0},{"$f":"'K20 - time schedule'!CE55","v":0},{"$f":"'K20 - time schedule'!CF55","v":0},{"$f":"'K20 - time schedule'!CG55","v":0},{"$f":"'K20 - time schedule'!CH55","v":0},{"$f":"'K20 - time schedule'!CI55","v":0},{"$f":"'K20 - time schedule'!CJ55","v":0},{"$f":"'K20 - time schedule'!CK55","v":0},{"$f":"'K20 - time schedule'!CL55","v":0},{"$f":"'K20 - time schedule'!CM55","v":0},{"$f":"'K20 - time schedule'!CN55","v":0},{"$f":"'K20 - time schedule'!CO55","v":0},{"$f":"'K20 - time schedule'!CP55","v":0},{"$f":"'K20 - time schedule'!CQ55","v":0},{"$f":"'K20 - time schedule'!CR55","v":0},{"$f":"'K20 - time schedule'!CS55","v":0},{"$f":"'K20 - time schedule'!CT55","v":0},{"$f":"'K20 - time schedule'!CU55","v":0},{"$f":"'K20 - time schedule'!CV55","v":0},{"$f":"'K20 - time schedule'!CW55","v":0},{"$f":"'K20 - time schedule'!CX55","v":0},{"$f":"'K20 - time schedule'!CY55","v":0},{"$f":"'K20 - time schedule'!CZ55","v":0},{"$f":"'K20 - time schedule'!DA55","v":0},{"$f":"'K20 - time schedule'!DB55","v":0},{"$f":"'K20 - time schedule'!DC55","v":0},{"$f":"'K20 - time schedule'!DD55","v":0},{"$f":"'K20 - time schedule'!DE55","v":0},{"$f":"'K20 - time schedule'!DF55","v":0},{"$f":"'K20 - time schedule'!DG55","v":0},{"$f":"'K20 - time schedule'!DH55","v":0},{"$f":"'K20 - time schedule'!DI55","v":0},{"$f":"'K20 - time schedule'!DJ55","v":0},{"$f":"'K20 - time schedule'!DK55","v":0},{"$f":"'K20 - time schedule'!DL55","v":0},{"$f":"'K20 - time schedule'!DM55","v":0},{"$f":"'K20 - time schedule'!DN55","v":0},{"$f":"'K20 - time schedule'!DO55","v":0},{"$f":"'K20 - time schedule'!DP55","v":0},{"$f":"'K20 - time schedule'!DQ55","v":0},{"$f":"'K20 - time schedule'!DR55","v":0},{"$f":"'K20 - time schedule'!DS55","v":0},{"$f":"'K20 - time schedule'!DT55","v":0},{"$f":"'K20 - time schedule'!DU55","v":0},{"$f":"'K20 - time schedule'!DV55","v":0},{"$f":"'K20 - time schedule'!DW55","v":0},{"$f":"'K20 - time schedule'!DX55","v":0},{"$f":"'K20 - time schedule'!DY55","v":0},{"$f":"'K20 - time schedule'!DZ55","v":0},{"$f":"'K20 - time schedule'!EA55","v":0},{"$f":"'K20 - time schedule'!EB55","v":0},{"$f":"'K20 - time schedule'!EC55","v":0},{"$f":"'K20 - time schedule'!ED55","v":0},{"$f":"'K20 - time schedule'!EE55","v":0},{"$f":"'K20 - time schedule'!EF55","v":0},{"$f":"'K20 - time schedule'!EG55","v":0},{"$f":"'K20 - time schedule'!EH55","v":0},{"$f":"'K20 - time schedule'!EI55","v":0},{"$f":"'K20 - time schedule'!EJ55","v":0},{"$f":"'K20 - time schedule'!EK55","v":0},{"$f":"'K20 - time schedule'!EL55","v":0},{"$f":"'K20 - time schedule'!EM55","v":0},{"$f":"'K20 - time schedule'!EN55","v":0},{"$f":"'K20 - time schedule'!EO55","v":0},{"$f":"'K20 - time schedule'!EP55","v":0},{"$f":"'K20 - time schedule'!EQ55","v":0},{"$f":"'K20 - time schedule'!ER55","v":0},{"$f":"'K20 - time schedule'!ES55","v":0},{"$f":"'K20 - time schedule'!ET55","v":0},{"$f":"'K20 - time schedule'!EU55","v":0},{"$f":"'K20 - time schedule'!EV55","v":0},{"$f":"'K20 - time schedule'!EW55","v":0},{"$f":"'K20 - time schedule'!EX55","v":0},{"$f":"'K20 - time schedule'!EY55","v":0},{"$f":"'K20 - time schedule'!EZ55","v":0},{"$f":"'K20 - time schedule'!FA55","v":0},{"$f":"'K20 - time schedule'!FB55","v":0},{"$f":"'K20 - time schedule'!FC55","v":0},{"$f":"'K20 - time schedule'!FD55","v":0},{"$f":"'K20 - time schedule'!FE55","v":0},{"$f":"'K20 - time schedule'!FF55","v":0},{"$f":"'K20 - time schedule'!FG55","v":0},{"$f":"'K20 - time schedule'!FH55","v":0},{"$f":"'K20 - time schedule'!FI55","v":0},{"$f":"'K20 - time schedule'!FJ55","v":0},{"$f":"'K20 - time schedule'!FK55","v":0},{"$f":"'K20 - time schedule'!FL55","v":0},{"$f":"'K20 - time schedule'!FM55","v":0},{"$f":"'K20 - time schedule'!FN55","v":0},{"$f":"'K20 - time schedule'!FO55","v":0},{"$f":"'K20 - time schedule'!FP55","v":0},{"$f":"'K20 - time schedule'!FQ55","v":0},{"$f":"'K20 - time schedule'!FR55","v":0},{"$f":"'K20 - time schedule'!FS55","v":0},{"$f":"'K20 - time schedule'!FT55","v":0},{"$f":"'K20 - time schedule'!FU55","v":0},{"$f":"'K20 - time schedule'!FV55","v":0},{"$f":"'K20 - time schedule'!FW55","v":0},{"$f":"'K20 - time schedule'!FX55","v":0},{"$f":"'K20 - time schedule'!FY55","v":0},{"$f":"'K20 - time schedule'!FZ55","v":0},{"$f":"'K20 - time schedule'!GA55","v":0},{"$f":"'K20 - time schedule'!GB55","v":0},{"$f":"'K20 - time schedule'!GC55","v":0},{"$f":"'K20 - time schedule'!GD55","v":0},{"$f":"'K20 - time schedule'!GE55","v":0},{"$f":"'K20 - time schedule'!GF55","v":0},{"$f":"'K20 - time schedule'!GG55","v":0},{"$f":"'K20 - time schedule'!GH34","v":0},{"$f":"'K20 - time schedule'!GI34","v":0},{"$f":"'K20 - time schedule'!GJ34","v":0},{"$f":"'K20 - time schedule'!GK34","v":0},{"$f":"'K20 - time schedule'!GL34","v":0},{"$f":"'K20 - time schedule'!GM34","v":0},{"$f":"'K20 - time schedule'!GN34","v":0},{"$f":"'K20 - time schedule'!GO34","v":0},{"$f":"'K20 - time schedule'!GP34","v":0},{"$f":"'K20 - time schedule'!GQ34","v":0},{"$f":"'K20 - time schedule'!GR34","v":0},{"$f":"'K20 - time schedule'!GS34","v":0},{"$f":"'K20 - time schedule'!GT34","v":0},{"$f":"'K20 - time schedule'!GU34","v":0},{"$f":"'K20 - time schedule'!GV34","v":0},{"$f":"'K20 - time schedule'!GW34","v":0},{"$f":"'K20 - time schedule'!GX34","v":0},{"$f":"'K20 - time schedule'!GY34","v":0},{"$f":"'K20 - time schedule'!GZ34","v":0},{"$f":"'K20 - time schedule'!HA34","v":0},{"$f":"'K20 - time schedule'!HB34","v":0},{"$f":"'K20 - time schedule'!HC34","v":0},{"$f":"'K20 - time schedule'!HD34","v":0},{"$f":"'K20 - time schedule'!HE34","v":0},{"$f":"'K20 - time schedule'!HF34","v":0},{"$f":"'K20 - time schedule'!HG34","v":0},{"$f":"'K20 - time schedule'!HH34","v":0},{"$f":"'K20 - time schedule'!HI34","v":0},{"$f":"'K20 - time schedule'!HJ34","v":0},{"$f":"'K20 - time schedule'!HK34","v":0},{"$f":"'K20 - time schedule'!HL34","v":0},{"$f":"'K20 - time schedule'!HM34","v":0},{"$f":"'K20 - time schedule'!HN34","v":0},{"$f":"'K20 - time schedule'!HO34","v":0},{"$f":"'K20 - time schedule'!HP34","v":0},{"$f":"'K20 - time schedule'!HQ34","v":0},{"$f":"'K20 - time schedule'!HR34","v":0},{"$f":"'K20 - time schedule'!HS34","v":0},{"$f":"'K20 - time schedule'!HT34","v":0},{"$f":"'K20 - time schedule'!HU34","v":0},{"$f":"'K20 - time schedule'!HV34","v":0},{"$f":"'K20 - time schedule'!HW34","v":0},{"$f":"'K20 - time schedule'!HX34","v":0},{"$f":"'K20 - time schedule'!HY34","v":0},{"$f":"'K20 - time schedule'!HZ34","v":0},{"$f":"'K20 - time schedule'!IA34","v":0},{"$f":"'K20 - time schedule'!IB34","v":0},{"$f":"'K20 - time schedule'!IC34","v":0},{"$f":"'K20 - time schedule'!ID34","v":0},{"$f":"'K20 - time schedule'!IE34","v":0},{"$f":"'K20 - time schedule'!IF34","v":0},{"$f":"'K20 - time schedule'!IG34","v":0},{"$f":"'K20 - time schedule'!IH34","v":0},{"$f":"'K20 - time schedule'!II34","v":0},{"$f":"'K20 - time schedule'!IJ34","v":0},{"$f":"'K20 - time schedule'!IK34","v":0},{"$f":"'K20 - time schedule'!IL34","v":0},{"$f":"'K20 - time schedule'!IM34","v":0},{"$f":"'K20 - time schedule'!IN34","v":0},{"$f":"'K20 - time schedule'!IO34","v":0},{"$f":"'K20 - time schedule'!IP34","v":0},{"$f":"'K20 - time schedule'!IQ34","v":0},{"$f":"'K20 - time schedule'!IR34","v":0},{"$f":"'K20 - time schedule'!IS34","v":0},{"$f":"'K20 - time schedule'!IT34","v":0},{"$f":"'K20 - time schedule'!IU34","v":0},{"$f":"'K20 - time schedule'!IV34","v":0},{"$f":"'K20 - time schedule'!IW34","v":0},{"$f":"'K20 - time schedule'!IX34","v":0},{"$f":"'K20 - time schedule'!IY34","v":0},{"$f":"'K20 - time schedule'!IZ34","v":0},{"$f":"'K20 - time schedule'!JA34","v":0},{"$f":"'K20 - time schedule'!JB34","v":0},{"$f":"'K20 - time schedule'!JC34","v":0},{"$f":"'K20 - time schedule'!JD34","v":0},{"$f":"'K20 - time schedule'!JE34","v":0},{"$f":"'K20 - time schedule'!JF34","v":0},{"$f":"'K20 - time schedule'!JG34","v":0},{"$f":"'K20 - time schedule'!JH34","v":0},{"$f":"'K20 - time schedule'!JI34","v":0},{"$f":"'K20 - time schedule'!JJ34","v":0},{"$f":"'K20 - time schedule'!JK34","v":0},{"$f":"'K20 - time schedule'!JL34","v":0},{"$f":"'K20 - time schedule'!JM34","v":0},{"$f":"'K20 - time schedule'!JN34","v":0},{"$f":"'K20 - time schedule'!JO34","v":0},{"$f":"'K20 - time schedule'!JP34","v":0},{"$f":"'K20 - time schedule'!JQ34","v":0},{"$f":"'K20 - time schedule'!JR34","v":0},{"$f":"'K20 - time schedule'!JS34","v":0},{"$f":"'K20 - time schedule'!JT34","v":0},{"$f":"'K20 - time schedule'!JU34","v":0},{"$f":"'K20 - time schedule'!JV34","v":0},{"$f":"'K20 - time schedule'!JW34","v":0},{"$f":"'K20 - time schedule'!JX34","v":0},{"$f":"'K20 - time schedule'!JY34","v":0},{"$f":"'K20 - time schedule'!JZ34","v":0},{"$f":"'K20 - time schedule'!KA34","v":0},{"$f":"'K20 - time schedule'!KB34","v":0},{"$f":"'K20 - time schedule'!KC34","v":0},{"$f":"'K20 - time schedule'!KD34","v":0},{"$f":"'K20 - time schedule'!KE34","v":0},{"$f":"'K20 - time schedule'!KF34","v":0},{"$f":"'K20 - time schedule'!KG34","v":0},{"$f":"'K20 - time schedule'!KH34","v":0},{"$f":"'K20 - time schedule'!KI34","v":0},{"$f":"'K20 - time schedule'!KJ34","v":0},{"$f":"'K20 - time schedule'!KK34","v":0},{"$f":"'K20 - time schedule'!KL34","v":0},{"$f":"'K20 - time schedule'!KM34","v":0},{"$f":"'K20 - time schedule'!KN34","v":0},{"$f":"'K20 - time schedule'!KO34","v":0},{"$f":"'K20 - time schedule'!KP34","v":0},{"$f":"'K20 - time schedule'!KQ34","v":0},{"$f":"'K20 - time schedule'!KR34","v":0},{"$f":"'K20 - time schedule'!KS34","v":0},{"$f":"'K20 - time schedule'!KT34","v":0}]
["Boiler room K20 - guarantee test A","K20",{"$f":"'K20 - time schedule'!G57","v":0},{"$f":"'K20 - time schedule'!H57","v":0},{"$f":"'K20 - time schedule'!I57","v":0},{"$f":"'K20 - time schedule'!J57","v":0},{"$f":"'K20 - time schedule'!K57","v":0},{"$f":"'K20 - time schedule'!L57","v":0},{"$f":"'K20 - time schedule'!M57","v":0},{"$f":"'K20 - time schedule'!N57","v":0},{"$f":"'K20 - time schedule'!O57","v":0},{"$f":"'K20 - time schedule'!P57","v":0},{"$f":"'K20 - time schedule'!Q57","v":0},{"$f":"'K20 - time schedule'!R57","v":0},{"$f":"'K20 - time schedule'!S57","v":0},{"$f":"'K20 - time schedule'!T57","v":0},{"$f":"'K20 - time schedule'!U57","v":0},{"$f":"'K20 - time schedule'!V57","v":0},{"$f":"'K20 - time schedule'!W57","v":0},{"$f":"'K20 - time schedule'!X57","v":0},{"$f":"'K20 - time schedule'!Y57","v":0},{"$f":"'K20 - time schedule'!Z57","v":0},{"$f":"'K20 - time schedule'!AA57","v":0},{"$f":"'K20 - time schedule'!AB57","v":0},{"$f":"'K20 - time schedule'!AC57","v":0},{"$f":"'K20 - time schedule'!AD57","v":0},{"$f":"'K20 - time schedule'!AE57","v":0},{"$f":"'K20 - time schedule'!AF57","v":0},{"$f":"'K20 - time schedule'!AG57","v":0},{"$f":"'K20 - time schedule'!AH57","v":0},{"$f":"'K20 - time schedule'!AI57","v":0},{"$f":"'K20 - time schedule'!AJ57","v":0},{"$f":"'K20 - time schedule'!AK57","v":0},{"$f":"'K20 - time schedule'!AL57","v":0},{"$f":"'K20 - time schedule'!AM57","v":0},{"$f":"'K20 - time schedule'!AN57","v":0},{"$f":"'K20 - time schedule'!AO57","v":0},{"$f":"'K20 - time schedule'!AP57","v":0},{"$f":"'K20 - time schedule'!AQ57","v":0},{"$f":"'K20 - time schedule'!AR57","v":0},{"$f":"'K20 - time schedule'!AS57","v":0},{"$f":"'K20 - time schedule'!AT57","v":0},{"$f":"'K20 - time schedule'!AU57","v":0},{"$f":"'K20 - time schedule'!AV57","v":0},{"$f":"'K20 - time schedule'!AW57","v":0},{"$f":"'K20 - time schedule'!AX57","v":0},{"$f":"'K20 - time schedule'!AY57","v":0},{"$f":"'K20 - time schedule'!AZ57","v":0},{"$f":"'K20 - time schedule'!BA57","v":0},{"$f":"'K20 - time schedule'!BB57","v":0},{"$f":"'K20 - time schedule'!BC57","v":0},{"$f":"'K20 - time schedule'!BD57","v":0},{"$f":"'K20 - time schedule'!BE57","v":0},{"$f":"'K20 - time schedule'!BF57","v":0},{"$f":"'K20 - time schedule'!BG57","v":0},{"$f":"'K20 - time schedule'!BH57","v":0},{"$f":"'K20 - time schedule'!BI57","v":0},{"$f":"'K20 - time schedule'!BJ57","v":0},{"$f":"'K20 - time schedule'!BK57","v":0},{"$f":"'K20 - time schedule'!BL57","v":0},{"$f":"'K20 - time schedule'!BM57","v":0},{"$f":"'K20 - time schedule'!BN57","v":0},{"$f":"'K20 - time schedule'!BO57","v":0},{"$f":"'K20 - time schedule'!BP57","v":0},{"$f":"'K20 - time schedule'!BQ57","v":0},{"$f":"'K20 - time schedule'!BR57","v":0},{"$f":"'K20 - time schedule'!BS57","v":0},{"$f":"'K20 - time schedule'!BT57","v":0},{"$f":"'K20 - time schedule'!BU57","v":0},{"$f":"'K20 - time schedule'!BV57","v":0},{"$f":"'K20 - time schedule'!BW57","v":0},{"$f":"'K20 - time schedule'!BX57","v":0},{"$f":"'K20 - time schedule'!BY57","v":0},{"$f":"'K20 - time schedule'!BZ57","v":0},{"$f":"'K20 - time schedule'!CA57","v":0},{"$f":"'K20 - time schedule'!CB57","v":0},{"$f":"'K20 - time schedule'!CC57","v":0},{"$f":"'K20 - time schedule'!CD57","v":0},{"$f":"'K20 - time schedule'!CE57","v":0},{"$f":"'K20 - time schedule'!CF57","v":0},{"$f":"'K20 - time schedule'!CG57","v":0},{"$f":"'K20 - time schedule'!CH57","v":0},{"$f":"'K20 - time schedule'!CI57","v":0},{"$f":"'K20 - time schedule'!CJ57","v":0},{"$f":"'K20 - time schedule'!CK57","v":0},{"$f":"'K20 - time schedule'!CL57","v":0},{"$f":"'K20 - time schedule'!CM57","v":0},{"$f":"'K20 - time schedule'!CN57","v":0},{"$f":"'K20 - time schedule'!CO57","v":0},{"$f":"'K20 - time schedule'!CP57","v":0},{"$f":"'K20 - time schedule'!CQ57","v":0},{"$f":"'K20 - time schedule'!CR57","v":0},{"$f":"'K20 - time schedule'!CS57","v":0},{"$f":"'K20 - time schedule'!CT57","v":0},{"$f":"'K20 - time schedule'!CU57","v":0},{"$f":"'K20 - time schedule'!CV57","v":0},{"$f":"'K20 - time schedule'!CW57","v":0},{"$f":"'K20 - time schedule'!CX57","v":0},{"$f":"'K20 - time schedule'!CY57","v":0},{"$f":"'K20 - time schedule'!CZ57","v":0},{"$f":"'K20 - time schedule'!DA57","v":0},{"$f":"'K20 - time schedule'!DB57","v":0},{"$f":"'K20 - time schedule'!DC57","v":0},{"$f":"'K20 - time schedule'!DD57","v":0},{"$f":"'K20 - time schedule'!DE57","v":0},{"$f":"'K20 - time schedule'!DF57","v":0},{"$f":"'K20 - time schedule'!DG57","v":0},{"$f":"'K20 - time schedule'!DH57","v":0},{"$f":"'K20 - time schedule'!DI57","v":0},{"$f":"'K20 - time schedule'!DJ57","v":0},{"$f":"'K20 - time schedule'!DK57","v":0},{"$f":"'K20 - time schedule'!DL57","v":0},{"$f":"'K20 - time schedule'!DM57","v":0},{"$f":"'K20 - time schedule'!DN57","v":0},{"$f":"'K20 - time schedule'!DO57","v":0},{"$f":"'K20 - time schedule'!DP57","v":0},{"$f":"'K20 - time schedule'!DQ57","v":0},{"$f":"'K20 - time schedule'!DR57","v":0},{"$f":"'K20 - time schedule'!DS57","v":0},{"$f":"'K20 - time schedule'!DT57","v":0},{"$f":"'K20 - time schedule'!DU57","v":0},{"$f":"'K20 - time schedule'!DV57","v":0},{"$f":"'K20 - time schedule'!DW57","v":0},{"$f":"'K20 - time schedule'!DX57","v":0},{"$f":"'K20 - time schedule'!DY57","v":0},{"$f":"'K20 - time schedule'!DZ57","v":0},{"$f":"'K20 - time schedule'!EA57","v":0},{"$f":"'K20 - time schedule'!EB57","v":0},{"$f":"'K20 - time schedule'!EC57","v":0},{"$f":"'K20 - time schedule'!ED57","v":0},{"$f":"'K20 - time schedule'!EE57","v":0},{"$f":"'K20 - time schedule'!EF57","v":0},{"$f":"'K20 - time schedule'!EG57","v":0},{"$f":"'K20 - time schedule'!EH57","v":0},{"$f":"'K20 - time schedule'!EI57","v":0},{"$f":"'K20 - time schedule'!EJ57","v":0},{"$f":"'K20 - time schedule'!EK57","v":0},{"$f":"'K20 - time schedule'!EL57","v":0},{"$f":"'K20 - time schedule'!EM57","v":0},{"$f":"'K20 - time schedule'!EN57","v":0},{"$f":"'K20 - time schedule'!EO57","v":0},{"$f":"'K20 - time schedule'!EP57","v":0},{"$f":"'K20 - time schedule'!EQ57","v":0},{"$f":"'K20 - time schedule'!ER57","v":0},{"$f":"'K20 - time schedule'!ES57","v":0},{"$f":"'K20 - time schedule'!ET57","v":0},{"$f":"'K20 - time schedule'!EU57","v":0},{"$f":"'K20 - time schedule'!EV57","v":0},{"$f":"'K20 - time schedule'!EW57","v":0},{"$f":"'K20 - time schedule'!EX57","v":0},{"$f":"'K20 - time schedule'!EY57","v":0},{"$f":"'K20 - time schedule'!EZ57","v":0},{"$f":"'K20 - time schedule'!FA57","v":0},{"$f":"'K20 - time schedule'!FB57","v":0},{"$f":"'K20 - time schedule'!FC57","v":0},{"$f":"'K20 - time schedule'!FD57","v":0},{"$f":"'K20 - time schedule'!FE57","v":0},{"$f":"'K20 - time schedule'!FF57","v":0},{"$f":"'K20 - time schedule'!FG57","v":0},{"$f":"'K20 - time schedule'!FH57","v":0},{"$f":"'K20 - time schedule'!FI57","v":0},{"$f":"'K20 - time schedule'!FJ57","v":0},{"$f":"'K20 - time schedule'!FK57","v":0},{"$f":"'K20 - time schedule'!FL57","v":0},{"$f":"'K20 - time schedule'!FM57","v":0},{"$f":"'K20 - time schedule'!FN57","v":0},{"$f":"'K20 - time schedule'!FO57","v":0},{"$f":"'K20 - time schedule'!FP57","v":0},{"$f":"'K20 - time schedule'!FQ57","v":0},{"$f":"'K20 - time schedule'!FR57","v":0},{"$f":"'K20 - time schedule'!FS57","v":0},{"$f":"'K20 - time schedule'!FT57","v":0},{"$f":"'K20 - time schedule'!FU57","v":0},{"$f":"'K20 - time schedule'!FV57","v":0},{"$f":"'K20 - time schedule'!FW57","v":0},{"$f":"'K20 - time schedule'!FX57","v":0},{"$f":"'K20 - time schedule'!FY57","v":0},{"$f":"'K20 - time schedule'!FZ57","v":0},{"$f":"'K20 - time schedule'!GA57","v":0},{"$f":"'K20 - time schedule'!GB57","v":0},{"$f":"'K20 - time schedule'!GC57","v":0},{"$f":"'K20 - time schedule'!GD57","v":0},{"$f":"'K20 - time schedule'!GE57","v":0},{"$f":"'K20 - time schedule'!GF57","v":0},{"$f":"'K20 - time schedule'!GG57","v":0},{"$f":"'K20 - time schedule'!GH35","v":0},{"$f":"'K20 - time schedule'!GI35","v":0},{"$f":"'K20 - time schedule'!GJ35","v":0},{"$f":"'K20 - time schedule'!GK35","v":0},{"$f":"'K20 - time schedule'!GL35","v":0},{"$f":"'K20 - time schedule'!GM35","v":0},{"$f":"'K20 - time schedule'!GN35","v":0},{"$f":"'K20 - time schedule'!GO35","v":0},{"$f":"'K20 - time schedule'!GP35","v":0},{"$f":"'K20 - time schedule'!GQ35","v":0},{"$f":"'K20 - time schedule'!GR35","v":0},{"$f":"'K20 - time schedule'!GS35","v":0},{"$f":"'K20 - time schedule'!GT35","v":0},{"$f":"'K20 - time schedule'!GU35","v":0},{"$f":"'K20 - time schedule'!GV35","v":0},{"$f":"'K20 - time schedule'!GW35","v":0},{"$f":"'K20 - time schedule'!GX35","v":0},{"$f":"'K20 - time schedule'!GY35","v":0},{"$f":"'K20 - time schedule'!GZ35","v":0},{"$f":"'K20 - time schedule'!HA35","v":0},{"$f":"'K20 - time schedule'!HB35","v":0},{"$f":"'K20 - time schedule'!HC35","v":0},{"$f":"'K20 - time schedule'!HD35","v":0},{"$f":"'K20 - time schedule'!HE35","v":0},{"$f":"'K20 - time schedule'!HF35","v":0},{"$f":"'K20 - time schedule'!HG35","v":0},{"$f":"'K20 - time schedule'!HH35","v":0},{"$f":"'K20 - time schedule'!HI35","v":0},{"$f":"'K20 - time schedule'!HJ35","v":0},{"$f":"'K20 - time schedule'!HK35","v":0},{"$f":"'K20 - time schedule'!HL35","v":0},{"$f":"'K20 - time schedule'!HM35","v":0},{"$f":"'K20 - time schedule'!HN35","v":0},{"$f":"'K20 - time schedule'!HO35","v":0},{"$f":"'K20 - time schedule'!HP35","v":0},{"$f":"'K20 - time schedule'!HQ35","v":0},{"$f":"'K20 - time schedule'!HR35","v":0},{"$f":"'K20 - time schedule'!HS35","v":0},{"$f":"'K20 - time schedule'!HT35","v":0},{"$f":"'K20 - time schedule'!HU35","v":0},{"$f":"'K20 - time schedule'!HV35","v":0},{"$f":"'K20 - time schedule'!HW35","v":0},{"$f":"'K20 - time schedule'!HX35","v":0},{"$f":"'K20 - time schedule'!HY35","v":0},{"$f":"'K20 - time schedule'!HZ35","v":0},{"$f":"'K20 - time schedule'!IA35","v":0},{"$f":"'K20 - time schedule'!IB35","v":0},{"$f":"'K20 - time schedule'!IC35","v":0},{"$f":"'K20 - time schedule'!ID35","v":0},{"$f":"'K20 - time schedule'!IE35","v":0},{"$f":"'K20 - time schedule'!IF35","v":0},{"$f":"'K20 - time schedule'!IG35","v":0},{"$f":"'K20 - time schedule'!IH35","v":0},{"$f":"'K20 - time schedule'!II35","v":0},{"$f":"'K20 - time schedule'!IJ35","v":0},{"$f":"'K20 - time schedule'!IK35","v":0},{"$f":"'K20 - time schedule'!IL35","v":0},{"$f":"'K20 - time schedule'!IM35","v":0},{"$f":"'K20 - time schedule'!IN35","v":0},{"$f":"'K20 - time schedule'!IO35","v":0},{"$f":"'K20 - time schedule'!IP35","v":0},{"$f":"'K20 - time schedule'!IQ35","v":0},{"$f":"'K20 - time schedule'!IR35","v":0},{"$f":"'K20 - time schedule'!IS35","v":0},{"$f":"'K20 - time schedule'!IT35","v":0},{"$f":"'K20 - time schedule'!IU35","v":0},{"$f":"'K20 - time schedule'!IV35","v":0},{"$f":"'K20 - time schedule'!IW35","v":0},{"$f":"'K20 - time schedule'!IX35","v":0},{"$f":"'K20 - time schedule'!IY35","v":0},{"$f":"'K20 - time schedule'!IZ35","v":0},{"$f":"'K20 - time schedule'!JA35","v":0},{"$f":"'K20 - time schedule'!JB35","v":0},{"$f":"'K20 - time schedule'!JC35","v":0},{"$f":"'K20 - time schedule'!JD35","v":0},{"$f":"'K20 - time schedule'!JE35","v":0},{"$f":"'K20 - time schedule'!JF35","v":0},{"$f":"'K20 - time schedule'!JG35","v":0},{"$f":"'K20 - time schedule'!JH35","v":0},{"$f":"'K20 - time schedule'!JI35","v":0},{"$f":"'K20 - time schedule'!JJ35","v":0},{"$f":"'K20 - time schedule'!JK35","v":0},{"$f":"'K20 - time schedule'!JL35","v":0},{"$f":"'K20 - time schedule'!JM35","v":0},{"$f":"'K20 - time schedule'!JN35","v":0},{"$f":"'K20 - time schedule'!JO35","v":0},{"$f":"'K20 - time schedule'!JP35","v":0},{"$f":"'K20 - time schedule'!JQ35","v":0},{"$f":"'K20 - time schedule'!JR35","v":0},{"$f":"'K20 - time schedule'!JS35","v":0},{"$f":"'K20 - time schedule'!JT35","v":0},{"$f":"'K20 - time schedule'!JU35","v":0},{"$f":"'K20 - time schedule'!JV35","v":0},{"$f":"'K20 - time schedule'!JW35","v":0},{"$f":"'K20 - time schedule'!JX35","v":0},{"$f":"'K20 - time schedule'!JY35","v":0},{"$f":"'K20 - time schedule'!JZ35","v":0},{"$f":"'K20 - time schedule'!KA35","v":0},{"$f":"'K20 - time schedule'!KB35","v":0},{"$f":"'K20 - time schedule'!KC35","v":0},{"$f":"'K20 - time schedule'!KD35","v":0},{"$f":"'K20 - time schedule'!KE35","v":0},{"$f":"'K20 - time schedule'!KF35","v":0},{"$f":"'K20 - time schedule'!KG35","v":0},{"$f":"'K20 - time schedule'!KH35","v":0},{"$f":"'K20 - time schedule'!KI35","v":0},{"$f":"'K20 - time schedule'!KJ35","v":0},{"$f":"'K20 - time schedule'!KK35","v":0},{"$f":"'K20 - time schedule'!KL35","v":0},{"$f":"'K20 - time schedule'!KM35","v":0},{"$f":"'K20 - time schedule'!KN35","v":0},{"$f":"'K20 - time schedule'!KO35","v":0},{"$f":"'K20 - time schedule'!KP35","v":0},{"$f":"'K20 - time schedule'!KQ35","v":0},{"$f":"'K20 - time schedule'!KR35","v":0},{"$f":"'K20 - time schedule'!KS35","v":0},{"$f":"'K20 - time schedule'!KT35","v":0}]
["Boiler room K20 - preliminary acceptance of the Work PAC","K20",{"$f":"'K20 - time schedule'!G59","v":0},{"$f":"'K20 - time schedule'!H59","v":0},{"$f":"'K20 - time schedule'!I59","v":0},{"$f":"'K20 - time schedule'!J59","v":0},{"$f":"'K20 - time schedule'!K59","v":0},{"$f":"'K20 - time schedule'!L59","v":0},{"$f":"'K20 - time schedule'!M59","v":0},{"$f":"'K20 - time schedule'!N59","v":0},{"$f":"'K20 - time schedule'!O59","v":0},{"$f":"'K20 - time schedule'!P59","v":0},{"$f":"'K20 - time schedule'!Q59","v":0},{"$f":"'K20 - time schedule'!R59","v":0},{"$f":"'K20 - time schedule'!S59","v":0},{"$f":"'K20 - time schedule'!T59","v":0},{"$f":"'K20 - time schedule'!U59","v":0},{"$f":"'K20 - time schedule'!V59","v":0},{"$f":"'K20 - time schedule'!W59","v":0},{"$f":"'K20 - time schedule'!X59","v":0},{"$f":"'K20 - time schedule'!Y59","v":0},{"$f":"'K20 - time schedule'!Z59","v":0},{"$f":"'K20 - time schedule'!AA59","v":0},{"$f":"'K20 - time schedule'!AB59","v":0},{"$f":"'K20 - time schedule'!AC59","v":0},{"$f":"'K20 - time schedule'!AD59","v":0},{"$f":"'K20 - time schedule'!AE59","v":0},{"$f":"'K20 - time schedule'!AF59","v":0},{"$f":"'K20 - time schedule'!AG59","v":0},{"$f":"'K20 - time schedule'!AH59","v":0},{"$f":"'K20 - time schedule'!AI59","v":0},{"$f":"'K20 - time schedule'!AJ59","v":0},{"$f":"'K20 - time schedule'!AK59","v":0},{"$f":"'K20 - time schedule'!AL59","v":0},{"$f":"'K20 - time schedule'!AM59","v":0},{"$f":"'K20 - time schedule'!AN59","v":0},{"$f":"'K20 - time schedule'!AO59","v":0},{"$f":"'K20 - time schedule'!AP59","v":0},{"$f":"'K20 - time schedule'!AQ59","v":0},{"$f":"'K20 - time schedule'!AR59","v":0},{"$f":"'K20 - time schedule'!AS59","v":0},{"$f":"'K20 - time schedule'!AT59","v":0},{"$f":"'K20 - time schedule'!AU59","v":0},{"$f":"'K20 - time schedule'!AV59","v":0},{"$f":"'K20 - time schedule'!AW59","v":0},{"$f":"'K20 - time schedule'!AX59","v":0},{"$f":"'K20 - time schedule'!AY59","v":0},{"$f":"'K20 - time schedule'!AZ59","v":0},{"$f":"'K20 - time schedule'!BA59","v":0},{"$f":"'K20 - time schedule'!BB59","v":0},{"$f":"'K20 - time schedule'!BC59","v":0},{"$f":"'K20 - time schedule'!BD59","v":0},{"$f":"'K20 - time schedule'!BE59","v":0},{"$f":"'K20 - time schedule'!BF59","v":0},{"$f":"'K20 - time schedule'!BG59","v":0},{"$f":"'K20 - time schedule'!BH59","v":0},{"$f":"'K20 - time schedule'!BI59","v":0},{"$f":"'K20 - time schedule'!BJ59","v":0},{"$f":"'K20 - time schedule'!BK59","v":0},{"$f":"'K20 - time schedule'!BL59","v":0},{"$f":"'K20 - time schedule'!BM59","v":0},{"$f":"'K20 - time schedule'!BN59","v":0},{"$f":"'K20 - time schedule'!BO59","v":0},{"$f":"'K20 - time schedule'!BP59","v":0},{"$f":"'K20 - time schedule'!BQ59","v":0},{"$f":"'K20 - time schedule'!BR59","v":0},{"$f":"'K20 - time schedule'!BS59","v":0},{"$f":"'K20 - time schedule'!BT59","v":0},{"$f":"'K20 - time schedule'!BU59","v":0},{"$f":"'K20 - time schedule'!BV59","v":0},{"$f":"'K20 - time schedule'!BW59","v":0},{"$f":"'K20 - time schedule'!BX59","v":0},{"$f":"'K20 - time schedule'!BY59","v":0},{"$f":"'K20 - time schedule'!BZ59","v":0},{"$f":"'K20 - time schedule'!CA59","v":0},{"$f":"'K20 - time schedule'!CB59","v":0},{"$f":"'K20 - time schedule'!CC59","v":0},{"$f":"'K20 - time schedule'!CD59","v":0},{"$f":"'K20 - time schedule'!CE59","v":0},{"$f":"'K20 - time schedule'!CF59","v":0},{"$f":"'K20 - time schedule'!CG59","v":0},{"$f":"'K20 - time schedule'!CH59","v":0},{"$f":"'K20 - time schedule'!CI59","v":0},{"$f":"'K20 - time schedule'!CJ59","v":0},{"$f":"'K20 - time schedule'!CK59","v":0},{"$f":"'K20 - time schedule'!CL59","v":0},{"$f":"'K20 - time schedule'!CM59","v":0},{"$f":"'K20 - time schedule'!CN59","v":0},{"$f":"'K20 - time schedule'!CO59","v":0},{"$f":"'K20 - time schedule'!CP59","v":0},{"$f":"'K20 - time schedule'!CQ59","v":0},{"$f":"'K20 - time schedule'!CR59","v":0},{"$f":"'K20 - time schedule'!CS59","v":0},{"$f":"'K20 - time schedule'!CT59","v":0},{"$f":"'K20 - time schedule'!CU59","v":0},{"$f":"'K20 - time schedule'!CV59","v":0},{"$f":"'K20 - time schedule'!CW59","v":0},{"$f":"'K20 - time schedule'!CX59","v":0},{"$f":"'K20 - time schedule'!CY59","v":0},{"$f":"'K20 - time schedule'!CZ59","v":0},{"$f":"'K20 - time schedule'!DA59","v":0},{"$f":"'K20 - time schedule'!DB59","v":0},{"$f":"'K20 - time schedule'!DC59","v":0},{"$f":"'K20 - time schedule'!DD59","v":0},{"$f":"'K20 - time schedule'!DE59","v":0},{"$f":"'K20 - time schedule'!DF59","v":0},{"$f":"'K20 - time schedule'!DG59","v":0},{"$f":"'K20 - time schedule'!DH59","v":0},{"$f":"'K20 - time schedule'!DI59","v":0},{"$f":"'K20 - time schedule'!DJ59","v":0},{"$f":"'K20 - time schedule'!DK59","v":0},{"$f":"'K20 - time schedule'!DL59","v":0},{"$f":"'K20 - time schedule'!DM59","v":0},{"$f":"'K20 - time schedule'!DN59","v":0},{"$f":"'K20 - time schedule'!DO59","v":0},{"$f":"'K20 - time schedule'!DP59","v":0},{"$f":"'K20 - time schedule'!DQ59","v":0},{"$f":"'K20 - time schedule'!DR59","v":0},{"$f":"'K20 - time schedule'!DS59","v":0},{"$f":"'K20 - time schedule'!DT59","v":0},{"$f":"'K20 - time schedule'!DU59","v":0},{"$f":"'K20 - time schedule'!DV59","v":0},{"$f":"'K20 - time schedule'!DW59","v":0},{"$f":"'K20 - time schedule'!DX59","v":0},{"$f":"'K20 - time schedule'!DY59","v":0},{"$f":"'K20 - time schedule'!DZ59","v":0},{"$f":"'K20 - time schedule'!EA59","v":0},{"$f":"'K20 - time schedule'!EB59","v":0},{"$f":"'K20 - time schedule'!EC59","v":0},{"$f":"'K20 - time schedule'!ED59","v":0},{"$f":"'K20 - time schedule'!EE59","v":0},{"$f":"'K20 - time schedule'!EF59","v":0},{"$f":"'K20 - time schedule'!EG59","v":0},{"$f":"'K20 - time schedule'!EH59","v":0},{"$f":"'K20 - time schedule'!EI59","v":0},{"$f":"'K20 - time schedule'!EJ59","v":0},{"$f":"'K20 - time schedule'!EK59","v":0},{"$f":"'K20 - time schedule'!EL59","v":0},{"$f":"'K20 - time schedule'!EM59","v":0},{"$f":"'K20 - time schedule'!EN59","v":0},{"$f":"'K20 - time schedule'!EO59","v":0},{"$f":"'K20 - time schedule'!EP59","v":0},{"$f":"'K20 - time schedule'!EQ59","v":0},{"$f":"'K20 - time schedule'!ER59","v":0},{"$f":"'K20 - time schedule'!ES59","v":0},{"$f":"'K20 - time schedule'!ET59","v":0},{"$f":"'K20 - time schedule'!EU59","v":0},{"$f":"'K20 - time schedule'!EV59","v":0},{"$f":"'K20 - time schedule'!EW59","v":0},{"$f":"'K20 - time schedule'!EX59","v":0},{"$f":"'K20 - time schedule'!EY59","v":0},{"$f":"'K20 - time schedule'!EZ59","v":0},{"$f":"'K20 - time schedule'!FA59","v":0},{"$f":"'K20 - time schedule'!FB59","v":0},{"$f":"'K20 - time schedule'!FC59","v":0},{"$f":"'K20 - time schedule'!FD59","v":0},{"$f":"'K20 - time schedule'!FE59","v":0},{"$f":"'K20 - time schedule'!FF59","v":0},{"$f":"'K20 - time schedule'!FG59","v":0},{"$f":"'K20 - time schedule'!FH59","v":0},{"$f":"'K20 - time schedule'!FI59","v":0},{"$f":"'K20 - time schedule'!FJ59","v":0},{"$f":"'K20 - time schedule'!FK59","v":0},{"$f":"'K20 - time schedule'!FL59","v":0},{"$f":"'K20 - time schedule'!FM59","v":0},{"$f":"'K20 - time schedule'!FN59","v":0},{"$f":"'K20 - time schedule'!FO59","v":0},{"$f":"'K20 - time schedule'!FP59","v":0},{"$f":"'K20 - time schedule'!FQ59","v":0},{"$f":"'K20 - time schedule'!FR59","v":0},{"$f":"'K20 - time schedule'!FS59","v":0},{"$f":"'K20 - time schedule'!FT59","v":0},{"$f":"'K20 - time schedule'!FU59","v":0},{"$f":"'K20 - time schedule'!FV59","v":0},{"$f":"'K20 - time schedule'!FW59","v":0},{"$f":"'K20 - time schedule'!FX59","v":0},{"$f":"'K20 - time schedule'!FY59","v":0},{"$f":"'K20 - time schedule'!FZ59","v":0},{"$f":"'K20 - time schedule'!GA59","v":0},{"$f":"'K20 - time schedule'!GB59","v":0},{"$f":"'K20 - time schedule'!GC59","v":0},{"$f":"'K20 - time schedule'!GD59","v":0},{"$f":"'K20 - time schedule'!GE59","v":0},{"$f":"'K20 - time schedule'!GF59","v":0},{"$f":"'K20 - time schedule'!GG59","v":0},{"$f":"'K20 - time schedule'!GH36","v":0},{"$f":"'K20 - time schedule'!GI36","v":0},{"$f":"'K20 - time schedule'!GJ36","v":0},{"$f":"'K20 - time schedule'!GK36","v":0},{"$f":"'K20 - time schedule'!GL36","v":0},{"$f":"'K20 - time schedule'!GM36","v":0},{"$f":"'K20 - time schedule'!GN36","v":0},{"$f":"'K20 - time schedule'!GO36","v":0},{"$f":"'K20 - time schedule'!GP36","v":0},{"$f":"'K20 - time schedule'!GQ36","v":0},{"$f":"'K20 - time schedule'!GR36","v":0},{"$f":"'K20 - time schedule'!GS36","v":0},{"$f":"'K20 - time schedule'!GT36","v":0},{"$f":"'K20 - time schedule'!GU36","v":0},{"$f":"'K20 - time schedule'!GV36","v":0},{"$f":"'K20 - time schedule'!GW36","v":0},{"$f":"'K20 - time schedule'!GX36","v":0},{"$f":"'K20 - time schedule'!GY36","v":0},{"$f":"'K20 - time schedule'!GZ36","v":0},{"$f":"'K20 - time schedule'!HA36","v":0},{"$f":"'K20 - time schedule'!HB36","v":0},{"$f":"'K20 - time schedule'!HC36","v":0},{"$f":"'K20 - time schedule'!HD36","v":0},{"$f":"'K20 - time schedule'!HE36","v":0},{"$f":"'K20 - time schedule'!HF36","v":0},{"$f":"'K20 - time schedule'!HG36","v":0},{"$f":"'K20 - time schedule'!HH36","v":0},{"$f":"'K20 - time schedule'!HI36","v":0},{"$f":"'K20 - time schedule'!HJ36","v":0},{"$f":"'K20 - time schedule'!HK36","v":0},{"$f":"'K20 - time schedule'!HL36","v":0},{"$f":"'K20 - time schedule'!HM36","v":0},{"$f":"'K20 - time schedule'!HN36","v":0},{"$f":"'K20 - time schedule'!HO36","v":0},{"$f":"'K20 - time schedule'!HP36","v":0},{"$f":"'K20 - time schedule'!HQ36","v":0},{"$f":"'K20 - time schedule'!HR36","v":0},{"$f":"'K20 - time schedule'!HS36","v":0},{"$f":"'K20 - time schedule'!HT36","v":0},{"$f":"'K20 - time schedule'!HU36","v":0},{"$f":"'K20 - time schedule'!HV36","v":0},{"$f":"'K20 - time schedule'!HW36","v":0},{"$f":"'K20 - time schedule'!HX36","v":0},{"$f":"'K20 - time schedule'!HY36","v":0},{"$f":"'K20 - time schedule'!HZ36","v":0},{"$f":"'K20 - time schedule'!IA36","v":0},{"$f":"'K20 - time schedule'!IB36","v":0},{"$f":"'K20 - time schedule'!IC36","v":0},{"$f":"'K20 - time schedule'!ID36","v":0},{"$f":"'K20 - time schedule'!IE36","v":0},{"$f":"'K20 - time schedule'!IF36","v":0},{"$f":"'K20 - time schedule'!IG36","v":0},{"$f":"'K20 - time schedule'!IH36","v":0},{"$f":"'K20 - time schedule'!II36","v":0},{"$f":"'K20 - time schedule'!IJ36","v":0},{"$f":"'K20 - time schedule'!IK36","v":0},{"$f":"'K20 - time schedule'!IL36","v":0},{"$f":"'K20 - time schedule'!IM36","v":0},{"$f":"'K20 - time schedule'!IN36","v":0},{"$f":"'K20 - time schedule'!IO36","v":0},{"$f":"'K20 - time schedule'!IP36","v":0},{"$f":"'K20 - time schedule'!IQ36","v":0},{"$f":"'K20 - time schedule'!IR36","v":0},{"$f":"'K20 - time schedule'!IS36","v":0},{"$f":"'K20 - time schedule'!IT36","v":0},{"$f":"'K20 - time schedule'!IU36","v":0},{"$f":"'K20 - time schedule'!IV36","v":0},{"$f":"'K20 - time schedule'!IW36","v":0},{"$f":"'K20 - time schedule'!IX36","v":0},{"$f":"'K20 - time schedule'!IY36","v":0},{"$f":"'K20 - time schedule'!IZ36","v":0},{"$f":"'K20 - time schedule'!JA36","v":0},{"$f":"'K20 - time schedule'!JB36","v":0},{"$f":"'K20 - time schedule'!JC36","v":0},{"$f":"'K20 - time schedule'!JD36","v":0},{"$f":"'K20 - time schedule'!JE36","v":0},{"$f":"'K20 - time schedule'!JF36","v":0},{"$f":"'K20 - time schedule'!JG36","v":0},{"$f":"'K20 - time schedule'!JH36","v":0},{"$f":"'K20 - time schedule'!JI36","v":0},{"$f":"'K20 - time schedule'!JJ36","v":0},{"$f":"'K20 - time schedule'!JK36","v":0},{"$f":"'K20 - time schedule'!JL36","v":0},{"$f":"'K20 - time schedule'!JM36","v":0},{"$f":"'K20 - time schedule'!JN36","v":0},{"$f":"'K20 - time schedule'!JO36","v":0},{"$f":"'K20 - time schedule'!JP36","v":0},{"$f":"'K20 - time schedule'!JQ36","v":0},{"$f":"'K20 - time schedule'!JR36","v":0},{"$f":"'K20 - time schedule'!JS36","v":0},{"$f":"'K20 - time schedule'!JT36","v":0},{"$f":"'K20 - time schedule'!JU36","v":0},{"$f":"'K20 - time schedule'!JV36","v":0},{"$f":"'K20 - time schedule'!JW36","v":0},{"$f":"'K20 - time schedule'!JX36","v":0},{"$f":"'K20 - time schedule'!JY36","v":0},{"$f":"'K20 - time schedule'!JZ36","v":0},{"$f":"'K20 - time schedule'!KA36","v":0},{"$f":"'K20 - time schedule'!KB36","v":0},{"$f":"'K20 - time schedule'!KC36","v":0},{"$f":"'K20 - time schedule'!KD36","v":0},{"$f":"'K20 - time schedule'!KE36","v":0},{"$f":"'K20 - time schedule'!KF36","v":0},{"$f":"'K20 - time schedule'!KG36","v":0},{"$f":"'K20 - time schedule'!KH36","v":0},{"$f":"'K20 - time schedule'!KI36","v":0},{"$f":"'K20 - time schedule'!KJ36","v":0},{"$f":"'K20 - time schedule'!KK36","v":0},{"$f":"'K20 - time schedule'!KL36","v":0},{"$f":"'K20 - time schedule'!KM36","v":0},{"$f":"'K20 - time schedule'!KN36","v":0},{"$f":"'K20 - time schedule'!KO36","v":0},{"$f":"'K20 - time schedule'!KP36","v":0},{"$f":"'K20 - time schedule'!KQ36","v":0},{"$f":"'K20 - time schedule'!KR36","v":0},{"$f":"'K20 - time schedule'!KS36","v":0},{"$f":"'K20 - time schedule'!KT36","v":0}]
["Boiler room K20 - guarantee test B","K20",{"$f":"'K20 - time schedule'!G61","v":0},{"$f":"'K20 - time schedule'!H61","v":0},{"$f":"'K20 - time schedule'!I61","v":0},{"$f":"'K20 - time schedule'!J61","v":0},{"$f":"'K20 - time schedule'!K61","v":0},{"$f":"'K20 - time schedule'!L61","v":0},{"$f":"'K20 - time schedule'!M61","v":0},{"$f":"'K20 - time schedule'!N61","v":0},{"$f":"'K20 - time schedule'!O61","v":0},{"$f":"'K20 - time schedule'!P61","v":0},{"$f":"'K20 - time schedule'!Q61","v":0},{"$f":"'K20 - time schedule'!R61","v":0},{"$f":"'K20 - time schedule'!S61","v":0},{"$f":"'K20 - time schedule'!T61","v":0},{"$f":"'K20 - time schedule'!U61","v":0},{"$f":"'K20 - time schedule'!V61","v":0},{"$f":"'K20 - time schedule'!W61","v":0},{"$f":"'K20 - time schedule'!X61","v":0},{"$f":"'K20 - time schedule'!Y61","v":0},{"$f":"'K20 - time schedule'!Z61","v":0},{"$f":"'K20 - time schedule'!AA61","v":0},{"$f":"'K20 - time schedule'!AB61","v":0},{"$f":"'K20 - time schedule'!AC61","v":0},{"$f":"'K20 - time schedule'!AD61","v":0},{"$f":"'K20 - time schedule'!AE61","v":0},{"$f":"'K20 - time schedule'!AF61","v":0},{"$f":"'K20 - time schedule'!AG61","v":0},{"$f":"'K20 - time schedule'!AH61","v":0},{"$f":"'K20 - time schedule'!AI61","v":0},{"$f":"'K20 - time schedule'!AJ61","v":0},{"$f":"'K20 - time schedule'!AK61","v":0},{"$f":"'K20 - time schedule'!AL61","v":0},{"$f":"'K20 - time schedule'!AM61","v":0},{"$f":"'K20 - time schedule'!AN61","v":0},{"$f":"'K20 - time schedule'!AO61","v":0},{"$f":"'K20 - time schedule'!AP61","v":0},{"$f":"'K20 - time schedule'!AQ61","v":0},{"$f":"'K20 - time schedule'!AR61","v":0},{"$f":"'K20 - time schedule'!AS61","v":0},{"$f":"'K20 - time schedule'!AT61","v":0},{"$f":"'K20 - time schedule'!AU61","v":0},{"$f":"'K20 - time schedule'!AV61","v":0},{"$f":"'K20 - time schedule'!AW61","v":0},{"$f":"'K20 - time schedule'!AX61","v":0},{"$f":"'K20 - time schedule'!AY61","v":0},{"$f":"'K20 - time schedule'!AZ61","v":0},{"$f":"'K20 - time schedule'!BA61","v":0},{"$f":"'K20 - time schedule'!BB61","v":0},{"$f":"'K20 - time schedule'!BC61","v":0},{"$f":"'K20 - time schedule'!BD61","v":0},{"$f":"'K20 - time schedule'!BE61","v":0},{"$f":"'K20 - time schedule'!BF61","v":0},{"$f":"'K20 - time schedule'!BG61","v":0},{"$f":"'K20 - time schedule'!BH61","v":0},{"$f":"'K20 - time schedule'!BI61","v":0},{"$f":"'K20 - time schedule'!BJ61","v":0},{"$f":"'K20 - time schedule'!BK61","v":0},{"$f":"'K20 - time schedule'!BL61","v":0},{"$f":"'K20 - time schedule'!BM61","v":0},{"$f":"'K20 - time schedule'!BN61","v":0},{"$f":"'K20 - time schedule'!BO61","v":0},{"$f":"'K20 - time schedule'!BP61","v":0},{"$f":"'K20 - time schedule'!BQ61","v":0},{"$f":"'K20 - time schedule'!BR61","v":0},{"$f":"'K20 - time schedule'!BS61","v":0},{"$f":"'K20 - time schedule'!BT61","v":0},{"$f":"'K20 - time schedule'!BU61","v":0},{"$f":"'K20 - time schedule'!BV61","v":0},{"$f":"'K20 - time schedule'!BW61","v":0},{"$f":"'K20 - time schedule'!BX61","v":0},{"$f":"'K20 - time schedule'!BY61","v":0},{"$f":"'K20 - time schedule'!BZ61","v":0},{"$f":"'K20 - time schedule'!CA61","v":0},{"$f":"'K20 - time schedule'!CB61","v":0},{"$f":"'K20 - time schedule'!CC61","v":0},{"$f":"'K20 - time schedule'!CD61","v":0},{"$f":"'K20 - time schedule'!CE61","v":0},{"$f":"'K20 - time schedule'!CF61","v":0},{"$f":"'K20 - time schedule'!CG61","v":0},{"$f":"'K20 - time schedule'!CH61","v":0},{"$f":"'K20 - time schedule'!CI61","v":0},{"$f":"'K20 - time schedule'!CJ61","v":0},{"$f":"'K20 - time schedule'!CK61","v":0},{"$f":"'K20 - time schedule'!CL61","v":0},{"$f":"'K20 - time schedule'!CM61","v":0},{"$f":"'K20 - time schedule'!CN61","v":0},{"$f":"'K20 - time schedule'!CO61","v":0},{"$f":"'K20 - time schedule'!CP61","v":0},{"$f":"'K20 - time schedule'!CQ61","v":0},{"$f":"'K20 - time schedule'!CR61","v":0},{"$f":"'K20 - time schedule'!CS61","v":0},{"$f":"'K20 - time schedule'!CT61","v":0},{"$f":"'K20 - time schedule'!CU61","v":0},{"$f":"'K20 - time schedule'!CV61","v":0},{"$f":"'K20 - time schedule'!CW61","v":0},{"$f":"'K20 - time schedule'!CX61","v":0},{"$f":"'K20 - time schedule'!CY61","v":0},{"$f":"'K20 - time schedule'!CZ61","v":0},{"$f":"'K20 - time schedule'!DA61","v":0},{"$f":"'K20 - time schedule'!DB61","v":0},{"$f":"'K20 - time schedule'!DC61","v":0},{"$f":"'K20 - time schedule'!DD61","v":0},{"$f":"'K20 - time schedule'!DE61","v":0},{"$f":"'K20 - time schedule'!DF61","v":0},{"$f":"'K20 - time schedule'!DG61","v":0},{"$f":"'K20 - time schedule'!DH61","v":0},{"$f":"'K20 - time schedule'!DI61","v":0},{"$f":"'K20 - time schedule'!DJ61","v":0},{"$f":"'K20 - time schedule'!DK61","v":0},{"$f":"'K20 - time schedule'!DL61","v":0},{"$f":"'K20 - time schedule'!DM61","v":0},{"$f":"'K20 - time schedule'!DN61","v":0},{"$f":"'K20 - time schedule'!DO61","v":0},{"$f":"'K20 - time schedule'!DP61","v":0},{"$f":"'K20 - time schedule'!DQ61","v":0},{"$f":"'K20 - time schedule'!DR61","v":0},{"$f":"'K20 - time schedule'!DS61","v":0},{"$f":"'K20 - time schedule'!DT61","v":0},{"$f":"'K20 - time schedule'!DU61","v":0},{"$f":"'K20 - time schedule'!DV61","v":0},{"$f":"'K20 - time schedule'!DW61","v":0},{"$f":"'K20 - time schedule'!DX61","v":0},{"$f":"'K20 - time schedule'!DY61","v":0},{"$f":"'K20 - time schedule'!DZ61","v":0},{"$f":"'K20 - time schedule'!EA61","v":0},{"$f":"'K20 - time schedule'!EB61","v":0},{"$f":"'K20 - time schedule'!EC61","v":0},{"$f":"'K20 - time schedule'!ED61","v":0},{"$f":"'K20 - time schedule'!EE61","v":0},{"$f":"'K20 - time schedule'!EF61","v":0},{"$f":"'K20 - time schedule'!EG61","v":0},{"$f":"'K20 - time schedule'!EH61","v":0},{"$f":"'K20 - time schedule'!EI61","v":0},{"$f":"'K20 - time schedule'!EJ61","v":0},{"$f":"'K20 - time schedule'!EK61","v":0},{"$f":"'K20 - time schedule'!EL61","v":0},{"$f":"'K20 - time schedule'!EM61","v":0},{"$f":"'K20 - time schedule'!EN61","v":0},{"$f":"'K20 - time schedule'!EO61","v":0},{"$f":"'K20 - time schedule'!EP61","v":0},{"$f":"'K20 - time schedule'!EQ61","v":0},{"$f":"'K20 - time schedule'!ER61","v":0},{"$f":"'K20 - time schedule'!ES61","v":0},{"$f":"'K20 - time schedule'!ET61","v":0},{"$f":"'K20 - time schedule'!EU61","v":0},{"$f":"'K20 - time schedule'!EV61","v":0},{"$f":"'K20 - time schedule'!EW61","v":0},{"$f":"'K20 - time schedule'!EX61","v":0},{"$f":"'K20 - time schedule'!EY61","v":0},{"$f":"'K20 - time schedule'!EZ61","v":0},{"$f":"'K20 - time schedule'!FA61","v":0},{"$f":"'K20 - time schedule'!FB61","v":0},{"$f":"'K20 - time schedule'!FC61","v":0},{"$f":"'K20 - time schedule'!FD61","v":0},{"$f":"'K20 - time schedule'!FE61","v":0},{"$f":"'K20 - time schedule'!FF61","v":0},{"$f":"'K20 - time schedule'!FG61","v":0},{"$f":"'K20 - time schedule'!FH61","v":0},{"$f":"'K20 - time schedule'!FI61","v":0},{"$f":"'K20 - time schedule'!FJ61","v":0},{"$f":"'K20 - time schedule'!FK61","v":0},{"$f":"'K20 - time schedule'!FL61","v":0},{"$f":"'K20 - time schedule'!FM61","v":0},{"$f":"'K20 - time schedule'!FN61","v":0},{"$f":"'K20 - time schedule'!FO61","v":0},{"$f":"'K20 - time schedule'!FP61","v":0},{"$f":"'K20 - time schedule'!FQ61","v":0},{"$f":"'K20 - time schedule'!FR61","v":0},{"$f":"'K20 - time schedule'!FS61","v":0},{"$f":"'K20 - time schedule'!FT61","v":0},{"$f":"'K20 - time schedule'!FU61","v":0},{"$f":"'K20 - time schedule'!FV61","v":0},{"$f":"'K20 - time schedule'!FW61","v":0},{"$f":"'K20 - time schedule'!FX61","v":0},{"$f":"'K20 - time schedule'!FY61","v":0},{"$f":"'K20 - time schedule'!FZ61","v":0},{"$f":"'K20 - time schedule'!GA61","v":0},{"$f":"'K20 - time schedule'!GB61","v":0},{"$f":"'K20 - time schedule'!GC61","v":0},{"$f":"'K20 - time schedule'!GD61","v":0},{"$f":"'K20 - time schedule'!GE61","v":0},{"$f":"'K20 - time schedule'!GF61","v":0},{"$f":"'K20 - time schedule'!GG61","v":0},{"$f":"'K20 - time schedule'!GH37","v":0},{"$f":"'K20 - time schedule'!GI37","v":0},{"$f":"'K20 - time schedule'!GJ37","v":0},{"$f":"'K20 - time schedule'!GK37","v":0},{"$f":"'K20 - time schedule'!GL37","v":0},{"$f":"'K20 - time schedule'!GM37","v":0},{"$f":"'K20 - time schedule'!GN37","v":0},{"$f":"'K20 - time schedule'!GO37","v":0},{"$f":"'K20 - time schedule'!GP37","v":0},{"$f":"'K20 - time schedule'!GQ37","v":0},{"$f":"'K20 - time schedule'!GR37","v":0},{"$f":"'K20 - time schedule'!GS37","v":0},{"$f":"'K20 - time schedule'!GT37","v":0},{"$f":"'K20 - time schedule'!GU37","v":0},{"$f":"'K20 - time schedule'!GV37","v":0},{"$f":"'K20 - time schedule'!GW37","v":0},{"$f":"'K20 - time schedule'!GX37","v":0},{"$f":"'K20 - time schedule'!GY37","v":0},{"$f":"'K20 - time schedule'!GZ37","v":0},{"$f":"'K20 - time schedule'!HA37","v":0},{"$f":"'K20 - time schedule'!HB37","v":0},{"$f":"'K20 - time schedule'!HC37","v":0},{"$f":"'K20 - time schedule'!HD37","v":0},{"$f":"'K20 - time schedule'!HE37","v":0},{"$f":"'K20 - time schedule'!HF37","v":0},{"$f":"'K20 - time schedule'!HG37","v":0},{"$f":"'K20 - time schedule'!HH37","v":0},{"$f":"'K20 - time schedule'!HI37","v":0},{"$f":"'K20 - time schedule'!HJ37","v":0},{"$f":"'K20 - time schedule'!HK37","v":0},{"$f":"'K20 - time schedule'!HL37","v":0},{"$f":"'K20 - time schedule'!HM37","v":0},{"$f":"'K20 - time schedule'!HN37","v":0},{"$f":"'K20 - time schedule'!HO37","v":0},{"$f":"'K20 - time schedule'!HP37","v":0},{"$f":"'K20 - time schedule'!HQ37","v":0},{"$f":"'K20 - time schedule'!HR37","v":0},{"$f":"'K20 - time schedule'!HS37","v":0},{"$f":"'K20 - time schedule'!HT37","v":0},{"$f":"'K20 - time schedule'!HU37","v":0},{"$f":"'K20 - time schedule'!HV37","v":0},{"$f":"'K20 - time schedule'!HW37","v":0},{"$f":"'K20 - time schedule'!HX37","v":0},{"$f":"'K20 - time schedule'!HY37","v":0},{"$f":"'K20 - time schedule'!HZ37","v":0},{"$f":"'K20 - time schedule'!IA37","v":0},{"$f":"'K20 - time schedule'!IB37","v":0},{"$f":"'K20 - time schedule'!IC37","v":0},{"$f":"'K20 - time schedule'!ID37","v":0},{"$f":"'K20 - time schedule'!IE37","v":0},{"$f":"'K20 - time schedule'!IF37","v":0},{"$f":"'K20 - time schedule'!IG37","v":0},{"$f":"'K20 - time schedule'!IH37","v":0},{"$f":"'K20 - time schedule'!II37","v":0},{"$f":"'K20 - time schedule'!IJ37","v":0},{"$f":"'K20 - time schedule'!IK37","v":0},{"$f":"'K20 - time schedule'!IL37","v":0},{"$f":"'K20 - time schedule'!IM37","v":0},{"$f":"'K20 - time schedule'!IN37","v":0},{"$f":"'K20 - time schedule'!IO37","v":0},{"$f":"'K20 - time schedule'!IP37","v":0},{"$f":"'K20 - time schedule'!IQ37","v":0},{"$f":"'K20 - time schedule'!IR37","v":0},{"$f":"'K20 - time schedule'!IS37","v":0},{"$f":"'K20 - time schedule'!IT37","v":0},{"$f":"'K20 - time schedule'!IU37","v":0},{"$f":"'K20 - time schedule'!IV37","v":0},{"$f":"'K20 - time schedule'!IW37","v":0},{"$f":"'K20 - time schedule'!IX37","v":0},{"$f":"'K20 - time schedule'!IY37","v":0},{"$f":"'K20 - time schedule'!IZ37","v":0},{"$f":"'K20 - time schedule'!JA37","v":0},{"$f":"'K20 - time schedule'!JB37","v":0},{"$f":"'K20 - time schedule'!JC37","v":0},{"$f":"'K20 - time schedule'!JD37","v":0},{"$f":"'K20 - time schedule'!JE37","v":0},{"$f":"'K20 - time schedule'!JF37","v":0},{"$f":"'K20 - time schedule'!JG37","v":0},{"$f":"'K20 - time schedule'!JH37","v":0},{"$f":"'K20 - time schedule'!JI37","v":0},{"$f":"'K20 - time schedule'!JJ37","v":0},{"$f":"'K20 - time schedule'!JK37","v":0},{"$f":"'K20 - time schedule'!JL37","v":0},{"$f":"'K20 - time schedule'!JM37","v":0},{"$f":"'K20 - time schedule'!JN37","v":0},{"$f":"'K20 - time schedule'!JO37","v":0},{"$f":"'K20 - time schedule'!JP37","v":0},{"$f":"'K20 - time schedule'!JQ37","v":0},{"$f":"'K20 - time schedule'!JR37","v":0},{"$f":"'K20 - time schedule'!JS37","v":0},{"$f":"'K20 - time schedule'!JT37","v":0},{"$f":"'K20 - time schedule'!JU37","v":0},{"$f":"'K20 - time schedule'!JV37","v":0},{"$f":"'K20 - time schedule'!JW37","v":0},{"$f":"'K20 - time schedule'!JX37","v":0},{"$f":"'K20 - time schedule'!JY37","v":0},{"$f":"'K20 - time schedule'!JZ37","v":0},{"$f":"'K20 - time schedule'!KA37","v":0},{"$f":"'K20 - time schedule'!KB37","v":0},{"$f":"'K20 - time schedule'!KC37","v":0},{"$f":"'K20 - time schedule'!KD37","v":0},{"$f":"'K20 - time schedule'!KE37","v":0},{"$f":"'K20 - time schedule'!KF37","v":0},{"$f":"'K20 - time schedule'!KG37","v":0},{"$f":"'K20 - time schedule'!KH37","v":0},{"$f":"'K20 - time schedule'!KI37","v":0},{"$f":"'K20 - time schedule'!KJ37","v":0},{"$f":"'K20 - time schedule'!KK37","v":0},{"$f":"'K20 - time schedule'!KL37","v":0},{"$f":"'K20 - time schedule'!KM37","v":0},{"$f":"'K20 - time schedule'!KN37","v":0},{"$f":"'K20 - time schedule'!KO37","v":0},{"$f":"'K20 - time schedule'!KP37","v":0},{"$f":"'K20 - time schedule'!KQ37","v":0},{"$f":"'K20 - time schedule'!KR37","v":0},{"$f":"'K20 - time schedule'!KS37","v":0},{"$f":"'K20 - time schedule'!KT37","v":0}]
["Boiler room K20 - final acceptance of the Work FAC","K20",{"$f":"'K20 - time schedule'!G63","v":0},{"$f":"'K20 - time schedule'!H63","v":0},{"$f":"'K20 - time schedule'!I63","v":0},{"$f":"'K20 - time schedule'!J63","v":0},{"$f":"'K20 - time schedule'!K63","v":0},{"$f":"'K20 - time schedule'!L63","v":0},{"$f":"'K20 - time schedule'!M63","v":0},{"$f":"'K20 - time schedule'!N63","v":0},{"$f":"'K20 - time schedule'!O63","v":0},{"$f":"'K20 - time schedule'!P63","v":0},{"$f":"'K20 - time schedule'!Q63","v":0},{"$f":"'K20 - time schedule'!R63","v":0},{"$f":"'K20 - time schedule'!S63","v":0},{"$f":"'K20 - time schedule'!T63","v":0},{"$f":"'K20 - time schedule'!U63","v":0},{"$f":"'K20 - time schedule'!V63","v":0},{"$f":"'K20 - time schedule'!W63","v":0},{"$f":"'K20 - time schedule'!X63","v":0},{"$f":"'K20 - time schedule'!Y63","v":0},{"$f":"'K20 - time schedule'!Z63","v":0},{"$f":"'K20 - time schedule'!AA63","v":0},{"$f":"'K20 - time schedule'!AB63","v":0},{"$f":"'K20 - time schedule'!AC63","v":0},{"$f":"'K20 - time schedule'!AD63","v":0},{"$f":"'K20 - time schedule'!AE63","v":0},{"$f":"'K20 - time schedule'!AF63","v":0},{"$f":"'K20 - time schedule'!AG63","v":0},{"$f":"'K20 - time schedule'!AH63","v":0},{"$f":"'K20 - time schedule'!AI63","v":0},{"$f":"'K20 - time schedule'!AJ63","v":0},{"$f":"'K20 - time schedule'!AK63","v":0},{"$f":"'K20 - time schedule'!AL63","v":0},{"$f":"'K20 - time schedule'!AM63","v":0},{"$f":"'K20 - time schedule'!AN63","v":0},{"$f":"'K20 - time schedule'!AO63","v":0},{"$f":"'K20 - time schedule'!AP63","v":0},{"$f":"'K20 - time schedule'!AQ63","v":0},{"$f":"'K20 - time schedule'!AR63","v":0},{"$f":"'K20 - time schedule'!AS63","v":0},{"$f":"'K20 - time schedule'!AT63","v":0},{"$f":"'K20 - time schedule'!AU63","v":0},{"$f":"'K20 - time schedule'!AV63","v":0},{"$f":"'K20 - time schedule'!AW63","v":0},{"$f":"'K20 - time schedule'!AX63","v":0},{"$f":"'K20 - time schedule'!AY63","v":0},{"$f":"'K20 - time schedule'!AZ63","v":0},{"$f":"'K20 - time schedule'!BA63","v":0},{"$f":"'K20 - time schedule'!BB63","v":0},{"$f":"'K20 - time schedule'!BC63","v":0},{"$f":"'K20 - time schedule'!BD63","v":0},{"$f":"'K20 - time schedule'!BE63","v":0},{"$f":"'K20 - time schedule'!BF63","v":0},{"$f":"'K20 - time schedule'!BG63","v":0},{"$f":"'K20 - time schedule'!BH63","v":0},{"$f":"'K20 - time schedule'!BI63","v":0},{"$f":"'K20 - time schedule'!BJ63","v":0},{"$f":"'K20 - time schedule'!BK63","v":0},{"$f":"'K20 - time schedule'!BL63","v":0},{"$f":"'K20 - time schedule'!BM63","v":0},{"$f":"'K20 - time schedule'!BN63","v":0},{"$f":"'K20 - time schedule'!BO63","v":0},{"$f":"'K20 - time schedule'!BP63","v":0},{"$f":"'K20 - time schedule'!BQ63","v":0},{"$f":"'K20 - time schedule'!BR63","v":0},{"$f":"'K20 - time schedule'!BS63","v":0},{"$f":"'K20 - time schedule'!BT63","v":0},{"$f":"'K20 - time schedule'!BU63","v":0},{"$f":"'K20 - time schedule'!BV63","v":0},{"$f":"'K20 - time schedule'!BW63","v":0},{"$f":"'K20 - time schedule'!BX63","v":0},{"$f":"'K20 - time schedule'!BY63","v":0},{"$f":"'K20 - time schedule'!BZ63","v":0},{"$f":"'K20 - time schedule'!CA63","v":0},{"$f":"'K20 - time schedule'!CB63","v":0},{"$f":"'K20 - time schedule'!CC63","v":0},{"$f":"'K20 - time schedule'!CD63","v":0},{"$f":"'K20 - time schedule'!CE63","v":0},{"$f":"'K20 - time schedule'!CF63","v":0},{"$f":"'K20 - time schedule'!CG63","v":0},{"$f":"'K20 - time schedule'!CH63","v":0},{"$f":"'K20 - time schedule'!CI63","v":0},{"$f":"'K20 - time schedule'!CJ63","v":0},{"$f":"'K20 - time schedule'!CK63","v":0},{"$f":"'K20 - time schedule'!CL63","v":0},{"$f":"'K20 - time schedule'!CM63","v":0},{"$f":"'K20 - time schedule'!CN63","v":0},{"$f":"'K20 - time schedule'!CO63","v":0},{"$f":"'K20 - time schedule'!CP63","v":0},{"$f":"'K20 - time schedule'!CQ63","v":0},{"$f":"'K20 - time schedule'!CR63","v":0},{"$f":"'K20 - time schedule'!CS63","v":0},{"$f":"'K20 - time schedule'!CT63","v":0},{"$f":"'K20 - time schedule'!CU63","v":0},{"$f":"'K20 - time schedule'!CV63","v":0},{"$f":"'K20 - time schedule'!CW63","v":0},{"$f":"'K20 - time schedule'!CX63","v":0},{"$f":"'K20 - time schedule'!CY63","v":0},{"$f":"'K20 - time schedule'!CZ63","v":0},{"$f":"'K20 - time schedule'!DA63","v":0},{"$f":"'K20 - time schedule'!DB63","v":0},{"$f":"'K20 - time schedule'!DC63","v":0},{"$f":"'K20 - time schedule'!DD63","v":0},{"$f":"'K20 - time schedule'!DE63","v":0},{"$f":"'K20 - time schedule'!DF63","v":0},{"$f":"'K20 - time schedule'!DG63","v":0},{"$f":"'K20 - time schedule'!DH63","v":0},{"$f":"'K20 - time schedule'!DI63","v":0},{"$f":"'K20 - time schedule'!DJ63","v":0},{"$f":"'K20 - time schedule'!DK63","v":0},{"$f":"'K20 - time schedule'!DL63","v":0},{"$f":"'K20 - time schedule'!DM63","v":0},{"$f":"'K20 - time schedule'!DN63","v":0},{"$f":"'K20 - time schedule'!DO63","v":0},{"$f":"'K20 - time schedule'!DP63","v":0},{"$f":"'K20 - time schedule'!DQ63","v":0},{"$f":"'K20 - time schedule'!DR63","v":0},{"$f":"'K20 - time schedule'!DS63","v":0},{"$f":"'K20 - time schedule'!DT63","v":0},{"$f":"'K20 - time schedule'!DU63","v":0},{"$f":"'K20 - time schedule'!DV63","v":0},{"$f":"'K20 - time schedule'!DW63","v":0},{"$f":"'K20 - time schedule'!DX63","v":0},{"$f":"'K20 - time schedule'!DY63","v":0},{"$f":"'K20 - time schedule'!DZ63","v":0},{"$f":"'K20 - time schedule'!EA63","v":0},{"$f":"'K20 - time schedule'!EB63","v":0},{"$f":"'K20 - time schedule'!EC63","v":0},{"$f":"'K20 - time schedule'!ED63","v":0},{"$f":"'K20 - time schedule'!EE63","v":0},{"$f":"'K20 - time schedule'!EF63","v":0},{"$f":"'K20 - time schedule'!EG63","v":0},{"$f":"'K20 - time schedule'!EH63","v":0},{"$f":"'K20 - time schedule'!EI63","v":0},{"$f":"'K20 - time schedule'!EJ63","v":0},{"$f":"'K20 - time schedule'!EK63","v":0},{"$f":"'K20 - time schedule'!EL63","v":0},{"$f":"'K20 - time schedule'!EM63","v":0},{"$f":"'K20 - time schedule'!EN63","v":0},{"$f":"'K20 - time schedule'!EO63","v":0},{"$f":"'K20 - time schedule'!EP63","v":0},{"$f":"'K20 - time schedule'!EQ63","v":0},{"$f":"'K20 - time schedule'!ER63","v":0},{"$f":"'K20 - time schedule'!ES63","v":0},{"$f":"'K20 - time schedule'!ET63","v":0},{"$f":"'K20 - time schedule'!EU63","v":0},{"$f":"'K20 - time schedule'!EV63","v":0},{"$f":"'K20 - time schedule'!EW63","v":0},{"$f":"'K20 - time schedule'!EX63","v":0},{"$f":"'K20 - time schedule'!EY63","v":0},{"$f":"'K20 - time schedule'!EZ63","v":0},{"$f":"'K20 - time schedule'!FA63","v":0},{"$f":"'K20 - time schedule'!FB63","v":0},{"$f":"'K20 - time schedule'!FC63","v":0},{"$f":"'K20 - time schedule'!FD63","v":0},{"$f":"'K20 - time schedule'!FE63","v":0},{"$f":"'K20 - time schedule'!FF63","v":0},{"$f":"'K20 - time schedule'!FG63","v":0},{"$f":"'K20 - time schedule'!FH63","v":0},{"$f":"'K20 - time schedule'!FI63","v":0},{"$f":"'K20 - time schedule'!FJ63","v":0},{"$f":"'K20 - time schedule'!FK63","v":0},{"$f":"'K20 - time schedule'!FL63","v":0},{"$f":"'K20 - time schedule'!FM63","v":0},{"$f":"'K20 - time schedule'!FN63","v":0},{"$f":"'K20 - time schedule'!FO63","v":0},{"$f":"'K20 - time schedule'!FP63","v":0},{"$f":"'K20 - time schedule'!FQ63","v":0},{"$f":"'K20 - time schedule'!FR63","v":0},{"$f":"'K20 - time schedule'!FS63","v":0},{"$f":"'K20 - time schedule'!FT63","v":0},{"$f":"'K20 - time schedule'!FU63","v":0},{"$f":"'K20 - time schedule'!FV63","v":0},{"$f":"'K20 - time schedule'!FW63","v":0},{"$f":"'K20 - time schedule'!FX63","v":0},{"$f":"'K20 - time schedule'!FY63","v":0},{"$f":"'K20 - time schedule'!FZ63","v":0},{"$f":"'K20 - time schedule'!GA63","v":0},{"$f":"'K20 - time schedule'!GB63","v":0},{"$f":"'K20 - time schedule'!GC63","v":0},{"$f":"'K20 - time schedule'!GD63","v":0},{"$f":"'K20 - time schedule'!GE63","v":0},{"$f":"'K20 - time schedule'!GF63","v":0},{"$f":"'K20 - time schedule'!GG63","v":0},{"$f":"'K20 - time schedule'!GH38","v":0},{"$f":"'K20 - time schedule'!GI38","v":0},{"$f":"'K20 - time schedule'!GJ38","v":0},{"$f":"'K20 - time schedule'!GK38","v":0},{"$f":"'K20 - time schedule'!GL38","v":0},{"$f":"'K20 - time schedule'!GM38","v":0},{"$f":"'K20 - time schedule'!GN38","v":0},{"$f":"'K20 - time schedule'!GO38","v":0},{"$f":"'K20 - time schedule'!GP38","v":0},{"$f":"'K20 - time schedule'!GQ38","v":0},{"$f":"'K20 - time schedule'!GR38","v":0},{"$f":"'K20 - time schedule'!GS38","v":0},{"$f":"'K20 - time schedule'!GT38","v":0},{"$f":"'K20 - time schedule'!GU38","v":0},{"$f":"'K20 - time schedule'!GV38","v":0},{"$f":"'K20 - time schedule'!GW38","v":0},{"$f":"'K20 - time schedule'!GX38","v":0},{"$f":"'K20 - time schedule'!GY38","v":0},{"$f":"'K20 - time schedule'!GZ38","v":0},{"$f":"'K20 - time schedule'!HA38","v":0},{"$f":"'K20 - time schedule'!HB38","v":0},{"$f":"'K20 - time schedule'!HC38","v":0},{"$f":"'K20 - time schedule'!HD38","v":0},{"$f":"'K20 - time schedule'!HE38","v":0},{"$f":"'K20 - time schedule'!HF38","v":0},{"$f":"'K20 - time schedule'!HG38","v":0},{"$f":"'K20 - time schedule'!HH38","v":0},{"$f":"'K20 - time schedule'!HI38","v":0},{"$f":"'K20 - time schedule'!HJ38","v":0},{"$f":"'K20 - time schedule'!HK38","v":0},{"$f":"'K20 - time schedule'!HL38","v":0},{"$f":"'K20 - time schedule'!HM38","v":0},{"$f":"'K20 - time schedule'!HN38","v":0},{"$f":"'K20 - time schedule'!HO38","v":0},{"$f":"'K20 - time schedule'!HP38","v":0},{"$f":"'K20 - time schedule'!HQ38","v":0},{"$f":"'K20 - time schedule'!HR38","v":0},{"$f":"'K20 - time schedule'!HS38","v":0},{"$f":"'K20 - time schedule'!HT38","v":0},{"$f":"'K20 - time schedule'!HU38","v":0},{"$f":"'K20 - time schedule'!HV38","v":0},{"$f":"'K20 - time schedule'!HW38","v":0},{"$f":"'K20 - time schedule'!HX38","v":0},{"$f":"'K20 - time schedule'!HY38","v":0},{"$f":"'K20 - time schedule'!HZ38","v":0},{"$f":"'K20 - time schedule'!IA38","v":0},{"$f":"'K20 - time schedule'!IB38","v":0},{"$f":"'K20 - time schedule'!IC38","v":0},{"$f":"'K20 - time schedule'!ID38","v":0},{"$f":"'K20 - time schedule'!IE38","v":0},{"$f":"'K20 - time schedule'!IF38","v":0},{"$f":"'K20 - time schedule'!IG38","v":0},{"$f":"'K20 - time schedule'!IH38","v":0},{"$f":"'K20 - time schedule'!II38","v":0},{"$f":"'K20 - time schedule'!IJ38","v":0},{"$f":"'K20 - time schedule'!IK38","v":0},{"$f":"'K20 - time schedule'!IL38","v":0},{"$f":"'K20 - time schedule'!IM38","v":0},{"$f":"'K20 - time schedule'!IN38","v":0},{"$f":"'K20 - time schedule'!IO38","v":0},{"$f":"'K20 - time schedule'!IP38","v":0},{"$f":"'K20 - time schedule'!IQ38","v":0},{"$f":"'K20 - time schedule'!IR38","v":0},{"$f":"'K20 - time schedule'!IS38","v":0},{"$f":"'K20 - time schedule'!IT38","v":0},{"$f":"'K20 - time schedule'!IU38","v":0},{"$f":"'K20 - time schedule'!IV38","v":0},{"$f":"'K20 - time schedule'!IW38","v":0},{"$f":"'K20 - time schedule'!IX38","v":0},{"$f":"'K20 - time schedule'!IY38","v":0},{"$f":"'K20 - time schedule'!IZ38","v":0},{"$f":"'K20 - time schedule'!JA38","v":0},{"$f":"'K20 - time schedule'!JB38","v":0},{"$f":"'K20 - time schedule'!JC38","v":0},{"$f":"'K20 - time schedule'!JD38","v":0},{"$f":"'K20 - time schedule'!JE38","v":0},{"$f":"'K20 - time schedule'!JF38","v":0},{"$f":"'K20 - time schedule'!JG38","v":0},{"$f":"'K20 - time schedule'!JH38","v":0},{"$f":"'K20 - time schedule'!JI38","v":0},{"$f":"'K20 - time schedule'!JJ38","v":0},{"$f":"'K20 - time schedule'!JK38","v":0},{"$f":"'K20 - time schedule'!JL38","v":0},{"$f":"'K20 - time schedule'!JM38","v":0},{"$f":"'K20 - time schedule'!JN38","v":0},{"$f":"'K20 - time schedule'!JO38","v":0},{"$f":"'K20 - time schedule'!JP38","v":0},{"$f":"'K20 - time schedule'!JQ38","v":0},{"$f":"'K20 - time schedule'!JR38","v":0},{"$f":"'K20 - time schedule'!JS38","v":0},{"$f":"'K20 - time schedule'!JT38","v":0},{"$f":"'K20 - time schedule'!JU38","v":0},{"$f":"'K20 - time schedule'!JV38","v":0},{"$f":"'K20 - time schedule'!JW38","v":0},{"$f":"'K20 - time schedule'!JX38","v":0},{"$f":"'K20 - time schedule'!JY38","v":0},{"$f":"'K20 - time schedule'!JZ38","v":0},{"$f":"'K20 - time schedule'!KA38","v":0},{"$f":"'K20 - time schedule'!KB38","v":0},{"$f":"'K20 - time schedule'!KC38","v":0},{"$f":"'K20 - time schedule'!KD38","v":0},{"$f":"'K20 - time schedule'!KE38","v":0},{"$f":"'K20 - time schedule'!KF38","v":0},{"$f":"'K20 - time schedule'!KG38","v":0},{"$f":"'K20 - time schedule'!KH38","v":0},{"$f":"'K20 - time schedule'!KI38","v":0},{"$f":"'K20 - time schedule'!KJ38","v":0},{"$f":"'K20 - time schedule'!KK38","v":0},{"$f":"'K20 - time schedule'!KL38","v":0},{"$f":"'K20 - time schedule'!KM38","v":0},{"$f":"'K20 - time schedule'!KN38","v":0},{"$f":"'K20 - time schedule'!KO38","v":0},{"$f":"'K20 - time schedule'!KP38","v":0},{"$f":"'K20 - time schedule'!KQ38","v":0},{"$f":"'K20 - time schedule'!KR38","v":0},{"$f":"'K20 - time schedule'!KS38","v":0},{"$f":"'K20 - time schedule'!KT38","v":0}]
["Boiler room K80 - initial technical meetings","K80",{"$f":"'K80 - time schedule'!G9","v":0},{"$f":"'K80 - time schedule'!H9","v":0},{"$f":"'K80 - time schedule'!I9","v":0},{"$f":"'K80 - time schedule'!J9","v":0},{"$f":"'K80 - time schedule'!K9","v":0},{"$f":"'K80 - time schedule'!L9","v":0},{"$f":"'K80 - time schedule'!M9","v":0},{"$f":"'K80 - time schedule'!N9","v":0},{"$f":"'K80 - time schedule'!O9","v":0},{"$f":"'K80 - time schedule'!P9","v":0},{"$f":"'K80 - time schedule'!Q9","v":0},{"$f":"'K80 - time schedule'!R9","v":0},{"$f":"'K80 - time schedule'!S9","v":0},{"$f":"'K80 - time schedule'!T9","v":0},{"$f":"'K80 - time schedule'!U9","v":0},{"$f":"'K80 - time schedule'!V9","v":0},{"$f":"'K80 - time schedule'!W9","v":0},{"$f":"'K80 - time schedule'!X9","v":0},{"$f":"'K80 - time schedule'!Y9","v":0},{"$f":"'K80 - time schedule'!Z9","v":0},{"$f":"'K80 - time schedule'!AA9","v":0},{"$f":"'K80 - time schedule'!AB9","v":0},{"$f":"'K80 - time schedule'!AC9","v":0},{"$f":"'K80 - time schedule'!AD9","v":0},{"$f":"'K80 - time schedule'!AE9","v":0},{"$f":"'K80 - time schedule'!AF9","v":0},{"$f":"'K80 - time schedule'!AG9","v":0},{"$f":"'K80 - time schedule'!AH9","v":0},{"$f":"'K80 - time schedule'!AI9","v":0},{"$f":"'K80 - time schedule'!AJ9","v":0},{"$f":"'K80 - time schedule'!AK9","v":0},{"$f":"'K80 - time schedule'!AL9","v":0},{"$f":"'K80 - time schedule'!AM9","v":0},{"$f":"'K80 - time schedule'!AN9","v":0},{"$f":"'K80 - time schedule'!AO9","v":0},{"$f":"'K80 - time schedule'!AP9","v":0},{"$f":"'K80 - time schedule'!AQ9","v":0},{"$f":"'K80 - time schedule'!AR9","v":0},{"$f":"'K80 - time schedule'!AS9","v":0},{"$f":"'K80 - time schedule'!AT9","v":0},{"$f":"'K80 - time schedule'!AU9","v":0},{"$f":"'K80 - time schedule'!AV9","v":0},{"$f":"'K80 - time schedule'!AW9","v":0},{"$f":"'K80 - time schedule'!AX9","v":0},{"$f":"'K80 - time schedule'!AY9","v":0},{"$f":"'K80 - time schedule'!AZ9","v":0},{"$f":"'K80 - time schedule'!BA9","v":0},{"$f":"'K80 - time schedule'!BB9","v":0},{"$f":"'K80 - time schedule'!BC9","v":0},{"$f":"'K80 - time schedule'!BD9","v":0},{"$f":"'K80 - time schedule'!BE9","v":0},{"$f":"'K80 - time schedule'!BF9","v":0},{"$f":"'K80 - time schedule'!BG9","v":0},{"$f":"'K80 - time schedule'!BH9","v":0},{"$f":"'K80 - time schedule'!BI9","v":0},{"$f":"'K80 - time schedule'!BJ9","v":0},{"$f":"'K80 - time schedule'!BK9","v":0},{"$f":"'K80 - time schedule'!BL9","v":0},{"$f":"'K80 - time schedule'!BM9","v":0},{"$f":"'K80 - time schedule'!BN9","v":0},{"$f":"'K80 - time schedule'!BO9","v":0},{"$f":"'K80 - time schedule'!BP9","v":0},{"$f":"'K80 - time schedule'!BQ9","v":0},{"$f":"'K80 - time schedule'!BR9","v":0},{"$f":"'K80 - time schedule'!BS9","v":0},{"$f":"'K80 - time schedule'!BT9","v":0},{"$f":"'K80 - time schedule'!BU9","v":0},{"$f":"'K80 - time schedule'!BV9","v":0},{"$f":"'K80 - time schedule'!BW9","v":0},{"$f":"'K80 - time schedule'!BX9","v":0},{"$f":"'K80 - time schedule'!BY9","v":0},{"$f":"'K80 - time schedule'!BZ9","v":0},{"$f":"'K80 - time schedule'!CA9","v":0},{"$f":"'K80 - time schedule'!CB9","v":0},{"$f":"'K80 - time schedule'!CC9","v":0},{"$f":"'K80 - time schedule'!CD9","v":0},{"$f":"'K80 - time schedule'!CE9","v":0},{"$f":"'K80 - time schedule'!CF9","v":0},{"$f":"'K80 - time schedule'!CG9","v":0},{"$f":"'K80 - time schedule'!CH9","v":0},{"$f":"'K80 - time schedule'!CI9","v":0},{"$f":"'K80 - time schedule'!CJ9","v":0},{"$f":"'K80 - time schedule'!CK9","v":0},{"$f":"'K80 - time schedule'!CL9","v":0},{"$f":"'K80 - time schedule'!CM9","v":0},{"$f":"'K80 - time schedule'!CN9","v":0},{"$f":"'K80 - time schedule'!CO9","v":0},{"$f":"'K80 - time schedule'!CP9","v":0},{"$f":"'K80 - time schedule'!CQ9","v":0},{"$f":"'K80 - time schedule'!CR9","v":0},{"$f":"'K80 - time schedule'!CS9","v":0},{"$f":"'K80 - time schedule'!CT9","v":0},{"$f":"'K80 - time schedule'!CU9","v":0},{"$f":"'K80 - time schedule'!CV9","v":0},{"$f":"'K80 - time schedule'!CW9","v":0},{"$f":"'K80 - time schedule'!CX9","v":0},{"$f":"'K80 - time schedule'!CY9","v":0},{"$f":"'K80 - time schedule'!CZ9","v":0},{"$f":"'K80 - time schedule'!DA9","v":0},{"$f":"'K80 - time schedule'!DB9","v":0},{"$f":"'K80 - time schedule'!DC9","v":0},{"$f":"'K80 - time schedule'!DD9","v":0},{"$f":"'K80 - time schedule'!DE9","v":0},{"$f":"'K80 - time schedule'!DF9","v":0},{"$f":"'K80 - time schedule'!DG9","v":0},{"$f":"'K80 - time schedule'!DH9","v":0},{"$f":"'K80 - time schedule'!DI9","v":0},{"$f":"'K80 - time schedule'!DJ9","v":0},{"$f":"'K80 - time schedule'!DK9","v":0},{"$f":"'K80 - time schedule'!DL9","v":0},{"$f":"'K80 - time schedule'!DM9","v":0},{"$f":"'K80 - time schedule'!DN9","v":0},{"$f":"'K80 - time schedule'!DO9","v":0},{"$f":"'K80 - time schedule'!DP9","v":0},{"$f":"'K80 - time schedule'!DQ9","v":0},{"$f":"'K80 - time schedule'!DR9","v":0},{"$f":"'K80 - time schedule'!DS9","v":0},{"$f":"'K80 - time schedule'!DT9","v":0},{"$f":"'K80 - time schedule'!DU9","v":0},{"$f":"'K80 - time schedule'!DV9","v":0},{"$f":"'K80 - time schedule'!DW9","v":0},{"$f":"'K80 - time schedule'!DX9","v":0},{"$f":"'K80 - time schedule'!DY9","v":0},{"$f":"'K80 - time schedule'!DZ9","v":0},{"$f":"'K80 - time schedule'!EA9","v":0},{"$f":"'K80 - time schedule'!EB9","v":0},{"$f":"'K80 - time schedule'!EC9","v":0},{"$f":"'K80 - time schedule'!ED9","v":0},{"$f":"'K80 - time schedule'!EE9","v":0},{"$f":"'K80 - time schedule'!EF9","v":0},{"$f":"'K80 - time schedule'!EG9","v":0},{"$f":"'K80 - time schedule'!EH9","v":0},{"$f":"'K80 - time schedule'!EI9","v":0},{"$f":"'K80 - time schedule'!EJ9","v":0},{"$f":"'K80 - time schedule'!EK9","v":0},{"$f":"'K80 - time schedule'!EL9","v":0},{"$f":"'K80 - time schedule'!EM9","v":0},{"$f":"'K80 - time schedule'!EN9","v":0},{"$f":"'K80 - time schedule'!EO9","v":0},{"$f":"'K80 - time schedule'!EP9","v":0},{"$f":"'K80 - time schedule'!EQ9","v":0},{"$f":"'K80 - time schedule'!ER9","v":0},{"$f":"'K80 - time schedule'!ES9","v":0},{"$f":"'K80 - time schedule'!ET9","v":0},{"$f":"'K80 - time schedule'!EU9","v":0},{"$f":"'K80 - time schedule'!EV9","v":0},{"$f":"'K80 - time schedule'!EW9","v":0},{"$f":"'K80 - time schedule'!EX9","v":0},{"$f":"'K80 - time schedule'!EY9","v":0},{"$f":"'K80 - time schedule'!EZ9","v":0},{"$f":"'K80 - time schedule'!FA9","v":0},{"$f":"'K80 - time schedule'!FB9","v":0},{"$f":"'K80 - time schedule'!FC9","v":0},{"$f":"'K80 - time schedule'!FD9","v":0},{"$f":"'K80 - time schedule'!FE9","v":0},{"$f":"'K80 - time schedule'!FF9","v":0},{"$f":"'K80 - time schedule'!FG9","v":0},{"$f":"'K80 - time schedule'!FH9","v":0},{"$f":"'K80 - time schedule'!FI9","v":0},{"$f":"'K80 - time schedule'!FJ9","v":0},{"$f":"'K80 - time schedule'!FK9","v":0},{"$f":"'K80 - time schedule'!FL9","v":0},{"$f":"'K80 - time schedule'!FM9","v":0},{"$f":"'K80 - time schedule'!FN9","v":0},{"$f":"'K80 - time schedule'!FO9","v":0},{"$f":"'K80 - time schedule'!FP9","v":0},{"$f":"'K80 - time schedule'!FQ9","v":0},{"$f":"'K80 - time schedule'!FR9","v":0},{"$f":"'K80 - time schedule'!FS9","v":0},{"$f":"'K80 - time schedule'!FT9","v":0},{"$f":"'K80 - time schedule'!FU9","v":0},{"$f":"'K80 - time schedule'!FV9","v":0},{"$f":"'K80 - time schedule'!FW9","v":0},{"$f":"'K80 - time schedule'!FX9","v":0},{"$f":"'K80 - time schedule'!FY9","v":0},{"$f":"'K80 - time schedule'!FZ9","v":0},{"$f":"'K80 - time schedule'!GA9","v":0},{"$f":"'K80 - time schedule'!GB9","v":0},{"$f":"'K80 - time schedule'!GC9","v":0},{"$f":"'K80 - time schedule'!GD9","v":0},{"$f":"'K80 - time schedule'!GE9","v":0},{"$f":"'K80 - time schedule'!GF9","v":0},{"$f":"'K80 - time schedule'!GG9","v":0},{"$f":"'K80 - time schedule'!GH9","v":0},{"$f":"'K80 - time schedule'!GI9","v":0},{"$f":"'K80 - time schedule'!GJ9","v":0},{"$f":"'K80 - time schedule'!GK9","v":0},{"$f":"'K80 - time schedule'!GL9","v":0},{"$f":"'K80 - time schedule'!GM9","v":0},{"$f":"'K80 - time schedule'!GN9","v":0},{"$f":"'K80 - time schedule'!GO9","v":0},{"$f":"'K80 - time schedule'!GP9","v":0},{"$f":"'K80 - time schedule'!GQ9","v":0},{"$f":"'K80 - time schedule'!GR9","v":0},{"$f":"'K80 - time schedule'!GS9","v":0},{"$f":"'K80 - time schedule'!GT9","v":0},{"$f":"'K80 - time schedule'!GU9","v":0},{"$f":"'K80 - time schedule'!GV9","v":0},{"$f":"'K80 - time schedule'!GW9","v":0},{"$f":"'K80 - time schedule'!GX9","v":0},{"$f":"'K80 - time schedule'!GY9","v":0},{"$f":"'K80 - time schedule'!GZ9","v":0},{"$f":"'K80 - time schedule'!HA9","v":0},{"$f":"'K80 - time schedule'!HB9","v":0},{"$f":"'K80 - time schedule'!HC9","v":0},{"$f":"'K80 - time schedule'!HD9","v":0},{"$f":"'K80 - time schedule'!HE9","v":0},{"$f":"'K80 - time schedule'!HF9","v":0},{"$f":"'K80 - time schedule'!HG9","v":0},{"$f":"'K80 - time schedule'!HH9","v":0},{"$f":"'K80 - time schedule'!HI9","v":0},{"$f":"'K80 - time schedule'!HJ9","v":0},{"$f":"'K80 - time schedule'!HK9","v":0},{"$f":"'K80 - time schedule'!HL9","v":0},{"$f":"'K80 - time schedule'!HM9","v":0},{"$f":"'K80 - time schedule'!HN9","v":0},{"$f":"'K80 - time schedule'!HO9","v":0},{"$f":"'K80 - time schedule'!HP9","v":0},{"$f":"'K80 - time schedule'!HQ9","v":0},{"$f":"'K80 - time schedule'!HR9","v":0},{"$f":"'K80 - time schedule'!HS9","v":0},{"$f":"'K80 - time schedule'!HT9","v":0},{"$f":"'K80 - time schedule'!HU9","v":0},{"$f":"'K80 - time schedule'!HV9","v":0},{"$f":"'K80 - time schedule'!HW9","v":0},{"$f":"'K80 - time schedule'!HX9","v":0},{"$f":"'K80 - time schedule'!HY9","v":0},{"$f":"'K80 - time schedule'!HZ9","v":0},{"$f":"'K80 - time schedule'!IA9","v":0},{"$f":"'K80 - time schedule'!IB9","v":0},{"$f":"'K80 - time schedule'!IC9","v":0},{"$f":"'K80 - time schedule'!ID9","v":0},{"$f":"'K80 - time schedule'!IE9","v":0},{"$f":"'K80 - time schedule'!IF9","v":0},{"$f":"'K80 - time schedule'!IG9","v":0},{"$f":"'K80 - time schedule'!IH9","v":0},{"$f":"'K80 - time schedule'!II9","v":0},{"$f":"'K80 - time schedule'!IJ9","v":0},{"$f":"'K80 - time schedule'!IK9","v":0},{"$f":"'K80 - time schedule'!IL9","v":0},{"$f":"'K80 - time schedule'!IM9","v":0},{"$f":"'K80 - time schedule'!IN9","v":0},{"$f":"'K80 - time schedule'!IO9","v":0},{"$f":"'K80 - time schedule'!IP9","v":0},{"$f":"'K80 - time schedule'!IQ9","v":0},{"$f":"'K80 - time schedule'!IR9","v":0},{"$f":"'K80 - time schedule'!IS9","v":0},{"$f":"'K80 - time schedule'!IT9","v":0},{"$f":"'K80 - time schedule'!IU9","v":0},{"$f":"'K80 - time schedule'!IV9","v":0},{"$f":"'K80 - time schedule'!IW9","v":0},{"$f":"'K80 - time schedule'!IX9","v":0},{"$f":"'K80 - time schedule'!IY9","v":0},{"$f":"'K80 - time schedule'!IZ9","v":0},{"$f":"'K80 - time schedule'!JA9","v":0},{"$f":"'K80 - time schedule'!JB9","v":0},{"$f":"'K80 - time schedule'!JC9","v":0},{"$f":"'K80 - time schedule'!JD9","v":0},{"$f":"'K80 - time schedule'!JE9","v":0},{"$f":"'K80 - time schedule'!JF9","v":0},{"$f":"'K80 - time schedule'!JG9","v":0},{"$f":"'K80 - time schedule'!JH9","v":0},{"$f":"'K80 - time schedule'!JI9","v":0},{"$f":"'K80 - time schedule'!JJ9","v":0},{"$f":"'K80 - time schedule'!JK9","v":0},{"$f":"'K80 - time schedule'!JL9","v":0},{"$f":"'K80 - time schedule'!JM9","v":0},{"$f":"'K80 - time schedule'!JN9","v":0},{"$f":"'K80 - time schedule'!JO9","v":0},{"$f":"'K80 - time schedule'!JP9","v":0},{"$f":"'K80 - time schedule'!JQ9","v":0},{"$f":"'K80 - time schedule'!JR9","v":0},{"$f":"'K80 - time schedule'!JS9","v":0},{"$f":"'K80 - time schedule'!JT9","v":0},{"$f":"'K80 - time schedule'!JU9","v":0},{"$f":"'K80 - time schedule'!JV9","v":0},{"$f":"'K80 - time schedule'!JW9","v":0},{"$f":"'K80 - time schedule'!JX9","v":0},{"$f":"'K80 - time schedule'!JY9","v":0},{"$f":"'K80 - time schedule'!JZ9","v":0},{"$f":"'K80 - time schedule'!KA9","v":0},{"$f":"'K80 - time schedule'!KB9","v":0},{"$f":"'K80 - time schedule'!KC9","v":0},{"$f":"'K80 - time schedule'!KD9","v":0},{"$f":"'K80 - time schedule'!KE9","v":0},{"$f":"'K80 - time schedule'!KF9","v":0},{"$f":"'K80 - time schedule'!KG9","v":0},{"$f":"'K80 - time schedule'!KH9","v":0},{"$f":"'K80 - time schedule'!KI9","v":0},{"$f":"'K80 - time schedule'!KJ9","v":0},{"$f":"'K80 - time schedule'!KK9","v":0},{"$f":"'K80 - time schedule'!KL9","v":0},{"$f":"'K80 - time schedule'!KM9","v":0},{"$f":"'K80 - time schedule'!KN9","v":0},{"$f":"'K80 - time schedule'!KO9","v":0},{"$f":"'K80 - time schedule'!KP9","v":0},{"$f":"'K80 - time schedule'!KQ9","v":0},{"$f":"'K80 - time schedule'!KR9","v":0},{"$f":"'K80 - time schedule'!KS9","v":0},{"$f":"'K80 - time schedule'!KT9","v":0}]
["Boiler room K80 - binding technical specification for OB 6 (Construction)","K80",{"$f":"'K80 - time schedule'!G10","v":0},{"$f":"'K80 - time schedule'!H10","v":0},{"$f":"'K80 - time schedule'!I10","v":0},{"$f":"'K80 - time schedule'!J10","v":0},{"$f":"'K80 - time schedule'!K10","v":0},{"$f":"'K80 - time schedule'!L10","v":0},{"$f":"'K80 - time schedule'!M10","v":0},{"$f":"'K80 - time schedule'!N10","v":0},{"$f":"'K80 - time schedule'!O10","v":0},{"$f":"'K80 - time schedule'!P10","v":0},{"$f":"'K80 - time schedule'!Q10","v":0},{"$f":"'K80 - time schedule'!R10","v":0},{"$f":"'K80 - time schedule'!S10","v":0},{"$f":"'K80 - time schedule'!T10","v":0},{"$f":"'K80 - time schedule'!U10","v":0},{"$f":"'K80 - time schedule'!V10","v":0},{"$f":"'K80 - time schedule'!W10","v":0},{"$f":"'K80 - time schedule'!X10","v":0},{"$f":"'K80 - time schedule'!Y10","v":0},{"$f":"'K80 - time schedule'!Z10","v":0},{"$f":"'K80 - time schedule'!AA10","v":0},{"$f":"'K80 - time schedule'!AB10","v":0},{"$f":"'K80 - time schedule'!AC10","v":0},{"$f":"'K80 - time schedule'!AD10","v":0},{"$f":"'K80 - time schedule'!AE10","v":0},{"$f":"'K80 - time schedule'!AF10","v":0},{"$f":"'K80 - time schedule'!AG10","v":0},{"$f":"'K80 - time schedule'!AH10","v":0},{"$f":"'K80 - time schedule'!AI10","v":0},{"$f":"'K80 - time schedule'!AJ10","v":0},{"$f":"'K80 - time schedule'!AK10","v":0},{"$f":"'K80 - time schedule'!AL10","v":0},{"$f":"'K80 - time schedule'!AM10","v":0},{"$f":"'K80 - time schedule'!AN10","v":0},{"$f":"'K80 - time schedule'!AO10","v":0},{"$f":"'K80 - time schedule'!AP10","v":0},{"$f":"'K80 - time schedule'!AQ10","v":0},{"$f":"'K80 - time schedule'!AR10","v":0},{"$f":"'K80 - time schedule'!AS10","v":0},{"$f":"'K80 - time schedule'!AT10","v":0},{"$f":"'K80 - time schedule'!AU10","v":0},{"$f":"'K80 - time schedule'!AV10","v":0},{"$f":"'K80 - time schedule'!AW10","v":0},{"$f":"'K80 - time schedule'!AX10","v":0},{"$f":"'K80 - time schedule'!AY10","v":0},{"$f":"'K80 - time schedule'!AZ10","v":0},{"$f":"'K80 - time schedule'!BA10","v":0},{"$f":"'K80 - time schedule'!BB10","v":0},{"$f":"'K80 - time schedule'!BC10","v":0},{"$f":"'K80 - time schedule'!BD10","v":0},{"$f":"'K80 - time schedule'!BE10","v":0},{"$f":"'K80 - time schedule'!BF10","v":0},{"$f":"'K80 - time schedule'!BG10","v":0},{"$f":"'K80 - time schedule'!BH10","v":0},{"$f":"'K80 - time schedule'!BI10","v":0},{"$f":"'K80 - time schedule'!BJ10","v":0},{"$f":"'K80 - time schedule'!BK10","v":0},{"$f":"'K80 - time schedule'!BL10","v":0},{"$f":"'K80 - time schedule'!BM10","v":0},{"$f":"'K80 - time schedule'!BN10","v":0},{"$f":"'K80 - time schedule'!BO10","v":0},{"$f":"'K80 - time schedule'!BP10","v":0},{"$f":"'K80 - time schedule'!BQ10","v":0},{"$f":"'K80 - time schedule'!BR10","v":0},{"$f":"'K80 - time schedule'!BS10","v":0},{"$f":"'K80 - time schedule'!BT10","v":0},{"$f":"'K80 - time schedule'!BU10","v":0},{"$f":"'K80 - time schedule'!BV10","v":0},{"$f":"'K80 - time schedule'!BW10","v":0},{"$f":"'K80 - time schedule'!BX10","v":0},{"$f":"'K80 - time schedule'!BY10","v":0},{"$f":"'K80 - time schedule'!BZ10","v":0},{"$f":"'K80 - time schedule'!CA10","v":0},{"$f":"'K80 - time schedule'!CB10","v":0},{"$f":"'K80 - time schedule'!CC10","v":0},{"$f":"'K80 - time schedule'!CD10","v":0},{"$f":"'K80 - time schedule'!CE10","v":0},{"$f":"'K80 - time schedule'!CF10","v":0},{"$f":"'K80 - time schedule'!CG10","v":0},{"$f":"'K80 - time schedule'!CH10","v":0},{"$f":"'K80 - time schedule'!CI10","v":0},{"$f":"'K80 - time schedule'!CJ10","v":0},{"$f":"'K80 - time schedule'!CK10","v":0},{"$f":"'K80 - time schedule'!CL10","v":0},{"$f":"'K80 - time schedule'!CM10","v":0},{"$f":"'K80 - time schedule'!CN10","v":0},{"$f":"'K80 - time schedule'!CO10","v":0},{"$f":"'K80 - time schedule'!CP10","v":0},{"$f":"'K80 - time schedule'!CQ10","v":0},{"$f":"'K80 - time schedule'!CR10","v":0},{"$f":"'K80 - time schedule'!CS10","v":0},{"$f":"'K80 - time schedule'!CT10","v":0},{"$f":"'K80 - time schedule'!CU10","v":0},{"$f":"'K80 - time schedule'!CV10","v":0},{"$f":"'K80 - time schedule'!CW10","v":0},{"$f":"'K80 - time schedule'!CX10","v":0},{"$f":"'K80 - time schedule'!CY10","v":0},{"$f":"'K80 - time schedule'!CZ10","v":0},{"$f":"'K80 - time schedule'!DA10","v":0},{"$f":"'K80 - time schedule'!DB10","v":0},{"$f":"'K80 - time schedule'!DC10","v":0},{"$f":"'K80 - time schedule'!DD10","v":0},{"$f":"'K80 - time schedule'!DE10","v":0},{"$f":"'K80 - time schedule'!DF10","v":0},{"$f":"'K80 - time schedule'!DG10","v":0},{"$f":"'K80 - time schedule'!DH10","v":0},{"$f":"'K80 - time schedule'!DI10","v":0},{"$f":"'K80 - time schedule'!DJ10","v":0},{"$f":"'K80 - time schedule'!DK10","v":0},{"$f":"'K80 - time schedule'!DL10","v":0},{"$f":"'K80 - time schedule'!DM10","v":0},{"$f":"'K80 - time schedule'!DN10","v":0},{"$f":"'K80 - time schedule'!DO10","v":0},{"$f":"'K80 - time schedule'!DP10","v":0},{"$f":"'K80 - time schedule'!DQ10","v":0},{"$f":"'K80 - time schedule'!DR10","v":0},{"$f":"'K80 - time schedule'!DS10","v":0},{"$f":"'K80 - time schedule'!DT10","v":0},{"$f":"'K80 - time schedule'!DU10","v":0},{"$f":"'K80 - time schedule'!DV10","v":0},{"$f":"'K80 - time schedule'!DW10","v":0},{"$f":"'K80 - time schedule'!DX10","v":0},{"$f":"'K80 - time schedule'!DY10","v":0},{"$f":"'K80 - time schedule'!DZ10","v":0},{"$f":"'K80 - time schedule'!EA10","v":0},{"$f":"'K80 - time schedule'!EB10","v":0},{"$f":"'K80 - time schedule'!EC10","v":0},{"$f":"'K80 - time schedule'!ED10","v":0},{"$f":"'K80 - time schedule'!EE10","v":0},{"$f":"'K80 - time schedule'!EF10","v":0},{"$f":"'K80 - time schedule'!EG10","v":0},{"$f":"'K80 - time schedule'!EH10","v":0},{"$f":"'K80 - time schedule'!EI10","v":0},{"$f":"'K80 - time schedule'!EJ10","v":0},{"$f":"'K80 - time schedule'!EK10","v":0},{"$f":"'K80 - time schedule'!EL10","v":0},{"$f":"'K80 - time schedule'!EM10","v":0},{"$f":"'K80 - time schedule'!EN10","v":0},{"$f":"'K80 - time schedule'!EO10","v":0},{"$f":"'K80 - time schedule'!EP10","v":0},{"$f":"'K80 - time schedule'!EQ10","v":0},{"$f":"'K80 - time schedule'!ER10","v":0},{"$f":"'K80 - time schedule'!ES10","v":0},{"$f":"'K80 - time schedule'!ET10","v":0},{"$f":"'K80 - time schedule'!EU10","v":0},{"$f":"'K80 - time schedule'!EV10","v":0},{"$f":"'K80 - time schedule'!EW10","v":0},{"$f":"'K80 - time schedule'!EX10","v":0},{"$f":"'K80 - time schedule'!EY10","v":0},{"$f":"'K80 - time schedule'!EZ10","v":0},{"$f":"'K80 - time schedule'!FA10","v":0},{"$f":"'K80 - time schedule'!FB10","v":0},{"$f":"'K80 - time schedule'!FC10","v":0},{"$f":"'K80 - time schedule'!FD10","v":0},{"$f":"'K80 - time schedule'!FE10","v":0},{"$f":"'K80 - time schedule'!FF10","v":0},{"$f":"'K80 - time schedule'!FG10","v":0},{"$f":"'K80 - time schedule'!FH10","v":0},{"$f":"'K80 - time schedule'!FI10","v":0},{"$f":"'K80 - time schedule'!FJ10","v":0},{"$f":"'K80 - time schedule'!FK10","v":0},{"$f":"'K80 - time schedule'!FL10","v":0},{"$f":"'K80 - time schedule'!FM10","v":0},{"$f":"'K80 - time schedule'!FN10","v":0},{"$f":"'K80 - time schedule'!FO10","v":0},{"$f":"'K80 - time schedule'!FP10","v":0},{"$f":"'K80 - time schedule'!FQ10","v":0},{"$f":"'K80 - time schedule'!FR10","v":0},{"$f":"'K80 - time schedule'!FS10","v":0},{"$f":"'K80 - time schedule'!FT10","v":0},{"$f":"'K80 - time schedule'!FU10","v":0},{"$f":"'K80 - time schedule'!FV10","v":0},{"$f":"'K80 - time schedule'!FW10","v":0},{"$f":"'K80 - time schedule'!FX10","v":0},{"$f":"'K80 - time schedule'!FY10","v":0},{"$f":"'K80 - time schedule'!FZ10","v":0},{"$f":"'K80 - time schedule'!GA10","v":0},{"$f":"'K80 - time schedule'!GB10","v":0},{"$f":"'K80 - time schedule'!GC10","v":0},{"$f":"'K80 - time schedule'!GD10","v":0},{"$f":"'K80 - time schedule'!GE10","v":0},{"$f":"'K80 - time schedule'!GF10","v":0},{"$f":"'K80 - time schedule'!GG10","v":0},{"$f":"'K80 - time schedule'!GH10","v":0},{"$f":"'K80 - time schedule'!GI10","v":0},{"$f":"'K80 - time schedule'!GJ10","v":0},{"$f":"'K80 - time schedule'!GK10","v":0},{"$f":"'K80 - time schedule'!GL10","v":0},{"$f":"'K80 - time schedule'!GM10","v":0},{"$f":"'K80 - time schedule'!GN10","v":0},{"$f":"'K80 - time schedule'!GO10","v":0},{"$f":"'K80 - time schedule'!GP10","v":0},{"$f":"'K80 - time schedule'!GQ10","v":0},{"$f":"'K80 - time schedule'!GR10","v":0},{"$f":"'K80 - time schedule'!GS10","v":0},{"$f":"'K80 - time schedule'!GT10","v":0},{"$f":"'K80 - time schedule'!GU10","v":0},{"$f":"'K80 - time schedule'!GV10","v":0},{"$f":"'K80 - time schedule'!GW10","v":0},{"$f":"'K80 - time schedule'!GX10","v":0},{"$f":"'K80 - time schedule'!GY10","v":0},{"$f":"'K80 - time schedule'!GZ10","v":0},{"$f":"'K80 - time schedule'!HA10","v":0},{"$f":"'K80 - time schedule'!HB10","v":0},{"$f":"'K80 - time schedule'!HC10","v":0},{"$f":"'K80 - time schedule'!HD10","v":0},{"$f":"'K80 - time schedule'!HE10","v":0},{"$f":"'K80 - time schedule'!HF10","v":0},{"$f":"'K80 - time schedule'!HG10","v":0},{"$f":"'K80 - time schedule'!HH10","v":0},{"$f":"'K80 - time schedule'!HI10","v":0},{"$f":"'K80 - time schedule'!HJ10","v":0},{"$f":"'K80 - time schedule'!HK10","v":0},{"$f":"'K80 - time schedule'!HL10","v":0},{"$f":"'K80 - time schedule'!HM10","v":0},{"$f":"'K80 - time schedule'!HN10","v":0},{"$f":"'K80 - time schedule'!HO10","v":0},{"$f":"'K80 - time schedule'!HP10","v":0},{"$f":"'K80 - time schedule'!HQ10","v":0},{"$f":"'K80 - time schedule'!HR10","v":0},{"$f":"'K80 - time schedule'!HS10","v":0},{"$f":"'K80 - time schedule'!HT10","v":0},{"$f":"'K80 - time schedule'!HU10","v":0},{"$f":"'K80 - time schedule'!HV10","v":0},{"$f":"'K80 - time schedule'!HW10","v":0},{"$f":"'K80 - time schedule'!HX10","v":0},{"$f":"'K80 - time schedule'!HY10","v":0},{"$f":"'K80 - time schedule'!HZ10","v":0},{"$f":"'K80 - time schedule'!IA10","v":0},{"$f":"'K80 - time schedule'!IB10","v":0},{"$f":"'K80 - time schedule'!IC10","v":0},{"$f":"'K80 - time schedule'!ID10","v":0},{"$f":"'K80 - time schedule'!IE10","v":0},{"$f":"'K80 - time schedule'!IF10","v":0},{"$f":"'K80 - time schedule'!IG10","v":0},{"$f":"'K80 - time schedule'!IH10","v":0},{"$f":"'K80 - time schedule'!II10","v":0},{"$f":"'K80 - time schedule'!IJ10","v":0},{"$f":"'K80 - time schedule'!IK10","v":0},{"$f":"'K80 - time schedule'!IL10","v":0},{"$f":"'K80 - time schedule'!IM10","v":0},{"$f":"'K80 - time schedule'!IN10","v":0},{"$f":"'K80 - time schedule'!IO10","v":0},{"$f":"'K80 - time schedule'!IP10","v":0},{"$f":"'K80 - time schedule'!IQ10","v":0},{"$f":"'K80 - time schedule'!IR10","v":0},{"$f":"'K80 - time schedule'!IS10","v":0},{"$f":"'K80 - time schedule'!IT10","v":0},{"$f":"'K80 - time schedule'!IU10","v":0},{"$f":"'K80 - time schedule'!IV10","v":0},{"$f":"'K80 - time schedule'!IW10","v":0},{"$f":"'K80 - time schedule'!IX10","v":0},{"$f":"'K80 - time schedule'!IY10","v":0},{"$f":"'K80 - time schedule'!IZ10","v":0},{"$f":"'K80 - time schedule'!JA10","v":0},{"$f":"'K80 - time schedule'!JB10","v":0},{"$f":"'K80 - time schedule'!JC10","v":0},{"$f":"'K80 - time schedule'!JD10","v":0},{"$f":"'K80 - time schedule'!JE10","v":0},{"$f":"'K80 - time schedule'!JF10","v":0},{"$f":"'K80 - time schedule'!JG10","v":0},{"$f":"'K80 - time schedule'!JH10","v":0},{"$f":"'K80 - time schedule'!JI10","v":0},{"$f":"'K80 - time schedule'!JJ10","v":0},{"$f":"'K80 - time schedule'!JK10","v":0},{"$f":"'K80 - time schedule'!JL10","v":0},{"$f":"'K80 - time schedule'!JM10","v":0},{"$f":"'K80 - time schedule'!JN10","v":0},{"$f":"'K80 - time schedule'!JO10","v":0},{"$f":"'K80 - time schedule'!JP10","v":0},{"$f":"'K80 - time schedule'!JQ10","v":0},{"$f":"'K80 - time schedule'!JR10","v":0},{"$f":"'K80 - time schedule'!JS10","v":0},{"$f":"'K80 - time schedule'!JT10","v":0},{"$f":"'K80 - time schedule'!JU10","v":0},{"$f":"'K80 - time schedule'!JV10","v":0},{"$f":"'K80 - time schedule'!JW10","v":0},{"$f":"'K80 - time schedule'!JX10","v":0},{"$f":"'K80 - time schedule'!JY10","v":0},{"$f":"'K80 - time schedule'!JZ10","v":0},{"$f":"'K80 - time schedule'!KA10","v":0},{"$f":"'K80 - time schedule'!KB10","v":0},{"$f":"'K80 - time schedule'!KC10","v":0},{"$f":"'K80 - time schedule'!KD10","v":0},{"$f":"'K80 - time schedule'!KE10","v":0},{"$f":"'K80 - time schedule'!KF10","v":0},{"$f":"'K80 - time schedule'!KG10","v":0},{"$f":"'K80 - time schedule'!KH10","v":0},{"$f":"'K80 - time schedule'!KI10","v":0},{"$f":"'K80 - time schedule'!KJ10","v":0},{"$f":"'K80 - time schedule'!KK10","v":0},{"$f":"'K80 - time schedule'!KL10","v":0},{"$f":"'K80 - time schedule'!KM10","v":0},{"$f":"'K80 - time schedule'!KN10","v":0},{"$f":"'K80 - time schedule'!KO10","v":0},{"$f":"'K80 - time schedule'!KP10","v":0},{"$f":"'K80 - time schedule'!KQ10","v":0},{"$f":"'K80 - time schedule'!KR10","v":0},{"$f":"'K80 - time schedule'!KS10","v":0},{"$f":"'K80 - time schedule'!KT10","v":0}]
["Boiler room K80 - binding technical specification for OB 1 (Fuel management) ","K80",{"$f":"'K80 - time schedule'!G12","v":0},{"$f":"'K80 - time schedule'!H12","v":0},{"$f":"'K80 - time schedule'!I12","v":0},{"$f":"'K80 - time schedule'!J12","v":0},{"$f":"'K80 - time schedule'!K12","v":0},{"$f":"'K80 - time schedule'!L12","v":0},{"$f":"'K80 - time schedule'!M12","v":0},{"$f":"'K80 - time schedule'!N12","v":0},{"$f":"'K80 - time schedule'!O12","v":0},{"$f":"'K80 - time schedule'!P12","v":0},{"$f":"'K80 - time schedule'!Q12","v":0},{"$f":"'K80 - time schedule'!R12","v":0},{"$f":"'K80 - time schedule'!S12","v":0},{"$f":"'K80 - time schedule'!T12","v":0},{"$f":"'K80 - time schedule'!U12","v":0},{"$f":"'K80 - time schedule'!V12","v":0},{"$f":"'K80 - time schedule'!W12","v":0},{"$f":"'K80 - time schedule'!X12","v":0},{"$f":"'K80 - time schedule'!Y12","v":0},{"$f":"'K80 - time schedule'!Z12","v":0},{"$f":"'K80 - time schedule'!AA12","v":0},{"$f":"'K80 - time schedule'!AB12","v":0},{"$f":"'K80 - time schedule'!AC12","v":0},{"$f":"'K80 - time schedule'!AD12","v":0},{"$f":"'K80 - time schedule'!AE12","v":0},{"$f":"'K80 - time schedule'!AF12","v":0},{"$f":"'K80 - time schedule'!AG12","v":0},{"$f":"'K80 - time schedule'!AH12","v":0},{"$f":"'K80 - time schedule'!AI12","v":0},{"$f":"'K80 - time schedule'!AJ12","v":0},{"$f":"'K80 - time schedule'!AK12","v":0},{"$f":"'K80 - time schedule'!AL12","v":0},{"$f":"'K80 - time schedule'!AM12","v":0},{"$f":"'K80 - time schedule'!AN12","v":0},{"$f":"'K80 - time schedule'!AO12","v":0},{"$f":"'K80 - time schedule'!AP12","v":0},{"$f":"'K80 - time schedule'!AQ12","v":0},{"$f":"'K80 - time schedule'!AR12","v":0},{"$f":"'K80 - time schedule'!AS12","v":0},{"$f":"'K80 - time schedule'!AT12","v":0},{"$f":"'K80 - time schedule'!AU12","v":0},{"$f":"'K80 - time schedule'!AV12","v":0},{"$f":"'K80 - time schedule'!AW12","v":0},{"$f":"'K80 - time schedule'!AX12","v":0},{"$f":"'K80 - time schedule'!AY12","v":0},{"$f":"'K80 - time schedule'!AZ12","v":0},{"$f":"'K80 - time schedule'!BA12","v":0},{"$f":"'K80 - time schedule'!BB12","v":0},{"$f":"'K80 - time schedule'!BC12","v":0},{"$f":"'K80 - time schedule'!BD12","v":0},{"$f":"'K80 - time schedule'!BE12","v":0},{"$f":"'K80 - time schedule'!BF12","v":0},{"$f":"'K80 - time schedule'!BG12","v":0},{"$f":"'K80 - time schedule'!BH12","v":0},{"$f":"'K80 - time schedule'!BI12","v":0},{"$f":"'K80 - time schedule'!BJ12","v":0},{"$f":"'K80 - time schedule'!BK12","v":0},{"$f":"'K80 - time schedule'!BL12","v":0},{"$f":"'K80 - time schedule'!BM12","v":0},{"$f":"'K80 - time schedule'!BN12","v":0},{"$f":"'K80 - time schedule'!BO12","v":0},{"$f":"'K80 - time schedule'!BP12","v":0},{"$f":"'K80 - time schedule'!BQ12","v":0},{"$f":"'K80 - time schedule'!BR12","v":0},{"$f":"'K80 - time schedule'!BS12","v":0},{"$f":"'K80 - time schedule'!BT12","v":0},{"$f":"'K80 - time schedule'!BU12","v":0},{"$f":"'K80 - time schedule'!BV12","v":0},{"$f":"'K80 - time schedule'!BW12","v":0},{"$f":"'K80 - time schedule'!BX12","v":0},{"$f":"'K80 - time schedule'!BY12","v":0},{"$f":"'K80 - time schedule'!BZ12","v":0},{"$f":"'K80 - time schedule'!CA12","v":0},{"$f":"'K80 - time schedule'!CB12","v":0},{"$f":"'K80 - time schedule'!CC12","v":0},{"$f":"'K80 - time schedule'!CD12","v":0},{"$f":"'K80 - time schedule'!CE12","v":0},{"$f":"'K80 - time schedule'!CF12","v":0},{"$f":"'K80 - time schedule'!CG12","v":0},{"$f":"'K80 - time schedule'!CH12","v":0},{"$f":"'K80 - time schedule'!CI12","v":0},{"$f":"'K80 - time schedule'!CJ12","v":0},{"$f":"'K80 - time schedule'!CK12","v":0},{"$f":"'K80 - time schedule'!CL12","v":0},{"$f":"'K80 - time schedule'!CM12","v":0},{"$f":"'K80 - time schedule'!CN12","v":0},{"$f":"'K80 - time schedule'!CO12","v":0},{"$f":"'K80 - time schedule'!CP12","v":0},{"$f":"'K80 - time schedule'!CQ12","v":0},{"$f":"'K80 - time schedule'!CR12","v":0},{"$f":"'K80 - time schedule'!CS12","v":0},{"$f":"'K80 - time schedule'!CT12","v":0},{"$f":"'K80 - time schedule'!CU12","v":0},{"$f":"'K80 - time schedule'!CV12","v":0},{"$f":"'K80 - time schedule'!CW12","v":0},{"$f":"'K80 - time schedule'!CX12","v":0},{"$f":"'K80 - time schedule'!CY12","v":0},{"$f":"'K80 - time schedule'!CZ12","v":0},{"$f":"'K80 - time schedule'!DA12","v":0},{"$f":"'K80 - time schedule'!DB12","v":0},{"$f":"'K80 - time schedule'!DC12","v":0},{"$f":"'K80 - time schedule'!DD12","v":0},{"$f":"'K80 - time schedule'!DE12","v":0},{"$f":"'K80 - time schedule'!DF12","v":0},{"$f":"'K80 - time schedule'!DG12","v":0},{"$f":"'K80 - time schedule'!DH12","v":0},{"$f":"'K80 - time schedule'!DI12","v":0},{"$f":"'K80 - time schedule'!DJ12","v":0},{"$f":"'K80 - time schedule'!DK12","v":0},{"$f":"'K80 - time schedule'!DL12","v":0},{"$f":"'K80 - time schedule'!DM12","v":0},{"$f":"'K80 - time schedule'!DN12","v":0},{"$f":"'K80 - time schedule'!DO12","v":0},{"$f":"'K80 - time schedule'!DP12","v":0},{"$f":"'K80 - time schedule'!DQ12","v":0},{"$f":"'K80 - time schedule'!DR12","v":0},{"$f":"'K80 - time schedule'!DS12","v":0},{"$f":"'K80 - time schedule'!DT12","v":0},{"$f":"'K80 - time schedule'!DU12","v":0},{"$f":"'K80 - time schedule'!DV12","v":0},{"$f":"'K80 - time schedule'!DW12","v":0},{"$f":"'K80 - time schedule'!DX12","v":0},{"$f":"'K80 - time schedule'!DY12","v":0},{"$f":"'K80 - time schedule'!DZ12","v":0},{"$f":"'K80 - time schedule'!EA12","v":0},{"$f":"'K80 - time schedule'!EB12","v":0},{"$f":"'K80 - time schedule'!EC12","v":0},{"$f":"'K80 - time schedule'!ED12","v":0},{"$f":"'K80 - time schedule'!EE12","v":0},{"$f":"'K80 - time schedule'!EF12","v":0},{"$f":"'K80 - time schedule'!EG12","v":0},{"$f":"'K80 - time schedule'!EH12","v":0},{"$f":"'K80 - time schedule'!EI12","v":0},{"$f":"'K80 - time schedule'!EJ12","v":0},{"$f":"'K80 - time schedule'!EK12","v":0},{"$f":"'K80 - time schedule'!EL12","v":0},{"$f":"'K80 - time schedule'!EM12","v":0},{"$f":"'K80 - time schedule'!EN12","v":0},{"$f":"'K80 - time schedule'!EO12","v":0},{"$f":"'K80 - time schedule'!EP12","v":0},{"$f":"'K80 - time schedule'!EQ12","v":0},{"$f":"'K80 - time schedule'!ER12","v":0},{"$f":"'K80 - time schedule'!ES12","v":0},{"$f":"'K80 - time schedule'!ET12","v":0},{"$f":"'K80 - time schedule'!EU12","v":0},{"$f":"'K80 - time schedule'!EV12","v":0},{"$f":"'K80 - time schedule'!EW12","v":0},{"$f":"'K80 - time schedule'!EX12","v":0},{"$f":"'K80 - time schedule'!EY12","v":0},{"$f":"'K80 - time schedule'!EZ12","v":0},{"$f":"'K80 - time schedule'!FA12","v":0},{"$f":"'K80 - time schedule'!FB12","v":0},{"$f":"'K80 - time schedule'!FC12","v":0},{"$f":"'K80 - time schedule'!FD12","v":0},{"$f":"'K80 - time schedule'!FE12","v":0},{"$f":"'K80 - time schedule'!FF12","v":0},{"$f":"'K80 - time schedule'!FG12","v":0},{"$f":"'K80 - time schedule'!FH12","v":0},{"$f":"'K80 - time schedule'!FI12","v":0},{"$f":"'K80 - time schedule'!FJ12","v":0},{"$f":"'K80 - time schedule'!FK12","v":0},{"$f":"'K80 - time schedule'!FL12","v":0},{"$f":"'K80 - time schedule'!FM12","v":0},{"$f":"'K80 - time schedule'!FN12","v":0},{"$f":"'K80 - time schedule'!FO12","v":0},{"$f":"'K80 - time schedule'!FP12","v":0},{"$f":"'K80 - time schedule'!FQ12","v":0},{"$f":"'K80 - time schedule'!FR12","v":0},{"$f":"'K80 - time schedule'!FS12","v":0},{"$f":"'K80 - time schedule'!FT12","v":0},{"$f":"'K80 - time schedule'!FU12","v":0},{"$f":"'K80 - time schedule'!FV12","v":0},{"$f":"'K80 - time schedule'!FW12","v":0},{"$f":"'K80 - time schedule'!FX12","v":0},{"$f":"'K80 - time schedule'!FY12","v":0},{"$f":"'K80 - time schedule'!FZ12","v":0},{"$f":"'K80 - time schedule'!GA12","v":0},{"$f":"'K80 - time schedule'!GB12","v":0},{"$f":"'K80 - time schedule'!GC12","v":0},{"$f":"'K80 - time schedule'!GD12","v":0},{"$f":"'K80 - time schedule'!GE12","v":0},{"$f":"'K80 - time schedule'!GF12","v":0},{"$f":"'K80 - time schedule'!GG12","v":0},{"$f":"'K80 - time schedule'!GH12","v":0},{"$f":"'K80 - time schedule'!GI12","v":0},{"$f":"'K80 - time schedule'!GJ12","v":0},{"$f":"'K80 - time schedule'!GK12","v":0},{"$f":"'K80 - time schedule'!GL12","v":0},{"$f":"'K80 - time schedule'!GM12","v":0},{"$f":"'K80 - time schedule'!GN12","v":0},{"$f":"'K80 - time schedule'!GO12","v":0},{"$f":"'K80 - time schedule'!GP12","v":0},{"$f":"'K80 - time schedule'!GQ12","v":0},{"$f":"'K80 - time schedule'!GR12","v":0},{"$f":"'K80 - time schedule'!GS12","v":0},{"$f":"'K80 - time schedule'!GT12","v":0},{"$f":"'K80 - time schedule'!GU12","v":0},{"$f":"'K80 - time schedule'!GV12","v":0},{"$f":"'K80 - time schedule'!GW12","v":0},{"$f":"'K80 - time schedule'!GX12","v":0},{"$f":"'K80 - time schedule'!GY12","v":0},{"$f":"'K80 - time schedule'!GZ12","v":0},{"$f":"'K80 - time schedule'!HA12","v":0},{"$f":"'K80 - time schedule'!HB12","v":0},{"$f":"'K80 - time schedule'!HC12","v":0},{"$f":"'K80 - time schedule'!HD12","v":0},{"$f":"'K80 - time schedule'!HE12","v":0},{"$f":"'K80 - time schedule'!HF12","v":0},{"$f":"'K80 - time schedule'!HG12","v":0},{"$f":"'K80 - time schedule'!HH12","v":0},{"$f":"'K80 - time schedule'!HI12","v":0},{"$f":"'K80 - time schedule'!HJ12","v":0},{"$f":"'K80 - time schedule'!HK12","v":0},{"$f":"'K80 - time schedule'!HL12","v":0},{"$f":"'K80 - time schedule'!HM12","v":0},{"$f":"'K80 - time schedule'!HN12","v":0},{"$f":"'K80 - time schedule'!HO12","v":0},{"$f":"'K80 - time schedule'!HP12","v":0},{"$f":"'K80 - time schedule'!HQ12","v":0},{"$f":"'K80 - time schedule'!HR12","v":0},{"$f":"'K80 - time schedule'!HS12","v":0},{"$f":"'K80 - time schedule'!HT12","v":0},{"$f":"'K80 - time schedule'!HU12","v":0},{"$f":"'K80 - time schedule'!HV12","v":0},{"$f":"'K80 - time schedule'!HW12","v":0},{"$f":"'K80 - time schedule'!HX12","v":0},{"$f":"'K80 - time schedule'!HY12","v":0},{"$f":"'K80 - time schedule'!HZ12","v":0},{"$f":"'K80 - time schedule'!IA12","v":0},{"$f":"'K80 - time schedule'!IB12","v":0},{"$f":"'K80 - time schedule'!IC12","v":0},{"$f":"'K80 - time schedule'!ID12","v":0},{"$f":"'K80 - time schedule'!IE12","v":0},{"$f":"'K80 - time schedule'!IF12","v":0},{"$f":"'K80 - time schedule'!IG12","v":0},{"$f":"'K80 - time schedule'!IH12","v":0},{"$f":"'K80 - time schedule'!II12","v":0},{"$f":"'K80 - time schedule'!IJ12","v":0},{"$f":"'K80 - time schedule'!IK12","v":0},{"$f":"'K80 - time schedule'!IL12","v":0},{"$f":"'K80 - time schedule'!IM12","v":0},{"$f":"'K80 - time schedule'!IN12","v":0},{"$f":"'K80 - time schedule'!IO12","v":0},{"$f":"'K80 - time schedule'!IP12","v":0},{"$f":"'K80 - time schedule'!IQ12","v":0},{"$f":"'K80 - time schedule'!IR12","v":0},{"$f":"'K80 - time schedule'!IS12","v":0},{"$f":"'K80 - time schedule'!IT12","v":0},{"$f":"'K80 - time schedule'!IU12","v":0},{"$f":"'K80 - time schedule'!IV12","v":0},{"$f":"'K80 - time schedule'!IW12","v":0},{"$f":"'K80 - time schedule'!IX12","v":0},{"$f":"'K80 - time schedule'!IY12","v":0},{"$f":"'K80 - time schedule'!IZ12","v":0},{"$f":"'K80 - time schedule'!JA12","v":0},{"$f":"'K80 - time schedule'!JB12","v":0},{"$f":"'K80 - time schedule'!JC12","v":0},{"$f":"'K80 - time schedule'!JD12","v":0},{"$f":"'K80 - time schedule'!JE12","v":0},{"$f":"'K80 - time schedule'!JF12","v":0},{"$f":"'K80 - time schedule'!JG12","v":0},{"$f":"'K80 - time schedule'!JH12","v":0},{"$f":"'K80 - time schedule'!JI12","v":0},{"$f":"'K80 - time schedule'!JJ12","v":0},{"$f":"'K80 - time schedule'!JK12","v":0},{"$f":"'K80 - time schedule'!JL12","v":0},{"$f":"'K80 - time schedule'!JM12","v":0},{"$f":"'K80 - time schedule'!JN12","v":0},{"$f":"'K80 - time schedule'!JO12","v":0},{"$f":"'K80 - time schedule'!JP12","v":0},{"$f":"'K80 - time schedule'!JQ12","v":0},{"$f":"'K80 - time schedule'!JR12","v":0},{"$f":"'K80 - time schedule'!JS12","v":0},{"$f":"'K80 - time schedule'!JT12","v":0},{"$f":"'K80 - time schedule'!JU12","v":0},{"$f":"'K80 - time schedule'!JV12","v":0},{"$f":"'K80 - time schedule'!JW12","v":0},{"$f":"'K80 - time schedule'!JX12","v":0},{"$f":"'K80 - time schedule'!JY12","v":0},{"$f":"'K80 - time schedule'!JZ12","v":0},{"$f":"'K80 - time schedule'!KA12","v":0},{"$f":"'K80 - time schedule'!KB12","v":0},{"$f":"'K80 - time schedule'!KC12","v":0},{"$f":"'K80 - time schedule'!KD12","v":0},{"$f":"'K80 - time schedule'!KE12","v":0},{"$f":"'K80 - time schedule'!KF12","v":0},{"$f":"'K80 - time schedule'!KG12","v":0},{"$f":"'K80 - time schedule'!KH12","v":0},{"$f":"'K80 - time schedule'!KI12","v":0},{"$f":"'K80 - time schedule'!KJ12","v":0},{"$f":"'K80 - time schedule'!KK12","v":0},{"$f":"'K80 - time schedule'!KL12","v":0},{"$f":"'K80 - time schedule'!KM12","v":0},{"$f":"'K80 - time schedule'!KN12","v":0},{"$f":"'K80 - time schedule'!KO12","v":0},{"$f":"'K80 - time schedule'!KP12","v":0},{"$f":"'K80 - time schedule'!KQ12","v":0},{"$f":"'K80 - time schedule'!KR12","v":0},{"$f":"'K80 - time schedule'!KS12","v":0},{"$f":"'K80 - time schedule'!KT12","v":0}]
["Boiler room K80 - binding technical specification for other OBs, for other suppliers of technological units ","K80",{"$f":"'K80 - time schedule'!G14","v":0},{"$f":"'K80 - time schedule'!H14","v":0},{"$f":"'K80 - time schedule'!I14","v":0},{"$f":"'K80 - time schedule'!J14","v":0},{"$f":"'K80 - time schedule'!K14","v":0},{"$f":"'K80 - time schedule'!L14","v":0},{"$f":"'K80 - time schedule'!M14","v":0},{"$f":"'K80 - time schedule'!N14","v":0},{"$f":"'K80 - time schedule'!O14","v":0},{"$f":"'K80 - time schedule'!P14","v":0},{"$f":"'K80 - time schedule'!Q14","v":0},{"$f":"'K80 - time schedule'!R14","v":0},{"$f":"'K80 - time schedule'!S14","v":0},{"$f":"'K80 - time schedule'!T14","v":0},{"$f":"'K80 - time schedule'!U14","v":0},{"$f":"'K80 - time schedule'!V14","v":0},{"$f":"'K80 - time schedule'!W14","v":0},{"$f":"'K80 - time schedule'!X14","v":0},{"$f":"'K80 - time schedule'!Y14","v":0},{"$f":"'K80 - time schedule'!Z14","v":0},{"$f":"'K80 - time schedule'!AA14","v":0},{"$f":"'K80 - time schedule'!AB14","v":0},{"$f":"'K80 - time schedule'!AC14","v":0},{"$f":"'K80 - time schedule'!AD14","v":0},{"$f":"'K80 - time schedule'!AE14","v":0},{"$f":"'K80 - time schedule'!AF14","v":0},{"$f":"'K80 - time schedule'!AG14","v":0},{"$f":"'K80 - time schedule'!AH14","v":0},{"$f":"'K80 - time schedule'!AI14","v":0},{"$f":"'K80 - time schedule'!AJ14","v":0},{"$f":"'K80 - time schedule'!AK14","v":0},{"$f":"'K80 - time schedule'!AL14","v":0},{"$f":"'K80 - time schedule'!AM14","v":0},{"$f":"'K80 - time schedule'!AN14","v":0},{"$f":"'K80 - time schedule'!AO14","v":0},{"$f":"'K80 - time schedule'!AP14","v":0},{"$f":"'K80 - time schedule'!AQ14","v":0},{"$f":"'K80 - time schedule'!AR14","v":0},{"$f":"'K80 - time schedule'!AS14","v":0},{"$f":"'K80 - time schedule'!AT14","v":0},{"$f":"'K80 - time schedule'!AU14","v":0},{"$f":"'K80 - time schedule'!AV14","v":0},{"$f":"'K80 - time schedule'!AW14","v":0},{"$f":"'K80 - time schedule'!AX14","v":0},{"$f":"'K80 - time schedule'!AY14","v":0},{"$f":"'K80 - time schedule'!AZ14","v":0},{"$f":"'K80 - time schedule'!BA14","v":0},{"$f":"'K80 - time schedule'!BB14","v":0},{"$f":"'K80 - time schedule'!BC14","v":0},{"$f":"'K80 - time schedule'!BD14","v":0},{"$f":"'K80 - time schedule'!BE14","v":0},{"$f":"'K80 - time schedule'!BF14","v":0},{"$f":"'K80 - time schedule'!BG14","v":0},{"$f":"'K80 - time schedule'!BH14","v":0},{"$f":"'K80 - time schedule'!BI14","v":0},{"$f":"'K80 - time schedule'!BJ14","v":0},{"$f":"'K80 - time schedule'!BK14","v":0},{"$f":"'K80 - time schedule'!BL14","v":0},{"$f":"'K80 - time schedule'!BM14","v":0},{"$f":"'K80 - time schedule'!BN14","v":0},{"$f":"'K80 - time schedule'!BO14","v":0},{"$f":"'K80 - time schedule'!BP14","v":0},{"$f":"'K80 - time schedule'!BQ14","v":0},{"$f":"'K80 - time schedule'!BR14","v":0},{"$f":"'K80 - time schedule'!BS14","v":0},{"$f":"'K80 - time schedule'!BT14","v":0},{"$f":"'K80 - time schedule'!BU14","v":0},{"$f":"'K80 - time schedule'!BV14","v":0},{"$f":"'K80 - time schedule'!BW14","v":0},{"$f":"'K80 - time schedule'!BX14","v":0},{"$f":"'K80 - time schedule'!BY14","v":0},{"$f":"'K80 - time schedule'!BZ14","v":0},{"$f":"'K80 - time schedule'!CA14","v":0},{"$f":"'K80 - time schedule'!CB14","v":0},{"$f":"'K80 - time schedule'!CC14","v":0},{"$f":"'K80 - time schedule'!CD14","v":0},{"$f":"'K80 - time schedule'!CE14","v":0},{"$f":"'K80 - time schedule'!CF14","v":0},{"$f":"'K80 - time schedule'!CG14","v":0},{"$f":"'K80 - time schedule'!CH14","v":0},{"$f":"'K80 - time schedule'!CI14","v":0},{"$f":"'K80 - time schedule'!CJ14","v":0},{"$f":"'K80 - time schedule'!CK14","v":0},{"$f":"'K80 - time schedule'!CL14","v":0},{"$f":"'K80 - time schedule'!CM14","v":0},{"$f":"'K80 - time schedule'!CN14","v":0},{"$f":"'K80 - time schedule'!CO14","v":0},{"$f":"'K80 - time schedule'!CP14","v":0},{"$f":"'K80 - time schedule'!CQ14","v":0},{"$f":"'K80 - time schedule'!CR14","v":0},{"$f":"'K80 - time schedule'!CS14","v":0},{"$f":"'K80 - time schedule'!CT14","v":0},{"$f":"'K80 - time schedule'!CU14","v":0},{"$f":"'K80 - time schedule'!CV14","v":0},{"$f":"'K80 - time schedule'!CW14","v":0},{"$f":"'K80 - time schedule'!CX14","v":0},{"$f":"'K80 - time schedule'!CY14","v":0},{"$f":"'K80 - time schedule'!CZ14","v":0},{"$f":"'K80 - time schedule'!DA14","v":0},{"$f":"'K80 - time schedule'!DB14","v":0},{"$f":"'K80 - time schedule'!DC14","v":0},{"$f":"'K80 - time schedule'!DD14","v":0},{"$f":"'K80 - time schedule'!DE14","v":0},{"$f":"'K80 - time schedule'!DF14","v":0},{"$f":"'K80 - time schedule'!DG14","v":0},{"$f":"'K80 - time schedule'!DH14","v":0},{"$f":"'K80 - time schedule'!DI14","v":0},{"$f":"'K80 - time schedule'!DJ14","v":0},{"$f":"'K80 - time schedule'!DK14","v":0},{"$f":"'K80 - time schedule'!DL14","v":0},{"$f":"'K80 - time schedule'!DM14","v":0},{"$f":"'K80 - time schedule'!DN14","v":0},{"$f":"'K80 - time schedule'!DO14","v":0},{"$f":"'K80 - time schedule'!DP14","v":0},{"$f":"'K80 - time schedule'!DQ14","v":0},{"$f":"'K80 - time schedule'!DR14","v":0},{"$f":"'K80 - time schedule'!DS14","v":0},{"$f":"'K80 - time schedule'!DT14","v":0},{"$f":"'K80 - time schedule'!DU14","v":0},{"$f":"'K80 - time schedule'!DV14","v":0},{"$f":"'K80 - time schedule'!DW14","v":0},{"$f":"'K80 - time schedule'!DX14","v":0},{"$f":"'K80 - time schedule'!DY14","v":0},{"$f":"'K80 - time schedule'!DZ14","v":0},{"$f":"'K80 - time schedule'!EA14","v":0},{"$f":"'K80 - time schedule'!EB14","v":0},{"$f":"'K80 - time schedule'!EC14","v":0},{"$f":"'K80 - time schedule'!ED14","v":0},{"$f":"'K80 - time schedule'!EE14","v":0},{"$f":"'K80 - time schedule'!EF14","v":0},{"$f":"'K80 - time schedule'!EG14","v":0},{"$f":"'K80 - time schedule'!EH14","v":0},{"$f":"'K80 - time schedule'!EI14","v":0},{"$f":"'K80 - time schedule'!EJ14","v":0},{"$f":"'K80 - time schedule'!EK14","v":0},{"$f":"'K80 - time schedule'!EL14","v":0},{"$f":"'K80 - time schedule'!EM14","v":0},{"$f":"'K80 - time schedule'!EN14","v":0},{"$f":"'K80 - time schedule'!EO14","v":0},{"$f":"'K80 - time schedule'!EP14","v":0},{"$f":"'K80 - time schedule'!EQ14","v":0},{"$f":"'K80 - time schedule'!ER14","v":0},{"$f":"'K80 - time schedule'!ES14","v":0},{"$f":"'K80 - time schedule'!ET14","v":0},{"$f":"'K80 - time schedule'!EU14","v":0},{"$f":"'K80 - time schedule'!EV14","v":0},{"$f":"'K80 - time schedule'!EW14","v":0},{"$f":"'K80 - time schedule'!EX14","v":0},{"$f":"'K80 - time schedule'!EY14","v":0},{"$f":"'K80 - time schedule'!EZ14","v":0},{"$f":"'K80 - time schedule'!FA14","v":0},{"$f":"'K80 - time schedule'!FB14","v":0},{"$f":"'K80 - time schedule'!FC14","v":0},{"$f":"'K80 - time schedule'!FD14","v":0},{"$f":"'K80 - time schedule'!FE14","v":0},{"$f":"'K80 - time schedule'!FF14","v":0},{"$f":"'K80 - time schedule'!FG14","v":0},{"$f":"'K80 - time schedule'!FH14","v":0},{"$f":"'K80 - time schedule'!FI14","v":0},{"$f":"'K80 - time schedule'!FJ14","v":0},{"$f":"'K80 - time schedule'!FK14","v":0},{"$f":"'K80 - time schedule'!FL14","v":0},{"$f":"'K80 - time schedule'!FM14","v":0},{"$f":"'K80 - time schedule'!FN14","v":0},{"$f":"'K80 - time schedule'!FO14","v":0},{"$f":"'K80 - time schedule'!FP14","v":0},{"$f":"'K80 - time schedule'!FQ14","v":0},{"$f":"'K80 - time schedule'!FR14","v":0},{"$f":"'K80 - time schedule'!FS14","v":0},{"$f":"'K80 - time schedule'!FT14","v":0},{"$f":"'K80 - time schedule'!FU14","v":0},{"$f":"'K80 - time schedule'!FV14","v":0},{"$f":"'K80 - time schedule'!FW14","v":0},{"$f":"'K80 - time schedule'!FX14","v":0},{"$f":"'K80 - time schedule'!FY14","v":0},{"$f":"'K80 - time schedule'!FZ14","v":0},{"$f":"'K80 - time schedule'!GA14","v":0},{"$f":"'K80 - time schedule'!GB14","v":0},{"$f":"'K80 - time schedule'!GC14","v":0},{"$f":"'K80 - time schedule'!GD14","v":0},{"$f":"'K80 - time schedule'!GE14","v":0},{"$f":"'K80 - time schedule'!GF14","v":0},{"$f":"'K80 - time schedule'!GG14","v":0},{"$f":"'K80 - time schedule'!GH14","v":0},{"$f":"'K80 - time schedule'!GI14","v":0},{"$f":"'K80 - time schedule'!GJ14","v":0},{"$f":"'K80 - time schedule'!GK14","v":0},{"$f":"'K80 - time schedule'!GL14","v":0},{"$f":"'K80 - time schedule'!GM14","v":0},{"$f":"'K80 - time schedule'!GN14","v":0},{"$f":"'K80 - time schedule'!GO14","v":0},{"$f":"'K80 - time schedule'!GP14","v":0},{"$f":"'K80 - time schedule'!GQ14","v":0},{"$f":"'K80 - time schedule'!GR14","v":0},{"$f":"'K80 - time schedule'!GS14","v":0},{"$f":"'K80 - time schedule'!GT14","v":0},{"$f":"'K80 - time schedule'!GU14","v":0},{"$f":"'K80 - time schedule'!GV14","v":0},{"$f":"'K80 - time schedule'!GW14","v":0},{"$f":"'K80 - time schedule'!GX14","v":0},{"$f":"'K80 - time schedule'!GY14","v":0},{"$f":"'K80 - time schedule'!GZ14","v":0},{"$f":"'K80 - time schedule'!HA14","v":0},{"$f":"'K80 - time schedule'!HB14","v":0},{"$f":"'K80 - time schedule'!HC14","v":0},{"$f":"'K80 - time schedule'!HD14","v":0},{"$f":"'K80 - time schedule'!HE14","v":0},{"$f":"'K80 - time schedule'!HF14","v":0},{"$f":"'K80 - time schedule'!HG14","v":0},{"$f":"'K80 - time schedule'!HH14","v":0},{"$f":"'K80 - time schedule'!HI14","v":0},{"$f":"'K80 - time schedule'!HJ14","v":0},{"$f":"'K80 - time schedule'!HK14","v":0},{"$f":"'K80 - time schedule'!HL14","v":0},{"$f":"'K80 - time schedule'!HM14","v":0},{"$f":"'K80 - time schedule'!HN14","v":0},{"$f":"'K80 - time schedule'!HO14","v":0},{"$f":"'K80 - time schedule'!HP14","v":0},{"$f":"'K80 - time schedule'!HQ14","v":0},{"$f":"'K80 - time schedule'!HR14","v":0},{"$f":"'K80 - time schedule'!HS14","v":0},{"$f":"'K80 - time schedule'!HT14","v":0},{"$f":"'K80 - time schedule'!HU14","v":0},{"$f":"'K80 - time schedule'!HV14","v":0},{"$f":"'K80 - time schedule'!HW14","v":0},{"$f":"'K80 - time schedule'!HX14","v":0},{"$f":"'K80 - time schedule'!HY14","v":0},{"$f":"'K80 - time schedule'!HZ14","v":0},{"$f":"'K80 - time schedule'!IA14","v":0},{"$f":"'K80 - time schedule'!IB14","v":0},{"$f":"'K80 - time schedule'!IC14","v":0},{"$f":"'K80 - time schedule'!ID14","v":0},{"$f":"'K80 - time schedule'!IE14","v":0},{"$f":"'K80 - time schedule'!IF14","v":0},{"$f":"'K80 - time schedule'!IG14","v":0},{"$f":"'K80 - time schedule'!IH14","v":0},{"$f":"'K80 - time schedule'!II14","v":0},{"$f":"'K80 - time schedule'!IJ14","v":0},{"$f":"'K80 - time schedule'!IK14","v":0},{"$f":"'K80 - time schedule'!IL14","v":0},{"$f":"'K80 - time schedule'!IM14","v":0},{"$f":"'K80 - time schedule'!IN14","v":0},{"$f":"'K80 - time schedule'!IO14","v":0},{"$f":"'K80 - time schedule'!IP14","v":0},{"$f":"'K80 - time schedule'!IQ14","v":0},{"$f":"'K80 - time schedule'!IR14","v":0},{"$f":"'K80 - time schedule'!IS14","v":0},{"$f":"'K80 - time schedule'!IT14","v":0},{"$f":"'K80 - time schedule'!IU14","v":0},{"$f":"'K80 - time schedule'!IV14","v":0},{"$f":"'K80 - time schedule'!IW14","v":0},{"$f":"'K80 - time schedule'!IX14","v":0},{"$f":"'K80 - time schedule'!IY14","v":0},{"$f":"'K80 - time schedule'!IZ14","v":0},{"$f":"'K80 - time schedule'!JA14","v":0},{"$f":"'K80 - time schedule'!JB14","v":0},{"$f":"'K80 - time schedule'!JC14","v":0},{"$f":"'K80 - time schedule'!JD14","v":0},{"$f":"'K80 - time schedule'!JE14","v":0},{"$f":"'K80 - time schedule'!JF14","v":0},{"$f":"'K80 - time schedule'!JG14","v":0},{"$f":"'K80 - time schedule'!JH14","v":0},{"$f":"'K80 - time schedule'!JI14","v":0},{"$f":"'K80 - time schedule'!JJ14","v":0},{"$f":"'K80 - time schedule'!JK14","v":0},{"$f":"'K80 - time schedule'!JL14","v":0},{"$f":"'K80 - time schedule'!JM14","v":0},{"$f":"'K80 - time schedule'!JN14","v":0},{"$f":"'K80 - time schedule'!JO14","v":0},{"$f":"'K80 - time schedule'!JP14","v":0},{"$f":"'K80 - time schedule'!JQ14","v":0},{"$f":"'K80 - time schedule'!JR14","v":0},{"$f":"'K80 - time schedule'!JS14","v":0},{"$f":"'K80 - time schedule'!JT14","v":0},{"$f":"'K80 - time schedule'!JU14","v":0},{"$f":"'K80 - time schedule'!JV14","v":0},{"$f":"'K80 - time schedule'!JW14","v":0},{"$f":"'K80 - time schedule'!JX14","v":0},{"$f":"'K80 - time schedule'!JY14","v":0},{"$f":"'K80 - time schedule'!JZ14","v":0},{"$f":"'K80 - time schedule'!KA14","v":0},{"$f":"'K80 - time schedule'!KB14","v":0},{"$f":"'K80 - time schedule'!KC14","v":0},{"$f":"'K80 - time schedule'!KD14","v":0},{"$f":"'K80 - time schedule'!KE14","v":0},{"$f":"'K80 - time schedule'!KF14","v":0},{"$f":"'K80 - time schedule'!KG14","v":0},{"$f":"'K80 - time schedule'!KH14","v":0},{"$f":"'K80 - time schedule'!KI14","v":0},{"$f":"'K80 - time schedule'!KJ14","v":0},{"$f":"'K80 - time schedule'!KK14","v":0},{"$f":"'K80 - time schedule'!KL14","v":0},{"$f":"'K80 - time schedule'!KM14","v":0},{"$f":"'K80 - time schedule'!KN14","v":0},{"$f":"'K80 - time schedule'!KO14","v":0},{"$f":"'K80 - time schedule'!KP14","v":0},{"$f":"'K80 - time schedule'!KQ14","v":0},{"$f":"'K80 - time schedule'!KR14","v":0},{"$f":"'K80 - time schedule'!KS14","v":0},{"$f":"'K80 - time schedule'!KT14","v":0}]
["Boiler room K80 - approved implementation documentation","K80",{"$f":"'K80 - time schedule'!G16","v":0},{"$f":"'K80 - time schedule'!H16","v":0},{"$f":"'K80 - time schedule'!I16","v":0},{"$f":"'K80 - time schedule'!J16","v":0},{"$f":"'K80 - time schedule'!K16","v":0},{"$f":"'K80 - time schedule'!L16","v":0},{"$f":"'K80 - time schedule'!M16","v":0},{"$f":"'K80 - time schedule'!N16","v":0},{"$f":"'K80 - time schedule'!O16","v":0},{"$f":"'K80 - time schedule'!P16","v":0},{"$f":"'K80 - time schedule'!Q16","v":0},{"$f":"'K80 - time schedule'!R16","v":0},{"$f":"'K80 - time schedule'!S16","v":0},{"$f":"'K80 - time schedule'!T16","v":0},{"$f":"'K80 - time schedule'!U16","v":0},{"$f":"'K80 - time schedule'!V16","v":0},{"$f":"'K80 - time schedule'!W16","v":0},{"$f":"'K80 - time schedule'!X16","v":0},{"$f":"'K80 - time schedule'!Y16","v":0},{"$f":"'K80 - time schedule'!Z16","v":0},{"$f":"'K80 - time schedule'!AA16","v":0},{"$f":"'K80 - time schedule'!AB16","v":0},{"$f":"'K80 - time schedule'!AC16","v":0},{"$f":"'K80 - time schedule'!AD16","v":0},{"$f":"'K80 - time schedule'!AE16","v":0},{"$f":"'K80 - time schedule'!AF16","v":0},{"$f":"'K80 - time schedule'!AG16","v":0},{"$f":"'K80 - time schedule'!AH16","v":0},{"$f":"'K80 - time schedule'!AI16","v":0},{"$f":"'K80 - time schedule'!AJ16","v":0},{"$f":"'K80 - time schedule'!AK16","v":0},{"$f":"'K80 - time schedule'!AL16","v":0},{"$f":"'K80 - time schedule'!AM16","v":0},{"$f":"'K80 - time schedule'!AN16","v":0},{"$f":"'K80 - time schedule'!AO16","v":0},{"$f":"'K80 - time schedule'!AP16","v":0},{"$f":"'K80 - time schedule'!AQ16","v":0},{"$f":"'K80 - time schedule'!AR16","v":0},{"$f":"'K80 - time schedule'!AS16","v":0},{"$f":"'K80 - time schedule'!AT16","v":0},{"$f":"'K80 - time schedule'!AU16","v":0},{"$f":"'K80 - time schedule'!AV16","v":0},{"$f":"'K80 - time schedule'!AW16","v":0},{"$f":"'K80 - time schedule'!AX16","v":0},{"$f":"'K80 - time schedule'!AY16","v":0},{"$f":"'K80 - time schedule'!AZ16","v":0},{"$f":"'K80 - time schedule'!BA16","v":0},{"$f":"'K80 - time schedule'!BB16","v":0},{"$f":"'K80 - time schedule'!BC16","v":0},{"$f":"'K80 - time schedule'!BD16","v":0},{"$f":"'K80 - time schedule'!BE16","v":0},{"$f":"'K80 - time schedule'!BF16","v":0},{"$f":"'K80 - time schedule'!BG16","v":0},{"$f":"'K80 - time schedule'!BH16","v":0},{"$f":"'K80 - time schedule'!BI16","v":0},{"$f":"'K80 - time schedule'!BJ16","v":0},{"$f":"'K80 - time schedule'!BK16","v":0},{"$f":"'K80 - time schedule'!BL16","v":0},{"$f":"'K80 - time schedule'!BM16","v":0},{"$f":"'K80 - time schedule'!BN16","v":0},{"$f":"'K80 - time schedule'!BO16","v":0},{"$f":"'K80 - time schedule'!BP16","v":0},{"$f":"'K80 - time schedule'!BQ16","v":0},{"$f":"'K80 - time schedule'!BR16","v":0},{"$f":"'K80 - time schedule'!BS16","v":0},{"$f":"'K80 - time schedule'!BT16","v":0},{"$f":"'K80 - time schedule'!BU16","v":0},{"$f":"'K80 - time schedule'!BV16","v":0},{"$f":"'K80 - time schedule'!BW16","v":0},{"$f":"'K80 - time schedule'!BX16","v":0},{"$f":"'K80 - time schedule'!BY16","v":0},{"$f":"'K80 - time schedule'!BZ16","v":0},{"$f":"'K80 - time schedule'!CA16","v":0},{"$f":"'K80 - time schedule'!CB16","v":0},{"$f":"'K80 - time schedule'!CC16","v":0},{"$f":"'K80 - time schedule'!CD16","v":0},{"$f":"'K80 - time schedule'!CE16","v":0},{"$f":"'K80 - time schedule'!CF16","v":0},{"$f":"'K80 - time schedule'!CG16","v":0},{"$f":"'K80 - time schedule'!CH16","v":0},{"$f":"'K80 - time schedule'!CI16","v":0},{"$f":"'K80 - time schedule'!CJ16","v":0},{"$f":"'K80 - time schedule'!CK16","v":0},{"$f":"'K80 - time schedule'!CL16","v":0},{"$f":"'K80 - time schedule'!CM16","v":0},{"$f":"'K80 - time schedule'!CN16","v":0},{"$f":"'K80 - time schedule'!CO16","v":0},{"$f":"'K80 - time schedule'!CP16","v":0},{"$f":"'K80 - time schedule'!CQ16","v":0},{"$f":"'K80 - time schedule'!CR16","v":0},{"$f":"'K80 - time schedule'!CS16","v":0},{"$f":"'K80 - time schedule'!CT16","v":0},{"$f":"'K80 - time schedule'!CU16","v":0},{"$f":"'K80 - time schedule'!CV16","v":0},{"$f":"'K80 - time schedule'!CW16","v":0},{"$f":"'K80 - time schedule'!CX16","v":0},{"$f":"'K80 - time schedule'!CY16","v":0},{"$f":"'K80 - time schedule'!CZ16","v":0},{"$f":"'K80 - time schedule'!DA16","v":0},{"$f":"'K80 - time schedule'!DB16","v":0},{"$f":"'K80 - time schedule'!DC16","v":0},{"$f":"'K80 - time schedule'!DD16","v":0},{"$f":"'K80 - time schedule'!DE16","v":0},{"$f":"'K80 - time schedule'!DF16","v":0},{"$f":"'K80 - time schedule'!DG16","v":0},{"$f":"'K80 - time schedule'!DH16","v":0},{"$f":"'K80 - time schedule'!DI16","v":0},{"$f":"'K80 - time schedule'!DJ16","v":0},{"$f":"'K80 - time schedule'!DK16","v":0},{"$f":"'K80 - time schedule'!DL16","v":0},{"$f":"'K80 - time schedule'!DM16","v":0},{"$f":"'K80 - time schedule'!DN16","v":0},{"$f":"'K80 - time schedule'!DO16","v":0},{"$f":"'K80 - time schedule'!DP16","v":0},{"$f":"'K80 - time schedule'!DQ16","v":0},{"$f":"'K80 - time schedule'!DR16","v":0},{"$f":"'K80 - time schedule'!DS16","v":0},{"$f":"'K80 - time schedule'!DT16","v":0},{"$f":"'K80 - time schedule'!DU16","v":0},{"$f":"'K80 - time schedule'!DV16","v":0},{"$f":"'K80 - time schedule'!DW16","v":0},{"$f":"'K80 - time schedule'!DX16","v":0},{"$f":"'K80 - time schedule'!DY16","v":0},{"$f":"'K80 - time schedule'!DZ16","v":0},{"$f":"'K80 - time schedule'!EA16","v":0},{"$f":"'K80 - time schedule'!EB16","v":0},{"$f":"'K80 - time schedule'!EC16","v":0},{"$f":"'K80 - time schedule'!ED16","v":0},{"$f":"'K80 - time schedule'!EE16","v":0},{"$f":"'K80 - time schedule'!EF16","v":0},{"$f":"'K80 - time schedule'!EG16","v":0},{"$f":"'K80 - time schedule'!EH16","v":0},{"$f":"'K80 - time schedule'!EI16","v":0},{"$f":"'K80 - time schedule'!EJ16","v":0},{"$f":"'K80 - time schedule'!EK16","v":0},{"$f":"'K80 - time schedule'!EL16","v":0},{"$f":"'K80 - time schedule'!EM16","v":0},{"$f":"'K80 - time schedule'!EN16","v":0},{"$f":"'K80 - time schedule'!EO16","v":0},{"$f":"'K80 - time schedule'!EP16","v":0},{"$f":"'K80 - time schedule'!EQ16","v":0},{"$f":"'K80 - time schedule'!ER16","v":0},{"$f":"'K80 - time schedule'!ES16","v":0},{"$f":"'K80 - time schedule'!ET16","v":0},{"$f":"'K80 - time schedule'!EU16","v":0},{"$f":"'K80 - time schedule'!EV16","v":0},{"$f":"'K80 - time schedule'!EW16","v":0},{"$f":"'K80 - time schedule'!EX16","v":0},{"$f":"'K80 - time schedule'!EY16","v":0},{"$f":"'K80 - time schedule'!EZ16","v":0},{"$f":"'K80 - time schedule'!FA16","v":0},{"$f":"'K80 - time schedule'!FB16","v":0},{"$f":"'K80 - time schedule'!FC16","v":0},{"$f":"'K80 - time schedule'!FD16","v":0},{"$f":"'K80 - time schedule'!FE16","v":0},{"$f":"'K80 - time schedule'!FF16","v":0},{"$f":"'K80 - time schedule'!FG16","v":0},{"$f":"'K80 - time schedule'!FH16","v":0},{"$f":"'K80 - time schedule'!FI16","v":0},{"$f":"'K80 - time schedule'!FJ16","v":0},{"$f":"'K80 - time schedule'!FK16","v":0},{"$f":"'K80 - time schedule'!FL16","v":0},{"$f":"'K80 - time schedule'!FM16","v":0},{"$f":"'K80 - time schedule'!FN16","v":0},{"$f":"'K80 - time schedule'!FO16","v":0},{"$f":"'K80 - time schedule'!FP16","v":0},{"$f":"'K80 - time schedule'!FQ16","v":0},{"$f":"'K80 - time schedule'!FR16","v":0},{"$f":"'K80 - time schedule'!FS16","v":0},{"$f":"'K80 - time schedule'!FT16","v":0},{"$f":"'K80 - time schedule'!FU16","v":0},{"$f":"'K80 - time schedule'!FV16","v":0},{"$f":"'K80 - time schedule'!FW16","v":0},{"$f":"'K80 - time schedule'!FX16","v":0},{"$f":"'K80 - time schedule'!FY16","v":0},{"$f":"'K80 - time schedule'!FZ16","v":0},{"$f":"'K80 - time schedule'!GA16","v":0},{"$f":"'K80 - time schedule'!GB16","v":0},{"$f":"'K80 - time schedule'!GC16","v":0},{"$f":"'K80 - time schedule'!GD16","v":0},{"$f":"'K80 - time schedule'!GE16","v":0},{"$f":"'K80 - time schedule'!GF16","v":0},{"$f":"'K80 - time schedule'!GG16","v":0},{"$f":"'K80 - time schedule'!GH16","v":0},{"$f":"'K80 - time schedule'!GI16","v":0},{"$f":"'K80 - time schedule'!GJ16","v":0},{"$f":"'K80 - time schedule'!GK16","v":0},{"$f":"'K80 - time schedule'!GL16","v":0},{"$f":"'K80 - time schedule'!GM16","v":0},{"$f":"'K80 - time schedule'!GN16","v":0},{"$f":"'K80 - time schedule'!GO16","v":0},{"$f":"'K80 - time schedule'!GP16","v":0},{"$f":"'K80 - time schedule'!GQ16","v":0},{"$f":"'K80 - time schedule'!GR16","v":0},{"$f":"'K80 - time schedule'!GS16","v":0},{"$f":"'K80 - time schedule'!GT16","v":0},{"$f":"'K80 - time schedule'!GU16","v":0},{"$f":"'K80 - time schedule'!GV16","v":0},{"$f":"'K80 - time schedule'!GW16","v":0},{"$f":"'K80 - time schedule'!GX16","v":0},{"$f":"'K80 - time schedule'!GY16","v":0},{"$f":"'K80 - time schedule'!GZ16","v":0},{"$f":"'K80 - time schedule'!HA16","v":0},{"$f":"'K80 - time schedule'!HB16","v":0},{"$f":"'K80 - time schedule'!HC16","v":0},{"$f":"'K80 - time schedule'!HD16","v":0},{"$f":"'K80 - time schedule'!HE16","v":0},{"$f":"'K80 - time schedule'!HF16","v":0},{"$f":"'K80 - time schedule'!HG16","v":0},{"$f":"'K80 - time schedule'!HH16","v":0},{"$f":"'K80 - time schedule'!HI16","v":0},{"$f":"'K80 - time schedule'!HJ16","v":0},{"$f":"'K80 - time schedule'!HK16","v":0},{"$f":"'K80 - time schedule'!HL16","v":0},{"$f":"'K80 - time schedule'!HM16","v":0},{"$f":"'K80 - time schedule'!HN16","v":0},{"$f":"'K80 - time schedule'!HO16","v":0},{"$f":"'K80 - time schedule'!HP16","v":0},{"$f":"'K80 - time schedule'!HQ16","v":0},{"$f":"'K80 - time schedule'!HR16","v":0},{"$f":"'K80 - time schedule'!HS16","v":0},{"$f":"'K80 - time schedule'!HT16","v":0},{"$f":"'K80 - time schedule'!HU16","v":0},{"$f":"'K80 - time schedule'!HV16","v":0},{"$f":"'K80 - time schedule'!HW16","v":0},{"$f":"'K80 - time schedule'!HX16","v":0},{"$f":"'K80 - time schedule'!HY16","v":0},{"$f":"'K80 - time schedule'!HZ16","v":0},{"$f":"'K80 - time schedule'!IA16","v":0},{"$f":"'K80 - time schedule'!IB16","v":0},{"$f":"'K80 - time schedule'!IC16","v":0},{"$f":"'K80 - time schedule'!ID16","v":0},{"$f":"'K80 - time schedule'!IE16","v":0},{"$f":"'K80 - time schedule'!IF16","v":0},{"$f":"'K80 - time schedule'!IG16","v":0},{"$f":"'K80 - time schedule'!IH16","v":0},{"$f":"'K80 - time schedule'!II16","v":0},{"$f":"'K80 - time schedule'!IJ16","v":0},{"$f":"'K80 - time schedule'!IK16","v":0},{"$f":"'K80 - time schedule'!IL16","v":0},{"$f":"'K80 - time schedule'!IM16","v":0},{"$f":"'K80 - time schedule'!IN16","v":0},{"$f":"'K80 - time schedule'!IO16","v":0},{"$f":"'K80 - time schedule'!IP16","v":0},{"$f":"'K80 - time schedule'!IQ16","v":0},{"$f":"'K80 - time schedule'!IR16","v":0},{"$f":"'K80 - time schedule'!IS16","v":0},{"$f":"'K80 - time schedule'!IT16","v":0},{"$f":"'K80 - time schedule'!IU16","v":0},{"$f":"'K80 - time schedule'!IV16","v":0},{"$f":"'K80 - time schedule'!IW16","v":0},{"$f":"'K80 - time schedule'!IX16","v":0},{"$f":"'K80 - time schedule'!IY16","v":0},{"$f":"'K80 - time schedule'!IZ16","v":0},{"$f":"'K80 - time schedule'!JA16","v":0},{"$f":"'K80 - time schedule'!JB16","v":0},{"$f":"'K80 - time schedule'!JC16","v":0},{"$f":"'K80 - time schedule'!JD16","v":0},{"$f":"'K80 - time schedule'!JE16","v":0},{"$f":"'K80 - time schedule'!JF16","v":0},{"$f":"'K80 - time schedule'!JG16","v":0},{"$f":"'K80 - time schedule'!JH16","v":0},{"$f":"'K80 - time schedule'!JI16","v":0},{"$f":"'K80 - time schedule'!JJ16","v":0},{"$f":"'K80 - time schedule'!JK16","v":0},{"$f":"'K80 - time schedule'!JL16","v":0},{"$f":"'K80 - time schedule'!JM16","v":0},{"$f":"'K80 - time schedule'!JN16","v":0},{"$f":"'K80 - time schedule'!JO16","v":0},{"$f":"'K80 - time schedule'!JP16","v":0},{"$f":"'K80 - time schedule'!JQ16","v":0},{"$f":"'K80 - time schedule'!JR16","v":0},{"$f":"'K80 - time schedule'!JS16","v":0},{"$f":"'K80 - time schedule'!JT16","v":0},{"$f":"'K80 - time schedule'!JU16","v":0},{"$f":"'K80 - time schedule'!JV16","v":0},{"$f":"'K80 - time schedule'!JW16","v":0},{"$f":"'K80 - time schedule'!JX16","v":0},{"$f":"'K80 - time schedule'!JY16","v":0},{"$f":"'K80 - time schedule'!JZ16","v":0},{"$f":"'K80 - time schedule'!KA16","v":0},{"$f":"'K80 - time schedule'!KB16","v":0},{"$f":"'K80 - time schedule'!KC16","v":0},{"$f":"'K80 - time schedule'!KD16","v":0},{"$f":"'K80 - time schedule'!KE16","v":0},{"$f":"'K80 - time schedule'!KF16","v":0},{"$f":"'K80 - time schedule'!KG16","v":0},{"$f":"'K80 - time schedule'!KH16","v":0},{"$f":"'K80 - time schedule'!KI16","v":0},{"$f":"'K80 - time schedule'!KJ16","v":0},{"$f":"'K80 - time schedule'!KK16","v":0},{"$f":"'K80 - time schedule'!KL16","v":0},{"$f":"'K80 - time schedule'!KM16","v":0},{"$f":"'K80 - time schedule'!KN16","v":0},{"$f":"'K80 - time schedule'!KO16","v":0},{"$f":"'K80 - time schedule'!KP16","v":0},{"$f":"'K80 - time schedule'!KQ16","v":0},{"$f":"'K80 - time schedule'!KR16","v":0},{"$f":"'K80 - time schedule'!KS16","v":0},{"$f":"'K80 - time schedule'!KT16","v":0}]
["Boiler room K80 - handover and acceptance of construction site","K80",{"$f":"'K80 - time schedule'!G18","v":0},{"$f":"'K80 - time schedule'!H18","v":0},{"$f":"'K80 - time schedule'!I18","v":0},{"$f":"'K80 - time schedule'!J18","v":0},{"$f":"'K80 - time schedule'!K18","v":0},{"$f":"'K80 - time schedule'!L18","v":0},{"$f":"'K80 - time schedule'!M18","v":0},{"$f":"'K80 - time schedule'!N18","v":0},{"$f":"'K80 - time schedule'!O18","v":0},{"$f":"'K80 - time schedule'!P18","v":0},{"$f":"'K80 - time schedule'!Q18","v":0},{"$f":"'K80 - time schedule'!R18","v":0},{"$f":"'K80 - time schedule'!S18","v":0},{"$f":"'K80 - time schedule'!T18","v":0},{"$f":"'K80 - time schedule'!U18","v":0},{"$f":"'K80 - time schedule'!V18","v":0},{"$f":"'K80 - time schedule'!W18","v":0},{"$f":"'K80 - time schedule'!X18","v":0},{"$f":"'K80 - time schedule'!Y18","v":0},{"$f":"'K80 - time schedule'!Z18","v":0},{"$f":"'K80 - time schedule'!AA18","v":0},{"$f":"'K80 - time schedule'!AB18","v":0},{"$f":"'K80 - time schedule'!AC18","v":0},{"$f":"'K80 - time schedule'!AD18","v":0},{"$f":"'K80 - time schedule'!AE18","v":0},{"$f":"'K80 - time schedule'!AF18","v":0},{"$f":"'K80 - time schedule'!AG18","v":0},{"$f":"'K80 - time schedule'!AH18","v":0},{"$f":"'K80 - time schedule'!AI18","v":0},{"$f":"'K80 - time schedule'!AJ18","v":0},{"$f":"'K80 - time schedule'!AK18","v":0},{"$f":"'K80 - time schedule'!AL18","v":0},{"$f":"'K80 - time schedule'!AM18","v":0},{"$f":"'K80 - time schedule'!AN18","v":0},{"$f":"'K80 - time schedule'!AO18","v":0},{"$f":"'K80 - time schedule'!AP18","v":0},{"$f":"'K80 - time schedule'!AQ18","v":0},{"$f":"'K80 - time schedule'!AR18","v":0},{"$f":"'K80 - time schedule'!AS18","v":0},{"$f":"'K80 - time schedule'!AT18","v":0},{"$f":"'K80 - time schedule'!AU18","v":0},{"$f":"'K80 - time schedule'!AV18","v":0},{"$f":"'K80 - time schedule'!AW18","v":0},{"$f":"'K80 - time schedule'!AX18","v":0},{"$f":"'K80 - time schedule'!AY18","v":0},{"$f":"'K80 - time schedule'!AZ18","v":0},{"$f":"'K80 - time schedule'!BA18","v":0},{"$f":"'K80 - time schedule'!BB18","v":0},{"$f":"'K80 - time schedule'!BC18","v":0},{"$f":"'K80 - time schedule'!BD18","v":0},{"$f":"'K80 - time schedule'!BE18","v":0},{"$f":"'K80 - time schedule'!BF18","v":0},{"$f":"'K80 - time schedule'!BG18","v":0},{"$f":"'K80 - time schedule'!BH18","v":0},{"$f":"'K80 - time schedule'!BI18","v":0},{"$f":"'K80 - time schedule'!BJ18","v":0},{"$f":"'K80 - time schedule'!BK18","v":0},{"$f":"'K80 - time schedule'!BL18","v":0},{"$f":"'K80 - time schedule'!BM18","v":0},{"$f":"'K80 - time schedule'!BN18","v":0},{"$f":"'K80 - time schedule'!BO18","v":0},{"$f":"'K80 - time schedule'!BP18","v":0},{"$f":"'K80 - time schedule'!BQ18","v":0},{"$f":"'K80 - time schedule'!BR18","v":0},{"$f":"'K80 - time schedule'!BS18","v":0},{"$f":"'K80 - time schedule'!BT18","v":0},{"$f":"'K80 - time schedule'!BU18","v":0},{"$f":"'K80 - time schedule'!BV18","v":0},{"$f":"'K80 - time schedule'!BW18","v":0},{"$f":"'K80 - time schedule'!BX18","v":0},{"$f":"'K80 - time schedule'!BY18","v":0},{"$f":"'K80 - time schedule'!BZ18","v":0},{"$f":"'K80 - time schedule'!CA18","v":0},{"$f":"'K80 - time schedule'!CB18","v":0},{"$f":"'K80 - time schedule'!CC18","v":0},{"$f":"'K80 - time schedule'!CD18","v":0},{"$f":"'K80 - time schedule'!CE18","v":0},{"$f":"'K80 - time schedule'!CF18","v":0},{"$f":"'K80 - time schedule'!CG18","v":0},{"$f":"'K80 - time schedule'!CH18","v":0},{"$f":"'K80 - time schedule'!CI18","v":0},{"$f":"'K80 - time schedule'!CJ18","v":0},{"$f":"'K80 - time schedule'!CK18","v":0},{"$f":"'K80 - time schedule'!CL18","v":0},{"$f":"'K80 - time schedule'!CM18","v":0},{"$f":"'K80 - time schedule'!CN18","v":0},{"$f":"'K80 - time schedule'!CO18","v":0},{"$f":"'K80 - time schedule'!CP18","v":0},{"$f":"'K80 - time schedule'!CQ18","v":0},{"$f":"'K80 - time schedule'!CR18","v":0},{"$f":"'K80 - time schedule'!CS18","v":0},{"$f":"'K80 - time schedule'!CT18","v":0},{"$f":"'K80 - time schedule'!CU18","v":0},{"$f":"'K80 - time schedule'!CV18","v":0},{"$f":"'K80 - time schedule'!CW18","v":0},{"$f":"'K80 - time schedule'!CX18","v":0},{"$f":"'K80 - time schedule'!CY18","v":0},{"$f":"'K80 - time schedule'!CZ18","v":0},{"$f":"'K80 - time schedule'!DA18","v":0},{"$f":"'K80 - time schedule'!DB18","v":0},{"$f":"'K80 - time schedule'!DC18","v":0},{"$f":"'K80 - time schedule'!DD18","v":0},{"$f":"'K80 - time schedule'!DE18","v":0},{"$f":"'K80 - time schedule'!DF18","v":0},{"$f":"'K80 - time schedule'!DG18","v":0},{"$f":"'K80 - time schedule'!DH18","v":0},{"$f":"'K80 - time schedule'!DI18","v":0},{"$f":"'K80 - time schedule'!DJ18","v":0},{"$f":"'K80 - time schedule'!DK18","v":0},{"$f":"'K80 - time schedule'!DL18","v":0},{"$f":"'K80 - time schedule'!DM18","v":0},{"$f":"'K80 - time schedule'!DN18","v":0},{"$f":"'K80 - time schedule'!DO18","v":0},{"$f":"'K80 - time schedule'!DP18","v":0},{"$f":"'K80 - time schedule'!DQ18","v":0},{"$f":"'K80 - time schedule'!DR18","v":0},{"$f":"'K80 - time schedule'!DS18","v":0},{"$f":"'K80 - time schedule'!DT18","v":0},{"$f":"'K80 - time schedule'!DU18","v":0},{"$f":"'K80 - time schedule'!DV18","v":0},{"$f":"'K80 - time schedule'!DW18","v":0},{"$f":"'K80 - time schedule'!DX18","v":0},{"$f":"'K80 - time schedule'!DY18","v":0},{"$f":"'K80 - time schedule'!DZ18","v":0},{"$f":"'K80 - time schedule'!EA18","v":0},{"$f":"'K80 - time schedule'!EB18","v":0},{"$f":"'K80 - time schedule'!EC18","v":0},{"$f":"'K80 - time schedule'!ED18","v":0},{"$f":"'K80 - time schedule'!EE18","v":0},{"$f":"'K80 - time schedule'!EF18","v":0},{"$f":"'K80 - time schedule'!EG18","v":0},{"$f":"'K80 - time schedule'!EH18","v":0},{"$f":"'K80 - time schedule'!EI18","v":0},{"$f":"'K80 - time schedule'!EJ18","v":0},{"$f":"'K80 - time schedule'!EK18","v":0},{"$f":"'K80 - time schedule'!EL18","v":0},{"$f":"'K80 - time schedule'!EM18","v":0},{"$f":"'K80 - time schedule'!EN18","v":0},{"$f":"'K80 - time schedule'!EO18","v":0},{"$f":"'K80 - time schedule'!EP18","v":0},{"$f":"'K80 - time schedule'!EQ18","v":0},{"$f":"'K80 - time schedule'!ER18","v":0},{"$f":"'K80 - time schedule'!ES18","v":0},{"$f":"'K80 - time schedule'!ET18","v":0},{"$f":"'K80 - time schedule'!EU18","v":0},{"$f":"'K80 - time schedule'!EV18","v":0},{"$f":"'K80 - time schedule'!EW18","v":0},{"$f":"'K80 - time schedule'!EX18","v":0},{"$f":"'K80 - time schedule'!EY18","v":0},{"$f":"'K80 - time schedule'!EZ18","v":0},{"$f":"'K80 - time schedule'!FA18","v":0},{"$f":"'K80 - time schedule'!FB18","v":0},{"$f":"'K80 - time schedule'!FC18","v":0},{"$f":"'K80 - time schedule'!FD18","v":0},{"$f":"'K80 - time schedule'!FE18","v":0},{"$f":"'K80 - time schedule'!FF18","v":0},{"$f":"'K80 - time schedule'!FG18","v":0},{"$f":"'K80 - time schedule'!FH18","v":0},{"$f":"'K80 - time schedule'!FI18","v":0},{"$f":"'K80 - time schedule'!FJ18","v":0},{"$f":"'K80 - time schedule'!FK18","v":0},{"$f":"'K80 - time schedule'!FL18","v":0},{"$f":"'K80 - time schedule'!FM18","v":0},{"$f":"'K80 - time schedule'!FN18","v":0},{"$f":"'K80 - time schedule'!FO18","v":0},{"$f":"'K80 - time schedule'!FP18","v":0},{"$f":"'K80 - time schedule'!FQ18","v":0},{"$f":"'K80 - time schedule'!FR18","v":0},{"$f":"'K80 - time schedule'!FS18","v":0},{"$f":"'K80 - time schedule'!FT18","v":0},{"$f":"'K80 - time schedule'!FU18","v":0},{"$f":"'K80 - time schedule'!FV18","v":0},{"$f":"'K80 - time schedule'!FW18","v":0},{"$f":"'K80 - time schedule'!FX18","v":0},{"$f":"'K80 - time schedule'!FY18","v":0},{"$f":"'K80 - time schedule'!FZ18","v":0},{"$f":"'K80 - time schedule'!GA18","v":0},{"$f":"'K80 - time schedule'!GB18","v":0},{"$f":"'K80 - time schedule'!GC18","v":0},{"$f":"'K80 - time schedule'!GD18","v":0},{"$f":"'K80 - time schedule'!GE18","v":0},{"$f":"'K80 - time schedule'!GF18","v":0},{"$f":"'K80 - time schedule'!GG18","v":0},{"$f":"'K80 - time schedule'!GH18","v":0},{"$f":"'K80 - time schedule'!GI18","v":0},{"$f":"'K80 - time schedule'!GJ18","v":0},{"$f":"'K80 - time schedule'!GK18","v":0},{"$f":"'K80 - time schedule'!GL18","v":0},{"$f":"'K80 - time schedule'!GM18","v":0},{"$f":"'K80 - time schedule'!GN18","v":0},{"$f":"'K80 - time schedule'!GO18","v":0},{"$f":"'K80 - time schedule'!GP18","v":0},{"$f":"'K80 - time schedule'!GQ18","v":0},{"$f":"'K80 - time schedule'!GR18","v":0},{"$f":"'K80 - time schedule'!GS18","v":0},{"$f":"'K80 - time schedule'!GT18","v":0},{"$f":"'K80 - time schedule'!GU18","v":0},{"$f":"'K80 - time schedule'!GV18","v":0},{"$f":"'K80 - time schedule'!GW18","v":0},{"$f":"'K80 - time schedule'!GX18","v":0},{"$f":"'K80 - time schedule'!GY18","v":0},{"$f":"'K80 - time schedule'!GZ18","v":0},{"$f":"'K80 - time schedule'!HA18","v":0},{"$f":"'K80 - time schedule'!HB18","v":0},{"$f":"'K80 - time schedule'!HC18","v":0},{"$f":"'K80 - time schedule'!HD18","v":0},{"$f":"'K80 - time schedule'!HE18","v":0},{"$f":"'K80 - time schedule'!HF18","v":0},{"$f":"'K80 - time schedule'!HG18","v":0},{"$f":"'K80 - time schedule'!HH18","v":0},{"$f":"'K80 - time schedule'!HI18","v":0},{"$f":"'K80 - time schedule'!HJ18","v":0},{"$f":"'K80 - time schedule'!HK18","v":0},{"$f":"'K80 - time schedule'!HL18","v":0},{"$f":"'K80 - time schedule'!HM18","v":0},{"$f":"'K80 - time schedule'!HN18","v":0},{"$f":"'K80 - time schedule'!HO18","v":0},{"$f":"'K80 - time schedule'!HP18","v":0},{"$f":"'K80 - time schedule'!HQ18","v":0},{"$f":"'K80 - time schedule'!HR18","v":0},{"$f":"'K80 - time schedule'!HS18","v":0},{"$f":"'K80 - time schedule'!HT18","v":0},{"$f":"'K80 - time schedule'!HU18","v":0},{"$f":"'K80 - time schedule'!HV18","v":0},{"$f":"'K80 - time schedule'!HW18","v":0},{"$f":"'K80 - time schedule'!HX18","v":0},{"$f":"'K80 - time schedule'!HY18","v":0},{"$f":"'K80 - time schedule'!HZ18","v":0},{"$f":"'K80 - time schedule'!IA18","v":0},{"$f":"'K80 - time schedule'!IB18","v":0},{"$f":"'K80 - time schedule'!IC18","v":0},{"$f":"'K80 - time schedule'!ID18","v":0},{"$f":"'K80 - time schedule'!IE18","v":0},{"$f":"'K80 - time schedule'!IF18","v":0},{"$f":"'K80 - time schedule'!IG18","v":0},{"$f":"'K80 - time schedule'!IH18","v":0},{"$f":"'K80 - time schedule'!II18","v":0},{"$f":"'K80 - time schedule'!IJ18","v":0},{"$f":"'K80 - time schedule'!IK18","v":0},{"$f":"'K80 - time schedule'!IL18","v":0},{"$f":"'K80 - time schedule'!IM18","v":0},{"$f":"'K80 - time schedule'!IN18","v":0},{"$f":"'K80 - time schedule'!IO18","v":0},{"$f":"'K80 - time schedule'!IP18","v":0},{"$f":"'K80 - time schedule'!IQ18","v":0},{"$f":"'K80 - time schedule'!IR18","v":0},{"$f":"'K80 - time schedule'!IS18","v":0},{"$f":"'K80 - time schedule'!IT18","v":0},{"$f":"'K80 - time schedule'!IU18","v":0},{"$f":"'K80 - time schedule'!IV18","v":0},{"$f":"'K80 - time schedule'!IW18","v":0},{"$f":"'K80 - time schedule'!IX18","v":0},{"$f":"'K80 - time schedule'!IY18","v":0},{"$f":"'K80 - time schedule'!IZ18","v":0},{"$f":"'K80 - time schedule'!JA18","v":0},{"$f":"'K80 - time schedule'!JB18","v":0},{"$f":"'K80 - time schedule'!JC18","v":0},{"$f":"'K80 - time schedule'!JD18","v":0},{"$f":"'K80 - time schedule'!JE18","v":0},{"$f":"'K80 - time schedule'!JF18","v":0},{"$f":"'K80 - time schedule'!JG18","v":0},{"$f":"'K80 - time schedule'!JH18","v":0},{"$f":"'K80 - time schedule'!JI18","v":0},{"$f":"'K80 - time schedule'!JJ18","v":0},{"$f":"'K80 - time schedule'!JK18","v":0},{"$f":"'K80 - time schedule'!JL18","v":0},{"$f":"'K80 - time schedule'!JM18","v":0},{"$f":"'K80 - time schedule'!JN18","v":0},{"$f":"'K80 - time schedule'!JO18","v":0},{"$f":"'K80 - time schedule'!JP18","v":0},{"$f":"'K80 - time schedule'!JQ18","v":0},{"$f":"'K80 - time schedule'!JR18","v":0},{"$f":"'K80 - time schedule'!JS18","v":0},{"$f":"'K80 - time schedule'!JT18","v":0},{"$f":"'K80 - time schedule'!JU18","v":0},{"$f":"'K80 - time schedule'!JV18","v":0},{"$f":"'K80 - time schedule'!JW18","v":0},{"$f":"'K80 - time schedule'!JX18","v":0},{"$f":"'K80 - time schedule'!JY18","v":0},{"$f":"'K80 - time schedule'!JZ18","v":0},{"$f":"'K80 - time schedule'!KA18","v":0},{"$f":"'K80 - time schedule'!KB18","v":0},{"$f":"'K80 - time schedule'!KC18","v":0},{"$f":"'K80 - time schedule'!KD18","v":0},{"$f":"'K80 - time schedule'!KE18","v":0},{"$f":"'K80 - time schedule'!KF18","v":0},{"$f":"'K80 - time schedule'!KG18","v":0},{"$f":"'K80 - time schedule'!KH18","v":0},{"$f":"'K80 - time schedule'!KI18","v":0},{"$f":"'K80 - time schedule'!KJ18","v":0},{"$f":"'K80 - time schedule'!KK18","v":0},{"$f":"'K80 - time schedule'!KL18","v":0},{"$f":"'K80 - time schedule'!KM18","v":0},{"$f":"'K80 - time schedule'!KN18","v":0},{"$f":"'K80 - time schedule'!KO18","v":0},{"$f":"'K80 - time schedule'!KP18","v":0},{"$f":"'K80 - time schedule'!KQ18","v":0},{"$f":"'K80 - time schedule'!KR18","v":0},{"$f":"'K80 - time schedule'!KS18","v":0},{"$f":"'K80 - time schedule'!KT18","v":0}]
["Boiler room K80 - shutdown of boiler K80","K80",{"$f":"'K80 - time schedule'!G19","v":0},{"$f":"'K80 - time schedule'!H19","v":0},{"$f":"'K80 - time schedule'!I19","v":0},{"$f":"'K80 - time schedule'!J19","v":0},{"$f":"'K80 - time schedule'!K19","v":0},{"$f":"'K80 - time schedule'!L19","v":0},{"$f":"'K80 - time schedule'!M19","v":0},{"$f":"'K80 - time schedule'!N19","v":0},{"$f":"'K80 - time schedule'!O19","v":0},{"$f":"'K80 - time schedule'!P19","v":0},{"$f":"'K80 - time schedule'!Q19","v":0},{"$f":"'K80 - time schedule'!R19","v":0},{"$f":"'K80 - time schedule'!S19","v":0},{"$f":"'K80 - time schedule'!T19","v":0},{"$f":"'K80 - time schedule'!U19","v":0},{"$f":"'K80 - time schedule'!V19","v":0},{"$f":"'K80 - time schedule'!W19","v":0},{"$f":"'K80 - time schedule'!X19","v":0},{"$f":"'K80 - time schedule'!Y19","v":0},{"$f":"'K80 - time schedule'!Z19","v":0},{"$f":"'K80 - time schedule'!AA19","v":0},{"$f":"'K80 - time schedule'!AB19","v":0},{"$f":"'K80 - time schedule'!AC19","v":0},{"$f":"'K80 - time schedule'!AD19","v":0},{"$f":"'K80 - time schedule'!AE19","v":0},{"$f":"'K80 - time schedule'!AF19","v":0},{"$f":"'K80 - time schedule'!AG19","v":0},{"$f":"'K80 - time schedule'!AH19","v":0},{"$f":"'K80 - time schedule'!AI19","v":0},{"$f":"'K80 - time schedule'!AJ19","v":0},{"$f":"'K80 - time schedule'!AK19","v":0},{"$f":"'K80 - time schedule'!AL19","v":0},{"$f":"'K80 - time schedule'!AM19","v":0},{"$f":"'K80 - time schedule'!AN19","v":0},{"$f":"'K80 - time schedule'!AO19","v":0},{"$f":"'K80 - time schedule'!AP19","v":0},{"$f":"'K80 - time schedule'!AQ19","v":0},{"$f":"'K80 - time schedule'!AR19","v":0},{"$f":"'K80 - time schedule'!AS19","v":0},{"$f":"'K80 - time schedule'!AT19","v":0},{"$f":"'K80 - time schedule'!AU19","v":0},{"$f":"'K80 - time schedule'!AV19","v":0},{"$f":"'K80 - time schedule'!AW19","v":0},{"$f":"'K80 - time schedule'!AX19","v":0},{"$f":"'K80 - time schedule'!AY19","v":0},{"$f":"'K80 - time schedule'!AZ19","v":0},{"$f":"'K80 - time schedule'!BA19","v":0},{"$f":"'K80 - time schedule'!BB19","v":0},{"$f":"'K80 - time schedule'!BC19","v":0},{"$f":"'K80 - time schedule'!BD19","v":0},{"$f":"'K80 - time schedule'!BE19","v":0},{"$f":"'K80 - time schedule'!BF19","v":0},{"$f":"'K80 - time schedule'!BG19","v":0},{"$f":"'K80 - time schedule'!BH19","v":0},{"$f":"'K80 - time schedule'!BI19","v":0},{"$f":"'K80 - time schedule'!BJ19","v":0},{"$f":"'K80 - time schedule'!BK19","v":0},{"$f":"'K80 - time schedule'!BL19","v":0},{"$f":"'K80 - time schedule'!BM19","v":0},{"$f":"'K80 - time schedule'!BN19","v":0},{"$f":"'K80 - time schedule'!BO19","v":0},{"$f":"'K80 - time schedule'!BP19","v":0},{"$f":"'K80 - time schedule'!BQ19","v":0},{"$f":"'K80 - time schedule'!BR19","v":0},{"$f":"'K80 - time schedule'!BS19","v":0},{"$f":"'K80 - time schedule'!BT19","v":0},{"$f":"'K80 - time schedule'!BU19","v":0},{"$f":"'K80 - time schedule'!BV19","v":0},{"$f":"'K80 - time schedule'!BW19","v":0},{"$f":"'K80 - time schedule'!BX19","v":0},{"$f":"'K80 - time schedule'!BY19","v":0},{"$f":"'K80 - time schedule'!BZ19","v":0},{"$f":"'K80 - time schedule'!CA19","v":0},{"$f":"'K80 - time schedule'!CB19","v":0},{"$f":"'K80 - time schedule'!CC19","v":0},{"$f":"'K80 - time schedule'!CD19","v":0},{"$f":"'K80 - time schedule'!CE19","v":0},{"$f":"'K80 - time schedule'!CF19","v":0},{"$f":"'K80 - time schedule'!CG19","v":0},{"$f":"'K80 - time schedule'!CH19","v":0},{"$f":"'K80 - time schedule'!CI19","v":0},{"$f":"'K80 - time schedule'!CJ19","v":0},{"$f":"'K80 - time schedule'!CK19","v":0},{"$f":"'K80 - time schedule'!CL19","v":0},{"$f":"'K80 - time schedule'!CM19","v":0},{"$f":"'K80 - time schedule'!CN19","v":0},{"$f":"'K80 - time schedule'!CO19","v":0},{"$f":"'K80 - time schedule'!CP19","v":0},{"$f":"'K80 - time schedule'!CQ19","v":0},{"$f":"'K80 - time schedule'!CR19","v":0},{"$f":"'K80 - time schedule'!CS19","v":0},{"$f":"'K80 - time schedule'!CT19","v":0},{"$f":"'K80 - time schedule'!CU19","v":0},{"$f":"'K80 - time schedule'!CV19","v":0},{"$f":"'K80 - time schedule'!CW19","v":0},{"$f":"'K80 - time schedule'!CX19","v":0},{"$f":"'K80 - time schedule'!CY19","v":0},{"$f":"'K80 - time schedule'!CZ19","v":0},{"$f":"'K80 - time schedule'!DA19","v":0},{"$f":"'K80 - time schedule'!DB19","v":0},{"$f":"'K80 - time schedule'!DC19","v":0},{"$f":"'K80 - time schedule'!DD19","v":0},{"$f":"'K80 - time schedule'!DE19","v":0},{"$f":"'K80 - time schedule'!DF19","v":0},{"$f":"'K80 - time schedule'!DG19","v":0},{"$f":"'K80 - time schedule'!DH19","v":0},{"$f":"'K80 - time schedule'!DI19","v":0},{"$f":"'K80 - time schedule'!DJ19","v":0},{"$f":"'K80 - time schedule'!DK19","v":0},{"$f":"'K80 - time schedule'!DL19","v":0},{"$f":"'K80 - time schedule'!DM19","v":0},{"$f":"'K80 - time schedule'!DN19","v":0},{"$f":"'K80 - time schedule'!DO19","v":0},{"$f":"'K80 - time schedule'!DP19","v":0},{"$f":"'K80 - time schedule'!DQ19","v":0},{"$f":"'K80 - time schedule'!DR19","v":0},{"$f":"'K80 - time schedule'!DS19","v":0},{"$f":"'K80 - time schedule'!DT19","v":0},{"$f":"'K80 - time schedule'!DU19","v":0},{"$f":"'K80 - time schedule'!DV19","v":0},{"$f":"'K80 - time schedule'!DW19","v":0},{"$f":"'K80 - time schedule'!DX19","v":0},{"$f":"'K80 - time schedule'!DY19","v":0},{"$f":"'K80 - time schedule'!DZ19","v":0},{"$f":"'K80 - time schedule'!EA19","v":0},{"$f":"'K80 - time schedule'!EB19","v":0},{"$f":"'K80 - time schedule'!EC19","v":0},{"$f":"'K80 - time schedule'!ED19","v":0},{"$f":"'K80 - time schedule'!EE19","v":0},{"$f":"'K80 - time schedule'!EF19","v":0},{"$f":"'K80 - time schedule'!EG19","v":0},{"$f":"'K80 - time schedule'!EH19","v":0},{"$f":"'K80 - time schedule'!EI19","v":0},{"$f":"'K80 - time schedule'!EJ19","v":0},{"$f":"'K80 - time schedule'!EK19","v":0},{"$f":"'K80 - time schedule'!EL19","v":0},{"$f":"'K80 - time schedule'!EM19","v":0},{"$f":"'K80 - time schedule'!EN19","v":0},{"$f":"'K80 - time schedule'!EO19","v":0},{"$f":"'K80 - time schedule'!EP19","v":0},{"$f":"'K80 - time schedule'!EQ19","v":0},{"$f":"'K80 - time schedule'!ER19","v":0},{"$f":"'K80 - time schedule'!ES19","v":0},{"$f":"'K80 - time schedule'!ET19","v":0},{"$f":"'K80 - time schedule'!EU19","v":0},{"$f":"'K80 - time schedule'!EV19","v":0},{"$f":"'K80 - time schedule'!EW19","v":0},{"$f":"'K80 - time schedule'!EX19","v":0},{"$f":"'K80 - time schedule'!EY19","v":0},{"$f":"'K80 - time schedule'!EZ19","v":0},{"$f":"'K80 - time schedule'!FA19","v":0},{"$f":"'K80 - time schedule'!FB19","v":0},{"$f":"'K80 - time schedule'!FC19","v":0},{"$f":"'K80 - time schedule'!FD19","v":0},{"$f":"'K80 - time schedule'!FE19","v":0},{"$f":"'K80 - time schedule'!FF19","v":0},{"$f":"'K80 - time schedule'!FG19","v":0},{"$f":"'K80 - time schedule'!FH19","v":0},{"$f":"'K80 - time schedule'!FI19","v":0},{"$f":"'K80 - time schedule'!FJ19","v":0},{"$f":"'K80 - time schedule'!FK19","v":0},{"$f":"'K80 - time schedule'!FL19","v":0},{"$f":"'K80 - time schedule'!FM19","v":0},{"$f":"'K80 - time schedule'!FN19","v":0},{"$f":"'K80 - time schedule'!FO19","v":0},{"$f":"'K80 - time schedule'!FP19","v":0},{"$f":"'K80 - time schedule'!FQ19","v":0},{"$f":"'K80 - time schedule'!FR19","v":0},{"$f":"'K80 - time schedule'!FS19","v":0},{"$f":"'K80 - time schedule'!FT19","v":0},{"$f":"'K80 - time schedule'!FU19","v":0},{"$f":"'K80 - time schedule'!FV19","v":0},{"$f":"'K80 - time schedule'!FW19","v":0},{"$f":"'K80 - time schedule'!FX19","v":0},{"$f":"'K80 - time schedule'!FY19","v":0},{"$f":"'K80 - time schedule'!FZ19","v":0},{"$f":"'K80 - time schedule'!GA19","v":0},{"$f":"'K80 - time schedule'!GB19","v":0},{"$f":"'K80 - time schedule'!GC19","v":0},{"$f":"'K80 - time schedule'!GD19","v":0},{"$f":"'K80 - time schedule'!GE19","v":0},{"$f":"'K80 - time schedule'!GF19","v":0},{"$f":"'K80 - time schedule'!GG19","v":0},{"$f":"'K80 - time schedule'!GH19","v":0},{"$f":"'K80 - time schedule'!GI19","v":0},{"$f":"'K80 - time schedule'!GJ19","v":0},{"$f":"'K80 - time schedule'!GK19","v":0},{"$f":"'K80 - time schedule'!GL19","v":0},{"$f":"'K80 - time schedule'!GM19","v":0},{"$f":"'K80 - time schedule'!GN19","v":0},{"$f":"'K80 - time schedule'!GO19","v":0},{"$f":"'K80 - time schedule'!GP19","v":0},{"$f":"'K80 - time schedule'!GQ19","v":0},{"$f":"'K80 - time schedule'!GR19","v":0},{"$f":"'K80 - time schedule'!GS19","v":0},{"$f":"'K80 - time schedule'!GT19","v":0},{"$f":"'K80 - time schedule'!GU19","v":0},{"$f":"'K80 - time schedule'!GV19","v":0},{"$f":"'K80 - time schedule'!GW19","v":0},{"$f":"'K80 - time schedule'!GX19","v":0},{"$f":"'K80 - time schedule'!GY19","v":0},{"$f":"'K80 - time schedule'!GZ19","v":0},{"$f":"'K80 - time schedule'!HA19","v":0},{"$f":"'K80 - time schedule'!HB19","v":0},{"$f":"'K80 - time schedule'!HC19","v":0},{"$f":"'K80 - time schedule'!HD19","v":0},{"$f":"'K80 - time schedule'!HE19","v":0},{"$f":"'K80 - time schedule'!HF19","v":0},{"$f":"'K80 - time schedule'!HG19","v":0},{"$f":"'K80 - time schedule'!HH19","v":0},{"$f":"'K80 - time schedule'!HI19","v":0},{"$f":"'K80 - time schedule'!HJ19","v":0},{"$f":"'K80 - time schedule'!HK19","v":0},{"$f":"'K80 - time schedule'!HL19","v":0},{"$f":"'K80 - time schedule'!HM19","v":0},{"$f":"'K80 - time schedule'!HN19","v":0},{"$f":"'K80 - time schedule'!HO19","v":0},{"$f":"'K80 - time schedule'!HP19","v":0},{"$f":"'K80 - time schedule'!HQ19","v":0},{"$f":"'K80 - time schedule'!HR19","v":0},{"$f":"'K80 - time schedule'!HS19","v":0},{"$f":"'K80 - time schedule'!HT19","v":0},{"$f":"'K80 - time schedule'!HU19","v":0},{"$f":"'K80 - time schedule'!HV19","v":0},{"$f":"'K80 - time schedule'!HW19","v":0},{"$f":"'K80 - time schedule'!HX19","v":0},{"$f":"'K80 - time schedule'!HY19","v":0},{"$f":"'K80 - time schedule'!HZ19","v":0},{"$f":"'K80 - time schedule'!IA19","v":0},{"$f":"'K80 - time schedule'!IB19","v":0},{"$f":"'K80 - time schedule'!IC19","v":0},{"$f":"'K80 - time schedule'!ID19","v":0},{"$f":"'K80 - time schedule'!IE19","v":0},{"$f":"'K80 - time schedule'!IF19","v":0},{"$f":"'K80 - time schedule'!IG19","v":0},{"$f":"'K80 - time schedule'!IH19","v":0},{"$f":"'K80 - time schedule'!II19","v":0},{"$f":"'K80 - time schedule'!IJ19","v":0},{"$f":"'K80 - time schedule'!IK19","v":0},{"$f":"'K80 - time schedule'!IL19","v":0},{"$f":"'K80 - time schedule'!IM19","v":0},{"$f":"'K80 - time schedule'!IN19","v":0},{"$f":"'K80 - time schedule'!IO19","v":0},{"$f":"'K80 - time schedule'!IP19","v":0},{"$f":"'K80 - time schedule'!IQ19","v":0},{"$f":"'K80 - time schedule'!IR19","v":0},{"$f":"'K80 - time schedule'!IS19","v":0},{"$f":"'K80 - time schedule'!IT19","v":0},{"$f":"'K80 - time schedule'!IU19","v":0},{"$f":"'K80 - time schedule'!IV19","v":0},{"$f":"'K80 - time schedule'!IW19","v":0},{"$f":"'K80 - time schedule'!IX19","v":0},{"$f":"'K80 - time schedule'!IY19","v":0},{"$f":"'K80 - time schedule'!IZ19","v":0},{"$f":"'K80 - time schedule'!JA19","v":0},{"$f":"'K80 - time schedule'!JB19","v":0},{"$f":"'K80 - time schedule'!JC19","v":0},{"$f":"'K80 - time schedule'!JD19","v":0},{"$f":"'K80 - time schedule'!JE19","v":0},{"$f":"'K80 - time schedule'!JF19","v":0},{"$f":"'K80 - time schedule'!JG19","v":0},{"$f":"'K80 - time schedule'!JH19","v":0},{"$f":"'K80 - time schedule'!JI19","v":0},{"$f":"'K80 - time schedule'!JJ19","v":0},{"$f":"'K80 - time schedule'!JK19","v":0},{"$f":"'K80 - time schedule'!JL19","v":0},{"$f":"'K80 - time schedule'!JM19","v":0},{"$f":"'K80 - time schedule'!JN19","v":0},{"$f":"'K80 - time schedule'!JO19","v":0},{"$f":"'K80 - time schedule'!JP19","v":0},{"$f":"'K80 - time schedule'!JQ19","v":0},{"$f":"'K80 - time schedule'!JR19","v":0},{"$f":"'K80 - time schedule'!JS19","v":0},{"$f":"'K80 - time schedule'!JT19","v":0},{"$f":"'K80 - time schedule'!JU19","v":0},{"$f":"'K80 - time schedule'!JV19","v":0},{"$f":"'K80 - time schedule'!JW19","v":0},{"$f":"'K80 - time schedule'!JX19","v":0},{"$f":"'K80 - time schedule'!JY19","v":0},{"$f":"'K80 - time schedule'!JZ19","v":0},{"$f":"'K80 - time schedule'!KA19","v":0},{"$f":"'K80 - time schedule'!KB19","v":0},{"$f":"'K80 - time schedule'!KC19","v":0},{"$f":"'K80 - time schedule'!KD19","v":0},{"$f":"'K80 - time schedule'!KE19","v":0},{"$f":"'K80 - time schedule'!KF19","v":0},{"$f":"'K80 - time schedule'!KG19","v":0},{"$f":"'K80 - time schedule'!KH19","v":0},{"$f":"'K80 - time schedule'!KI19","v":0},{"$f":"'K80 - time schedule'!KJ19","v":0},{"$f":"'K80 - time schedule'!KK19","v":0},{"$f":"'K80 - time schedule'!KL19","v":0},{"$f":"'K80 - time schedule'!KM19","v":0},{"$f":"'K80 - time schedule'!KN19","v":0},{"$f":"'K80 - time schedule'!KO19","v":0},{"$f":"'K80 - time schedule'!KP19","v":0},{"$f":"'K80 - time schedule'!KQ19","v":0},{"$f":"'K80 - time schedule'!KR19","v":0},{"$f":"'K80 - time schedule'!KS19","v":0},{"$f":"'K80 - time schedule'!KT19","v":0}]
["Boiler room K80 - dismantling","K80",{"$f":"'K80 - time schedule'!G20","v":0},{"$f":"'K80 - time schedule'!H20","v":0},{"$f":"'K80 - time schedule'!I20","v":0},{"$f":"'K80 - time schedule'!J20","v":0},{"$f":"'K80 - time schedule'!K20","v":0},{"$f":"'K80 - time schedule'!L20","v":0},{"$f":"'K80 - time schedule'!M20","v":0},{"$f":"'K80 - time schedule'!N20","v":0},{"$f":"'K80 - time schedule'!O20","v":0},{"$f":"'K80 - time schedule'!P20","v":0},{"$f":"'K80 - time schedule'!Q20","v":0},{"$f":"'K80 - time schedule'!R20","v":0},{"$f":"'K80 - time schedule'!S20","v":0},{"$f":"'K80 - time schedule'!T20","v":0},{"$f":"'K80 - time schedule'!U20","v":0},{"$f":"'K80 - time schedule'!V20","v":0},{"$f":"'K80 - time schedule'!W20","v":0},{"$f":"'K80 - time schedule'!X20","v":0},{"$f":"'K80 - time schedule'!Y20","v":0},{"$f":"'K80 - time schedule'!Z20","v":0},{"$f":"'K80 - time schedule'!AA20","v":0},{"$f":"'K80 - time schedule'!AB20","v":0},{"$f":"'K80 - time schedule'!AC20","v":0},{"$f":"'K80 - time schedule'!AD20","v":0},{"$f":"'K80 - time schedule'!AE20","v":0},{"$f":"'K80 - time schedule'!AF20","v":0},{"$f":"'K80 - time schedule'!AG20","v":0},{"$f":"'K80 - time schedule'!AH20","v":0},{"$f":"'K80 - time schedule'!AI20","v":0},{"$f":"'K80 - time schedule'!AJ20","v":0},{"$f":"'K80 - time schedule'!AK20","v":0},{"$f":"'K80 - time schedule'!AL20","v":0},{"$f":"'K80 - time schedule'!AM20","v":0},{"$f":"'K80 - time schedule'!AN20","v":0},{"$f":"'K80 - time schedule'!AO20","v":0},{"$f":"'K80 - time schedule'!AP20","v":0},{"$f":"'K80 - time schedule'!AQ20","v":0},{"$f":"'K80 - time schedule'!AR20","v":0},{"$f":"'K80 - time schedule'!AS20","v":0},{"$f":"'K80 - time schedule'!AT20","v":0},{"$f":"'K80 - time schedule'!AU20","v":0},{"$f":"'K80 - time schedule'!AV20","v":0},{"$f":"'K80 - time schedule'!AW20","v":0},{"$f":"'K80 - time schedule'!AX20","v":0},{"$f":"'K80 - time schedule'!AY20","v":0},{"$f":"'K80 - time schedule'!AZ20","v":0},{"$f":"'K80 - time schedule'!BA20","v":0},{"$f":"'K80 - time schedule'!BB20","v":0},{"$f":"'K80 - time schedule'!BC20","v":0},{"$f":"'K80 - time schedule'!BD20","v":0},{"$f":"'K80 - time schedule'!BE20","v":0},{"$f":"'K80 - time schedule'!BF20","v":0},{"$f":"'K80 - time schedule'!BG20","v":0},{"$f":"'K80 - time schedule'!BH20","v":0},{"$f":"'K80 - time schedule'!BI20","v":0},{"$f":"'K80 - time schedule'!BJ20","v":0},{"$f":"'K80 - time schedule'!BK20","v":0},{"$f":"'K80 - time schedule'!BL20","v":0},{"$f":"'K80 - time schedule'!BM20","v":0},{"$f":"'K80 - time schedule'!BN20","v":0},{"$f":"'K80 - time schedule'!BO20","v":0},{"$f":"'K80 - time schedule'!BP20","v":0},{"$f":"'K80 - time schedule'!BQ20","v":0},{"$f":"'K80 - time schedule'!BR20","v":0},{"$f":"'K80 - time schedule'!BS20","v":0},{"$f":"'K80 - time schedule'!BT20","v":0},{"$f":"'K80 - time schedule'!BU20","v":0},{"$f":"'K80 - time schedule'!BV20","v":0},{"$f":"'K80 - time schedule'!BW20","v":0},{"$f":"'K80 - time schedule'!BX20","v":0},{"$f":"'K80 - time schedule'!BY20","v":0},{"$f":"'K80 - time schedule'!BZ20","v":0},{"$f":"'K80 - time schedule'!CA20","v":0},{"$f":"'K80 - time schedule'!CB20","v":0},{"$f":"'K80 - time schedule'!CC20","v":0},{"$f":"'K80 - time schedule'!CD20","v":0},{"$f":"'K80 - time schedule'!CE20","v":0},{"$f":"'K80 - time schedule'!CF20","v":0},{"$f":"'K80 - time schedule'!CG20","v":0},{"$f":"'K80 - time schedule'!CH20","v":0},{"$f":"'K80 - time schedule'!CI20","v":0},{"$f":"'K80 - time schedule'!CJ20","v":0},{"$f":"'K80 - time schedule'!CK20","v":0},{"$f":"'K80 - time schedule'!CL20","v":0},{"$f":"'K80 - time schedule'!CM20","v":0},{"$f":"'K80 - time schedule'!CN20","v":0},{"$f":"'K80 - time schedule'!CO20","v":0},{"$f":"'K80 - time schedule'!CP20","v":0},{"$f":"'K80 - time schedule'!CQ20","v":0},{"$f":"'K80 - time schedule'!CR20","v":0},{"$f":"'K80 - time schedule'!CS20","v":0},{"$f":"'K80 - time schedule'!CT20","v":0},{"$f":"'K80 - time schedule'!CU20","v":0},{"$f":"'K80 - time schedule'!CV20","v":0},{"$f":"'K80 - time schedule'!CW20","v":0},{"$f":"'K80 - time schedule'!CX20","v":0},{"$f":"'K80 - time schedule'!CY20","v":0},{"$f":"'K80 - time schedule'!CZ20","v":0},{"$f":"'K80 - time schedule'!DA20","v":0},{"$f":"'K80 - time schedule'!DB20","v":0},{"$f":"'K80 - time schedule'!DC20","v":0},{"$f":"'K80 - time schedule'!DD20","v":0},{"$f":"'K80 - time schedule'!DE20","v":0},{"$f":"'K80 - time schedule'!DF20","v":0},{"$f":"'K80 - time schedule'!DG20","v":0},{"$f":"'K80 - time schedule'!DH20","v":0},{"$f":"'K80 - time schedule'!DI20","v":0},{"$f":"'K80 - time schedule'!DJ20","v":0},{"$f":"'K80 - time schedule'!DK20","v":0},{"$f":"'K80 - time schedule'!DL20","v":0},{"$f":"'K80 - time schedule'!DM20","v":0},{"$f":"'K80 - time schedule'!DN20","v":0},{"$f":"'K80 - time schedule'!DO20","v":0},{"$f":"'K80 - time schedule'!DP20","v":0},{"$f":"'K80 - time schedule'!DQ20","v":0},{"$f":"'K80 - time schedule'!DR20","v":0},{"$f":"'K80 - time schedule'!DS20","v":0},{"$f":"'K80 - time schedule'!DT20","v":0},{"$f":"'K80 - time schedule'!DU20","v":0},{"$f":"'K80 - time schedule'!DV20","v":0},{"$f":"'K80 - time schedule'!DW20","v":0},{"$f":"'K80 - time schedule'!DX20","v":0},{"$f":"'K80 - time schedule'!DY20","v":0},{"$f":"'K80 - time schedule'!DZ20","v":0},{"$f":"'K80 - time schedule'!EA20","v":0},{"$f":"'K80 - time schedule'!EB20","v":0},{"$f":"'K80 - time schedule'!EC20","v":0},{"$f":"'K80 - time schedule'!ED20","v":0},{"$f":"'K80 - time schedule'!EE20","v":0},{"$f":"'K80 - time schedule'!EF20","v":0},{"$f":"'K80 - time schedule'!EG20","v":0},{"$f":"'K80 - time schedule'!EH20","v":0},{"$f":"'K80 - time schedule'!EI20","v":0},{"$f":"'K80 - time schedule'!EJ20","v":0},{"$f":"'K80 - time schedule'!EK20","v":0},{"$f":"'K80 - time schedule'!EL20","v":0},{"$f":"'K80 - time schedule'!EM20","v":0},{"$f":"'K80 - time schedule'!EN20","v":0},{"$f":"'K80 - time schedule'!EO20","v":0},{"$f":"'K80 - time schedule'!EP20","v":0},{"$f":"'K80 - time schedule'!EQ20","v":0},{"$f":"'K80 - time schedule'!ER20","v":0},{"$f":"'K80 - time schedule'!ES20","v":0},{"$f":"'K80 - time schedule'!ET20","v":0},{"$f":"'K80 - time schedule'!EU20","v":0},{"$f":"'K80 - time schedule'!EV20","v":0},{"$f":"'K80 - time schedule'!EW20","v":0},{"$f":"'K80 - time schedule'!EX20","v":0},{"$f":"'K80 - time schedule'!EY20","v":0},{"$f":"'K80 - time schedule'!EZ20","v":0},{"$f":"'K80 - time schedule'!FA20","v":0},{"$f":"'K80 - time schedule'!FB20","v":0},{"$f":"'K80 - time schedule'!FC20","v":0},{"$f":"'K80 - time schedule'!FD20","v":0},{"$f":"'K80 - time schedule'!FE20","v":0},{"$f":"'K80 - time schedule'!FF20","v":0},{"$f":"'K80 - time schedule'!FG20","v":0},{"$f":"'K80 - time schedule'!FH20","v":0},{"$f":"'K80 - time schedule'!FI20","v":0},{"$f":"'K80 - time schedule'!FJ20","v":0},{"$f":"'K80 - time schedule'!FK20","v":0},{"$f":"'K80 - time schedule'!FL20","v":0},{"$f":"'K80 - time schedule'!FM20","v":0},{"$f":"'K80 - time schedule'!FN20","v":0},{"$f":"'K80 - time schedule'!FO20","v":0},{"$f":"'K80 - time schedule'!FP20","v":0},{"$f":"'K80 - time schedule'!FQ20","v":0},{"$f":"'K80 - time schedule'!FR20","v":0},{"$f":"'K80 - time schedule'!FS20","v":0},{"$f":"'K80 - time schedule'!FT20","v":0},{"$f":"'K80 - time schedule'!FU20","v":0},{"$f":"'K80 - time schedule'!FV20","v":0},{"$f":"'K80 - time schedule'!FW20","v":0},{"$f":"'K80 - time schedule'!FX20","v":0},{"$f":"'K80 - time schedule'!FY20","v":0},{"$f":"'K80 - time schedule'!FZ20","v":0},{"$f":"'K80 - time schedule'!GA20","v":0},{"$f":"'K80 - time schedule'!GB20","v":0},{"$f":"'K80 - time schedule'!GC20","v":0},{"$f":"'K80 - time schedule'!GD20","v":0},{"$f":"'K80 - time schedule'!GE20","v":0},{"$f":"'K80 - time schedule'!GF20","v":0},{"$f":"'K80 - time schedule'!GG20","v":0},{"$f":"'K80 - time schedule'!GH20","v":0},{"$f":"'K80 - time schedule'!GI20","v":0},{"$f":"'K80 - time schedule'!GJ20","v":0},{"$f":"'K80 - time schedule'!GK20","v":0},{"$f":"'K80 - time schedule'!GL20","v":0},{"$f":"'K80 - time schedule'!GM20","v":0},{"$f":"'K80 - time schedule'!GN20","v":0},{"$f":"'K80 - time schedule'!GO20","v":0},{"$f":"'K80 - time schedule'!GP20","v":0},{"$f":"'K80 - time schedule'!GQ20","v":0},{"$f":"'K80 - time schedule'!GR20","v":0},{"$f":"'K80 - time schedule'!GS20","v":0},{"$f":"'K80 - time schedule'!GT20","v":0},{"$f":"'K80 - time schedule'!GU20","v":0},{"$f":"'K80 - time schedule'!GV20","v":0},{"$f":"'K80 - time schedule'!GW20","v":0},{"$f":"'K80 - time schedule'!GX20","v":0},{"$f":"'K80 - time schedule'!GY20","v":0},{"$f":"'K80 - time schedule'!GZ20","v":0},{"$f":"'K80 - time schedule'!HA20","v":0},{"$f":"'K80 - time schedule'!HB20","v":0},{"$f":"'K80 - time schedule'!HC20","v":0},{"$f":"'K80 - time schedule'!HD20","v":0},{"$f":"'K80 - time schedule'!HE20","v":0},{"$f":"'K80 - time schedule'!HF20","v":0},{"$f":"'K80 - time schedule'!HG20","v":0},{"$f":"'K80 - time schedule'!HH20","v":0},{"$f":"'K80 - time schedule'!HI20","v":0},{"$f":"'K80 - time schedule'!HJ20","v":0},{"$f":"'K80 - time schedule'!HK20","v":0},{"$f":"'K80 - time schedule'!HL20","v":0},{"$f":"'K80 - time schedule'!HM20","v":0},{"$f":"'K80 - time schedule'!HN20","v":0},{"$f":"'K80 - time schedule'!HO20","v":0},{"$f":"'K80 - time schedule'!HP20","v":0},{"$f":"'K80 - time schedule'!HQ20","v":0},{"$f":"'K80 - time schedule'!HR20","v":0},{"$f":"'K80 - time schedule'!HS20","v":0},{"$f":"'K80 - time schedule'!HT20","v":0},{"$f":"'K80 - time schedule'!HU20","v":0},{"$f":"'K80 - time schedule'!HV20","v":0},{"$f":"'K80 - time schedule'!HW20","v":0},{"$f":"'K80 - time schedule'!HX20","v":0},{"$f":"'K80 - time schedule'!HY20","v":0},{"$f":"'K80 - time schedule'!HZ20","v":0},{"$f":"'K80 - time schedule'!IA20","v":0},{"$f":"'K80 - time schedule'!IB20","v":0},{"$f":"'K80 - time schedule'!IC20","v":0},{"$f":"'K80 - time schedule'!ID20","v":0},{"$f":"'K80 - time schedule'!IE20","v":0},{"$f":"'K80 - time schedule'!IF20","v":0},{"$f":"'K80 - time schedule'!IG20","v":0},{"$f":"'K80 - time schedule'!IH20","v":0},{"$f":"'K80 - time schedule'!II20","v":0},{"$f":"'K80 - time schedule'!IJ20","v":0},{"$f":"'K80 - time schedule'!IK20","v":0},{"$f":"'K80 - time schedule'!IL20","v":0},{"$f":"'K80 - time schedule'!IM20","v":0},{"$f":"'K80 - time schedule'!IN20","v":0},{"$f":"'K80 - time schedule'!IO20","v":0},{"$f":"'K80 - time schedule'!IP20","v":0},{"$f":"'K80 - time schedule'!IQ20","v":0},{"$f":"'K80 - time schedule'!IR20","v":0},{"$f":"'K80 - time schedule'!IS20","v":0},{"$f":"'K80 - time schedule'!IT20","v":0},{"$f":"'K80 - time schedule'!IU20","v":0},{"$f":"'K80 - time schedule'!IV20","v":0},{"$f":"'K80 - time schedule'!IW20","v":0},{"$f":"'K80 - time schedule'!IX20","v":0},{"$f":"'K80 - time schedule'!IY20","v":0},{"$f":"'K80 - time schedule'!IZ20","v":0},{"$f":"'K80 - time schedule'!JA20","v":0},{"$f":"'K80 - time schedule'!JB20","v":0},{"$f":"'K80 - time schedule'!JC20","v":0},{"$f":"'K80 - time schedule'!JD20","v":0},{"$f":"'K80 - time schedule'!JE20","v":0},{"$f":"'K80 - time schedule'!JF20","v":0},{"$f":"'K80 - time schedule'!JG20","v":0},{"$f":"'K80 - time schedule'!JH20","v":0},{"$f":"'K80 - time schedule'!JI20","v":0},{"$f":"'K80 - time schedule'!JJ20","v":0},{"$f":"'K80 - time schedule'!JK20","v":0},{"$f":"'K80 - time schedule'!JL20","v":0},{"$f":"'K80 - time schedule'!JM20","v":0},{"$f":"'K80 - time schedule'!JN20","v":0},{"$f":"'K80 - time schedule'!JO20","v":0},{"$f":"'K80 - time schedule'!JP20","v":0},{"$f":"'K80 - time schedule'!JQ20","v":0},{"$f":"'K80 - time schedule'!JR20","v":0},{"$f":"'K80 - time schedule'!JS20","v":0},{"$f":"'K80 - time schedule'!JT20","v":0},{"$f":"'K80 - time schedule'!JU20","v":0},{"$f":"'K80 - time schedule'!JV20","v":0},{"$f":"'K80 - time schedule'!JW20","v":0},{"$f":"'K80 - time schedule'!JX20","v":0},{"$f":"'K80 - time schedule'!JY20","v":0},{"$f":"'K80 - time schedule'!JZ20","v":0},{"$f":"'K80 - time schedule'!KA20","v":0},{"$f":"'K80 - time schedule'!KB20","v":0},{"$f":"'K80 - time schedule'!KC20","v":0},{"$f":"'K80 - time schedule'!KD20","v":0},{"$f":"'K80 - time schedule'!KE20","v":0},{"$f":"'K80 - time schedule'!KF20","v":0},{"$f":"'K80 - time schedule'!KG20","v":0},{"$f":"'K80 - time schedule'!KH20","v":0},{"$f":"'K80 - time schedule'!KI20","v":0},{"$f":"'K80 - time schedule'!KJ20","v":0},{"$f":"'K80 - time schedule'!KK20","v":0},{"$f":"'K80 - time schedule'!KL20","v":0},{"$f":"'K80 - time schedule'!KM20","v":0},{"$f":"'K80 - time schedule'!KN20","v":0},{"$f":"'K80 - time schedule'!KO20","v":0},{"$f":"'K80 - time schedule'!KP20","v":0},{"$f":"'K80 - time schedule'!KQ20","v":0},{"$f":"'K80 - time schedule'!KR20","v":0},{"$f":"'K80 - time schedule'!KS20","v":0},{"$f":"'K80 - time schedule'!KT20","v":0}]
["Boiler room K80 - supply of combustion air","K80",{"$f":"'K80 - time schedule'!G22","v":0},{"$f":"'K80 - time schedule'!H22","v":0},{"$f":"'K80 - time schedule'!I22","v":0},{"$f":"'K80 - time schedule'!J22","v":0},{"$f":"'K80 - time schedule'!K22","v":0},{"$f":"'K80 - time schedule'!L22","v":0},{"$f":"'K80 - time schedule'!M22","v":0},{"$f":"'K80 - time schedule'!N22","v":0},{"$f":"'K80 - time schedule'!O22","v":0},{"$f":"'K80 - time schedule'!P22","v":0},{"$f":"'K80 - time schedule'!Q22","v":0},{"$f":"'K80 - time schedule'!R22","v":0},{"$f":"'K80 - time schedule'!S22","v":0},{"$f":"'K80 - time schedule'!T22","v":0},{"$f":"'K80 - time schedule'!U22","v":0},{"$f":"'K80 - time schedule'!V22","v":0},{"$f":"'K80 - time schedule'!W22","v":0},{"$f":"'K80 - time schedule'!X22","v":0},{"$f":"'K80 - time schedule'!Y22","v":0},{"$f":"'K80 - time schedule'!Z22","v":0},{"$f":"'K80 - time schedule'!AA22","v":0},{"$f":"'K80 - time schedule'!AB22","v":0},{"$f":"'K80 - time schedule'!AC22","v":0},{"$f":"'K80 - time schedule'!AD22","v":0},{"$f":"'K80 - time schedule'!AE22","v":0},{"$f":"'K80 - time schedule'!AF22","v":0},{"$f":"'K80 - time schedule'!AG22","v":0},{"$f":"'K80 - time schedule'!AH22","v":0},{"$f":"'K80 - time schedule'!AI22","v":0},{"$f":"'K80 - time schedule'!AJ22","v":0},{"$f":"'K80 - time schedule'!AK22","v":0},{"$f":"'K80 - time schedule'!AL22","v":0},{"$f":"'K80 - time schedule'!AM22","v":0},{"$f":"'K80 - time schedule'!AN22","v":0},{"$f":"'K80 - time schedule'!AO22","v":0},{"$f":"'K80 - time schedule'!AP22","v":0},{"$f":"'K80 - time schedule'!AQ22","v":0},{"$f":"'K80 - time schedule'!AR22","v":0},{"$f":"'K80 - time schedule'!AS22","v":0},{"$f":"'K80 - time schedule'!AT22","v":0},{"$f":"'K80 - time schedule'!AU22","v":0},{"$f":"'K80 - time schedule'!AV22","v":0},{"$f":"'K80 - time schedule'!AW22","v":0},{"$f":"'K80 - time schedule'!AX22","v":0},{"$f":"'K80 - time schedule'!AY22","v":0},{"$f":"'K80 - time schedule'!AZ22","v":0},{"$f":"'K80 - time schedule'!BA22","v":0},{"$f":"'K80 - time schedule'!BB22","v":0},{"$f":"'K80 - time schedule'!BC22","v":0},{"$f":"'K80 - time schedule'!BD22","v":0},{"$f":"'K80 - time schedule'!BE22","v":0},{"$f":"'K80 - time schedule'!BF22","v":0},{"$f":"'K80 - time schedule'!BG22","v":0},{"$f":"'K80 - time schedule'!BH22","v":0},{"$f":"'K80 - time schedule'!BI22","v":0},{"$f":"'K80 - time schedule'!BJ22","v":0},{"$f":"'K80 - time schedule'!BK22","v":0},{"$f":"'K80 - time schedule'!BL22","v":0},{"$f":"'K80 - time schedule'!BM22","v":0},{"$f":"'K80 - time schedule'!BN22","v":0},{"$f":"'K80 - time schedule'!BO22","v":0},{"$f":"'K80 - time schedule'!BP22","v":0},{"$f":"'K80 - time schedule'!BQ22","v":0},{"$f":"'K80 - time schedule'!BR22","v":0},{"$f":"'K80 - time schedule'!BS22","v":0},{"$f":"'K80 - time schedule'!BT22","v":0},{"$f":"'K80 - time schedule'!BU22","v":0},{"$f":"'K80 - time schedule'!BV22","v":0},{"$f":"'K80 - time schedule'!BW22","v":0},{"$f":"'K80 - time schedule'!BX22","v":0},{"$f":"'K80 - time schedule'!BY22","v":0},{"$f":"'K80 - time schedule'!BZ22","v":0},{"$f":"'K80 - time schedule'!CA22","v":0},{"$f":"'K80 - time schedule'!CB22","v":0},{"$f":"'K80 - time schedule'!CC22","v":0},{"$f":"'K80 - time schedule'!CD22","v":0},{"$f":"'K80 - time schedule'!CE22","v":0},{"$f":"'K80 - time schedule'!CF22","v":0},{"$f":"'K80 - time schedule'!CG22","v":0},{"$f":"'K80 - time schedule'!CH22","v":0},{"$f":"'K80 - time schedule'!CI22","v":0},{"$f":"'K80 - time schedule'!CJ22","v":0},{"$f":"'K80 - time schedule'!CK22","v":0},{"$f":"'K80 - time schedule'!CL22","v":0},{"$f":"'K80 - time schedule'!CM22","v":0},{"$f":"'K80 - time schedule'!CN22","v":0},{"$f":"'K80 - time schedule'!CO22","v":0},{"$f":"'K80 - time schedule'!CP22","v":0},{"$f":"'K80 - time schedule'!CQ22","v":0},{"$f":"'K80 - time schedule'!CR22","v":0},{"$f":"'K80 - time schedule'!CS22","v":0},{"$f":"'K80 - time schedule'!CT22","v":0},{"$f":"'K80 - time schedule'!CU22","v":0},{"$f":"'K80 - time schedule'!CV22","v":0},{"$f":"'K80 - time schedule'!CW22","v":0},{"$f":"'K80 - time schedule'!CX22","v":0},{"$f":"'K80 - time schedule'!CY22","v":0},{"$f":"'K80 - time schedule'!CZ22","v":0},{"$f":"'K80 - time schedule'!DA22","v":0},{"$f":"'K80 - time schedule'!DB22","v":0},{"$f":"'K80 - time schedule'!DC22","v":0},{"$f":"'K80 - time schedule'!DD22","v":0},{"$f":"'K80 - time schedule'!DE22","v":0},{"$f":"'K80 - time schedule'!DF22","v":0},{"$f":"'K80 - time schedule'!DG22","v":0},{"$f":"'K80 - time schedule'!DH22","v":0},{"$f":"'K80 - time schedule'!DI22","v":0},{"$f":"'K80 - time schedule'!DJ22","v":0},{"$f":"'K80 - time schedule'!DK22","v":0},{"$f":"'K80 - time schedule'!DL22","v":0},{"$f":"'K80 - time schedule'!DM22","v":0},{"$f":"'K80 - time schedule'!DN22","v":0},{"$f":"'K80 - time schedule'!DO22","v":0},{"$f":"'K80 - time schedule'!DP22","v":0},{"$f":"'K80 - time schedule'!DQ22","v":0},{"$f":"'K80 - time schedule'!DR22","v":0},{"$f":"'K80 - time schedule'!DS22","v":0},{"$f":"'K80 - time schedule'!DT22","v":0},{"$f":"'K80 - time schedule'!DU22","v":0},{"$f":"'K80 - time schedule'!DV22","v":0},{"$f":"'K80 - time schedule'!DW22","v":0},{"$f":"'K80 - time schedule'!DX22","v":0},{"$f":"'K80 - time schedule'!DY22","v":0},{"$f":"'K80 - time schedule'!DZ22","v":0},{"$f":"'K80 - time schedule'!EA22","v":0},{"$f":"'K80 - time schedule'!EB22","v":0},{"$f":"'K80 - time schedule'!EC22","v":0},{"$f":"'K80 - time schedule'!ED22","v":0},{"$f":"'K80 - time schedule'!EE22","v":0},{"$f":"'K80 - time schedule'!EF22","v":0},{"$f":"'K80 - time schedule'!EG22","v":0},{"$f":"'K80 - time schedule'!EH22","v":0},{"$f":"'K80 - time schedule'!EI22","v":0},{"$f":"'K80 - time schedule'!EJ22","v":0},{"$f":"'K80 - time schedule'!EK22","v":0},{"$f":"'K80 - time schedule'!EL22","v":0},{"$f":"'K80 - time schedule'!EM22","v":0},{"$f":"'K80 - time schedule'!EN22","v":0},{"$f":"'K80 - time schedule'!EO22","v":0},{"$f":"'K80 - time schedule'!EP22","v":0},{"$f":"'K80 - time schedule'!EQ22","v":0},{"$f":"'K80 - time schedule'!ER22","v":0},{"$f":"'K80 - time schedule'!ES22","v":0},{"$f":"'K80 - time schedule'!ET22","v":0},{"$f":"'K80 - time schedule'!EU22","v":0},{"$f":"'K80 - time schedule'!EV22","v":0},{"$f":"'K80 - time schedule'!EW22","v":0},{"$f":"'K80 - time schedule'!EX22","v":0},{"$f":"'K80 - time schedule'!EY22","v":0},{"$f":"'K80 - time schedule'!EZ22","v":0},{"$f":"'K80 - time schedule'!FA22","v":0},{"$f":"'K80 - time schedule'!FB22","v":0},{"$f":"'K80 - time schedule'!FC22","v":0},{"$f":"'K80 - time schedule'!FD22","v":0},{"$f":"'K80 - time schedule'!FE22","v":0},{"$f":"'K80 - time schedule'!FF22","v":0},{"$f":"'K80 - time schedule'!FG22","v":0},{"$f":"'K80 - time schedule'!FH22","v":0},{"$f":"'K80 - time schedule'!FI22","v":0},{"$f":"'K80 - time schedule'!FJ22","v":0},{"$f":"'K80 - time schedule'!FK22","v":0},{"$f":"'K80 - time schedule'!FL22","v":0},{"$f":"'K80 - time schedule'!FM22","v":0},{"$f":"'K80 - time schedule'!FN22","v":0},{"$f":"'K80 - time schedule'!FO22","v":0},{"$f":"'K80 - time schedule'!FP22","v":0},{"$f":"'K80 - time schedule'!FQ22","v":0},{"$f":"'K80 - time schedule'!FR22","v":0},{"$f":"'K80 - time schedule'!FS22","v":0},{"$f":"'K80 - time schedule'!FT22","v":0},{"$f":"'K80 - time schedule'!FU22","v":0},{"$f":"'K80 - time schedule'!FV22","v":0},{"$f":"'K80 - time schedule'!FW22","v":0},{"$f":"'K80 - time schedule'!FX22","v":0},{"$f":"'K80 - time schedule'!FY22","v":0},{"$f":"'K80 - time schedule'!FZ22","v":0},{"$f":"'K80 - time schedule'!GA22","v":0},{"$f":"'K80 - time schedule'!GB22","v":0},{"$f":"'K80 - time schedule'!GC22","v":0},{"$f":"'K80 - time schedule'!GD22","v":0},{"$f":"'K80 - time schedule'!GE22","v":0},{"$f":"'K80 - time schedule'!GF22","v":0},{"$f":"'K80 - time schedule'!GG22","v":0},{"$f":"'K80 - time schedule'!GH22","v":0},{"$f":"'K80 - time schedule'!GI22","v":0},{"$f":"'K80 - time schedule'!GJ22","v":0},{"$f":"'K80 - time schedule'!GK22","v":0},{"$f":"'K80 - time schedule'!GL22","v":0},{"$f":"'K80 - time schedule'!GM22","v":0},{"$f":"'K80 - time schedule'!GN22","v":0},{"$f":"'K80 - time schedule'!GO22","v":0},{"$f":"'K80 - time schedule'!GP22","v":0},{"$f":"'K80 - time schedule'!GQ22","v":0},{"$f":"'K80 - time schedule'!GR22","v":0},{"$f":"'K80 - time schedule'!GS22","v":0},{"$f":"'K80 - time schedule'!GT22","v":0},{"$f":"'K80 - time schedule'!GU22","v":0},{"$f":"'K80 - time schedule'!GV22","v":0},{"$f":"'K80 - time schedule'!GW22","v":0},{"$f":"'K80 - time schedule'!GX22","v":0},{"$f":"'K80 - time schedule'!GY22","v":0},{"$f":"'K80 - time schedule'!GZ22","v":0},{"$f":"'K80 - time schedule'!HA22","v":0},{"$f":"'K80 - time schedule'!HB22","v":0},{"$f":"'K80 - time schedule'!HC22","v":0},{"$f":"'K80 - time schedule'!HD22","v":0},{"$f":"'K80 - time schedule'!HE22","v":0},{"$f":"'K80 - time schedule'!HF22","v":0},{"$f":"'K80 - time schedule'!HG22","v":0},{"$f":"'K80 - time schedule'!HH22","v":0},{"$f":"'K80 - time schedule'!HI22","v":0},{"$f":"'K80 - time schedule'!HJ22","v":0},{"$f":"'K80 - time schedule'!HK22","v":0},{"$f":"'K80 - time schedule'!HL22","v":0},{"$f":"'K80 - time schedule'!HM22","v":0},{"$f":"'K80 - time schedule'!HN22","v":0},{"$f":"'K80 - time schedule'!HO22","v":0},{"$f":"'K80 - time schedule'!HP22","v":0},{"$f":"'K80 - time schedule'!HQ22","v":0},{"$f":"'K80 - time schedule'!HR22","v":0},{"$f":"'K80 - time schedule'!HS22","v":0},{"$f":"'K80 - time schedule'!HT22","v":0},{"$f":"'K80 - time schedule'!HU22","v":0},{"$f":"'K80 - time schedule'!HV22","v":0},{"$f":"'K80 - time schedule'!HW22","v":0},{"$f":"'K80 - time schedule'!HX22","v":0},{"$f":"'K80 - time schedule'!HY22","v":0},{"$f":"'K80 - time schedule'!HZ22","v":0},{"$f":"'K80 - time schedule'!IA22","v":0},{"$f":"'K80 - time schedule'!IB22","v":0},{"$f":"'K80 - time schedule'!IC22","v":0},{"$f":"'K80 - time schedule'!ID22","v":0},{"$f":"'K80 - time schedule'!IE22","v":0},{"$f":"'K80 - time schedule'!IF22","v":0},{"$f":"'K80 - time schedule'!IG22","v":0},{"$f":"'K80 - time schedule'!IH22","v":0},{"$f":"'K80 - time schedule'!II22","v":0},{"$f":"'K80 - time schedule'!IJ22","v":0},{"$f":"'K80 - time schedule'!IK22","v":0},{"$f":"'K80 - time schedule'!IL22","v":0},{"$f":"'K80 - time schedule'!IM22","v":0},{"$f":"'K80 - time schedule'!IN22","v":0},{"$f":"'K80 - time schedule'!IO22","v":0},{"$f":"'K80 - time schedule'!IP22","v":0},{"$f":"'K80 - time schedule'!IQ22","v":0},{"$f":"'K80 - time schedule'!IR22","v":0},{"$f":"'K80 - time schedule'!IS22","v":0},{"$f":"'K80 - time schedule'!IT22","v":0},{"$f":"'K80 - time schedule'!IU22","v":0},{"$f":"'K80 - time schedule'!IV22","v":0},{"$f":"'K80 - time schedule'!IW22","v":0},{"$f":"'K80 - time schedule'!IX22","v":0},{"$f":"'K80 - time schedule'!IY22","v":0},{"$f":"'K80 - time schedule'!IZ22","v":0},{"$f":"'K80 - time schedule'!JA22","v":0},{"$f":"'K80 - time schedule'!JB22","v":0},{"$f":"'K80 - time schedule'!JC22","v":0},{"$f":"'K80 - time schedule'!JD22","v":0},{"$f":"'K80 - time schedule'!JE22","v":0},{"$f":"'K80 - time schedule'!JF22","v":0},{"$f":"'K80 - time schedule'!JG22","v":0},{"$f":"'K80 - time schedule'!JH22","v":0},{"$f":"'K80 - time schedule'!JI22","v":0},{"$f":"'K80 - time schedule'!JJ22","v":0},{"$f":"'K80 - time schedule'!JK22","v":0},{"$f":"'K80 - time schedule'!JL22","v":0},{"$f":"'K80 - time schedule'!JM22","v":0},{"$f":"'K80 - time schedule'!JN22","v":0},{"$f":"'K80 - time schedule'!JO22","v":0},{"$f":"'K80 - time schedule'!JP22","v":0},{"$f":"'K80 - time schedule'!JQ22","v":0},{"$f":"'K80 - time schedule'!JR22","v":0},{"$f":"'K80 - time schedule'!JS22","v":0},{"$f":"'K80 - time schedule'!JT22","v":0},{"$f":"'K80 - time schedule'!JU22","v":0},{"$f":"'K80 - time schedule'!JV22","v":0},{"$f":"'K80 - time schedule'!JW22","v":0},{"$f":"'K80 - time schedule'!JX22","v":0},{"$f":"'K80 - time schedule'!JY22","v":0},{"$f":"'K80 - time schedule'!JZ22","v":0},{"$f":"'K80 - time schedule'!KA22","v":0},{"$f":"'K80 - time schedule'!KB22","v":0},{"$f":"'K80 - time schedule'!KC22","v":0},{"$f":"'K80 - time schedule'!KD22","v":0},{"$f":"'K80 - time schedule'!KE22","v":0},{"$f":"'K80 - time schedule'!KF22","v":0},{"$f":"'K80 - time schedule'!KG22","v":0},{"$f":"'K80 - time schedule'!KH22","v":0},{"$f":"'K80 - time schedule'!KI22","v":0},{"$f":"'K80 - time schedule'!KJ22","v":0},{"$f":"'K80 - time schedule'!KK22","v":0},{"$f":"'K80 - time schedule'!KL22","v":0},{"$f":"'K80 - time schedule'!KM22","v":0},{"$f":"'K80 - time schedule'!KN22","v":0},{"$f":"'K80 - time schedule'!KO22","v":0},{"$f":"'K80 - time schedule'!KP22","v":0},{"$f":"'K80 - time schedule'!KQ22","v":0},{"$f":"'K80 - time schedule'!KR22","v":0},{"$f":"'K80 - time schedule'!KS22","v":0},{"$f":"'K80 - time schedule'!KT22","v":0}]
["Boiler room K80 - fuel silos, including transport of fuel to the boiler","K80",{"$f":"'K80 - time schedule'!G24","v":0},{"$f":"'K80 - time schedule'!H24","v":0},{"$f":"'K80 - time schedule'!I24","v":0},{"$f":"'K80 - time schedule'!J24","v":0},{"$f":"'K80 - time schedule'!K24","v":0},{"$f":"'K80 - time schedule'!L24","v":0},{"$f":"'K80 - time schedule'!M24","v":0},{"$f":"'K80 - time schedule'!N24","v":0},{"$f":"'K80 - time schedule'!O24","v":0},{"$f":"'K80 - time schedule'!P24","v":0},{"$f":"'K80 - time schedule'!Q24","v":0},{"$f":"'K80 - time schedule'!R24","v":0},{"$f":"'K80 - time schedule'!S24","v":0},{"$f":"'K80 - time schedule'!T24","v":0},{"$f":"'K80 - time schedule'!U24","v":0},{"$f":"'K80 - time schedule'!V24","v":0},{"$f":"'K80 - time schedule'!W24","v":0},{"$f":"'K80 - time schedule'!X24","v":0},{"$f":"'K80 - time schedule'!Y24","v":0},{"$f":"'K80 - time schedule'!Z24","v":0},{"$f":"'K80 - time schedule'!AA24","v":0},{"$f":"'K80 - time schedule'!AB24","v":0},{"$f":"'K80 - time schedule'!AC24","v":0},{"$f":"'K80 - time schedule'!AD24","v":0},{"$f":"'K80 - time schedule'!AE24","v":0},{"$f":"'K80 - time schedule'!AF24","v":0},{"$f":"'K80 - time schedule'!AG24","v":0},{"$f":"'K80 - time schedule'!AH24","v":0},{"$f":"'K80 - time schedule'!AI24","v":0},{"$f":"'K80 - time schedule'!AJ24","v":0},{"$f":"'K80 - time schedule'!AK24","v":0},{"$f":"'K80 - time schedule'!AL24","v":0},{"$f":"'K80 - time schedule'!AM24","v":0},{"$f":"'K80 - time schedule'!AN24","v":0},{"$f":"'K80 - time schedule'!AO24","v":0},{"$f":"'K80 - time schedule'!AP24","v":0},{"$f":"'K80 - time schedule'!AQ24","v":0},{"$f":"'K80 - time schedule'!AR24","v":0},{"$f":"'K80 - time schedule'!AS24","v":0},{"$f":"'K80 - time schedule'!AT24","v":0},{"$f":"'K80 - time schedule'!AU24","v":0},{"$f":"'K80 - time schedule'!AV24","v":0},{"$f":"'K80 - time schedule'!AW24","v":0},{"$f":"'K80 - time schedule'!AX24","v":0},{"$f":"'K80 - time schedule'!AY24","v":0},{"$f":"'K80 - time schedule'!AZ24","v":0},{"$f":"'K80 - time schedule'!BA24","v":0},{"$f":"'K80 - time schedule'!BB24","v":0},{"$f":"'K80 - time schedule'!BC24","v":0},{"$f":"'K80 - time schedule'!BD24","v":0},{"$f":"'K80 - time schedule'!BE24","v":0},{"$f":"'K80 - time schedule'!BF24","v":0},{"$f":"'K80 - time schedule'!BG24","v":0},{"$f":"'K80 - time schedule'!BH24","v":0},{"$f":"'K80 - time schedule'!BI24","v":0},{"$f":"'K80 - time schedule'!BJ24","v":0},{"$f":"'K80 - time schedule'!BK24","v":0},{"$f":"'K80 - time schedule'!BL24","v":0},{"$f":"'K80 - time schedule'!BM24","v":0},{"$f":"'K80 - time schedule'!BN24","v":0},{"$f":"'K80 - time schedule'!BO24","v":0},{"$f":"'K80 - time schedule'!BP24","v":0},{"$f":"'K80 - time schedule'!BQ24","v":0},{"$f":"'K80 - time schedule'!BR24","v":0},{"$f":"'K80 - time schedule'!BS24","v":0},{"$f":"'K80 - time schedule'!BT24","v":0},{"$f":"'K80 - time schedule'!BU24","v":0},{"$f":"'K80 - time schedule'!BV24","v":0},{"$f":"'K80 - time schedule'!BW24","v":0},{"$f":"'K80 - time schedule'!BX24","v":0},{"$f":"'K80 - time schedule'!BY24","v":0},{"$f":"'K80 - time schedule'!BZ24","v":0},{"$f":"'K80 - time schedule'!CA24","v":0},{"$f":"'K80 - time schedule'!CB24","v":0},{"$f":"'K80 - time schedule'!CC24","v":0},{"$f":"'K80 - time schedule'!CD24","v":0},{"$f":"'K80 - time schedule'!CE24","v":0},{"$f":"'K80 - time schedule'!CF24","v":0},{"$f":"'K80 - time schedule'!CG24","v":0},{"$f":"'K80 - time schedule'!CH24","v":0},{"$f":"'K80 - time schedule'!CI24","v":0},{"$f":"'K80 - time schedule'!CJ24","v":0},{"$f":"'K80 - time schedule'!CK24","v":0},{"$f":"'K80 - time schedule'!CL24","v":0},{"$f":"'K80 - time schedule'!CM24","v":0},{"$f":"'K80 - time schedule'!CN24","v":0},{"$f":"'K80 - time schedule'!CO24","v":0},{"$f":"'K80 - time schedule'!CP24","v":0},{"$f":"'K80 - time schedule'!CQ24","v":0},{"$f":"'K80 - time schedule'!CR24","v":0},{"$f":"'K80 - time schedule'!CS24","v":0},{"$f":"'K80 - time schedule'!CT24","v":0},{"$f":"'K80 - time schedule'!CU24","v":0},{"$f":"'K80 - time schedule'!CV24","v":0},{"$f":"'K80 - time schedule'!CW24","v":0},{"$f":"'K80 - time schedule'!CX24","v":0},{"$f":"'K80 - time schedule'!CY24","v":0},{"$f":"'K80 - time schedule'!CZ24","v":0},{"$f":"'K80 - time schedule'!DA24","v":0},{"$f":"'K80 - time schedule'!DB24","v":0},{"$f":"'K80 - time schedule'!DC24","v":0},{"$f":"'K80 - time schedule'!DD24","v":0},{"$f":"'K80 - time schedule'!DE24","v":0},{"$f":"'K80 - time schedule'!DF24","v":0},{"$f":"'K80 - time schedule'!DG24","v":0},{"$f":"'K80 - time schedule'!DH24","v":0},{"$f":"'K80 - time schedule'!DI24","v":0},{"$f":"'K80 - time schedule'!DJ24","v":0},{"$f":"'K80 - time schedule'!DK24","v":0},{"$f":"'K80 - time schedule'!DL24","v":0},{"$f":"'K80 - time schedule'!DM24","v":0},{"$f":"'K80 - time schedule'!DN24","v":0},{"$f":"'K80 - time schedule'!DO24","v":0},{"$f":"'K80 - time schedule'!DP24","v":0},{"$f":"'K80 - time schedule'!DQ24","v":0},{"$f":"'K80 - time schedule'!DR24","v":0},{"$f":"'K80 - time schedule'!DS24","v":0},{"$f":"'K80 - time schedule'!DT24","v":0},{"$f":"'K80 - time schedule'!DU24","v":0},{"$f":"'K80 - time schedule'!DV24","v":0},{"$f":"'K80 - time schedule'!DW24","v":0},{"$f":"'K80 - time schedule'!DX24","v":0},{"$f":"'K80 - time schedule'!DY24","v":0},{"$f":"'K80 - time schedule'!DZ24","v":0},{"$f":"'K80 - time schedule'!EA24","v":0},{"$f":"'K80 - time schedule'!EB24","v":0},{"$f":"'K80 - time schedule'!EC24","v":0},{"$f":"'K80 - time schedule'!ED24","v":0},{"$f":"'K80 - time schedule'!EE24","v":0},{"$f":"'K80 - time schedule'!EF24","v":0},{"$f":"'K80 - time schedule'!EG24","v":0},{"$f":"'K80 - time schedule'!EH24","v":0},{"$f":"'K80 - time schedule'!EI24","v":0},{"$f":"'K80 - time schedule'!EJ24","v":0},{"$f":"'K80 - time schedule'!EK24","v":0},{"$f":"'K80 - time schedule'!EL24","v":0},{"$f":"'K80 - time schedule'!EM24","v":0},{"$f":"'K80 - time schedule'!EN24","v":0},{"$f":"'K80 - time schedule'!EO24","v":0},{"$f":"'K80 - time schedule'!EP24","v":0},{"$f":"'K80 - time schedule'!EQ24","v":0},{"$f":"'K80 - time schedule'!ER24","v":0},{"$f":"'K80 - time schedule'!ES24","v":0},{"$f":"'K80 - time schedule'!ET24","v":0},{"$f":"'K80 - time schedule'!EU24","v":0},{"$f":"'K80 - time schedule'!EV24","v":0},{"$f":"'K80 - time schedule'!EW24","v":0},{"$f":"'K80 - time schedule'!EX24","v":0},{"$f":"'K80 - time schedule'!EY24","v":0},{"$f":"'K80 - time schedule'!EZ24","v":0},{"$f":"'K80 - time schedule'!FA24","v":0},{"$f":"'K80 - time schedule'!FB24","v":0},{"$f":"'K80 - time schedule'!FC24","v":0},{"$f":"'K80 - time schedule'!FD24","v":0},{"$f":"'K80 - time schedule'!FE24","v":0},{"$f":"'K80 - time schedule'!FF24","v":0},{"$f":"'K80 - time schedule'!FG24","v":0},{"$f":"'K80 - time schedule'!FH24","v":0},{"$f":"'K80 - time schedule'!FI24","v":0},{"$f":"'K80 - time schedule'!FJ24","v":0},{"$f":"'K80 - time schedule'!FK24","v":0},{"$f":"'K80 - time schedule'!FL24","v":0},{"$f":"'K80 - time schedule'!FM24","v":0},{"$f":"'K80 - time schedule'!FN24","v":0},{"$f":"'K80 - time schedule'!FO24","v":0},{"$f":"'K80 - time schedule'!FP24","v":0},{"$f":"'K80 - time schedule'!FQ24","v":0},{"$f":"'K80 - time schedule'!FR24","v":0},{"$f":"'K80 - time schedule'!FS24","v":0},{"$f":"'K80 - time schedule'!FT24","v":0},{"$f":"'K80 - time schedule'!FU24","v":0},{"$f":"'K80 - time schedule'!FV24","v":0},{"$f":"'K80 - time schedule'!FW24","v":0},{"$f":"'K80 - time schedule'!FX24","v":0},{"$f":"'K80 - time schedule'!FY24","v":0},{"$f":"'K80 - time schedule'!FZ24","v":0},{"$f":"'K80 - time schedule'!GA24","v":0},{"$f":"'K80 - time schedule'!GB24","v":0},{"$f":"'K80 - time schedule'!GC24","v":0},{"$f":"'K80 - time schedule'!GD24","v":0},{"$f":"'K80 - time schedule'!GE24","v":0},{"$f":"'K80 - time schedule'!GF24","v":0},{"$f":"'K80 - time schedule'!GG24","v":0},{"$f":"'K80 - time schedule'!GH24","v":0},{"$f":"'K80 - time schedule'!GI24","v":0},{"$f":"'K80 - time schedule'!GJ24","v":0},{"$f":"'K80 - time schedule'!GK24","v":0},{"$f":"'K80 - time schedule'!GL24","v":0},{"$f":"'K80 - time schedule'!GM24","v":0},{"$f":"'K80 - time schedule'!GN24","v":0},{"$f":"'K80 - time schedule'!GO24","v":0},{"$f":"'K80 - time schedule'!GP24","v":0},{"$f":"'K80 - time schedule'!GQ24","v":0},{"$f":"'K80 - time schedule'!GR24","v":0},{"$f":"'K80 - time schedule'!GS24","v":0},{"$f":"'K80 - time schedule'!GT24","v":0},{"$f":"'K80 - time schedule'!GU24","v":0},{"$f":"'K80 - time schedule'!GV24","v":0},{"$f":"'K80 - time schedule'!GW24","v":0},{"$f":"'K80 - time schedule'!GX24","v":0},{"$f":"'K80 - time schedule'!GY24","v":0},{"$f":"'K80 - time schedule'!GZ24","v":0},{"$f":"'K80 - time schedule'!HA24","v":0},{"$f":"'K80 - time schedule'!HB24","v":0},{"$f":"'K80 - time schedule'!HC24","v":0},{"$f":"'K80 - time schedule'!HD24","v":0},{"$f":"'K80 - time schedule'!HE24","v":0},{"$f":"'K80 - time schedule'!HF24","v":0},{"$f":"'K80 - time schedule'!HG24","v":0},{"$f":"'K80 - time schedule'!HH24","v":0},{"$f":"'K80 - time schedule'!HI24","v":0},{"$f":"'K80 - time schedule'!HJ24","v":0},{"$f":"'K80 - time schedule'!HK24","v":0},{"$f":"'K80 - time schedule'!HL24","v":0},{"$f":"'K80 - time schedule'!HM24","v":0},{"$f":"'K80 - time schedule'!HN24","v":0},{"$f":"'K80 - time schedule'!HO24","v":0},{"$f":"'K80 - time schedule'!HP24","v":0},{"$f":"'K80 - time schedule'!HQ24","v":0},{"$f":"'K80 - time schedule'!HR24","v":0},{"$f":"'K80 - time schedule'!HS24","v":0},{"$f":"'K80 - time schedule'!HT24","v":0},{"$f":"'K80 - time schedule'!HU24","v":0},{"$f":"'K80 - time schedule'!HV24","v":0},{"$f":"'K80 - time schedule'!HW24","v":0},{"$f":"'K80 - time schedule'!HX24","v":0},{"$f":"'K80 - time schedule'!HY24","v":0},{"$f":"'K80 - time schedule'!HZ24","v":0},{"$f":"'K80 - time schedule'!IA24","v":0},{"$f":"'K80 - time schedule'!IB24","v":0},{"$f":"'K80 - time schedule'!IC24","v":0},{"$f":"'K80 - time schedule'!ID24","v":0},{"$f":"'K80 - time schedule'!IE24","v":0},{"$f":"'K80 - time schedule'!IF24","v":0},{"$f":"'K80 - time schedule'!IG24","v":0},{"$f":"'K80 - time schedule'!IH24","v":0},{"$f":"'K80 - time schedule'!II24","v":0},{"$f":"'K80 - time schedule'!IJ24","v":0},{"$f":"'K80 - time schedule'!IK24","v":0},{"$f":"'K80 - time schedule'!IL24","v":0},{"$f":"'K80 - time schedule'!IM24","v":0},{"$f":"'K80 - time schedule'!IN24","v":0},{"$f":"'K80 - time schedule'!IO24","v":0},{"$f":"'K80 - time schedule'!IP24","v":0},{"$f":"'K80 - time schedule'!IQ24","v":0},{"$f":"'K80 - time schedule'!IR24","v":0},{"$f":"'K80 - time schedule'!IS24","v":0},{"$f":"'K80 - time schedule'!IT24","v":0},{"$f":"'K80 - time schedule'!IU24","v":0},{"$f":"'K80 - time schedule'!IV24","v":0},{"$f":"'K80 - time schedule'!IW24","v":0},{"$f":"'K80 - time schedule'!IX24","v":0},{"$f":"'K80 - time schedule'!IY24","v":0},{"$f":"'K80 - time schedule'!IZ24","v":0},{"$f":"'K80 - time schedule'!JA24","v":0},{"$f":"'K80 - time schedule'!JB24","v":0},{"$f":"'K80 - time schedule'!JC24","v":0},{"$f":"'K80 - time schedule'!JD24","v":0},{"$f":"'K80 - time schedule'!JE24","v":0},{"$f":"'K80 - time schedule'!JF24","v":0},{"$f":"'K80 - time schedule'!JG24","v":0},{"$f":"'K80 - time schedule'!JH24","v":0},{"$f":"'K80 - time schedule'!JI24","v":0},{"$f":"'K80 - time schedule'!JJ24","v":0},{"$f":"'K80 - time schedule'!JK24","v":0},{"$f":"'K80 - time schedule'!JL24","v":0},{"$f":"'K80 - time schedule'!JM24","v":0},{"$f":"'K80 - time schedule'!JN24","v":0},{"$f":"'K80 - time schedule'!JO24","v":0},{"$f":"'K80 - time schedule'!JP24","v":0},{"$f":"'K80 - time schedule'!JQ24","v":0},{"$f":"'K80 - time schedule'!JR24","v":0},{"$f":"'K80 - time schedule'!JS24","v":0},{"$f":"'K80 - time schedule'!JT24","v":0},{"$f":"'K80 - time schedule'!JU24","v":0},{"$f":"'K80 - time schedule'!JV24","v":0},{"$f":"'K80 - time schedule'!JW24","v":0},{"$f":"'K80 - time schedule'!JX24","v":0},{"$f":"'K80 - time schedule'!JY24","v":0},{"$f":"'K80 - time schedule'!JZ24","v":0},{"$f":"'K80 - time schedule'!KA24","v":0},{"$f":"'K80 - time schedule'!KB24","v":0},{"$f":"'K80 - time schedule'!KC24","v":0},{"$f":"'K80 - time schedule'!KD24","v":0},{"$f":"'K80 - time schedule'!KE24","v":0},{"$f":"'K80 - time schedule'!KF24","v":0},{"$f":"'K80 - time schedule'!KG24","v":0},{"$f":"'K80 - time schedule'!KH24","v":0},{"$f":"'K80 - time schedule'!KI24","v":0},{"$f":"'K80 - time schedule'!KJ24","v":0},{"$f":"'K80 - time schedule'!KK24","v":0},{"$f":"'K80 - time schedule'!KL24","v":0},{"$f":"'K80 - time schedule'!KM24","v":0},{"$f":"'K80 - time schedule'!KN24","v":0},{"$f":"'K80 - time schedule'!KO24","v":0},{"$f":"'K80 - time schedule'!KP24","v":0},{"$f":"'K80 - time schedule'!KQ24","v":0},{"$f":"'K80 - time schedule'!KR24","v":0},{"$f":"'K80 - time schedule'!KS24","v":0},{"$f":"'K80 - time schedule'!KT24","v":0}]
["Boiler room K80 - air heating","K80",{"$f":"'K80 - time schedule'!G26","v":0},{"$f":"'K80 - time schedule'!H26","v":0},{"$f":"'K80 - time schedule'!I26","v":0},{"$f":"'K80 - time schedule'!J26","v":0},{"$f":"'K80 - time schedule'!K26","v":0},{"$f":"'K80 - time schedule'!L26","v":0},{"$f":"'K80 - time schedule'!M26","v":0},{"$f":"'K80 - time schedule'!N26","v":0},{"$f":"'K80 - time schedule'!O26","v":0},{"$f":"'K80 - time schedule'!P26","v":0},{"$f":"'K80 - time schedule'!Q26","v":0},{"$f":"'K80 - time schedule'!R26","v":0},{"$f":"'K80 - time schedule'!S26","v":0},{"$f":"'K80 - time schedule'!T26","v":0},{"$f":"'K80 - time schedule'!U26","v":0},{"$f":"'K80 - time schedule'!V26","v":0},{"$f":"'K80 - time schedule'!W26","v":0},{"$f":"'K80 - time schedule'!X26","v":0},{"$f":"'K80 - time schedule'!Y26","v":0},{"$f":"'K80 - time schedule'!Z26","v":0},{"$f":"'K80 - time schedule'!AA26","v":0},{"$f":"'K80 - time schedule'!AB26","v":0},{"$f":"'K80 - time schedule'!AC26","v":0},{"$f":"'K80 - time schedule'!AD26","v":0},{"$f":"'K80 - time schedule'!AE26","v":0},{"$f":"'K80 - time schedule'!AF26","v":0},{"$f":"'K80 - time schedule'!AG26","v":0},{"$f":"'K80 - time schedule'!AH26","v":0},{"$f":"'K80 - time schedule'!AI26","v":0},{"$f":"'K80 - time schedule'!AJ26","v":0},{"$f":"'K80 - time schedule'!AK26","v":0},{"$f":"'K80 - time schedule'!AL26","v":0},{"$f":"'K80 - time schedule'!AM26","v":0},{"$f":"'K80 - time schedule'!AN26","v":0},{"$f":"'K80 - time schedule'!AO26","v":0},{"$f":"'K80 - time schedule'!AP26","v":0},{"$f":"'K80 - time schedule'!AQ26","v":0},{"$f":"'K80 - time schedule'!AR26","v":0},{"$f":"'K80 - time schedule'!AS26","v":0},{"$f":"'K80 - time schedule'!AT26","v":0},{"$f":"'K80 - time schedule'!AU26","v":0},{"$f":"'K80 - time schedule'!AV26","v":0},{"$f":"'K80 - time schedule'!AW26","v":0},{"$f":"'K80 - time schedule'!AX26","v":0},{"$f":"'K80 - time schedule'!AY26","v":0},{"$f":"'K80 - time schedule'!AZ26","v":0},{"$f":"'K80 - time schedule'!BA26","v":0},{"$f":"'K80 - time schedule'!BB26","v":0},{"$f":"'K80 - time schedule'!BC26","v":0},{"$f":"'K80 - time schedule'!BD26","v":0},{"$f":"'K80 - time schedule'!BE26","v":0},{"$f":"'K80 - time schedule'!BF26","v":0},{"$f":"'K80 - time schedule'!BG26","v":0},{"$f":"'K80 - time schedule'!BH26","v":0},{"$f":"'K80 - time schedule'!BI26","v":0},{"$f":"'K80 - time schedule'!BJ26","v":0},{"$f":"'K80 - time schedule'!BK26","v":0},{"$f":"'K80 - time schedule'!BL26","v":0},{"$f":"'K80 - time schedule'!BM26","v":0},{"$f":"'K80 - time schedule'!BN26","v":0},{"$f":"'K80 - time schedule'!BO26","v":0},{"$f":"'K80 - time schedule'!BP26","v":0},{"$f":"'K80 - time schedule'!BQ26","v":0},{"$f":"'K80 - time schedule'!BR26","v":0},{"$f":"'K80 - time schedule'!BS26","v":0},{"$f":"'K80 - time schedule'!BT26","v":0},{"$f":"'K80 - time schedule'!BU26","v":0},{"$f":"'K80 - time schedule'!BV26","v":0},{"$f":"'K80 - time schedule'!BW26","v":0},{"$f":"'K80 - time schedule'!BX26","v":0},{"$f":"'K80 - time schedule'!BY26","v":0},{"$f":"'K80 - time schedule'!BZ26","v":0},{"$f":"'K80 - time schedule'!CA26","v":0},{"$f":"'K80 - time schedule'!CB26","v":0},{"$f":"'K80 - time schedule'!CC26","v":0},{"$f":"'K80 - time schedule'!CD26","v":0},{"$f":"'K80 - time schedule'!CE26","v":0},{"$f":"'K80 - time schedule'!CF26","v":0},{"$f":"'K80 - time schedule'!CG26","v":0},{"$f":"'K80 - time schedule'!CH26","v":0},{"$f":"'K80 - time schedule'!CI26","v":0},{"$f":"'K80 - time schedule'!CJ26","v":0},{"$f":"'K80 - time schedule'!CK26","v":0},{"$f":"'K80 - time schedule'!CL26","v":0},{"$f":"'K80 - time schedule'!CM26","v":0},{"$f":"'K80 - time schedule'!CN26","v":0},{"$f":"'K80 - time schedule'!CO26","v":0},{"$f":"'K80 - time schedule'!CP26","v":0},{"$f":"'K80 - time schedule'!CQ26","v":0},{"$f":"'K80 - time schedule'!CR26","v":0},{"$f":"'K80 - time schedule'!CS26","v":0},{"$f":"'K80 - time schedule'!CT26","v":0},{"$f":"'K80 - time schedule'!CU26","v":0},{"$f":"'K80 - time schedule'!CV26","v":0},{"$f":"'K80 - time schedule'!CW26","v":0},{"$f":"'K80 - time schedule'!CX26","v":0},{"$f":"'K80 - time schedule'!CY26","v":0},{"$f":"'K80 - time schedule'!CZ26","v":0},{"$f":"'K80 - time schedule'!DA26","v":0},{"$f":"'K80 - time schedule'!DB26","v":0},{"$f":"'K80 - time schedule'!DC26","v":0},{"$f":"'K80 - time schedule'!DD26","v":0},{"$f":"'K80 - time schedule'!DE26","v":0},{"$f":"'K80 - time schedule'!DF26","v":0},{"$f":"'K80 - time schedule'!DG26","v":0},{"$f":"'K80 - time schedule'!DH26","v":0},{"$f":"'K80 - time schedule'!DI26","v":0},{"$f":"'K80 - time schedule'!DJ26","v":0},{"$f":"'K80 - time schedule'!DK26","v":0},{"$f":"'K80 - time schedule'!DL26","v":0},{"$f":"'K80 - time schedule'!DM26","v":0},{"$f":"'K80 - time schedule'!DN26","v":0},{"$f":"'K80 - time schedule'!DO26","v":0},{"$f":"'K80 - time schedule'!DP26","v":0},{"$f":"'K80 - time schedule'!DQ26","v":0},{"$f":"'K80 - time schedule'!DR26","v":0},{"$f":"'K80 - time schedule'!DS26","v":0},{"$f":"'K80 - time schedule'!DT26","v":0},{"$f":"'K80 - time schedule'!DU26","v":0},{"$f":"'K80 - time schedule'!DV26","v":0},{"$f":"'K80 - time schedule'!DW26","v":0},{"$f":"'K80 - time schedule'!DX26","v":0},{"$f":"'K80 - time schedule'!DY26","v":0},{"$f":"'K80 - time schedule'!DZ26","v":0},{"$f":"'K80 - time schedule'!EA26","v":0},{"$f":"'K80 - time schedule'!EB26","v":0},{"$f":"'K80 - time schedule'!EC26","v":0},{"$f":"'K80 - time schedule'!ED26","v":0},{"$f":"'K80 - time schedule'!EE26","v":0},{"$f":"'K80 - time schedule'!EF26","v":0},{"$f":"'K80 - time schedule'!EG26","v":0},{"$f":"'K80 - time schedule'!EH26","v":0},{"$f":"'K80 - time schedule'!EI26","v":0},{"$f":"'K80 - time schedule'!EJ26","v":0},{"$f":"'K80 - time schedule'!EK26","v":0},{"$f":"'K80 - time schedule'!EL26","v":0},{"$f":"'K80 - time schedule'!EM26","v":0},{"$f":"'K80 - time schedule'!EN26","v":0},{"$f":"'K80 - time schedule'!EO26","v":0},{"$f":"'K80 - time schedule'!EP26","v":0},{"$f":"'K80 - time schedule'!EQ26","v":0},{"$f":"'K80 - time schedule'!ER26","v":0},{"$f":"'K80 - time schedule'!ES26","v":0},{"$f":"'K80 - time schedule'!ET26","v":0},{"$f":"'K80 - time schedule'!EU26","v":0},{"$f":"'K80 - time schedule'!EV26","v":0},{"$f":"'K80 - time schedule'!EW26","v":0},{"$f":"'K80 - time schedule'!EX26","v":0},{"$f":"'K80 - time schedule'!EY26","v":0},{"$f":"'K80 - time schedule'!EZ26","v":0},{"$f":"'K80 - time schedule'!FA26","v":0},{"$f":"'K80 - time schedule'!FB26","v":0},{"$f":"'K80 - time schedule'!FC26","v":0},{"$f":"'K80 - time schedule'!FD26","v":0},{"$f":"'K80 - time schedule'!FE26","v":0},{"$f":"'K80 - time schedule'!FF26","v":0},{"$f":"'K80 - time schedule'!FG26","v":0},{"$f":"'K80 - time schedule'!FH26","v":0},{"$f":"'K80 - time schedule'!FI26","v":0},{"$f":"'K80 - time schedule'!FJ26","v":0},{"$f":"'K80 - time schedule'!FK26","v":0},{"$f":"'K80 - time schedule'!FL26","v":0},{"$f":"'K80 - time schedule'!FM26","v":0},{"$f":"'K80 - time schedule'!FN26","v":0},{"$f":"'K80 - time schedule'!FO26","v":0},{"$f":"'K80 - time schedule'!FP26","v":0},{"$f":"'K80 - time schedule'!FQ26","v":0},{"$f":"'K80 - time schedule'!FR26","v":0},{"$f":"'K80 - time schedule'!FS26","v":0},{"$f":"'K80 - time schedule'!FT26","v":0},{"$f":"'K80 - time schedule'!FU26","v":0},{"$f":"'K80 - time schedule'!FV26","v":0},{"$f":"'K80 - time schedule'!FW26","v":0},{"$f":"'K80 - time schedule'!FX26","v":0},{"$f":"'K80 - time schedule'!FY26","v":0},{"$f":"'K80 - time schedule'!FZ26","v":0},{"$f":"'K80 - time schedule'!GA26","v":0},{"$f":"'K80 - time schedule'!GB26","v":0},{"$f":"'K80 - time schedule'!GC26","v":0},{"$f":"'K80 - time schedule'!GD26","v":0},{"$f":"'K80 - time schedule'!GE26","v":0},{"$f":"'K80 - time schedule'!GF26","v":0},{"$f":"'K80 - time schedule'!GG26","v":0},{"$f":"'K80 - time schedule'!GH26","v":0},{"$f":"'K80 - time schedule'!GI26","v":0},{"$f":"'K80 - time schedule'!GJ26","v":0},{"$f":"'K80 - time schedule'!GK26","v":0},{"$f":"'K80 - time schedule'!GL26","v":0},{"$f":"'K80 - time schedule'!GM26","v":0},{"$f":"'K80 - time schedule'!GN26","v":0},{"$f":"'K80 - time schedule'!GO26","v":0},{"$f":"'K80 - time schedule'!GP26","v":0},{"$f":"'K80 - time schedule'!GQ26","v":0},{"$f":"'K80 - time schedule'!GR26","v":0},{"$f":"'K80 - time schedule'!GS26","v":0},{"$f":"'K80 - time schedule'!GT26","v":0},{"$f":"'K80 - time schedule'!GU26","v":0},{"$f":"'K80 - time schedule'!GV26","v":0},{"$f":"'K80 - time schedule'!GW26","v":0},{"$f":"'K80 - time schedule'!GX26","v":0},{"$f":"'K80 - time schedule'!GY26","v":0},{"$f":"'K80 - time schedule'!GZ26","v":0},{"$f":"'K80 - time schedule'!HA26","v":0},{"$f":"'K80 - time schedule'!HB26","v":0},{"$f":"'K80 - time schedule'!HC26","v":0},{"$f":"'K80 - time schedule'!HD26","v":0},{"$f":"'K80 - time schedule'!HE26","v":0},{"$f":"'K80 - time schedule'!HF26","v":0},{"$f":"'K80 - time schedule'!HG26","v":0},{"$f":"'K80 - time schedule'!HH26","v":0},{"$f":"'K80 - time schedule'!HI26","v":0},{"$f":"'K80 - time schedule'!HJ26","v":0},{"$f":"'K80 - time schedule'!HK26","v":0},{"$f":"'K80 - time schedule'!HL26","v":0},{"$f":"'K80 - time schedule'!HM26","v":0},{"$f":"'K80 - time schedule'!HN26","v":0},{"$f":"'K80 - time schedule'!HO26","v":0},{"$f":"'K80 - time schedule'!HP26","v":0},{"$f":"'K80 - time schedule'!HQ26","v":0},{"$f":"'K80 - time schedule'!HR26","v":0},{"$f":"'K80 - time schedule'!HS26","v":0},{"$f":"'K80 - time schedule'!HT26","v":0},{"$f":"'K80 - time schedule'!HU26","v":0},{"$f":"'K80 - time schedule'!HV26","v":0},{"$f":"'K80 - time schedule'!HW26","v":0},{"$f":"'K80 - time schedule'!HX26","v":0},{"$f":"'K80 - time schedule'!HY26","v":0},{"$f":"'K80 - time schedule'!HZ26","v":0},{"$f":"'K80 - time schedule'!IA26","v":0},{"$f":"'K80 - time schedule'!IB26","v":0},{"$f":"'K80 - time schedule'!IC26","v":0},{"$f":"'K80 - time schedule'!ID26","v":0},{"$f":"'K80 - time schedule'!IE26","v":0},{"$f":"'K80 - time schedule'!IF26","v":0},{"$f":"'K80 - time schedule'!IG26","v":0},{"$f":"'K80 - time schedule'!IH26","v":0},{"$f":"'K80 - time schedule'!II26","v":0},{"$f":"'K80 - time schedule'!IJ26","v":0},{"$f":"'K80 - time schedule'!IK26","v":0},{"$f":"'K80 - time schedule'!IL26","v":0},{"$f":"'K80 - time schedule'!IM26","v":0},{"$f":"'K80 - time schedule'!IN26","v":0},{"$f":"'K80 - time schedule'!IO26","v":0},{"$f":"'K80 - time schedule'!IP26","v":0},{"$f":"'K80 - time schedule'!IQ26","v":0},{"$f":"'K80 - time schedule'!IR26","v":0},{"$f":"'K80 - time schedule'!IS26","v":0},{"$f":"'K80 - time schedule'!IT26","v":0},{"$f":"'K80 - time schedule'!IU26","v":0},{"$f":"'K80 - time schedule'!IV26","v":0},{"$f":"'K80 - time schedule'!IW26","v":0},{"$f":"'K80 - time schedule'!IX26","v":0},{"$f":"'K80 - time schedule'!IY26","v":0},{"$f":"'K80 - time schedule'!IZ26","v":0},{"$f":"'K80 - time schedule'!JA26","v":0},{"$f":"'K80 - time schedule'!JB26","v":0},{"$f":"'K80 - time schedule'!JC26","v":0},{"$f":"'K80 - time schedule'!JD26","v":0},{"$f":"'K80 - time schedule'!JE26","v":0},{"$f":"'K80 - time schedule'!JF26","v":0},{"$f":"'K80 - time schedule'!JG26","v":0},{"$f":"'K80 - time schedule'!JH26","v":0},{"$f":"'K80 - time schedule'!JI26","v":0},{"$f":"'K80 - time schedule'!JJ26","v":0},{"$f":"'K80 - time schedule'!JK26","v":0},{"$f":"'K80 - time schedule'!JL26","v":0},{"$f":"'K80 - time schedule'!JM26","v":0},{"$f":"'K80 - time schedule'!JN26","v":0},{"$f":"'K80 - time schedule'!JO26","v":0},{"$f":"'K80 - time schedule'!JP26","v":0},{"$f":"'K80 - time schedule'!JQ26","v":0},{"$f":"'K80 - time schedule'!JR26","v":0},{"$f":"'K80 - time schedule'!JS26","v":0},{"$f":"'K80 - time schedule'!JT26","v":0},{"$f":"'K80 - time schedule'!JU26","v":0},{"$f":"'K80 - time schedule'!JV26","v":0},{"$f":"'K80 - time schedule'!JW26","v":0},{"$f":"'K80 - time schedule'!JX26","v":0},{"$f":"'K80 - time schedule'!JY26","v":0},{"$f":"'K80 - time schedule'!JZ26","v":0},{"$f":"'K80 - time schedule'!KA26","v":0},{"$f":"'K80 - time schedule'!KB26","v":0},{"$f":"'K80 - time schedule'!KC26","v":0},{"$f":"'K80 - time schedule'!KD26","v":0},{"$f":"'K80 - time schedule'!KE26","v":0},{"$f":"'K80 - time schedule'!KF26","v":0},{"$f":"'K80 - time schedule'!KG26","v":0},{"$f":"'K80 - time schedule'!KH26","v":0},{"$f":"'K80 - time schedule'!KI26","v":0},{"$f":"'K80 - time schedule'!KJ26","v":0},{"$f":"'K80 - time schedule'!KK26","v":0},{"$f":"'K80 - time schedule'!KL26","v":0},{"$f":"'K80 - time schedule'!KM26","v":0},{"$f":"'K80 - time schedule'!KN26","v":0},{"$f":"'K80 - time schedule'!KO26","v":0},{"$f":"'K80 - time schedule'!KP26","v":0},{"$f":"'K80 - time schedule'!KQ26","v":0},{"$f":"'K80 - time schedule'!KR26","v":0},{"$f":"'K80 - time schedule'!KS26","v":0},{"$f":"'K80 - time schedule'!KT26","v":0}]
["Boiler room K80 - overheating","K80",{"$f":"'K80 - time schedule'!G28","v":0},{"$f":"'K80 - time schedule'!H28","v":0},{"$f":"'K80 - time schedule'!I28","v":0},{"$f":"'K80 - time schedule'!J28","v":0},{"$f":"'K80 - time schedule'!K28","v":0},{"$f":"'K80 - time schedule'!L28","v":0},{"$f":"'K80 - time schedule'!M28","v":0},{"$f":"'K80 - time schedule'!N28","v":0},{"$f":"'K80 - time schedule'!O28","v":0},{"$f":"'K80 - time schedule'!P28","v":0},{"$f":"'K80 - time schedule'!Q28","v":0},{"$f":"'K80 - time schedule'!R28","v":0},{"$f":"'K80 - time schedule'!S28","v":0},{"$f":"'K80 - time schedule'!T28","v":0},{"$f":"'K80 - time schedule'!U28","v":0},{"$f":"'K80 - time schedule'!V28","v":0},{"$f":"'K80 - time schedule'!W28","v":0},{"$f":"'K80 - time schedule'!X28","v":0},{"$f":"'K80 - time schedule'!Y28","v":0},{"$f":"'K80 - time schedule'!Z28","v":0},{"$f":"'K80 - time schedule'!AA28","v":0},{"$f":"'K80 - time schedule'!AB28","v":0},{"$f":"'K80 - time schedule'!AC28","v":0},{"$f":"'K80 - time schedule'!AD28","v":0},{"$f":"'K80 - time schedule'!AE28","v":0},{"$f":"'K80 - time schedule'!AF28","v":0},{"$f":"'K80 - time schedule'!AG28","v":0},{"$f":"'K80 - time schedule'!AH28","v":0},{"$f":"'K80 - time schedule'!AI28","v":0},{"$f":"'K80 - time schedule'!AJ28","v":0},{"$f":"'K80 - time schedule'!AK28","v":0},{"$f":"'K80 - time schedule'!AL28","v":0},{"$f":"'K80 - time schedule'!AM28","v":0},{"$f":"'K80 - time schedule'!AN28","v":0},{"$f":"'K80 - time schedule'!AO28","v":0},{"$f":"'K80 - time schedule'!AP28","v":0},{"$f":"'K80 - time schedule'!AQ28","v":0},{"$f":"'K80 - time schedule'!AR28","v":0},{"$f":"'K80 - time schedule'!AS28","v":0},{"$f":"'K80 - time schedule'!AT28","v":0},{"$f":"'K80 - time schedule'!AU28","v":0},{"$f":"'K80 - time schedule'!AV28","v":0},{"$f":"'K80 - time schedule'!AW28","v":0},{"$f":"'K80 - time schedule'!AX28","v":0},{"$f":"'K80 - time schedule'!AY28","v":0},{"$f":"'K80 - time schedule'!AZ28","v":0},{"$f":"'K80 - time schedule'!BA28","v":0},{"$f":"'K80 - time schedule'!BB28","v":0},{"$f":"'K80 - time schedule'!BC28","v":0},{"$f":"'K80 - time schedule'!BD28","v":0},{"$f":"'K80 - time schedule'!BE28","v":0},{"$f":"'K80 - time schedule'!BF28","v":0},{"$f":"'K80 - time schedule'!BG28","v":0},{"$f":"'K80 - time schedule'!BH28","v":0},{"$f":"'K80 - time schedule'!BI28","v":0},{"$f":"'K80 - time schedule'!BJ28","v":0},{"$f":"'K80 - time schedule'!BK28","v":0},{"$f":"'K80 - time schedule'!BL28","v":0},{"$f":"'K80 - time schedule'!BM28","v":0},{"$f":"'K80 - time schedule'!BN28","v":0},{"$f":"'K80 - time schedule'!BO28","v":0},{"$f":"'K80 - time schedule'!BP28","v":0},{"$f":"'K80 - time schedule'!BQ28","v":0},{"$f":"'K80 - time schedule'!BR28","v":0},{"$f":"'K80 - time schedule'!BS28","v":0},{"$f":"'K80 - time schedule'!BT28","v":0},{"$f":"'K80 - time schedule'!BU28","v":0},{"$f":"'K80 - time schedule'!BV28","v":0},{"$f":"'K80 - time schedule'!BW28","v":0},{"$f":"'K80 - time schedule'!BX28","v":0},{"$f":"'K80 - time schedule'!BY28","v":0},{"$f":"'K80 - time schedule'!BZ28","v":0},{"$f":"'K80 - time schedule'!CA28","v":0},{"$f":"'K80 - time schedule'!CB28","v":0},{"$f":"'K80 - time schedule'!CC28","v":0},{"$f":"'K80 - time schedule'!CD28","v":0},{"$f":"'K80 - time schedule'!CE28","v":0},{"$f":"'K80 - time schedule'!CF28","v":0},{"$f":"'K80 - time schedule'!CG28","v":0},{"$f":"'K80 - time schedule'!CH28","v":0},{"$f":"'K80 - time schedule'!CI28","v":0},{"$f":"'K80 - time schedule'!CJ28","v":0},{"$f":"'K80 - time schedule'!CK28","v":0},{"$f":"'K80 - time schedule'!CL28","v":0},{"$f":"'K80 - time schedule'!CM28","v":0},{"$f":"'K80 - time schedule'!CN28","v":0},{"$f":"'K80 - time schedule'!CO28","v":0},{"$f":"'K80 - time schedule'!CP28","v":0},{"$f":"'K80 - time schedule'!CQ28","v":0},{"$f":"'K80 - time schedule'!CR28","v":0},{"$f":"'K80 - time schedule'!CS28","v":0},{"$f":"'K80 - time schedule'!CT28","v":0},{"$f":"'K80 - time schedule'!CU28","v":0},{"$f":"'K80 - time schedule'!CV28","v":0},{"$f":"'K80 - time schedule'!CW28","v":0},{"$f":"'K80 - time schedule'!CX28","v":0},{"$f":"'K80 - time schedule'!CY28","v":0},{"$f":"'K80 - time schedule'!CZ28","v":0},{"$f":"'K80 - time schedule'!DA28","v":0},{"$f":"'K80 - time schedule'!DB28","v":0},{"$f":"'K80 - time schedule'!DC28","v":0},{"$f":"'K80 - time schedule'!DD28","v":0},{"$f":"'K80 - time schedule'!DE28","v":0},{"$f":"'K80 - time schedule'!DF28","v":0},{"$f":"'K80 - time schedule'!DG28","v":0},{"$f":"'K80 - time schedule'!DH28","v":0},{"$f":"'K80 - time schedule'!DI28","v":0},{"$f":"'K80 - time schedule'!DJ28","v":0},{"$f":"'K80 - time schedule'!DK28","v":0},{"$f":"'K80 - time schedule'!DL28","v":0},{"$f":"'K80 - time schedule'!DM28","v":0},{"$f":"'K80 - time schedule'!DN28","v":0},{"$f":"'K80 - time schedule'!DO28","v":0},{"$f":"'K80 - time schedule'!DP28","v":0},{"$f":"'K80 - time schedule'!DQ28","v":0},{"$f":"'K80 - time schedule'!DR28","v":0},{"$f":"'K80 - time schedule'!DS28","v":0},{"$f":"'K80 - time schedule'!DT28","v":0},{"$f":"'K80 - time schedule'!DU28","v":0},{"$f":"'K80 - time schedule'!DV28","v":0},{"$f":"'K80 - time schedule'!DW28","v":0},{"$f":"'K80 - time schedule'!DX28","v":0},{"$f":"'K80 - time schedule'!DY28","v":0},{"$f":"'K80 - time schedule'!DZ28","v":0},{"$f":"'K80 - time schedule'!EA28","v":0},{"$f":"'K80 - time schedule'!EB28","v":0},{"$f":"'K80 - time schedule'!EC28","v":0},{"$f":"'K80 - time schedule'!ED28","v":0},{"$f":"'K80 - time schedule'!EE28","v":0},{"$f":"'K80 - time schedule'!EF28","v":0},{"$f":"'K80 - time schedule'!EG28","v":0},{"$f":"'K80 - time schedule'!EH28","v":0},{"$f":"'K80 - time schedule'!EI28","v":0},{"$f":"'K80 - time schedule'!EJ28","v":0},{"$f":"'K80 - time schedule'!EK28","v":0},{"$f":"'K80 - time schedule'!EL28","v":0},{"$f":"'K80 - time schedule'!EM28","v":0},{"$f":"'K80 - time schedule'!EN28","v":0},{"$f":"'K80 - time schedule'!EO28","v":0},{"$f":"'K80 - time schedule'!EP28","v":0},{"$f":"'K80 - time schedule'!EQ28","v":0},{"$f":"'K80 - time schedule'!ER28","v":0},{"$f":"'K80 - time schedule'!ES28","v":0},{"$f":"'K80 - time schedule'!ET28","v":0},{"$f":"'K80 - time schedule'!EU28","v":0},{"$f":"'K80 - time schedule'!EV28","v":0},{"$f":"'K80 - time schedule'!EW28","v":0},{"$f":"'K80 - time schedule'!EX28","v":0},{"$f":"'K80 - time schedule'!EY28","v":0},{"$f":"'K80 - time schedule'!EZ28","v":0},{"$f":"'K80 - time schedule'!FA28","v":0},{"$f":"'K80 - time schedule'!FB28","v":0},{"$f":"'K80 - time schedule'!FC28","v":0},{"$f":"'K80 - time schedule'!FD28","v":0},{"$f":"'K80 - time schedule'!FE28","v":0},{"$f":"'K80 - time schedule'!FF28","v":0},{"$f":"'K80 - time schedule'!FG28","v":0},{"$f":"'K80 - time schedule'!FH28","v":0},{"$f":"'K80 - time schedule'!FI28","v":0},{"$f":"'K80 - time schedule'!FJ28","v":0},{"$f":"'K80 - time schedule'!FK28","v":0},{"$f":"'K80 - time schedule'!FL28","v":0},{"$f":"'K80 - time schedule'!FM28","v":0},{"$f":"'K80 - time schedule'!FN28","v":0},{"$f":"'K80 - time schedule'!FO28","v":0},{"$f":"'K80 - time schedule'!FP28","v":0},{"$f":"'K80 - time schedule'!FQ28","v":0},{"$f":"'K80 - time schedule'!FR28","v":0},{"$f":"'K80 - time schedule'!FS28","v":0},{"$f":"'K80 - time schedule'!FT28","v":0},{"$f":"'K80 - time schedule'!FU28","v":0},{"$f":"'K80 - time schedule'!FV28","v":0},{"$f":"'K80 - time schedule'!FW28","v":0},{"$f":"'K80 - time schedule'!FX28","v":0},{"$f":"'K80 - time schedule'!FY28","v":0},{"$f":"'K80 - time schedule'!FZ28","v":0},{"$f":"'K80 - time schedule'!GA28","v":0},{"$f":"'K80 - time schedule'!GB28","v":0},{"$f":"'K80 - time schedule'!GC28","v":0},{"$f":"'K80 - time schedule'!GD28","v":0},{"$f":"'K80 - time schedule'!GE28","v":0},{"$f":"'K80 - time schedule'!GF28","v":0},{"$f":"'K80 - time schedule'!GG28","v":0},{"$f":"'K80 - time schedule'!GH28","v":0},{"$f":"'K80 - time schedule'!GI28","v":0},{"$f":"'K80 - time schedule'!GJ28","v":0},{"$f":"'K80 - time schedule'!GK28","v":0},{"$f":"'K80 - time schedule'!GL28","v":0},{"$f":"'K80 - time schedule'!GM28","v":0},{"$f":"'K80 - time schedule'!GN28","v":0},{"$f":"'K80 - time schedule'!GO28","v":0},{"$f":"'K80 - time schedule'!GP28","v":0},{"$f":"'K80 - time schedule'!GQ28","v":0},{"$f":"'K80 - time schedule'!GR28","v":0},{"$f":"'K80 - time schedule'!GS28","v":0},{"$f":"'K80 - time schedule'!GT28","v":0},{"$f":"'K80 - time schedule'!GU28","v":0},{"$f":"'K80 - time schedule'!GV28","v":0},{"$f":"'K80 - time schedule'!GW28","v":0},{"$f":"'K80 - time schedule'!GX28","v":0},{"$f":"'K80 - time schedule'!GY28","v":0},{"$f":"'K80 - time schedule'!GZ28","v":0},{"$f":"'K80 - time schedule'!HA28","v":0},{"$f":"'K80 - time schedule'!HB28","v":0},{"$f":"'K80 - time schedule'!HC28","v":0},{"$f":"'K80 - time schedule'!HD28","v":0},{"$f":"'K80 - time schedule'!HE28","v":0},{"$f":"'K80 - time schedule'!HF28","v":0},{"$f":"'K80 - time schedule'!HG28","v":0},{"$f":"'K80 - time schedule'!HH28","v":0},{"$f":"'K80 - time schedule'!HI28","v":0},{"$f":"'K80 - time schedule'!HJ28","v":0},{"$f":"'K80 - time schedule'!HK28","v":0},{"$f":"'K80 - time schedule'!HL28","v":0},{"$f":"'K80 - time schedule'!HM28","v":0},{"$f":"'K80 - time schedule'!HN28","v":0},{"$f":"'K80 - time schedule'!HO28","v":0},{"$f":"'K80 - time schedule'!HP28","v":0},{"$f":"'K80 - time schedule'!HQ28","v":0},{"$f":"'K80 - time schedule'!HR28","v":0},{"$f":"'K80 - time schedule'!HS28","v":0},{"$f":"'K80 - time schedule'!HT28","v":0},{"$f":"'K80 - time schedule'!HU28","v":0},{"$f":"'K80 - time schedule'!HV28","v":0},{"$f":"'K80 - time schedule'!HW28","v":0},{"$f":"'K80 - time schedule'!HX28","v":0},{"$f":"'K80 - time schedule'!HY28","v":0},{"$f":"'K80 - time schedule'!HZ28","v":0},{"$f":"'K80 - time schedule'!IA28","v":0},{"$f":"'K80 - time schedule'!IB28","v":0},{"$f":"'K80 - time schedule'!IC28","v":0},{"$f":"'K80 - time schedule'!ID28","v":0},{"$f":"'K80 - time schedule'!IE28","v":0},{"$f":"'K80 - time schedule'!IF28","v":0},{"$f":"'K80 - time schedule'!IG28","v":0},{"$f":"'K80 - time schedule'!IH28","v":0},{"$f":"'K80 - time schedule'!II28","v":0},{"$f":"'K80 - time schedule'!IJ28","v":0},{"$f":"'K80 - time schedule'!IK28","v":0},{"$f":"'K80 - time schedule'!IL28","v":0},{"$f":"'K80 - time schedule'!IM28","v":0},{"$f":"'K80 - time schedule'!IN28","v":0},{"$f":"'K80 - time schedule'!IO28","v":0},{"$f":"'K80 - time schedule'!IP28","v":0},{"$f":"'K80 - time schedule'!IQ28","v":0},{"$f":"'K80 - time schedule'!IR28","v":0},{"$f":"'K80 - time schedule'!IS28","v":0},{"$f":"'K80 - time schedule'!IT28","v":0},{"$f":"'K80 - time schedule'!IU28","v":0},{"$f":"'K80 - time schedule'!IV28","v":0},{"$f":"'K80 - time schedule'!IW28","v":0},{"$f":"'K80 - time schedule'!IX28","v":0},{"$f":"'K80 - time schedule'!IY28","v":0},{"$f":"'K80 - time schedule'!IZ28","v":0},{"$f":"'K80 - time schedule'!JA28","v":0},{"$f":"'K80 - time schedule'!JB28","v":0},{"$f":"'K80 - time schedule'!JC28","v":0},{"$f":"'K80 - time schedule'!JD28","v":0},{"$f":"'K80 - time schedule'!JE28","v":0},{"$f":"'K80 - time schedule'!JF28","v":0},{"$f":"'K80 - time schedule'!JG28","v":0},{"$f":"'K80 - time schedule'!JH28","v":0},{"$f":"'K80 - time schedule'!JI28","v":0},{"$f":"'K80 - time schedule'!JJ28","v":0},{"$f":"'K80 - time schedule'!JK28","v":0},{"$f":"'K80 - time schedule'!JL28","v":0},{"$f":"'K80 - time schedule'!JM28","v":0},{"$f":"'K80 - time schedule'!JN28","v":0},{"$f":"'K80 - time schedule'!JO28","v":0},{"$f":"'K80 - time schedule'!JP28","v":0},{"$f":"'K80 - time schedule'!JQ28","v":0},{"$f":"'K80 - time schedule'!JR28","v":0},{"$f":"'K80 - time schedule'!JS28","v":0},{"$f":"'K80 - time schedule'!JT28","v":0},{"$f":"'K80 - time schedule'!JU28","v":0},{"$f":"'K80 - time schedule'!JV28","v":0},{"$f":"'K80 - time schedule'!JW28","v":0},{"$f":"'K80 - time schedule'!JX28","v":0},{"$f":"'K80 - time schedule'!JY28","v":0},{"$f":"'K80 - time schedule'!JZ28","v":0},{"$f":"'K80 - time schedule'!KA28","v":0},{"$f":"'K80 - time schedule'!KB28","v":0},{"$f":"'K80 - time schedule'!KC28","v":0},{"$f":"'K80 - time schedule'!KD28","v":0},{"$f":"'K80 - time schedule'!KE28","v":0},{"$f":"'K80 - time schedule'!KF28","v":0},{"$f":"'K80 - time schedule'!KG28","v":0},{"$f":"'K80 - time schedule'!KH28","v":0},{"$f":"'K80 - time schedule'!KI28","v":0},{"$f":"'K80 - time schedule'!KJ28","v":0},{"$f":"'K80 - time schedule'!KK28","v":0},{"$f":"'K80 - time schedule'!KL28","v":0},{"$f":"'K80 - time schedule'!KM28","v":0},{"$f":"'K80 - time schedule'!KN28","v":0},{"$f":"'K80 - time schedule'!KO28","v":0},{"$f":"'K80 - time schedule'!KP28","v":0},{"$f":"'K80 - time schedule'!KQ28","v":0},{"$f":"'K80 - time schedule'!KR28","v":0},{"$f":"'K80 - time schedule'!KS28","v":0},{"$f":"'K80 - time schedule'!KT28","v":0}]
["Boiler room K80 - economizer","K80",{"$f":"'K80 - time schedule'!G30","v":0},{"$f":"'K80 - time schedule'!H30","v":0},{"$f":"'K80 - time schedule'!I30","v":0},{"$f":"'K80 - time schedule'!J30","v":0},{"$f":"'K80 - time schedule'!K30","v":0},{"$f":"'K80 - time schedule'!L30","v":0},{"$f":"'K80 - time schedule'!M30","v":0},{"$f":"'K80 - time schedule'!N30","v":0},{"$f":"'K80 - time schedule'!O30","v":0},{"$f":"'K80 - time schedule'!P30","v":0},{"$f":"'K80 - time schedule'!Q30","v":0},{"$f":"'K80 - time schedule'!R30","v":0},{"$f":"'K80 - time schedule'!S30","v":0},{"$f":"'K80 - time schedule'!T30","v":0},{"$f":"'K80 - time schedule'!U30","v":0},{"$f":"'K80 - time schedule'!V30","v":0},{"$f":"'K80 - time schedule'!W30","v":0},{"$f":"'K80 - time schedule'!X30","v":0},{"$f":"'K80 - time schedule'!Y30","v":0},{"$f":"'K80 - time schedule'!Z30","v":0},{"$f":"'K80 - time schedule'!AA30","v":0},{"$f":"'K80 - time schedule'!AB30","v":0},{"$f":"'K80 - time schedule'!AC30","v":0},{"$f":"'K80 - time schedule'!AD30","v":0},{"$f":"'K80 - time schedule'!AE30","v":0},{"$f":"'K80 - time schedule'!AF30","v":0},{"$f":"'K80 - time schedule'!AG30","v":0},{"$f":"'K80 - time schedule'!AH30","v":0},{"$f":"'K80 - time schedule'!AI30","v":0},{"$f":"'K80 - time schedule'!AJ30","v":0},{"$f":"'K80 - time schedule'!AK30","v":0},{"$f":"'K80 - time schedule'!AL30","v":0},{"$f":"'K80 - time schedule'!AM30","v":0},{"$f":"'K80 - time schedule'!AN30","v":0},{"$f":"'K80 - time schedule'!AO30","v":0},{"$f":"'K80 - time schedule'!AP30","v":0},{"$f":"'K80 - time schedule'!AQ30","v":0},{"$f":"'K80 - time schedule'!AR30","v":0},{"$f":"'K80 - time schedule'!AS30","v":0},{"$f":"'K80 - time schedule'!AT30","v":0},{"$f":"'K80 - time schedule'!AU30","v":0},{"$f":"'K80 - time schedule'!AV30","v":0},{"$f":"'K80 - time schedule'!AW30","v":0},{"$f":"'K80 - time schedule'!AX30","v":0},{"$f":"'K80 - time schedule'!AY30","v":0},{"$f":"'K80 - time schedule'!AZ30","v":0},{"$f":"'K80 - time schedule'!BA30","v":0},{"$f":"'K80 - time schedule'!BB30","v":0},{"$f":"'K80 - time schedule'!BC30","v":0},{"$f":"'K80 - time schedule'!BD30","v":0},{"$f":"'K80 - time schedule'!BE30","v":0},{"$f":"'K80 - time schedule'!BF30","v":0},{"$f":"'K80 - time schedule'!BG30","v":0},{"$f":"'K80 - time schedule'!BH30","v":0},{"$f":"'K80 - time schedule'!BI30","v":0},{"$f":"'K80 - time schedule'!BJ30","v":0},{"$f":"'K80 - time schedule'!BK30","v":0},{"$f":"'K80 - time schedule'!BL30","v":0},{"$f":"'K80 - time schedule'!BM30","v":0},{"$f":"'K80 - time schedule'!BN30","v":0},{"$f":"'K80 - time schedule'!BO30","v":0},{"$f":"'K80 - time schedule'!BP30","v":0},{"$f":"'K80 - time schedule'!BQ30","v":0},{"$f":"'K80 - time schedule'!BR30","v":0},{"$f":"'K80 - time schedule'!BS30","v":0},{"$f":"'K80 - time schedule'!BT30","v":0},{"$f":"'K80 - time schedule'!BU30","v":0},{"$f":"'K80 - time schedule'!BV30","v":0},{"$f":"'K80 - time schedule'!BW30","v":0},{"$f":"'K80 - time schedule'!BX30","v":0},{"$f":"'K80 - time schedule'!BY30","v":0},{"$f":"'K80 - time schedule'!BZ30","v":0},{"$f":"'K80 - time schedule'!CA30","v":0},{"$f":"'K80 - time schedule'!CB30","v":0},{"$f":"'K80 - time schedule'!CC30","v":0},{"$f":"'K80 - time schedule'!CD30","v":0},{"$f":"'K80 - time schedule'!CE30","v":0},{"$f":"'K80 - time schedule'!CF30","v":0},{"$f":"'K80 - time schedule'!CG30","v":0},{"$f":"'K80 - time schedule'!CH30","v":0},{"$f":"'K80 - time schedule'!CI30","v":0},{"$f":"'K80 - time schedule'!CJ30","v":0},{"$f":"'K80 - time schedule'!CK30","v":0},{"$f":"'K80 - time schedule'!CL30","v":0},{"$f":"'K80 - time schedule'!CM30","v":0},{"$f":"'K80 - time schedule'!CN30","v":0},{"$f":"'K80 - time schedule'!CO30","v":0},{"$f":"'K80 - time schedule'!CP30","v":0},{"$f":"'K80 - time schedule'!CQ30","v":0},{"$f":"'K80 - time schedule'!CR30","v":0},{"$f":"'K80 - time schedule'!CS30","v":0},{"$f":"'K80 - time schedule'!CT30","v":0},{"$f":"'K80 - time schedule'!CU30","v":0},{"$f":"'K80 - time schedule'!CV30","v":0},{"$f":"'K80 - time schedule'!CW30","v":0},{"$f":"'K80 - time schedule'!CX30","v":0},{"$f":"'K80 - time schedule'!CY30","v":0},{"$f":"'K80 - time schedule'!CZ30","v":0},{"$f":"'K80 - time schedule'!DA30","v":0},{"$f":"'K80 - time schedule'!DB30","v":0},{"$f":"'K80 - time schedule'!DC30","v":0},{"$f":"'K80 - time schedule'!DD30","v":0},{"$f":"'K80 - time schedule'!DE30","v":0},{"$f":"'K80 - time schedule'!DF30","v":0},{"$f":"'K80 - time schedule'!DG30","v":0},{"$f":"'K80 - time schedule'!DH30","v":0},{"$f":"'K80 - time schedule'!DI30","v":0},{"$f":"'K80 - time schedule'!DJ30","v":0},{"$f":"'K80 - time schedule'!DK30","v":0},{"$f":"'K80 - time schedule'!DL30","v":0},{"$f":"'K80 - time schedule'!DM30","v":0},{"$f":"'K80 - time schedule'!DN30","v":0},{"$f":"'K80 - time schedule'!DO30","v":0},{"$f":"'K80 - time schedule'!DP30","v":0},{"$f":"'K80 - time schedule'!DQ30","v":0},{"$f":"'K80 - time schedule'!DR30","v":0},{"$f":"'K80 - time schedule'!DS30","v":0},{"$f":"'K80 - time schedule'!DT30","v":0},{"$f":"'K80 - time schedule'!DU30","v":0},{"$f":"'K80 - time schedule'!DV30","v":0},{"$f":"'K80 - time schedule'!DW30","v":0},{"$f":"'K80 - time schedule'!DX30","v":0},{"$f":"'K80 - time schedule'!DY30","v":0},{"$f":"'K80 - time schedule'!DZ30","v":0},{"$f":"'K80 - time schedule'!EA30","v":0},{"$f":"'K80 - time schedule'!EB30","v":0},{"$f":"'K80 - time schedule'!EC30","v":0},{"$f":"'K80 - time schedule'!ED30","v":0},{"$f":"'K80 - time schedule'!EE30","v":0},{"$f":"'K80 - time schedule'!EF30","v":0},{"$f":"'K80 - time schedule'!EG30","v":0},{"$f":"'K80 - time schedule'!EH30","v":0},{"$f":"'K80 - time schedule'!EI30","v":0},{"$f":"'K80 - time schedule'!EJ30","v":0},{"$f":"'K80 - time schedule'!EK30","v":0},{"$f":"'K80 - time schedule'!EL30","v":0},{"$f":"'K80 - time schedule'!EM30","v":0},{"$f":"'K80 - time schedule'!EN30","v":0},{"$f":"'K80 - time schedule'!EO30","v":0},{"$f":"'K80 - time schedule'!EP30","v":0},{"$f":"'K80 - time schedule'!EQ30","v":0},{"$f":"'K80 - time schedule'!ER30","v":0},{"$f":"'K80 - time schedule'!ES30","v":0},{"$f":"'K80 - time schedule'!ET30","v":0},{"$f":"'K80 - time schedule'!EU30","v":0},{"$f":"'K80 - time schedule'!EV30","v":0},{"$f":"'K80 - time schedule'!EW30","v":0},{"$f":"'K80 - time schedule'!EX30","v":0},{"$f":"'K80 - time schedule'!EY30","v":0},{"$f":"'K80 - time schedule'!EZ30","v":0},{"$f":"'K80 - time schedule'!FA30","v":0},{"$f":"'K80 - time schedule'!FB30","v":0},{"$f":"'K80 - time schedule'!FC30","v":0},{"$f":"'K80 - time schedule'!FD30","v":0},{"$f":"'K80 - time schedule'!FE30","v":0},{"$f":"'K80 - time schedule'!FF30","v":0},{"$f":"'K80 - time schedule'!FG30","v":0},{"$f":"'K80 - time schedule'!FH30","v":0},{"$f":"'K80 - time schedule'!FI30","v":0},{"$f":"'K80 - time schedule'!FJ30","v":0},{"$f":"'K80 - time schedule'!FK30","v":0},{"$f":"'K80 - time schedule'!FL30","v":0},{"$f":"'K80 - time schedule'!FM30","v":0},{"$f":"'K80 - time schedule'!FN30","v":0},{"$f":"'K80 - time schedule'!FO30","v":0},{"$f":"'K80 - time schedule'!FP30","v":0},{"$f":"'K80 - time schedule'!FQ30","v":0},{"$f":"'K80 - time schedule'!FR30","v":0},{"$f":"'K80 - time schedule'!FS30","v":0},{"$f":"'K80 - time schedule'!FT30","v":0},{"$f":"'K80 - time schedule'!FU30","v":0},{"$f":"'K80 - time schedule'!FV30","v":0},{"$f":"'K80 - time schedule'!FW30","v":0},{"$f":"'K80 - time schedule'!FX30","v":0},{"$f":"'K80 - time schedule'!FY30","v":0},{"$f":"'K80 - time schedule'!FZ30","v":0},{"$f":"'K80 - time schedule'!GA30","v":0},{"$f":"'K80 - time schedule'!GB30","v":0},{"$f":"'K80 - time schedule'!GC30","v":0},{"$f":"'K80 - time schedule'!GD30","v":0},{"$f":"'K80 - time schedule'!GE30","v":0},{"$f":"'K80 - time schedule'!GF30","v":0},{"$f":"'K80 - time schedule'!GG30","v":0},{"$f":"'K80 - time schedule'!GH30","v":0},{"$f":"'K80 - time schedule'!GI30","v":0},{"$f":"'K80 - time schedule'!GJ30","v":0},{"$f":"'K80 - time schedule'!GK30","v":0},{"$f":"'K80 - time schedule'!GL30","v":0},{"$f":"'K80 - time schedule'!GM30","v":0},{"$f":"'K80 - time schedule'!GN30","v":0},{"$f":"'K80 - time schedule'!GO30","v":0},{"$f":"'K80 - time schedule'!GP30","v":0},{"$f":"'K80 - time schedule'!GQ30","v":0},{"$f":"'K80 - time schedule'!GR30","v":0},{"$f":"'K80 - time schedule'!GS30","v":0},{"$f":"'K80 - time schedule'!GT30","v":0},{"$f":"'K80 - time schedule'!GU30","v":0},{"$f":"'K80 - time schedule'!GV30","v":0},{"$f":"'K80 - time schedule'!GW30","v":0},{"$f":"'K80 - time schedule'!GX30","v":0},{"$f":"'K80 - time schedule'!GY30","v":0},{"$f":"'K80 - time schedule'!GZ30","v":0},{"$f":"'K80 - time schedule'!HA30","v":0},{"$f":"'K80 - time schedule'!HB30","v":0},{"$f":"'K80 - time schedule'!HC30","v":0},{"$f":"'K80 - time schedule'!HD30","v":0},{"$f":"'K80 - time schedule'!HE30","v":0},{"$f":"'K80 - time schedule'!HF30","v":0},{"$f":"'K80 - time schedule'!HG30","v":0},{"$f":"'K80 - time schedule'!HH30","v":0},{"$f":"'K80 - time schedule'!HI30","v":0},{"$f":"'K80 - time schedule'!HJ30","v":0},{"$f":"'K80 - time schedule'!HK30","v":0},{"$f":"'K80 - time schedule'!HL30","v":0},{"$f":"'K80 - time schedule'!HM30","v":0},{"$f":"'K80 - time schedule'!HN30","v":0},{"$f":"'K80 - time schedule'!HO30","v":0},{"$f":"'K80 - time schedule'!HP30","v":0},{"$f":"'K80 - time schedule'!HQ30","v":0},{"$f":"'K80 - time schedule'!HR30","v":0},{"$f":"'K80 - time schedule'!HS30","v":0},{"$f":"'K80 - time schedule'!HT30","v":0},{"$f":"'K80 - time schedule'!HU30","v":0},{"$f":"'K80 - time schedule'!HV30","v":0},{"$f":"'K80 - time schedule'!HW30","v":0},{"$f":"'K80 - time schedule'!HX30","v":0},{"$f":"'K80 - time schedule'!HY30","v":0},{"$f":"'K80 - time schedule'!HZ30","v":0},{"$f":"'K80 - time schedule'!IA30","v":0},{"$f":"'K80 - time schedule'!IB30","v":0},{"$f":"'K80 - time schedule'!IC30","v":0},{"$f":"'K80 - time schedule'!ID30","v":0},{"$f":"'K80 - time schedule'!IE30","v":0},{"$f":"'K80 - time schedule'!IF30","v":0},{"$f":"'K80 - time schedule'!IG30","v":0},{"$f":"'K80 - time schedule'!IH30","v":0},{"$f":"'K80 - time schedule'!II30","v":0},{"$f":"'K80 - time schedule'!IJ30","v":0},{"$f":"'K80 - time schedule'!IK30","v":0},{"$f":"'K80 - time schedule'!IL30","v":0},{"$f":"'K80 - time schedule'!IM30","v":0},{"$f":"'K80 - time schedule'!IN30","v":0},{"$f":"'K80 - time schedule'!IO30","v":0},{"$f":"'K80 - time schedule'!IP30","v":0},{"$f":"'K80 - time schedule'!IQ30","v":0},{"$f":"'K80 - time schedule'!IR30","v":0},{"$f":"'K80 - time schedule'!IS30","v":0},{"$f":"'K80 - time schedule'!IT30","v":0},{"$f":"'K80 - time schedule'!IU30","v":0},{"$f":"'K80 - time schedule'!IV30","v":0},{"$f":"'K80 - time schedule'!IW30","v":0},{"$f":"'K80 - time schedule'!IX30","v":0},{"$f":"'K80 - time schedule'!IY30","v":0},{"$f":"'K80 - time schedule'!IZ30","v":0},{"$f":"'K80 - time schedule'!JA30","v":0},{"$f":"'K80 - time schedule'!JB30","v":0},{"$f":"'K80 - time schedule'!JC30","v":0},{"$f":"'K80 - time schedule'!JD30","v":0},{"$f":"'K80 - time schedule'!JE30","v":0},{"$f":"'K80 - time schedule'!JF30","v":0},{"$f":"'K80 - time schedule'!JG30","v":0},{"$f":"'K80 - time schedule'!JH30","v":0},{"$f":"'K80 - time schedule'!JI30","v":0},{"$f":"'K80 - time schedule'!JJ30","v":0},{"$f":"'K80 - time schedule'!JK30","v":0},{"$f":"'K80 - time schedule'!JL30","v":0},{"$f":"'K80 - time schedule'!JM30","v":0},{"$f":"'K80 - time schedule'!JN30","v":0},{"$f":"'K80 - time schedule'!JO30","v":0},{"$f":"'K80 - time schedule'!JP30","v":0},{"$f":"'K80 - time schedule'!JQ30","v":0},{"$f":"'K80 - time schedule'!JR30","v":0},{"$f":"'K80 - time schedule'!JS30","v":0},{"$f":"'K80 - time schedule'!JT30","v":0},{"$f":"'K80 - time schedule'!JU30","v":0},{"$f":"'K80 - time schedule'!JV30","v":0},{"$f":"'K80 - time schedule'!JW30","v":0},{"$f":"'K80 - time schedule'!JX30","v":0},{"$f":"'K80 - time schedule'!JY30","v":0},{"$f":"'K80 - time schedule'!JZ30","v":0},{"$f":"'K80 - time schedule'!KA30","v":0},{"$f":"'K80 - time schedule'!KB30","v":0},{"$f":"'K80 - time schedule'!KC30","v":0},{"$f":"'K80 - time schedule'!KD30","v":0},{"$f":"'K80 - time schedule'!KE30","v":0},{"$f":"'K80 - time schedule'!KF30","v":0},{"$f":"'K80 - time schedule'!KG30","v":0},{"$f":"'K80 - time schedule'!KH30","v":0},{"$f":"'K80 - time schedule'!KI30","v":0},{"$f":"'K80 - time schedule'!KJ30","v":0},{"$f":"'K80 - time schedule'!KK30","v":0},{"$f":"'K80 - time schedule'!KL30","v":0},{"$f":"'K80 - time schedule'!KM30","v":0},{"$f":"'K80 - time schedule'!KN30","v":0},{"$f":"'K80 - time schedule'!KO30","v":0},{"$f":"'K80 - time schedule'!KP30","v":0},{"$f":"'K80 - time schedule'!KQ30","v":0},{"$f":"'K80 - time schedule'!KR30","v":0},{"$f":"'K80 - time schedule'!KS30","v":0},{"$f":"'K80 - time schedule'!KT30","v":0}]
["Boiler room K80 - lining","K80",{"$f":"'K80 - time schedule'!G32","v":0},{"$f":"'K80 - time schedule'!H32","v":0},{"$f":"'K80 - time schedule'!I32","v":0},{"$f":"'K80 - time schedule'!J32","v":0},{"$f":"'K80 - time schedule'!K32","v":0},{"$f":"'K80 - time schedule'!L32","v":0},{"$f":"'K80 - time schedule'!M32","v":0},{"$f":"'K80 - time schedule'!N32","v":0},{"$f":"'K80 - time schedule'!O32","v":0},{"$f":"'K80 - time schedule'!P32","v":0},{"$f":"'K80 - time schedule'!Q32","v":0},{"$f":"'K80 - time schedule'!R32","v":0},{"$f":"'K80 - time schedule'!S32","v":0},{"$f":"'K80 - time schedule'!T32","v":0},{"$f":"'K80 - time schedule'!U32","v":0},{"$f":"'K80 - time schedule'!V32","v":0},{"$f":"'K80 - time schedule'!W32","v":0},{"$f":"'K80 - time schedule'!X32","v":0},{"$f":"'K80 - time schedule'!Y32","v":0},{"$f":"'K80 - time schedule'!Z32","v":0},{"$f":"'K80 - time schedule'!AA32","v":0},{"$f":"'K80 - time schedule'!AB32","v":0},{"$f":"'K80 - time schedule'!AC32","v":0},{"$f":"'K80 - time schedule'!AD32","v":0},{"$f":"'K80 - time schedule'!AE32","v":0},{"$f":"'K80 - time schedule'!AF32","v":0},{"$f":"'K80 - time schedule'!AG32","v":0},{"$f":"'K80 - time schedule'!AH32","v":0},{"$f":"'K80 - time schedule'!AI32","v":0},{"$f":"'K80 - time schedule'!AJ32","v":0},{"$f":"'K80 - time schedule'!AK32","v":0},{"$f":"'K80 - time schedule'!AL32","v":0},{"$f":"'K80 - time schedule'!AM32","v":0},{"$f":"'K80 - time schedule'!AN32","v":0},{"$f":"'K80 - time schedule'!AO32","v":0},{"$f":"'K80 - time schedule'!AP32","v":0},{"$f":"'K80 - time schedule'!AQ32","v":0},{"$f":"'K80 - time schedule'!AR32","v":0},{"$f":"'K80 - time schedule'!AS32","v":0},{"$f":"'K80 - time schedule'!AT32","v":0},{"$f":"'K80 - time schedule'!AU32","v":0},{"$f":"'K80 - time schedule'!AV32","v":0},{"$f":"'K80 - time schedule'!AW32","v":0},{"$f":"'K80 - time schedule'!AX32","v":0},{"$f":"'K80 - time schedule'!AY32","v":0},{"$f":"'K80 - time schedule'!AZ32","v":0},{"$f":"'K80 - time schedule'!BA32","v":0},{"$f":"'K80 - time schedule'!BB32","v":0},{"$f":"'K80 - time schedule'!BC32","v":0},{"$f":"'K80 - time schedule'!BD32","v":0},{"$f":"'K80 - time schedule'!BE32","v":0},{"$f":"'K80 - time schedule'!BF32","v":0},{"$f":"'K80 - time schedule'!BG32","v":0},{"$f":"'K80 - time schedule'!BH32","v":0},{"$f":"'K80 - time schedule'!BI32","v":0},{"$f":"'K80 - time schedule'!BJ32","v":0},{"$f":"'K80 - time schedule'!BK32","v":0},{"$f":"'K80 - time schedule'!BL32","v":0},{"$f":"'K80 - time schedule'!BM32","v":0},{"$f":"'K80 - time schedule'!BN32","v":0},{"$f":"'K80 - time schedule'!BO32","v":0},{"$f":"'K80 - time schedule'!BP32","v":0},{"$f":"'K80 - time schedule'!BQ32","v":0},{"$f":"'K80 - time schedule'!BR32","v":0},{"$f":"'K80 - time schedule'!BS32","v":0},{"$f":"'K80 - time schedule'!BT32","v":0},{"$f":"'K80 - time schedule'!BU32","v":0},{"$f":"'K80 - time schedule'!BV32","v":0},{"$f":"'K80 - time schedule'!BW32","v":0},{"$f":"'K80 - time schedule'!BX32","v":0},{"$f":"'K80 - time schedule'!BY32","v":0},{"$f":"'K80 - time schedule'!BZ32","v":0},{"$f":"'K80 - time schedule'!CA32","v":0},{"$f":"'K80 - time schedule'!CB32","v":0},{"$f":"'K80 - time schedule'!CC32","v":0},{"$f":"'K80 - time schedule'!CD32","v":0},{"$f":"'K80 - time schedule'!CE32","v":0},{"$f":"'K80 - time schedule'!CF32","v":0},{"$f":"'K80 - time schedule'!CG32","v":0},{"$f":"'K80 - time schedule'!CH32","v":0},{"$f":"'K80 - time schedule'!CI32","v":0},{"$f":"'K80 - time schedule'!CJ32","v":0},{"$f":"'K80 - time schedule'!CK32","v":0},{"$f":"'K80 - time schedule'!CL32","v":0},{"$f":"'K80 - time schedule'!CM32","v":0},{"$f":"'K80 - time schedule'!CN32","v":0},{"$f":"'K80 - time schedule'!CO32","v":0},{"$f":"'K80 - time schedule'!CP32","v":0},{"$f":"'K80 - time schedule'!CQ32","v":0},{"$f":"'K80 - time schedule'!CR32","v":0},{"$f":"'K80 - time schedule'!CS32","v":0},{"$f":"'K80 - time schedule'!CT32","v":0},{"$f":"'K80 - time schedule'!CU32","v":0},{"$f":"'K80 - time schedule'!CV32","v":0},{"$f":"'K80 - time schedule'!CW32","v":0},{"$f":"'K80 - time schedule'!CX32","v":0},{"$f":"'K80 - time schedule'!CY32","v":0},{"$f":"'K80 - time schedule'!CZ32","v":0},{"$f":"'K80 - time schedule'!DA32","v":0},{"$f":"'K80 - time schedule'!DB32","v":0},{"$f":"'K80 - time schedule'!DC32","v":0},{"$f":"'K80 - time schedule'!DD32","v":0},{"$f":"'K80 - time schedule'!DE32","v":0},{"$f":"'K80 - time schedule'!DF32","v":0},{"$f":"'K80 - time schedule'!DG32","v":0},{"$f":"'K80 - time schedule'!DH32","v":0},{"$f":"'K80 - time schedule'!DI32","v":0},{"$f":"'K80 - time schedule'!DJ32","v":0},{"$f":"'K80 - time schedule'!DK32","v":0},{"$f":"'K80 - time schedule'!DL32","v":0},{"$f":"'K80 - time schedule'!DM32","v":0},{"$f":"'K80 - time schedule'!DN32","v":0},{"$f":"'K80 - time schedule'!DO32","v":0},{"$f":"'K80 - time schedule'!DP32","v":0},{"$f":"'K80 - time schedule'!DQ32","v":0},{"$f":"'K80 - time schedule'!DR32","v":0},{"$f":"'K80 - time schedule'!DS32","v":0},{"$f":"'K80 - time schedule'!DT32","v":0},{"$f":"'K80 - time schedule'!DU32","v":0},{"$f":"'K80 - time schedule'!DV32","v":0},{"$f":"'K80 - time schedule'!DW32","v":0},{"$f":"'K80 - time schedule'!DX32","v":0},{"$f":"'K80 - time schedule'!DY32","v":0},{"$f":"'K80 - time schedule'!DZ32","v":0},{"$f":"'K80 - time schedule'!EA32","v":0},{"$f":"'K80 - time schedule'!EB32","v":0},{"$f":"'K80 - time schedule'!EC32","v":0},{"$f":"'K80 - time schedule'!ED32","v":0},{"$f":"'K80 - time schedule'!EE32","v":0},{"$f":"'K80 - time schedule'!EF32","v":0},{"$f":"'K80 - time schedule'!EG32","v":0},{"$f":"'K80 - time schedule'!EH32","v":0},{"$f":"'K80 - time schedule'!EI32","v":0},{"$f":"'K80 - time schedule'!EJ32","v":0},{"$f":"'K80 - time schedule'!EK32","v":0},{"$f":"'K80 - time schedule'!EL32","v":0},{"$f":"'K80 - time schedule'!EM32","v":0},{"$f":"'K80 - time schedule'!EN32","v":0},{"$f":"'K80 - time schedule'!EO32","v":0},{"$f":"'K80 - time schedule'!EP32","v":0},{"$f":"'K80 - time schedule'!EQ32","v":0},{"$f":"'K80 - time schedule'!ER32","v":0},{"$f":"'K80 - time schedule'!ES32","v":0},{"$f":"'K80 - time schedule'!ET32","v":0},{"$f":"'K80 - time schedule'!EU32","v":0},{"$f":"'K80 - time schedule'!EV32","v":0},{"$f":"'K80 - time schedule'!EW32","v":0},{"$f":"'K80 - time schedule'!EX32","v":0},{"$f":"'K80 - time schedule'!EY32","v":0},{"$f":"'K80 - time schedule'!EZ32","v":0},{"$f":"'K80 - time schedule'!FA32","v":0},{"$f":"'K80 - time schedule'!FB32","v":0},{"$f":"'K80 - time schedule'!FC32","v":0},{"$f":"'K80 - time schedule'!FD32","v":0},{"$f":"'K80 - time schedule'!FE32","v":0},{"$f":"'K80 - time schedule'!FF32","v":0},{"$f":"'K80 - time schedule'!FG32","v":0},{"$f":"'K80 - time schedule'!FH32","v":0},{"$f":"'K80 - time schedule'!FI32","v":0},{"$f":"'K80 - time schedule'!FJ32","v":0},{"$f":"'K80 - time schedule'!FK32","v":0},{"$f":"'K80 - time schedule'!FL32","v":0},{"$f":"'K80 - time schedule'!FM32","v":0},{"$f":"'K80 - time schedule'!FN32","v":0},{"$f":"'K80 - time schedule'!FO32","v":0},{"$f":"'K80 - time schedule'!FP32","v":0},{"$f":"'K80 - time schedule'!FQ32","v":0},{"$f":"'K80 - time schedule'!FR32","v":0},{"$f":"'K80 - time schedule'!FS32","v":0},{"$f":"'K80 - time schedule'!FT32","v":0},{"$f":"'K80 - time schedule'!FU32","v":0},{"$f":"'K80 - time schedule'!FV32","v":0},{"$f":"'K80 - time schedule'!FW32","v":0},{"$f":"'K80 - time schedule'!FX32","v":0},{"$f":"'K80 - time schedule'!FY32","v":0},{"$f":"'K80 - time schedule'!FZ32","v":0},{"$f":"'K80 - time schedule'!GA32","v":0},{"$f":"'K80 - time schedule'!GB32","v":0},{"$f":"'K80 - time schedule'!GC32","v":0},{"$f":"'K80 - time schedule'!GD32","v":0},{"$f":"'K80 - time schedule'!GE32","v":0},{"$f":"'K80 - time schedule'!GF32","v":0},{"$f":"'K80 - time schedule'!GG32","v":0},{"$f":"'K80 - time schedule'!GH32","v":0},{"$f":"'K80 - time schedule'!GI32","v":0},{"$f":"'K80 - time schedule'!GJ32","v":0},{"$f":"'K80 - time schedule'!GK32","v":0},{"$f":"'K80 - time schedule'!GL32","v":0},{"$f":"'K80 - time schedule'!GM32","v":0},{"$f":"'K80 - time schedule'!GN32","v":0},{"$f":"'K80 - time schedule'!GO32","v":0},{"$f":"'K80 - time schedule'!GP32","v":0},{"$f":"'K80 - time schedule'!GQ32","v":0},{"$f":"'K80 - time schedule'!GR32","v":0},{"$f":"'K80 - time schedule'!GS32","v":0},{"$f":"'K80 - time schedule'!GT32","v":0},{"$f":"'K80 - time schedule'!GU32","v":0},{"$f":"'K80 - time schedule'!GV32","v":0},{"$f":"'K80 - time schedule'!GW32","v":0},{"$f":"'K80 - time schedule'!GX32","v":0},{"$f":"'K80 - time schedule'!GY32","v":0},{"$f":"'K80 - time schedule'!GZ32","v":0},{"$f":"'K80 - time schedule'!HA32","v":0},{"$f":"'K80 - time schedule'!HB32","v":0},{"$f":"'K80 - time schedule'!HC32","v":0},{"$f":"'K80 - time schedule'!HD32","v":0},{"$f":"'K80 - time schedule'!HE32","v":0},{"$f":"'K80 - time schedule'!HF32","v":0},{"$f":"'K80 - time schedule'!HG32","v":0},{"$f":"'K80 - time schedule'!HH32","v":0},{"$f":"'K80 - time schedule'!HI32","v":0},{"$f":"'K80 - time schedule'!HJ32","v":0},{"$f":"'K80 - time schedule'!HK32","v":0},{"$f":"'K80 - time schedule'!HL32","v":0},{"$f":"'K80 - time schedule'!HM32","v":0},{"$f":"'K80 - time schedule'!HN32","v":0},{"$f":"'K80 - time schedule'!HO32","v":0},{"$f":"'K80 - time schedule'!HP32","v":0},{"$f":"'K80 - time schedule'!HQ32","v":0},{"$f":"'K80 - time schedule'!HR32","v":0},{"$f":"'K80 - time schedule'!HS32","v":0},{"$f":"'K80 - time schedule'!HT32","v":0},{"$f":"'K80 - time schedule'!HU32","v":0},{"$f":"'K80 - time schedule'!HV32","v":0},{"$f":"'K80 - time schedule'!HW32","v":0},{"$f":"'K80 - time schedule'!HX32","v":0},{"$f":"'K80 - time schedule'!HY32","v":0},{"$f":"'K80 - time schedule'!HZ32","v":0},{"$f":"'K80 - time schedule'!IA32","v":0},{"$f":"'K80 - time schedule'!IB32","v":0},{"$f":"'K80 - time schedule'!IC32","v":0},{"$f":"'K80 - time schedule'!ID32","v":0},{"$f":"'K80 - time schedule'!IE32","v":0},{"$f":"'K80 - time schedule'!IF32","v":0},{"$f":"'K80 - time schedule'!IG32","v":0},{"$f":"'K80 - time schedule'!IH32","v":0},{"$f":"'K80 - time schedule'!II32","v":0},{"$f":"'K80 - time schedule'!IJ32","v":0},{"$f":"'K80 - time schedule'!IK32","v":0},{"$f":"'K80 - time schedule'!IL32","v":0},{"$f":"'K80 - time schedule'!IM32","v":0},{"$f":"'K80 - time schedule'!IN32","v":0},{"$f":"'K80 - time schedule'!IO32","v":0},{"$f":"'K80 - time schedule'!IP32","v":0},{"$f":"'K80 - time schedule'!IQ32","v":0},{"$f":"'K80 - time schedule'!IR32","v":0},{"$f":"'K80 - time schedule'!IS32","v":0},{"$f":"'K80 - time schedule'!IT32","v":0},{"$f":"'K80 - time schedule'!IU32","v":0},{"$f":"'K80 - time schedule'!IV32","v":0},{"$f":"'K80 - time schedule'!IW32","v":0},{"$f":"'K80 - time schedule'!IX32","v":0},{"$f":"'K80 - time schedule'!IY32","v":0},{"$f":"'K80 - time schedule'!IZ32","v":0},{"$f":"'K80 - time schedule'!JA32","v":0},{"$f":"'K80 - time schedule'!JB32","v":0},{"$f":"'K80 - time schedule'!JC32","v":0},{"$f":"'K80 - time schedule'!JD32","v":0},{"$f":"'K80 - time schedule'!JE32","v":0},{"$f":"'K80 - time schedule'!JF32","v":0},{"$f":"'K80 - time schedule'!JG32","v":0},{"$f":"'K80 - time schedule'!JH32","v":0},{"$f":"'K80 - time schedule'!JI32","v":0},{"$f":"'K80 - time schedule'!JJ32","v":0},{"$f":"'K80 - time schedule'!JK32","v":0},{"$f":"'K80 - time schedule'!JL32","v":0},{"$f":"'K80 - time schedule'!JM32","v":0},{"$f":"'K80 - time schedule'!JN32","v":0},{"$f":"'K80 - time schedule'!JO32","v":0},{"$f":"'K80 - time schedule'!JP32","v":0},{"$f":"'K80 - time schedule'!JQ32","v":0},{"$f":"'K80 - time schedule'!JR32","v":0},{"$f":"'K80 - time schedule'!JS32","v":0},{"$f":"'K80 - time schedule'!JT32","v":0},{"$f":"'K80 - time schedule'!JU32","v":0},{"$f":"'K80 - time schedule'!JV32","v":0},{"$f":"'K80 - time schedule'!JW32","v":0},{"$f":"'K80 - time schedule'!JX32","v":0},{"$f":"'K80 - time schedule'!JY32","v":0},{"$f":"'K80 - time schedule'!JZ32","v":0},{"$f":"'K80 - time schedule'!KA32","v":0},{"$f":"'K80 - time schedule'!KB32","v":0},{"$f":"'K80 - time schedule'!KC32","v":0},{"$f":"'K80 - time schedule'!KD32","v":0},{"$f":"'K80 - time schedule'!KE32","v":0},{"$f":"'K80 - time schedule'!KF32","v":0},{"$f":"'K80 - time schedule'!KG32","v":0},{"$f":"'K80 - time schedule'!KH32","v":0},{"$f":"'K80 - time schedule'!KI32","v":0},{"$f":"'K80 - time schedule'!KJ32","v":0},{"$f":"'K80 - time schedule'!KK32","v":0},{"$f":"'K80 - time schedule'!KL32","v":0},{"$f":"'K80 - time schedule'!KM32","v":0},{"$f":"'K80 - time schedule'!KN32","v":0},{"$f":"'K80 - time schedule'!KO32","v":0},{"$f":"'K80 - time schedule'!KP32","v":0},{"$f":"'K80 - time schedule'!KQ32","v":0},{"$f":"'K80 - time schedule'!KR32","v":0},{"$f":"'K80 - time schedule'!KS32","v":0},{"$f":"'K80 - time schedule'!KT32","v":0}]
["Boiler room K80 - bottom of combustion chamber","K80",{"$f":"'K80 - time schedule'!G34","v":0},{"$f":"'K80 - time schedule'!H34","v":0},{"$f":"'K80 - time schedule'!I34","v":0},{"$f":"'K80 - time schedule'!J34","v":0},{"$f":"'K80 - time schedule'!K34","v":0},{"$f":"'K80 - time schedule'!L34","v":0},{"$f":"'K80 - time schedule'!M34","v":0},{"$f":"'K80 - time schedule'!N34","v":0},{"$f":"'K80 - time schedule'!O34","v":0},{"$f":"'K80 - time schedule'!P34","v":0},{"$f":"'K80 - time schedule'!Q34","v":0},{"$f":"'K80 - time schedule'!R34","v":0},{"$f":"'K80 - time schedule'!S34","v":0},{"$f":"'K80 - time schedule'!T34","v":0},{"$f":"'K80 - time schedule'!U34","v":0},{"$f":"'K80 - time schedule'!V34","v":0},{"$f":"'K80 - time schedule'!W34","v":0},{"$f":"'K80 - time schedule'!X34","v":0},{"$f":"'K80 - time schedule'!Y34","v":0},{"$f":"'K80 - time schedule'!Z34","v":0},{"$f":"'K80 - time schedule'!AA34","v":0},{"$f":"'K80 - time schedule'!AB34","v":0},{"$f":"'K80 - time schedule'!AC34","v":0},{"$f":"'K80 - time schedule'!AD34","v":0},{"$f":"'K80 - time schedule'!AE34","v":0},{"$f":"'K80 - time schedule'!AF34","v":0},{"$f":"'K80 - time schedule'!AG34","v":0},{"$f":"'K80 - time schedule'!AH34","v":0},{"$f":"'K80 - time schedule'!AI34","v":0},{"$f":"'K80 - time schedule'!AJ34","v":0},{"$f":"'K80 - time schedule'!AK34","v":0},{"$f":"'K80 - time schedule'!AL34","v":0},{"$f":"'K80 - time schedule'!AM34","v":0},{"$f":"'K80 - time schedule'!AN34","v":0},{"$f":"'K80 - time schedule'!AO34","v":0},{"$f":"'K80 - time schedule'!AP34","v":0},{"$f":"'K80 - time schedule'!AQ34","v":0},{"$f":"'K80 - time schedule'!AR34","v":0},{"$f":"'K80 - time schedule'!AS34","v":0},{"$f":"'K80 - time schedule'!AT34","v":0},{"$f":"'K80 - time schedule'!AU34","v":0},{"$f":"'K80 - time schedule'!AV34","v":0},{"$f":"'K80 - time schedule'!AW34","v":0},{"$f":"'K80 - time schedule'!AX34","v":0},{"$f":"'K80 - time schedule'!AY34","v":0},{"$f":"'K80 - time schedule'!AZ34","v":0},{"$f":"'K80 - time schedule'!BA34","v":0},{"$f":"'K80 - time schedule'!BB34","v":0},{"$f":"'K80 - time schedule'!BC34","v":0},{"$f":"'K80 - time schedule'!BD34","v":0},{"$f":"'K80 - time schedule'!BE34","v":0},{"$f":"'K80 - time schedule'!BF34","v":0},{"$f":"'K80 - time schedule'!BG34","v":0},{"$f":"'K80 - time schedule'!BH34","v":0},{"$f":"'K80 - time schedule'!BI34","v":0},{"$f":"'K80 - time schedule'!BJ34","v":0},{"$f":"'K80 - time schedule'!BK34","v":0},{"$f":"'K80 - time schedule'!BL34","v":0},{"$f":"'K80 - time schedule'!BM34","v":0},{"$f":"'K80 - time schedule'!BN34","v":0},{"$f":"'K80 - time schedule'!BO34","v":0},{"$f":"'K80 - time schedule'!BP34","v":0},{"$f":"'K80 - time schedule'!BQ34","v":0},{"$f":"'K80 - time schedule'!BR34","v":0},{"$f":"'K80 - time schedule'!BS34","v":0},{"$f":"'K80 - time schedule'!BT34","v":0},{"$f":"'K80 - time schedule'!BU34","v":0},{"$f":"'K80 - time schedule'!BV34","v":0},{"$f":"'K80 - time schedule'!BW34","v":0},{"$f":"'K80 - time schedule'!BX34","v":0},{"$f":"'K80 - time schedule'!BY34","v":0},{"$f":"'K80 - time schedule'!BZ34","v":0},{"$f":"'K80 - time schedule'!CA34","v":0},{"$f":"'K80 - time schedule'!CB34","v":0},{"$f":"'K80 - time schedule'!CC34","v":0},{"$f":"'K80 - time schedule'!CD34","v":0},{"$f":"'K80 - time schedule'!CE34","v":0},{"$f":"'K80 - time schedule'!CF34","v":0},{"$f":"'K80 - time schedule'!CG34","v":0},{"$f":"'K80 - time schedule'!CH34","v":0},{"$f":"'K80 - time schedule'!CI34","v":0},{"$f":"'K80 - time schedule'!CJ34","v":0},{"$f":"'K80 - time schedule'!CK34","v":0},{"$f":"'K80 - time schedule'!CL34","v":0},{"$f":"'K80 - time schedule'!CM34","v":0},{"$f":"'K80 - time schedule'!CN34","v":0},{"$f":"'K80 - time schedule'!CO34","v":0},{"$f":"'K80 - time schedule'!CP34","v":0},{"$f":"'K80 - time schedule'!CQ34","v":0},{"$f":"'K80 - time schedule'!CR34","v":0},{"$f":"'K80 - time schedule'!CS34","v":0},{"$f":"'K80 - time schedule'!CT34","v":0},{"$f":"'K80 - time schedule'!CU34","v":0},{"$f":"'K80 - time schedule'!CV34","v":0},{"$f":"'K80 - time schedule'!CW34","v":0},{"$f":"'K80 - time schedule'!CX34","v":0},{"$f":"'K80 - time schedule'!CY34","v":0},{"$f":"'K80 - time schedule'!CZ34","v":0},{"$f":"'K80 - time schedule'!DA34","v":0},{"$f":"'K80 - time schedule'!DB34","v":0},{"$f":"'K80 - time schedule'!DC34","v":0},{"$f":"'K80 - time schedule'!DD34","v":0},{"$f":"'K80 - time schedule'!DE34","v":0},{"$f":"'K80 - time schedule'!DF34","v":0},{"$f":"'K80 - time schedule'!DG34","v":0},{"$f":"'K80 - time schedule'!DH34","v":0},{"$f":"'K80 - time schedule'!DI34","v":0},{"$f":"'K80 - time schedule'!DJ34","v":0},{"$f":"'K80 - time schedule'!DK34","v":0},{"$f":"'K80 - time schedule'!DL34","v":0},{"$f":"'K80 - time schedule'!DM34","v":0},{"$f":"'K80 - time schedule'!DN34","v":0},{"$f":"'K80 - time schedule'!DO34","v":0},{"$f":"'K80 - time schedule'!DP34","v":0},{"$f":"'K80 - time schedule'!DQ34","v":0},{"$f":"'K80 - time schedule'!DR34","v":0},{"$f":"'K80 - time schedule'!DS34","v":0},{"$f":"'K80 - time schedule'!DT34","v":0},{"$f":"'K80 - time schedule'!DU34","v":0},{"$f":"'K80 - time schedule'!DV34","v":0},{"$f":"'K80 - time schedule'!DW34","v":0},{"$f":"'K80 - time schedule'!DX34","v":0},{"$f":"'K80 - time schedule'!DY34","v":0},{"$f":"'K80 - time schedule'!DZ34","v":0},{"$f":"'K80 - time schedule'!EA34","v":0},{"$f":"'K80 - time schedule'!EB34","v":0},{"$f":"'K80 - time schedule'!EC34","v":0},{"$f":"'K80 - time schedule'!ED34","v":0},{"$f":"'K80 - time schedule'!EE34","v":0},{"$f":"'K80 - time schedule'!EF34","v":0},{"$f":"'K80 - time schedule'!EG34","v":0},{"$f":"'K80 - time schedule'!EH34","v":0},{"$f":"'K80 - time schedule'!EI34","v":0},{"$f":"'K80 - time schedule'!EJ34","v":0},{"$f":"'K80 - time schedule'!EK34","v":0},{"$f":"'K80 - time schedule'!EL34","v":0},{"$f":"'K80 - time schedule'!EM34","v":0},{"$f":"'K80 - time schedule'!EN34","v":0},{"$f":"'K80 - time schedule'!EO34","v":0},{"$f":"'K80 - time schedule'!EP34","v":0},{"$f":"'K80 - time schedule'!EQ34","v":0},{"$f":"'K80 - time schedule'!ER34","v":0},{"$f":"'K80 - time schedule'!ES34","v":0},{"$f":"'K80 - time schedule'!ET34","v":0},{"$f":"'K80 - time schedule'!EU34","v":0},{"$f":"'K80 - time schedule'!EV34","v":0},{"$f":"'K80 - time schedule'!EW34","v":0},{"$f":"'K80 - time schedule'!EX34","v":0},{"$f":"'K80 - time schedule'!EY34","v":0},{"$f":"'K80 - time schedule'!EZ34","v":0},{"$f":"'K80 - time schedule'!FA34","v":0},{"$f":"'K80 - time schedule'!FB34","v":0},{"$f":"'K80 - time schedule'!FC34","v":0},{"$f":"'K80 - time schedule'!FD34","v":0},{"$f":"'K80 - time schedule'!FE34","v":0},{"$f":"'K80 - time schedule'!FF34","v":0},{"$f":"'K80 - time schedule'!FG34","v":0},{"$f":"'K80 - time schedule'!FH34","v":0},{"$f":"'K80 - time schedule'!FI34","v":0},{"$f":"'K80 - time schedule'!FJ34","v":0},{"$f":"'K80 - time schedule'!FK34","v":0},{"$f":"'K80 - time schedule'!FL34","v":0},{"$f":"'K80 - time schedule'!FM34","v":0},{"$f":"'K80 - time schedule'!FN34","v":0},{"$f":"'K80 - time schedule'!FO34","v":0},{"$f":"'K80 - time schedule'!FP34","v":0},{"$f":"'K80 - time schedule'!FQ34","v":0},{"$f":"'K80 - time schedule'!FR34","v":0},{"$f":"'K80 - time schedule'!FS34","v":0},{"$f":"'K80 - time schedule'!FT34","v":0},{"$f":"'K80 - time schedule'!FU34","v":0},{"$f":"'K80 - time schedule'!FV34","v":0},{"$f":"'K80 - time schedule'!FW34","v":0},{"$f":"'K80 - time schedule'!FX34","v":0},{"$f":"'K80 - time schedule'!FY34","v":0},{"$f":"'K80 - time schedule'!FZ34","v":0},{"$f":"'K80 - time schedule'!GA34","v":0},{"$f":"'K80 - time schedule'!GB34","v":0},{"$f":"'K80 - time schedule'!GC34","v":0},{"$f":"'K80 - time schedule'!GD34","v":0},{"$f":"'K80 - time schedule'!GE34","v":0},{"$f":"'K80 - time schedule'!GF34","v":0},{"$f":"'K80 - time schedule'!GG34","v":0},{"$f":"'K80 - time schedule'!GH34","v":0},{"$f":"'K80 - time schedule'!GI34","v":0},{"$f":"'K80 - time schedule'!GJ34","v":0},{"$f":"'K80 - time schedule'!GK34","v":0},{"$f":"'K80 - time schedule'!GL34","v":0},{"$f":"'K80 - time schedule'!GM34","v":0},{"$f":"'K80 - time schedule'!GN34","v":0},{"$f":"'K80 - time schedule'!GO34","v":0},{"$f":"'K80 - time schedule'!GP34","v":0},{"$f":"'K80 - time schedule'!GQ34","v":0},{"$f":"'K80 - time schedule'!GR34","v":0},{"$f":"'K80 - time schedule'!GS34","v":0},{"$f":"'K80 - time schedule'!GT34","v":0},{"$f":"'K80 - time schedule'!GU34","v":0},{"$f":"'K80 - time schedule'!GV34","v":0},{"$f":"'K80 - time schedule'!GW34","v":0},{"$f":"'K80 - time schedule'!GX34","v":0},{"$f":"'K80 - time schedule'!GY34","v":0},{"$f":"'K80 - time schedule'!GZ34","v":0},{"$f":"'K80 - time schedule'!HA34","v":0},{"$f":"'K80 - time schedule'!HB34","v":0},{"$f":"'K80 - time schedule'!HC34","v":0},{"$f":"'K80 - time schedule'!HD34","v":0},{"$f":"'K80 - time schedule'!HE34","v":0},{"$f":"'K80 - time schedule'!HF34","v":0},{"$f":"'K80 - time schedule'!HG34","v":0},{"$f":"'K80 - time schedule'!HH34","v":0},{"$f":"'K80 - time schedule'!HI34","v":0},{"$f":"'K80 - time schedule'!HJ34","v":0},{"$f":"'K80 - time schedule'!HK34","v":0},{"$f":"'K80 - time schedule'!HL34","v":0},{"$f":"'K80 - time schedule'!HM34","v":0},{"$f":"'K80 - time schedule'!HN34","v":0},{"$f":"'K80 - time schedule'!HO34","v":0},{"$f":"'K80 - time schedule'!HP34","v":0},{"$f":"'K80 - time schedule'!HQ34","v":0},{"$f":"'K80 - time schedule'!HR34","v":0},{"$f":"'K80 - time schedule'!HS34","v":0},{"$f":"'K80 - time schedule'!HT34","v":0},{"$f":"'K80 - time schedule'!HU34","v":0},{"$f":"'K80 - time schedule'!HV34","v":0},{"$f":"'K80 - time schedule'!HW34","v":0},{"$f":"'K80 - time schedule'!HX34","v":0},{"$f":"'K80 - time schedule'!HY34","v":0},{"$f":"'K80 - time schedule'!HZ34","v":0},{"$f":"'K80 - time schedule'!IA34","v":0},{"$f":"'K80 - time schedule'!IB34","v":0},{"$f":"'K80 - time schedule'!IC34","v":0},{"$f":"'K80 - time schedule'!ID34","v":0},{"$f":"'K80 - time schedule'!IE34","v":0},{"$f":"'K80 - time schedule'!IF34","v":0},{"$f":"'K80 - time schedule'!IG34","v":0},{"$f":"'K80 - time schedule'!IH34","v":0},{"$f":"'K80 - time schedule'!II34","v":0},{"$f":"'K80 - time schedule'!IJ34","v":0},{"$f":"'K80 - time schedule'!IK34","v":0},{"$f":"'K80 - time schedule'!IL34","v":0},{"$f":"'K80 - time schedule'!IM34","v":0},{"$f":"'K80 - time schedule'!IN34","v":0},{"$f":"'K80 - time schedule'!IO34","v":0},{"$f":"'K80 - time schedule'!IP34","v":0},{"$f":"'K80 - time schedule'!IQ34","v":0},{"$f":"'K80 - time schedule'!IR34","v":0},{"$f":"'K80 - time schedule'!IS34","v":0},{"$f":"'K80 - time schedule'!IT34","v":0},{"$f":"'K80 - time schedule'!IU34","v":0},{"$f":"'K80 - time schedule'!IV34","v":0},{"$f":"'K80 - time schedule'!IW34","v":0},{"$f":"'K80 - time schedule'!IX34","v":0},{"$f":"'K80 - time schedule'!IY34","v":0},{"$f":"'K80 - time schedule'!IZ34","v":0},{"$f":"'K80 - time schedule'!JA34","v":0},{"$f":"'K80 - time schedule'!JB34","v":0},{"$f":"'K80 - time schedule'!JC34","v":0},{"$f":"'K80 - time schedule'!JD34","v":0},{"$f":"'K80 - time schedule'!JE34","v":0},{"$f":"'K80 - time schedule'!JF34","v":0},{"$f":"'K80 - time schedule'!JG34","v":0},{"$f":"'K80 - time schedule'!JH34","v":0},{"$f":"'K80 - time schedule'!JI34","v":0},{"$f":"'K80 - time schedule'!JJ34","v":0},{"$f":"'K80 - time schedule'!JK34","v":0},{"$f":"'K80 - time schedule'!JL34","v":0},{"$f":"'K80 - time schedule'!JM34","v":0},{"$f":"'K80 - time schedule'!JN34","v":0},{"$f":"'K80 - time schedule'!JO34","v":0},{"$f":"'K80 - time schedule'!JP34","v":0},{"$f":"'K80 - time schedule'!JQ34","v":0},{"$f":"'K80 - time schedule'!JR34","v":0},{"$f":"'K80 - time schedule'!JS34","v":0},{"$f":"'K80 - time schedule'!JT34","v":0},{"$f":"'K80 - time schedule'!JU34","v":0},{"$f":"'K80 - time schedule'!JV34","v":0},{"$f":"'K80 - time schedule'!JW34","v":0},{"$f":"'K80 - time schedule'!JX34","v":0},{"$f":"'K80 - time schedule'!JY34","v":0},{"$f":"'K80 - time schedule'!JZ34","v":0},{"$f":"'K80 - time schedule'!KA34","v":0},{"$f":"'K80 - time schedule'!KB34","v":0},{"$f":"'K80 - time schedule'!KC34","v":0},{"$f":"'K80 - time schedule'!KD34","v":0},{"$f":"'K80 - time schedule'!KE34","v":0},{"$f":"'K80 - time schedule'!KF34","v":0},{"$f":"'K80 - time schedule'!KG34","v":0},{"$f":"'K80 - time schedule'!KH34","v":0},{"$f":"'K80 - time schedule'!KI34","v":0},{"$f":"'K80 - time schedule'!KJ34","v":0},{"$f":"'K80 - time schedule'!KK34","v":0},{"$f":"'K80 - time schedule'!KL34","v":0},{"$f":"'K80 - time schedule'!KM34","v":0},{"$f":"'K80 - time schedule'!KN34","v":0},{"$f":"'K80 - time schedule'!KO34","v":0},{"$f":"'K80 - time schedule'!KP34","v":0},{"$f":"'K80 - time schedule'!KQ34","v":0},{"$f":"'K80 - time schedule'!KR34","v":0},{"$f":"'K80 - time schedule'!KS34","v":0},{"$f":"'K80 - time schedule'!KT34","v":0}]
["Boiler room K80 - flue lines, including fabric filter","K80",{"$f":"'K80 - time schedule'!G36","v":0},{"$f":"'K80 - time schedule'!H36","v":0},{"$f":"'K80 - time schedule'!I36","v":0},{"$f":"'K80 - time schedule'!J36","v":0},{"$f":"'K80 - time schedule'!K36","v":0},{"$f":"'K80 - time schedule'!L36","v":0},{"$f":"'K80 - time schedule'!M36","v":0},{"$f":"'K80 - time schedule'!N36","v":0},{"$f":"'K80 - time schedule'!O36","v":0},{"$f":"'K80 - time schedule'!P36","v":0},{"$f":"'K80 - time schedule'!Q36","v":0},{"$f":"'K80 - time schedule'!R36","v":0},{"$f":"'K80 - time schedule'!S36","v":0},{"$f":"'K80 - time schedule'!T36","v":0},{"$f":"'K80 - time schedule'!U36","v":0},{"$f":"'K80 - time schedule'!V36","v":0},{"$f":"'K80 - time schedule'!W36","v":0},{"$f":"'K80 - time schedule'!X36","v":0},{"$f":"'K80 - time schedule'!Y36","v":0},{"$f":"'K80 - time schedule'!Z36","v":0},{"$f":"'K80 - time schedule'!AA36","v":0},{"$f":"'K80 - time schedule'!AB36","v":0},{"$f":"'K80 - time schedule'!AC36","v":0},{"$f":"'K80 - time schedule'!AD36","v":0},{"$f":"'K80 - time schedule'!AE36","v":0},{"$f":"'K80 - time schedule'!AF36","v":0},{"$f":"'K80 - time schedule'!AG36","v":0},{"$f":"'K80 - time schedule'!AH36","v":0},{"$f":"'K80 - time schedule'!AI36","v":0},{"$f":"'K80 - time schedule'!AJ36","v":0},{"$f":"'K80 - time schedule'!AK36","v":0},{"$f":"'K80 - time schedule'!AL36","v":0},{"$f":"'K80 - time schedule'!AM36","v":0},{"$f":"'K80 - time schedule'!AN36","v":0},{"$f":"'K80 - time schedule'!AO36","v":0},{"$f":"'K80 - time schedule'!AP36","v":0},{"$f":"'K80 - time schedule'!AQ36","v":0},{"$f":"'K80 - time schedule'!AR36","v":0},{"$f":"'K80 - time schedule'!AS36","v":0},{"$f":"'K80 - time schedule'!AT36","v":0},{"$f":"'K80 - time schedule'!AU36","v":0},{"$f":"'K80 - time schedule'!AV36","v":0},{"$f":"'K80 - time schedule'!AW36","v":0},{"$f":"'K80 - time schedule'!AX36","v":0},{"$f":"'K80 - time schedule'!AY36","v":0},{"$f":"'K80 - time schedule'!AZ36","v":0},{"$f":"'K80 - time schedule'!BA36","v":0},{"$f":"'K80 - time schedule'!BB36","v":0},{"$f":"'K80 - time schedule'!BC36","v":0},{"$f":"'K80 - time schedule'!BD36","v":0},{"$f":"'K80 - time schedule'!BE36","v":0},{"$f":"'K80 - time schedule'!BF36","v":0},{"$f":"'K80 - time schedule'!BG36","v":0},{"$f":"'K80 - time schedule'!BH36","v":0},{"$f":"'K80 - time schedule'!BI36","v":0},{"$f":"'K80 - time schedule'!BJ36","v":0},{"$f":"'K80 - time schedule'!BK36","v":0},{"$f":"'K80 - time schedule'!BL36","v":0},{"$f":"'K80 - time schedule'!BM36","v":0},{"$f":"'K80 - time schedule'!BN36","v":0},{"$f":"'K80 - time schedule'!BO36","v":0},{"$f":"'K80 - time schedule'!BP36","v":0},{"$f":"'K80 - time schedule'!BQ36","v":0},{"$f":"'K80 - time schedule'!BR36","v":0},{"$f":"'K80 - time schedule'!BS36","v":0},{"$f":"'K80 - time schedule'!BT36","v":0},{"$f":"'K80 - time schedule'!BU36","v":0},{"$f":"'K80 - time schedule'!BV36","v":0},{"$f":"'K80 - time schedule'!BW36","v":0},{"$f":"'K80 - time schedule'!BX36","v":0},{"$f":"'K80 - time schedule'!BY36","v":0},{"$f":"'K80 - time schedule'!BZ36","v":0},{"$f":"'K80 - time schedule'!CA36","v":0},{"$f":"'K80 - time schedule'!CB36","v":0},{"$f":"'K80 - time schedule'!CC36","v":0},{"$f":"'K80 - time schedule'!CD36","v":0},{"$f":"'K80 - time schedule'!CE36","v":0},{"$f":"'K80 - time schedule'!CF36","v":0},{"$f":"'K80 - time schedule'!CG36","v":0},{"$f":"'K80 - time schedule'!CH36","v":0},{"$f":"'K80 - time schedule'!CI36","v":0},{"$f":"'K80 - time schedule'!CJ36","v":0},{"$f":"'K80 - time schedule'!CK36","v":0},{"$f":"'K80 - time schedule'!CL36","v":0},{"$f":"'K80 - time schedule'!CM36","v":0},{"$f":"'K80 - time schedule'!CN36","v":0},{"$f":"'K80 - time schedule'!CO36","v":0},{"$f":"'K80 - time schedule'!CP36","v":0},{"$f":"'K80 - time schedule'!CQ36","v":0},{"$f":"'K80 - time schedule'!CR36","v":0},{"$f":"'K80 - time schedule'!CS36","v":0},{"$f":"'K80 - time schedule'!CT36","v":0},{"$f":"'K80 - time schedule'!CU36","v":0},{"$f":"'K80 - time schedule'!CV36","v":0},{"$f":"'K80 - time schedule'!CW36","v":0},{"$f":"'K80 - time schedule'!CX36","v":0},{"$f":"'K80 - time schedule'!CY36","v":0},{"$f":"'K80 - time schedule'!CZ36","v":0},{"$f":"'K80 - time schedule'!DA36","v":0},{"$f":"'K80 - time schedule'!DB36","v":0},{"$f":"'K80 - time schedule'!DC36","v":0},{"$f":"'K80 - time schedule'!DD36","v":0},{"$f":"'K80 - time schedule'!DE36","v":0},{"$f":"'K80 - time schedule'!DF36","v":0},{"$f":"'K80 - time schedule'!DG36","v":0},{"$f":"'K80 - time schedule'!DH36","v":0},{"$f":"'K80 - time schedule'!DI36","v":0},{"$f":"'K80 - time schedule'!DJ36","v":0},{"$f":"'K80 - time schedule'!DK36","v":0},{"$f":"'K80 - time schedule'!DL36","v":0},{"$f":"'K80 - time schedule'!DM36","v":0},{"$f":"'K80 - time schedule'!DN36","v":0},{"$f":"'K80 - time schedule'!DO36","v":0},{"$f":"'K80 - time schedule'!DP36","v":0},{"$f":"'K80 - time schedule'!DQ36","v":0},{"$f":"'K80 - time schedule'!DR36","v":0},{"$f":"'K80 - time schedule'!DS36","v":0},{"$f":"'K80 - time schedule'!DT36","v":0},{"$f":"'K80 - time schedule'!DU36","v":0},{"$f":"'K80 - time schedule'!DV36","v":0},{"$f":"'K80 - time schedule'!DW36","v":0},{"$f":"'K80 - time schedule'!DX36","v":0},{"$f":"'K80 - time schedule'!DY36","v":0},{"$f":"'K80 - time schedule'!DZ36","v":0},{"$f":"'K80 - time schedule'!EA36","v":0},{"$f":"'K80 - time schedule'!EB36","v":0},{"$f":"'K80 - time schedule'!EC36","v":0},{"$f":"'K80 - time schedule'!ED36","v":0},{"$f":"'K80 - time schedule'!EE36","v":0},{"$f":"'K80 - time schedule'!EF36","v":0},{"$f":"'K80 - time schedule'!EG36","v":0},{"$f":"'K80 - time schedule'!EH36","v":0},{"$f":"'K80 - time schedule'!EI36","v":0},{"$f":"'K80 - time schedule'!EJ36","v":0},{"$f":"'K80 - time schedule'!EK36","v":0},{"$f":"'K80 - time schedule'!EL36","v":0},{"$f":"'K80 - time schedule'!EM36","v":0},{"$f":"'K80 - time schedule'!EN36","v":0},{"$f":"'K80 - time schedule'!EO36","v":0},{"$f":"'K80 - time schedule'!EP36","v":0},{"$f":"'K80 - time schedule'!EQ36","v":0},{"$f":"'K80 - time schedule'!ER36","v":0},{"$f":"'K80 - time schedule'!ES36","v":0},{"$f":"'K80 - time schedule'!ET36","v":0},{"$f":"'K80 - time schedule'!EU36","v":0},{"$f":"'K80 - time schedule'!EV36","v":0},{"$f":"'K80 - time schedule'!EW36","v":0},{"$f":"'K80 - time schedule'!EX36","v":0},{"$f":"'K80 - time schedule'!EY36","v":0},{"$f":"'K80 - time schedule'!EZ36","v":0},{"$f":"'K80 - time schedule'!FA36","v":0},{"$f":"'K80 - time schedule'!FB36","v":0},{"$f":"'K80 - time schedule'!FC36","v":0},{"$f":"'K80 - time schedule'!FD36","v":0},{"$f":"'K80 - time schedule'!FE36","v":0},{"$f":"'K80 - time schedule'!FF36","v":0},{"$f":"'K80 - time schedule'!FG36","v":0},{"$f":"'K80 - time schedule'!FH36","v":0},{"$f":"'K80 - time schedule'!FI36","v":0},{"$f":"'K80 - time schedule'!FJ36","v":0},{"$f":"'K80 - time schedule'!FK36","v":0},{"$f":"'K80 - time schedule'!FL36","v":0},{"$f":"'K80 - time schedule'!FM36","v":0},{"$f":"'K80 - time schedule'!FN36","v":0},{"$f":"'K80 - time schedule'!FO36","v":0},{"$f":"'K80 - time schedule'!FP36","v":0},{"$f":"'K80 - time schedule'!FQ36","v":0},{"$f":"'K80 - time schedule'!FR36","v":0},{"$f":"'K80 - time schedule'!FS36","v":0},{"$f":"'K80 - time schedule'!FT36","v":0},{"$f":"'K80 - time schedule'!FU36","v":0},{"$f":"'K80 - time schedule'!FV36","v":0},{"$f":"'K80 - time schedule'!FW36","v":0},{"$f":"'K80 - time schedule'!FX36","v":0},{"$f":"'K80 - time schedule'!FY36","v":0},{"$f":"'K80 - time schedule'!FZ36","v":0},{"$f":"'K80 - time schedule'!GA36","v":0},{"$f":"'K80 - time schedule'!GB36","v":0},{"$f":"'K80 - time schedule'!GC36","v":0},{"$f":"'K80 - time schedule'!GD36","v":0},{"$f":"'K80 - time schedule'!GE36","v":0},{"$f":"'K80 - time schedule'!GF36","v":0},{"$f":"'K80 - time schedule'!GG36","v":0},{"$f":"'K80 - time schedule'!GH36","v":0},{"$f":"'K80 - time schedule'!GI36","v":0},{"$f":"'K80 - time schedule'!GJ36","v":0},{"$f":"'K80 - time schedule'!GK36","v":0},{"$f":"'K80 - time schedule'!GL36","v":0},{"$f":"'K80 - time schedule'!GM36","v":0},{"$f":"'K80 - time schedule'!GN36","v":0},{"$f":"'K80 - time schedule'!GO36","v":0},{"$f":"'K80 - time schedule'!GP36","v":0},{"$f":"'K80 - time schedule'!GQ36","v":0},{"$f":"'K80 - time schedule'!GR36","v":0},{"$f":"'K80 - time schedule'!GS36","v":0},{"$f":"'K80 - time schedule'!GT36","v":0},{"$f":"'K80 - time schedule'!GU36","v":0},{"$f":"'K80 - time schedule'!GV36","v":0},{"$f":"'K80 - time schedule'!GW36","v":0},{"$f":"'K80 - time schedule'!GX36","v":0},{"$f":"'K80 - time schedule'!GY36","v":0},{"$f":"'K80 - time schedule'!GZ36","v":0},{"$f":"'K80 - time schedule'!HA36","v":0},{"$f":"'K80 - time schedule'!HB36","v":0},{"$f":"'K80 - time schedule'!HC36","v":0},{"$f":"'K80 - time schedule'!HD36","v":0},{"$f":"'K80 - time schedule'!HE36","v":0},{"$f":"'K80 - time schedule'!HF36","v":0},{"$f":"'K80 - time schedule'!HG36","v":0},{"$f":"'K80 - time schedule'!HH36","v":0},{"$f":"'K80 - time schedule'!HI36","v":0},{"$f":"'K80 - time schedule'!HJ36","v":0},{"$f":"'K80 - time schedule'!HK36","v":0},{"$f":"'K80 - time schedule'!HL36","v":0},{"$f":"'K80 - time schedule'!HM36","v":0},{"$f":"'K80 - time schedule'!HN36","v":0},{"$f":"'K80 - time schedule'!HO36","v":0},{"$f":"'K80 - time schedule'!HP36","v":0},{"$f":"'K80 - time schedule'!HQ36","v":0},{"$f":"'K80 - time schedule'!HR36","v":0},{"$f":"'K80 - time schedule'!HS36","v":0},{"$f":"'K80 - time schedule'!HT36","v":0},{"$f":"'K80 - time schedule'!HU36","v":0},{"$f":"'K80 - time schedule'!HV36","v":0},{"$f":"'K80 - time schedule'!HW36","v":0},{"$f":"'K80 - time schedule'!HX36","v":0},{"$f":"'K80 - time schedule'!HY36","v":0},{"$f":"'K80 - time schedule'!HZ36","v":0},{"$f":"'K80 - time schedule'!IA36","v":0},{"$f":"'K80 - time schedule'!IB36","v":0},{"$f":"'K80 - time schedule'!IC36","v":0},{"$f":"'K80 - time schedule'!ID36","v":0},{"$f":"'K80 - time schedule'!IE36","v":0},{"$f":"'K80 - time schedule'!IF36","v":0},{"$f":"'K80 - time schedule'!IG36","v":0},{"$f":"'K80 - time schedule'!IH36","v":0},{"$f":"'K80 - time schedule'!II36","v":0},{"$f":"'K80 - time schedule'!IJ36","v":0},{"$f":"'K80 - time schedule'!IK36","v":0},{"$f":"'K80 - time schedule'!IL36","v":0},{"$f":"'K80 - time schedule'!IM36","v":0},{"$f":"'K80 - time schedule'!IN36","v":0},{"$f":"'K80 - time schedule'!IO36","v":0},{"$f":"'K80 - time schedule'!IP36","v":0},{"$f":"'K80 - time schedule'!IQ36","v":0},{"$f":"'K80 - time schedule'!IR36","v":0},{"$f":"'K80 - time schedule'!IS36","v":0},{"$f":"'K80 - time schedule'!IT36","v":0},{"$f":"'K80 - time schedule'!IU36","v":0},{"$f":"'K80 - time schedule'!IV36","v":0},{"$f":"'K80 - time schedule'!IW36","v":0},{"$f":"'K80 - time schedule'!IX36","v":0},{"$f":"'K80 - time schedule'!IY36","v":0},{"$f":"'K80 - time schedule'!IZ36","v":0},{"$f":"'K80 - time schedule'!JA36","v":0},{"$f":"'K80 - time schedule'!JB36","v":0},{"$f":"'K80 - time schedule'!JC36","v":0},{"$f":"'K80 - time schedule'!JD36","v":0},{"$f":"'K80 - time schedule'!JE36","v":0},{"$f":"'K80 - time schedule'!JF36","v":0},{"$f":"'K80 - time schedule'!JG36","v":0},{"$f":"'K80 - time schedule'!JH36","v":0},{"$f":"'K80 - time schedule'!JI36","v":0},{"$f":"'K80 - time schedule'!JJ36","v":0},{"$f":"'K80 - time schedule'!JK36","v":0},{"$f":"'K80 - time schedule'!JL36","v":0},{"$f":"'K80 - time schedule'!JM36","v":0},{"$f":"'K80 - time schedule'!JN36","v":0},{"$f":"'K80 - time schedule'!JO36","v":0},{"$f":"'K80 - time schedule'!JP36","v":0},{"$f":"'K80 - time schedule'!JQ36","v":0},{"$f":"'K80 - time schedule'!JR36","v":0},{"$f":"'K80 - time schedule'!JS36","v":0},{"$f":"'K80 - time schedule'!JT36","v":0},{"$f":"'K80 - time schedule'!JU36","v":0},{"$f":"'K80 - time schedule'!JV36","v":0},{"$f":"'K80 - time schedule'!JW36","v":0},{"$f":"'K80 - time schedule'!JX36","v":0},{"$f":"'K80 - time schedule'!JY36","v":0},{"$f":"'K80 - time schedule'!JZ36","v":0},{"$f":"'K80 - time schedule'!KA36","v":0},{"$f":"'K80 - time schedule'!KB36","v":0},{"$f":"'K80 - time schedule'!KC36","v":0},{"$f":"'K80 - time schedule'!KD36","v":0},{"$f":"'K80 - time schedule'!KE36","v":0},{"$f":"'K80 - time schedule'!KF36","v":0},{"$f":"'K80 - time schedule'!KG36","v":0},{"$f":"'K80 - time schedule'!KH36","v":0},{"$f":"'K80 - time schedule'!KI36","v":0},{"$f":"'K80 - time schedule'!KJ36","v":0},{"$f":"'K80 - time schedule'!KK36","v":0},{"$f":"'K80 - time schedule'!KL36","v":0},{"$f":"'K80 - time schedule'!KM36","v":0},{"$f":"'K80 - time schedule'!KN36","v":0},{"$f":"'K80 - time schedule'!KO36","v":0},{"$f":"'K80 - time schedule'!KP36","v":0},{"$f":"'K80 - time schedule'!KQ36","v":0},{"$f":"'K80 - time schedule'!KR36","v":0},{"$f":"'K80 - time schedule'!KS36","v":0},{"$f":"'K80 - time schedule'!KT36","v":0}]
["Boiler room K80 - electrical installation","K80",{"$f":"'K80 - time schedule'!G38","v":0},{"$f":"'K80 - time schedule'!H38","v":0},{"$f":"'K80 - time schedule'!I38","v":0},{"$f":"'K80 - time schedule'!J38","v":0},{"$f":"'K80 - time schedule'!K38","v":0},{"$f":"'K80 - time schedule'!L38","v":0},{"$f":"'K80 - time schedule'!M38","v":0},{"$f":"'K80 - time schedule'!N38","v":0},{"$f":"'K80 - time schedule'!O38","v":0},{"$f":"'K80 - time schedule'!P38","v":0},{"$f":"'K80 - time schedule'!Q38","v":0},{"$f":"'K80 - time schedule'!R38","v":0},{"$f":"'K80 - time schedule'!S38","v":0},{"$f":"'K80 - time schedule'!T38","v":0},{"$f":"'K80 - time schedule'!U38","v":0},{"$f":"'K80 - time schedule'!V38","v":0},{"$f":"'K80 - time schedule'!W38","v":0},{"$f":"'K80 - time schedule'!X38","v":0},{"$f":"'K80 - time schedule'!Y38","v":0},{"$f":"'K80 - time schedule'!Z38","v":0},{"$f":"'K80 - time schedule'!AA38","v":0},{"$f":"'K80 - time schedule'!AB38","v":0},{"$f":"'K80 - time schedule'!AC38","v":0},{"$f":"'K80 - time schedule'!AD38","v":0},{"$f":"'K80 - time schedule'!AE38","v":0},{"$f":"'K80 - time schedule'!AF38","v":0},{"$f":"'K80 - time schedule'!AG38","v":0},{"$f":"'K80 - time schedule'!AH38","v":0},{"$f":"'K80 - time schedule'!AI38","v":0},{"$f":"'K80 - time schedule'!AJ38","v":0},{"$f":"'K80 - time schedule'!AK38","v":0},{"$f":"'K80 - time schedule'!AL38","v":0},{"$f":"'K80 - time schedule'!AM38","v":0},{"$f":"'K80 - time schedule'!AN38","v":0},{"$f":"'K80 - time schedule'!AO38","v":0},{"$f":"'K80 - time schedule'!AP38","v":0},{"$f":"'K80 - time schedule'!AQ38","v":0},{"$f":"'K80 - time schedule'!AR38","v":0},{"$f":"'K80 - time schedule'!AS38","v":0},{"$f":"'K80 - time schedule'!AT38","v":0},{"$f":"'K80 - time schedule'!AU38","v":0},{"$f":"'K80 - time schedule'!AV38","v":0},{"$f":"'K80 - time schedule'!AW38","v":0},{"$f":"'K80 - time schedule'!AX38","v":0},{"$f":"'K80 - time schedule'!AY38","v":0},{"$f":"'K80 - time schedule'!AZ38","v":0},{"$f":"'K80 - time schedule'!BA38","v":0},{"$f":"'K80 - time schedule'!BB38","v":0},{"$f":"'K80 - time schedule'!BC38","v":0},{"$f":"'K80 - time schedule'!BD38","v":0},{"$f":"'K80 - time schedule'!BE38","v":0},{"$f":"'K80 - time schedule'!BF38","v":0},{"$f":"'K80 - time schedule'!BG38","v":0},{"$f":"'K80 - time schedule'!BH38","v":0},{"$f":"'K80 - time schedule'!BI38","v":0},{"$f":"'K80 - time schedule'!BJ38","v":0},{"$f":"'K80 - time schedule'!BK38","v":0},{"$f":"'K80 - time schedule'!BL38","v":0},{"$f":"'K80 - time schedule'!BM38","v":0},{"$f":"'K80 - time schedule'!BN38","v":0},{"$f":"'K80 - time schedule'!BO38","v":0},{"$f":"'K80 - time schedule'!BP38","v":0},{"$f":"'K80 - time schedule'!BQ38","v":0},{"$f":"'K80 - time schedule'!BR38","v":0},{"$f":"'K80 - time schedule'!BS38","v":0},{"$f":"'K80 - time schedule'!BT38","v":0},{"$f":"'K80 - time schedule'!BU38","v":0},{"$f":"'K80 - time schedule'!BV38","v":0},{"$f":"'K80 - time schedule'!BW38","v":0},{"$f":"'K80 - time schedule'!BX38","v":0},{"$f":"'K80 - time schedule'!BY38","v":0},{"$f":"'K80 - time schedule'!BZ38","v":0},{"$f":"'K80 - time schedule'!CA38","v":0},{"$f":"'K80 - time schedule'!CB38","v":0},{"$f":"'K80 - time schedule'!CC38","v":0},{"$f":"'K80 - time schedule'!CD38","v":0},{"$f":"'K80 - time schedule'!CE38","v":0},{"$f":"'K80 - time schedule'!CF38","v":0},{"$f":"'K80 - time schedule'!CG38","v":0},{"$f":"'K80 - time schedule'!CH38","v":0},{"$f":"'K80 - time schedule'!CI38","v":0},{"$f":"'K80 - time schedule'!CJ38","v":0},{"$f":"'K80 - time schedule'!CK38","v":0},{"$f":"'K80 - time schedule'!CL38","v":0},{"$f":"'K80 - time schedule'!CM38","v":0},{"$f":"'K80 - time schedule'!CN38","v":0},{"$f":"'K80 - time schedule'!CO38","v":0},{"$f":"'K80 - time schedule'!CP38","v":0},{"$f":"'K80 - time schedule'!CQ38","v":0},{"$f":"'K80 - time schedule'!CR38","v":0},{"$f":"'K80 - time schedule'!CS38","v":0},{"$f":"'K80 - time schedule'!CT38","v":0},{"$f":"'K80 - time schedule'!CU38","v":0},{"$f":"'K80 - time schedule'!CV38","v":0},{"$f":"'K80 - time schedule'!CW38","v":0},{"$f":"'K80 - time schedule'!CX38","v":0},{"$f":"'K80 - time schedule'!CY38","v":0},{"$f":"'K80 - time schedule'!CZ38","v":0},{"$f":"'K80 - time schedule'!DA38","v":0},{"$f":"'K80 - time schedule'!DB38","v":0},{"$f":"'K80 - time schedule'!DC38","v":0},{"$f":"'K80 - time schedule'!DD38","v":0},{"$f":"'K80 - time schedule'!DE38","v":0},{"$f":"'K80 - time schedule'!DF38","v":0},{"$f":"'K80 - time schedule'!DG38","v":0},{"$f":"'K80 - time schedule'!DH38","v":0},{"$f":"'K80 - time schedule'!DI38","v":0},{"$f":"'K80 - time schedule'!DJ38","v":0},{"$f":"'K80 - time schedule'!DK38","v":0},{"$f":"'K80 - time schedule'!DL38","v":0},{"$f":"'K80 - time schedule'!DM38","v":0},{"$f":"'K80 - time schedule'!DN38","v":0},{"$f":"'K80 - time schedule'!DO38","v":0},{"$f":"'K80 - time schedule'!DP38","v":0},{"$f":"'K80 - time schedule'!DQ38","v":0},{"$f":"'K80 - time schedule'!DR38","v":0},{"$f":"'K80 - time schedule'!DS38","v":0},{"$f":"'K80 - time schedule'!DT38","v":0},{"$f":"'K80 - time schedule'!DU38","v":0},{"$f":"'K80 - time schedule'!DV38","v":0},{"$f":"'K80 - time schedule'!DW38","v":0},{"$f":"'K80 - time schedule'!DX38","v":0},{"$f":"'K80 - time schedule'!DY38","v":0},{"$f":"'K80 - time schedule'!DZ38","v":0},{"$f":"'K80 - time schedule'!EA38","v":0},{"$f":"'K80 - time schedule'!EB38","v":0},{"$f":"'K80 - time schedule'!EC38","v":0},{"$f":"'K80 - time schedule'!ED38","v":0},{"$f":"'K80 - time schedule'!EE38","v":0},{"$f":"'K80 - time schedule'!EF38","v":0},{"$f":"'K80 - time schedule'!EG38","v":0},{"$f":"'K80 - time schedule'!EH38","v":0},{"$f":"'K80 - time schedule'!EI38","v":0},{"$f":"'K80 - time schedule'!EJ38","v":0},{"$f":"'K80 - time schedule'!EK38","v":0},{"$f":"'K80 - time schedule'!EL38","v":0},{"$f":"'K80 - time schedule'!EM38","v":0},{"$f":"'K80 - time schedule'!EN38","v":0},{"$f":"'K80 - time schedule'!EO38","v":0},{"$f":"'K80 - time schedule'!EP38","v":0},{"$f":"'K80 - time schedule'!EQ38","v":0},{"$f":"'K80 - time schedule'!ER38","v":0},{"$f":"'K80 - time schedule'!ES38","v":0},{"$f":"'K80 - time schedule'!ET38","v":0},{"$f":"'K80 - time schedule'!EU38","v":0},{"$f":"'K80 - time schedule'!EV38","v":0},{"$f":"'K80 - time schedule'!EW38","v":0},{"$f":"'K80 - time schedule'!EX38","v":0},{"$f":"'K80 - time schedule'!EY38","v":0},{"$f":"'K80 - time schedule'!EZ38","v":0},{"$f":"'K80 - time schedule'!FA38","v":0},{"$f":"'K80 - time schedule'!FB38","v":0},{"$f":"'K80 - time schedule'!FC38","v":0},{"$f":"'K80 - time schedule'!FD38","v":0},{"$f":"'K80 - time schedule'!FE38","v":0},{"$f":"'K80 - time schedule'!FF38","v":0},{"$f":"'K80 - time schedule'!FG38","v":0},{"$f":"'K80 - time schedule'!FH38","v":0},{"$f":"'K80 - time schedule'!FI38","v":0},{"$f":"'K80 - time schedule'!FJ38","v":0},{"$f":"'K80 - time schedule'!FK38","v":0},{"$f":"'K80 - time schedule'!FL38","v":0},{"$f":"'K80 - time schedule'!FM38","v":0},{"$f":"'K80 - time schedule'!FN38","v":0},{"$f":"'K80 - time schedule'!FO38","v":0},{"$f":"'K80 - time schedule'!FP38","v":0},{"$f":"'K80 - time schedule'!FQ38","v":0},{"$f":"'K80 - time schedule'!FR38","v":0},{"$f":"'K80 - time schedule'!FS38","v":0},{"$f":"'K80 - time schedule'!FT38","v":0},{"$f":"'K80 - time schedule'!FU38","v":0},{"$f":"'K80 - time schedule'!FV38","v":0},{"$f":"'K80 - time schedule'!FW38","v":0},{"$f":"'K80 - time schedule'!FX38","v":0},{"$f":"'K80 - time schedule'!FY38","v":0},{"$f":"'K80 - time schedule'!FZ38","v":0},{"$f":"'K80 - time schedule'!GA38","v":0},{"$f":"'K80 - time schedule'!GB38","v":0},{"$f":"'K80 - time schedule'!GC38","v":0},{"$f":"'K80 - time schedule'!GD38","v":0},{"$f":"'K80 - time schedule'!GE38","v":0},{"$f":"'K80 - time schedule'!GF38","v":0},{"$f":"'K80 - time schedule'!GG38","v":0},{"$f":"'K80 - time schedule'!GH38","v":0},{"$f":"'K80 - time schedule'!GI38","v":0},{"$f":"'K80 - time schedule'!GJ38","v":0},{"$f":"'K80 - time schedule'!GK38","v":0},{"$f":"'K80 - time schedule'!GL38","v":0},{"$f":"'K80 - time schedule'!GM38","v":0},{"$f":"'K80 - time schedule'!GN38","v":0},{"$f":"'K80 - time schedule'!GO38","v":0},{"$f":"'K80 - time schedule'!GP38","v":0},{"$f":"'K80 - time schedule'!GQ38","v":0},{"$f":"'K80 - time schedule'!GR38","v":0},{"$f":"'K80 - time schedule'!GS38","v":0},{"$f":"'K80 - time schedule'!GT38","v":0},{"$f":"'K80 - time schedule'!GU38","v":0},{"$f":"'K80 - time schedule'!GV38","v":0},{"$f":"'K80 - time schedule'!GW38","v":0},{"$f":"'K80 - time schedule'!GX38","v":0},{"$f":"'K80 - time schedule'!GY38","v":0},{"$f":"'K80 - time schedule'!GZ38","v":0},{"$f":"'K80 - time schedule'!HA38","v":0},{"$f":"'K80 - time schedule'!HB38","v":0},{"$f":"'K80 - time schedule'!HC38","v":0},{"$f":"'K80 - time schedule'!HD38","v":0},{"$f":"'K80 - time schedule'!HE38","v":0},{"$f":"'K80 - time schedule'!HF38","v":0},{"$f":"'K80 - time schedule'!HG38","v":0},{"$f":"'K80 - time schedule'!HH38","v":0},{"$f":"'K80 - time schedule'!HI38","v":0},{"$f":"'K80 - time schedule'!HJ38","v":0},{"$f":"'K80 - time schedule'!HK38","v":0},{"$f":"'K80 - time schedule'!HL38","v":0},{"$f":"'K80 - time schedule'!HM38","v":0},{"$f":"'K80 - time schedule'!HN38","v":0},{"$f":"'K80 - time schedule'!HO38","v":0},{"$f":"'K80 - time schedule'!HP38","v":0},{"$f":"'K80 - time schedule'!HQ38","v":0},{"$f":"'K80 - time schedule'!HR38","v":0},{"$f":"'K80 - time schedule'!HS38","v":0},{"$f":"'K80 - time schedule'!HT38","v":0},{"$f":"'K80 - time schedule'!HU38","v":0},{"$f":"'K80 - time schedule'!HV38","v":0},{"$f":"'K80 - time schedule'!HW38","v":0},{"$f":"'K80 - time schedule'!HX38","v":0},{"$f":"'K80 - time schedule'!HY38","v":0},{"$f":"'K80 - time schedule'!HZ38","v":0},{"$f":"'K80 - time schedule'!IA38","v":0},{"$f":"'K80 - time schedule'!IB38","v":0},{"$f":"'K80 - time schedule'!IC38","v":0},{"$f":"'K80 - time schedule'!ID38","v":0},{"$f":"'K80 - time schedule'!IE38","v":0},{"$f":"'K80 - time schedule'!IF38","v":0},{"$f":"'K80 - time schedule'!IG38","v":0},{"$f":"'K80 - time schedule'!IH38","v":0},{"$f":"'K80 - time schedule'!II38","v":0},{"$f":"'K80 - time schedule'!IJ38","v":0},{"$f":"'K80 - time schedule'!IK38","v":0},{"$f":"'K80 - time schedule'!IL38","v":0},{"$f":"'K80 - time schedule'!IM38","v":0},{"$f":"'K80 - time schedule'!IN38","v":0},{"$f":"'K80 - time schedule'!IO38","v":0},{"$f":"'K80 - time schedule'!IP38","v":0},{"$f":"'K80 - time schedule'!IQ38","v":0},{"$f":"'K80 - time schedule'!IR38","v":0},{"$f":"'K80 - time schedule'!IS38","v":0},{"$f":"'K80 - time schedule'!IT38","v":0},{"$f":"'K80 - time schedule'!IU38","v":0},{"$f":"'K80 - time schedule'!IV38","v":0},{"$f":"'K80 - time schedule'!IW38","v":0},{"$f":"'K80 - time schedule'!IX38","v":0},{"$f":"'K80 - time schedule'!IY38","v":0},{"$f":"'K80 - time schedule'!IZ38","v":0},{"$f":"'K80 - time schedule'!JA38","v":0},{"$f":"'K80 - time schedule'!JB38","v":0},{"$f":"'K80 - time schedule'!JC38","v":0},{"$f":"'K80 - time schedule'!JD38","v":0},{"$f":"'K80 - time schedule'!JE38","v":0},{"$f":"'K80 - time schedule'!JF38","v":0},{"$f":"'K80 - time schedule'!JG38","v":0},{"$f":"'K80 - time schedule'!JH38","v":0},{"$f":"'K80 - time schedule'!JI38","v":0},{"$f":"'K80 - time schedule'!JJ38","v":0},{"$f":"'K80 - time schedule'!JK38","v":0},{"$f":"'K80 - time schedule'!JL38","v":0},{"$f":"'K80 - time schedule'!JM38","v":0},{"$f":"'K80 - time schedule'!JN38","v":0},{"$f":"'K80 - time schedule'!JO38","v":0},{"$f":"'K80 - time schedule'!JP38","v":0},{"$f":"'K80 - time schedule'!JQ38","v":0},{"$f":"'K80 - time schedule'!JR38","v":0},{"$f":"'K80 - time schedule'!JS38","v":0},{"$f":"'K80 - time schedule'!JT38","v":0},{"$f":"'K80 - time schedule'!JU38","v":0},{"$f":"'K80 - time schedule'!JV38","v":0},{"$f":"'K80 - time schedule'!JW38","v":0},{"$f":"'K80 - time schedule'!JX38","v":0},{"$f":"'K80 - time schedule'!JY38","v":0},{"$f":"'K80 - time schedule'!JZ38","v":0},{"$f":"'K80 - time schedule'!KA38","v":0},{"$f":"'K80 - time schedule'!KB38","v":0},{"$f":"'K80 - time schedule'!KC38","v":0},{"$f":"'K80 - time schedule'!KD38","v":0},{"$f":"'K80 - time schedule'!KE38","v":0},{"$f":"'K80 - time schedule'!KF38","v":0},{"$f":"'K80 - time schedule'!KG38","v":0},{"$f":"'K80 - time schedule'!KH38","v":0},{"$f":"'K80 - time schedule'!KI38","v":0},{"$f":"'K80 - time schedule'!KJ38","v":0},{"$f":"'K80 - time schedule'!KK38","v":0},{"$f":"'K80 - time schedule'!KL38","v":0},{"$f":"'K80 - time schedule'!KM38","v":0},{"$f":"'K80 - time schedule'!KN38","v":0},{"$f":"'K80 - time schedule'!KO38","v":0},{"$f":"'K80 - time schedule'!KP38","v":0},{"$f":"'K80 - time schedule'!KQ38","v":0},{"$f":"'K80 - time schedule'!KR38","v":0},{"$f":"'K80 - time schedule'!KS38","v":0},{"$f":"'K80 - time schedule'!KT38","v":0}]
["Boiler room K80 - management of automatic control system","K80",{"$f":"'K80 - time schedule'!G40","v":0},{"$f":"'K80 - time schedule'!H40","v":0},{"$f":"'K80 - time schedule'!I40","v":0},{"$f":"'K80 - time schedule'!J40","v":0},{"$f":"'K80 - time schedule'!K40","v":0},{"$f":"'K80 - time schedule'!L40","v":0},{"$f":"'K80 - time schedule'!M40","v":0},{"$f":"'K80 - time schedule'!N40","v":0},{"$f":"'K80 - time schedule'!O40","v":0},{"$f":"'K80 - time schedule'!P40","v":0},{"$f":"'K80 - time schedule'!Q40","v":0},{"$f":"'K80 - time schedule'!R40","v":0},{"$f":"'K80 - time schedule'!S40","v":0},{"$f":"'K80 - time schedule'!T40","v":0},{"$f":"'K80 - time schedule'!U40","v":0},{"$f":"'K80 - time schedule'!V40","v":0},{"$f":"'K80 - time schedule'!W40","v":0},{"$f":"'K80 - time schedule'!X40","v":0},{"$f":"'K80 - time schedule'!Y40","v":0},{"$f":"'K80 - time schedule'!Z40","v":0},{"$f":"'K80 - time schedule'!AA40","v":0},{"$f":"'K80 - time schedule'!AB40","v":0},{"$f":"'K80 - time schedule'!AC40","v":0},{"$f":"'K80 - time schedule'!AD40","v":0},{"$f":"'K80 - time schedule'!AE40","v":0},{"$f":"'K80 - time schedule'!AF40","v":0},{"$f":"'K80 - time schedule'!AG40","v":0},{"$f":"'K80 - time schedule'!AH40","v":0},{"$f":"'K80 - time schedule'!AI40","v":0},{"$f":"'K80 - time schedule'!AJ40","v":0},{"$f":"'K80 - time schedule'!AK40","v":0},{"$f":"'K80 - time schedule'!AL40","v":0},{"$f":"'K80 - time schedule'!AM40","v":0},{"$f":"'K80 - time schedule'!AN40","v":0},{"$f":"'K80 - time schedule'!AO40","v":0},{"$f":"'K80 - time schedule'!AP40","v":0},{"$f":"'K80 - time schedule'!AQ40","v":0},{"$f":"'K80 - time schedule'!AR40","v":0},{"$f":"'K80 - time schedule'!AS40","v":0},{"$f":"'K80 - time schedule'!AT40","v":0},{"$f":"'K80 - time schedule'!AU40","v":0},{"$f":"'K80 - time schedule'!AV40","v":0},{"$f":"'K80 - time schedule'!AW40","v":0},{"$f":"'K80 - time schedule'!AX40","v":0},{"$f":"'K80 - time schedule'!AY40","v":0},{"$f":"'K80 - time schedule'!AZ40","v":0},{"$f":"'K80 - time schedule'!BA40","v":0},{"$f":"'K80 - time schedule'!BB40","v":0},{"$f":"'K80 - time schedule'!BC40","v":0},{"$f":"'K80 - time schedule'!BD40","v":0},{"$f":"'K80 - time schedule'!BE40","v":0},{"$f":"'K80 - time schedule'!BF40","v":0},{"$f":"'K80 - time schedule'!BG40","v":0},{"$f":"'K80 - time schedule'!BH40","v":0},{"$f":"'K80 - time schedule'!BI40","v":0},{"$f":"'K80 - time schedule'!BJ40","v":0},{"$f":"'K80 - time schedule'!BK40","v":0},{"$f":"'K80 - time schedule'!BL40","v":0},{"$f":"'K80 - time schedule'!BM40","v":0},{"$f":"'K80 - time schedule'!BN40","v":0},{"$f":"'K80 - time schedule'!BO40","v":0},{"$f":"'K80 - time schedule'!BP40","v":0},{"$f":"'K80 - time schedule'!BQ40","v":0},{"$f":"'K80 - time schedule'!BR40","v":0},{"$f":"'K80 - time schedule'!BS40","v":0},{"$f":"'K80 - time schedule'!BT40","v":0},{"$f":"'K80 - time schedule'!BU40","v":0},{"$f":"'K80 - time schedule'!BV40","v":0},{"$f":"'K80 - time schedule'!BW40","v":0},{"$f":"'K80 - time schedule'!BX40","v":0},{"$f":"'K80 - time schedule'!BY40","v":0},{"$f":"'K80 - time schedule'!BZ40","v":0},{"$f":"'K80 - time schedule'!CA40","v":0},{"$f":"'K80 - time schedule'!CB40","v":0},{"$f":"'K80 - time schedule'!CC40","v":0},{"$f":"'K80 - time schedule'!CD40","v":0},{"$f":"'K80 - time schedule'!CE40","v":0},{"$f":"'K80 - time schedule'!CF40","v":0},{"$f":"'K80 - time schedule'!CG40","v":0},{"$f":"'K80 - time schedule'!CH40","v":0},{"$f":"'K80 - time schedule'!CI40","v":0},{"$f":"'K80 - time schedule'!CJ40","v":0},{"$f":"'K80 - time schedule'!CK40","v":0},{"$f":"'K80 - time schedule'!CL40","v":0},{"$f":"'K80 - time schedule'!CM40","v":0},{"$f":"'K80 - time schedule'!CN40","v":0},{"$f":"'K80 - time schedule'!CO40","v":0},{"$f":"'K80 - time schedule'!CP40","v":0},{"$f":"'K80 - time schedule'!CQ40","v":0},{"$f":"'K80 - time schedule'!CR40","v":0},{"$f":"'K80 - time schedule'!CS40","v":0},{"$f":"'K80 - time schedule'!CT40","v":0},{"$f":"'K80 - time schedule'!CU40","v":0},{"$f":"'K80 - time schedule'!CV40","v":0},{"$f":"'K80 - time schedule'!CW40","v":0},{"$f":"'K80 - time schedule'!CX40","v":0},{"$f":"'K80 - time schedule'!CY40","v":0},{"$f":"'K80 - time schedule'!CZ40","v":0},{"$f":"'K80 - time schedule'!DA40","v":0},{"$f":"'K80 - time schedule'!DB40","v":0},{"$f":"'K80 - time schedule'!DC40","v":0},{"$f":"'K80 - time schedule'!DD40","v":0},{"$f":"'K80 - time schedule'!DE40","v":0},{"$f":"'K80 - time schedule'!DF40","v":0},{"$f":"'K80 - time schedule'!DG40","v":0},{"$f":"'K80 - time schedule'!DH40","v":0},{"$f":"'K80 - time schedule'!DI40","v":0},{"$f":"'K80 - time schedule'!DJ40","v":0},{"$f":"'K80 - time schedule'!DK40","v":0},{"$f":"'K80 - time schedule'!DL40","v":0},{"$f":"'K80 - time schedule'!DM40","v":0},{"$f":"'K80 - time schedule'!DN40","v":0},{"$f":"'K80 - time schedule'!DO40","v":0},{"$f":"'K80 - time schedule'!DP40","v":0},{"$f":"'K80 - time schedule'!DQ40","v":0},{"$f":"'K80 - time schedule'!DR40","v":0},{"$f":"'K80 - time schedule'!DS40","v":0},{"$f":"'K80 - time schedule'!DT40","v":0},{"$f":"'K80 - time schedule'!DU40","v":0},{"$f":"'K80 - time schedule'!DV40","v":0},{"$f":"'K80 - time schedule'!DW40","v":0},{"$f":"'K80 - time schedule'!DX40","v":0},{"$f":"'K80 - time schedule'!DY40","v":0},{"$f":"'K80 - time schedule'!DZ40","v":0},{"$f":"'K80 - time schedule'!EA40","v":0},{"$f":"'K80 - time schedule'!EB40","v":0},{"$f":"'K80 - time schedule'!EC40","v":0},{"$f":"'K80 - time schedule'!ED40","v":0},{"$f":"'K80 - time schedule'!EE40","v":0},{"$f":"'K80 - time schedule'!EF40","v":0},{"$f":"'K80 - time schedule'!EG40","v":0},{"$f":"'K80 - time schedule'!EH40","v":0},{"$f":"'K80 - time schedule'!EI40","v":0},{"$f":"'K80 - time schedule'!EJ40","v":0},{"$f":"'K80 - time schedule'!EK40","v":0},{"$f":"'K80 - time schedule'!EL40","v":0},{"$f":"'K80 - time schedule'!EM40","v":0},{"$f":"'K80 - time schedule'!EN40","v":0},{"$f":"'K80 - time schedule'!EO40","v":0},{"$f":"'K80 - time schedule'!EP40","v":0},{"$f":"'K80 - time schedule'!EQ40","v":0},{"$f":"'K80 - time schedule'!ER40","v":0},{"$f":"'K80 - time schedule'!ES40","v":0},{"$f":"'K80 - time schedule'!ET40","v":0},{"$f":"'K80 - time schedule'!EU40","v":0},{"$f":"'K80 - time schedule'!EV40","v":0},{"$f":"'K80 - time schedule'!EW40","v":0},{"$f":"'K80 - time schedule'!EX40","v":0},{"$f":"'K80 - time schedule'!EY40","v":0},{"$f":"'K80 - time schedule'!EZ40","v":0},{"$f":"'K80 - time schedule'!FA40","v":0},{"$f":"'K80 - time schedule'!FB40","v":0},{"$f":"'K80 - time schedule'!FC40","v":0},{"$f":"'K80 - time schedule'!FD40","v":0},{"$f":"'K80 - time schedule'!FE40","v":0},{"$f":"'K80 - time schedule'!FF40","v":0},{"$f":"'K80 - time schedule'!FG40","v":0},{"$f":"'K80 - time schedule'!FH40","v":0},{"$f":"'K80 - time schedule'!FI40","v":0},{"$f":"'K80 - time schedule'!FJ40","v":0},{"$f":"'K80 - time schedule'!FK40","v":0},{"$f":"'K80 - time schedule'!FL40","v":0},{"$f":"'K80 - time schedule'!FM40","v":0},{"$f":"'K80 - time schedule'!FN40","v":0},{"$f":"'K80 - time schedule'!FO40","v":0},{"$f":"'K80 - time schedule'!FP40","v":0},{"$f":"'K80 - time schedule'!FQ40","v":0},{"$f":"'K80 - time schedule'!FR40","v":0},{"$f":"'K80 - time schedule'!FS40","v":0},{"$f":"'K80 - time schedule'!FT40","v":0},{"$f":"'K80 - time schedule'!FU40","v":0},{"$f":"'K80 - time schedule'!FV40","v":0},{"$f":"'K80 - time schedule'!FW40","v":0},{"$f":"'K80 - time schedule'!FX40","v":0},{"$f":"'K80 - time schedule'!FY40","v":0},{"$f":"'K80 - time schedule'!FZ40","v":0},{"$f":"'K80 - time schedule'!GA40","v":0},{"$f":"'K80 - time schedule'!GB40","v":0},{"$f":"'K80 - time schedule'!GC40","v":0},{"$f":"'K80 - time schedule'!GD40","v":0},{"$f":"'K80 - time schedule'!GE40","v":0},{"$f":"'K80 - time schedule'!GF40","v":0},{"$f":"'K80 - time schedule'!GG40","v":0},{"$f":"'K80 - time schedule'!GH40","v":0},{"$f":"'K80 - time schedule'!GI40","v":0},{"$f":"'K80 - time schedule'!GJ40","v":0},{"$f":"'K80 - time schedule'!GK40","v":0},{"$f":"'K80 - time schedule'!GL40","v":0},{"$f":"'K80 - time schedule'!GM40","v":0},{"$f":"'K80 - time schedule'!GN40","v":0},{"$f":"'K80 - time schedule'!GO40","v":0},{"$f":"'K80 - time schedule'!GP40","v":0},{"$f":"'K80 - time schedule'!GQ40","v":0},{"$f":"'K80 - time schedule'!GR40","v":0},{"$f":"'K80 - time schedule'!GS40","v":0},{"$f":"'K80 - time schedule'!GT40","v":0},{"$f":"'K80 - time schedule'!GU40","v":0},{"$f":"'K80 - time schedule'!GV40","v":0},{"$f":"'K80 - time schedule'!GW40","v":0},{"$f":"'K80 - time schedule'!GX40","v":0},{"$f":"'K80 - time schedule'!GY40","v":0},{"$f":"'K80 - time schedule'!GZ40","v":0},{"$f":"'K80 - time schedule'!HA40","v":0},{"$f":"'K80 - time schedule'!HB40","v":0},{"$f":"'K80 - time schedule'!HC40","v":0},{"$f":"'K80 - time schedule'!HD40","v":0},{"$f":"'K80 - time schedule'!HE40","v":0},{"$f":"'K80 - time schedule'!HF40","v":0},{"$f":"'K80 - time schedule'!HG40","v":0},{"$f":"'K80 - time schedule'!HH40","v":0},{"$f":"'K80 - time schedule'!HI40","v":0},{"$f":"'K80 - time schedule'!HJ40","v":0},{"$f":"'K80 - time schedule'!HK40","v":0},{"$f":"'K80 - time schedule'!HL40","v":0},{"$f":"'K80 - time schedule'!HM40","v":0},{"$f":"'K80 - time schedule'!HN40","v":0},{"$f":"'K80 - time schedule'!HO40","v":0},{"$f":"'K80 - time schedule'!HP40","v":0},{"$f":"'K80 - time schedule'!HQ40","v":0},{"$f":"'K80 - time schedule'!HR40","v":0},{"$f":"'K80 - time schedule'!HS40","v":0},{"$f":"'K80 - time schedule'!HT40","v":0},{"$f":"'K80 - time schedule'!HU40","v":0},{"$f":"'K80 - time schedule'!HV40","v":0},{"$f":"'K80 - time schedule'!HW40","v":0},{"$f":"'K80 - time schedule'!HX40","v":0},{"$f":"'K80 - time schedule'!HY40","v":0},{"$f":"'K80 - time schedule'!HZ40","v":0},{"$f":"'K80 - time schedule'!IA40","v":0},{"$f":"'K80 - time schedule'!IB40","v":0},{"$f":"'K80 - time schedule'!IC40","v":0},{"$f":"'K80 - time schedule'!ID40","v":0},{"$f":"'K80 - time schedule'!IE40","v":0},{"$f":"'K80 - time schedule'!IF40","v":0},{"$f":"'K80 - time schedule'!IG40","v":0},{"$f":"'K80 - time schedule'!IH40","v":0},{"$f":"'K80 - time schedule'!II40","v":0},{"$f":"'K80 - time schedule'!IJ40","v":0},{"$f":"'K80 - time schedule'!IK40","v":0},{"$f":"'K80 - time schedule'!IL40","v":0},{"$f":"'K80 - time schedule'!IM40","v":0},{"$f":"'K80 - time schedule'!IN40","v":0},{"$f":"'K80 - time schedule'!IO40","v":0},{"$f":"'K80 - time schedule'!IP40","v":0},{"$f":"'K80 - time schedule'!IQ40","v":0},{"$f":"'K80 - time schedule'!IR40","v":0},{"$f":"'K80 - time schedule'!IS40","v":0},{"$f":"'K80 - time schedule'!IT40","v":0},{"$f":"'K80 - time schedule'!IU40","v":0},{"$f":"'K80 - time schedule'!IV40","v":0},{"$f":"'K80 - time schedule'!IW40","v":0},{"$f":"'K80 - time schedule'!IX40","v":0},{"$f":"'K80 - time schedule'!IY40","v":0},{"$f":"'K80 - time schedule'!IZ40","v":0},{"$f":"'K80 - time schedule'!JA40","v":0},{"$f":"'K80 - time schedule'!JB40","v":0},{"$f":"'K80 - time schedule'!JC40","v":0},{"$f":"'K80 - time schedule'!JD40","v":0},{"$f":"'K80 - time schedule'!JE40","v":0},{"$f":"'K80 - time schedule'!JF40","v":0},{"$f":"'K80 - time schedule'!JG40","v":0},{"$f":"'K80 - time schedule'!JH40","v":0},{"$f":"'K80 - time schedule'!JI40","v":0},{"$f":"'K80 - time schedule'!JJ40","v":0},{"$f":"'K80 - time schedule'!JK40","v":0},{"$f":"'K80 - time schedule'!JL40","v":0},{"$f":"'K80 - time schedule'!JM40","v":0},{"$f":"'K80 - time schedule'!JN40","v":0},{"$f":"'K80 - time schedule'!JO40","v":0},{"$f":"'K80 - time schedule'!JP40","v":0},{"$f":"'K80 - time schedule'!JQ40","v":0},{"$f":"'K80 - time schedule'!JR40","v":0},{"$f":"'K80 - time schedule'!JS40","v":0},{"$f":"'K80 - time schedule'!JT40","v":0},{"$f":"'K80 - time schedule'!JU40","v":0},{"$f":"'K80 - time schedule'!JV40","v":0},{"$f":"'K80 - time schedule'!JW40","v":0},{"$f":"'K80 - time schedule'!JX40","v":0},{"$f":"'K80 - time schedule'!JY40","v":0},{"$f":"'K80 - time schedule'!JZ40","v":0},{"$f":"'K80 - time schedule'!KA40","v":0},{"$f":"'K80 - time schedule'!KB40","v":0},{"$f":"'K80 - time schedule'!KC40","v":0},{"$f":"'K80 - time schedule'!KD40","v":0},{"$f":"'K80 - time schedule'!KE40","v":0},{"$f":"'K80 - time schedule'!KF40","v":0},{"$f":"'K80 - time schedule'!KG40","v":0},{"$f":"'K80 - time schedule'!KH40","v":0},{"$f":"'K80 - time schedule'!KI40","v":0},{"$f":"'K80 - time schedule'!KJ40","v":0},{"$f":"'K80 - time schedule'!KK40","v":0},{"$f":"'K80 - time schedule'!KL40","v":0},{"$f":"'K80 - time schedule'!KM40","v":0},{"$f":"'K80 - time schedule'!KN40","v":0},{"$f":"'K80 - time schedule'!KO40","v":0},{"$f":"'K80 - time schedule'!KP40","v":0},{"$f":"'K80 - time schedule'!KQ40","v":0},{"$f":"'K80 - time schedule'!KR40","v":0},{"$f":"'K80 - time schedule'!KS40","v":0},{"$f":"'K80 - time schedule'!KT40","v":0}]
["Boiler room K80 - construction structures","K80",{"$f":"'K80 - time schedule'!G42","v":0},{"$f":"'K80 - time schedule'!H42","v":0},{"$f":"'K80 - time schedule'!I42","v":0},{"$f":"'K80 - time schedule'!J42","v":0},{"$f":"'K80 - time schedule'!K42","v":0},{"$f":"'K80 - time schedule'!L42","v":0},{"$f":"'K80 - time schedule'!M42","v":0},{"$f":"'K80 - time schedule'!N42","v":0},{"$f":"'K80 - time schedule'!O42","v":0},{"$f":"'K80 - time schedule'!P42","v":0},{"$f":"'K80 - time schedule'!Q42","v":0},{"$f":"'K80 - time schedule'!R42","v":0},{"$f":"'K80 - time schedule'!S42","v":0},{"$f":"'K80 - time schedule'!T42","v":0},{"$f":"'K80 - time schedule'!U42","v":0},{"$f":"'K80 - time schedule'!V42","v":0},{"$f":"'K80 - time schedule'!W42","v":0},{"$f":"'K80 - time schedule'!X42","v":0},{"$f":"'K80 - time schedule'!Y42","v":0},{"$f":"'K80 - time schedule'!Z42","v":0},{"$f":"'K80 - time schedule'!AA42","v":0},{"$f":"'K80 - time schedule'!AB42","v":0},{"$f":"'K80 - time schedule'!AC42","v":0},{"$f":"'K80 - time schedule'!AD42","v":0},{"$f":"'K80 - time schedule'!AE42","v":0},{"$f":"'K80 - time schedule'!AF42","v":0},{"$f":"'K80 - time schedule'!AG42","v":0},{"$f":"'K80 - time schedule'!AH42","v":0},{"$f":"'K80 - time schedule'!AI42","v":0},{"$f":"'K80 - time schedule'!AJ42","v":0},{"$f":"'K80 - time schedule'!AK42","v":0},{"$f":"'K80 - time schedule'!AL42","v":0},{"$f":"'K80 - time schedule'!AM42","v":0},{"$f":"'K80 - time schedule'!AN42","v":0},{"$f":"'K80 - time schedule'!AO42","v":0},{"$f":"'K80 - time schedule'!AP42","v":0},{"$f":"'K80 - time schedule'!AQ42","v":0},{"$f":"'K80 - time schedule'!AR42","v":0},{"$f":"'K80 - time schedule'!AS42","v":0},{"$f":"'K80 - time schedule'!AT42","v":0},{"$f":"'K80 - time schedule'!AU42","v":0},{"$f":"'K80 - time schedule'!AV42","v":0},{"$f":"'K80 - time schedule'!AW42","v":0},{"$f":"'K80 - time schedule'!AX42","v":0},{"$f":"'K80 - time schedule'!AY42","v":0},{"$f":"'K80 - time schedule'!AZ42","v":0},{"$f":"'K80 - time schedule'!BA42","v":0},{"$f":"'K80 - time schedule'!BB42","v":0},{"$f":"'K80 - time schedule'!BC42","v":0},{"$f":"'K80 - time schedule'!BD42","v":0},{"$f":"'K80 - time schedule'!BE42","v":0},{"$f":"'K80 - time schedule'!BF42","v":0},{"$f":"'K80 - time schedule'!BG42","v":0},{"$f":"'K80 - time schedule'!BH42","v":0},{"$f":"'K80 - time schedule'!BI42","v":0},{"$f":"'K80 - time schedule'!BJ42","v":0},{"$f":"'K80 - time schedule'!BK42","v":0},{"$f":"'K80 - time schedule'!BL42","v":0},{"$f":"'K80 - time schedule'!BM42","v":0},{"$f":"'K80 - time schedule'!BN42","v":0},{"$f":"'K80 - time schedule'!BO42","v":0},{"$f":"'K80 - time schedule'!BP42","v":0},{"$f":"'K80 - time schedule'!BQ42","v":0},{"$f":"'K80 - time schedule'!BR42","v":0},{"$f":"'K80 - time schedule'!BS42","v":0},{"$f":"'K80 - time schedule'!BT42","v":0},{"$f":"'K80 - time schedule'!BU42","v":0},{"$f":"'K80 - time schedule'!BV42","v":0},{"$f":"'K80 - time schedule'!BW42","v":0},{"$f":"'K80 - time schedule'!BX42","v":0},{"$f":"'K80 - time schedule'!BY42","v":0},{"$f":"'K80 - time schedule'!BZ42","v":0},{"$f":"'K80 - time schedule'!CA42","v":0},{"$f":"'K80 - time schedule'!CB42","v":0},{"$f":"'K80 - time schedule'!CC42","v":0},{"$f":"'K80 - time schedule'!CD42","v":0},{"$f":"'K80 - time schedule'!CE42","v":0},{"$f":"'K80 - time schedule'!CF42","v":0},{"$f":"'K80 - time schedule'!CG42","v":0},{"$f":"'K80 - time schedule'!CH42","v":0},{"$f":"'K80 - time schedule'!CI42","v":0},{"$f":"'K80 - time schedule'!CJ42","v":0},{"$f":"'K80 - time schedule'!CK42","v":0},{"$f":"'K80 - time schedule'!CL42","v":0},{"$f":"'K80 - time schedule'!CM42","v":0},{"$f":"'K80 - time schedule'!CN42","v":0},{"$f":"'K80 - time schedule'!CO42","v":0},{"$f":"'K80 - time schedule'!CP42","v":0},{"$f":"'K80 - time schedule'!CQ42","v":0},{"$f":"'K80 - time schedule'!CR42","v":0},{"$f":"'K80 - time schedule'!CS42","v":0},{"$f":"'K80 - time schedule'!CT42","v":0},{"$f":"'K80 - time schedule'!CU42","v":0},{"$f":"'K80 - time schedule'!CV42","v":0},{"$f":"'K80 - time schedule'!CW42","v":0},{"$f":"'K80 - time schedule'!CX42","v":0},{"$f":"'K80 - time schedule'!CY42","v":0},{"$f":"'K80 - time schedule'!CZ42","v":0},{"$f":"'K80 - time schedule'!DA42","v":0},{"$f":"'K80 - time schedule'!DB42","v":0},{"$f":"'K80 - time schedule'!DC42","v":0},{"$f":"'K80 - time schedule'!DD42","v":0},{"$f":"'K80 - time schedule'!DE42","v":0},{"$f":"'K80 - time schedule'!DF42","v":0},{"$f":"'K80 - time schedule'!DG42","v":0},{"$f":"'K80 - time schedule'!DH42","v":0},{"$f":"'K80 - time schedule'!DI42","v":0},{"$f":"'K80 - time schedule'!DJ42","v":0},{"$f":"'K80 - time schedule'!DK42","v":0},{"$f":"'K80 - time schedule'!DL42","v":0},{"$f":"'K80 - time schedule'!DM42","v":0},{"$f":"'K80 - time schedule'!DN42","v":0},{"$f":"'K80 - time schedule'!DO42","v":0},{"$f":"'K80 - time schedule'!DP42","v":0},{"$f":"'K80 - time schedule'!DQ42","v":0},{"$f":"'K80 - time schedule'!DR42","v":0},{"$f":"'K80 - time schedule'!DS42","v":0},{"$f":"'K80 - time schedule'!DT42","v":0},{"$f":"'K80 - time schedule'!DU42","v":0},{"$f":"'K80 - time schedule'!DV42","v":0},{"$f":"'K80 - time schedule'!DW42","v":0},{"$f":"'K80 - time schedule'!DX42","v":0},{"$f":"'K80 - time schedule'!DY42","v":0},{"$f":"'K80 - time schedule'!DZ42","v":0},{"$f":"'K80 - time schedule'!EA42","v":0},{"$f":"'K80 - time schedule'!EB42","v":0},{"$f":"'K80 - time schedule'!EC42","v":0},{"$f":"'K80 - time schedule'!ED42","v":0},{"$f":"'K80 - time schedule'!EE42","v":0},{"$f":"'K80 - time schedule'!EF42","v":0},{"$f":"'K80 - time schedule'!EG42","v":0},{"$f":"'K80 - time schedule'!EH42","v":0},{"$f":"'K80 - time schedule'!EI42","v":0},{"$f":"'K80 - time schedule'!EJ42","v":0},{"$f":"'K80 - time schedule'!EK42","v":0},{"$f":"'K80 - time schedule'!EL42","v":0},{"$f":"'K80 - time schedule'!EM42","v":0},{"$f":"'K80 - time schedule'!EN42","v":0},{"$f":"'K80 - time schedule'!EO42","v":0},{"$f":"'K80 - time schedule'!EP42","v":0},{"$f":"'K80 - time schedule'!EQ42","v":0},{"$f":"'K80 - time schedule'!ER42","v":0},{"$f":"'K80 - time schedule'!ES42","v":0},{"$f":"'K80 - time schedule'!ET42","v":0},{"$f":"'K80 - time schedule'!EU42","v":0},{"$f":"'K80 - time schedule'!EV42","v":0},{"$f":"'K80 - time schedule'!EW42","v":0},{"$f":"'K80 - time schedule'!EX42","v":0},{"$f":"'K80 - time schedule'!EY42","v":0},{"$f":"'K80 - time schedule'!EZ42","v":0},{"$f":"'K80 - time schedule'!FA42","v":0},{"$f":"'K80 - time schedule'!FB42","v":0},{"$f":"'K80 - time schedule'!FC42","v":0},{"$f":"'K80 - time schedule'!FD42","v":0},{"$f":"'K80 - time schedule'!FE42","v":0},{"$f":"'K80 - time schedule'!FF42","v":0},{"$f":"'K80 - time schedule'!FG42","v":0},{"$f":"'K80 - time schedule'!FH42","v":0},{"$f":"'K80 - time schedule'!FI42","v":0},{"$f":"'K80 - time schedule'!FJ42","v":0},{"$f":"'K80 - time schedule'!FK42","v":0},{"$f":"'K80 - time schedule'!FL42","v":0},{"$f":"'K80 - time schedule'!FM42","v":0},{"$f":"'K80 - time schedule'!FN42","v":0},{"$f":"'K80 - time schedule'!FO42","v":0},{"$f":"'K80 - time schedule'!FP42","v":0},{"$f":"'K80 - time schedule'!FQ42","v":0},{"$f":"'K80 - time schedule'!FR42","v":0},{"$f":"'K80 - time schedule'!FS42","v":0},{"$f":"'K80 - time schedule'!FT42","v":0},{"$f":"'K80 - time schedule'!FU42","v":0},{"$f":"'K80 - time schedule'!FV42","v":0},{"$f":"'K80 - time schedule'!FW42","v":0},{"$f":"'K80 - time schedule'!FX42","v":0},{"$f":"'K80 - time schedule'!FY42","v":0},{"$f":"'K80 - time schedule'!FZ42","v":0},{"$f":"'K80 - time schedule'!GA42","v":0},{"$f":"'K80 - time schedule'!GB42","v":0},{"$f":"'K80 - time schedule'!GC42","v":0},{"$f":"'K80 - time schedule'!GD42","v":0},{"$f":"'K80 - time schedule'!GE42","v":0},{"$f":"'K80 - time schedule'!GF42","v":0},{"$f":"'K80 - time schedule'!GG42","v":0},{"$f":"'K80 - time schedule'!GH42","v":0},{"$f":"'K80 - time schedule'!GI42","v":0},{"$f":"'K80 - time schedule'!GJ42","v":0},{"$f":"'K80 - time schedule'!GK42","v":0},{"$f":"'K80 - time schedule'!GL42","v":0},{"$f":"'K80 - time schedule'!GM42","v":0},{"$f":"'K80 - time schedule'!GN42","v":0},{"$f":"'K80 - time schedule'!GO42","v":0},{"$f":"'K80 - time schedule'!GP42","v":0},{"$f":"'K80 - time schedule'!GQ42","v":0},{"$f":"'K80 - time schedule'!GR42","v":0},{"$f":"'K80 - time schedule'!GS42","v":0},{"$f":"'K80 - time schedule'!GT42","v":0},{"$f":"'K80 - time schedule'!GU42","v":0},{"$f":"'K80 - time schedule'!GV42","v":0},{"$f":"'K80 - time schedule'!GW42","v":0},{"$f":"'K80 - time schedule'!GX42","v":0},{"$f":"'K80 - time schedule'!GY42","v":0},{"$f":"'K80 - time schedule'!GZ42","v":0},{"$f":"'K80 - time schedule'!HA42","v":0},{"$f":"'K80 - time schedule'!HB42","v":0},{"$f":"'K80 - time schedule'!HC42","v":0},{"$f":"'K80 - time schedule'!HD42","v":0},{"$f":"'K80 - time schedule'!HE42","v":0},{"$f":"'K80 - time schedule'!HF42","v":0},{"$f":"'K80 - time schedule'!HG42","v":0},{"$f":"'K80 - time schedule'!HH42","v":0},{"$f":"'K80 - time schedule'!HI42","v":0},{"$f":"'K80 - time schedule'!HJ42","v":0},{"$f":"'K80 - time schedule'!HK42","v":0},{"$f":"'K80 - time schedule'!HL42","v":0},{"$f":"'K80 - time schedule'!HM42","v":0},{"$f":"'K80 - time schedule'!HN42","v":0},{"$f":"'K80 - time schedule'!HO42","v":0},{"$f":"'K80 - time schedule'!HP42","v":0},{"$f":"'K80 - time schedule'!HQ42","v":0},{"$f":"'K80 - time schedule'!HR42","v":0},{"$f":"'K80 - time schedule'!HS42","v":0},{"$f":"'K80 - time schedule'!HT42","v":0},{"$f":"'K80 - time schedule'!HU42","v":0},{"$f":"'K80 - time schedule'!HV42","v":0},{"$f":"'K80 - time schedule'!HW42","v":0},{"$f":"'K80 - time schedule'!HX42","v":0},{"$f":"'K80 - time schedule'!HY42","v":0},{"$f":"'K80 - time schedule'!HZ42","v":0},{"$f":"'K80 - time schedule'!IA42","v":0},{"$f":"'K80 - time schedule'!IB42","v":0},{"$f":"'K80 - time schedule'!IC42","v":0},{"$f":"'K80 - time schedule'!ID42","v":0},{"$f":"'K80 - time schedule'!IE42","v":0},{"$f":"'K80 - time schedule'!IF42","v":0},{"$f":"'K80 - time schedule'!IG42","v":0},{"$f":"'K80 - time schedule'!IH42","v":0},{"$f":"'K80 - time schedule'!II42","v":0},{"$f":"'K80 - time schedule'!IJ42","v":0},{"$f":"'K80 - time schedule'!IK42","v":0},{"$f":"'K80 - time schedule'!IL42","v":0},{"$f":"'K80 - time schedule'!IM42","v":0},{"$f":"'K80 - time schedule'!IN42","v":0},{"$f":"'K80 - time schedule'!IO42","v":0},{"$f":"'K80 - time schedule'!IP42","v":0},{"$f":"'K80 - time schedule'!IQ42","v":0},{"$f":"'K80 - time schedule'!IR42","v":0},{"$f":"'K80 - time schedule'!IS42","v":0},{"$f":"'K80 - time schedule'!IT42","v":0},{"$f":"'K80 - time schedule'!IU42","v":0},{"$f":"'K80 - time schedule'!IV42","v":0},{"$f":"'K80 - time schedule'!IW42","v":0},{"$f":"'K80 - time schedule'!IX42","v":0},{"$f":"'K80 - time schedule'!IY42","v":0},{"$f":"'K80 - time schedule'!IZ42","v":0},{"$f":"'K80 - time schedule'!JA42","v":0},{"$f":"'K80 - time schedule'!JB42","v":0},{"$f":"'K80 - time schedule'!JC42","v":0},{"$f":"'K80 - time schedule'!JD42","v":0},{"$f":"'K80 - time schedule'!JE42","v":0},{"$f":"'K80 - time schedule'!JF42","v":0},{"$f":"'K80 - time schedule'!JG42","v":0},{"$f":"'K80 - time schedule'!JH42","v":0},{"$f":"'K80 - time schedule'!JI42","v":0},{"$f":"'K80 - time schedule'!JJ42","v":0},{"$f":"'K80 - time schedule'!JK42","v":0},{"$f":"'K80 - time schedule'!JL42","v":0},{"$f":"'K80 - time schedule'!JM42","v":0},{"$f":"'K80 - time schedule'!JN42","v":0},{"$f":"'K80 - time schedule'!JO42","v":0},{"$f":"'K80 - time schedule'!JP42","v":0},{"$f":"'K80 - time schedule'!JQ42","v":0},{"$f":"'K80 - time schedule'!JR42","v":0},{"$f":"'K80 - time schedule'!JS42","v":0},{"$f":"'K80 - time schedule'!JT42","v":0},{"$f":"'K80 - time schedule'!JU42","v":0},{"$f":"'K80 - time schedule'!JV42","v":0},{"$f":"'K80 - time schedule'!JW42","v":0},{"$f":"'K80 - time schedule'!JX42","v":0},{"$f":"'K80 - time schedule'!JY42","v":0},{"$f":"'K80 - time schedule'!JZ42","v":0},{"$f":"'K80 - time schedule'!KA42","v":0},{"$f":"'K80 - time schedule'!KB42","v":0},{"$f":"'K80 - time schedule'!KC42","v":0},{"$f":"'K80 - time schedule'!KD42","v":0},{"$f":"'K80 - time schedule'!KE42","v":0},{"$f":"'K80 - time schedule'!KF42","v":0},{"$f":"'K80 - time schedule'!KG42","v":0},{"$f":"'K80 - time schedule'!KH42","v":0},{"$f":"'K80 - time schedule'!KI42","v":0},{"$f":"'K80 - time schedule'!KJ42","v":0},{"$f":"'K80 - time schedule'!KK42","v":0},{"$f":"'K80 - time schedule'!KL42","v":0},{"$f":"'K80 - time schedule'!KM42","v":0},{"$f":"'K80 - time schedule'!KN42","v":0},{"$f":"'K80 - time schedule'!KO42","v":0},{"$f":"'K80 - time schedule'!KP42","v":0},{"$f":"'K80 - time schedule'!KQ42","v":0},{"$f":"'K80 - time schedule'!KR42","v":0},{"$f":"'K80 - time schedule'!KS42","v":0},{"$f":"'K80 - time schedule'!KT42","v":0}]
["Boiler room K80 - ash management (transport piping, silos)","K80",{"$f":"'K80 - time schedule'!G44","v":0},{"$f":"'K80 - time schedule'!H44","v":0},{"$f":"'K80 - time schedule'!I44","v":0},{"$f":"'K80 - time schedule'!J44","v":0},{"$f":"'K80 - time schedule'!K44","v":0},{"$f":"'K80 - time schedule'!L44","v":0},{"$f":"'K80 - time schedule'!M44","v":0},{"$f":"'K80 - time schedule'!N44","v":0},{"$f":"'K80 - time schedule'!O44","v":0},{"$f":"'K80 - time schedule'!P44","v":0},{"$f":"'K80 - time schedule'!Q44","v":0},{"$f":"'K80 - time schedule'!R44","v":0},{"$f":"'K80 - time schedule'!S44","v":0},{"$f":"'K80 - time schedule'!T44","v":0},{"$f":"'K80 - time schedule'!U44","v":0},{"$f":"'K80 - time schedule'!V44","v":0},{"$f":"'K80 - time schedule'!W44","v":0},{"$f":"'K80 - time schedule'!X44","v":0},{"$f":"'K80 - time schedule'!Y44","v":0},{"$f":"'K80 - time schedule'!Z44","v":0},{"$f":"'K80 - time schedule'!AA44","v":0},{"$f":"'K80 - time schedule'!AB44","v":0},{"$f":"'K80 - time schedule'!AC44","v":0},{"$f":"'K80 - time schedule'!AD44","v":0},{"$f":"'K80 - time schedule'!AE44","v":0},{"$f":"'K80 - time schedule'!AF44","v":0},{"$f":"'K80 - time schedule'!AG44","v":0},{"$f":"'K80 - time schedule'!AH44","v":0},{"$f":"'K80 - time schedule'!AI44","v":0},{"$f":"'K80 - time schedule'!AJ44","v":0},{"$f":"'K80 - time schedule'!AK44","v":0},{"$f":"'K80 - time schedule'!AL44","v":0},{"$f":"'K80 - time schedule'!AM44","v":0},{"$f":"'K80 - time schedule'!AN44","v":0},{"$f":"'K80 - time schedule'!AO44","v":0},{"$f":"'K80 - time schedule'!AP44","v":0},{"$f":"'K80 - time schedule'!AQ44","v":0},{"$f":"'K80 - time schedule'!AR44","v":0},{"$f":"'K80 - time schedule'!AS44","v":0},{"$f":"'K80 - time schedule'!AT44","v":0},{"$f":"'K80 - time schedule'!AU44","v":0},{"$f":"'K80 - time schedule'!AV44","v":0},{"$f":"'K80 - time schedule'!AW44","v":0},{"$f":"'K80 - time schedule'!AX44","v":0},{"$f":"'K80 - time schedule'!AY44","v":0},{"$f":"'K80 - time schedule'!AZ44","v":0},{"$f":"'K80 - time schedule'!BA44","v":0},{"$f":"'K80 - time schedule'!BB44","v":0},{"$f":"'K80 - time schedule'!BC44","v":0},{"$f":"'K80 - time schedule'!BD44","v":0},{"$f":"'K80 - time schedule'!BE44","v":0},{"$f":"'K80 - time schedule'!BF44","v":0},{"$f":"'K80 - time schedule'!BG44","v":0},{"$f":"'K80 - time schedule'!BH44","v":0},{"$f":"'K80 - time schedule'!BI44","v":0},{"$f":"'K80 - time schedule'!BJ44","v":0},{"$f":"'K80 - time schedule'!BK44","v":0},{"$f":"'K80 - time schedule'!BL44","v":0},{"$f":"'K80 - time schedule'!BM44","v":0},{"$f":"'K80 - time schedule'!BN44","v":0},{"$f":"'K80 - time schedule'!BO44","v":0},{"$f":"'K80 - time schedule'!BP44","v":0},{"$f":"'K80 - time schedule'!BQ44","v":0},{"$f":"'K80 - time schedule'!BR44","v":0},{"$f":"'K80 - time schedule'!BS44","v":0},{"$f":"'K80 - time schedule'!BT44","v":0},{"$f":"'K80 - time schedule'!BU44","v":0},{"$f":"'K80 - time schedule'!BV44","v":0},{"$f":"'K80 - time schedule'!BW44","v":0},{"$f":"'K80 - time schedule'!BX44","v":0},{"$f":"'K80 - time schedule'!BY44","v":0},{"$f":"'K80 - time schedule'!BZ44","v":0},{"$f":"'K80 - time schedule'!CA44","v":0},{"$f":"'K80 - time schedule'!CB44","v":0},{"$f":"'K80 - time schedule'!CC44","v":0},{"$f":"'K80 - time schedule'!CD44","v":0},{"$f":"'K80 - time schedule'!CE44","v":0},{"$f":"'K80 - time schedule'!CF44","v":0},{"$f":"'K80 - time schedule'!CG44","v":0},{"$f":"'K80 - time schedule'!CH44","v":0},{"$f":"'K80 - time schedule'!CI44","v":0},{"$f":"'K80 - time schedule'!CJ44","v":0},{"$f":"'K80 - time schedule'!CK44","v":0},{"$f":"'K80 - time schedule'!CL44","v":0},{"$f":"'K80 - time schedule'!CM44","v":0},{"$f":"'K80 - time schedule'!CN44","v":0},{"$f":"'K80 - time schedule'!CO44","v":0},{"$f":"'K80 - time schedule'!CP44","v":0},{"$f":"'K80 - time schedule'!CQ44","v":0},{"$f":"'K80 - time schedule'!CR44","v":0},{"$f":"'K80 - time schedule'!CS44","v":0},{"$f":"'K80 - time schedule'!CT44","v":0},{"$f":"'K80 - time schedule'!CU44","v":0},{"$f":"'K80 - time schedule'!CV44","v":0},{"$f":"'K80 - time schedule'!CW44","v":0},{"$f":"'K80 - time schedule'!CX44","v":0},{"$f":"'K80 - time schedule'!CY44","v":0},{"$f":"'K80 - time schedule'!CZ44","v":0},{"$f":"'K80 - time schedule'!DA44","v":0},{"$f":"'K80 - time schedule'!DB44","v":0},{"$f":"'K80 - time schedule'!DC44","v":0},{"$f":"'K80 - time schedule'!DD44","v":0},{"$f":"'K80 - time schedule'!DE44","v":0},{"$f":"'K80 - time schedule'!DF44","v":0},{"$f":"'K80 - time schedule'!DG44","v":0},{"$f":"'K80 - time schedule'!DH44","v":0},{"$f":"'K80 - time schedule'!DI44","v":0},{"$f":"'K80 - time schedule'!DJ44","v":0},{"$f":"'K80 - time schedule'!DK44","v":0},{"$f":"'K80 - time schedule'!DL44","v":0},{"$f":"'K80 - time schedule'!DM44","v":0},{"$f":"'K80 - time schedule'!DN44","v":0},{"$f":"'K80 - time schedule'!DO44","v":0},{"$f":"'K80 - time schedule'!DP44","v":0},{"$f":"'K80 - time schedule'!DQ44","v":0},{"$f":"'K80 - time schedule'!DR44","v":0},{"$f":"'K80 - time schedule'!DS44","v":0},{"$f":"'K80 - time schedule'!DT44","v":0},{"$f":"'K80 - time schedule'!DU44","v":0},{"$f":"'K80 - time schedule'!DV44","v":0},{"$f":"'K80 - time schedule'!DW44","v":0},{"$f":"'K80 - time schedule'!DX44","v":0},{"$f":"'K80 - time schedule'!DY44","v":0},{"$f":"'K80 - time schedule'!DZ44","v":0},{"$f":"'K80 - time schedule'!EA44","v":0},{"$f":"'K80 - time schedule'!EB44","v":0},{"$f":"'K80 - time schedule'!EC44","v":0},{"$f":"'K80 - time schedule'!ED44","v":0},{"$f":"'K80 - time schedule'!EE44","v":0},{"$f":"'K80 - time schedule'!EF44","v":0},{"$f":"'K80 - time schedule'!EG44","v":0},{"$f":"'K80 - time schedule'!EH44","v":0},{"$f":"'K80 - time schedule'!EI44","v":0},{"$f":"'K80 - time schedule'!EJ44","v":0},{"$f":"'K80 - time schedule'!EK44","v":0},{"$f":"'K80 - time schedule'!EL44","v":0},{"$f":"'K80 - time schedule'!EM44","v":0},{"$f":"'K80 - time schedule'!EN44","v":0},{"$f":"'K80 - time schedule'!EO44","v":0},{"$f":"'K80 - time schedule'!EP44","v":0},{"$f":"'K80 - time schedule'!EQ44","v":0},{"$f":"'K80 - time schedule'!ER44","v":0},{"$f":"'K80 - time schedule'!ES44","v":0},{"$f":"'K80 - time schedule'!ET44","v":0},{"$f":"'K80 - time schedule'!EU44","v":0},{"$f":"'K80 - time schedule'!EV44","v":0},{"$f":"'K80 - time schedule'!EW44","v":0},{"$f":"'K80 - time schedule'!EX44","v":0},{"$f":"'K80 - time schedule'!EY44","v":0},{"$f":"'K80 - time schedule'!EZ44","v":0},{"$f":"'K80 - time schedule'!FA44","v":0},{"$f":"'K80 - time schedule'!FB44","v":0},{"$f":"'K80 - time schedule'!FC44","v":0},{"$f":"'K80 - time schedule'!FD44","v":0},{"$f":"'K80 - time schedule'!FE44","v":0},{"$f":"'K80 - time schedule'!FF44","v":0},{"$f":"'K80 - time schedule'!FG44","v":0},{"$f":"'K80 - time schedule'!FH44","v":0},{"$f":"'K80 - time schedule'!FI44","v":0},{"$f":"'K80 - time schedule'!FJ44","v":0},{"$f":"'K80 - time schedule'!FK44","v":0},{"$f":"'K80 - time schedule'!FL44","v":0},{"$f":"'K80 - time schedule'!FM44","v":0},{"$f":"'K80 - time schedule'!FN44","v":0},{"$f":"'K80 - time schedule'!FO44","v":0},{"$f":"'K80 - time schedule'!FP44","v":0},{"$f":"'K80 - time schedule'!FQ44","v":0},{"$f":"'K80 - time schedule'!FR44","v":0},{"$f":"'K80 - time schedule'!FS44","v":0},{"$f":"'K80 - time schedule'!FT44","v":0},{"$f":"'K80 - time schedule'!FU44","v":0},{"$f":"'K80 - time schedule'!FV44","v":0},{"$f":"'K80 - time schedule'!FW44","v":0},{"$f":"'K80 - time schedule'!FX44","v":0},{"$f":"'K80 - time schedule'!FY44","v":0},{"$f":"'K80 - time schedule'!FZ44","v":0},{"$f":"'K80 - time schedule'!GA44","v":0},{"$f":"'K80 - time schedule'!GB44","v":0},{"$f":"'K80 - time schedule'!GC44","v":0},{"$f":"'K80 - time schedule'!GD44","v":0},{"$f":"'K80 - time schedule'!GE44","v":0},{"$f":"'K80 - time schedule'!GF44","v":0},{"$f":"'K80 - time schedule'!GG44","v":0},{"$f":"'K80 - time schedule'!GH44","v":0},{"$f":"'K80 - time schedule'!GI44","v":0},{"$f":"'K80 - time schedule'!GJ44","v":0},{"$f":"'K80 - time schedule'!GK44","v":0},{"$f":"'K80 - time schedule'!GL44","v":0},{"$f":"'K80 - time schedule'!GM44","v":0},{"$f":"'K80 - time schedule'!GN44","v":0},{"$f":"'K80 - time schedule'!GO44","v":0},{"$f":"'K80 - time schedule'!GP44","v":0},{"$f":"'K80 - time schedule'!GQ44","v":0},{"$f":"'K80 - time schedule'!GR44","v":0},{"$f":"'K80 - time schedule'!GS44","v":0},{"$f":"'K80 - time schedule'!GT44","v":0},{"$f":"'K80 - time schedule'!GU44","v":0},{"$f":"'K80 - time schedule'!GV44","v":0},{"$f":"'K80 - time schedule'!GW44","v":0},{"$f":"'K80 - time schedule'!GX44","v":0},{"$f":"'K80 - time schedule'!GY44","v":0},{"$f":"'K80 - time schedule'!GZ44","v":0},{"$f":"'K80 - time schedule'!HA44","v":0},{"$f":"'K80 - time schedule'!HB44","v":0},{"$f":"'K80 - time schedule'!HC44","v":0},{"$f":"'K80 - time schedule'!HD44","v":0},{"$f":"'K80 - time schedule'!HE44","v":0},{"$f":"'K80 - time schedule'!HF44","v":0},{"$f":"'K80 - time schedule'!HG44","v":0},{"$f":"'K80 - time schedule'!HH44","v":0},{"$f":"'K80 - time schedule'!HI44","v":0},{"$f":"'K80 - time schedule'!HJ44","v":0},{"$f":"'K80 - time schedule'!HK44","v":0},{"$f":"'K80 - time schedule'!HL44","v":0},{"$f":"'K80 - time schedule'!HM44","v":0},{"$f":"'K80 - time schedule'!HN44","v":0},{"$f":"'K80 - time schedule'!HO44","v":0},{"$f":"'K80 - time schedule'!HP44","v":0},{"$f":"'K80 - time schedule'!HQ44","v":0},{"$f":"'K80 - time schedule'!HR44","v":0},{"$f":"'K80 - time schedule'!HS44","v":0},{"$f":"'K80 - time schedule'!HT44","v":0},{"$f":"'K80 - time schedule'!HU44","v":0},{"$f":"'K80 - time schedule'!HV44","v":0},{"$f":"'K80 - time schedule'!HW44","v":0},{"$f":"'K80 - time schedule'!HX44","v":0},{"$f":"'K80 - time schedule'!HY44","v":0},{"$f":"'K80 - time schedule'!HZ44","v":0},{"$f":"'K80 - time schedule'!IA44","v":0},{"$f":"'K80 - time schedule'!IB44","v":0},{"$f":"'K80 - time schedule'!IC44","v":0},{"$f":"'K80 - time schedule'!ID44","v":0},{"$f":"'K80 - time schedule'!IE44","v":0},{"$f":"'K80 - time schedule'!IF44","v":0},{"$f":"'K80 - time schedule'!IG44","v":0},{"$f":"'K80 - time schedule'!IH44","v":0},{"$f":"'K80 - time schedule'!II44","v":0},{"$f":"'K80 - time schedule'!IJ44","v":0},{"$f":"'K80 - time schedule'!IK44","v":0},{"$f":"'K80 - time schedule'!IL44","v":0},{"$f":"'K80 - time schedule'!IM44","v":0},{"$f":"'K80 - time schedule'!IN44","v":0},{"$f":"'K80 - time schedule'!IO44","v":0},{"$f":"'K80 - time schedule'!IP44","v":0},{"$f":"'K80 - time schedule'!IQ44","v":0},{"$f":"'K80 - time schedule'!IR44","v":0},{"$f":"'K80 - time schedule'!IS44","v":0},{"$f":"'K80 - time schedule'!IT44","v":0},{"$f":"'K80 - time schedule'!IU44","v":0},{"$f":"'K80 - time schedule'!IV44","v":0},{"$f":"'K80 - time schedule'!IW44","v":0},{"$f":"'K80 - time schedule'!IX44","v":0},{"$f":"'K80 - time schedule'!IY44","v":0},{"$f":"'K80 - time schedule'!IZ44","v":0},{"$f":"'K80 - time schedule'!JA44","v":0},{"$f":"'K80 - time schedule'!JB44","v":0},{"$f":"'K80 - time schedule'!JC44","v":0},{"$f":"'K80 - time schedule'!JD44","v":0},{"$f":"'K80 - time schedule'!JE44","v":0},{"$f":"'K80 - time schedule'!JF44","v":0},{"$f":"'K80 - time schedule'!JG44","v":0},{"$f":"'K80 - time schedule'!JH44","v":0},{"$f":"'K80 - time schedule'!JI44","v":0},{"$f":"'K80 - time schedule'!JJ44","v":0},{"$f":"'K80 - time schedule'!JK44","v":0},{"$f":"'K80 - time schedule'!JL44","v":0},{"$f":"'K80 - time schedule'!JM44","v":0},{"$f":"'K80 - time schedule'!JN44","v":0},{"$f":"'K80 - time schedule'!JO44","v":0},{"$f":"'K80 - time schedule'!JP44","v":0},{"$f":"'K80 - time schedule'!JQ44","v":0},{"$f":"'K80 - time schedule'!JR44","v":0},{"$f":"'K80 - time schedule'!JS44","v":0},{"$f":"'K80 - time schedule'!JT44","v":0},{"$f":"'K80 - time schedule'!JU44","v":0},{"$f":"'K80 - time schedule'!JV44","v":0},{"$f":"'K80 - time schedule'!JW44","v":0},{"$f":"'K80 - time schedule'!JX44","v":0},{"$f":"'K80 - time schedule'!JY44","v":0},{"$f":"'K80 - time schedule'!JZ44","v":0},{"$f":"'K80 - time schedule'!KA44","v":0},{"$f":"'K80 - time schedule'!KB44","v":0},{"$f":"'K80 - time schedule'!KC44","v":0},{"$f":"'K80 - time schedule'!KD44","v":0},{"$f":"'K80 - time schedule'!KE44","v":0},{"$f":"'K80 - time schedule'!KF44","v":0},{"$f":"'K80 - time schedule'!KG44","v":0},{"$f":"'K80 - time schedule'!KH44","v":0},{"$f":"'K80 - time schedule'!KI44","v":0},{"$f":"'K80 - time schedule'!KJ44","v":0},{"$f":"'K80 - time schedule'!KK44","v":0},{"$f":"'K80 - time schedule'!KL44","v":0},{"$f":"'K80 - time schedule'!KM44","v":0},{"$f":"'K80 - time schedule'!KN44","v":0},{"$f":"'K80 - time schedule'!KO44","v":0},{"$f":"'K80 - time schedule'!KP44","v":0},{"$f":"'K80 - time schedule'!KQ44","v":0},{"$f":"'K80 - time schedule'!KR44","v":0},{"$f":"'K80 - time schedule'!KS44","v":0},{"$f":"'K80 - time schedule'!KT44","v":0}]
["Boiler room K80 - other above not specified items","K80",{"$f":"'K80 - time schedule'!G46","v":0},{"$f":"'K80 - time schedule'!H46","v":0},{"$f":"'K80 - time schedule'!I46","v":0},{"$f":"'K80 - time schedule'!J46","v":0},{"$f":"'K80 - time schedule'!K46","v":0},{"$f":"'K80 - time schedule'!L46","v":0},{"$f":"'K80 - time schedule'!M46","v":0},{"$f":"'K80 - time schedule'!N46","v":0},{"$f":"'K80 - time schedule'!O46","v":0},{"$f":"'K80 - time schedule'!P46","v":0},{"$f":"'K80 - time schedule'!Q46","v":0},{"$f":"'K80 - time schedule'!R46","v":0},{"$f":"'K80 - time schedule'!S46","v":0},{"$f":"'K80 - time schedule'!T46","v":0},{"$f":"'K80 - time schedule'!U46","v":0},{"$f":"'K80 - time schedule'!V46","v":0},{"$f":"'K80 - time schedule'!W46","v":0},{"$f":"'K80 - time schedule'!X46","v":0},{"$f":"'K80 - time schedule'!Y46","v":0},{"$f":"'K80 - time schedule'!Z46","v":0},{"$f":"'K80 - time schedule'!AA46","v":0},{"$f":"'K80 - time schedule'!AB46","v":0},{"$f":"'K80 - time schedule'!AC46","v":0},{"$f":"'K80 - time schedule'!AD46","v":0},{"$f":"'K80 - time schedule'!AE46","v":0},{"$f":"'K80 - time schedule'!AF46","v":0},{"$f":"'K80 - time schedule'!AG46","v":0},{"$f":"'K80 - time schedule'!AH46","v":0},{"$f":"'K80 - time schedule'!AI46","v":0},{"$f":"'K80 - time schedule'!AJ46","v":0},{"$f":"'K80 - time schedule'!AK46","v":0},{"$f":"'K80 - time schedule'!AL46","v":0},{"$f":"'K80 - time schedule'!AM46","v":0},{"$f":"'K80 - time schedule'!AN46","v":0},{"$f":"'K80 - time schedule'!AO46","v":0},{"$f":"'K80 - time schedule'!AP46","v":0},{"$f":"'K80 - time schedule'!AQ46","v":0},{"$f":"'K80 - time schedule'!AR46","v":0},{"$f":"'K80 - time schedule'!AS46","v":0},{"$f":"'K80 - time schedule'!AT46","v":0},{"$f":"'K80 - time schedule'!AU46","v":0},{"$f":"'K80 - time schedule'!AV46","v":0},{"$f":"'K80 - time schedule'!AW46","v":0},{"$f":"'K80 - time schedule'!AX46","v":0},{"$f":"'K80 - time schedule'!AY46","v":0},{"$f":"'K80 - time schedule'!AZ46","v":0},{"$f":"'K80 - time schedule'!BA46","v":0},{"$f":"'K80 - time schedule'!BB46","v":0},{"$f":"'K80 - time schedule'!BC46","v":0},{"$f":"'K80 - time schedule'!BD46","v":0},{"$f":"'K80 - time schedule'!BE46","v":0},{"$f":"'K80 - time schedule'!BF46","v":0},{"$f":"'K80 - time schedule'!BG46","v":0},{"$f":"'K80 - time schedule'!BH46","v":0},{"$f":"'K80 - time schedule'!BI46","v":0},{"$f":"'K80 - time schedule'!BJ46","v":0},{"$f":"'K80 - time schedule'!BK46","v":0},{"$f":"'K80 - time schedule'!BL46","v":0},{"$f":"'K80 - time schedule'!BM46","v":0},{"$f":"'K80 - time schedule'!BN46","v":0},{"$f":"'K80 - time schedule'!BO46","v":0},{"$f":"'K80 - time schedule'!BP46","v":0},{"$f":"'K80 - time schedule'!BQ46","v":0},{"$f":"'K80 - time schedule'!BR46","v":0},{"$f":"'K80 - time schedule'!BS46","v":0},{"$f":"'K80 - time schedule'!BT46","v":0},{"$f":"'K80 - time schedule'!BU46","v":0},{"$f":"'K80 - time schedule'!BV46","v":0},{"$f":"'K80 - time schedule'!BW46","v":0},{"$f":"'K80 - time schedule'!BX46","v":0},{"$f":"'K80 - time schedule'!BY46","v":0},{"$f":"'K80 - time schedule'!BZ46","v":0},{"$f":"'K80 - time schedule'!CA46","v":0},{"$f":"'K80 - time schedule'!CB46","v":0},{"$f":"'K80 - time schedule'!CC46","v":0},{"$f":"'K80 - time schedule'!CD46","v":0},{"$f":"'K80 - time schedule'!CE46","v":0},{"$f":"'K80 - time schedule'!CF46","v":0},{"$f":"'K80 - time schedule'!CG46","v":0},{"$f":"'K80 - time schedule'!CH46","v":0},{"$f":"'K80 - time schedule'!CI46","v":0},{"$f":"'K80 - time schedule'!CJ46","v":0},{"$f":"'K80 - time schedule'!CK46","v":0},{"$f":"'K80 - time schedule'!CL46","v":0},{"$f":"'K80 - time schedule'!CM46","v":0},{"$f":"'K80 - time schedule'!CN46","v":0},{"$f":"'K80 - time schedule'!CO46","v":0},{"$f":"'K80 - time schedule'!CP46","v":0},{"$f":"'K80 - time schedule'!CQ46","v":0},{"$f":"'K80 - time schedule'!CR46","v":0},{"$f":"'K80 - time schedule'!CS46","v":0},{"$f":"'K80 - time schedule'!CT46","v":0},{"$f":"'K80 - time schedule'!CU46","v":0},{"$f":"'K80 - time schedule'!CV46","v":0},{"$f":"'K80 - time schedule'!CW46","v":0},{"$f":"'K80 - time schedule'!CX46","v":0},{"$f":"'K80 - time schedule'!CY46","v":0},{"$f":"'K80 - time schedule'!CZ46","v":0},{"$f":"'K80 - time schedule'!DA46","v":0},{"$f":"'K80 - time schedule'!DB46","v":0},{"$f":"'K80 - time schedule'!DC46","v":0},{"$f":"'K80 - time schedule'!DD46","v":0},{"$f":"'K80 - time schedule'!DE46","v":0},{"$f":"'K80 - time schedule'!DF46","v":0},{"$f":"'K80 - time schedule'!DG46","v":0},{"$f":"'K80 - time schedule'!DH46","v":0},{"$f":"'K80 - time schedule'!DI46","v":0},{"$f":"'K80 - time schedule'!DJ46","v":0},{"$f":"'K80 - time schedule'!DK46","v":0},{"$f":"'K80 - time schedule'!DL46","v":0},{"$f":"'K80 - time schedule'!DM46","v":0},{"$f":"'K80 - time schedule'!DN46","v":0},{"$f":"'K80 - time schedule'!DO46","v":0},{"$f":"'K80 - time schedule'!DP46","v":0},{"$f":"'K80 - time schedule'!DQ46","v":0},{"$f":"'K80 - time schedule'!DR46","v":0},{"$f":"'K80 - time schedule'!DS46","v":0},{"$f":"'K80 - time schedule'!DT46","v":0},{"$f":"'K80 - time schedule'!DU46","v":0},{"$f":"'K80 - time schedule'!DV46","v":0},{"$f":"'K80 - time schedule'!DW46","v":0},{"$f":"'K80 - time schedule'!DX46","v":0},{"$f":"'K80 - time schedule'!DY46","v":0},{"$f":"'K80 - time schedule'!DZ46","v":0},{"$f":"'K80 - time schedule'!EA46","v":0},{"$f":"'K80 - time schedule'!EB46","v":0},{"$f":"'K80 - time schedule'!EC46","v":0},{"$f":"'K80 - time schedule'!ED46","v":0},{"$f":"'K80 - time schedule'!EE46","v":0},{"$f":"'K80 - time schedule'!EF46","v":0},{"$f":"'K80 - time schedule'!EG46","v":0},{"$f":"'K80 - time schedule'!EH46","v":0},{"$f":"'K80 - time schedule'!EI46","v":0},{"$f":"'K80 - time schedule'!EJ46","v":0},{"$f":"'K80 - time schedule'!EK46","v":0},{"$f":"'K80 - time schedule'!EL46","v":0},{"$f":"'K80 - time schedule'!EM46","v":0},{"$f":"'K80 - time schedule'!EN46","v":0},{"$f":"'K80 - time schedule'!EO46","v":0},{"$f":"'K80 - time schedule'!EP46","v":0},{"$f":"'K80 - time schedule'!EQ46","v":0},{"$f":"'K80 - time schedule'!ER46","v":0},{"$f":"'K80 - time schedule'!ES46","v":0},{"$f":"'K80 - time schedule'!ET46","v":0},{"$f":"'K80 - time schedule'!EU46","v":0},{"$f":"'K80 - time schedule'!EV46","v":0},{"$f":"'K80 - time schedule'!EW46","v":0},{"$f":"'K80 - time schedule'!EX46","v":0},{"$f":"'K80 - time schedule'!EY46","v":0},{"$f":"'K80 - time schedule'!EZ46","v":0},{"$f":"'K80 - time schedule'!FA46","v":0},{"$f":"'K80 - time schedule'!FB46","v":0},{"$f":"'K80 - time schedule'!FC46","v":0},{"$f":"'K80 - time schedule'!FD46","v":0},{"$f":"'K80 - time schedule'!FE46","v":0},{"$f":"'K80 - time schedule'!FF46","v":0},{"$f":"'K80 - time schedule'!FG46","v":0},{"$f":"'K80 - time schedule'!FH46","v":0},{"$f":"'K80 - time schedule'!FI46","v":0},{"$f":"'K80 - time schedule'!FJ46","v":0},{"$f":"'K80 - time schedule'!FK46","v":0},{"$f":"'K80 - time schedule'!FL46","v":0},{"$f":"'K80 - time schedule'!FM46","v":0},{"$f":"'K80 - time schedule'!FN46","v":0},{"$f":"'K80 - time schedule'!FO46","v":0},{"$f":"'K80 - time schedule'!FP46","v":0},{"$f":"'K80 - time schedule'!FQ46","v":0},{"$f":"'K80 - time schedule'!FR46","v":0},{"$f":"'K80 - time schedule'!FS46","v":0},{"$f":"'K80 - time schedule'!FT46","v":0},{"$f":"'K80 - time schedule'!FU46","v":0},{"$f":"'K80 - time schedule'!FV46","v":0},{"$f":"'K80 - time schedule'!FW46","v":0},{"$f":"'K80 - time schedule'!FX46","v":0},{"$f":"'K80 - time schedule'!FY46","v":0},{"$f":"'K80 - time schedule'!FZ46","v":0},{"$f":"'K80 - time schedule'!GA46","v":0},{"$f":"'K80 - time schedule'!GB46","v":0},{"$f":"'K80 - time schedule'!GC46","v":0},{"$f":"'K80 - time schedule'!GD46","v":0},{"$f":"'K80 - time schedule'!GE46","v":0},{"$f":"'K80 - time schedule'!GF46","v":0},{"$f":"'K80 - time schedule'!GG46","v":0},{"$f":"'K80 - time schedule'!GH46","v":0},{"$f":"'K80 - time schedule'!GI46","v":0},{"$f":"'K80 - time schedule'!GJ46","v":0},{"$f":"'K80 - time schedule'!GK46","v":0},{"$f":"'K80 - time schedule'!GL46","v":0},{"$f":"'K80 - time schedule'!GM46","v":0},{"$f":"'K80 - time schedule'!GN46","v":0},{"$f":"'K80 - time schedule'!GO46","v":0},{"$f":"'K80 - time schedule'!GP46","v":0},{"$f":"'K80 - time schedule'!GQ46","v":0},{"$f":"'K80 - time schedule'!GR46","v":0},{"$f":"'K80 - time schedule'!GS46","v":0},{"$f":"'K80 - time schedule'!GT46","v":0},{"$f":"'K80 - time schedule'!GU46","v":0},{"$f":"'K80 - time schedule'!GV46","v":0},{"$f":"'K80 - time schedule'!GW46","v":0},{"$f":"'K80 - time schedule'!GX46","v":0},{"$f":"'K80 - time schedule'!GY46","v":0},{"$f":"'K80 - time schedule'!GZ46","v":0},{"$f":"'K80 - time schedule'!HA46","v":0},{"$f":"'K80 - time schedule'!HB46","v":0},{"$f":"'K80 - time schedule'!HC46","v":0},{"$f":"'K80 - time schedule'!HD46","v":0},{"$f":"'K80 - time schedule'!HE46","v":0},{"$f":"'K80 - time schedule'!HF46","v":0},{"$f":"'K80 - time schedule'!HG46","v":0},{"$f":"'K80 - time schedule'!HH46","v":0},{"$f":"'K80 - time schedule'!HI46","v":0},{"$f":"'K80 - time schedule'!HJ46","v":0},{"$f":"'K80 - time schedule'!HK46","v":0},{"$f":"'K80 - time schedule'!HL46","v":0},{"$f":"'K80 - time schedule'!HM46","v":0},{"$f":"'K80 - time schedule'!HN46","v":0},{"$f":"'K80 - time schedule'!HO46","v":0},{"$f":"'K80 - time schedule'!HP46","v":0},{"$f":"'K80 - time schedule'!HQ46","v":0},{"$f":"'K80 - time schedule'!HR46","v":0},{"$f":"'K80 - time schedule'!HS46","v":0},{"$f":"'K80 - time schedule'!HT46","v":0},{"$f":"'K80 - time schedule'!HU46","v":0},{"$f":"'K80 - time schedule'!HV46","v":0},{"$f":"'K80 - time schedule'!HW46","v":0},{"$f":"'K80 - time schedule'!HX46","v":0},{"$f":"'K80 - time schedule'!HY46","v":0},{"$f":"'K80 - time schedule'!HZ46","v":0},{"$f":"'K80 - time schedule'!IA46","v":0},{"$f":"'K80 - time schedule'!IB46","v":0},{"$f":"'K80 - time schedule'!IC46","v":0},{"$f":"'K80 - time schedule'!ID46","v":0},{"$f":"'K80 - time schedule'!IE46","v":0},{"$f":"'K80 - time schedule'!IF46","v":0},{"$f":"'K80 - time schedule'!IG46","v":0},{"$f":"'K80 - time schedule'!IH46","v":0},{"$f":"'K80 - time schedule'!II46","v":0},{"$f":"'K80 - time schedule'!IJ46","v":0},{"$f":"'K80 - time schedule'!IK46","v":0},{"$f":"'K80 - time schedule'!IL46","v":0},{"$f":"'K80 - time schedule'!IM46","v":0},{"$f":"'K80 - time schedule'!IN46","v":0},{"$f":"'K80 - time schedule'!IO46","v":0},{"$f":"'K80 - time schedule'!IP46","v":0},{"$f":"'K80 - time schedule'!IQ46","v":0},{"$f":"'K80 - time schedule'!IR46","v":0},{"$f":"'K80 - time schedule'!IS46","v":0},{"$f":"'K80 - time schedule'!IT46","v":0},{"$f":"'K80 - time schedule'!IU46","v":0},{"$f":"'K80 - time schedule'!IV46","v":0},{"$f":"'K80 - time schedule'!IW46","v":0},{"$f":"'K80 - time schedule'!IX46","v":0},{"$f":"'K80 - time schedule'!IY46","v":0},{"$f":"'K80 - time schedule'!IZ46","v":0},{"$f":"'K80 - time schedule'!JA46","v":0},{"$f":"'K80 - time schedule'!JB46","v":0},{"$f":"'K80 - time schedule'!JC46","v":0},{"$f":"'K80 - time schedule'!JD46","v":0},{"$f":"'K80 - time schedule'!JE46","v":0},{"$f":"'K80 - time schedule'!JF46","v":0},{"$f":"'K80 - time schedule'!JG46","v":0},{"$f":"'K80 - time schedule'!JH46","v":0},{"$f":"'K80 - time schedule'!JI46","v":0},{"$f":"'K80 - time schedule'!JJ46","v":0},{"$f":"'K80 - time schedule'!JK46","v":0},{"$f":"'K80 - time schedule'!JL46","v":0},{"$f":"'K80 - time schedule'!JM46","v":0},{"$f":"'K80 - time schedule'!JN46","v":0},{"$f":"'K80 - time schedule'!JO46","v":0},{"$f":"'K80 - time schedule'!JP46","v":0},{"$f":"'K80 - time schedule'!JQ46","v":0},{"$f":"'K80 - time schedule'!JR46","v":0},{"$f":"'K80 - time schedule'!JS46","v":0},{"$f":"'K80 - time schedule'!JT46","v":0},{"$f":"'K80 - time schedule'!JU46","v":0},{"$f":"'K80 - time schedule'!JV46","v":0},{"$f":"'K80 - time schedule'!JW46","v":0},{"$f":"'K80 - time schedule'!JX46","v":0},{"$f":"'K80 - time schedule'!JY46","v":0},{"$f":"'K80 - time schedule'!JZ46","v":0},{"$f":"'K80 - time schedule'!KA46","v":0},{"$f":"'K80 - time schedule'!KB46","v":0},{"$f":"'K80 - time schedule'!KC46","v":0},{"$f":"'K80 - time schedule'!KD46","v":0},{"$f":"'K80 - time schedule'!KE46","v":0},{"$f":"'K80 - time schedule'!KF46","v":0},{"$f":"'K80 - time schedule'!KG46","v":0},{"$f":"'K80 - time schedule'!KH46","v":0},{"$f":"'K80 - time schedule'!KI46","v":0},{"$f":"'K80 - time schedule'!KJ46","v":0},{"$f":"'K80 - time schedule'!KK46","v":0},{"$f":"'K80 - time schedule'!KL46","v":0},{"$f":"'K80 - time schedule'!KM46","v":0},{"$f":"'K80 - time schedule'!KN46","v":0},{"$f":"'K80 - time schedule'!KO46","v":0},{"$f":"'K80 - time schedule'!KP46","v":0},{"$f":"'K80 - time schedule'!KQ46","v":0},{"$f":"'K80 - time schedule'!KR46","v":0},{"$f":"'K80 - time schedule'!KS46","v":0},{"$f":"'K80 - time schedule'!KT46","v":0}]
["Boiler room K80 - completion of construction works","K80",{"$f":"'K80 - time schedule'!G48","v":0},{"$f":"'K80 - time schedule'!H48","v":0},{"$f":"'K80 - time schedule'!I48","v":0},{"$f":"'K80 - time schedule'!J48","v":0},{"$f":"'K80 - time schedule'!K48","v":0},{"$f":"'K80 - time schedule'!L48","v":0},{"$f":"'K80 - time schedule'!M48","v":0},{"$f":"'K80 - time schedule'!N48","v":0},{"$f":"'K80 - time schedule'!O48","v":0},{"$f":"'K80 - time schedule'!P48","v":0},{"$f":"'K80 - time schedule'!Q48","v":0},{"$f":"'K80 - time schedule'!R48","v":0},{"$f":"'K80 - time schedule'!S48","v":0},{"$f":"'K80 - time schedule'!T48","v":0},{"$f":"'K80 - time schedule'!U48","v":0},{"$f":"'K80 - time schedule'!V48","v":0},{"$f":"'K80 - time schedule'!W48","v":0},{"$f":"'K80 - time schedule'!X48","v":0},{"$f":"'K80 - time schedule'!Y48","v":0},{"$f":"'K80 - time schedule'!Z48","v":0},{"$f":"'K80 - time schedule'!AA48","v":0},{"$f":"'K80 - time schedule'!AB48","v":0},{"$f":"'K80 - time schedule'!AC48","v":0},{"$f":"'K80 - time schedule'!AD48","v":0},{"$f":"'K80 - time schedule'!AE48","v":0},{"$f":"'K80 - time schedule'!AF48","v":0},{"$f":"'K80 - time schedule'!AG48","v":0},{"$f":"'K80 - time schedule'!AH48","v":0},{"$f":"'K80 - time schedule'!AI48","v":0},{"$f":"'K80 - time schedule'!AJ48","v":0},{"$f":"'K80 - time schedule'!AK48","v":0},{"$f":"'K80 - time schedule'!AL48","v":0},{"$f":"'K80 - time schedule'!AM48","v":0},{"$f":"'K80 - time schedule'!AN48","v":0},{"$f":"'K80 - time schedule'!AO48","v":0},{"$f":"'K80 - time schedule'!AP48","v":0},{"$f":"'K80 - time schedule'!AQ48","v":0},{"$f":"'K80 - time schedule'!AR48","v":0},{"$f":"'K80 - time schedule'!AS48","v":0},{"$f":"'K80 - time schedule'!AT48","v":0},{"$f":"'K80 - time schedule'!AU48","v":0},{"$f":"'K80 - time schedule'!AV48","v":0},{"$f":"'K80 - time schedule'!AW48","v":0},{"$f":"'K80 - time schedule'!AX48","v":0},{"$f":"'K80 - time schedule'!AY48","v":0},{"$f":"'K80 - time schedule'!AZ48","v":0},{"$f":"'K80 - time schedule'!BA48","v":0},{"$f":"'K80 - time schedule'!BB48","v":0},{"$f":"'K80 - time schedule'!BC48","v":0},{"$f":"'K80 - time schedule'!BD48","v":0},{"$f":"'K80 - time schedule'!BE48","v":0},{"$f":"'K80 - time schedule'!BF48","v":0},{"$f":"'K80 - time schedule'!BG48","v":0},{"$f":"'K80 - time schedule'!BH48","v":0},{"$f":"'K80 - time schedule'!BI48","v":0},{"$f":"'K80 - time schedule'!BJ48","v":0},{"$f":"'K80 - time schedule'!BK48","v":0},{"$f":"'K80 - time schedule'!BL48","v":0},{"$f":"'K80 - time schedule'!BM48","v":0},{"$f":"'K80 - time schedule'!BN48","v":0},{"$f":"'K80 - time schedule'!BO48","v":0},{"$f":"'K80 - time schedule'!BP48","v":0},{"$f":"'K80 - time schedule'!BQ48","v":0},{"$f":"'K80 - time schedule'!BR48","v":0},{"$f":"'K80 - time schedule'!BS48","v":0},{"$f":"'K80 - time schedule'!BT48","v":0},{"$f":"'K80 - time schedule'!BU48","v":0},{"$f":"'K80 - time schedule'!BV48","v":0},{"$f":"'K80 - time schedule'!BW48","v":0},{"$f":"'K80 - time schedule'!BX48","v":0},{"$f":"'K80 - time schedule'!BY48","v":0},{"$f":"'K80 - time schedule'!BZ48","v":0},{"$f":"'K80 - time schedule'!CA48","v":0},{"$f":"'K80 - time schedule'!CB48","v":0},{"$f":"'K80 - time schedule'!CC48","v":0},{"$f":"'K80 - time schedule'!CD48","v":0},{"$f":"'K80 - time schedule'!CE48","v":0},{"$f":"'K80 - time schedule'!CF48","v":0},{"$f":"'K80 - time schedule'!CG48","v":0},{"$f":"'K80 - time schedule'!CH48","v":0},{"$f":"'K80 - time schedule'!CI48","v":0},{"$f":"'K80 - time schedule'!CJ48","v":0},{"$f":"'K80 - time schedule'!CK48","v":0},{"$f":"'K80 - time schedule'!CL48","v":0},{"$f":"'K80 - time schedule'!CM48","v":0},{"$f":"'K80 - time schedule'!CN48","v":0},{"$f":"'K80 - time schedule'!CO48","v":0},{"$f":"'K80 - time schedule'!CP48","v":0},{"$f":"'K80 - time schedule'!CQ48","v":0},{"$f":"'K80 - time schedule'!CR48","v":0},{"$f":"'K80 - time schedule'!CS48","v":0},{"$f":"'K80 - time schedule'!CT48","v":0},{"$f":"'K80 - time schedule'!CU48","v":0},{"$f":"'K80 - time schedule'!CV48","v":0},{"$f":"'K80 - time schedule'!CW48","v":0},{"$f":"'K80 - time schedule'!CX48","v":0},{"$f":"'K80 - time schedule'!CY48","v":0},{"$f":"'K80 - time schedule'!CZ48","v":0},{"$f":"'K80 - time schedule'!DA48","v":0},{"$f":"'K80 - time schedule'!DB48","v":0},{"$f":"'K80 - time schedule'!DC48","v":0},{"$f":"'K80 - time schedule'!DD48","v":0},{"$f":"'K80 - time schedule'!DE48","v":0},{"$f":"'K80 - time schedule'!DF48","v":0},{"$f":"'K80 - time schedule'!DG48","v":0},{"$f":"'K80 - time schedule'!DH48","v":0},{"$f":"'K80 - time schedule'!DI48","v":0},{"$f":"'K80 - time schedule'!DJ48","v":0},{"$f":"'K80 - time schedule'!DK48","v":0},{"$f":"'K80 - time schedule'!DL48","v":0},{"$f":"'K80 - time schedule'!DM48","v":0},{"$f":"'K80 - time schedule'!DN48","v":0},{"$f":"'K80 - time schedule'!DO48","v":0},{"$f":"'K80 - time schedule'!DP48","v":0},{"$f":"'K80 - time schedule'!DQ48","v":0},{"$f":"'K80 - time schedule'!DR48","v":0},{"$f":"'K80 - time schedule'!DS48","v":0},{"$f":"'K80 - time schedule'!DT48","v":0},{"$f":"'K80 - time schedule'!DU48","v":0},{"$f":"'K80 - time schedule'!DV48","v":0},{"$f":"'K80 - time schedule'!DW48","v":0},{"$f":"'K80 - time schedule'!DX48","v":0},{"$f":"'K80 - time schedule'!DY48","v":0},{"$f":"'K80 - time schedule'!DZ48","v":0},{"$f":"'K80 - time schedule'!EA48","v":0},{"$f":"'K80 - time schedule'!EB48","v":0},{"$f":"'K80 - time schedule'!EC48","v":0},{"$f":"'K80 - time schedule'!ED48","v":0},{"$f":"'K80 - time schedule'!EE48","v":0},{"$f":"'K80 - time schedule'!EF48","v":0},{"$f":"'K80 - time schedule'!EG48","v":0},{"$f":"'K80 - time schedule'!EH48","v":0},{"$f":"'K80 - time schedule'!EI48","v":0},{"$f":"'K80 - time schedule'!EJ48","v":0},{"$f":"'K80 - time schedule'!EK48","v":0},{"$f":"'K80 - time schedule'!EL48","v":0},{"$f":"'K80 - time schedule'!EM48","v":0},{"$f":"'K80 - time schedule'!EN48","v":0},{"$f":"'K80 - time schedule'!EO48","v":0},{"$f":"'K80 - time schedule'!EP48","v":0},{"$f":"'K80 - time schedule'!EQ48","v":0},{"$f":"'K80 - time schedule'!ER48","v":0},{"$f":"'K80 - time schedule'!ES48","v":0},{"$f":"'K80 - time schedule'!ET48","v":0},{"$f":"'K80 - time schedule'!EU48","v":0},{"$f":"'K80 - time schedule'!EV48","v":0},{"$f":"'K80 - time schedule'!EW48","v":0},{"$f":"'K80 - time schedule'!EX48","v":0},{"$f":"'K80 - time schedule'!EY48","v":0},{"$f":"'K80 - time schedule'!EZ48","v":0},{"$f":"'K80 - time schedule'!FA48","v":0},{"$f":"'K80 - time schedule'!FB48","v":0},{"$f":"'K80 - time schedule'!FC48","v":0},{"$f":"'K80 - time schedule'!FD48","v":0},{"$f":"'K80 - time schedule'!FE48","v":0},{"$f":"'K80 - time schedule'!FF48","v":0},{"$f":"'K80 - time schedule'!FG48","v":0},{"$f":"'K80 - time schedule'!FH48","v":0},{"$f":"'K80 - time schedule'!FI48","v":0},{"$f":"'K80 - time schedule'!FJ48","v":0},{"$f":"'K80 - time schedule'!FK48","v":0},{"$f":"'K80 - time schedule'!FL48","v":0},{"$f":"'K80 - time schedule'!FM48","v":0},{"$f":"'K80 - time schedule'!FN48","v":0},{"$f":"'K80 - time schedule'!FO48","v":0},{"$f":"'K80 - time schedule'!FP48","v":0},{"$f":"'K80 - time schedule'!FQ48","v":0},{"$f":"'K80 - time schedule'!FR48","v":0},{"$f":"'K80 - time schedule'!FS48","v":0},{"$f":"'K80 - time schedule'!FT48","v":0},{"$f":"'K80 - time schedule'!FU48","v":0},{"$f":"'K80 - time schedule'!FV48","v":0},{"$f":"'K80 - time schedule'!FW48","v":0},{"$f":"'K80 - time schedule'!FX48","v":0},{"$f":"'K80 - time schedule'!FY48","v":0},{"$f":"'K80 - time schedule'!FZ48","v":0},{"$f":"'K80 - time schedule'!GA48","v":0},{"$f":"'K80 - time schedule'!GB48","v":0},{"$f":"'K80 - time schedule'!GC48","v":0},{"$f":"'K80 - time schedule'!GD48","v":0},{"$f":"'K80 - time schedule'!GE48","v":0},{"$f":"'K80 - time schedule'!GF48","v":0},{"$f":"'K80 - time schedule'!GG48","v":0},{"$f":"'K80 - time schedule'!GH48","v":0},{"$f":"'K80 - time schedule'!GI48","v":0},{"$f":"'K80 - time schedule'!GJ48","v":0},{"$f":"'K80 - time schedule'!GK48","v":0},{"$f":"'K80 - time schedule'!GL48","v":0},{"$f":"'K80 - time schedule'!GM48","v":0},{"$f":"'K80 - time schedule'!GN48","v":0},{"$f":"'K80 - time schedule'!GO48","v":0},{"$f":"'K80 - time schedule'!GP48","v":0},{"$f":"'K80 - time schedule'!GQ48","v":0},{"$f":"'K80 - time schedule'!GR48","v":0},{"$f":"'K80 - time schedule'!GS48","v":0},{"$f":"'K80 - time schedule'!GT48","v":0},{"$f":"'K80 - time schedule'!GU48","v":0},{"$f":"'K80 - time schedule'!GV48","v":0},{"$f":"'K80 - time schedule'!GW48","v":0},{"$f":"'K80 - time schedule'!GX48","v":0},{"$f":"'K80 - time schedule'!GY48","v":0},{"$f":"'K80 - time schedule'!GZ48","v":0},{"$f":"'K80 - time schedule'!HA48","v":0},{"$f":"'K80 - time schedule'!HB48","v":0},{"$f":"'K80 - time schedule'!HC48","v":0},{"$f":"'K80 - time schedule'!HD48","v":0},{"$f":"'K80 - time schedule'!HE48","v":0},{"$f":"'K80 - time schedule'!HF48","v":0},{"$f":"'K80 - time schedule'!HG48","v":0},{"$f":"'K80 - time schedule'!HH48","v":0},{"$f":"'K80 - time schedule'!HI48","v":0},{"$f":"'K80 - time schedule'!HJ48","v":0},{"$f":"'K80 - time schedule'!HK48","v":0},{"$f":"'K80 - time schedule'!HL48","v":0},{"$f":"'K80 - time schedule'!HM48","v":0},{"$f":"'K80 - time schedule'!HN48","v":0},{"$f":"'K80 - time schedule'!HO48","v":0},{"$f":"'K80 - time schedule'!HP48","v":0},{"$f":"'K80 - time schedule'!HQ48","v":0},{"$f":"'K80 - time schedule'!HR48","v":0},{"$f":"'K80 - time schedule'!HS48","v":0},{"$f":"'K80 - time schedule'!HT48","v":0},{"$f":"'K80 - time schedule'!HU48","v":0},{"$f":"'K80 - time schedule'!HV48","v":0},{"$f":"'K80 - time schedule'!HW48","v":0},{"$f":"'K80 - time schedule'!HX48","v":0},{"$f":"'K80 - time schedule'!HY48","v":0},{"$f":"'K80 - time schedule'!HZ48","v":0},{"$f":"'K80 - time schedule'!IA48","v":0},{"$f":"'K80 - time schedule'!IB48","v":0},{"$f":"'K80 - time schedule'!IC48","v":0},{"$f":"'K80 - time schedule'!ID48","v":0},{"$f":"'K80 - time schedule'!IE48","v":0},{"$f":"'K80 - time schedule'!IF48","v":0},{"$f":"'K80 - time schedule'!IG48","v":0},{"$f":"'K80 - time schedule'!IH48","v":0},{"$f":"'K80 - time schedule'!II48","v":0},{"$f":"'K80 - time schedule'!IJ48","v":0},{"$f":"'K80 - time schedule'!IK48","v":0},{"$f":"'K80 - time schedule'!IL48","v":0},{"$f":"'K80 - time schedule'!IM48","v":0},{"$f":"'K80 - time schedule'!IN48","v":0},{"$f":"'K80 - time schedule'!IO48","v":0},{"$f":"'K80 - time schedule'!IP48","v":0},{"$f":"'K80 - time schedule'!IQ48","v":0},{"$f":"'K80 - time schedule'!IR48","v":0},{"$f":"'K80 - time schedule'!IS48","v":0},{"$f":"'K80 - time schedule'!IT48","v":0},{"$f":"'K80 - time schedule'!IU48","v":0},{"$f":"'K80 - time schedule'!IV48","v":0},{"$f":"'K80 - time schedule'!IW48","v":0},{"$f":"'K80 - time schedule'!IX48","v":0},{"$f":"'K80 - time schedule'!IY48","v":0},{"$f":"'K80 - time schedule'!IZ48","v":0},{"$f":"'K80 - time schedule'!JA48","v":0},{"$f":"'K80 - time schedule'!JB48","v":0},{"$f":"'K80 - time schedule'!JC48","v":0},{"$f":"'K80 - time schedule'!JD48","v":0},{"$f":"'K80 - time schedule'!JE48","v":0},{"$f":"'K80 - time schedule'!JF48","v":0},{"$f":"'K80 - time schedule'!JG48","v":0},{"$f":"'K80 - time schedule'!JH48","v":0},{"$f":"'K80 - time schedule'!JI48","v":0},{"$f":"'K80 - time schedule'!JJ48","v":0},{"$f":"'K80 - time schedule'!JK48","v":0},{"$f":"'K80 - time schedule'!JL48","v":0},{"$f":"'K80 - time schedule'!JM48","v":0},{"$f":"'K80 - time schedule'!JN48","v":0},{"$f":"'K80 - time schedule'!JO48","v":0},{"$f":"'K80 - time schedule'!JP48","v":0},{"$f":"'K80 - time schedule'!JQ48","v":0},{"$f":"'K80 - time schedule'!JR48","v":0},{"$f":"'K80 - time schedule'!JS48","v":0},{"$f":"'K80 - time schedule'!JT48","v":0},{"$f":"'K80 - time schedule'!JU48","v":0},{"$f":"'K80 - time schedule'!JV48","v":0},{"$f":"'K80 - time schedule'!JW48","v":0},{"$f":"'K80 - time schedule'!JX48","v":0},{"$f":"'K80 - time schedule'!JY48","v":0},{"$f":"'K80 - time schedule'!JZ48","v":0},{"$f":"'K80 - time schedule'!KA48","v":0},{"$f":"'K80 - time schedule'!KB48","v":0},{"$f":"'K80 - time schedule'!KC48","v":0},{"$f":"'K80 - time schedule'!KD48","v":0},{"$f":"'K80 - time schedule'!KE48","v":0},{"$f":"'K80 - time schedule'!KF48","v":0},{"$f":"'K80 - time schedule'!KG48","v":0},{"$f":"'K80 - time schedule'!KH48","v":0},{"$f":"'K80 - time schedule'!KI48","v":0},{"$f":"'K80 - time schedule'!KJ48","v":0},{"$f":"'K80 - time schedule'!KK48","v":0},{"$f":"'K80 - time schedule'!KL48","v":0},{"$f":"'K80 - time schedule'!KM48","v":0},{"$f":"'K80 - time schedule'!KN48","v":0},{"$f":"'K80 - time schedule'!KO48","v":0},{"$f":"'K80 - time schedule'!KP48","v":0},{"$f":"'K80 - time schedule'!KQ48","v":0},{"$f":"'K80 - time schedule'!KR48","v":0},{"$f":"'K80 - time schedule'!KS48","v":0},{"$f":"'K80 - time schedule'!KT48","v":0}]
["Boiler room K80 - completion of installation works","K80",{"$f":"'K80 - time schedule'!G49","v":0},{"$f":"'K80 - time schedule'!H49","v":0},{"$f":"'K80 - time schedule'!I49","v":0},{"$f":"'K80 - time schedule'!J49","v":0},{"$f":"'K80 - time schedule'!K49","v":0},{"$f":"'K80 - time schedule'!L49","v":0},{"$f":"'K80 - time schedule'!M49","v":0},{"$f":"'K80 - time schedule'!N49","v":0},{"$f":"'K80 - time schedule'!O49","v":0},{"$f":"'K80 - time schedule'!P49","v":0},{"$f":"'K80 - time schedule'!Q49","v":0},{"$f":"'K80 - time schedule'!R49","v":0},{"$f":"'K80 - time schedule'!S49","v":0},{"$f":"'K80 - time schedule'!T49","v":0},{"$f":"'K80 - time schedule'!U49","v":0},{"$f":"'K80 - time schedule'!V49","v":0},{"$f":"'K80 - time schedule'!W49","v":0},{"$f":"'K80 - time schedule'!X49","v":0},{"$f":"'K80 - time schedule'!Y49","v":0},{"$f":"'K80 - time schedule'!Z49","v":0},{"$f":"'K80 - time schedule'!AA49","v":0},{"$f":"'K80 - time schedule'!AB49","v":0},{"$f":"'K80 - time schedule'!AC49","v":0},{"$f":"'K80 - time schedule'!AD49","v":0},{"$f":"'K80 - time schedule'!AE49","v":0},{"$f":"'K80 - time schedule'!AF49","v":0},{"$f":"'K80 - time schedule'!AG49","v":0},{"$f":"'K80 - time schedule'!AH49","v":0},{"$f":"'K80 - time schedule'!AI49","v":0},{"$f":"'K80 - time schedule'!AJ49","v":0},{"$f":"'K80 - time schedule'!AK49","v":0},{"$f":"'K80 - time schedule'!AL49","v":0},{"$f":"'K80 - time schedule'!AM49","v":0},{"$f":"'K80 - time schedule'!AN49","v":0},{"$f":"'K80 - time schedule'!AO49","v":0},{"$f":"'K80 - time schedule'!AP49","v":0},{"$f":"'K80 - time schedule'!AQ49","v":0},{"$f":"'K80 - time schedule'!AR49","v":0},{"$f":"'K80 - time schedule'!AS49","v":0},{"$f":"'K80 - time schedule'!AT49","v":0},{"$f":"'K80 - time schedule'!AU49","v":0},{"$f":"'K80 - time schedule'!AV49","v":0},{"$f":"'K80 - time schedule'!AW49","v":0},{"$f":"'K80 - time schedule'!AX49","v":0},{"$f":"'K80 - time schedule'!AY49","v":0},{"$f":"'K80 - time schedule'!AZ49","v":0},{"$f":"'K80 - time schedule'!BA49","v":0},{"$f":"'K80 - time schedule'!BB49","v":0},{"$f":"'K80 - time schedule'!BC49","v":0},{"$f":"'K80 - time schedule'!BD49","v":0},{"$f":"'K80 - time schedule'!BE49","v":0},{"$f":"'K80 - time schedule'!BF49","v":0},{"$f":"'K80 - time schedule'!BG49","v":0},{"$f":"'K80 - time schedule'!BH49","v":0},{"$f":"'K80 - time schedule'!BI49","v":0},{"$f":"'K80 - time schedule'!BJ49","v":0},{"$f":"'K80 - time schedule'!BK49","v":0},{"$f":"'K80 - time schedule'!BL49","v":0},{"$f":"'K80 - time schedule'!BM49","v":0},{"$f":"'K80 - time schedule'!BN49","v":0},{"$f":"'K80 - time schedule'!BO49","v":0},{"$f":"'K80 - time schedule'!BP49","v":0},{"$f":"'K80 - time schedule'!BQ49","v":0},{"$f":"'K80 - time schedule'!BR49","v":0},{"$f":"'K80 - time schedule'!BS49","v":0},{"$f":"'K80 - time schedule'!BT49","v":0},{"$f":"'K80 - time schedule'!BU49","v":0},{"$f":"'K80 - time schedule'!BV49","v":0},{"$f":"'K80 - time schedule'!BW49","v":0},{"$f":"'K80 - time schedule'!BX49","v":0},{"$f":"'K80 - time schedule'!BY49","v":0},{"$f":"'K80 - time schedule'!BZ49","v":0},{"$f":"'K80 - time schedule'!CA49","v":0},{"$f":"'K80 - time schedule'!CB49","v":0},{"$f":"'K80 - time schedule'!CC49","v":0},{"$f":"'K80 - time schedule'!CD49","v":0},{"$f":"'K80 - time schedule'!CE49","v":0},{"$f":"'K80 - time schedule'!CF49","v":0},{"$f":"'K80 - time schedule'!CG49","v":0},{"$f":"'K80 - time schedule'!CH49","v":0},{"$f":"'K80 - time schedule'!CI49","v":0},{"$f":"'K80 - time schedule'!CJ49","v":0},{"$f":"'K80 - time schedule'!CK49","v":0},{"$f":"'K80 - time schedule'!CL49","v":0},{"$f":"'K80 - time schedule'!CM49","v":0},{"$f":"'K80 - time schedule'!CN49","v":0},{"$f":"'K80 - time schedule'!CO49","v":0},{"$f":"'K80 - time schedule'!CP49","v":0},{"$f":"'K80 - time schedule'!CQ49","v":0},{"$f":"'K80 - time schedule'!CR49","v":0},{"$f":"'K80 - time schedule'!CS49","v":0},{"$f":"'K80 - time schedule'!CT49","v":0},{"$f":"'K80 - time schedule'!CU49","v":0},{"$f":"'K80 - time schedule'!CV49","v":0},{"$f":"'K80 - time schedule'!CW49","v":0},{"$f":"'K80 - time schedule'!CX49","v":0},{"$f":"'K80 - time schedule'!CY49","v":0},{"$f":"'K80 - time schedule'!CZ49","v":0},{"$f":"'K80 - time schedule'!DA49","v":0},{"$f":"'K80 - time schedule'!DB49","v":0},{"$f":"'K80 - time schedule'!DC49","v":0},{"$f":"'K80 - time schedule'!DD49","v":0},{"$f":"'K80 - time schedule'!DE49","v":0},{"$f":"'K80 - time schedule'!DF49","v":0},{"$f":"'K80 - time schedule'!DG49","v":0},{"$f":"'K80 - time schedule'!DH49","v":0},{"$f":"'K80 - time schedule'!DI49","v":0},{"$f":"'K80 - time schedule'!DJ49","v":0},{"$f":"'K80 - time schedule'!DK49","v":0},{"$f":"'K80 - time schedule'!DL49","v":0},{"$f":"'K80 - time schedule'!DM49","v":0},{"$f":"'K80 - time schedule'!DN49","v":0},{"$f":"'K80 - time schedule'!DO49","v":0},{"$f":"'K80 - time schedule'!DP49","v":0},{"$f":"'K80 - time schedule'!DQ49","v":0},{"$f":"'K80 - time schedule'!DR49","v":0},{"$f":"'K80 - time schedule'!DS49","v":0},{"$f":"'K80 - time schedule'!DT49","v":0},{"$f":"'K80 - time schedule'!DU49","v":0},{"$f":"'K80 - time schedule'!DV49","v":0},{"$f":"'K80 - time schedule'!DW49","v":0},{"$f":"'K80 - time schedule'!DX49","v":0},{"$f":"'K80 - time schedule'!DY49","v":0},{"$f":"'K80 - time schedule'!DZ49","v":0},{"$f":"'K80 - time schedule'!EA49","v":0},{"$f":"'K80 - time schedule'!EB49","v":0},{"$f":"'K80 - time schedule'!EC49","v":0},{"$f":"'K80 - time schedule'!ED49","v":0},{"$f":"'K80 - time schedule'!EE49","v":0},{"$f":"'K80 - time schedule'!EF49","v":0},{"$f":"'K80 - time schedule'!EG49","v":0},{"$f":"'K80 - time schedule'!EH49","v":0},{"$f":"'K80 - time schedule'!EI49","v":0},{"$f":"'K80 - time schedule'!EJ49","v":0},{"$f":"'K80 - time schedule'!EK49","v":0},{"$f":"'K80 - time schedule'!EL49","v":0},{"$f":"'K80 - time schedule'!EM49","v":0},{"$f":"'K80 - time schedule'!EN49","v":0},{"$f":"'K80 - time schedule'!EO49","v":0},{"$f":"'K80 - time schedule'!EP49","v":0},{"$f":"'K80 - time schedule'!EQ49","v":0},{"$f":"'K80 - time schedule'!ER49","v":0},{"$f":"'K80 - time schedule'!ES49","v":0},{"$f":"'K80 - time schedule'!ET49","v":0},{"$f":"'K80 - time schedule'!EU49","v":0},{"$f":"'K80 - time schedule'!EV49","v":0},{"$f":"'K80 - time schedule'!EW49","v":0},{"$f":"'K80 - time schedule'!EX49","v":0},{"$f":"'K80 - time schedule'!EY49","v":0},{"$f":"'K80 - time schedule'!EZ49","v":0},{"$f":"'K80 - time schedule'!FA49","v":0},{"$f":"'K80 - time schedule'!FB49","v":0},{"$f":"'K80 - time schedule'!FC49","v":0},{"$f":"'K80 - time schedule'!FD49","v":0},{"$f":"'K80 - time schedule'!FE49","v":0},{"$f":"'K80 - time schedule'!FF49","v":0},{"$f":"'K80 - time schedule'!FG49","v":0},{"$f":"'K80 - time schedule'!FH49","v":0},{"$f":"'K80 - time schedule'!FI49","v":0},{"$f":"'K80 - time schedule'!FJ49","v":0},{"$f":"'K80 - time schedule'!FK49","v":0},{"$f":"'K80 - time schedule'!FL49","v":0},{"$f":"'K80 - time schedule'!FM49","v":0},{"$f":"'K80 - time schedule'!FN49","v":0},{"$f":"'K80 - time schedule'!FO49","v":0},{"$f":"'K80 - time schedule'!FP49","v":0},{"$f":"'K80 - time schedule'!FQ49","v":0},{"$f":"'K80 - time schedule'!FR49","v":0},{"$f":"'K80 - time schedule'!FS49","v":0},{"$f":"'K80 - time schedule'!FT49","v":0},{"$f":"'K80 - time schedule'!FU49","v":0},{"$f":"'K80 - time schedule'!FV49","v":0},{"$f":"'K80 - time schedule'!FW49","v":0},{"$f":"'K80 - time schedule'!FX49","v":0},{"$f":"'K80 - time schedule'!FY49","v":0},{"$f":"'K80 - time schedule'!FZ49","v":0},{"$f":"'K80 - time schedule'!GA49","v":0},{"$f":"'K80 - time schedule'!GB49","v":0},{"$f":"'K80 - time schedule'!GC49","v":0},{"$f":"'K80 - time schedule'!GD49","v":0},{"$f":"'K80 - time schedule'!GE49","v":0},{"$f":"'K80 - time schedule'!GF49","v":0},{"$f":"'K80 - time schedule'!GG49","v":0},{"$f":"'K80 - time schedule'!GH49","v":0},{"$f":"'K80 - time schedule'!GI49","v":0},{"$f":"'K80 - time schedule'!GJ49","v":0},{"$f":"'K80 - time schedule'!GK49","v":0},{"$f":"'K80 - time schedule'!GL49","v":0},{"$f":"'K80 - time schedule'!GM49","v":0},{"$f":"'K80 - time schedule'!GN49","v":0},{"$f":"'K80 - time schedule'!GO49","v":0},{"$f":"'K80 - time schedule'!GP49","v":0},{"$f":"'K80 - time schedule'!GQ49","v":0},{"$f":"'K80 - time schedule'!GR49","v":0},{"$f":"'K80 - time schedule'!GS49","v":0},{"$f":"'K80 - time schedule'!GT49","v":0},{"$f":"'K80 - time schedule'!GU49","v":0},{"$f":"'K80 - time schedule'!GV49","v":0},{"$f":"'K80 - time schedule'!GW49","v":0},{"$f":"'K80 - time schedule'!GX49","v":0},{"$f":"'K80 - time schedule'!GY49","v":0},{"$f":"'K80 - time schedule'!GZ49","v":0},{"$f":"'K80 - time schedule'!HA49","v":0},{"$f":"'K80 - time schedule'!HB49","v":0},{"$f":"'K80 - time schedule'!HC49","v":0},{"$f":"'K80 - time schedule'!HD49","v":0},{"$f":"'K80 - time schedule'!HE49","v":0},{"$f":"'K80 - time schedule'!HF49","v":0},{"$f":"'K80 - time schedule'!HG49","v":0},{"$f":"'K80 - time schedule'!HH49","v":0},{"$f":"'K80 - time schedule'!HI49","v":0},{"$f":"'K80 - time schedule'!HJ49","v":0},{"$f":"'K80 - time schedule'!HK49","v":0},{"$f":"'K80 - time schedule'!HL49","v":0},{"$f":"'K80 - time schedule'!HM49","v":0},{"$f":"'K80 - time schedule'!HN49","v":0},{"$f":"'K80 - time schedule'!HO49","v":0},{"$f":"'K80 - time schedule'!HP49","v":0},{"$f":"'K80 - time schedule'!HQ49","v":0},{"$f":"'K80 - time schedule'!HR49","v":0},{"$f":"'K80 - time schedule'!HS49","v":0},{"$f":"'K80 - time schedule'!HT49","v":0},{"$f":"'K80 - time schedule'!HU49","v":0},{"$f":"'K80 - time schedule'!HV49","v":0},{"$f":"'K80 - time schedule'!HW49","v":0},{"$f":"'K80 - time schedule'!HX49","v":0},{"$f":"'K80 - time schedule'!HY49","v":0},{"$f":"'K80 - time schedule'!HZ49","v":0},{"$f":"'K80 - time schedule'!IA49","v":0},{"$f":"'K80 - time schedule'!IB49","v":0},{"$f":"'K80 - time schedule'!IC49","v":0},{"$f":"'K80 - time schedule'!ID49","v":0},{"$f":"'K80 - time schedule'!IE49","v":0},{"$f":"'K80 - time schedule'!IF49","v":0},{"$f":"'K80 - time schedule'!IG49","v":0},{"$f":"'K80 - time schedule'!IH49","v":0},{"$f":"'K80 - time schedule'!II49","v":0},{"$f":"'K80 - time schedule'!IJ49","v":0},{"$f":"'K80 - time schedule'!IK49","v":0},{"$f":"'K80 - time schedule'!IL49","v":0},{"$f":"'K80 - time schedule'!IM49","v":0},{"$f":"'K80 - time schedule'!IN49","v":0},{"$f":"'K80 - time schedule'!IO49","v":0},{"$f":"'K80 - time schedule'!IP49","v":0},{"$f":"'K80 - time schedule'!IQ49","v":0},{"$f":"'K80 - time schedule'!IR49","v":0},{"$f":"'K80 - time schedule'!IS49","v":0},{"$f":"'K80 - time schedule'!IT49","v":0},{"$f":"'K80 - time schedule'!IU49","v":0},{"$f":"'K80 - time schedule'!IV49","v":0},{"$f":"'K80 - time schedule'!IW49","v":0},{"$f":"'K80 - time schedule'!IX49","v":0},{"$f":"'K80 - time schedule'!IY49","v":0},{"$f":"'K80 - time schedule'!IZ49","v":0},{"$f":"'K80 - time schedule'!JA49","v":0},{"$f":"'K80 - time schedule'!JB49","v":0},{"$f":"'K80 - time schedule'!JC49","v":0},{"$f":"'K80 - time schedule'!JD49","v":0},{"$f":"'K80 - time schedule'!JE49","v":0},{"$f":"'K80 - time schedule'!JF49","v":0},{"$f":"'K80 - time schedule'!JG49","v":0},{"$f":"'K80 - time schedule'!JH49","v":0},{"$f":"'K80 - time schedule'!JI49","v":0},{"$f":"'K80 - time schedule'!JJ49","v":0},{"$f":"'K80 - time schedule'!JK49","v":0},{"$f":"'K80 - time schedule'!JL49","v":0},{"$f":"'K80 - time schedule'!JM49","v":0},{"$f":"'K80 - time schedule'!JN49","v":0},{"$f":"'K80 - time schedule'!JO49","v":0},{"$f":"'K80 - time schedule'!JP49","v":0},{"$f":"'K80 - time schedule'!JQ49","v":0},{"$f":"'K80 - time schedule'!JR49","v":0},{"$f":"'K80 - time schedule'!JS49","v":0},{"$f":"'K80 - time schedule'!JT49","v":0},{"$f":"'K80 - time schedule'!JU49","v":0},{"$f":"'K80 - time schedule'!JV49","v":0},{"$f":"'K80 - time schedule'!JW49","v":0},{"$f":"'K80 - time schedule'!JX49","v":0},{"$f":"'K80 - time schedule'!JY49","v":0},{"$f":"'K80 - time schedule'!JZ49","v":0},{"$f":"'K80 - time schedule'!KA49","v":0},{"$f":"'K80 - time schedule'!KB49","v":0},{"$f":"'K80 - time schedule'!KC49","v":0},{"$f":"'K80 - time schedule'!KD49","v":0},{"$f":"'K80 - time schedule'!KE49","v":0},{"$f":"'K80 - time schedule'!KF49","v":0},{"$f":"'K80 - time schedule'!KG49","v":0},{"$f":"'K80 - time schedule'!KH49","v":0},{"$f":"'K80 - time schedule'!KI49","v":0},{"$f":"'K80 - time schedule'!KJ49","v":0},{"$f":"'K80 - time schedule'!KK49","v":0},{"$f":"'K80 - time schedule'!KL49","v":0},{"$f":"'K80 - time schedule'!KM49","v":0},{"$f":"'K80 - time schedule'!KN49","v":0},{"$f":"'K80 - time schedule'!KO49","v":0},{"$f":"'K80 - time schedule'!KP49","v":0},{"$f":"'K80 - time schedule'!KQ49","v":0},{"$f":"'K80 - time schedule'!KR49","v":0},{"$f":"'K80 - time schedule'!KS49","v":0},{"$f":"'K80 - time schedule'!KT49","v":0}]
["Boiler room K80 - operating staff training","K80",{"$f":"'K80 - time schedule'!G50","v":0},{"$f":"'K80 - time schedule'!H50","v":0},{"$f":"'K80 - time schedule'!I50","v":0},{"$f":"'K80 - time schedule'!J50","v":0},{"$f":"'K80 - time schedule'!K50","v":0},{"$f":"'K80 - time schedule'!L50","v":0},{"$f":"'K80 - time schedule'!M50","v":0},{"$f":"'K80 - time schedule'!N50","v":0},{"$f":"'K80 - time schedule'!O50","v":0},{"$f":"'K80 - time schedule'!P50","v":0},{"$f":"'K80 - time schedule'!Q50","v":0},{"$f":"'K80 - time schedule'!R50","v":0},{"$f":"'K80 - time schedule'!S50","v":0},{"$f":"'K80 - time schedule'!T50","v":0},{"$f":"'K80 - time schedule'!U50","v":0},{"$f":"'K80 - time schedule'!V50","v":0},{"$f":"'K80 - time schedule'!W50","v":0},{"$f":"'K80 - time schedule'!X50","v":0},{"$f":"'K80 - time schedule'!Y50","v":0},{"$f":"'K80 - time schedule'!Z50","v":0},{"$f":"'K80 - time schedule'!AA50","v":0},{"$f":"'K80 - time schedule'!AB50","v":0},{"$f":"'K80 - time schedule'!AC50","v":0},{"$f":"'K80 - time schedule'!AD50","v":0},{"$f":"'K80 - time schedule'!AE50","v":0},{"$f":"'K80 - time schedule'!AF50","v":0},{"$f":"'K80 - time schedule'!AG50","v":0},{"$f":"'K80 - time schedule'!AH50","v":0},{"$f":"'K80 - time schedule'!AI50","v":0},{"$f":"'K80 - time schedule'!AJ50","v":0},{"$f":"'K80 - time schedule'!AK50","v":0},{"$f":"'K80 - time schedule'!AL50","v":0},{"$f":"'K80 - time schedule'!AM50","v":0},{"$f":"'K80 - time schedule'!AN50","v":0},{"$f":"'K80 - time schedule'!AO50","v":0},{"$f":"'K80 - time schedule'!AP50","v":0},{"$f":"'K80 - time schedule'!AQ50","v":0},{"$f":"'K80 - time schedule'!AR50","v":0},{"$f":"'K80 - time schedule'!AS50","v":0},{"$f":"'K80 - time schedule'!AT50","v":0},{"$f":"'K80 - time schedule'!AU50","v":0},{"$f":"'K80 - time schedule'!AV50","v":0},{"$f":"'K80 - time schedule'!AW50","v":0},{"$f":"'K80 - time schedule'!AX50","v":0},{"$f":"'K80 - time schedule'!AY50","v":0},{"$f":"'K80 - time schedule'!AZ50","v":0},{"$f":"'K80 - time schedule'!BA50","v":0},{"$f":"'K80 - time schedule'!BB50","v":0},{"$f":"'K80 - time schedule'!BC50","v":0},{"$f":"'K80 - time schedule'!BD50","v":0},{"$f":"'K80 - time schedule'!BE50","v":0},{"$f":"'K80 - time schedule'!BF50","v":0},{"$f":"'K80 - time schedule'!BG50","v":0},{"$f":"'K80 - time schedule'!BH50","v":0},{"$f":"'K80 - time schedule'!BI50","v":0},{"$f":"'K80 - time schedule'!BJ50","v":0},{"$f":"'K80 - time schedule'!BK50","v":0},{"$f":"'K80 - time schedule'!BL50","v":0},{"$f":"'K80 - time schedule'!BM50","v":0},{"$f":"'K80 - time schedule'!BN50","v":0},{"$f":"'K80 - time schedule'!BO50","v":0},{"$f":"'K80 - time schedule'!BP50","v":0},{"$f":"'K80 - time schedule'!BQ50","v":0},{"$f":"'K80 - time schedule'!BR50","v":0},{"$f":"'K80 - time schedule'!BS50","v":0},{"$f":"'K80 - time schedule'!BT50","v":0},{"$f":"'K80 - time schedule'!BU50","v":0},{"$f":"'K80 - time schedule'!BV50","v":0},{"$f":"'K80 - time schedule'!BW50","v":0},{"$f":"'K80 - time schedule'!BX50","v":0},{"$f":"'K80 - time schedule'!BY50","v":0},{"$f":"'K80 - time schedule'!BZ50","v":0},{"$f":"'K80 - time schedule'!CA50","v":0},{"$f":"'K80 - time schedule'!CB50","v":0},{"$f":"'K80 - time schedule'!CC50","v":0},{"$f":"'K80 - time schedule'!CD50","v":0},{"$f":"'K80 - time schedule'!CE50","v":0},{"$f":"'K80 - time schedule'!CF50","v":0},{"$f":"'K80 - time schedule'!CG50","v":0},{"$f":"'K80 - time schedule'!CH50","v":0},{"$f":"'K80 - time schedule'!CI50","v":0},{"$f":"'K80 - time schedule'!CJ50","v":0},{"$f":"'K80 - time schedule'!CK50","v":0},{"$f":"'K80 - time schedule'!CL50","v":0},{"$f":"'K80 - time schedule'!CM50","v":0},{"$f":"'K80 - time schedule'!CN50","v":0},{"$f":"'K80 - time schedule'!CO50","v":0},{"$f":"'K80 - time schedule'!CP50","v":0},{"$f":"'K80 - time schedule'!CQ50","v":0},{"$f":"'K80 - time schedule'!CR50","v":0},{"$f":"'K80 - time schedule'!CS50","v":0},{"$f":"'K80 - time schedule'!CT50","v":0},{"$f":"'K80 - time schedule'!CU50","v":0},{"$f":"'K80 - time schedule'!CV50","v":0},{"$f":"'K80 - time schedule'!CW50","v":0},{"$f":"'K80 - time schedule'!CX50","v":0},{"$f":"'K80 - time schedule'!CY50","v":0},{"$f":"'K80 - time schedule'!CZ50","v":0},{"$f":"'K80 - time schedule'!DA50","v":0},{"$f":"'K80 - time schedule'!DB50","v":0},{"$f":"'K80 - time schedule'!DC50","v":0},{"$f":"'K80 - time schedule'!DD50","v":0},{"$f":"'K80 - time schedule'!DE50","v":0},{"$f":"'K80 - time schedule'!DF50","v":0},{"$f":"'K80 - time schedule'!DG50","v":0},{"$f":"'K80 - time schedule'!DH50","v":0},{"$f":"'K80 - time schedule'!DI50","v":0},{"$f":"'K80 - time schedule'!DJ50","v":0},{"$f":"'K80 - time schedule'!DK50","v":0},{"$f":"'K80 - time schedule'!DL50","v":0},{"$f":"'K80 - time schedule'!DM50","v":0},{"$f":"'K80 - time schedule'!DN50","v":0},{"$f":"'K80 - time schedule'!DO50","v":0},{"$f":"'K80 - time schedule'!DP50","v":0},{"$f":"'K80 - time schedule'!DQ50","v":0},{"$f":"'K80 - time schedule'!DR50","v":0},{"$f":"'K80 - time schedule'!DS50","v":0},{"$f":"'K80 - time schedule'!DT50","v":0},{"$f":"'K80 - time schedule'!DU50","v":0},{"$f":"'K80 - time schedule'!DV50","v":0},{"$f":"'K80 - time schedule'!DW50","v":0},{"$f":"'K80 - time schedule'!DX50","v":0},{"$f":"'K80 - time schedule'!DY50","v":0},{"$f":"'K80 - time schedule'!DZ50","v":0},{"$f":"'K80 - time schedule'!EA50","v":0},{"$f":"'K80 - time schedule'!EB50","v":0},{"$f":"'K80 - time schedule'!EC50","v":0},{"$f":"'K80 - time schedule'!ED50","v":0},{"$f":"'K80 - time schedule'!EE50","v":0},{"$f":"'K80 - time schedule'!EF50","v":0},{"$f":"'K80 - time schedule'!EG50","v":0},{"$f":"'K80 - time schedule'!EH50","v":0},{"$f":"'K80 - time schedule'!EI50","v":0},{"$f":"'K80 - time schedule'!EJ50","v":0},{"$f":"'K80 - time schedule'!EK50","v":0},{"$f":"'K80 - time schedule'!EL50","v":0},{"$f":"'K80 - time schedule'!EM50","v":0},{"$f":"'K80 - time schedule'!EN50","v":0},{"$f":"'K80 - time schedule'!EO50","v":0},{"$f":"'K80 - time schedule'!EP50","v":0},{"$f":"'K80 - time schedule'!EQ50","v":0},{"$f":"'K80 - time schedule'!ER50","v":0},{"$f":"'K80 - time schedule'!ES50","v":0},{"$f":"'K80 - time schedule'!ET50","v":0},{"$f":"'K80 - time schedule'!EU50","v":0},{"$f":"'K80 - time schedule'!EV50","v":0},{"$f":"'K80 - time schedule'!EW50","v":0},{"$f":"'K80 - time schedule'!EX50","v":0},{"$f":"'K80 - time schedule'!EY50","v":0},{"$f":"'K80 - time schedule'!EZ50","v":0},{"$f":"'K80 - time schedule'!FA50","v":0},{"$f":"'K80 - time schedule'!FB50","v":0},{"$f":"'K80 - time schedule'!FC50","v":0},{"$f":"'K80 - time schedule'!FD50","v":0},{"$f":"'K80 - time schedule'!FE50","v":0},{"$f":"'K80 - time schedule'!FF50","v":0},{"$f":"'K80 - time schedule'!FG50","v":0},{"$f":"'K80 - time schedule'!FH50","v":0},{"$f":"'K80 - time schedule'!FI50","v":0},{"$f":"'K80 - time schedule'!FJ50","v":0},{"$f":"'K80 - time schedule'!FK50","v":0},{"$f":"'K80 - time schedule'!FL50","v":0},{"$f":"'K80 - time schedule'!FM50","v":0},{"$f":"'K80 - time schedule'!FN50","v":0},{"$f":"'K80 - time schedule'!FO50","v":0},{"$f":"'K80 - time schedule'!FP50","v":0},{"$f":"'K80 - time schedule'!FQ50","v":0},{"$f":"'K80 - time schedule'!FR50","v":0},{"$f":"'K80 - time schedule'!FS50","v":0},{"$f":"'K80 - time schedule'!FT50","v":0},{"$f":"'K80 - time schedule'!FU50","v":0},{"$f":"'K80 - time schedule'!FV50","v":0},{"$f":"'K80 - time schedule'!FW50","v":0},{"$f":"'K80 - time schedule'!FX50","v":0},{"$f":"'K80 - time schedule'!FY50","v":0},{"$f":"'K80 - time schedule'!FZ50","v":0},{"$f":"'K80 - time schedule'!GA50","v":0},{"$f":"'K80 - time schedule'!GB50","v":0},{"$f":"'K80 - time schedule'!GC50","v":0},{"$f":"'K80 - time schedule'!GD50","v":0},{"$f":"'K80 - time schedule'!GE50","v":0},{"$f":"'K80 - time schedule'!GF50","v":0},{"$f":"'K80 - time schedule'!GG50","v":0},{"$f":"'K80 - time schedule'!GH50","v":0},{"$f":"'K80 - time schedule'!GI50","v":0},{"$f":"'K80 - time schedule'!GJ50","v":0},{"$f":"'K80 - time schedule'!GK50","v":0},{"$f":"'K80 - time schedule'!GL50","v":0},{"$f":"'K80 - time schedule'!GM50","v":0},{"$f":"'K80 - time schedule'!GN50","v":0},{"$f":"'K80 - time schedule'!GO50","v":0},{"$f":"'K80 - time schedule'!GP50","v":0},{"$f":"'K80 - time schedule'!GQ50","v":0},{"$f":"'K80 - time schedule'!GR50","v":0},{"$f":"'K80 - time schedule'!GS50","v":0},{"$f":"'K80 - time schedule'!GT50","v":0},{"$f":"'K80 - time schedule'!GU50","v":0},{"$f":"'K80 - time schedule'!GV50","v":0},{"$f":"'K80 - time schedule'!GW50","v":0},{"$f":"'K80 - time schedule'!GX50","v":0},{"$f":"'K80 - time schedule'!GY50","v":0},{"$f":"'K80 - time schedule'!GZ50","v":0},{"$f":"'K80 - time schedule'!HA50","v":0},{"$f":"'K80 - time schedule'!HB50","v":0},{"$f":"'K80 - time schedule'!HC50","v":0},{"$f":"'K80 - time schedule'!HD50","v":0},{"$f":"'K80 - time schedule'!HE50","v":0},{"$f":"'K80 - time schedule'!HF50","v":0},{"$f":"'K80 - time schedule'!HG50","v":0},{"$f":"'K80 - time schedule'!HH50","v":0},{"$f":"'K80 - time schedule'!HI50","v":0},{"$f":"'K80 - time schedule'!HJ50","v":0},{"$f":"'K80 - time schedule'!HK50","v":0},{"$f":"'K80 - time schedule'!HL50","v":0},{"$f":"'K80 - time schedule'!HM50","v":0},{"$f":"'K80 - time schedule'!HN50","v":0},{"$f":"'K80 - time schedule'!HO50","v":0},{"$f":"'K80 - time schedule'!HP50","v":0},{"$f":"'K80 - time schedule'!HQ50","v":0},{"$f":"'K80 - time schedule'!HR50","v":0},{"$f":"'K80 - time schedule'!HS50","v":0},{"$f":"'K80 - time schedule'!HT50","v":0},{"$f":"'K80 - time schedule'!HU50","v":0},{"$f":"'K80 - time schedule'!HV50","v":0},{"$f":"'K80 - time schedule'!HW50","v":0},{"$f":"'K80 - time schedule'!HX50","v":0},{"$f":"'K80 - time schedule'!HY50","v":0},{"$f":"'K80 - time schedule'!HZ50","v":0},{"$f":"'K80 - time schedule'!IA50","v":0},{"$f":"'K80 - time schedule'!IB50","v":0},{"$f":"'K80 - time schedule'!IC50","v":0},{"$f":"'K80 - time schedule'!ID50","v":0},{"$f":"'K80 - time schedule'!IE50","v":0},{"$f":"'K80 - time schedule'!IF50","v":0},{"$f":"'K80 - time schedule'!IG50","v":0},{"$f":"'K80 - time schedule'!IH50","v":0},{"$f":"'K80 - time schedule'!II50","v":0},{"$f":"'K80 - time schedule'!IJ50","v":0},{"$f":"'K80 - time schedule'!IK50","v":0},{"$f":"'K80 - time schedule'!IL50","v":0},{"$f":"'K80 - time schedule'!IM50","v":0},{"$f":"'K80 - time schedule'!IN50","v":0},{"$f":"'K80 - time schedule'!IO50","v":0},{"$f":"'K80 - time schedule'!IP50","v":0},{"$f":"'K80 - time schedule'!IQ50","v":0},{"$f":"'K80 - time schedule'!IR50","v":0},{"$f":"'K80 - time schedule'!IS50","v":0},{"$f":"'K80 - time schedule'!IT50","v":0},{"$f":"'K80 - time schedule'!IU50","v":0},{"$f":"'K80 - time schedule'!IV50","v":0},{"$f":"'K80 - time schedule'!IW50","v":0},{"$f":"'K80 - time schedule'!IX50","v":0},{"$f":"'K80 - time schedule'!IY50","v":0},{"$f":"'K80 - time schedule'!IZ50","v":0},{"$f":"'K80 - time schedule'!JA50","v":0},{"$f":"'K80 - time schedule'!JB50","v":0},{"$f":"'K80 - time schedule'!JC50","v":0},{"$f":"'K80 - time schedule'!JD50","v":0},{"$f":"'K80 - time schedule'!JE50","v":0},{"$f":"'K80 - time schedule'!JF50","v":0},{"$f":"'K80 - time schedule'!JG50","v":0},{"$f":"'K80 - time schedule'!JH50","v":0},{"$f":"'K80 - time schedule'!JI50","v":0},{"$f":"'K80 - time schedule'!JJ50","v":0},{"$f":"'K80 - time schedule'!JK50","v":0},{"$f":"'K80 - time schedule'!JL50","v":0},{"$f":"'K80 - time schedule'!JM50","v":0},{"$f":"'K80 - time schedule'!JN50","v":0},{"$f":"'K80 - time schedule'!JO50","v":0},{"$f":"'K80 - time schedule'!JP50","v":0},{"$f":"'K80 - time schedule'!JQ50","v":0},{"$f":"'K80 - time schedule'!JR50","v":0},{"$f":"'K80 - time schedule'!JS50","v":0},{"$f":"'K80 - time schedule'!JT50","v":0},{"$f":"'K80 - time schedule'!JU50","v":0},{"$f":"'K80 - time schedule'!JV50","v":0},{"$f":"'K80 - time schedule'!JW50","v":0},{"$f":"'K80 - time schedule'!JX50","v":0},{"$f":"'K80 - time schedule'!JY50","v":0},{"$f":"'K80 - time schedule'!JZ50","v":0},{"$f":"'K80 - time schedule'!KA50","v":0},{"$f":"'K80 - time schedule'!KB50","v":0},{"$f":"'K80 - time schedule'!KC50","v":0},{"$f":"'K80 - time schedule'!KD50","v":0},{"$f":"'K80 - time schedule'!KE50","v":0},{"$f":"'K80 - time schedule'!KF50","v":0},{"$f":"'K80 - time schedule'!KG50","v":0},{"$f":"'K80 - time schedule'!KH50","v":0},{"$f":"'K80 - time schedule'!KI50","v":0},{"$f":"'K80 - time schedule'!KJ50","v":0},{"$f":"'K80 - time schedule'!KK50","v":0},{"$f":"'K80 - time schedule'!KL50","v":0},{"$f":"'K80 - time schedule'!KM50","v":0},{"$f":"'K80 - time schedule'!KN50","v":0},{"$f":"'K80 - time schedule'!KO50","v":0},{"$f":"'K80 - time schedule'!KP50","v":0},{"$f":"'K80 - time schedule'!KQ50","v":0},{"$f":"'K80 - time schedule'!KR50","v":0},{"$f":"'K80 - time schedule'!KS50","v":0},{"$f":"'K80 - time schedule'!KT50","v":0}]
["Boiler room K80 - preparation for comprehensive testing","K80",{"$f":"'K80 - time schedule'!G52","v":0},{"$f":"'K80 - time schedule'!H52","v":0},{"$f":"'K80 - time schedule'!I52","v":0},{"$f":"'K80 - time schedule'!J52","v":0},{"$f":"'K80 - time schedule'!K52","v":0},{"$f":"'K80 - time schedule'!L52","v":0},{"$f":"'K80 - time schedule'!M52","v":0},{"$f":"'K80 - time schedule'!N52","v":0},{"$f":"'K80 - time schedule'!O52","v":0},{"$f":"'K80 - time schedule'!P52","v":0},{"$f":"'K80 - time schedule'!Q52","v":0},{"$f":"'K80 - time schedule'!R52","v":0},{"$f":"'K80 - time schedule'!S52","v":0},{"$f":"'K80 - time schedule'!T52","v":0},{"$f":"'K80 - time schedule'!U52","v":0},{"$f":"'K80 - time schedule'!V52","v":0},{"$f":"'K80 - time schedule'!W52","v":0},{"$f":"'K80 - time schedule'!X52","v":0},{"$f":"'K80 - time schedule'!Y52","v":0},{"$f":"'K80 - time schedule'!Z52","v":0},{"$f":"'K80 - time schedule'!AA52","v":0},{"$f":"'K80 - time schedule'!AB52","v":0},{"$f":"'K80 - time schedule'!AC52","v":0},{"$f":"'K80 - time schedule'!AD52","v":0},{"$f":"'K80 - time schedule'!AE52","v":0},{"$f":"'K80 - time schedule'!AF52","v":0},{"$f":"'K80 - time schedule'!AG52","v":0},{"$f":"'K80 - time schedule'!AH52","v":0},{"$f":"'K80 - time schedule'!AI52","v":0},{"$f":"'K80 - time schedule'!AJ52","v":0},{"$f":"'K80 - time schedule'!AK52","v":0},{"$f":"'K80 - time schedule'!AL52","v":0},{"$f":"'K80 - time schedule'!AM52","v":0},{"$f":"'K80 - time schedule'!AN52","v":0},{"$f":"'K80 - time schedule'!AO52","v":0},{"$f":"'K80 - time schedule'!AP52","v":0},{"$f":"'K80 - time schedule'!AQ52","v":0},{"$f":"'K80 - time schedule'!AR52","v":0},{"$f":"'K80 - time schedule'!AS52","v":0},{"$f":"'K80 - time schedule'!AT52","v":0},{"$f":"'K80 - time schedule'!AU52","v":0},{"$f":"'K80 - time schedule'!AV52","v":0},{"$f":"'K80 - time schedule'!AW52","v":0},{"$f":"'K80 - time schedule'!AX52","v":0},{"$f":"'K80 - time schedule'!AY52","v":0},{"$f":"'K80 - time schedule'!AZ52","v":0},{"$f":"'K80 - time schedule'!BA52","v":0},{"$f":"'K80 - time schedule'!BB52","v":0},{"$f":"'K80 - time schedule'!BC52","v":0},{"$f":"'K80 - time schedule'!BD52","v":0},{"$f":"'K80 - time schedule'!BE52","v":0},{"$f":"'K80 - time schedule'!BF52","v":0},{"$f":"'K80 - time schedule'!BG52","v":0},{"$f":"'K80 - time schedule'!BH52","v":0},{"$f":"'K80 - time schedule'!BI52","v":0},{"$f":"'K80 - time schedule'!BJ52","v":0},{"$f":"'K80 - time schedule'!BK52","v":0},{"$f":"'K80 - time schedule'!BL52","v":0},{"$f":"'K80 - time schedule'!BM52","v":0},{"$f":"'K80 - time schedule'!BN52","v":0},{"$f":"'K80 - time schedule'!BO52","v":0},{"$f":"'K80 - time schedule'!BP52","v":0},{"$f":"'K80 - time schedule'!BQ52","v":0},{"$f":"'K80 - time schedule'!BR52","v":0},{"$f":"'K80 - time schedule'!BS52","v":0},{"$f":"'K80 - time schedule'!BT52","v":0},{"$f":"'K80 - time schedule'!BU52","v":0},{"$f":"'K80 - time schedule'!BV52","v":0},{"$f":"'K80 - time schedule'!BW52","v":0},{"$f":"'K80 - time schedule'!BX52","v":0},{"$f":"'K80 - time schedule'!BY52","v":0},{"$f":"'K80 - time schedule'!BZ52","v":0},{"$f":"'K80 - time schedule'!CA52","v":0},{"$f":"'K80 - time schedule'!CB52","v":0},{"$f":"'K80 - time schedule'!CC52","v":0},{"$f":"'K80 - time schedule'!CD52","v":0},{"$f":"'K80 - time schedule'!CE52","v":0},{"$f":"'K80 - time schedule'!CF52","v":0},{"$f":"'K80 - time schedule'!CG52","v":0},{"$f":"'K80 - time schedule'!CH52","v":0},{"$f":"'K80 - time schedule'!CI52","v":0},{"$f":"'K80 - time schedule'!CJ52","v":0},{"$f":"'K80 - time schedule'!CK52","v":0},{"$f":"'K80 - time schedule'!CL52","v":0},{"$f":"'K80 - time schedule'!CM52","v":0},{"$f":"'K80 - time schedule'!CN52","v":0},{"$f":"'K80 - time schedule'!CO52","v":0},{"$f":"'K80 - time schedule'!CP52","v":0},{"$f":"'K80 - time schedule'!CQ52","v":0},{"$f":"'K80 - time schedule'!CR52","v":0},{"$f":"'K80 - time schedule'!CS52","v":0},{"$f":"'K80 - time schedule'!CT52","v":0},{"$f":"'K80 - time schedule'!CU52","v":0},{"$f":"'K80 - time schedule'!CV52","v":0},{"$f":"'K80 - time schedule'!CW52","v":0},{"$f":"'K80 - time schedule'!CX52","v":0},{"$f":"'K80 - time schedule'!CY52","v":0},{"$f":"'K80 - time schedule'!CZ52","v":0},{"$f":"'K80 - time schedule'!DA52","v":0},{"$f":"'K80 - time schedule'!DB52","v":0},{"$f":"'K80 - time schedule'!DC52","v":0},{"$f":"'K80 - time schedule'!DD52","v":0},{"$f":"'K80 - time schedule'!DE52","v":0},{"$f":"'K80 - time schedule'!DF52","v":0},{"$f":"'K80 - time schedule'!DG52","v":0},{"$f":"'K80 - time schedule'!DH52","v":0},{"$f":"'K80 - time schedule'!DI52","v":0},{"$f":"'K80 - time schedule'!DJ52","v":0},{"$f":"'K80 - time schedule'!DK52","v":0},{"$f":"'K80 - time schedule'!DL52","v":0},{"$f":"'K80 - time schedule'!DM52","v":0},{"$f":"'K80 - time schedule'!DN52","v":0},{"$f":"'K80 - time schedule'!DO52","v":0},{"$f":"'K80 - time schedule'!DP52","v":0},{"$f":"'K80 - time schedule'!DQ52","v":0},{"$f":"'K80 - time schedule'!DR52","v":0},{"$f":"'K80 - time schedule'!DS52","v":0},{"$f":"'K80 - time schedule'!DT52","v":0},{"$f":"'K80 - time schedule'!DU52","v":0},{"$f":"'K80 - time schedule'!DV52","v":0},{"$f":"'K80 - time schedule'!DW52","v":0},{"$f":"'K80 - time schedule'!DX52","v":0},{"$f":"'K80 - time schedule'!DY52","v":0},{"$f":"'K80 - time schedule'!DZ52","v":0},{"$f":"'K80 - time schedule'!EA52","v":0},{"$f":"'K80 - time schedule'!EB52","v":0},{"$f":"'K80 - time schedule'!EC52","v":0},{"$f":"'K80 - time schedule'!ED52","v":0},{"$f":"'K80 - time schedule'!EE52","v":0},{"$f":"'K80 - time schedule'!EF52","v":0},{"$f":"'K80 - time schedule'!EG52","v":0},{"$f":"'K80 - time schedule'!EH52","v":0},{"$f":"'K80 - time schedule'!EI52","v":0},{"$f":"'K80 - time schedule'!EJ52","v":0},{"$f":"'K80 - time schedule'!EK52","v":0},{"$f":"'K80 - time schedule'!EL52","v":0},{"$f":"'K80 - time schedule'!EM52","v":0},{"$f":"'K80 - time schedule'!EN52","v":0},{"$f":"'K80 - time schedule'!EO52","v":0},{"$f":"'K80 - time schedule'!EP52","v":0},{"$f":"'K80 - time schedule'!EQ52","v":0},{"$f":"'K80 - time schedule'!ER52","v":0},{"$f":"'K80 - time schedule'!ES52","v":0},{"$f":"'K80 - time schedule'!ET52","v":0},{"$f":"'K80 - time schedule'!EU52","v":0},{"$f":"'K80 - time schedule'!EV52","v":0},{"$f":"'K80 - time schedule'!EW52","v":0},{"$f":"'K80 - time schedule'!EX52","v":0},{"$f":"'K80 - time schedule'!EY52","v":0},{"$f":"'K80 - time schedule'!EZ52","v":0},{"$f":"'K80 - time schedule'!FA52","v":0},{"$f":"'K80 - time schedule'!FB52","v":0},{"$f":"'K80 - time schedule'!FC52","v":0},{"$f":"'K80 - time schedule'!FD52","v":0},{"$f":"'K80 - time schedule'!FE52","v":0},{"$f":"'K80 - time schedule'!FF52","v":0},{"$f":"'K80 - time schedule'!FG52","v":0},{"$f":"'K80 - time schedule'!FH52","v":0},{"$f":"'K80 - time schedule'!FI52","v":0},{"$f":"'K80 - time schedule'!FJ52","v":0},{"$f":"'K80 - time schedule'!FK52","v":0},{"$f":"'K80 - time schedule'!FL52","v":0},{"$f":"'K80 - time schedule'!FM52","v":0},{"$f":"'K80 - time schedule'!FN52","v":0},{"$f":"'K80 - time schedule'!FO52","v":0},{"$f":"'K80 - time schedule'!FP52","v":0},{"$f":"'K80 - time schedule'!FQ52","v":0},{"$f":"'K80 - time schedule'!FR52","v":0},{"$f":"'K80 - time schedule'!FS52","v":0},{"$f":"'K80 - time schedule'!FT52","v":0},{"$f":"'K80 - time schedule'!FU52","v":0},{"$f":"'K80 - time schedule'!FV52","v":0},{"$f":"'K80 - time schedule'!FW52","v":0},{"$f":"'K80 - time schedule'!FX52","v":0},{"$f":"'K80 - time schedule'!FY52","v":0},{"$f":"'K80 - time schedule'!FZ52","v":0},{"$f":"'K80 - time schedule'!GA52","v":0},{"$f":"'K80 - time schedule'!GB52","v":0},{"$f":"'K80 - time schedule'!GC52","v":0},{"$f":"'K80 - time schedule'!GD52","v":0},{"$f":"'K80 - time schedule'!GE52","v":0},{"$f":"'K80 - time schedule'!GF52","v":0},{"$f":"'K80 - time schedule'!GG52","v":0},{"$f":"'K80 - time schedule'!GH52","v":0},{"$f":"'K80 - time schedule'!GI52","v":0},{"$f":"'K80 - time schedule'!GJ52","v":0},{"$f":"'K80 - time schedule'!GK52","v":0},{"$f":"'K80 - time schedule'!GL52","v":0},{"$f":"'K80 - time schedule'!GM52","v":0},{"$f":"'K80 - time schedule'!GN52","v":0},{"$f":"'K80 - time schedule'!GO52","v":0},{"$f":"'K80 - time schedule'!GP52","v":0},{"$f":"'K80 - time schedule'!GQ52","v":0},{"$f":"'K80 - time schedule'!GR52","v":0},{"$f":"'K80 - time schedule'!GS52","v":0},{"$f":"'K80 - time schedule'!GT52","v":0},{"$f":"'K80 - time schedule'!GU52","v":0},{"$f":"'K80 - time schedule'!GV52","v":0},{"$f":"'K80 - time schedule'!GW52","v":0},{"$f":"'K80 - time schedule'!GX52","v":0},{"$f":"'K80 - time schedule'!GY52","v":0},{"$f":"'K80 - time schedule'!GZ52","v":0},{"$f":"'K80 - time schedule'!HA52","v":0},{"$f":"'K80 - time schedule'!HB52","v":0},{"$f":"'K80 - time schedule'!HC52","v":0},{"$f":"'K80 - time schedule'!HD52","v":0},{"$f":"'K80 - time schedule'!HE52","v":0},{"$f":"'K80 - time schedule'!HF52","v":0},{"$f":"'K80 - time schedule'!HG52","v":0},{"$f":"'K80 - time schedule'!HH52","v":0},{"$f":"'K80 - time schedule'!HI52","v":0},{"$f":"'K80 - time schedule'!HJ52","v":0},{"$f":"'K80 - time schedule'!HK52","v":0},{"$f":"'K80 - time schedule'!HL52","v":0},{"$f":"'K80 - time schedule'!HM52","v":0},{"$f":"'K80 - time schedule'!HN52","v":0},{"$f":"'K80 - time schedule'!HO52","v":0},{"$f":"'K80 - time schedule'!HP52","v":0},{"$f":"'K80 - time schedule'!HQ52","v":0},{"$f":"'K80 - time schedule'!HR52","v":0},{"$f":"'K80 - time schedule'!HS52","v":0},{"$f":"'K80 - time schedule'!HT52","v":0},{"$f":"'K80 - time schedule'!HU52","v":0},{"$f":"'K80 - time schedule'!HV52","v":0},{"$f":"'K80 - time schedule'!HW52","v":0},{"$f":"'K80 - time schedule'!HX52","v":0},{"$f":"'K80 - time schedule'!HY52","v":0},{"$f":"'K80 - time schedule'!HZ52","v":0},{"$f":"'K80 - time schedule'!IA52","v":0},{"$f":"'K80 - time schedule'!IB52","v":0},{"$f":"'K80 - time schedule'!IC52","v":0},{"$f":"'K80 - time schedule'!ID52","v":0},{"$f":"'K80 - time schedule'!IE52","v":0},{"$f":"'K80 - time schedule'!IF52","v":0},{"$f":"'K80 - time schedule'!IG52","v":0},{"$f":"'K80 - time schedule'!IH52","v":0},{"$f":"'K80 - time schedule'!II52","v":0},{"$f":"'K80 - time schedule'!IJ52","v":0},{"$f":"'K80 - time schedule'!IK52","v":0},{"$f":"'K80 - time schedule'!IL52","v":0},{"$f":"'K80 - time schedule'!IM52","v":0},{"$f":"'K80 - time schedule'!IN52","v":0},{"$f":"'K80 - time schedule'!IO52","v":0},{"$f":"'K80 - time schedule'!IP52","v":0},{"$f":"'K80 - time schedule'!IQ52","v":0},{"$f":"'K80 - time schedule'!IR52","v":0},{"$f":"'K80 - time schedule'!IS52","v":0},{"$f":"'K80 - time schedule'!IT52","v":0},{"$f":"'K80 - time schedule'!IU52","v":0},{"$f":"'K80 - time schedule'!IV52","v":0},{"$f":"'K80 - time schedule'!IW52","v":0},{"$f":"'K80 - time schedule'!IX52","v":0},{"$f":"'K80 - time schedule'!IY52","v":0},{"$f":"'K80 - time schedule'!IZ52","v":0},{"$f":"'K80 - time schedule'!JA52","v":0},{"$f":"'K80 - time schedule'!JB52","v":0},{"$f":"'K80 - time schedule'!JC52","v":0},{"$f":"'K80 - time schedule'!JD52","v":0},{"$f":"'K80 - time schedule'!JE52","v":0},{"$f":"'K80 - time schedule'!JF52","v":0},{"$f":"'K80 - time schedule'!JG52","v":0},{"$f":"'K80 - time schedule'!JH52","v":0},{"$f":"'K80 - time schedule'!JI52","v":0},{"$f":"'K80 - time schedule'!JJ52","v":0},{"$f":"'K80 - time schedule'!JK52","v":0},{"$f":"'K80 - time schedule'!JL52","v":0},{"$f":"'K80 - time schedule'!JM52","v":0},{"$f":"'K80 - time schedule'!JN52","v":0},{"$f":"'K80 - time schedule'!JO52","v":0},{"$f":"'K80 - time schedule'!JP52","v":0},{"$f":"'K80 - time schedule'!JQ52","v":0},{"$f":"'K80 - time schedule'!JR52","v":0},{"$f":"'K80 - time schedule'!JS52","v":0},{"$f":"'K80 - time schedule'!JT52","v":0},{"$f":"'K80 - time schedule'!JU52","v":0},{"$f":"'K80 - time schedule'!JV52","v":0},{"$f":"'K80 - time schedule'!JW52","v":0},{"$f":"'K80 - time schedule'!JX52","v":0},{"$f":"'K80 - time schedule'!JY52","v":0},{"$f":"'K80 - time schedule'!JZ52","v":0},{"$f":"'K80 - time schedule'!KA52","v":0},{"$f":"'K80 - time schedule'!KB52","v":0},{"$f":"'K80 - time schedule'!KC52","v":0},{"$f":"'K80 - time schedule'!KD52","v":0},{"$f":"'K80 - time schedule'!KE52","v":0},{"$f":"'K80 - time schedule'!KF52","v":0},{"$f":"'K80 - time schedule'!KG52","v":0},{"$f":"'K80 - time schedule'!KH52","v":0},{"$f":"'K80 - time schedule'!KI52","v":0},{"$f":"'K80 - time schedule'!KJ52","v":0},{"$f":"'K80 - time schedule'!KK52","v":0},{"$f":"'K80 - time schedule'!KL52","v":0},{"$f":"'K80 - time schedule'!KM52","v":0},{"$f":"'K80 - time schedule'!KN52","v":0},{"$f":"'K80 - time schedule'!KO52","v":0},{"$f":"'K80 - time schedule'!KP52","v":0},{"$f":"'K80 - time schedule'!KQ52","v":0},{"$f":"'K80 - time schedule'!KR52","v":0},{"$f":"'K80 - time schedule'!KS52","v":0},{"$f":"'K80 - time schedule'!KT52","v":0}]
["Boiler room K80 - comprehensive testing","K80",{"$f":"'K80 - time schedule'!G53","v":0},{"$f":"'K80 - time schedule'!H53","v":0},{"$f":"'K80 - time schedule'!I53","v":0},{"$f":"'K80 - time schedule'!J53","v":0},{"$f":"'K80 - time schedule'!K53","v":0},{"$f":"'K80 - time schedule'!L53","v":0},{"$f":"'K80 - time schedule'!M53","v":0},{"$f":"'K80 - time schedule'!N53","v":0},{"$f":"'K80 - time schedule'!O53","v":0},{"$f":"'K80 - time schedule'!P53","v":0},{"$f":"'K80 - time schedule'!Q53","v":0},{"$f":"'K80 - time schedule'!R53","v":0},{"$f":"'K80 - time schedule'!S53","v":0},{"$f":"'K80 - time schedule'!T53","v":0},{"$f":"'K80 - time schedule'!U53","v":0},{"$f":"'K80 - time schedule'!V53","v":0},{"$f":"'K80 - time schedule'!W53","v":0},{"$f":"'K80 - time schedule'!X53","v":0},{"$f":"'K80 - time schedule'!Y53","v":0},{"$f":"'K80 - time schedule'!Z53","v":0},{"$f":"'K80 - time schedule'!AA53","v":0},{"$f":"'K80 - time schedule'!AB53","v":0},{"$f":"'K80 - time schedule'!AC53","v":0},{"$f":"'K80 - time schedule'!AD53","v":0},{"$f":"'K80 - time schedule'!AE53","v":0},{"$f":"'K80 - time schedule'!AF53","v":0},{"$f":"'K80 - time schedule'!AG53","v":0},{"$f":"'K80 - time schedule'!AH53","v":0},{"$f":"'K80 - time schedule'!AI53","v":0},{"$f":"'K80 - time schedule'!AJ53","v":0},{"$f":"'K80 - time schedule'!AK53","v":0},{"$f":"'K80 - time schedule'!AL53","v":0},{"$f":"'K80 - time schedule'!AM53","v":0},{"$f":"'K80 - time schedule'!AN53","v":0},{"$f":"'K80 - time schedule'!AO53","v":0},{"$f":"'K80 - time schedule'!AP53","v":0},{"$f":"'K80 - time schedule'!AQ53","v":0},{"$f":"'K80 - time schedule'!AR53","v":0},{"$f":"'K80 - time schedule'!AS53","v":0},{"$f":"'K80 - time schedule'!AT53","v":0},{"$f":"'K80 - time schedule'!AU53","v":0},{"$f":"'K80 - time schedule'!AV53","v":0},{"$f":"'K80 - time schedule'!AW53","v":0},{"$f":"'K80 - time schedule'!AX53","v":0},{"$f":"'K80 - time schedule'!AY53","v":0},{"$f":"'K80 - time schedule'!AZ53","v":0},{"$f":"'K80 - time schedule'!BA53","v":0},{"$f":"'K80 - time schedule'!BB53","v":0},{"$f":"'K80 - time schedule'!BC53","v":0},{"$f":"'K80 - time schedule'!BD53","v":0},{"$f":"'K80 - time schedule'!BE53","v":0},{"$f":"'K80 - time schedule'!BF53","v":0},{"$f":"'K80 - time schedule'!BG53","v":0},{"$f":"'K80 - time schedule'!BH53","v":0},{"$f":"'K80 - time schedule'!BI53","v":0},{"$f":"'K80 - time schedule'!BJ53","v":0},{"$f":"'K80 - time schedule'!BK53","v":0},{"$f":"'K80 - time schedule'!BL53","v":0},{"$f":"'K80 - time schedule'!BM53","v":0},{"$f":"'K80 - time schedule'!BN53","v":0},{"$f":"'K80 - time schedule'!BO53","v":0},{"$f":"'K80 - time schedule'!BP53","v":0},{"$f":"'K80 - time schedule'!BQ53","v":0},{"$f":"'K80 - time schedule'!BR53","v":0},{"$f":"'K80 - time schedule'!BS53","v":0},{"$f":"'K80 - time schedule'!BT53","v":0},{"$f":"'K80 - time schedule'!BU53","v":0},{"$f":"'K80 - time schedule'!BV53","v":0},{"$f":"'K80 - time schedule'!BW53","v":0},{"$f":"'K80 - time schedule'!BX53","v":0},{"$f":"'K80 - time schedule'!BY53","v":0},{"$f":"'K80 - time schedule'!BZ53","v":0},{"$f":"'K80 - time schedule'!CA53","v":0},{"$f":"'K80 - time schedule'!CB53","v":0},{"$f":"'K80 - time schedule'!CC53","v":0},{"$f":"'K80 - time schedule'!CD53","v":0},{"$f":"'K80 - time schedule'!CE53","v":0},{"$f":"'K80 - time schedule'!CF53","v":0},{"$f":"'K80 - time schedule'!CG53","v":0},{"$f":"'K80 - time schedule'!CH53","v":0},{"$f":"'K80 - time schedule'!CI53","v":0},{"$f":"'K80 - time schedule'!CJ53","v":0},{"$f":"'K80 - time schedule'!CK53","v":0},{"$f":"'K80 - time schedule'!CL53","v":0},{"$f":"'K80 - time schedule'!CM53","v":0},{"$f":"'K80 - time schedule'!CN53","v":0},{"$f":"'K80 - time schedule'!CO53","v":0},{"$f":"'K80 - time schedule'!CP53","v":0},{"$f":"'K80 - time schedule'!CQ53","v":0},{"$f":"'K80 - time schedule'!CR53","v":0},{"$f":"'K80 - time schedule'!CS53","v":0},{"$f":"'K80 - time schedule'!CT53","v":0},{"$f":"'K80 - time schedule'!CU53","v":0},{"$f":"'K80 - time schedule'!CV53","v":0},{"$f":"'K80 - time schedule'!CW53","v":0},{"$f":"'K80 - time schedule'!CX53","v":0},{"$f":"'K80 - time schedule'!CY53","v":0},{"$f":"'K80 - time schedule'!CZ53","v":0},{"$f":"'K80 - time schedule'!DA53","v":0},{"$f":"'K80 - time schedule'!DB53","v":0},{"$f":"'K80 - time schedule'!DC53","v":0},{"$f":"'K80 - time schedule'!DD53","v":0},{"$f":"'K80 - time schedule'!DE53","v":0},{"$f":"'K80 - time schedule'!DF53","v":0},{"$f":"'K80 - time schedule'!DG53","v":0},{"$f":"'K80 - time schedule'!DH53","v":0},{"$f":"'K80 - time schedule'!DI53","v":0},{"$f":"'K80 - time schedule'!DJ53","v":0},{"$f":"'K80 - time schedule'!DK53","v":0},{"$f":"'K80 - time schedule'!DL53","v":0},{"$f":"'K80 - time schedule'!DM53","v":0},{"$f":"'K80 - time schedule'!DN53","v":0},{"$f":"'K80 - time schedule'!DO53","v":0},{"$f":"'K80 - time schedule'!DP53","v":0},{"$f":"'K80 - time schedule'!DQ53","v":0},{"$f":"'K80 - time schedule'!DR53","v":0},{"$f":"'K80 - time schedule'!DS53","v":0},{"$f":"'K80 - time schedule'!DT53","v":0},{"$f":"'K80 - time schedule'!DU53","v":0},{"$f":"'K80 - time schedule'!DV53","v":0},{"$f":"'K80 - time schedule'!DW53","v":0},{"$f":"'K80 - time schedule'!DX53","v":0},{"$f":"'K80 - time schedule'!DY53","v":0},{"$f":"'K80 - time schedule'!DZ53","v":0},{"$f":"'K80 - time schedule'!EA53","v":0},{"$f":"'K80 - time schedule'!EB53","v":0},{"$f":"'K80 - time schedule'!EC53","v":0},{"$f":"'K80 - time schedule'!ED53","v":0},{"$f":"'K80 - time schedule'!EE53","v":0},{"$f":"'K80 - time schedule'!EF53","v":0},{"$f":"'K80 - time schedule'!EG53","v":0},{"$f":"'K80 - time schedule'!EH53","v":0},{"$f":"'K80 - time schedule'!EI53","v":0},{"$f":"'K80 - time schedule'!EJ53","v":0},{"$f":"'K80 - time schedule'!EK53","v":0},{"$f":"'K80 - time schedule'!EL53","v":0},{"$f":"'K80 - time schedule'!EM53","v":0},{"$f":"'K80 - time schedule'!EN53","v":0},{"$f":"'K80 - time schedule'!EO53","v":0},{"$f":"'K80 - time schedule'!EP53","v":0},{"$f":"'K80 - time schedule'!EQ53","v":0},{"$f":"'K80 - time schedule'!ER53","v":0},{"$f":"'K80 - time schedule'!ES53","v":0},{"$f":"'K80 - time schedule'!ET53","v":0},{"$f":"'K80 - time schedule'!EU53","v":0},{"$f":"'K80 - time schedule'!EV53","v":0},{"$f":"'K80 - time schedule'!EW53","v":0},{"$f":"'K80 - time schedule'!EX53","v":0},{"$f":"'K80 - time schedule'!EY53","v":0},{"$f":"'K80 - time schedule'!EZ53","v":0},{"$f":"'K80 - time schedule'!FA53","v":0},{"$f":"'K80 - time schedule'!FB53","v":0},{"$f":"'K80 - time schedule'!FC53","v":0},{"$f":"'K80 - time schedule'!FD53","v":0},{"$f":"'K80 - time schedule'!FE53","v":0},{"$f":"'K80 - time schedule'!FF53","v":0},{"$f":"'K80 - time schedule'!FG53","v":0},{"$f":"'K80 - time schedule'!FH53","v":0},{"$f":"'K80 - time schedule'!FI53","v":0},{"$f":"'K80 - time schedule'!FJ53","v":0},{"$f":"'K80 - time schedule'!FK53","v":0},{"$f":"'K80 - time schedule'!FL53","v":0},{"$f":"'K80 - time schedule'!FM53","v":0},{"$f":"'K80 - time schedule'!FN53","v":0},{"$f":"'K80 - time schedule'!FO53","v":0},{"$f":"'K80 - time schedule'!FP53","v":0},{"$f":"'K80 - time schedule'!FQ53","v":0},{"$f":"'K80 - time schedule'!FR53","v":0},{"$f":"'K80 - time schedule'!FS53","v":0},{"$f":"'K80 - time schedule'!FT53","v":0},{"$f":"'K80 - time schedule'!FU53","v":0},{"$f":"'K80 - time schedule'!FV53","v":0},{"$f":"'K80 - time schedule'!FW53","v":0},{"$f":"'K80 - time schedule'!FX53","v":0},{"$f":"'K80 - time schedule'!FY53","v":0},{"$f":"'K80 - time schedule'!FZ53","v":0},{"$f":"'K80 - time schedule'!GA53","v":0},{"$f":"'K80 - time schedule'!GB53","v":0},{"$f":"'K80 - time schedule'!GC53","v":0},{"$f":"'K80 - time schedule'!GD53","v":0},{"$f":"'K80 - time schedule'!GE53","v":0},{"$f":"'K80 - time schedule'!GF53","v":0},{"$f":"'K80 - time schedule'!GG53","v":0},{"$f":"'K80 - time schedule'!GH53","v":0},{"$f":"'K80 - time schedule'!GI53","v":0},{"$f":"'K80 - time schedule'!GJ53","v":0},{"$f":"'K80 - time schedule'!GK53","v":0},{"$f":"'K80 - time schedule'!GL53","v":0},{"$f":"'K80 - time schedule'!GM53","v":0},{"$f":"'K80 - time schedule'!GN53","v":0},{"$f":"'K80 - time schedule'!GO53","v":0},{"$f":"'K80 - time schedule'!GP53","v":0},{"$f":"'K80 - time schedule'!GQ53","v":0},{"$f":"'K80 - time schedule'!GR53","v":0},{"$f":"'K80 - time schedule'!GS53","v":0},{"$f":"'K80 - time schedule'!GT53","v":0},{"$f":"'K80 - time schedule'!GU53","v":0},{"$f":"'K80 - time schedule'!GV53","v":0},{"$f":"'K80 - time schedule'!GW53","v":0},{"$f":"'K80 - time schedule'!GX53","v":0},{"$f":"'K80 - time schedule'!GY53","v":0},{"$f":"'K80 - time schedule'!GZ53","v":0},{"$f":"'K80 - time schedule'!HA53","v":0},{"$f":"'K80 - time schedule'!HB53","v":0},{"$f":"'K80 - time schedule'!HC53","v":0},{"$f":"'K80 - time schedule'!HD53","v":0},{"$f":"'K80 - time schedule'!HE53","v":0},{"$f":"'K80 - time schedule'!HF53","v":0},{"$f":"'K80 - time schedule'!HG53","v":0},{"$f":"'K80 - time schedule'!HH53","v":0},{"$f":"'K80 - time schedule'!HI53","v":0},{"$f":"'K80 - time schedule'!HJ53","v":0},{"$f":"'K80 - time schedule'!HK53","v":0},{"$f":"'K80 - time schedule'!HL53","v":0},{"$f":"'K80 - time schedule'!HM53","v":0},{"$f":"'K80 - time schedule'!HN53","v":0},{"$f":"'K80 - time schedule'!HO53","v":0},{"$f":"'K80 - time schedule'!HP53","v":0},{"$f":"'K80 - time schedule'!HQ53","v":0},{"$f":"'K80 - time schedule'!HR53","v":0},{"$f":"'K80 - time schedule'!HS53","v":0},{"$f":"'K80 - time schedule'!HT53","v":0},{"$f":"'K80 - time schedule'!HU53","v":0},{"$f":"'K80 - time schedule'!HV53","v":0},{"$f":"'K80 - time schedule'!HW53","v":0},{"$f":"'K80 - time schedule'!HX53","v":0},{"$f":"'K80 - time schedule'!HY53","v":0},{"$f":"'K80 - time schedule'!HZ53","v":0},{"$f":"'K80 - time schedule'!IA53","v":0},{"$f":"'K80 - time schedule'!IB53","v":0},{"$f":"'K80 - time schedule'!IC53","v":0},{"$f":"'K80 - time schedule'!ID53","v":0},{"$f":"'K80 - time schedule'!IE53","v":0},{"$f":"'K80 - time schedule'!IF53","v":0},{"$f":"'K80 - time schedule'!IG53","v":0},{"$f":"'K80 - time schedule'!IH53","v":0},{"$f":"'K80 - time schedule'!II53","v":0},{"$f":"'K80 - time schedule'!IJ53","v":0},{"$f":"'K80 - time schedule'!IK53","v":0},{"$f":"'K80 - time schedule'!IL53","v":0},{"$f":"'K80 - time schedule'!IM53","v":0},{"$f":"'K80 - time schedule'!IN53","v":0},{"$f":"'K80 - time schedule'!IO53","v":0},{"$f":"'K80 - time schedule'!IP53","v":0},{"$f":"'K80 - time schedule'!IQ53","v":0},{"$f":"'K80 - time schedule'!IR53","v":0},{"$f":"'K80 - time schedule'!IS53","v":0},{"$f":"'K80 - time schedule'!IT53","v":0},{"$f":"'K80 - time schedule'!IU53","v":0},{"$f":"'K80 - time schedule'!IV53","v":0},{"$f":"'K80 - time schedule'!IW53","v":0},{"$f":"'K80 - time schedule'!IX53","v":0},{"$f":"'K80 - time schedule'!IY53","v":0},{"$f":"'K80 - time schedule'!IZ53","v":0},{"$f":"'K80 - time schedule'!JA53","v":0},{"$f":"'K80 - time schedule'!JB53","v":0},{"$f":"'K80 - time schedule'!JC53","v":0},{"$f":"'K80 - time schedule'!JD53","v":0},{"$f":"'K80 - time schedule'!JE53","v":0},{"$f":"'K80 - time schedule'!JF53","v":0},{"$f":"'K80 - time schedule'!JG53","v":0},{"$f":"'K80 - time schedule'!JH53","v":0},{"$f":"'K80 - time schedule'!JI53","v":0},{"$f":"'K80 - time schedule'!JJ53","v":0},{"$f":"'K80 - time schedule'!JK53","v":0},{"$f":"'K80 - time schedule'!JL53","v":0},{"$f":"'K80 - time schedule'!JM53","v":0},{"$f":"'K80 - time schedule'!JN53","v":0},{"$f":"'K80 - time schedule'!JO53","v":0},{"$f":"'K80 - time schedule'!JP53","v":0},{"$f":"'K80 - time schedule'!JQ53","v":0},{"$f":"'K80 - time schedule'!JR53","v":0},{"$f":"'K80 - time schedule'!JS53","v":0},{"$f":"'K80 - time schedule'!JT53","v":0},{"$f":"'K80 - time schedule'!JU53","v":0},{"$f":"'K80 - time schedule'!JV53","v":0},{"$f":"'K80 - time schedule'!JW53","v":0},{"$f":"'K80 - time schedule'!JX53","v":0},{"$f":"'K80 - time schedule'!JY53","v":0},{"$f":"'K80 - time schedule'!JZ53","v":0},{"$f":"'K80 - time schedule'!KA53","v":0},{"$f":"'K80 - time schedule'!KB53","v":0},{"$f":"'K80 - time schedule'!KC53","v":0},{"$f":"'K80 - time schedule'!KD53","v":0},{"$f":"'K80 - time schedule'!KE53","v":0},{"$f":"'K80 - time schedule'!KF53","v":0},{"$f":"'K80 - time schedule'!KG53","v":0},{"$f":"'K80 - time schedule'!KH53","v":0},{"$f":"'K80 - time schedule'!KI53","v":0},{"$f":"'K80 - time schedule'!KJ53","v":0},{"$f":"'K80 - time schedule'!KK53","v":0},{"$f":"'K80 - time schedule'!KL53","v":0},{"$f":"'K80 - time schedule'!KM53","v":0},{"$f":"'K80 - time schedule'!KN53","v":0},{"$f":"'K80 - time schedule'!KO53","v":0},{"$f":"'K80 - time schedule'!KP53","v":0},{"$f":"'K80 - time schedule'!KQ53","v":0},{"$f":"'K80 - time schedule'!KR53","v":0},{"$f":"'K80 - time schedule'!KS53","v":0},{"$f":"'K80 - time schedule'!KT53","v":0}]
["Boiler room K80 - trial operation","K80",{"$f":"'K80 - time schedule'!G55","v":0},{"$f":"'K80 - time schedule'!H55","v":0},{"$f":"'K80 - time schedule'!I55","v":0},{"$f":"'K80 - time schedule'!J55","v":0},{"$f":"'K80 - time schedule'!K55","v":0},{"$f":"'K80 - time schedule'!L55","v":0},{"$f":"'K80 - time schedule'!M55","v":0},{"$f":"'K80 - time schedule'!N55","v":0},{"$f":"'K80 - time schedule'!O55","v":0},{"$f":"'K80 - time schedule'!P55","v":0},{"$f":"'K80 - time schedule'!Q55","v":0},{"$f":"'K80 - time schedule'!R55","v":0},{"$f":"'K80 - time schedule'!S55","v":0},{"$f":"'K80 - time schedule'!T55","v":0},{"$f":"'K80 - time schedule'!U55","v":0},{"$f":"'K80 - time schedule'!V55","v":0},{"$f":"'K80 - time schedule'!W55","v":0},{"$f":"'K80 - time schedule'!X55","v":0},{"$f":"'K80 - time schedule'!Y55","v":0},{"$f":"'K80 - time schedule'!Z55","v":0},{"$f":"'K80 - time schedule'!AA55","v":0},{"$f":"'K80 - time schedule'!AB55","v":0},{"$f":"'K80 - time schedule'!AC55","v":0},{"$f":"'K80 - time schedule'!AD55","v":0},{"$f":"'K80 - time schedule'!AE55","v":0},{"$f":"'K80 - time schedule'!AF55","v":0},{"$f":"'K80 - time schedule'!AG55","v":0},{"$f":"'K80 - time schedule'!AH55","v":0},{"$f":"'K80 - time schedule'!AI55","v":0},{"$f":"'K80 - time schedule'!AJ55","v":0},{"$f":"'K80 - time schedule'!AK55","v":0},{"$f":"'K80 - time schedule'!AL55","v":0},{"$f":"'K80 - time schedule'!AM55","v":0},{"$f":"'K80 - time schedule'!AN55","v":0},{"$f":"'K80 - time schedule'!AO55","v":0},{"$f":"'K80 - time schedule'!AP55","v":0},{"$f":"'K80 - time schedule'!AQ55","v":0},{"$f":"'K80 - time schedule'!AR55","v":0},{"$f":"'K80 - time schedule'!AS55","v":0},{"$f":"'K80 - time schedule'!AT55","v":0},{"$f":"'K80 - time schedule'!AU55","v":0},{"$f":"'K80 - time schedule'!AV55","v":0},{"$f":"'K80 - time schedule'!AW55","v":0},{"$f":"'K80 - time schedule'!AX55","v":0},{"$f":"'K80 - time schedule'!AY55","v":0},{"$f":"'K80 - time schedule'!AZ55","v":0},{"$f":"'K80 - time schedule'!BA55","v":0},{"$f":"'K80 - time schedule'!BB55","v":0},{"$f":"'K80 - time schedule'!BC55","v":0},{"$f":"'K80 - time schedule'!BD55","v":0},{"$f":"'K80 - time schedule'!BE55","v":0},{"$f":"'K80 - time schedule'!BF55","v":0},{"$f":"'K80 - time schedule'!BG55","v":0},{"$f":"'K80 - time schedule'!BH55","v":0},{"$f":"'K80 - time schedule'!BI55","v":0},{"$f":"'K80 - time schedule'!BJ55","v":0},{"$f":"'K80 - time schedule'!BK55","v":0},{"$f":"'K80 - time schedule'!BL55","v":0},{"$f":"'K80 - time schedule'!BM55","v":0},{"$f":"'K80 - time schedule'!BN55","v":0},{"$f":"'K80 - time schedule'!BO55","v":0},{"$f":"'K80 - time schedule'!BP55","v":0},{"$f":"'K80 - time schedule'!BQ55","v":0},{"$f":"'K80 - time schedule'!BR55","v":0},{"$f":"'K80 - time schedule'!BS55","v":0},{"$f":"'K80 - time schedule'!BT55","v":0},{"$f":"'K80 - time schedule'!BU55","v":0},{"$f":"'K80 - time schedule'!BV55","v":0},{"$f":"'K80 - time schedule'!BW55","v":0},{"$f":"'K80 - time schedule'!BX55","v":0},{"$f":"'K80 - time schedule'!BY55","v":0},{"$f":"'K80 - time schedule'!BZ55","v":0},{"$f":"'K80 - time schedule'!CA55","v":0},{"$f":"'K80 - time schedule'!CB55","v":0},{"$f":"'K80 - time schedule'!CC55","v":0},{"$f":"'K80 - time schedule'!CD55","v":0},{"$f":"'K80 - time schedule'!CE55","v":0},{"$f":"'K80 - time schedule'!CF55","v":0},{"$f":"'K80 - time schedule'!CG55","v":0},{"$f":"'K80 - time schedule'!CH55","v":0},{"$f":"'K80 - time schedule'!CI55","v":0},{"$f":"'K80 - time schedule'!CJ55","v":0},{"$f":"'K80 - time schedule'!CK55","v":0},{"$f":"'K80 - time schedule'!CL55","v":0},{"$f":"'K80 - time schedule'!CM55","v":0},{"$f":"'K80 - time schedule'!CN55","v":0},{"$f":"'K80 - time schedule'!CO55","v":0},{"$f":"'K80 - time schedule'!CP55","v":0},{"$f":"'K80 - time schedule'!CQ55","v":0},{"$f":"'K80 - time schedule'!CR55","v":0},{"$f":"'K80 - time schedule'!CS55","v":0},{"$f":"'K80 - time schedule'!CT55","v":0},{"$f":"'K80 - time schedule'!CU55","v":0},{"$f":"'K80 - time schedule'!CV55","v":0},{"$f":"'K80 - time schedule'!CW55","v":0},{"$f":"'K80 - time schedule'!CX55","v":0},{"$f":"'K80 - time schedule'!CY55","v":0},{"$f":"'K80 - time schedule'!CZ55","v":0},{"$f":"'K80 - time schedule'!DA55","v":0},{"$f":"'K80 - time schedule'!DB55","v":0},{"$f":"'K80 - time schedule'!DC55","v":0},{"$f":"'K80 - time schedule'!DD55","v":0},{"$f":"'K80 - time schedule'!DE55","v":0},{"$f":"'K80 - time schedule'!DF55","v":0},{"$f":"'K80 - time schedule'!DG55","v":0},{"$f":"'K80 - time schedule'!DH55","v":0},{"$f":"'K80 - time schedule'!DI55","v":0},{"$f":"'K80 - time schedule'!DJ55","v":0},{"$f":"'K80 - time schedule'!DK55","v":0},{"$f":"'K80 - time schedule'!DL55","v":0},{"$f":"'K80 - time schedule'!DM55","v":0},{"$f":"'K80 - time schedule'!DN55","v":0},{"$f":"'K80 - time schedule'!DO55","v":0},{"$f":"'K80 - time schedule'!DP55","v":0},{"$f":"'K80 - time schedule'!DQ55","v":0},{"$f":"'K80 - time schedule'!DR55","v":0},{"$f":"'K80 - time schedule'!DS55","v":0},{"$f":"'K80 - time schedule'!DT55","v":0},{"$f":"'K80 - time schedule'!DU55","v":0},{"$f":"'K80 - time schedule'!DV55","v":0},{"$f":"'K80 - time schedule'!DW55","v":0},{"$f":"'K80 - time schedule'!DX55","v":0},{"$f":"'K80 - time schedule'!DY55","v":0},{"$f":"'K80 - time schedule'!DZ55","v":0},{"$f":"'K80 - time schedule'!EA55","v":0},{"$f":"'K80 - time schedule'!EB55","v":0},{"$f":"'K80 - time schedule'!EC55","v":0},{"$f":"'K80 - time schedule'!ED55","v":0},{"$f":"'K80 - time schedule'!EE55","v":0},{"$f":"'K80 - time schedule'!EF55","v":0},{"$f":"'K80 - time schedule'!EG55","v":0},{"$f":"'K80 - time schedule'!EH55","v":0},{"$f":"'K80 - time schedule'!EI55","v":0},{"$f":"'K80 - time schedule'!EJ55","v":0},{"$f":"'K80 - time schedule'!EK55","v":0},{"$f":"'K80 - time schedule'!EL55","v":0},{"$f":"'K80 - time schedule'!EM55","v":0},{"$f":"'K80 - time schedule'!EN55","v":0},{"$f":"'K80 - time schedule'!EO55","v":0},{"$f":"'K80 - time schedule'!EP55","v":0},{"$f":"'K80 - time schedule'!EQ55","v":0},{"$f":"'K80 - time schedule'!ER55","v":0},{"$f":"'K80 - time schedule'!ES55","v":0},{"$f":"'K80 - time schedule'!ET55","v":0},{"$f":"'K80 - time schedule'!EU55","v":0},{"$f":"'K80 - time schedule'!EV55","v":0},{"$f":"'K80 - time schedule'!EW55","v":0},{"$f":"'K80 - time schedule'!EX55","v":0},{"$f":"'K80 - time schedule'!EY55","v":0},{"$f":"'K80 - time schedule'!EZ55","v":0},{"$f":"'K80 - time schedule'!FA55","v":0},{"$f":"'K80 - time schedule'!FB55","v":0},{"$f":"'K80 - time schedule'!FC55","v":0},{"$f":"'K80 - time schedule'!FD55","v":0},{"$f":"'K80 - time schedule'!FE55","v":0},{"$f":"'K80 - time schedule'!FF55","v":0},{"$f":"'K80 - time schedule'!FG55","v":0},{"$f":"'K80 - time schedule'!FH55","v":0},{"$f":"'K80 - time schedule'!FI55","v":0},{"$f":"'K80 - time schedule'!FJ55","v":0},{"$f":"'K80 - time schedule'!FK55","v":0},{"$f":"'K80 - time schedule'!FL55","v":0},{"$f":"'K80 - time schedule'!FM55","v":0},{"$f":"'K80 - time schedule'!FN55","v":0},{"$f":"'K80 - time schedule'!FO55","v":0},{"$f":"'K80 - time schedule'!FP55","v":0},{"$f":"'K80 - time schedule'!FQ55","v":0},{"$f":"'K80 - time schedule'!FR55","v":0},{"$f":"'K80 - time schedule'!FS55","v":0},{"$f":"'K80 - time schedule'!FT55","v":0},{"$f":"'K80 - time schedule'!FU55","v":0},{"$f":"'K80 - time schedule'!FV55","v":0},{"$f":"'K80 - time schedule'!FW55","v":0},{"$f":"'K80 - time schedule'!FX55","v":0},{"$f":"'K80 - time schedule'!FY55","v":0},{"$f":"'K80 - time schedule'!FZ55","v":0},{"$f":"'K80 - time schedule'!GA55","v":0},{"$f":"'K80 - time schedule'!GB55","v":0},{"$f":"'K80 - time schedule'!GC55","v":0},{"$f":"'K80 - time schedule'!GD55","v":0},{"$f":"'K80 - time schedule'!GE55","v":0},{"$f":"'K80 - time schedule'!GF55","v":0},{"$f":"'K80 - time schedule'!GG55","v":0},{"$f":"'K80 - time schedule'!GH55","v":0},{"$f":"'K80 - time schedule'!GI55","v":0},{"$f":"'K80 - time schedule'!GJ55","v":0},{"$f":"'K80 - time schedule'!GK55","v":0},{"$f":"'K80 - time schedule'!GL55","v":0},{"$f":"'K80 - time schedule'!GM55","v":0},{"$f":"'K80 - time schedule'!GN55","v":0},{"$f":"'K80 - time schedule'!GO55","v":0},{"$f":"'K80 - time schedule'!GP55","v":0},{"$f":"'K80 - time schedule'!GQ55","v":0},{"$f":"'K80 - time schedule'!GR55","v":0},{"$f":"'K80 - time schedule'!GS55","v":0},{"$f":"'K80 - time schedule'!GT55","v":0},{"$f":"'K80 - time schedule'!GU55","v":0},{"$f":"'K80 - time schedule'!GV55","v":0},{"$f":"'K80 - time schedule'!GW55","v":0},{"$f":"'K80 - time schedule'!GX55","v":0},{"$f":"'K80 - time schedule'!GY55","v":0},{"$f":"'K80 - time schedule'!GZ55","v":0},{"$f":"'K80 - time schedule'!HA55","v":0},{"$f":"'K80 - time schedule'!HB55","v":0},{"$f":"'K80 - time schedule'!HC55","v":0},{"$f":"'K80 - time schedule'!HD55","v":0},{"$f":"'K80 - time schedule'!HE55","v":0},{"$f":"'K80 - time schedule'!HF55","v":0},{"$f":"'K80 - time schedule'!HG55","v":0},{"$f":"'K80 - time schedule'!HH55","v":0},{"$f":"'K80 - time schedule'!HI55","v":0},{"$f":"'K80 - time schedule'!HJ55","v":0},{"$f":"'K80 - time schedule'!HK55","v":0},{"$f":"'K80 - time schedule'!HL55","v":0},{"$f":"'K80 - time schedule'!HM55","v":0},{"$f":"'K80 - time schedule'!HN55","v":0},{"$f":"'K80 - time schedule'!HO55","v":0},{"$f":"'K80 - time schedule'!HP55","v":0},{"$f":"'K80 - time schedule'!HQ55","v":0},{"$f":"'K80 - time schedule'!HR55","v":0},{"$f":"'K80 - time schedule'!HS55","v":0},{"$f":"'K80 - time schedule'!HT55","v":0},{"$f":"'K80 - time schedule'!HU55","v":0},{"$f":"'K80 - time schedule'!HV55","v":0},{"$f":"'K80 - time schedule'!HW55","v":0},{"$f":"'K80 - time schedule'!HX55","v":0},{"$f":"'K80 - time schedule'!HY55","v":0},{"$f":"'K80 - time schedule'!HZ55","v":0},{"$f":"'K80 - time schedule'!IA55","v":0},{"$f":"'K80 - time schedule'!IB55","v":0},{"$f":"'K80 - time schedule'!IC55","v":0},{"$f":"'K80 - time schedule'!ID55","v":0},{"$f":"'K80 - time schedule'!IE55","v":0},{"$f":"'K80 - time schedule'!IF55","v":0},{"$f":"'K80 - time schedule'!IG55","v":0},{"$f":"'K80 - time schedule'!IH55","v":0},{"$f":"'K80 - time schedule'!II55","v":0},{"$f":"'K80 - time schedule'!IJ55","v":0},{"$f":"'K80 - time schedule'!IK55","v":0},{"$f":"'K80 - time schedule'!IL55","v":0},{"$f":"'K80 - time schedule'!IM55","v":0},{"$f":"'K80 - time schedule'!IN55","v":0},{"$f":"'K80 - time schedule'!IO55","v":0},{"$f":"'K80 - time schedule'!IP55","v":0},{"$f":"'K80 - time schedule'!IQ55","v":0},{"$f":"'K80 - time schedule'!IR55","v":0},{"$f":"'K80 - time schedule'!IS55","v":0},{"$f":"'K80 - time schedule'!IT55","v":0},{"$f":"'K80 - time schedule'!IU55","v":0},{"$f":"'K80 - time schedule'!IV55","v":0},{"$f":"'K80 - time schedule'!IW55","v":0},{"$f":"'K80 - time schedule'!IX55","v":0},{"$f":"'K80 - time schedule'!IY55","v":0},{"$f":"'K80 - time schedule'!IZ55","v":0},{"$f":"'K80 - time schedule'!JA55","v":0},{"$f":"'K80 - time schedule'!JB55","v":0},{"$f":"'K80 - time schedule'!JC55","v":0},{"$f":"'K80 - time schedule'!JD55","v":0},{"$f":"'K80 - time schedule'!JE55","v":0},{"$f":"'K80 - time schedule'!JF55","v":0},{"$f":"'K80 - time schedule'!JG55","v":0},{"$f":"'K80 - time schedule'!JH55","v":0},{"$f":"'K80 - time schedule'!JI55","v":0},{"$f":"'K80 - time schedule'!JJ55","v":0},{"$f":"'K80 - time schedule'!JK55","v":0},{"$f":"'K80 - time schedule'!JL55","v":0},{"$f":"'K80 - time schedule'!JM55","v":0},{"$f":"'K80 - time schedule'!JN55","v":0},{"$f":"'K80 - time schedule'!JO55","v":0},{"$f":"'K80 - time schedule'!JP55","v":0},{"$f":"'K80 - time schedule'!JQ55","v":0},{"$f":"'K80 - time schedule'!JR55","v":0},{"$f":"'K80 - time schedule'!JS55","v":0},{"$f":"'K80 - time schedule'!JT55","v":0},{"$f":"'K80 - time schedule'!JU55","v":0},{"$f":"'K80 - time schedule'!JV55","v":0},{"$f":"'K80 - time schedule'!JW55","v":0},{"$f":"'K80 - time schedule'!JX55","v":0},{"$f":"'K80 - time schedule'!JY55","v":0},{"$f":"'K80 - time schedule'!JZ55","v":0},{"$f":"'K80 - time schedule'!KA55","v":0},{"$f":"'K80 - time schedule'!KB55","v":0},{"$f":"'K80 - time schedule'!KC55","v":0},{"$f":"'K80 - time schedule'!KD55","v":0},{"$f":"'K80 - time schedule'!KE55","v":0},{"$f":"'K80 - time schedule'!KF55","v":0},{"$f":"'K80 - time schedule'!KG55","v":0},{"$f":"'K80 - time schedule'!KH55","v":0},{"$f":"'K80 - time schedule'!KI55","v":0},{"$f":"'K80 - time schedule'!KJ55","v":0},{"$f":"'K80 - time schedule'!KK55","v":0},{"$f":"'K80 - time schedule'!KL55","v":0},{"$f":"'K80 - time schedule'!KM55","v":0},{"$f":"'K80 - time schedule'!KN55","v":0},{"$f":"'K80 - time schedule'!KO55","v":0},{"$f":"'K80 - time schedule'!KP55","v":0},{"$f":"'K80 - time schedule'!KQ55","v":0},{"$f":"'K80 - time schedule'!KR55","v":0},{"$f":"'K80 - time schedule'!KS55","v":0},{"$f":"'K80 - time schedule'!KT55","v":0}]
["Boiler room K80 - guarantee test A","K80",{"$f":"'K80 - time schedule'!G57","v":0},{"$f":"'K80 - time schedule'!H57","v":0},{"$f":"'K80 - time schedule'!I57","v":0},{"$f":"'K80 - time schedule'!J57","v":0},{"$f":"'K80 - time schedule'!K57","v":0},{"$f":"'K80 - time schedule'!L57","v":0},{"$f":"'K80 - time schedule'!M57","v":0},{"$f":"'K80 - time schedule'!N57","v":0},{"$f":"'K80 - time schedule'!O57","v":0},{"$f":"'K80 - time schedule'!P57","v":0},{"$f":"'K80 - time schedule'!Q57","v":0},{"$f":"'K80 - time schedule'!R57","v":0},{"$f":"'K80 - time schedule'!S57","v":0},{"$f":"'K80 - time schedule'!T57","v":0},{"$f":"'K80 - time schedule'!U57","v":0},{"$f":"'K80 - time schedule'!V57","v":0},{"$f":"'K80 - time schedule'!W57","v":0},{"$f":"'K80 - time schedule'!X57","v":0},{"$f":"'K80 - time schedule'!Y57","v":0},{"$f":"'K80 - time schedule'!Z57","v":0},{"$f":"'K80 - time schedule'!AA57","v":0},{"$f":"'K80 - time schedule'!AB57","v":0},{"$f":"'K80 - time schedule'!AC57","v":0},{"$f":"'K80 - time schedule'!AD57","v":0},{"$f":"'K80 - time schedule'!AE57","v":0},{"$f":"'K80 - time schedule'!AF57","v":0},{"$f":"'K80 - time schedule'!AG57","v":0},{"$f":"'K80 - time schedule'!AH57","v":0},{"$f":"'K80 - time schedule'!AI57","v":0},{"$f":"'K80 - time schedule'!AJ57","v":0},{"$f":"'K80 - time schedule'!AK57","v":0},{"$f":"'K80 - time schedule'!AL57","v":0},{"$f":"'K80 - time schedule'!AM57","v":0},{"$f":"'K80 - time schedule'!AN57","v":0},{"$f":"'K80 - time schedule'!AO57","v":0},{"$f":"'K80 - time schedule'!AP57","v":0},{"$f":"'K80 - time schedule'!AQ57","v":0},{"$f":"'K80 - time schedule'!AR57","v":0},{"$f":"'K80 - time schedule'!AS57","v":0},{"$f":"'K80 - time schedule'!AT57","v":0},{"$f":"'K80 - time schedule'!AU57","v":0},{"$f":"'K80 - time schedule'!AV57","v":0},{"$f":"'K80 - time schedule'!AW57","v":0},{"$f":"'K80 - time schedule'!AX57","v":0},{"$f":"'K80 - time schedule'!AY57","v":0},{"$f":"'K80 - time schedule'!AZ57","v":0},{"$f":"'K80 - time schedule'!BA57","v":0},{"$f":"'K80 - time schedule'!BB57","v":0},{"$f":"'K80 - time schedule'!BC57","v":0},{"$f":"'K80 - time schedule'!BD57","v":0},{"$f":"'K80 - time schedule'!BE57","v":0},{"$f":"'K80 - time schedule'!BF57","v":0},{"$f":"'K80 - time schedule'!BG57","v":0},{"$f":"'K80 - time schedule'!BH57","v":0},{"$f":"'K80 - time schedule'!BI57","v":0},{"$f":"'K80 - time schedule'!BJ57","v":0},{"$f":"'K80 - time schedule'!BK57","v":0},{"$f":"'K80 - time schedule'!BL57","v":0},{"$f":"'K80 - time schedule'!BM57","v":0},{"$f":"'K80 - time schedule'!BN57","v":0},{"$f":"'K80 - time schedule'!BO57","v":0},{"$f":"'K80 - time schedule'!BP57","v":0},{"$f":"'K80 - time schedule'!BQ57","v":0},{"$f":"'K80 - time schedule'!BR57","v":0},{"$f":"'K80 - time schedule'!BS57","v":0},{"$f":"'K80 - time schedule'!BT57","v":0},{"$f":"'K80 - time schedule'!BU57","v":0},{"$f":"'K80 - time schedule'!BV57","v":0},{"$f":"'K80 - time schedule'!BW57","v":0},{"$f":"'K80 - time schedule'!BX57","v":0},{"$f":"'K80 - time schedule'!BY57","v":0},{"$f":"'K80 - time schedule'!BZ57","v":0},{"$f":"'K80 - time schedule'!CA57","v":0},{"$f":"'K80 - time schedule'!CB57","v":0},{"$f":"'K80 - time schedule'!CC57","v":0},{"$f":"'K80 - time schedule'!CD57","v":0},{"$f":"'K80 - time schedule'!CE57","v":0},{"$f":"'K80 - time schedule'!CF57","v":0},{"$f":"'K80 - time schedule'!CG57","v":0},{"$f":"'K80 - time schedule'!CH57","v":0},{"$f":"'K80 - time schedule'!CI57","v":0},{"$f":"'K80 - time schedule'!CJ57","v":0},{"$f":"'K80 - time schedule'!CK57","v":0},{"$f":"'K80 - time schedule'!CL57","v":0},{"$f":"'K80 - time schedule'!CM57","v":0},{"$f":"'K80 - time schedule'!CN57","v":0},{"$f":"'K80 - time schedule'!CO57","v":0},{"$f":"'K80 - time schedule'!CP57","v":0},{"$f":"'K80 - time schedule'!CQ57","v":0},{"$f":"'K80 - time schedule'!CR57","v":0},{"$f":"'K80 - time schedule'!CS57","v":0},{"$f":"'K80 - time schedule'!CT57","v":0},{"$f":"'K80 - time schedule'!CU57","v":0},{"$f":"'K80 - time schedule'!CV57","v":0},{"$f":"'K80 - time schedule'!CW57","v":0},{"$f":"'K80 - time schedule'!CX57","v":0},{"$f":"'K80 - time schedule'!CY57","v":0},{"$f":"'K80 - time schedule'!CZ57","v":0},{"$f":"'K80 - time schedule'!DA57","v":0},{"$f":"'K80 - time schedule'!DB57","v":0},{"$f":"'K80 - time schedule'!DC57","v":0},{"$f":"'K80 - time schedule'!DD57","v":0},{"$f":"'K80 - time schedule'!DE57","v":0},{"$f":"'K80 - time schedule'!DF57","v":0},{"$f":"'K80 - time schedule'!DG57","v":0},{"$f":"'K80 - time schedule'!DH57","v":0},{"$f":"'K80 - time schedule'!DI57","v":0},{"$f":"'K80 - time schedule'!DJ57","v":0},{"$f":"'K80 - time schedule'!DK57","v":0},{"$f":"'K80 - time schedule'!DL57","v":0},{"$f":"'K80 - time schedule'!DM57","v":0},{"$f":"'K80 - time schedule'!DN57","v":0},{"$f":"'K80 - time schedule'!DO57","v":0},{"$f":"'K80 - time schedule'!DP57","v":0},{"$f":"'K80 - time schedule'!DQ57","v":0},{"$f":"'K80 - time schedule'!DR57","v":0},{"$f":"'K80 - time schedule'!DS57","v":0},{"$f":"'K80 - time schedule'!DT57","v":0},{"$f":"'K80 - time schedule'!DU57","v":0},{"$f":"'K80 - time schedule'!DV57","v":0},{"$f":"'K80 - time schedule'!DW57","v":0},{"$f":"'K80 - time schedule'!DX57","v":0},{"$f":"'K80 - time schedule'!DY57","v":0},{"$f":"'K80 - time schedule'!DZ57","v":0},{"$f":"'K80 - time schedule'!EA57","v":0},{"$f":"'K80 - time schedule'!EB57","v":0},{"$f":"'K80 - time schedule'!EC57","v":0},{"$f":"'K80 - time schedule'!ED57","v":0},{"$f":"'K80 - time schedule'!EE57","v":0},{"$f":"'K80 - time schedule'!EF57","v":0},{"$f":"'K80 - time schedule'!EG57","v":0},{"$f":"'K80 - time schedule'!EH57","v":0},{"$f":"'K80 - time schedule'!EI57","v":0},{"$f":"'K80 - time schedule'!EJ57","v":0},{"$f":"'K80 - time schedule'!EK57","v":0},{"$f":"'K80 - time schedule'!EL57","v":0},{"$f":"'K80 - time schedule'!EM57","v":0},{"$f":"'K80 - time schedule'!EN57","v":0},{"$f":"'K80 - time schedule'!EO57","v":0},{"$f":"'K80 - time schedule'!EP57","v":0},{"$f":"'K80 - time schedule'!EQ57","v":0},{"$f":"'K80 - time schedule'!ER57","v":0},{"$f":"'K80 - time schedule'!ES57","v":0},{"$f":"'K80 - time schedule'!ET57","v":0},{"$f":"'K80 - time schedule'!EU57","v":0},{"$f":"'K80 - time schedule'!EV57","v":0},{"$f":"'K80 - time schedule'!EW57","v":0},{"$f":"'K80 - time schedule'!EX57","v":0},{"$f":"'K80 - time schedule'!EY57","v":0},{"$f":"'K80 - time schedule'!EZ57","v":0},{"$f":"'K80 - time schedule'!FA57","v":0},{"$f":"'K80 - time schedule'!FB57","v":0},{"$f":"'K80 - time schedule'!FC57","v":0},{"$f":"'K80 - time schedule'!FD57","v":0},{"$f":"'K80 - time schedule'!FE57","v":0},{"$f":"'K80 - time schedule'!FF57","v":0},{"$f":"'K80 - time schedule'!FG57","v":0},{"$f":"'K80 - time schedule'!FH57","v":0},{"$f":"'K80 - time schedule'!FI57","v":0},{"$f":"'K80 - time schedule'!FJ57","v":0},{"$f":"'K80 - time schedule'!FK57","v":0},{"$f":"'K80 - time schedule'!FL57","v":0},{"$f":"'K80 - time schedule'!FM57","v":0},{"$f":"'K80 - time schedule'!FN57","v":0},{"$f":"'K80 - time schedule'!FO57","v":0},{"$f":"'K80 - time schedule'!FP57","v":0},{"$f":"'K80 - time schedule'!FQ57","v":0},{"$f":"'K80 - time schedule'!FR57","v":0},{"$f":"'K80 - time schedule'!FS57","v":0},{"$f":"'K80 - time schedule'!FT57","v":0},{"$f":"'K80 - time schedule'!FU57","v":0},{"$f":"'K80 - time schedule'!FV57","v":0},{"$f":"'K80 - time schedule'!FW57","v":0},{"$f":"'K80 - time schedule'!FX57","v":0},{"$f":"'K80 - time schedule'!FY57","v":0},{"$f":"'K80 - time schedule'!FZ57","v":0},{"$f":"'K80 - time schedule'!GA57","v":0},{"$f":"'K80 - time schedule'!GB57","v":0},{"$f":"'K80 - time schedule'!GC57","v":0},{"$f":"'K80 - time schedule'!GD57","v":0},{"$f":"'K80 - time schedule'!GE57","v":0},{"$f":"'K80 - time schedule'!GF57","v":0},{"$f":"'K80 - time schedule'!GG57","v":0},{"$f":"'K80 - time schedule'!GH57","v":0},{"$f":"'K80 - time schedule'!GI57","v":0},{"$f":"'K80 - time schedule'!GJ57","v":0},{"$f":"'K80 - time schedule'!GK57","v":0},{"$f":"'K80 - time schedule'!GL57","v":0},{"$f":"'K80 - time schedule'!GM57","v":0},{"$f":"'K80 - time schedule'!GN57","v":0},{"$f":"'K80 - time schedule'!GO57","v":0},{"$f":"'K80 - time schedule'!GP57","v":0},{"$f":"'K80 - time schedule'!GQ57","v":0},{"$f":"'K80 - time schedule'!GR57","v":0},{"$f":"'K80 - time schedule'!GS57","v":0},{"$f":"'K80 - time schedule'!GT57","v":0},{"$f":"'K80 - time schedule'!GU57","v":0},{"$f":"'K80 - time schedule'!GV57","v":0},{"$f":"'K80 - time schedule'!GW57","v":0},{"$f":"'K80 - time schedule'!GX57","v":0},{"$f":"'K80 - time schedule'!GY57","v":0},{"$f":"'K80 - time schedule'!GZ57","v":0},{"$f":"'K80 - time schedule'!HA57","v":0},{"$f":"'K80 - time schedule'!HB57","v":0},{"$f":"'K80 - time schedule'!HC57","v":0},{"$f":"'K80 - time schedule'!HD57","v":0},{"$f":"'K80 - time schedule'!HE57","v":0},{"$f":"'K80 - time schedule'!HF57","v":0},{"$f":"'K80 - time schedule'!HG57","v":0},{"$f":"'K80 - time schedule'!HH57","v":0},{"$f":"'K80 - time schedule'!HI57","v":0},{"$f":"'K80 - time schedule'!HJ57","v":0},{"$f":"'K80 - time schedule'!HK57","v":0},{"$f":"'K80 - time schedule'!HL57","v":0},{"$f":"'K80 - time schedule'!HM57","v":0},{"$f":"'K80 - time schedule'!HN57","v":0},{"$f":"'K80 - time schedule'!HO57","v":0},{"$f":"'K80 - time schedule'!HP57","v":0},{"$f":"'K80 - time schedule'!HQ57","v":0},{"$f":"'K80 - time schedule'!HR57","v":0},{"$f":"'K80 - time schedule'!HS57","v":0},{"$f":"'K80 - time schedule'!HT57","v":0},{"$f":"'K80 - time schedule'!HU57","v":0},{"$f":"'K80 - time schedule'!HV57","v":0},{"$f":"'K80 - time schedule'!HW57","v":0},{"$f":"'K80 - time schedule'!HX57","v":0},{"$f":"'K80 - time schedule'!HY57","v":0},{"$f":"'K80 - time schedule'!HZ57","v":0},{"$f":"'K80 - time schedule'!IA57","v":0},{"$f":"'K80 - time schedule'!IB57","v":0},{"$f":"'K80 - time schedule'!IC57","v":0},{"$f":"'K80 - time schedule'!ID57","v":0},{"$f":"'K80 - time schedule'!IE57","v":0},{"$f":"'K80 - time schedule'!IF57","v":0},{"$f":"'K80 - time schedule'!IG57","v":0},{"$f":"'K80 - time schedule'!IH57","v":0},{"$f":"'K80 - time schedule'!II57","v":0},{"$f":"'K80 - time schedule'!IJ57","v":0},{"$f":"'K80 - time schedule'!IK57","v":0},{"$f":"'K80 - time schedule'!IL57","v":0},{"$f":"'K80 - time schedule'!IM57","v":0},{"$f":"'K80 - time schedule'!IN57","v":0},{"$f":"'K80 - time schedule'!IO57","v":0},{"$f":"'K80 - time schedule'!IP57","v":0},{"$f":"'K80 - time schedule'!IQ57","v":0},{"$f":"'K80 - time schedule'!IR57","v":0},{"$f":"'K80 - time schedule'!IS57","v":0},{"$f":"'K80 - time schedule'!IT57","v":0},{"$f":"'K80 - time schedule'!IU57","v":0},{"$f":"'K80 - time schedule'!IV57","v":0},{"$f":"'K80 - time schedule'!IW57","v":0},{"$f":"'K80 - time schedule'!IX57","v":0},{"$f":"'K80 - time schedule'!IY57","v":0},{"$f":"'K80 - time schedule'!IZ57","v":0},{"$f":"'K80 - time schedule'!JA57","v":0},{"$f":"'K80 - time schedule'!JB57","v":0},{"$f":"'K80 - time schedule'!JC57","v":0},{"$f":"'K80 - time schedule'!JD57","v":0},{"$f":"'K80 - time schedule'!JE57","v":0},{"$f":"'K80 - time schedule'!JF57","v":0},{"$f":"'K80 - time schedule'!JG57","v":0},{"$f":"'K80 - time schedule'!JH57","v":0},{"$f":"'K80 - time schedule'!JI57","v":0},{"$f":"'K80 - time schedule'!JJ57","v":0},{"$f":"'K80 - time schedule'!JK57","v":0},{"$f":"'K80 - time schedule'!JL57","v":0},{"$f":"'K80 - time schedule'!JM57","v":0},{"$f":"'K80 - time schedule'!JN57","v":0},{"$f":"'K80 - time schedule'!JO57","v":0},{"$f":"'K80 - time schedule'!JP57","v":0},{"$f":"'K80 - time schedule'!JQ57","v":0},{"$f":"'K80 - time schedule'!JR57","v":0},{"$f":"'K80 - time schedule'!JS57","v":0},{"$f":"'K80 - time schedule'!JT57","v":0},{"$f":"'K80 - time schedule'!JU57","v":0},{"$f":"'K80 - time schedule'!JV57","v":0},{"$f":"'K80 - time schedule'!JW57","v":0},{"$f":"'K80 - time schedule'!JX57","v":0},{"$f":"'K80 - time schedule'!JY57","v":0},{"$f":"'K80 - time schedule'!JZ57","v":0},{"$f":"'K80 - time schedule'!KA57","v":0},{"$f":"'K80 - time schedule'!KB57","v":0},{"$f":"'K80 - time schedule'!KC57","v":0},{"$f":"'K80 - time schedule'!KD57","v":0},{"$f":"'K80 - time schedule'!KE57","v":0},{"$f":"'K80 - time schedule'!KF57","v":0},{"$f":"'K80 - time schedule'!KG57","v":0},{"$f":"'K80 - time schedule'!KH57","v":0},{"$f":"'K80 - time schedule'!KI57","v":0},{"$f":"'K80 - time schedule'!KJ57","v":0},{"$f":"'K80 - time schedule'!KK57","v":0},{"$f":"'K80 - time schedule'!KL57","v":0},{"$f":"'K80 - time schedule'!KM57","v":0},{"$f":"'K80 - time schedule'!KN57","v":0},{"$f":"'K80 - time schedule'!KO57","v":0},{"$f":"'K80 - time schedule'!KP57","v":0},{"$f":"'K80 - time schedule'!KQ57","v":0},{"$f":"'K80 - time schedule'!KR57","v":0},{"$f":"'K80 - time schedule'!KS57","v":0},{"$f":"'K80 - time schedule'!KT57","v":0}]
["Boiler room K80 - preliminary acceptance of the Work PAC","K80",{"$f":"'K80 - time schedule'!G59","v":0},{"$f":"'K80 - time schedule'!H59","v":0},{"$f":"'K80 - time schedule'!I59","v":0},{"$f":"'K80 - time schedule'!J59","v":0},{"$f":"'K80 - time schedule'!K59","v":0},{"$f":"'K80 - time schedule'!L59","v":0},{"$f":"'K80 - time schedule'!M59","v":0},{"$f":"'K80 - time schedule'!N59","v":0},{"$f":"'K80 - time schedule'!O59","v":0},{"$f":"'K80 - time schedule'!P59","v":0},{"$f":"'K80 - time schedule'!Q59","v":0},{"$f":"'K80 - time schedule'!R59","v":0},{"$f":"'K80 - time schedule'!S59","v":0},{"$f":"'K80 - time schedule'!T59","v":0},{"$f":"'K80 - time schedule'!U59","v":0},{"$f":"'K80 - time schedule'!V59","v":0},{"$f":"'K80 - time schedule'!W59","v":0},{"$f":"'K80 - time schedule'!X59","v":0},{"$f":"'K80 - time schedule'!Y59","v":0},{"$f":"'K80 - time schedule'!Z59","v":0},{"$f":"'K80 - time schedule'!AA59","v":0},{"$f":"'K80 - time schedule'!AB59","v":0},{"$f":"'K80 - time schedule'!AC59","v":0},{"$f":"'K80 - time schedule'!AD59","v":0},{"$f":"'K80 - time schedule'!AE59","v":0},{"$f":"'K80 - time schedule'!AF59","v":0},{"$f":"'K80 - time schedule'!AG59","v":0},{"$f":"'K80 - time schedule'!AH59","v":0},{"$f":"'K80 - time schedule'!AI59","v":0},{"$f":"'K80 - time schedule'!AJ59","v":0},{"$f":"'K80 - time schedule'!AK59","v":0},{"$f":"'K80 - time schedule'!AL59","v":0},{"$f":"'K80 - time schedule'!AM59","v":0},{"$f":"'K80 - time schedule'!AN59","v":0},{"$f":"'K80 - time schedule'!AO59","v":0},{"$f":"'K80 - time schedule'!AP59","v":0},{"$f":"'K80 - time schedule'!AQ59","v":0},{"$f":"'K80 - time schedule'!AR59","v":0},{"$f":"'K80 - time schedule'!AS59","v":0},{"$f":"'K80 - time schedule'!AT59","v":0},{"$f":"'K80 - time schedule'!AU59","v":0},{"$f":"'K80 - time schedule'!AV59","v":0},{"$f":"'K80 - time schedule'!AW59","v":0},{"$f":"'K80 - time schedule'!AX59","v":0},{"$f":"'K80 - time schedule'!AY59","v":0},{"$f":"'K80 - time schedule'!AZ59","v":0},{"$f":"'K80 - time schedule'!BA59","v":0},{"$f":"'K80 - time schedule'!BB59","v":0},{"$f":"'K80 - time schedule'!BC59","v":0},{"$f":"'K80 - time schedule'!BD59","v":0},{"$f":"'K80 - time schedule'!BE59","v":0},{"$f":"'K80 - time schedule'!BF59","v":0},{"$f":"'K80 - time schedule'!BG59","v":0},{"$f":"'K80 - time schedule'!BH59","v":0},{"$f":"'K80 - time schedule'!BI59","v":0},{"$f":"'K80 - time schedule'!BJ59","v":0},{"$f":"'K80 - time schedule'!BK59","v":0},{"$f":"'K80 - time schedule'!BL59","v":0},{"$f":"'K80 - time schedule'!BM59","v":0},{"$f":"'K80 - time schedule'!BN59","v":0},{"$f":"'K80 - time schedule'!BO59","v":0},{"$f":"'K80 - time schedule'!BP59","v":0},{"$f":"'K80 - time schedule'!BQ59","v":0},{"$f":"'K80 - time schedule'!BR59","v":0},{"$f":"'K80 - time schedule'!BS59","v":0},{"$f":"'K80 - time schedule'!BT59","v":0},{"$f":"'K80 - time schedule'!BU59","v":0},{"$f":"'K80 - time schedule'!BV59","v":0},{"$f":"'K80 - time schedule'!BW59","v":0},{"$f":"'K80 - time schedule'!BX59","v":0},{"$f":"'K80 - time schedule'!BY59","v":0},{"$f":"'K80 - time schedule'!BZ59","v":0},{"$f":"'K80 - time schedule'!CA59","v":0},{"$f":"'K80 - time schedule'!CB59","v":0},{"$f":"'K80 - time schedule'!CC59","v":0},{"$f":"'K80 - time schedule'!CD59","v":0},{"$f":"'K80 - time schedule'!CE59","v":0},{"$f":"'K80 - time schedule'!CF59","v":0},{"$f":"'K80 - time schedule'!CG59","v":0},{"$f":"'K80 - time schedule'!CH59","v":0},{"$f":"'K80 - time schedule'!CI59","v":0},{"$f":"'K80 - time schedule'!CJ59","v":0},{"$f":"'K80 - time schedule'!CK59","v":0},{"$f":"'K80 - time schedule'!CL59","v":0},{"$f":"'K80 - time schedule'!CM59","v":0},{"$f":"'K80 - time schedule'!CN59","v":0},{"$f":"'K80 - time schedule'!CO59","v":0},{"$f":"'K80 - time schedule'!CP59","v":0},{"$f":"'K80 - time schedule'!CQ59","v":0},{"$f":"'K80 - time schedule'!CR59","v":0},{"$f":"'K80 - time schedule'!CS59","v":0},{"$f":"'K80 - time schedule'!CT59","v":0},{"$f":"'K80 - time schedule'!CU59","v":0},{"$f":"'K80 - time schedule'!CV59","v":0},{"$f":"'K80 - time schedule'!CW59","v":0},{"$f":"'K80 - time schedule'!CX59","v":0},{"$f":"'K80 - time schedule'!CY59","v":0},{"$f":"'K80 - time schedule'!CZ59","v":0},{"$f":"'K80 - time schedule'!DA59","v":0},{"$f":"'K80 - time schedule'!DB59","v":0},{"$f":"'K80 - time schedule'!DC59","v":0},{"$f":"'K80 - time schedule'!DD59","v":0},{"$f":"'K80 - time schedule'!DE59","v":0},{"$f":"'K80 - time schedule'!DF59","v":0},{"$f":"'K80 - time schedule'!DG59","v":0},{"$f":"'K80 - time schedule'!DH59","v":0},{"$f":"'K80 - time schedule'!DI59","v":0},{"$f":"'K80 - time schedule'!DJ59","v":0},{"$f":"'K80 - time schedule'!DK59","v":0},{"$f":"'K80 - time schedule'!DL59","v":0},{"$f":"'K80 - time schedule'!DM59","v":0},{"$f":"'K80 - time schedule'!DN59","v":0},{"$f":"'K80 - time schedule'!DO59","v":0},{"$f":"'K80 - time schedule'!DP59","v":0},{"$f":"'K80 - time schedule'!DQ59","v":0},{"$f":"'K80 - time schedule'!DR59","v":0},{"$f":"'K80 - time schedule'!DS59","v":0},{"$f":"'K80 - time schedule'!DT59","v":0},{"$f":"'K80 - time schedule'!DU59","v":0},{"$f":"'K80 - time schedule'!DV59","v":0},{"$f":"'K80 - time schedule'!DW59","v":0},{"$f":"'K80 - time schedule'!DX59","v":0},{"$f":"'K80 - time schedule'!DY59","v":0},{"$f":"'K80 - time schedule'!DZ59","v":0},{"$f":"'K80 - time schedule'!EA59","v":0},{"$f":"'K80 - time schedule'!EB59","v":0},{"$f":"'K80 - time schedule'!EC59","v":0},{"$f":"'K80 - time schedule'!ED59","v":0},{"$f":"'K80 - time schedule'!EE59","v":0},{"$f":"'K80 - time schedule'!EF59","v":0},{"$f":"'K80 - time schedule'!EG59","v":0},{"$f":"'K80 - time schedule'!EH59","v":0},{"$f":"'K80 - time schedule'!EI59","v":0},{"$f":"'K80 - time schedule'!EJ59","v":0},{"$f":"'K80 - time schedule'!EK59","v":0},{"$f":"'K80 - time schedule'!EL59","v":0},{"$f":"'K80 - time schedule'!EM59","v":0},{"$f":"'K80 - time schedule'!EN59","v":0},{"$f":"'K80 - time schedule'!EO59","v":0},{"$f":"'K80 - time schedule'!EP59","v":0},{"$f":"'K80 - time schedule'!EQ59","v":0},{"$f":"'K80 - time schedule'!ER59","v":0},{"$f":"'K80 - time schedule'!ES59","v":0},{"$f":"'K80 - time schedule'!ET59","v":0},{"$f":"'K80 - time schedule'!EU59","v":0},{"$f":"'K80 - time schedule'!EV59","v":0},{"$f":"'K80 - time schedule'!EW59","v":0},{"$f":"'K80 - time schedule'!EX59","v":0},{"$f":"'K80 - time schedule'!EY59","v":0},{"$f":"'K80 - time schedule'!EZ59","v":0},{"$f":"'K80 - time schedule'!FA59","v":0},{"$f":"'K80 - time schedule'!FB59","v":0},{"$f":"'K80 - time schedule'!FC59","v":0},{"$f":"'K80 - time schedule'!FD59","v":0},{"$f":"'K80 - time schedule'!FE59","v":0},{"$f":"'K80 - time schedule'!FF59","v":0},{"$f":"'K80 - time schedule'!FG59","v":0},{"$f":"'K80 - time schedule'!FH59","v":0},{"$f":"'K80 - time schedule'!FI59","v":0},{"$f":"'K80 - time schedule'!FJ59","v":0},{"$f":"'K80 - time schedule'!FK59","v":0},{"$f":"'K80 - time schedule'!FL59","v":0},{"$f":"'K80 - time schedule'!FM59","v":0},{"$f":"'K80 - time schedule'!FN59","v":0},{"$f":"'K80 - time schedule'!FO59","v":0},{"$f":"'K80 - time schedule'!FP59","v":0},{"$f":"'K80 - time schedule'!FQ59","v":0},{"$f":"'K80 - time schedule'!FR59","v":0},{"$f":"'K80 - time schedule'!FS59","v":0},{"$f":"'K80 - time schedule'!FT59","v":0},{"$f":"'K80 - time schedule'!FU59","v":0},{"$f":"'K80 - time schedule'!FV59","v":0},{"$f":"'K80 - time schedule'!FW59","v":0},{"$f":"'K80 - time schedule'!FX59","v":0},{"$f":"'K80 - time schedule'!FY59","v":0},{"$f":"'K80 - time schedule'!FZ59","v":0},{"$f":"'K80 - time schedule'!GA59","v":0},{"$f":"'K80 - time schedule'!GB59","v":0},{"$f":"'K80 - time schedule'!GC59","v":0},{"$f":"'K80 - time schedule'!GD59","v":0},{"$f":"'K80 - time schedule'!GE59","v":0},{"$f":"'K80 - time schedule'!GF59","v":0},{"$f":"'K80 - time schedule'!GG59","v":0},{"$f":"'K80 - time schedule'!GH59","v":0},{"$f":"'K80 - time schedule'!GI59","v":0},{"$f":"'K80 - time schedule'!GJ59","v":0},{"$f":"'K80 - time schedule'!GK59","v":0},{"$f":"'K80 - time schedule'!GL59","v":0},{"$f":"'K80 - time schedule'!GM59","v":0},{"$f":"'K80 - time schedule'!GN59","v":0},{"$f":"'K80 - time schedule'!GO59","v":0},{"$f":"'K80 - time schedule'!GP59","v":0},{"$f":"'K80 - time schedule'!GQ59","v":0},{"$f":"'K80 - time schedule'!GR59","v":0},{"$f":"'K80 - time schedule'!GS59","v":0},{"$f":"'K80 - time schedule'!GT59","v":0},{"$f":"'K80 - time schedule'!GU59","v":0},{"$f":"'K80 - time schedule'!GV59","v":0},{"$f":"'K80 - time schedule'!GW59","v":0},{"$f":"'K80 - time schedule'!GX59","v":0},{"$f":"'K80 - time schedule'!GY59","v":0},{"$f":"'K80 - time schedule'!GZ59","v":0},{"$f":"'K80 - time schedule'!HA59","v":0},{"$f":"'K80 - time schedule'!HB59","v":0},{"$f":"'K80 - time schedule'!HC59","v":0},{"$f":"'K80 - time schedule'!HD59","v":0},{"$f":"'K80 - time schedule'!HE59","v":0},{"$f":"'K80 - time schedule'!HF59","v":0},{"$f":"'K80 - time schedule'!HG59","v":0},{"$f":"'K80 - time schedule'!HH59","v":0},{"$f":"'K80 - time schedule'!HI59","v":0},{"$f":"'K80 - time schedule'!HJ59","v":0},{"$f":"'K80 - time schedule'!HK59","v":0},{"$f":"'K80 - time schedule'!HL59","v":0},{"$f":"'K80 - time schedule'!HM59","v":0},{"$f":"'K80 - time schedule'!HN59","v":0},{"$f":"'K80 - time schedule'!HO59","v":0},{"$f":"'K80 - time schedule'!HP59","v":0},{"$f":"'K80 - time schedule'!HQ59","v":0},{"$f":"'K80 - time schedule'!HR59","v":0},{"$f":"'K80 - time schedule'!HS59","v":0},{"$f":"'K80 - time schedule'!HT59","v":0},{"$f":"'K80 - time schedule'!HU59","v":0},{"$f":"'K80 - time schedule'!HV59","v":0},{"$f":"'K80 - time schedule'!HW59","v":0},{"$f":"'K80 - time schedule'!HX59","v":0},{"$f":"'K80 - time schedule'!HY59","v":0},{"$f":"'K80 - time schedule'!HZ59","v":0},{"$f":"'K80 - time schedule'!IA59","v":0},{"$f":"'K80 - time schedule'!IB59","v":0},{"$f":"'K80 - time schedule'!IC59","v":0},{"$f":"'K80 - time schedule'!ID59","v":0},{"$f":"'K80 - time schedule'!IE59","v":0},{"$f":"'K80 - time schedule'!IF59","v":0},{"$f":"'K80 - time schedule'!IG59","v":0},{"$f":"'K80 - time schedule'!IH59","v":0},{"$f":"'K80 - time schedule'!II59","v":0},{"$f":"'K80 - time schedule'!IJ59","v":0},{"$f":"'K80 - time schedule'!IK59","v":0},{"$f":"'K80 - time schedule'!IL59","v":0},{"$f":"'K80 - time schedule'!IM59","v":0},{"$f":"'K80 - time schedule'!IN59","v":0},{"$f":"'K80 - time schedule'!IO59","v":0},{"$f":"'K80 - time schedule'!IP59","v":0},{"$f":"'K80 - time schedule'!IQ59","v":0},{"$f":"'K80 - time schedule'!IR59","v":0},{"$f":"'K80 - time schedule'!IS59","v":0},{"$f":"'K80 - time schedule'!IT59","v":0},{"$f":"'K80 - time schedule'!IU59","v":0},{"$f":"'K80 - time schedule'!IV59","v":0},{"$f":"'K80 - time schedule'!IW59","v":0},{"$f":"'K80 - time schedule'!IX59","v":0},{"$f":"'K80 - time schedule'!IY59","v":0},{"$f":"'K80 - time schedule'!IZ59","v":0},{"$f":"'K80 - time schedule'!JA59","v":0},{"$f":"'K80 - time schedule'!JB59","v":0},{"$f":"'K80 - time schedule'!JC59","v":0},{"$f":"'K80 - time schedule'!JD59","v":0},{"$f":"'K80 - time schedule'!JE59","v":0},{"$f":"'K80 - time schedule'!JF59","v":0},{"$f":"'K80 - time schedule'!JG59","v":0},{"$f":"'K80 - time schedule'!JH59","v":0},{"$f":"'K80 - time schedule'!JI59","v":0},{"$f":"'K80 - time schedule'!JJ59","v":0},{"$f":"'K80 - time schedule'!JK59","v":0},{"$f":"'K80 - time schedule'!JL59","v":0},{"$f":"'K80 - time schedule'!JM59","v":0},{"$f":"'K80 - time schedule'!JN59","v":0},{"$f":"'K80 - time schedule'!JO59","v":0},{"$f":"'K80 - time schedule'!JP59","v":0},{"$f":"'K80 - time schedule'!JQ59","v":0},{"$f":"'K80 - time schedule'!JR59","v":0},{"$f":"'K80 - time schedule'!JS59","v":0},{"$f":"'K80 - time schedule'!JT59","v":0},{"$f":"'K80 - time schedule'!JU59","v":0},{"$f":"'K80 - time schedule'!JV59","v":0},{"$f":"'K80 - time schedule'!JW59","v":0},{"$f":"'K80 - time schedule'!JX59","v":0},{"$f":"'K80 - time schedule'!JY59","v":0},{"$f":"'K80 - time schedule'!JZ59","v":0},{"$f":"'K80 - time schedule'!KA59","v":0},{"$f":"'K80 - time schedule'!KB59","v":0},{"$f":"'K80 - time schedule'!KC59","v":0},{"$f":"'K80 - time schedule'!KD59","v":0},{"$f":"'K80 - time schedule'!KE59","v":0},{"$f":"'K80 - time schedule'!KF59","v":0},{"$f":"'K80 - time schedule'!KG59","v":0},{"$f":"'K80 - time schedule'!KH59","v":0},{"$f":"'K80 - time schedule'!KI59","v":0},{"$f":"'K80 - time schedule'!KJ59","v":0},{"$f":"'K80 - time schedule'!KK59","v":0},{"$f":"'K80 - time schedule'!KL59","v":0},{"$f":"'K80 - time schedule'!KM59","v":0},{"$f":"'K80 - time schedule'!KN59","v":0},{"$f":"'K80 - time schedule'!KO59","v":0},{"$f":"'K80 - time schedule'!KP59","v":0},{"$f":"'K80 - time schedule'!KQ59","v":0},{"$f":"'K80 - time schedule'!KR59","v":0},{"$f":"'K80 - time schedule'!KS59","v":0},{"$f":"'K80 - time schedule'!KT59","v":0}]
["Boiler room K80 - guarantee test B","K80",{"$f":"'K80 - time schedule'!G61","v":0},{"$f":"'K80 - time schedule'!H61","v":0},{"$f":"'K80 - time schedule'!I61","v":0},{"$f":"'K80 - time schedule'!J61","v":0},{"$f":"'K80 - time schedule'!K61","v":0},{"$f":"'K80 - time schedule'!L61","v":0},{"$f":"'K80 - time schedule'!M61","v":0},{"$f":"'K80 - time schedule'!N61","v":0},{"$f":"'K80 - time schedule'!O61","v":0},{"$f":"'K80 - time schedule'!P61","v":0},{"$f":"'K80 - time schedule'!Q61","v":0},{"$f":"'K80 - time schedule'!R61","v":0},{"$f":"'K80 - time schedule'!S61","v":0},{"$f":"'K80 - time schedule'!T61","v":0},{"$f":"'K80 - time schedule'!U61","v":0},{"$f":"'K80 - time schedule'!V61","v":0},{"$f":"'K80 - time schedule'!W61","v":0},{"$f":"'K80 - time schedule'!X61","v":0},{"$f":"'K80 - time schedule'!Y61","v":0},{"$f":"'K80 - time schedule'!Z61","v":0},{"$f":"'K80 - time schedule'!AA61","v":0},{"$f":"'K80 - time schedule'!AB61","v":0},{"$f":"'K80 - time schedule'!AC61","v":0},{"$f":"'K80 - time schedule'!AD61","v":0},{"$f":"'K80 - time schedule'!AE61","v":0},{"$f":"'K80 - time schedule'!AF61","v":0},{"$f":"'K80 - time schedule'!AG61","v":0},{"$f":"'K80 - time schedule'!AH61","v":0},{"$f":"'K80 - time schedule'!AI61","v":0},{"$f":"'K80 - time schedule'!AJ61","v":0},{"$f":"'K80 - time schedule'!AK61","v":0},{"$f":"'K80 - time schedule'!AL61","v":0},{"$f":"'K80 - time schedule'!AM61","v":0},{"$f":"'K80 - time schedule'!AN61","v":0},{"$f":"'K80 - time schedule'!AO61","v":0},{"$f":"'K80 - time schedule'!AP61","v":0},{"$f":"'K80 - time schedule'!AQ61","v":0},{"$f":"'K80 - time schedule'!AR61","v":0},{"$f":"'K80 - time schedule'!AS61","v":0},{"$f":"'K80 - time schedule'!AT61","v":0},{"$f":"'K80 - time schedule'!AU61","v":0},{"$f":"'K80 - time schedule'!AV61","v":0},{"$f":"'K80 - time schedule'!AW61","v":0},{"$f":"'K80 - time schedule'!AX61","v":0},{"$f":"'K80 - time schedule'!AY61","v":0},{"$f":"'K80 - time schedule'!AZ61","v":0},{"$f":"'K80 - time schedule'!BA61","v":0},{"$f":"'K80 - time schedule'!BB61","v":0},{"$f":"'K80 - time schedule'!BC61","v":0},{"$f":"'K80 - time schedule'!BD61","v":0},{"$f":"'K80 - time schedule'!BE61","v":0},{"$f":"'K80 - time schedule'!BF61","v":0},{"$f":"'K80 - time schedule'!BG61","v":0},{"$f":"'K80 - time schedule'!BH61","v":0},{"$f":"'K80 - time schedule'!BI61","v":0},{"$f":"'K80 - time schedule'!BJ61","v":0},{"$f":"'K80 - time schedule'!BK61","v":0},{"$f":"'K80 - time schedule'!BL61","v":0},{"$f":"'K80 - time schedule'!BM61","v":0},{"$f":"'K80 - time schedule'!BN61","v":0},{"$f":"'K80 - time schedule'!BO61","v":0},{"$f":"'K80 - time schedule'!BP61","v":0},{"$f":"'K80 - time schedule'!BQ61","v":0},{"$f":"'K80 - time schedule'!BR61","v":0},{"$f":"'K80 - time schedule'!BS61","v":0},{"$f":"'K80 - time schedule'!BT61","v":0},{"$f":"'K80 - time schedule'!BU61","v":0},{"$f":"'K80 - time schedule'!BV61","v":0},{"$f":"'K80 - time schedule'!BW61","v":0},{"$f":"'K80 - time schedule'!BX61","v":0},{"$f":"'K80 - time schedule'!BY61","v":0},{"$f":"'K80 - time schedule'!BZ61","v":0},{"$f":"'K80 - time schedule'!CA61","v":0},{"$f":"'K80 - time schedule'!CB61","v":0},{"$f":"'K80 - time schedule'!CC61","v":0},{"$f":"'K80 - time schedule'!CD61","v":0},{"$f":"'K80 - time schedule'!CE61","v":0},{"$f":"'K80 - time schedule'!CF61","v":0},{"$f":"'K80 - time schedule'!CG61","v":0},{"$f":"'K80 - time schedule'!CH61","v":0},{"$f":"'K80 - time schedule'!CI61","v":0},{"$f":"'K80 - time schedule'!CJ61","v":0},{"$f":"'K80 - time schedule'!CK61","v":0},{"$f":"'K80 - time schedule'!CL61","v":0},{"$f":"'K80 - time schedule'!CM61","v":0},{"$f":"'K80 - time schedule'!CN61","v":0},{"$f":"'K80 - time schedule'!CO61","v":0},{"$f":"'K80 - time schedule'!CP61","v":0},{"$f":"'K80 - time schedule'!CQ61","v":0},{"$f":"'K80 - time schedule'!CR61","v":0},{"$f":"'K80 - time schedule'!CS61","v":0},{"$f":"'K80 - time schedule'!CT61","v":0},{"$f":"'K80 - time schedule'!CU61","v":0},{"$f":"'K80 - time schedule'!CV61","v":0},{"$f":"'K80 - time schedule'!CW61","v":0},{"$f":"'K80 - time schedule'!CX61","v":0},{"$f":"'K80 - time schedule'!CY61","v":0},{"$f":"'K80 - time schedule'!CZ61","v":0},{"$f":"'K80 - time schedule'!DA61","v":0},{"$f":"'K80 - time schedule'!DB61","v":0},{"$f":"'K80 - time schedule'!DC61","v":0},{"$f":"'K80 - time schedule'!DD61","v":0},{"$f":"'K80 - time schedule'!DE61","v":0},{"$f":"'K80 - time schedule'!DF61","v":0},{"$f":"'K80 - time schedule'!DG61","v":0},{"$f":"'K80 - time schedule'!DH61","v":0},{"$f":"'K80 - time schedule'!DI61","v":0},{"$f":"'K80 - time schedule'!DJ61","v":0},{"$f":"'K80 - time schedule'!DK61","v":0},{"$f":"'K80 - time schedule'!DL61","v":0},{"$f":"'K80 - time schedule'!DM61","v":0},{"$f":"'K80 - time schedule'!DN61","v":0},{"$f":"'K80 - time schedule'!DO61","v":0},{"$f":"'K80 - time schedule'!DP61","v":0},{"$f":"'K80 - time schedule'!DQ61","v":0},{"$f":"'K80 - time schedule'!DR61","v":0},{"$f":"'K80 - time schedule'!DS61","v":0},{"$f":"'K80 - time schedule'!DT61","v":0},{"$f":"'K80 - time schedule'!DU61","v":0},{"$f":"'K80 - time schedule'!DV61","v":0},{"$f":"'K80 - time schedule'!DW61","v":0},{"$f":"'K80 - time schedule'!DX61","v":0},{"$f":"'K80 - time schedule'!DY61","v":0},{"$f":"'K80 - time schedule'!DZ61","v":0},{"$f":"'K80 - time schedule'!EA61","v":0},{"$f":"'K80 - time schedule'!EB61","v":0},{"$f":"'K80 - time schedule'!EC61","v":0},{"$f":"'K80 - time schedule'!ED61","v":0},{"$f":"'K80 - time schedule'!EE61","v":0},{"$f":"'K80 - time schedule'!EF61","v":0},{"$f":"'K80 - time schedule'!EG61","v":0},{"$f":"'K80 - time schedule'!EH61","v":0},{"$f":"'K80 - time schedule'!EI61","v":0},{"$f":"'K80 - time schedule'!EJ61","v":0},{"$f":"'K80 - time schedule'!EK61","v":0},{"$f":"'K80 - time schedule'!EL61","v":0},{"$f":"'K80 - time schedule'!EM61","v":0},{"$f":"'K80 - time schedule'!EN61","v":0},{"$f":"'K80 - time schedule'!EO61","v":0},{"$f":"'K80 - time schedule'!EP61","v":0},{"$f":"'K80 - time schedule'!EQ61","v":0},{"$f":"'K80 - time schedule'!ER61","v":0},{"$f":"'K80 - time schedule'!ES61","v":0},{"$f":"'K80 - time schedule'!ET61","v":0},{"$f":"'K80 - time schedule'!EU61","v":0},{"$f":"'K80 - time schedule'!EV61","v":0},{"$f":"'K80 - time schedule'!EW61","v":0},{"$f":"'K80 - time schedule'!EX61","v":0},{"$f":"'K80 - time schedule'!EY61","v":0},{"$f":"'K80 - time schedule'!EZ61","v":0},{"$f":"'K80 - time schedule'!FA61","v":0},{"$f":"'K80 - time schedule'!FB61","v":0},{"$f":"'K80 - time schedule'!FC61","v":0},{"$f":"'K80 - time schedule'!FD61","v":0},{"$f":"'K80 - time schedule'!FE61","v":0},{"$f":"'K80 - time schedule'!FF61","v":0},{"$f":"'K80 - time schedule'!FG61","v":0},{"$f":"'K80 - time schedule'!FH61","v":0},{"$f":"'K80 - time schedule'!FI61","v":0},{"$f":"'K80 - time schedule'!FJ61","v":0},{"$f":"'K80 - time schedule'!FK61","v":0},{"$f":"'K80 - time schedule'!FL61","v":0},{"$f":"'K80 - time schedule'!FM61","v":0},{"$f":"'K80 - time schedule'!FN61","v":0},{"$f":"'K80 - time schedule'!FO61","v":0},{"$f":"'K80 - time schedule'!FP61","v":0},{"$f":"'K80 - time schedule'!FQ61","v":0},{"$f":"'K80 - time schedule'!FR61","v":0},{"$f":"'K80 - time schedule'!FS61","v":0},{"$f":"'K80 - time schedule'!FT61","v":0},{"$f":"'K80 - time schedule'!FU61","v":0},{"$f":"'K80 - time schedule'!FV61","v":0},{"$f":"'K80 - time schedule'!FW61","v":0},{"$f":"'K80 - time schedule'!FX61","v":0},{"$f":"'K80 - time schedule'!FY61","v":0},{"$f":"'K80 - time schedule'!FZ61","v":0},{"$f":"'K80 - time schedule'!GA61","v":0},{"$f":"'K80 - time schedule'!GB61","v":0},{"$f":"'K80 - time schedule'!GC61","v":0},{"$f":"'K80 - time schedule'!GD61","v":0},{"$f":"'K80 - time schedule'!GE61","v":0},{"$f":"'K80 - time schedule'!GF61","v":0},{"$f":"'K80 - time schedule'!GG61","v":0},{"$f":"'K80 - time schedule'!GH61","v":0},{"$f":"'K80 - time schedule'!GI61","v":0},{"$f":"'K80 - time schedule'!GJ61","v":0},{"$f":"'K80 - time schedule'!GK61","v":0},{"$f":"'K80 - time schedule'!GL61","v":0},{"$f":"'K80 - time schedule'!GM61","v":0},{"$f":"'K80 - time schedule'!GN61","v":0},{"$f":"'K80 - time schedule'!GO61","v":0},{"$f":"'K80 - time schedule'!GP61","v":0},{"$f":"'K80 - time schedule'!GQ61","v":0},{"$f":"'K80 - time schedule'!GR61","v":0},{"$f":"'K80 - time schedule'!GS61","v":0},{"$f":"'K80 - time schedule'!GT61","v":0},{"$f":"'K80 - time schedule'!GU61","v":0},{"$f":"'K80 - time schedule'!GV61","v":0},{"$f":"'K80 - time schedule'!GW61","v":0},{"$f":"'K80 - time schedule'!GX61","v":0},{"$f":"'K80 - time schedule'!GY61","v":0},{"$f":"'K80 - time schedule'!GZ61","v":0},{"$f":"'K80 - time schedule'!HA61","v":0},{"$f":"'K80 - time schedule'!HB61","v":0},{"$f":"'K80 - time schedule'!HC61","v":0},{"$f":"'K80 - time schedule'!HD61","v":0},{"$f":"'K80 - time schedule'!HE61","v":0},{"$f":"'K80 - time schedule'!HF61","v":0},{"$f":"'K80 - time schedule'!HG61","v":0},{"$f":"'K80 - time schedule'!HH61","v":0},{"$f":"'K80 - time schedule'!HI61","v":0},{"$f":"'K80 - time schedule'!HJ61","v":0},{"$f":"'K80 - time schedule'!HK61","v":0},{"$f":"'K80 - time schedule'!HL61","v":0},{"$f":"'K80 - time schedule'!HM61","v":0},{"$f":"'K80 - time schedule'!HN61","v":0},{"$f":"'K80 - time schedule'!HO61","v":0},{"$f":"'K80 - time schedule'!HP61","v":0},{"$f":"'K80 - time schedule'!HQ61","v":0},{"$f":"'K80 - time schedule'!HR61","v":0},{"$f":"'K80 - time schedule'!HS61","v":0},{"$f":"'K80 - time schedule'!HT61","v":0},{"$f":"'K80 - time schedule'!HU61","v":0},{"$f":"'K80 - time schedule'!HV61","v":0},{"$f":"'K80 - time schedule'!HW61","v":0},{"$f":"'K80 - time schedule'!HX61","v":0},{"$f":"'K80 - time schedule'!HY61","v":0},{"$f":"'K80 - time schedule'!HZ61","v":0},{"$f":"'K80 - time schedule'!IA61","v":0},{"$f":"'K80 - time schedule'!IB61","v":0},{"$f":"'K80 - time schedule'!IC61","v":0},{"$f":"'K80 - time schedule'!ID61","v":0},{"$f":"'K80 - time schedule'!IE61","v":0},{"$f":"'K80 - time schedule'!IF61","v":0},{"$f":"'K80 - time schedule'!IG61","v":0},{"$f":"'K80 - time schedule'!IH61","v":0},{"$f":"'K80 - time schedule'!II61","v":0},{"$f":"'K80 - time schedule'!IJ61","v":0},{"$f":"'K80 - time schedule'!IK61","v":0},{"$f":"'K80 - time schedule'!IL61","v":0},{"$f":"'K80 - time schedule'!IM61","v":0},{"$f":"'K80 - time schedule'!IN61","v":0},{"$f":"'K80 - time schedule'!IO61","v":0},{"$f":"'K80 - time schedule'!IP61","v":0},{"$f":"'K80 - time schedule'!IQ61","v":0},{"$f":"'K80 - time schedule'!IR61","v":0},{"$f":"'K80 - time schedule'!IS61","v":0},{"$f":"'K80 - time schedule'!IT61","v":0},{"$f":"'K80 - time schedule'!IU61","v":0},{"$f":"'K80 - time schedule'!IV61","v":0},{"$f":"'K80 - time schedule'!IW61","v":0},{"$f":"'K80 - time schedule'!IX61","v":0},{"$f":"'K80 - time schedule'!IY61","v":0},{"$f":"'K80 - time schedule'!IZ61","v":0},{"$f":"'K80 - time schedule'!JA61","v":0},{"$f":"'K80 - time schedule'!JB61","v":0},{"$f":"'K80 - time schedule'!JC61","v":0},{"$f":"'K80 - time schedule'!JD61","v":0},{"$f":"'K80 - time schedule'!JE61","v":0},{"$f":"'K80 - time schedule'!JF61","v":0},{"$f":"'K80 - time schedule'!JG61","v":0},{"$f":"'K80 - time schedule'!JH61","v":0},{"$f":"'K80 - time schedule'!JI61","v":0},{"$f":"'K80 - time schedule'!JJ61","v":0},{"$f":"'K80 - time schedule'!JK61","v":0},{"$f":"'K80 - time schedule'!JL61","v":0},{"$f":"'K80 - time schedule'!JM61","v":0},{"$f":"'K80 - time schedule'!JN61","v":0},{"$f":"'K80 - time schedule'!JO61","v":0},{"$f":"'K80 - time schedule'!JP61","v":0},{"$f":"'K80 - time schedule'!JQ61","v":0},{"$f":"'K80 - time schedule'!JR61","v":0},{"$f":"'K80 - time schedule'!JS61","v":0},{"$f":"'K80 - time schedule'!JT61","v":0},{"$f":"'K80 - time schedule'!JU61","v":0},{"$f":"'K80 - time schedule'!JV61","v":0},{"$f":"'K80 - time schedule'!JW61","v":0},{"$f":"'K80 - time schedule'!JX61","v":0},{"$f":"'K80 - time schedule'!JY61","v":0},{"$f":"'K80 - time schedule'!JZ61","v":0},{"$f":"'K80 - time schedule'!KA61","v":0},{"$f":"'K80 - time schedule'!KB61","v":0},{"$f":"'K80 - time schedule'!KC61","v":0},{"$f":"'K80 - time schedule'!KD61","v":0},{"$f":"'K80 - time schedule'!KE61","v":0},{"$f":"'K80 - time schedule'!KF61","v":0},{"$f":"'K80 - time schedule'!KG61","v":0},{"$f":"'K80 - time schedule'!KH61","v":0},{"$f":"'K80 - time schedule'!KI61","v":0},{"$f":"'K80 - time schedule'!KJ61","v":0},{"$f":"'K80 - time schedule'!KK61","v":0},{"$f":"'K80 - time schedule'!KL61","v":0},{"$f":"'K80 - time schedule'!KM61","v":0},{"$f":"'K80 - time schedule'!KN61","v":0},{"$f":"'K80 - time schedule'!KO61","v":0},{"$f":"'K80 - time schedule'!KP61","v":0},{"$f":"'K80 - time schedule'!KQ61","v":0},{"$f":"'K80 - time schedule'!KR61","v":0},{"$f":"'K80 - time schedule'!KS61","v":0},{"$f":"'K80 - time schedule'!KT61","v":0}]
["Boiler room K80 - final acceptance of the Work FAC","K80",{"$f":"'K80 - time schedule'!G63","v":0},{"$f":"'K80 - time schedule'!H63","v":0},{"$f":"'K80 - time schedule'!I63","v":0},{"$f":"'K80 - time schedule'!J63","v":0},{"$f":"'K80 - time schedule'!K63","v":0},{"$f":"'K80 - time schedule'!L63","v":0},{"$f":"'K80 - time schedule'!M63","v":0},{"$f":"'K80 - time schedule'!N63","v":0},{"$f":"'K80 - time schedule'!O63","v":0},{"$f":"'K80 - time schedule'!P63","v":0},{"$f":"'K80 - time schedule'!Q63","v":0},{"$f":"'K80 - time schedule'!R63","v":0},{"$f":"'K80 - time schedule'!S63","v":0},{"$f":"'K80 - time schedule'!T63","v":0},{"$f":"'K80 - time schedule'!U63","v":0},{"$f":"'K80 - time schedule'!V63","v":0},{"$f":"'K80 - time schedule'!W63","v":0},{"$f":"'K80 - time schedule'!X63","v":0},{"$f":"'K80 - time schedule'!Y63","v":0},{"$f":"'K80 - time schedule'!Z63","v":0},{"$f":"'K80 - time schedule'!AA63","v":0},{"$f":"'K80 - time schedule'!AB63","v":0},{"$f":"'K80 - time schedule'!AC63","v":0},{"$f":"'K80 - time schedule'!AD63","v":0},{"$f":"'K80 - time schedule'!AE63","v":0},{"$f":"'K80 - time schedule'!AF63","v":0},{"$f":"'K80 - time schedule'!AG63","v":0},{"$f":"'K80 - time schedule'!AH63","v":0},{"$f":"'K80 - time schedule'!AI63","v":0},{"$f":"'K80 - time schedule'!AJ63","v":0},{"$f":"'K80 - time schedule'!AK63","v":0},{"$f":"'K80 - time schedule'!AL63","v":0},{"$f":"'K80 - time schedule'!AM63","v":0},{"$f":"'K80 - time schedule'!AN63","v":0},{"$f":"'K80 - time schedule'!AO63","v":0},{"$f":"'K80 - time schedule'!AP63","v":0},{"$f":"'K80 - time schedule'!AQ63","v":0},{"$f":"'K80 - time schedule'!AR63","v":0},{"$f":"'K80 - time schedule'!AS63","v":0},{"$f":"'K80 - time schedule'!AT63","v":0},{"$f":"'K80 - time schedule'!AU63","v":0},{"$f":"'K80 - time schedule'!AV63","v":0},{"$f":"'K80 - time schedule'!AW63","v":0},{"$f":"'K80 - time schedule'!AX63","v":0},{"$f":"'K80 - time schedule'!AY63","v":0},{"$f":"'K80 - time schedule'!AZ63","v":0},{"$f":"'K80 - time schedule'!BA63","v":0},{"$f":"'K80 - time schedule'!BB63","v":0},{"$f":"'K80 - time schedule'!BC63","v":0},{"$f":"'K80 - time schedule'!BD63","v":0},{"$f":"'K80 - time schedule'!BE63","v":0},{"$f":"'K80 - time schedule'!BF63","v":0},{"$f":"'K80 - time schedule'!BG63","v":0},{"$f":"'K80 - time schedule'!BH63","v":0},{"$f":"'K80 - time schedule'!BI63","v":0},{"$f":"'K80 - time schedule'!BJ63","v":0},{"$f":"'K80 - time schedule'!BK63","v":0},{"$f":"'K80 - time schedule'!BL63","v":0},{"$f":"'K80 - time schedule'!BM63","v":0},{"$f":"'K80 - time schedule'!BN63","v":0},{"$f":"'K80 - time schedule'!BO63","v":0},{"$f":"'K80 - time schedule'!BP63","v":0},{"$f":"'K80 - time schedule'!BQ63","v":0},{"$f":"'K80 - time schedule'!BR63","v":0},{"$f":"'K80 - time schedule'!BS63","v":0},{"$f":"'K80 - time schedule'!BT63","v":0},{"$f":"'K80 - time schedule'!BU63","v":0},{"$f":"'K80 - time schedule'!BV63","v":0},{"$f":"'K80 - time schedule'!BW63","v":0},{"$f":"'K80 - time schedule'!BX63","v":0},{"$f":"'K80 - time schedule'!BY63","v":0},{"$f":"'K80 - time schedule'!BZ63","v":0},{"$f":"'K80 - time schedule'!CA63","v":0},{"$f":"'K80 - time schedule'!CB63","v":0},{"$f":"'K80 - time schedule'!CC63","v":0},{"$f":"'K80 - time schedule'!CD63","v":0},{"$f":"'K80 - time schedule'!CE63","v":0},{"$f":"'K80 - time schedule'!CF63","v":0},{"$f":"'K80 - time schedule'!CG63","v":0},{"$f":"'K80 - time schedule'!CH63","v":0},{"$f":"'K80 - time schedule'!CI63","v":0},{"$f":"'K80 - time schedule'!CJ63","v":0},{"$f":"'K80 - time schedule'!CK63","v":0},{"$f":"'K80 - time schedule'!CL63","v":0},{"$f":"'K80 - time schedule'!CM63","v":0},{"$f":"'K80 - time schedule'!CN63","v":0},{"$f":"'K80 - time schedule'!CO63","v":0},{"$f":"'K80 - time schedule'!CP63","v":0},{"$f":"'K80 - time schedule'!CQ63","v":0},{"$f":"'K80 - time schedule'!CR63","v":0},{"$f":"'K80 - time schedule'!CS63","v":0},{"$f":"'K80 - time schedule'!CT63","v":0},{"$f":"'K80 - time schedule'!CU63","v":0},{"$f":"'K80 - time schedule'!CV63","v":0},{"$f":"'K80 - time schedule'!CW63","v":0},{"$f":"'K80 - time schedule'!CX63","v":0},{"$f":"'K80 - time schedule'!CY63","v":0},{"$f":"'K80 - time schedule'!CZ63","v":0},{"$f":"'K80 - time schedule'!DA63","v":0},{"$f":"'K80 - time schedule'!DB63","v":0},{"$f":"'K80 - time schedule'!DC63","v":0},{"$f":"'K80 - time schedule'!DD63","v":0},{"$f":"'K80 - time schedule'!DE63","v":0},{"$f":"'K80 - time schedule'!DF63","v":0},{"$f":"'K80 - time schedule'!DG63","v":0},{"$f":"'K80 - time schedule'!DH63","v":0},{"$f":"'K80 - time schedule'!DI63","v":0},{"$f":"'K80 - time schedule'!DJ63","v":0},{"$f":"'K80 - time schedule'!DK63","v":0},{"$f":"'K80 - time schedule'!DL63","v":0},{"$f":"'K80 - time schedule'!DM63","v":0},{"$f":"'K80 - time schedule'!DN63","v":0},{"$f":"'K80 - time schedule'!DO63","v":0},{"$f":"'K80 - time schedule'!DP63","v":0},{"$f":"'K80 - time schedule'!DQ63","v":0},{"$f":"'K80 - time schedule'!DR63","v":0},{"$f":"'K80 - time schedule'!DS63","v":0},{"$f":"'K80 - time schedule'!DT63","v":0},{"$f":"'K80 - time schedule'!DU63","v":0},{"$f":"'K80 - time schedule'!DV63","v":0},{"$f":"'K80 - time schedule'!DW63","v":0},{"$f":"'K80 - time schedule'!DX63","v":0},{"$f":"'K80 - time schedule'!DY63","v":0},{"$f":"'K80 - time schedule'!DZ63","v":0},{"$f":"'K80 - time schedule'!EA63","v":0},{"$f":"'K80 - time schedule'!EB63","v":0},{"$f":"'K80 - time schedule'!EC63","v":0},{"$f":"'K80 - time schedule'!ED63","v":0},{"$f":"'K80 - time schedule'!EE63","v":0},{"$f":"'K80 - time schedule'!EF63","v":0},{"$f":"'K80 - time schedule'!EG63","v":0},{"$f":"'K80 - time schedule'!EH63","v":0},{"$f":"'K80 - time schedule'!EI63","v":0},{"$f":"'K80 - time schedule'!EJ63","v":0},{"$f":"'K80 - time schedule'!EK63","v":0},{"$f":"'K80 - time schedule'!EL63","v":0},{"$f":"'K80 - time schedule'!EM63","v":0},{"$f":"'K80 - time schedule'!EN63","v":0},{"$f":"'K80 - time schedule'!EO63","v":0},{"$f":"'K80 - time schedule'!EP63","v":0},{"$f":"'K80 - time schedule'!EQ63","v":0},{"$f":"'K80 - time schedule'!ER63","v":0},{"$f":"'K80 - time schedule'!ES63","v":0},{"$f":"'K80 - time schedule'!ET63","v":0},{"$f":"'K80 - time schedule'!EU63","v":0},{"$f":"'K80 - time schedule'!EV63","v":0},{"$f":"'K80 - time schedule'!EW63","v":0},{"$f":"'K80 - time schedule'!EX63","v":0},{"$f":"'K80 - time schedule'!EY63","v":0},{"$f":"'K80 - time schedule'!EZ63","v":0},{"$f":"'K80 - time schedule'!FA63","v":0},{"$f":"'K80 - time schedule'!FB63","v":0},{"$f":"'K80 - time schedule'!FC63","v":0},{"$f":"'K80 - time schedule'!FD63","v":0},{"$f":"'K80 - time schedule'!FE63","v":0},{"$f":"'K80 - time schedule'!FF63","v":0},{"$f":"'K80 - time schedule'!FG63","v":0},{"$f":"'K80 - time schedule'!FH63","v":0},{"$f":"'K80 - time schedule'!FI63","v":0},{"$f":"'K80 - time schedule'!FJ63","v":0},{"$f":"'K80 - time schedule'!FK63","v":0},{"$f":"'K80 - time schedule'!FL63","v":0},{"$f":"'K80 - time schedule'!FM63","v":0},{"$f":"'K80 - time schedule'!FN63","v":0},{"$f":"'K80 - time schedule'!FO63","v":0},{"$f":"'K80 - time schedule'!FP63","v":0},{"$f":"'K80 - time schedule'!FQ63","v":0},{"$f":"'K80 - time schedule'!FR63","v":0},{"$f":"'K80 - time schedule'!FS63","v":0},{"$f":"'K80 - time schedule'!FT63","v":0},{"$f":"'K80 - time schedule'!FU63","v":0},{"$f":"'K80 - time schedule'!FV63","v":0},{"$f":"'K80 - time schedule'!FW63","v":0},{"$f":"'K80 - time schedule'!FX63","v":0},{"$f":"'K80 - time schedule'!FY63","v":0},{"$f":"'K80 - time schedule'!FZ63","v":0},{"$f":"'K80 - time schedule'!GA63","v":0},{"$f":"'K80 - time schedule'!GB63","v":0},{"$f":"'K80 - time schedule'!GC63","v":0},{"$f":"'K80 - time schedule'!GD63","v":0},{"$f":"'K80 - time schedule'!GE63","v":0},{"$f":"'K80 - time schedule'!GF63","v":0},{"$f":"'K80 - time schedule'!GG63","v":0},{"$f":"'K80 - time schedule'!GH63","v":0},{"$f":"'K80 - time schedule'!GI63","v":0},{"$f":"'K80 - time schedule'!GJ63","v":0},{"$f":"'K80 - time schedule'!GK63","v":0},{"$f":"'K80 - time schedule'!GL63","v":0},{"$f":"'K80 - time schedule'!GM63","v":0},{"$f":"'K80 - time schedule'!GN63","v":0},{"$f":"'K80 - time schedule'!GO63","v":0},{"$f":"'K80 - time schedule'!GP63","v":0},{"$f":"'K80 - time schedule'!GQ63","v":0},{"$f":"'K80 - time schedule'!GR63","v":0},{"$f":"'K80 - time schedule'!GS63","v":0},{"$f":"'K80 - time schedule'!GT63","v":0},{"$f":"'K80 - time schedule'!GU63","v":0},{"$f":"'K80 - time schedule'!GV63","v":0},{"$f":"'K80 - time schedule'!GW63","v":0},{"$f":"'K80 - time schedule'!GX63","v":0},{"$f":"'K80 - time schedule'!GY63","v":0},{"$f":"'K80 - time schedule'!GZ63","v":0},{"$f":"'K80 - time schedule'!HA63","v":0},{"$f":"'K80 - time schedule'!HB63","v":0},{"$f":"'K80 - time schedule'!HC63","v":0},{"$f":"'K80 - time schedule'!HD63","v":0},{"$f":"'K80 - time schedule'!HE63","v":0},{"$f":"'K80 - time schedule'!HF63","v":0},{"$f":"'K80 - time schedule'!HG63","v":0},{"$f":"'K80 - time schedule'!HH63","v":0},{"$f":"'K80 - time schedule'!HI63","v":0},{"$f":"'K80 - time schedule'!HJ63","v":0},{"$f":"'K80 - time schedule'!HK63","v":0},{"$f":"'K80 - time schedule'!HL63","v":0},{"$f":"'K80 - time schedule'!HM63","v":0},{"$f":"'K80 - time schedule'!HN63","v":0},{"$f":"'K80 - time schedule'!HO63","v":0},{"$f":"'K80 - time schedule'!HP63","v":0},{"$f":"'K80 - time schedule'!HQ63","v":0},{"$f":"'K80 - time schedule'!HR63","v":0},{"$f":"'K80 - time schedule'!HS63","v":0},{"$f":"'K80 - time schedule'!HT63","v":0},{"$f":"'K80 - time schedule'!HU63","v":0},{"$f":"'K80 - time schedule'!HV63","v":0},{"$f":"'K80 - time schedule'!HW63","v":0},{"$f":"'K80 - time schedule'!HX63","v":0},{"$f":"'K80 - time schedule'!HY63","v":0},{"$f":"'K80 - time schedule'!HZ63","v":0},{"$f":"'K80 - time schedule'!IA63","v":0},{"$f":"'K80 - time schedule'!IB63","v":0},{"$f":"'K80 - time schedule'!IC63","v":0},{"$f":"'K80 - time schedule'!ID63","v":0},{"$f":"'K80 - time schedule'!IE63","v":0},{"$f":"'K80 - time schedule'!IF63","v":0},{"$f":"'K80 - time schedule'!IG63","v":0},{"$f":"'K80 - time schedule'!IH63","v":0},{"$f":"'K80 - time schedule'!II63","v":0},{"$f":"'K80 - time schedule'!IJ63","v":0},{"$f":"'K80 - time schedule'!IK63","v":0},{"$f":"'K80 - time schedule'!IL63","v":0},{"$f":"'K80 - time schedule'!IM63","v":0},{"$f":"'K80 - time schedule'!IN63","v":0},{"$f":"'K80 - time schedule'!IO63","v":0},{"$f":"'K80 - time schedule'!IP63","v":0},{"$f":"'K80 - time schedule'!IQ63","v":0},{"$f":"'K80 - time schedule'!IR63","v":0},{"$f":"'K80 - time schedule'!IS63","v":0},{"$f":"'K80 - time schedule'!IT63","v":0},{"$f":"'K80 - time schedule'!IU63","v":0},{"$f":"'K80 - time schedule'!IV63","v":0},{"$f":"'K80 - time schedule'!IW63","v":0},{"$f":"'K80 - time schedule'!IX63","v":0},{"$f":"'K80 - time schedule'!IY63","v":0},{"$f":"'K80 - time schedule'!IZ63","v":0},{"$f":"'K80 - time schedule'!JA63","v":0},{"$f":"'K80 - time schedule'!JB63","v":0},{"$f":"'K80 - time schedule'!JC63","v":0},{"$f":"'K80 - time schedule'!JD63","v":0},{"$f":"'K80 - time schedule'!JE63","v":0},{"$f":"'K80 - time schedule'!JF63","v":0},{"$f":"'K80 - time schedule'!JG63","v":0},{"$f":"'K80 - time schedule'!JH63","v":0},{"$f":"'K80 - time schedule'!JI63","v":0},{"$f":"'K80 - time schedule'!JJ63","v":0},{"$f":"'K80 - time schedule'!JK63","v":0},{"$f":"'K80 - time schedule'!JL63","v":0},{"$f":"'K80 - time schedule'!JM63","v":0},{"$f":"'K80 - time schedule'!JN63","v":0},{"$f":"'K80 - time schedule'!JO63","v":0},{"$f":"'K80 - time schedule'!JP63","v":0},{"$f":"'K80 - time schedule'!JQ63","v":0},{"$f":"'K80 - time schedule'!JR63","v":0},{"$f":"'K80 - time schedule'!JS63","v":0},{"$f":"'K80 - time schedule'!JT63","v":0},{"$f":"'K80 - time schedule'!JU63","v":0},{"$f":"'K80 - time schedule'!JV63","v":0},{"$f":"'K80 - time schedule'!JW63","v":0},{"$f":"'K80 - time schedule'!JX63","v":0},{"$f":"'K80 - time schedule'!JY63","v":0},{"$f":"'K80 - time schedule'!JZ63","v":0},{"$f":"'K80 - time schedule'!KA63","v":0},{"$f":"'K80 - time schedule'!KB63","v":0},{"$f":"'K80 - time schedule'!KC63","v":0},{"$f":"'K80 - time schedule'!KD63","v":0},{"$f":"'K80 - time schedule'!KE63","v":0},{"$f":"'K80 - time schedule'!KF63","v":0},{"$f":"'K80 - time schedule'!KG63","v":0},{"$f":"'K80 - time schedule'!KH63","v":0},{"$f":"'K80 - time schedule'!KI63","v":0},{"$f":"'K80 - time schedule'!KJ63","v":0},{"$f":"'K80 - time schedule'!KK63","v":0},{"$f":"'K80 - time schedule'!KL63","v":0},{"$f":"'K80 - time schedule'!KM63","v":0},{"$f":"'K80 - time schedule'!KN63","v":0},{"$f":"'K80 - time schedule'!KO63","v":0},{"$f":"'K80 - time schedule'!KP63","v":0},{"$f":"'K80 - time schedule'!KQ63","v":0},{"$f":"'K80 - time schedule'!KR63","v":0},{"$f":"'K80 - time schedule'!KS63","v":0},{"$f":"'K80 - time schedule'!KT63","v":0}]
["Boiler room K90 - initial technical meetings","K90",{"$f":"'K90 - time schedule'!G9","v":0},{"$f":"'K90 - time schedule'!H9","v":0},{"$f":"'K90 - time schedule'!I9","v":0},{"$f":"'K90 - time schedule'!J9","v":0},{"$f":"'K90 - time schedule'!K9","v":0},{"$f":"'K90 - time schedule'!L9","v":0},{"$f":"'K90 - time schedule'!M9","v":0},{"$f":"'K90 - time schedule'!N9","v":0},{"$f":"'K90 - time schedule'!O9","v":0},{"$f":"'K90 - time schedule'!P9","v":0},{"$f":"'K90 - time schedule'!Q9","v":0},{"$f":"'K90 - time schedule'!R9","v":0},{"$f":"'K90 - time schedule'!S9","v":0},{"$f":"'K90 - time schedule'!T9","v":0},{"$f":"'K90 - time schedule'!U9","v":0},{"$f":"'K90 - time schedule'!V9","v":0},{"$f":"'K90 - time schedule'!W9","v":0},{"$f":"'K90 - time schedule'!X9","v":0},{"$f":"'K90 - time schedule'!Y9","v":0},{"$f":"'K90 - time schedule'!Z9","v":0},{"$f":"'K90 - time schedule'!AA9","v":0},{"$f":"'K90 - time schedule'!AB9","v":0},{"$f":"'K90 - time schedule'!AC9","v":0},{"$f":"'K90 - time schedule'!AD9","v":0},{"$f":"'K90 - time schedule'!AE9","v":0},{"$f":"'K90 - time schedule'!AF9","v":0},{"$f":"'K90 - time schedule'!AG9","v":0},{"$f":"'K90 - time schedule'!AH9","v":0},{"$f":"'K90 - time schedule'!AI9","v":0},{"$f":"'K90 - time schedule'!AJ9","v":0},{"$f":"'K90 - time schedule'!AK9","v":0},{"$f":"'K90 - time schedule'!AL9","v":0},{"$f":"'K90 - time schedule'!AM9","v":0},{"$f":"'K90 - time schedule'!AN9","v":0},{"$f":"'K90 - time schedule'!AO9","v":0},{"$f":"'K90 - time schedule'!AP9","v":0},{"$f":"'K90 - time schedule'!AQ9","v":0},{"$f":"'K90 - time schedule'!AR9","v":0},{"$f":"'K90 - time schedule'!AS9","v":0},{"$f":"'K90 - time schedule'!AT9","v":0},{"$f":"'K90 - time schedule'!AU9","v":0},{"$f":"'K90 - time schedule'!AV9","v":0},{"$f":"'K90 - time schedule'!AW9","v":0},{"$f":"'K90 - time schedule'!AX9","v":0},{"$f":"'K90 - time schedule'!AY9","v":0},{"$f":"'K90 - time schedule'!AZ9","v":0},{"$f":"'K90 - time schedule'!BA9","v":0},{"$f":"'K90 - time schedule'!BB9","v":0},{"$f":"'K90 - time schedule'!BC9","v":0},{"$f":"'K90 - time schedule'!BD9","v":0},{"$f":"'K90 - time schedule'!BE9","v":0},{"$f":"'K90 - time schedule'!BF9","v":0},{"$f":"'K90 - time schedule'!BG9","v":0},{"$f":"'K90 - time schedule'!BH9","v":0},{"$f":"'K90 - time schedule'!BI9","v":0},{"$f":"'K90 - time schedule'!BJ9","v":0},{"$f":"'K90 - time schedule'!BK9","v":0},{"$f":"'K90 - time schedule'!BL9","v":0},{"$f":"'K90 - time schedule'!BM9","v":0},{"$f":"'K90 - time schedule'!BN9","v":0},{"$f":"'K90 - time schedule'!BO9","v":0},{"$f":"'K90 - time schedule'!BP9","v":0},{"$f":"'K90 - time schedule'!BQ9","v":0},{"$f":"'K90 - time schedule'!BR9","v":0},{"$f":"'K90 - time schedule'!BS9","v":0},{"$f":"'K90 - time schedule'!BT9","v":0},{"$f":"'K90 - time schedule'!BU9","v":0},{"$f":"'K90 - time schedule'!BV9","v":0},{"$f":"'K90 - time schedule'!BW9","v":0},{"$f":"'K90 - time schedule'!BX9","v":0},{"$f":"'K90 - time schedule'!BY9","v":0},{"$f":"'K90 - time schedule'!BZ9","v":0},{"$f":"'K90 - time schedule'!CA9","v":0},{"$f":"'K90 - time schedule'!CB9","v":0},{"$f":"'K90 - time schedule'!CC9","v":0},{"$f":"'K90 - time schedule'!CD9","v":0},{"$f":"'K90 - time schedule'!CE9","v":0},{"$f":"'K90 - time schedule'!CF9","v":0},{"$f":"'K90 - time schedule'!CG9","v":0},{"$f":"'K90 - time schedule'!CH9","v":0},{"$f":"'K90 - time schedule'!CI9","v":0},{"$f":"'K90 - time schedule'!CJ9","v":0},{"$f":"'K90 - time schedule'!CK9","v":0},{"$f":"'K90 - time schedule'!CL9","v":0},{"$f":"'K90 - time schedule'!CM9","v":0},{"$f":"'K90 - time schedule'!CN9","v":0},{"$f":"'K90 - time schedule'!CO9","v":0},{"$f":"'K90 - time schedule'!CP9","v":0},{"$f":"'K90 - time schedule'!CQ9","v":0},{"$f":"'K90 - time schedule'!CR9","v":0},{"$f":"'K90 - time schedule'!CS9","v":0},{"$f":"'K90 - time schedule'!CT9","v":0},{"$f":"'K90 - time schedule'!CU9","v":0},{"$f":"'K90 - time schedule'!CV9","v":0},{"$f":"'K90 - time schedule'!CW9","v":0},{"$f":"'K90 - time schedule'!CX9","v":0},{"$f":"'K90 - time schedule'!CY9","v":0},{"$f":"'K90 - time schedule'!CZ9","v":0},{"$f":"'K90 - time schedule'!DA9","v":0},{"$f":"'K90 - time schedule'!DB9","v":0},{"$f":"'K90 - time schedule'!DC9","v":0},{"$f":"'K90 - time schedule'!DD9","v":0},{"$f":"'K90 - time schedule'!DE9","v":0},{"$f":"'K90 - time schedule'!DF9","v":0},{"$f":"'K90 - time schedule'!DG9","v":0},{"$f":"'K90 - time schedule'!DH9","v":0},{"$f":"'K90 - time schedule'!DI9","v":0},{"$f":"'K90 - time schedule'!DJ9","v":0},{"$f":"'K90 - time schedule'!DK9","v":0},{"$f":"'K90 - time schedule'!DL9","v":0},{"$f":"'K90 - time schedule'!DM9","v":0},{"$f":"'K90 - time schedule'!DN9","v":0},{"$f":"'K90 - time schedule'!DO9","v":0},{"$f":"'K90 - time schedule'!DP9","v":0},{"$f":"'K90 - time schedule'!DQ9","v":0},{"$f":"'K90 - time schedule'!DR9","v":0},{"$f":"'K90 - time schedule'!DS9","v":0},{"$f":"'K90 - time schedule'!DT9","v":0},{"$f":"'K90 - time schedule'!DU9","v":0},{"$f":"'K90 - time schedule'!DV9","v":0},{"$f":"'K90 - time schedule'!DW9","v":0},{"$f":"'K90 - time schedule'!DX9","v":0},{"$f":"'K90 - time schedule'!DY9","v":0},{"$f":"'K90 - time schedule'!DZ9","v":0},{"$f":"'K90 - time schedule'!EA9","v":0},{"$f":"'K90 - time schedule'!EB9","v":0},{"$f":"'K90 - time schedule'!EC9","v":0},{"$f":"'K90 - time schedule'!ED9","v":0},{"$f":"'K90 - time schedule'!EE9","v":0},{"$f":"'K90 - time schedule'!EF9","v":0},{"$f":"'K90 - time schedule'!EG9","v":0},{"$f":"'K90 - time schedule'!EH9","v":0},{"$f":"'K90 - time schedule'!EI9","v":0},{"$f":"'K90 - time schedule'!EJ9","v":0},{"$f":"'K90 - time schedule'!EK9","v":0},{"$f":"'K90 - time schedule'!EL9","v":0},{"$f":"'K90 - time schedule'!EM9","v":0},{"$f":"'K90 - time schedule'!EN9","v":0},{"$f":"'K90 - time schedule'!EO9","v":0},{"$f":"'K90 - time schedule'!EP9","v":0},{"$f":"'K90 - time schedule'!EQ9","v":0},{"$f":"'K90 - time schedule'!ER9","v":0},{"$f":"'K90 - time schedule'!ES9","v":0},{"$f":"'K90 - time schedule'!ET9","v":0},{"$f":"'K90 - time schedule'!EU9","v":0},{"$f":"'K90 - time schedule'!EV9","v":0},{"$f":"'K90 - time schedule'!EW9","v":0},{"$f":"'K90 - time schedule'!EX9","v":0},{"$f":"'K90 - time schedule'!EY9","v":0},{"$f":"'K90 - time schedule'!EZ9","v":0},{"$f":"'K90 - time schedule'!FA9","v":0},{"$f":"'K90 - time schedule'!FB9","v":0},{"$f":"'K90 - time schedule'!FC9","v":0},{"$f":"'K90 - time schedule'!FD9","v":0},{"$f":"'K90 - time schedule'!FE9","v":0},{"$f":"'K90 - time schedule'!FF9","v":0},{"$f":"'K90 - time schedule'!FG9","v":0},{"$f":"'K90 - time schedule'!FH9","v":0},{"$f":"'K90 - time schedule'!FI9","v":0},{"$f":"'K90 - time schedule'!FJ9","v":0},{"$f":"'K90 - time schedule'!FK9","v":0},{"$f":"'K90 - time schedule'!FL9","v":0},{"$f":"'K90 - time schedule'!FM9","v":0},{"$f":"'K90 - time schedule'!FN9","v":0},{"$f":"'K90 - time schedule'!FO9","v":0},{"$f":"'K90 - time schedule'!FP9","v":0},{"$f":"'K90 - time schedule'!FQ9","v":0},{"$f":"'K90 - time schedule'!FR9","v":0},{"$f":"'K90 - time schedule'!FS9","v":0},{"$f":"'K90 - time schedule'!FT9","v":0},{"$f":"'K90 - time schedule'!FU9","v":0},{"$f":"'K90 - time schedule'!FV9","v":0},{"$f":"'K90 - time schedule'!FW9","v":0},{"$f":"'K90 - time schedule'!FX9","v":0},{"$f":"'K90 - time schedule'!FY9","v":0},{"$f":"'K90 - time schedule'!FZ9","v":0},{"$f":"'K90 - time schedule'!GA9","v":0},{"$f":"'K90 - time schedule'!GB9","v":0},{"$f":"'K90 - time schedule'!GC9","v":0},{"$f":"'K90 - time schedule'!GD9","v":0},{"$f":"'K90 - time schedule'!GE9","v":0},{"$f":"'K90 - time schedule'!GF9","v":0},{"$f":"'K90 - time schedule'!GG9","v":0},{"$f":"'K90 - time schedule'!GH9","v":0},{"$f":"'K90 - time schedule'!GI9","v":0},{"$f":"'K90 - time schedule'!GJ9","v":0},{"$f":"'K90 - time schedule'!GK9","v":0},{"$f":"'K90 - time schedule'!GL9","v":0},{"$f":"'K90 - time schedule'!GM9","v":0},{"$f":"'K90 - time schedule'!GN9","v":0},{"$f":"'K90 - time schedule'!GO9","v":0},{"$f":"'K90 - time schedule'!GP9","v":0},{"$f":"'K90 - time schedule'!GQ9","v":0},{"$f":"'K90 - time schedule'!GR9","v":0},{"$f":"'K90 - time schedule'!GS9","v":0},{"$f":"'K90 - time schedule'!GT9","v":0},{"$f":"'K90 - time schedule'!GU9","v":0},{"$f":"'K90 - time schedule'!GV9","v":0},{"$f":"'K90 - time schedule'!GW9","v":0},{"$f":"'K90 - time schedule'!GX9","v":0},{"$f":"'K90 - time schedule'!GY9","v":0},{"$f":"'K90 - time schedule'!GZ9","v":0},{"$f":"'K90 - time schedule'!HA9","v":0},{"$f":"'K90 - time schedule'!HB9","v":0},{"$f":"'K90 - time schedule'!HC9","v":0},{"$f":"'K90 - time schedule'!HD9","v":0},{"$f":"'K90 - time schedule'!HE9","v":0},{"$f":"'K90 - time schedule'!HF9","v":0},{"$f":"'K90 - time schedule'!HG9","v":0},{"$f":"'K90 - time schedule'!HH9","v":0},{"$f":"'K90 - time schedule'!HI9","v":0},{"$f":"'K90 - time schedule'!HJ9","v":0},{"$f":"'K90 - time schedule'!HK9","v":0},{"$f":"'K90 - time schedule'!HL9","v":0},{"$f":"'K90 - time schedule'!HM9","v":0},{"$f":"'K90 - time schedule'!HN9","v":0},{"$f":"'K90 - time schedule'!HO9","v":0},{"$f":"'K90 - time schedule'!HP9","v":0},{"$f":"'K90 - time schedule'!HQ9","v":0},{"$f":"'K90 - time schedule'!HR9","v":0},{"$f":"'K90 - time schedule'!HS9","v":0},{"$f":"'K90 - time schedule'!HT9","v":0},{"$f":"'K90 - time schedule'!HU9","v":0},{"$f":"'K90 - time schedule'!HV9","v":0},{"$f":"'K90 - time schedule'!HW9","v":0},{"$f":"'K90 - time schedule'!HX9","v":0},{"$f":"'K90 - time schedule'!HY9","v":0},{"$f":"'K90 - time schedule'!HZ9","v":0},{"$f":"'K90 - time schedule'!IA9","v":0},{"$f":"'K90 - time schedule'!IB9","v":0},{"$f":"'K90 - time schedule'!IC9","v":0},{"$f":"'K90 - time schedule'!ID9","v":0},{"$f":"'K90 - time schedule'!IE9","v":0},{"$f":"'K90 - time schedule'!IF9","v":0},{"$f":"'K90 - time schedule'!IG9","v":0},{"$f":"'K90 - time schedule'!IH9","v":0},{"$f":"'K90 - time schedule'!II9","v":0},{"$f":"'K90 - time schedule'!IJ9","v":0},{"$f":"'K90 - time schedule'!IK9","v":0},{"$f":"'K90 - time schedule'!IL9","v":0},{"$f":"'K90 - time schedule'!IM9","v":0},{"$f":"'K90 - time schedule'!IN9","v":0},{"$f":"'K90 - time schedule'!IO9","v":0},{"$f":"'K90 - time schedule'!IP9","v":0},{"$f":"'K90 - time schedule'!IQ9","v":0},{"$f":"'K90 - time schedule'!IR9","v":0},{"$f":"'K90 - time schedule'!IS9","v":0},{"$f":"'K90 - time schedule'!IT9","v":0},{"$f":"'K90 - time schedule'!IU9","v":0},{"$f":"'K90 - time schedule'!IV9","v":0},{"$f":"'K90 - time schedule'!IW9","v":0},{"$f":"'K90 - time schedule'!IX9","v":0},{"$f":"'K90 - time schedule'!IY9","v":0},{"$f":"'K90 - time schedule'!IZ9","v":0},{"$f":"'K90 - time schedule'!JA9","v":0},{"$f":"'K90 - time schedule'!JB9","v":0},{"$f":"'K90 - time schedule'!JC9","v":0},{"$f":"'K90 - time schedule'!JD9","v":0},{"$f":"'K90 - time schedule'!JE9","v":0},{"$f":"'K90 - time schedule'!JF9","v":0},{"$f":"'K90 - time schedule'!JG9","v":0},{"$f":"'K90 - time schedule'!JH9","v":0},{"$f":"'K90 - time schedule'!JI9","v":0},{"$f":"'K90 - time schedule'!JJ9","v":0},{"$f":"'K90 - time schedule'!JK9","v":0},{"$f":"'K90 - time schedule'!JL9","v":0},{"$f":"'K90 - time schedule'!JM9","v":0},{"$f":"'K90 - time schedule'!JN9","v":0},{"$f":"'K90 - time schedule'!JO9","v":0},{"$f":"'K90 - time schedule'!JP9","v":0},{"$f":"'K90 - time schedule'!JQ9","v":0},{"$f":"'K90 - time schedule'!JR9","v":0},{"$f":"'K90 - time schedule'!JS9","v":0},{"$f":"'K90 - time schedule'!JT9","v":0},{"$f":"'K90 - time schedule'!JU9","v":0},{"$f":"'K90 - time schedule'!JV9","v":0},{"$f":"'K90 - time schedule'!JW9","v":0},{"$f":"'K90 - time schedule'!JX9","v":0},{"$f":"'K90 - time schedule'!JY9","v":0},{"$f":"'K90 - time schedule'!JZ9","v":0},{"$f":"'K90 - time schedule'!KA9","v":0},{"$f":"'K90 - time schedule'!KB9","v":0},{"$f":"'K90 - time schedule'!KC9","v":0},{"$f":"'K90 - time schedule'!KD9","v":0},{"$f":"'K90 - time schedule'!KE9","v":0},{"$f":"'K90 - time schedule'!KF9","v":0},{"$f":"'K90 - time schedule'!KG9","v":0},{"$f":"'K90 - time schedule'!KH9","v":0},{"$f":"'K90 - time schedule'!KI9","v":0},{"$f":"'K90 - time schedule'!KJ9","v":0},{"$f":"'K90 - time schedule'!KK9","v":0},{"$f":"'K90 - time schedule'!KL9","v":0},{"$f":"'K90 - time schedule'!KM9","v":0},{"$f":"'K90 - time schedule'!KN9","v":0},{"$f":"'K90 - time schedule'!KO9","v":0},{"$f":"'K90 - time schedule'!KP9","v":0},{"$f":"'K90 - time schedule'!KQ9","v":0},{"$f":"'K90 - time schedule'!KR9","v":0},{"$f":"'K90 - time schedule'!KS9","v":0},{"$f":"'K90 - time schedule'!KT9","v":0}]
["Boiler room K90 - binding technical specification for OB 6 (Construction)","K90",{"$f":"'K90 - time schedule'!G10","v":0},{"$f":"'K90 - time schedule'!H10","v":0},{"$f":"'K90 - time schedule'!I10","v":0},{"$f":"'K90 - time schedule'!J10","v":0},{"$f":"'K90 - time schedule'!K10","v":0},{"$f":"'K90 - time schedule'!L10","v":0},{"$f":"'K90 - time schedule'!M10","v":0},{"$f":"'K90 - time schedule'!N10","v":0},{"$f":"'K90 - time schedule'!O10","v":0},{"$f":"'K90 - time schedule'!P10","v":0},{"$f":"'K90 - time schedule'!Q10","v":0},{"$f":"'K90 - time schedule'!R10","v":0},{"$f":"'K90 - time schedule'!S10","v":0},{"$f":"'K90 - time schedule'!T10","v":0},{"$f":"'K90 - time schedule'!U10","v":0},{"$f":"'K90 - time schedule'!V10","v":0},{"$f":"'K90 - time schedule'!W10","v":0},{"$f":"'K90 - time schedule'!X10","v":0},{"$f":"'K90 - time schedule'!Y10","v":0},{"$f":"'K90 - time schedule'!Z10","v":0},{"$f":"'K90 - time schedule'!AA10","v":0},{"$f":"'K90 - time schedule'!AB10","v":0},{"$f":"'K90 - time schedule'!AC10","v":0},{"$f":"'K90 - time schedule'!AD10","v":0},{"$f":"'K90 - time schedule'!AE10","v":0},{"$f":"'K90 - time schedule'!AF10","v":0},{"$f":"'K90 - time schedule'!AG10","v":0},{"$f":"'K90 - time schedule'!AH10","v":0},{"$f":"'K90 - time schedule'!AI10","v":0},{"$f":"'K90 - time schedule'!AJ10","v":0},{"$f":"'K90 - time schedule'!AK10","v":0},{"$f":"'K90 - time schedule'!AL10","v":0},{"$f":"'K90 - time schedule'!AM10","v":0},{"$f":"'K90 - time schedule'!AN10","v":0},{"$f":"'K90 - time schedule'!AO10","v":0},{"$f":"'K90 - time schedule'!AP10","v":0},{"$f":"'K90 - time schedule'!AQ10","v":0},{"$f":"'K90 - time schedule'!AR10","v":0},{"$f":"'K90 - time schedule'!AS10","v":0},{"$f":"'K90 - time schedule'!AT10","v":0},{"$f":"'K90 - time schedule'!AU10","v":0},{"$f":"'K90 - time schedule'!AV10","v":0},{"$f":"'K90 - time schedule'!AW10","v":0},{"$f":"'K90 - time schedule'!AX10","v":0},{"$f":"'K90 - time schedule'!AY10","v":0},{"$f":"'K90 - time schedule'!AZ10","v":0},{"$f":"'K90 - time schedule'!BA10","v":0},{"$f":"'K90 - time schedule'!BB10","v":0},{"$f":"'K90 - time schedule'!BC10","v":0},{"$f":"'K90 - time schedule'!BD10","v":0},{"$f":"'K90 - time schedule'!BE10","v":0},{"$f":"'K90 - time schedule'!BF10","v":0},{"$f":"'K90 - time schedule'!BG10","v":0},{"$f":"'K90 - time schedule'!BH10","v":0},{"$f":"'K90 - time schedule'!BI10","v":0},{"$f":"'K90 - time schedule'!BJ10","v":0},{"$f":"'K90 - time schedule'!BK10","v":0},{"$f":"'K90 - time schedule'!BL10","v":0},{"$f":"'K90 - time schedule'!BM10","v":0},{"$f":"'K90 - time schedule'!BN10","v":0},{"$f":"'K90 - time schedule'!BO10","v":0},{"$f":"'K90 - time schedule'!BP10","v":0},{"$f":"'K90 - time schedule'!BQ10","v":0},{"$f":"'K90 - time schedule'!BR10","v":0},{"$f":"'K90 - time schedule'!BS10","v":0},{"$f":"'K90 - time schedule'!BT10","v":0},{"$f":"'K90 - time schedule'!BU10","v":0},{"$f":"'K90 - time schedule'!BV10","v":0},{"$f":"'K90 - time schedule'!BW10","v":0},{"$f":"'K90 - time schedule'!BX10","v":0},{"$f":"'K90 - time schedule'!BY10","v":0},{"$f":"'K90 - time schedule'!BZ10","v":0},{"$f":"'K90 - time schedule'!CA10","v":0},{"$f":"'K90 - time schedule'!CB10","v":0},{"$f":"'K90 - time schedule'!CC10","v":0},{"$f":"'K90 - time schedule'!CD10","v":0},{"$f":"'K90 - time schedule'!CE10","v":0},{"$f":"'K90 - time schedule'!CF10","v":0},{"$f":"'K90 - time schedule'!CG10","v":0},{"$f":"'K90 - time schedule'!CH10","v":0},{"$f":"'K90 - time schedule'!CI10","v":0},{"$f":"'K90 - time schedule'!CJ10","v":0},{"$f":"'K90 - time schedule'!CK10","v":0},{"$f":"'K90 - time schedule'!CL10","v":0},{"$f":"'K90 - time schedule'!CM10","v":0},{"$f":"'K90 - time schedule'!CN10","v":0},{"$f":"'K90 - time schedule'!CO10","v":0},{"$f":"'K90 - time schedule'!CP10","v":0},{"$f":"'K90 - time schedule'!CQ10","v":0},{"$f":"'K90 - time schedule'!CR10","v":0},{"$f":"'K90 - time schedule'!CS10","v":0},{"$f":"'K90 - time schedule'!CT10","v":0},{"$f":"'K90 - time schedule'!CU10","v":0},{"$f":"'K90 - time schedule'!CV10","v":0},{"$f":"'K90 - time schedule'!CW10","v":0},{"$f":"'K90 - time schedule'!CX10","v":0},{"$f":"'K90 - time schedule'!CY10","v":0},{"$f":"'K90 - time schedule'!CZ10","v":0},{"$f":"'K90 - time schedule'!DA10","v":0},{"$f":"'K90 - time schedule'!DB10","v":0},{"$f":"'K90 - time schedule'!DC10","v":0},{"$f":"'K90 - time schedule'!DD10","v":0},{"$f":"'K90 - time schedule'!DE10","v":0},{"$f":"'K90 - time schedule'!DF10","v":0},{"$f":"'K90 - time schedule'!DG10","v":0},{"$f":"'K90 - time schedule'!DH10","v":0},{"$f":"'K90 - time schedule'!DI10","v":0},{"$f":"'K90 - time schedule'!DJ10","v":0},{"$f":"'K90 - time schedule'!DK10","v":0},{"$f":"'K90 - time schedule'!DL10","v":0},{"$f":"'K90 - time schedule'!DM10","v":0},{"$f":"'K90 - time schedule'!DN10","v":0},{"$f":"'K90 - time schedule'!DO10","v":0},{"$f":"'K90 - time schedule'!DP10","v":0},{"$f":"'K90 - time schedule'!DQ10","v":0},{"$f":"'K90 - time schedule'!DR10","v":0},{"$f":"'K90 - time schedule'!DS10","v":0},{"$f":"'K90 - time schedule'!DT10","v":0},{"$f":"'K90 - time schedule'!DU10","v":0},{"$f":"'K90 - time schedule'!DV10","v":0},{"$f":"'K90 - time schedule'!DW10","v":0},{"$f":"'K90 - time schedule'!DX10","v":0},{"$f":"'K90 - time schedule'!DY10","v":0},{"$f":"'K90 - time schedule'!DZ10","v":0},{"$f":"'K90 - time schedule'!EA10","v":0},{"$f":"'K90 - time schedule'!EB10","v":0},{"$f":"'K90 - time schedule'!EC10","v":0},{"$f":"'K90 - time schedule'!ED10","v":0},{"$f":"'K90 - time schedule'!EE10","v":0},{"$f":"'K90 - time schedule'!EF10","v":0},{"$f":"'K90 - time schedule'!EG10","v":0},{"$f":"'K90 - time schedule'!EH10","v":0},{"$f":"'K90 - time schedule'!EI10","v":0},{"$f":"'K90 - time schedule'!EJ10","v":0},{"$f":"'K90 - time schedule'!EK10","v":0},{"$f":"'K90 - time schedule'!EL10","v":0},{"$f":"'K90 - time schedule'!EM10","v":0},{"$f":"'K90 - time schedule'!EN10","v":0},{"$f":"'K90 - time schedule'!EO10","v":0},{"$f":"'K90 - time schedule'!EP10","v":0},{"$f":"'K90 - time schedule'!EQ10","v":0},{"$f":"'K90 - time schedule'!ER10","v":0},{"$f":"'K90 - time schedule'!ES10","v":0},{"$f":"'K90 - time schedule'!ET10","v":0},{"$f":"'K90 - time schedule'!EU10","v":0},{"$f":"'K90 - time schedule'!EV10","v":0},{"$f":"'K90 - time schedule'!EW10","v":0},{"$f":"'K90 - time schedule'!EX10","v":0},{"$f":"'K90 - time schedule'!EY10","v":0},{"$f":"'K90 - time schedule'!EZ10","v":0},{"$f":"'K90 - time schedule'!FA10","v":0},{"$f":"'K90 - time schedule'!FB10","v":0},{"$f":"'K90 - time schedule'!FC10","v":0},{"$f":"'K90 - time schedule'!FD10","v":0},{"$f":"'K90 - time schedule'!FE10","v":0},{"$f":"'K90 - time schedule'!FF10","v":0},{"$f":"'K90 - time schedule'!FG10","v":0},{"$f":"'K90 - time schedule'!FH10","v":0},{"$f":"'K90 - time schedule'!FI10","v":0},{"$f":"'K90 - time schedule'!FJ10","v":0},{"$f":"'K90 - time schedule'!FK10","v":0},{"$f":"'K90 - time schedule'!FL10","v":0},{"$f":"'K90 - time schedule'!FM10","v":0},{"$f":"'K90 - time schedule'!FN10","v":0},{"$f":"'K90 - time schedule'!FO10","v":0},{"$f":"'K90 - time schedule'!FP10","v":0},{"$f":"'K90 - time schedule'!FQ10","v":0},{"$f":"'K90 - time schedule'!FR10","v":0},{"$f":"'K90 - time schedule'!FS10","v":0},{"$f":"'K90 - time schedule'!FT10","v":0},{"$f":"'K90 - time schedule'!FU10","v":0},{"$f":"'K90 - time schedule'!FV10","v":0},{"$f":"'K90 - time schedule'!FW10","v":0},{"$f":"'K90 - time schedule'!FX10","v":0},{"$f":"'K90 - time schedule'!FY10","v":0},{"$f":"'K90 - time schedule'!FZ10","v":0},{"$f":"'K90 - time schedule'!GA10","v":0},{"$f":"'K90 - time schedule'!GB10","v":0},{"$f":"'K90 - time schedule'!GC10","v":0},{"$f":"'K90 - time schedule'!GD10","v":0},{"$f":"'K90 - time schedule'!GE10","v":0},{"$f":"'K90 - time schedule'!GF10","v":0},{"$f":"'K90 - time schedule'!GG10","v":0},{"$f":"'K90 - time schedule'!GH10","v":0},{"$f":"'K90 - time schedule'!GI10","v":0},{"$f":"'K90 - time schedule'!GJ10","v":0},{"$f":"'K90 - time schedule'!GK10","v":0},{"$f":"'K90 - time schedule'!GL10","v":0},{"$f":"'K90 - time schedule'!GM10","v":0},{"$f":"'K90 - time schedule'!GN10","v":0},{"$f":"'K90 - time schedule'!GO10","v":0},{"$f":"'K90 - time schedule'!GP10","v":0},{"$f":"'K90 - time schedule'!GQ10","v":0},{"$f":"'K90 - time schedule'!GR10","v":0},{"$f":"'K90 - time schedule'!GS10","v":0},{"$f":"'K90 - time schedule'!GT10","v":0},{"$f":"'K90 - time schedule'!GU10","v":0},{"$f":"'K90 - time schedule'!GV10","v":0},{"$f":"'K90 - time schedule'!GW10","v":0},{"$f":"'K90 - time schedule'!GX10","v":0},{"$f":"'K90 - time schedule'!GY10","v":0},{"$f":"'K90 - time schedule'!GZ10","v":0},{"$f":"'K90 - time schedule'!HA10","v":0},{"$f":"'K90 - time schedule'!HB10","v":0},{"$f":"'K90 - time schedule'!HC10","v":0},{"$f":"'K90 - time schedule'!HD10","v":0},{"$f":"'K90 - time schedule'!HE10","v":0},{"$f":"'K90 - time schedule'!HF10","v":0},{"$f":"'K90 - time schedule'!HG10","v":0},{"$f":"'K90 - time schedule'!HH10","v":0},{"$f":"'K90 - time schedule'!HI10","v":0},{"$f":"'K90 - time schedule'!HJ10","v":0},{"$f":"'K90 - time schedule'!HK10","v":0},{"$f":"'K90 - time schedule'!HL10","v":0},{"$f":"'K90 - time schedule'!HM10","v":0},{"$f":"'K90 - time schedule'!HN10","v":0},{"$f":"'K90 - time schedule'!HO10","v":0},{"$f":"'K90 - time schedule'!HP10","v":0},{"$f":"'K90 - time schedule'!HQ10","v":0},{"$f":"'K90 - time schedule'!HR10","v":0},{"$f":"'K90 - time schedule'!HS10","v":0},{"$f":"'K90 - time schedule'!HT10","v":0},{"$f":"'K90 - time schedule'!HU10","v":0},{"$f":"'K90 - time schedule'!HV10","v":0},{"$f":"'K90 - time schedule'!HW10","v":0},{"$f":"'K90 - time schedule'!HX10","v":0},{"$f":"'K90 - time schedule'!HY10","v":0},{"$f":"'K90 - time schedule'!HZ10","v":0},{"$f":"'K90 - time schedule'!IA10","v":0},{"$f":"'K90 - time schedule'!IB10","v":0},{"$f":"'K90 - time schedule'!IC10","v":0},{"$f":"'K90 - time schedule'!ID10","v":0},{"$f":"'K90 - time schedule'!IE10","v":0},{"$f":"'K90 - time schedule'!IF10","v":0},{"$f":"'K90 - time schedule'!IG10","v":0},{"$f":"'K90 - time schedule'!IH10","v":0},{"$f":"'K90 - time schedule'!II10","v":0},{"$f":"'K90 - time schedule'!IJ10","v":0},{"$f":"'K90 - time schedule'!IK10","v":0},{"$f":"'K90 - time schedule'!IL10","v":0},{"$f":"'K90 - time schedule'!IM10","v":0},{"$f":"'K90 - time schedule'!IN10","v":0},{"$f":"'K90 - time schedule'!IO10","v":0},{"$f":"'K90 - time schedule'!IP10","v":0},{"$f":"'K90 - time schedule'!IQ10","v":0},{"$f":"'K90 - time schedule'!IR10","v":0},{"$f":"'K90 - time schedule'!IS10","v":0},{"$f":"'K90 - time schedule'!IT10","v":0},{"$f":"'K90 - time schedule'!IU10","v":0},{"$f":"'K90 - time schedule'!IV10","v":0},{"$f":"'K90 - time schedule'!IW10","v":0},{"$f":"'K90 - time schedule'!IX10","v":0},{"$f":"'K90 - time schedule'!IY10","v":0},{"$f":"'K90 - time schedule'!IZ10","v":0},{"$f":"'K90 - time schedule'!JA10","v":0},{"$f":"'K90 - time schedule'!JB10","v":0},{"$f":"'K90 - time schedule'!JC10","v":0},{"$f":"'K90 - time schedule'!JD10","v":0},{"$f":"'K90 - time schedule'!JE10","v":0},{"$f":"'K90 - time schedule'!JF10","v":0},{"$f":"'K90 - time schedule'!JG10","v":0},{"$f":"'K90 - time schedule'!JH10","v":0},{"$f":"'K90 - time schedule'!JI10","v":0},{"$f":"'K90 - time schedule'!JJ10","v":0},{"$f":"'K90 - time schedule'!JK10","v":0},{"$f":"'K90 - time schedule'!JL10","v":0},{"$f":"'K90 - time schedule'!JM10","v":0},{"$f":"'K90 - time schedule'!JN10","v":0},{"$f":"'K90 - time schedule'!JO10","v":0},{"$f":"'K90 - time schedule'!JP10","v":0},{"$f":"'K90 - time schedule'!JQ10","v":0},{"$f":"'K90 - time schedule'!JR10","v":0},{"$f":"'K90 - time schedule'!JS10","v":0},{"$f":"'K90 - time schedule'!JT10","v":0},{"$f":"'K90 - time schedule'!JU10","v":0},{"$f":"'K90 - time schedule'!JV10","v":0},{"$f":"'K90 - time schedule'!JW10","v":0},{"$f":"'K90 - time schedule'!JX10","v":0},{"$f":"'K90 - time schedule'!JY10","v":0},{"$f":"'K90 - time schedule'!JZ10","v":0},{"$f":"'K90 - time schedule'!KA10","v":0},{"$f":"'K90 - time schedule'!KB10","v":0},{"$f":"'K90 - time schedule'!KC10","v":0},{"$f":"'K90 - time schedule'!KD10","v":0},{"$f":"'K90 - time schedule'!KE10","v":0},{"$f":"'K90 - time schedule'!KF10","v":0},{"$f":"'K90 - time schedule'!KG10","v":0},{"$f":"'K90 - time schedule'!KH10","v":0},{"$f":"'K90 - time schedule'!KI10","v":0},{"$f":"'K90 - time schedule'!KJ10","v":0},{"$f":"'K90 - time schedule'!KK10","v":0},{"$f":"'K90 - time schedule'!KL10","v":0},{"$f":"'K90 - time schedule'!KM10","v":0},{"$f":"'K90 - time schedule'!KN10","v":0},{"$f":"'K90 - time schedule'!KO10","v":0},{"$f":"'K90 - time schedule'!KP10","v":0},{"$f":"'K90 - time schedule'!KQ10","v":0},{"$f":"'K90 - time schedule'!KR10","v":0},{"$f":"'K90 - time schedule'!KS10","v":0},{"$f":"'K90 - time schedule'!KT10","v":0}]
["Boiler room K90 - binding technical specification for OB 1 (Fuel management) ","K90",{"$f":"'K90 - time schedule'!G12","v":0},{"$f":"'K90 - time schedule'!H12","v":0},{"$f":"'K90 - time schedule'!I12","v":0},{"$f":"'K90 - time schedule'!J12","v":0},{"$f":"'K90 - time schedule'!K12","v":0},{"$f":"'K90 - time schedule'!L12","v":0},{"$f":"'K90 - time schedule'!M12","v":0},{"$f":"'K90 - time schedule'!N12","v":0},{"$f":"'K90 - time schedule'!O12","v":0},{"$f":"'K90 - time schedule'!P12","v":0},{"$f":"'K90 - time schedule'!Q12","v":0},{"$f":"'K90 - time schedule'!R12","v":0},{"$f":"'K90 - time schedule'!S12","v":0},{"$f":"'K90 - time schedule'!T12","v":0},{"$f":"'K90 - time schedule'!U12","v":0},{"$f":"'K90 - time schedule'!V12","v":0},{"$f":"'K90 - time schedule'!W12","v":0},{"$f":"'K90 - time schedule'!X12","v":0},{"$f":"'K90 - time schedule'!Y12","v":0},{"$f":"'K90 - time schedule'!Z12","v":0},{"$f":"'K90 - time schedule'!AA12","v":0},{"$f":"'K90 - time schedule'!AB12","v":0},{"$f":"'K90 - time schedule'!AC12","v":0},{"$f":"'K90 - time schedule'!AD12","v":0},{"$f":"'K90 - time schedule'!AE12","v":0},{"$f":"'K90 - time schedule'!AF12","v":0},{"$f":"'K90 - time schedule'!AG12","v":0},{"$f":"'K90 - time schedule'!AH12","v":0},{"$f":"'K90 - time schedule'!AI12","v":0},{"$f":"'K90 - time schedule'!AJ12","v":0},{"$f":"'K90 - time schedule'!AK12","v":0},{"$f":"'K90 - time schedule'!AL12","v":0},{"$f":"'K90 - time schedule'!AM12","v":0},{"$f":"'K90 - time schedule'!AN12","v":0},{"$f":"'K90 - time schedule'!AO12","v":0},{"$f":"'K90 - time schedule'!AP12","v":0},{"$f":"'K90 - time schedule'!AQ12","v":0},{"$f":"'K90 - time schedule'!AR12","v":0},{"$f":"'K90 - time schedule'!AS12","v":0},{"$f":"'K90 - time schedule'!AT12","v":0},{"$f":"'K90 - time schedule'!AU12","v":0},{"$f":"'K90 - time schedule'!AV12","v":0},{"$f":"'K90 - time schedule'!AW12","v":0},{"$f":"'K90 - time schedule'!AX12","v":0},{"$f":"'K90 - time schedule'!AY12","v":0},{"$f":"'K90 - time schedule'!AZ12","v":0},{"$f":"'K90 - time schedule'!BA12","v":0},{"$f":"'K90 - time schedule'!BB12","v":0},{"$f":"'K90 - time schedule'!BC12","v":0},{"$f":"'K90 - time schedule'!BD12","v":0},{"$f":"'K90 - time schedule'!BE12","v":0},{"$f":"'K90 - time schedule'!BF12","v":0},{"$f":"'K90 - time schedule'!BG12","v":0},{"$f":"'K90 - time schedule'!BH12","v":0},{"$f":"'K90 - time schedule'!BI12","v":0},{"$f":"'K90 - time schedule'!BJ12","v":0},{"$f":"'K90 - time schedule'!BK12","v":0},{"$f":"'K90 - time schedule'!BL12","v":0},{"$f":"'K90 - time schedule'!BM12","v":0},{"$f":"'K90 - time schedule'!BN12","v":0},{"$f":"'K90 - time schedule'!BO12","v":0},{"$f":"'K90 - time schedule'!BP12","v":0},{"$f":"'K90 - time schedule'!BQ12","v":0},{"$f":"'K90 - time schedule'!BR12","v":0},{"$f":"'K90 - time schedule'!BS12","v":0},{"$f":"'K90 - time schedule'!BT12","v":0},{"$f":"'K90 - time schedule'!BU12","v":0},{"$f":"'K90 - time schedule'!BV12","v":0},{"$f":"'K90 - time schedule'!BW12","v":0},{"$f":"'K90 - time schedule'!BX12","v":0},{"$f":"'K90 - time schedule'!BY12","v":0},{"$f":"'K90 - time schedule'!BZ12","v":0},{"$f":"'K90 - time schedule'!CA12","v":0},{"$f":"'K90 - time schedule'!CB12","v":0},{"$f":"'K90 - time schedule'!CC12","v":0},{"$f":"'K90 - time schedule'!CD12","v":0},{"$f":"'K90 - time schedule'!CE12","v":0},{"$f":"'K90 - time schedule'!CF12","v":0},{"$f":"'K90 - time schedule'!CG12","v":0},{"$f":"'K90 - time schedule'!CH12","v":0},{"$f":"'K90 - time schedule'!CI12","v":0},{"$f":"'K90 - time schedule'!CJ12","v":0},{"$f":"'K90 - time schedule'!CK12","v":0},{"$f":"'K90 - time schedule'!CL12","v":0},{"$f":"'K90 - time schedule'!CM12","v":0},{"$f":"'K90 - time schedule'!CN12","v":0},{"$f":"'K90 - time schedule'!CO12","v":0},{"$f":"'K90 - time schedule'!CP12","v":0},{"$f":"'K90 - time schedule'!CQ12","v":0},{"$f":"'K90 - time schedule'!CR12","v":0},{"$f":"'K90 - time schedule'!CS12","v":0},{"$f":"'K90 - time schedule'!CT12","v":0},{"$f":"'K90 - time schedule'!CU12","v":0},{"$f":"'K90 - time schedule'!CV12","v":0},{"$f":"'K90 - time schedule'!CW12","v":0},{"$f":"'K90 - time schedule'!CX12","v":0},{"$f":"'K90 - time schedule'!CY12","v":0},{"$f":"'K90 - time schedule'!CZ12","v":0},{"$f":"'K90 - time schedule'!DA12","v":0},{"$f":"'K90 - time schedule'!DB12","v":0},{"$f":"'K90 - time schedule'!DC12","v":0},{"$f":"'K90 - time schedule'!DD12","v":0},{"$f":"'K90 - time schedule'!DE12","v":0},{"$f":"'K90 - time schedule'!DF12","v":0},{"$f":"'K90 - time schedule'!DG12","v":0},{"$f":"'K90 - time schedule'!DH12","v":0},{"$f":"'K90 - time schedule'!DI12","v":0},{"$f":"'K90 - time schedule'!DJ12","v":0},{"$f":"'K90 - time schedule'!DK12","v":0},{"$f":"'K90 - time schedule'!DL12","v":0},{"$f":"'K90 - time schedule'!DM12","v":0},{"$f":"'K90 - time schedule'!DN12","v":0},{"$f":"'K90 - time schedule'!DO12","v":0},{"$f":"'K90 - time schedule'!DP12","v":0},{"$f":"'K90 - time schedule'!DQ12","v":0},{"$f":"'K90 - time schedule'!DR12","v":0},{"$f":"'K90 - time schedule'!DS12","v":0},{"$f":"'K90 - time schedule'!DT12","v":0},{"$f":"'K90 - time schedule'!DU12","v":0},{"$f":"'K90 - time schedule'!DV12","v":0},{"$f":"'K90 - time schedule'!DW12","v":0},{"$f":"'K90 - time schedule'!DX12","v":0},{"$f":"'K90 - time schedule'!DY12","v":0},{"$f":"'K90 - time schedule'!DZ12","v":0},{"$f":"'K90 - time schedule'!EA12","v":0},{"$f":"'K90 - time schedule'!EB12","v":0},{"$f":"'K90 - time schedule'!EC12","v":0},{"$f":"'K90 - time schedule'!ED12","v":0},{"$f":"'K90 - time schedule'!EE12","v":0},{"$f":"'K90 - time schedule'!EF12","v":0},{"$f":"'K90 - time schedule'!EG12","v":0},{"$f":"'K90 - time schedule'!EH12","v":0},{"$f":"'K90 - time schedule'!EI12","v":0},{"$f":"'K90 - time schedule'!EJ12","v":0},{"$f":"'K90 - time schedule'!EK12","v":0},{"$f":"'K90 - time schedule'!EL12","v":0},{"$f":"'K90 - time schedule'!EM12","v":0},{"$f":"'K90 - time schedule'!EN12","v":0},{"$f":"'K90 - time schedule'!EO12","v":0},{"$f":"'K90 - time schedule'!EP12","v":0},{"$f":"'K90 - time schedule'!EQ12","v":0},{"$f":"'K90 - time schedule'!ER12","v":0},{"$f":"'K90 - time schedule'!ES12","v":0},{"$f":"'K90 - time schedule'!ET12","v":0},{"$f":"'K90 - time schedule'!EU12","v":0},{"$f":"'K90 - time schedule'!EV12","v":0},{"$f":"'K90 - time schedule'!EW12","v":0},{"$f":"'K90 - time schedule'!EX12","v":0},{"$f":"'K90 - time schedule'!EY12","v":0},{"$f":"'K90 - time schedule'!EZ12","v":0},{"$f":"'K90 - time schedule'!FA12","v":0},{"$f":"'K90 - time schedule'!FB12","v":0},{"$f":"'K90 - time schedule'!FC12","v":0},{"$f":"'K90 - time schedule'!FD12","v":0},{"$f":"'K90 - time schedule'!FE12","v":0},{"$f":"'K90 - time schedule'!FF12","v":0},{"$f":"'K90 - time schedule'!FG12","v":0},{"$f":"'K90 - time schedule'!FH12","v":0},{"$f":"'K90 - time schedule'!FI12","v":0},{"$f":"'K90 - time schedule'!FJ12","v":0},{"$f":"'K90 - time schedule'!FK12","v":0},{"$f":"'K90 - time schedule'!FL12","v":0},{"$f":"'K90 - time schedule'!FM12","v":0},{"$f":"'K90 - time schedule'!FN12","v":0},{"$f":"'K90 - time schedule'!FO12","v":0},{"$f":"'K90 - time schedule'!FP12","v":0},{"$f":"'K90 - time schedule'!FQ12","v":0},{"$f":"'K90 - time schedule'!FR12","v":0},{"$f":"'K90 - time schedule'!FS12","v":0},{"$f":"'K90 - time schedule'!FT12","v":0},{"$f":"'K90 - time schedule'!FU12","v":0},{"$f":"'K90 - time schedule'!FV12","v":0},{"$f":"'K90 - time schedule'!FW12","v":0},{"$f":"'K90 - time schedule'!FX12","v":0},{"$f":"'K90 - time schedule'!FY12","v":0},{"$f":"'K90 - time schedule'!FZ12","v":0},{"$f":"'K90 - time schedule'!GA12","v":0},{"$f":"'K90 - time schedule'!GB12","v":0},{"$f":"'K90 - time schedule'!GC12","v":0},{"$f":"'K90 - time schedule'!GD12","v":0},{"$f":"'K90 - time schedule'!GE12","v":0},{"$f":"'K90 - time schedule'!GF12","v":0},{"$f":"'K90 - time schedule'!GG12","v":0},{"$f":"'K90 - time schedule'!GH12","v":0},{"$f":"'K90 - time schedule'!GI12","v":0},{"$f":"'K90 - time schedule'!GJ12","v":0},{"$f":"'K90 - time schedule'!GK12","v":0},{"$f":"'K90 - time schedule'!GL12","v":0},{"$f":"'K90 - time schedule'!GM12","v":0},{"$f":"'K90 - time schedule'!GN12","v":0},{"$f":"'K90 - time schedule'!GO12","v":0},{"$f":"'K90 - time schedule'!GP12","v":0},{"$f":"'K90 - time schedule'!GQ12","v":0},{"$f":"'K90 - time schedule'!GR12","v":0},{"$f":"'K90 - time schedule'!GS12","v":0},{"$f":"'K90 - time schedule'!GT12","v":0},{"$f":"'K90 - time schedule'!GU12","v":0},{"$f":"'K90 - time schedule'!GV12","v":0},{"$f":"'K90 - time schedule'!GW12","v":0},{"$f":"'K90 - time schedule'!GX12","v":0},{"$f":"'K90 - time schedule'!GY12","v":0},{"$f":"'K90 - time schedule'!GZ12","v":0},{"$f":"'K90 - time schedule'!HA12","v":0},{"$f":"'K90 - time schedule'!HB12","v":0},{"$f":"'K90 - time schedule'!HC12","v":0},{"$f":"'K90 - time schedule'!HD12","v":0},{"$f":"'K90 - time schedule'!HE12","v":0},{"$f":"'K90 - time schedule'!HF12","v":0},{"$f":"'K90 - time schedule'!HG12","v":0},{"$f":"'K90 - time schedule'!HH12","v":0},{"$f":"'K90 - time schedule'!HI12","v":0},{"$f":"'K90 - time schedule'!HJ12","v":0},{"$f":"'K90 - time schedule'!HK12","v":0},{"$f":"'K90 - time schedule'!HL12","v":0},{"$f":"'K90 - time schedule'!HM12","v":0},{"$f":"'K90 - time schedule'!HN12","v":0},{"$f":"'K90 - time schedule'!HO12","v":0},{"$f":"'K90 - time schedule'!HP12","v":0},{"$f":"'K90 - time schedule'!HQ12","v":0},{"$f":"'K90 - time schedule'!HR12","v":0},{"$f":"'K90 - time schedule'!HS12","v":0},{"$f":"'K90 - time schedule'!HT12","v":0},{"$f":"'K90 - time schedule'!HU12","v":0},{"$f":"'K90 - time schedule'!HV12","v":0},{"$f":"'K90 - time schedule'!HW12","v":0},{"$f":"'K90 - time schedule'!HX12","v":0},{"$f":"'K90 - time schedule'!HY12","v":0},{"$f":"'K90 - time schedule'!HZ12","v":0},{"$f":"'K90 - time schedule'!IA12","v":0},{"$f":"'K90 - time schedule'!IB12","v":0},{"$f":"'K90 - time schedule'!IC12","v":0},{"$f":"'K90 - time schedule'!ID12","v":0},{"$f":"'K90 - time schedule'!IE12","v":0},{"$f":"'K90 - time schedule'!IF12","v":0},{"$f":"'K90 - time schedule'!IG12","v":0},{"$f":"'K90 - time schedule'!IH12","v":0},{"$f":"'K90 - time schedule'!II12","v":0},{"$f":"'K90 - time schedule'!IJ12","v":0},{"$f":"'K90 - time schedule'!IK12","v":0},{"$f":"'K90 - time schedule'!IL12","v":0},{"$f":"'K90 - time schedule'!IM12","v":0},{"$f":"'K90 - time schedule'!IN12","v":0},{"$f":"'K90 - time schedule'!IO12","v":0},{"$f":"'K90 - time schedule'!IP12","v":0},{"$f":"'K90 - time schedule'!IQ12","v":0},{"$f":"'K90 - time schedule'!IR12","v":0},{"$f":"'K90 - time schedule'!IS12","v":0},{"$f":"'K90 - time schedule'!IT12","v":0},{"$f":"'K90 - time schedule'!IU12","v":0},{"$f":"'K90 - time schedule'!IV12","v":0},{"$f":"'K90 - time schedule'!IW12","v":0},{"$f":"'K90 - time schedule'!IX12","v":0},{"$f":"'K90 - time schedule'!IY12","v":0},{"$f":"'K90 - time schedule'!IZ12","v":0},{"$f":"'K90 - time schedule'!JA12","v":0},{"$f":"'K90 - time schedule'!JB12","v":0},{"$f":"'K90 - time schedule'!JC12","v":0},{"$f":"'K90 - time schedule'!JD12","v":0},{"$f":"'K90 - time schedule'!JE12","v":0},{"$f":"'K90 - time schedule'!JF12","v":0},{"$f":"'K90 - time schedule'!JG12","v":0},{"$f":"'K90 - time schedule'!JH12","v":0},{"$f":"'K90 - time schedule'!JI12","v":0},{"$f":"'K90 - time schedule'!JJ12","v":0},{"$f":"'K90 - time schedule'!JK12","v":0},{"$f":"'K90 - time schedule'!JL12","v":0},{"$f":"'K90 - time schedule'!JM12","v":0},{"$f":"'K90 - time schedule'!JN12","v":0},{"$f":"'K90 - time schedule'!JO12","v":0},{"$f":"'K90 - time schedule'!JP12","v":0},{"$f":"'K90 - time schedule'!JQ12","v":0},{"$f":"'K90 - time schedule'!JR12","v":0},{"$f":"'K90 - time schedule'!JS12","v":0},{"$f":"'K90 - time schedule'!JT12","v":0},{"$f":"'K90 - time schedule'!JU12","v":0},{"$f":"'K90 - time schedule'!JV12","v":0},{"$f":"'K90 - time schedule'!JW12","v":0},{"$f":"'K90 - time schedule'!JX12","v":0},{"$f":"'K90 - time schedule'!JY12","v":0},{"$f":"'K90 - time schedule'!JZ12","v":0},{"$f":"'K90 - time schedule'!KA12","v":0},{"$f":"'K90 - time schedule'!KB12","v":0},{"$f":"'K90 - time schedule'!KC12","v":0},{"$f":"'K90 - time schedule'!KD12","v":0},{"$f":"'K90 - time schedule'!KE12","v":0},{"$f":"'K90 - time schedule'!KF12","v":0},{"$f":"'K90 - time schedule'!KG12","v":0},{"$f":"'K90 - time schedule'!KH12","v":0},{"$f":"'K90 - time schedule'!KI12","v":0},{"$f":"'K90 - time schedule'!KJ12","v":0},{"$f":"'K90 - time schedule'!KK12","v":0},{"$f":"'K90 - time schedule'!KL12","v":0},{"$f":"'K90 - time schedule'!KM12","v":0},{"$f":"'K90 - time schedule'!KN12","v":0},{"$f":"'K90 - time schedule'!KO12","v":0},{"$f":"'K90 - time schedule'!KP12","v":0},{"$f":"'K90 - time schedule'!KQ12","v":0},{"$f":"'K90 - time schedule'!KR12","v":0},{"$f":"'K90 - time schedule'!KS12","v":0},{"$f":"'K90 - time schedule'!KT12","v":0}]
["Boiler room K90 - binding technical specification for other OBs, for other suppliers of technological units ","K90",{"$f":"'K90 - time schedule'!G14","v":0},{"$f":"'K90 - time schedule'!H14","v":0},{"$f":"'K90 - time schedule'!I14","v":0},{"$f":"'K90 - time schedule'!J14","v":0},{"$f":"'K90 - time schedule'!K14","v":0},{"$f":"'K90 - time schedule'!L14","v":0},{"$f":"'K90 - time schedule'!M14","v":0},{"$f":"'K90 - time schedule'!N14","v":0},{"$f":"'K90 - time schedule'!O14","v":0},{"$f":"'K90 - time schedule'!P14","v":0},{"$f":"'K90 - time schedule'!Q14","v":0},{"$f":"'K90 - time schedule'!R14","v":0},{"$f":"'K90 - time schedule'!S14","v":0},{"$f":"'K90 - time schedule'!T14","v":0},{"$f":"'K90 - time schedule'!U14","v":0},{"$f":"'K90 - time schedule'!V14","v":0},{"$f":"'K90 - time schedule'!W14","v":0},{"$f":"'K90 - time schedule'!X14","v":0},{"$f":"'K90 - time schedule'!Y14","v":0},{"$f":"'K90 - time schedule'!Z14","v":0},{"$f":"'K90 - time schedule'!AA14","v":0},{"$f":"'K90 - time schedule'!AB14","v":0},{"$f":"'K90 - time schedule'!AC14","v":0},{"$f":"'K90 - time schedule'!AD14","v":0},{"$f":"'K90 - time schedule'!AE14","v":0},{"$f":"'K90 - time schedule'!AF14","v":0},{"$f":"'K90 - time schedule'!AG14","v":0},{"$f":"'K90 - time schedule'!AH14","v":0},{"$f":"'K90 - time schedule'!AI14","v":0},{"$f":"'K90 - time schedule'!AJ14","v":0},{"$f":"'K90 - time schedule'!AK14","v":0},{"$f":"'K90 - time schedule'!AL14","v":0},{"$f":"'K90 - time schedule'!AM14","v":0},{"$f":"'K90 - time schedule'!AN14","v":0},{"$f":"'K90 - time schedule'!AO14","v":0},{"$f":"'K90 - time schedule'!AP14","v":0},{"$f":"'K90 - time schedule'!AQ14","v":0},{"$f":"'K90 - time schedule'!AR14","v":0},{"$f":"'K90 - time schedule'!AS14","v":0},{"$f":"'K90 - time schedule'!AT14","v":0},{"$f":"'K90 - time schedule'!AU14","v":0},{"$f":"'K90 - time schedule'!AV14","v":0},{"$f":"'K90 - time schedule'!AW14","v":0},{"$f":"'K90 - time schedule'!AX14","v":0},{"$f":"'K90 - time schedule'!AY14","v":0},{"$f":"'K90 - time schedule'!AZ14","v":0},{"$f":"'K90 - time schedule'!BA14","v":0},{"$f":"'K90 - time schedule'!BB14","v":0},{"$f":"'K90 - time schedule'!BC14","v":0},{"$f":"'K90 - time schedule'!BD14","v":0},{"$f":"'K90 - time schedule'!BE14","v":0},{"$f":"'K90 - time schedule'!BF14","v":0},{"$f":"'K90 - time schedule'!BG14","v":0},{"$f":"'K90 - time schedule'!BH14","v":0},{"$f":"'K90 - time schedule'!BI14","v":0},{"$f":"'K90 - time schedule'!BJ14","v":0},{"$f":"'K90 - time schedule'!BK14","v":0},{"$f":"'K90 - time schedule'!BL14","v":0},{"$f":"'K90 - time schedule'!BM14","v":0},{"$f":"'K90 - time schedule'!BN14","v":0},{"$f":"'K90 - time schedule'!BO14","v":0},{"$f":"'K90 - time schedule'!BP14","v":0},{"$f":"'K90 - time schedule'!BQ14","v":0},{"$f":"'K90 - time schedule'!BR14","v":0},{"$f":"'K90 - time schedule'!BS14","v":0},{"$f":"'K90 - time schedule'!BT14","v":0},{"$f":"'K90 - time schedule'!BU14","v":0},{"$f":"'K90 - time schedule'!BV14","v":0},{"$f":"'K90 - time schedule'!BW14","v":0},{"$f":"'K90 - time schedule'!BX14","v":0},{"$f":"'K90 - time schedule'!BY14","v":0},{"$f":"'K90 - time schedule'!BZ14","v":0},{"$f":"'K90 - time schedule'!CA14","v":0},{"$f":"'K90 - time schedule'!CB14","v":0},{"$f":"'K90 - time schedule'!CC14","v":0},{"$f":"'K90 - time schedule'!CD14","v":0},{"$f":"'K90 - time schedule'!CE14","v":0},{"$f":"'K90 - time schedule'!CF14","v":0},{"$f":"'K90 - time schedule'!CG14","v":0},{"$f":"'K90 - time schedule'!CH14","v":0},{"$f":"'K90 - time schedule'!CI14","v":0},{"$f":"'K90 - time schedule'!CJ14","v":0},{"$f":"'K90 - time schedule'!CK14","v":0},{"$f":"'K90 - time schedule'!CL14","v":0},{"$f":"'K90 - time schedule'!CM14","v":0},{"$f":"'K90 - time schedule'!CN14","v":0},{"$f":"'K90 - time schedule'!CO14","v":0},{"$f":"'K90 - time schedule'!CP14","v":0},{"$f":"'K90 - time schedule'!CQ14","v":0},{"$f":"'K90 - time schedule'!CR14","v":0},{"$f":"'K90 - time schedule'!CS14","v":0},{"$f":"'K90 - time schedule'!CT14","v":0},{"$f":"'K90 - time schedule'!CU14","v":0},{"$f":"'K90 - time schedule'!CV14","v":0},{"$f":"'K90 - time schedule'!CW14","v":0},{"$f":"'K90 - time schedule'!CX14","v":0},{"$f":"'K90 - time schedule'!CY14","v":0},{"$f":"'K90 - time schedule'!CZ14","v":0},{"$f":"'K90 - time schedule'!DA14","v":0},{"$f":"'K90 - time schedule'!DB14","v":0},{"$f":"'K90 - time schedule'!DC14","v":0},{"$f":"'K90 - time schedule'!DD14","v":0},{"$f":"'K90 - time schedule'!DE14","v":0},{"$f":"'K90 - time schedule'!DF14","v":0},{"$f":"'K90 - time schedule'!DG14","v":0},{"$f":"'K90 - time schedule'!DH14","v":0},{"$f":"'K90 - time schedule'!DI14","v":0},{"$f":"'K90 - time schedule'!DJ14","v":0},{"$f":"'K90 - time schedule'!DK14","v":0},{"$f":"'K90 - time schedule'!DL14","v":0},{"$f":"'K90 - time schedule'!DM14","v":0},{"$f":"'K90 - time schedule'!DN14","v":0},{"$f":"'K90 - time schedule'!DO14","v":0},{"$f":"'K90 - time schedule'!DP14","v":0},{"$f":"'K90 - time schedule'!DQ14","v":0},{"$f":"'K90 - time schedule'!DR14","v":0},{"$f":"'K90 - time schedule'!DS14","v":0},{"$f":"'K90 - time schedule'!DT14","v":0},{"$f":"'K90 - time schedule'!DU14","v":0},{"$f":"'K90 - time schedule'!DV14","v":0},{"$f":"'K90 - time schedule'!DW14","v":0},{"$f":"'K90 - time schedule'!DX14","v":0},{"$f":"'K90 - time schedule'!DY14","v":0},{"$f":"'K90 - time schedule'!DZ14","v":0},{"$f":"'K90 - time schedule'!EA14","v":0},{"$f":"'K90 - time schedule'!EB14","v":0},{"$f":"'K90 - time schedule'!EC14","v":0},{"$f":"'K90 - time schedule'!ED14","v":0},{"$f":"'K90 - time schedule'!EE14","v":0},{"$f":"'K90 - time schedule'!EF14","v":0},{"$f":"'K90 - time schedule'!EG14","v":0},{"$f":"'K90 - time schedule'!EH14","v":0},{"$f":"'K90 - time schedule'!EI14","v":0},{"$f":"'K90 - time schedule'!EJ14","v":0},{"$f":"'K90 - time schedule'!EK14","v":0},{"$f":"'K90 - time schedule'!EL14","v":0},{"$f":"'K90 - time schedule'!EM14","v":0},{"$f":"'K90 - time schedule'!EN14","v":0},{"$f":"'K90 - time schedule'!EO14","v":0},{"$f":"'K90 - time schedule'!EP14","v":0},{"$f":"'K90 - time schedule'!EQ14","v":0},{"$f":"'K90 - time schedule'!ER14","v":0},{"$f":"'K90 - time schedule'!ES14","v":0},{"$f":"'K90 - time schedule'!ET14","v":0},{"$f":"'K90 - time schedule'!EU14","v":0},{"$f":"'K90 - time schedule'!EV14","v":0},{"$f":"'K90 - time schedule'!EW14","v":0},{"$f":"'K90 - time schedule'!EX14","v":0},{"$f":"'K90 - time schedule'!EY14","v":0},{"$f":"'K90 - time schedule'!EZ14","v":0},{"$f":"'K90 - time schedule'!FA14","v":0},{"$f":"'K90 - time schedule'!FB14","v":0},{"$f":"'K90 - time schedule'!FC14","v":0},{"$f":"'K90 - time schedule'!FD14","v":0},{"$f":"'K90 - time schedule'!FE14","v":0},{"$f":"'K90 - time schedule'!FF14","v":0},{"$f":"'K90 - time schedule'!FG14","v":0},{"$f":"'K90 - time schedule'!FH14","v":0},{"$f":"'K90 - time schedule'!FI14","v":0},{"$f":"'K90 - time schedule'!FJ14","v":0},{"$f":"'K90 - time schedule'!FK14","v":0},{"$f":"'K90 - time schedule'!FL14","v":0},{"$f":"'K90 - time schedule'!FM14","v":0},{"$f":"'K90 - time schedule'!FN14","v":0},{"$f":"'K90 - time schedule'!FO14","v":0},{"$f":"'K90 - time schedule'!FP14","v":0},{"$f":"'K90 - time schedule'!FQ14","v":0},{"$f":"'K90 - time schedule'!FR14","v":0},{"$f":"'K90 - time schedule'!FS14","v":0},{"$f":"'K90 - time schedule'!FT14","v":0},{"$f":"'K90 - time schedule'!FU14","v":0},{"$f":"'K90 - time schedule'!FV14","v":0},{"$f":"'K90 - time schedule'!FW14","v":0},{"$f":"'K90 - time schedule'!FX14","v":0},{"$f":"'K90 - time schedule'!FY14","v":0},{"$f":"'K90 - time schedule'!FZ14","v":0},{"$f":"'K90 - time schedule'!GA14","v":0},{"$f":"'K90 - time schedule'!GB14","v":0},{"$f":"'K90 - time schedule'!GC14","v":0},{"$f":"'K90 - time schedule'!GD14","v":0},{"$f":"'K90 - time schedule'!GE14","v":0},{"$f":"'K90 - time schedule'!GF14","v":0},{"$f":"'K90 - time schedule'!GG14","v":0},{"$f":"'K90 - time schedule'!GH14","v":0},{"$f":"'K90 - time schedule'!GI14","v":0},{"$f":"'K90 - time schedule'!GJ14","v":0},{"$f":"'K90 - time schedule'!GK14","v":0},{"$f":"'K90 - time schedule'!GL14","v":0},{"$f":"'K90 - time schedule'!GM14","v":0},{"$f":"'K90 - time schedule'!GN14","v":0},{"$f":"'K90 - time schedule'!GO14","v":0},{"$f":"'K90 - time schedule'!GP14","v":0},{"$f":"'K90 - time schedule'!GQ14","v":0},{"$f":"'K90 - time schedule'!GR14","v":0},{"$f":"'K90 - time schedule'!GS14","v":0},{"$f":"'K90 - time schedule'!GT14","v":0},{"$f":"'K90 - time schedule'!GU14","v":0},{"$f":"'K90 - time schedule'!GV14","v":0},{"$f":"'K90 - time schedule'!GW14","v":0},{"$f":"'K90 - time schedule'!GX14","v":0},{"$f":"'K90 - time schedule'!GY14","v":0},{"$f":"'K90 - time schedule'!GZ14","v":0},{"$f":"'K90 - time schedule'!HA14","v":0},{"$f":"'K90 - time schedule'!HB14","v":0},{"$f":"'K90 - time schedule'!HC14","v":0},{"$f":"'K90 - time schedule'!HD14","v":0},{"$f":"'K90 - time schedule'!HE14","v":0},{"$f":"'K90 - time schedule'!HF14","v":0},{"$f":"'K90 - time schedule'!HG14","v":0},{"$f":"'K90 - time schedule'!HH14","v":0},{"$f":"'K90 - time schedule'!HI14","v":0},{"$f":"'K90 - time schedule'!HJ14","v":0},{"$f":"'K90 - time schedule'!HK14","v":0},{"$f":"'K90 - time schedule'!HL14","v":0},{"$f":"'K90 - time schedule'!HM14","v":0},{"$f":"'K90 - time schedule'!HN14","v":0},{"$f":"'K90 - time schedule'!HO14","v":0},{"$f":"'K90 - time schedule'!HP14","v":0},{"$f":"'K90 - time schedule'!HQ14","v":0},{"$f":"'K90 - time schedule'!HR14","v":0},{"$f":"'K90 - time schedule'!HS14","v":0},{"$f":"'K90 - time schedule'!HT14","v":0},{"$f":"'K90 - time schedule'!HU14","v":0},{"$f":"'K90 - time schedule'!HV14","v":0},{"$f":"'K90 - time schedule'!HW14","v":0},{"$f":"'K90 - time schedule'!HX14","v":0},{"$f":"'K90 - time schedule'!HY14","v":0},{"$f":"'K90 - time schedule'!HZ14","v":0},{"$f":"'K90 - time schedule'!IA14","v":0},{"$f":"'K90 - time schedule'!IB14","v":0},{"$f":"'K90 - time schedule'!IC14","v":0},{"$f":"'K90 - time schedule'!ID14","v":0},{"$f":"'K90 - time schedule'!IE14","v":0},{"$f":"'K90 - time schedule'!IF14","v":0},{"$f":"'K90 - time schedule'!IG14","v":0},{"$f":"'K90 - time schedule'!IH14","v":0},{"$f":"'K90 - time schedule'!II14","v":0},{"$f":"'K90 - time schedule'!IJ14","v":0},{"$f":"'K90 - time schedule'!IK14","v":0},{"$f":"'K90 - time schedule'!IL14","v":0},{"$f":"'K90 - time schedule'!IM14","v":0},{"$f":"'K90 - time schedule'!IN14","v":0},{"$f":"'K90 - time schedule'!IO14","v":0},{"$f":"'K90 - time schedule'!IP14","v":0},{"$f":"'K90 - time schedule'!IQ14","v":0},{"$f":"'K90 - time schedule'!IR14","v":0},{"$f":"'K90 - time schedule'!IS14","v":0},{"$f":"'K90 - time schedule'!IT14","v":0},{"$f":"'K90 - time schedule'!IU14","v":0},{"$f":"'K90 - time schedule'!IV14","v":0},{"$f":"'K90 - time schedule'!IW14","v":0},{"$f":"'K90 - time schedule'!IX14","v":0},{"$f":"'K90 - time schedule'!IY14","v":0},{"$f":"'K90 - time schedule'!IZ14","v":0},{"$f":"'K90 - time schedule'!JA14","v":0},{"$f":"'K90 - time schedule'!JB14","v":0},{"$f":"'K90 - time schedule'!JC14","v":0},{"$f":"'K90 - time schedule'!JD14","v":0},{"$f":"'K90 - time schedule'!JE14","v":0},{"$f":"'K90 - time schedule'!JF14","v":0},{"$f":"'K90 - time schedule'!JG14","v":0},{"$f":"'K90 - time schedule'!JH14","v":0},{"$f":"'K90 - time schedule'!JI14","v":0},{"$f":"'K90 - time schedule'!JJ14","v":0},{"$f":"'K90 - time schedule'!JK14","v":0},{"$f":"'K90 - time schedule'!JL14","v":0},{"$f":"'K90 - time schedule'!JM14","v":0},{"$f":"'K90 - time schedule'!JN14","v":0},{"$f":"'K90 - time schedule'!JO14","v":0},{"$f":"'K90 - time schedule'!JP14","v":0},{"$f":"'K90 - time schedule'!JQ14","v":0},{"$f":"'K90 - time schedule'!JR14","v":0},{"$f":"'K90 - time schedule'!JS14","v":0},{"$f":"'K90 - time schedule'!JT14","v":0},{"$f":"'K90 - time schedule'!JU14","v":0},{"$f":"'K90 - time schedule'!JV14","v":0},{"$f":"'K90 - time schedule'!JW14","v":0},{"$f":"'K90 - time schedule'!JX14","v":0},{"$f":"'K90 - time schedule'!JY14","v":0},{"$f":"'K90 - time schedule'!JZ14","v":0},{"$f":"'K90 - time schedule'!KA14","v":0},{"$f":"'K90 - time schedule'!KB14","v":0},{"$f":"'K90 - time schedule'!KC14","v":0},{"$f":"'K90 - time schedule'!KD14","v":0},{"$f":"'K90 - time schedule'!KE14","v":0},{"$f":"'K90 - time schedule'!KF14","v":0},{"$f":"'K90 - time schedule'!KG14","v":0},{"$f":"'K90 - time schedule'!KH14","v":0},{"$f":"'K90 - time schedule'!KI14","v":0},{"$f":"'K90 - time schedule'!KJ14","v":0},{"$f":"'K90 - time schedule'!KK14","v":0},{"$f":"'K90 - time schedule'!KL14","v":0},{"$f":"'K90 - time schedule'!KM14","v":0},{"$f":"'K90 - time schedule'!KN14","v":0},{"$f":"'K90 - time schedule'!KO14","v":0},{"$f":"'K90 - time schedule'!KP14","v":0},{"$f":"'K90 - time schedule'!KQ14","v":0},{"$f":"'K90 - time schedule'!KR14","v":0},{"$f":"'K90 - time schedule'!KS14","v":0},{"$f":"'K90 - time schedule'!KT14","v":0}]
["Boiler room K90 - approved implementation documentation","K90",{"$f":"'K90 - time schedule'!G16","v":0},{"$f":"'K90 - time schedule'!H16","v":0},{"$f":"'K90 - time schedule'!I16","v":0},{"$f":"'K90 - time schedule'!J16","v":0},{"$f":"'K90 - time schedule'!K16","v":0},{"$f":"'K90 - time schedule'!L16","v":0},{"$f":"'K90 - time schedule'!M16","v":0},{"$f":"'K90 - time schedule'!N16","v":0},{"$f":"'K90 - time schedule'!O16","v":0},{"$f":"'K90 - time schedule'!P16","v":0},{"$f":"'K90 - time schedule'!Q16","v":0},{"$f":"'K90 - time schedule'!R16","v":0},{"$f":"'K90 - time schedule'!S16","v":0},{"$f":"'K90 - time schedule'!T16","v":0},{"$f":"'K90 - time schedule'!U16","v":0},{"$f":"'K90 - time schedule'!V16","v":0},{"$f":"'K90 - time schedule'!W16","v":0},{"$f":"'K90 - time schedule'!X16","v":0},{"$f":"'K90 - time schedule'!Y16","v":0},{"$f":"'K90 - time schedule'!Z16","v":0},{"$f":"'K90 - time schedule'!AA16","v":0},{"$f":"'K90 - time schedule'!AB16","v":0},{"$f":"'K90 - time schedule'!AC16","v":0},{"$f":"'K90 - time schedule'!AD16","v":0},{"$f":"'K90 - time schedule'!AE16","v":0},{"$f":"'K90 - time schedule'!AF16","v":0},{"$f":"'K90 - time schedule'!AG16","v":0},{"$f":"'K90 - time schedule'!AH16","v":0},{"$f":"'K90 - time schedule'!AI16","v":0},{"$f":"'K90 - time schedule'!AJ16","v":0},{"$f":"'K90 - time schedule'!AK16","v":0},{"$f":"'K90 - time schedule'!AL16","v":0},{"$f":"'K90 - time schedule'!AM16","v":0},{"$f":"'K90 - time schedule'!AN16","v":0},{"$f":"'K90 - time schedule'!AO16","v":0},{"$f":"'K90 - time schedule'!AP16","v":0},{"$f":"'K90 - time schedule'!AQ16","v":0},{"$f":"'K90 - time schedule'!AR16","v":0},{"$f":"'K90 - time schedule'!AS16","v":0},{"$f":"'K90 - time schedule'!AT16","v":0},{"$f":"'K90 - time schedule'!AU16","v":0},{"$f":"'K90 - time schedule'!AV16","v":0},{"$f":"'K90 - time schedule'!AW16","v":0},{"$f":"'K90 - time schedule'!AX16","v":0},{"$f":"'K90 - time schedule'!AY16","v":0},{"$f":"'K90 - time schedule'!AZ16","v":0},{"$f":"'K90 - time schedule'!BA16","v":0},{"$f":"'K90 - time schedule'!BB16","v":0},{"$f":"'K90 - time schedule'!BC16","v":0},{"$f":"'K90 - time schedule'!BD16","v":0},{"$f":"'K90 - time schedule'!BE16","v":0},{"$f":"'K90 - time schedule'!BF16","v":0},{"$f":"'K90 - time schedule'!BG16","v":0},{"$f":"'K90 - time schedule'!BH16","v":0},{"$f":"'K90 - time schedule'!BI16","v":0},{"$f":"'K90 - time schedule'!BJ16","v":0},{"$f":"'K90 - time schedule'!BK16","v":0},{"$f":"'K90 - time schedule'!BL16","v":0},{"$f":"'K90 - time schedule'!BM16","v":0},{"$f":"'K90 - time schedule'!BN16","v":0},{"$f":"'K90 - time schedule'!BO16","v":0},{"$f":"'K90 - time schedule'!BP16","v":0},{"$f":"'K90 - time schedule'!BQ16","v":0},{"$f":"'K90 - time schedule'!BR16","v":0},{"$f":"'K90 - time schedule'!BS16","v":0},{"$f":"'K90 - time schedule'!BT16","v":0},{"$f":"'K90 - time schedule'!BU16","v":0},{"$f":"'K90 - time schedule'!BV16","v":0},{"$f":"'K90 - time schedule'!BW16","v":0},{"$f":"'K90 - time schedule'!BX16","v":0},{"$f":"'K90 - time schedule'!BY16","v":0},{"$f":"'K90 - time schedule'!BZ16","v":0},{"$f":"'K90 - time schedule'!CA16","v":0},{"$f":"'K90 - time schedule'!CB16","v":0},{"$f":"'K90 - time schedule'!CC16","v":0},{"$f":"'K90 - time schedule'!CD16","v":0},{"$f":"'K90 - time schedule'!CE16","v":0},{"$f":"'K90 - time schedule'!CF16","v":0},{"$f":"'K90 - time schedule'!CG16","v":0},{"$f":"'K90 - time schedule'!CH16","v":0},{"$f":"'K90 - time schedule'!CI16","v":0},{"$f":"'K90 - time schedule'!CJ16","v":0},{"$f":"'K90 - time schedule'!CK16","v":0},{"$f":"'K90 - time schedule'!CL16","v":0},{"$f":"'K90 - time schedule'!CM16","v":0},{"$f":"'K90 - time schedule'!CN16","v":0},{"$f":"'K90 - time schedule'!CO16","v":0},{"$f":"'K90 - time schedule'!CP16","v":0},{"$f":"'K90 - time schedule'!CQ16","v":0},{"$f":"'K90 - time schedule'!CR16","v":0},{"$f":"'K90 - time schedule'!CS16","v":0},{"$f":"'K90 - time schedule'!CT16","v":0},{"$f":"'K90 - time schedule'!CU16","v":0},{"$f":"'K90 - time schedule'!CV16","v":0},{"$f":"'K90 - time schedule'!CW16","v":0},{"$f":"'K90 - time schedule'!CX16","v":0},{"$f":"'K90 - time schedule'!CY16","v":0},{"$f":"'K90 - time schedule'!CZ16","v":0},{"$f":"'K90 - time schedule'!DA16","v":0},{"$f":"'K90 - time schedule'!DB16","v":0},{"$f":"'K90 - time schedule'!DC16","v":0},{"$f":"'K90 - time schedule'!DD16","v":0},{"$f":"'K90 - time schedule'!DE16","v":0},{"$f":"'K90 - time schedule'!DF16","v":0},{"$f":"'K90 - time schedule'!DG16","v":0},{"$f":"'K90 - time schedule'!DH16","v":0},{"$f":"'K90 - time schedule'!DI16","v":0},{"$f":"'K90 - time schedule'!DJ16","v":0},{"$f":"'K90 - time schedule'!DK16","v":0},{"$f":"'K90 - time schedule'!DL16","v":0},{"$f":"'K90 - time schedule'!DM16","v":0},{"$f":"'K90 - time schedule'!DN16","v":0},{"$f":"'K90 - time schedule'!DO16","v":0},{"$f":"'K90 - time schedule'!DP16","v":0},{"$f":"'K90 - time schedule'!DQ16","v":0},{"$f":"'K90 - time schedule'!DR16","v":0},{"$f":"'K90 - time schedule'!DS16","v":0},{"$f":"'K90 - time schedule'!DT16","v":0},{"$f":"'K90 - time schedule'!DU16","v":0},{"$f":"'K90 - time schedule'!DV16","v":0},{"$f":"'K90 - time schedule'!DW16","v":0},{"$f":"'K90 - time schedule'!DX16","v":0},{"$f":"'K90 - time schedule'!DY16","v":0},{"$f":"'K90 - time schedule'!DZ16","v":0},{"$f":"'K90 - time schedule'!EA16","v":0},{"$f":"'K90 - time schedule'!EB16","v":0},{"$f":"'K90 - time schedule'!EC16","v":0},{"$f":"'K90 - time schedule'!ED16","v":0},{"$f":"'K90 - time schedule'!EE16","v":0},{"$f":"'K90 - time schedule'!EF16","v":0},{"$f":"'K90 - time schedule'!EG16","v":0},{"$f":"'K90 - time schedule'!EH16","v":0},{"$f":"'K90 - time schedule'!EI16","v":0},{"$f":"'K90 - time schedule'!EJ16","v":0},{"$f":"'K90 - time schedule'!EK16","v":0},{"$f":"'K90 - time schedule'!EL16","v":0},{"$f":"'K90 - time schedule'!EM16","v":0},{"$f":"'K90 - time schedule'!EN16","v":0},{"$f":"'K90 - time schedule'!EO16","v":0},{"$f":"'K90 - time schedule'!EP16","v":0},{"$f":"'K90 - time schedule'!EQ16","v":0},{"$f":"'K90 - time schedule'!ER16","v":0},{"$f":"'K90 - time schedule'!ES16","v":0},{"$f":"'K90 - time schedule'!ET16","v":0},{"$f":"'K90 - time schedule'!EU16","v":0},{"$f":"'K90 - time schedule'!EV16","v":0},{"$f":"'K90 - time schedule'!EW16","v":0},{"$f":"'K90 - time schedule'!EX16","v":0},{"$f":"'K90 - time schedule'!EY16","v":0},{"$f":"'K90 - time schedule'!EZ16","v":0},{"$f":"'K90 - time schedule'!FA16","v":0},{"$f":"'K90 - time schedule'!FB16","v":0},{"$f":"'K90 - time schedule'!FC16","v":0},{"$f":"'K90 - time schedule'!FD16","v":0},{"$f":"'K90 - time schedule'!FE16","v":0},{"$f":"'K90 - time schedule'!FF16","v":0},{"$f":"'K90 - time schedule'!FG16","v":0},{"$f":"'K90 - time schedule'!FH16","v":0},{"$f":"'K90 - time schedule'!FI16","v":0},{"$f":"'K90 - time schedule'!FJ16","v":0},{"$f":"'K90 - time schedule'!FK16","v":0},{"$f":"'K90 - time schedule'!FL16","v":0},{"$f":"'K90 - time schedule'!FM16","v":0},{"$f":"'K90 - time schedule'!FN16","v":0},{"$f":"'K90 - time schedule'!FO16","v":0},{"$f":"'K90 - time schedule'!FP16","v":0},{"$f":"'K90 - time schedule'!FQ16","v":0},{"$f":"'K90 - time schedule'!FR16","v":0},{"$f":"'K90 - time schedule'!FS16","v":0},{"$f":"'K90 - time schedule'!FT16","v":0},{"$f":"'K90 - time schedule'!FU16","v":0},{"$f":"'K90 - time schedule'!FV16","v":0},{"$f":"'K90 - time schedule'!FW16","v":0},{"$f":"'K90 - time schedule'!FX16","v":0},{"$f":"'K90 - time schedule'!FY16","v":0},{"$f":"'K90 - time schedule'!FZ16","v":0},{"$f":"'K90 - time schedule'!GA16","v":0},{"$f":"'K90 - time schedule'!GB16","v":0},{"$f":"'K90 - time schedule'!GC16","v":0},{"$f":"'K90 - time schedule'!GD16","v":0},{"$f":"'K90 - time schedule'!GE16","v":0},{"$f":"'K90 - time schedule'!GF16","v":0},{"$f":"'K90 - time schedule'!GG16","v":0},{"$f":"'K90 - time schedule'!GH16","v":0},{"$f":"'K90 - time schedule'!GI16","v":0},{"$f":"'K90 - time schedule'!GJ16","v":0},{"$f":"'K90 - time schedule'!GK16","v":0},{"$f":"'K90 - time schedule'!GL16","v":0},{"$f":"'K90 - time schedule'!GM16","v":0},{"$f":"'K90 - time schedule'!GN16","v":0},{"$f":"'K90 - time schedule'!GO16","v":0},{"$f":"'K90 - time schedule'!GP16","v":0},{"$f":"'K90 - time schedule'!GQ16","v":0},{"$f":"'K90 - time schedule'!GR16","v":0},{"$f":"'K90 - time schedule'!GS16","v":0},{"$f":"'K90 - time schedule'!GT16","v":0},{"$f":"'K90 - time schedule'!GU16","v":0},{"$f":"'K90 - time schedule'!GV16","v":0},{"$f":"'K90 - time schedule'!GW16","v":0},{"$f":"'K90 - time schedule'!GX16","v":0},{"$f":"'K90 - time schedule'!GY16","v":0},{"$f":"'K90 - time schedule'!GZ16","v":0},{"$f":"'K90 - time schedule'!HA16","v":0},{"$f":"'K90 - time schedule'!HB16","v":0},{"$f":"'K90 - time schedule'!HC16","v":0},{"$f":"'K90 - time schedule'!HD16","v":0},{"$f":"'K90 - time schedule'!HE16","v":0},{"$f":"'K90 - time schedule'!HF16","v":0},{"$f":"'K90 - time schedule'!HG16","v":0},{"$f":"'K90 - time schedule'!HH16","v":0},{"$f":"'K90 - time schedule'!HI16","v":0},{"$f":"'K90 - time schedule'!HJ16","v":0},{"$f":"'K90 - time schedule'!HK16","v":0},{"$f":"'K90 - time schedule'!HL16","v":0},{"$f":"'K90 - time schedule'!HM16","v":0},{"$f":"'K90 - time schedule'!HN16","v":0},{"$f":"'K90 - time schedule'!HO16","v":0},{"$f":"'K90 - time schedule'!HP16","v":0},{"$f":"'K90 - time schedule'!HQ16","v":0},{"$f":"'K90 - time schedule'!HR16","v":0},{"$f":"'K90 - time schedule'!HS16","v":0},{"$f":"'K90 - time schedule'!HT16","v":0},{"$f":"'K90 - time schedule'!HU16","v":0},{"$f":"'K90 - time schedule'!HV16","v":0},{"$f":"'K90 - time schedule'!HW16","v":0},{"$f":"'K90 - time schedule'!HX16","v":0},{"$f":"'K90 - time schedule'!HY16","v":0},{"$f":"'K90 - time schedule'!HZ16","v":0},{"$f":"'K90 - time schedule'!IA16","v":0},{"$f":"'K90 - time schedule'!IB16","v":0},{"$f":"'K90 - time schedule'!IC16","v":0},{"$f":"'K90 - time schedule'!ID16","v":0},{"$f":"'K90 - time schedule'!IE16","v":0},{"$f":"'K90 - time schedule'!IF16","v":0},{"$f":"'K90 - time schedule'!IG16","v":0},{"$f":"'K90 - time schedule'!IH16","v":0},{"$f":"'K90 - time schedule'!II16","v":0},{"$f":"'K90 - time schedule'!IJ16","v":0},{"$f":"'K90 - time schedule'!IK16","v":0},{"$f":"'K90 - time schedule'!IL16","v":0},{"$f":"'K90 - time schedule'!IM16","v":0},{"$f":"'K90 - time schedule'!IN16","v":0},{"$f":"'K90 - time schedule'!IO16","v":0},{"$f":"'K90 - time schedule'!IP16","v":0},{"$f":"'K90 - time schedule'!IQ16","v":0},{"$f":"'K90 - time schedule'!IR16","v":0},{"$f":"'K90 - time schedule'!IS16","v":0},{"$f":"'K90 - time schedule'!IT16","v":0},{"$f":"'K90 - time schedule'!IU16","v":0},{"$f":"'K90 - time schedule'!IV16","v":0},{"$f":"'K90 - time schedule'!IW16","v":0},{"$f":"'K90 - time schedule'!IX16","v":0},{"$f":"'K90 - time schedule'!IY16","v":0},{"$f":"'K90 - time schedule'!IZ16","v":0},{"$f":"'K90 - time schedule'!JA16","v":0},{"$f":"'K90 - time schedule'!JB16","v":0},{"$f":"'K90 - time schedule'!JC16","v":0},{"$f":"'K90 - time schedule'!JD16","v":0},{"$f":"'K90 - time schedule'!JE16","v":0},{"$f":"'K90 - time schedule'!JF16","v":0},{"$f":"'K90 - time schedule'!JG16","v":0},{"$f":"'K90 - time schedule'!JH16","v":0},{"$f":"'K90 - time schedule'!JI16","v":0},{"$f":"'K90 - time schedule'!JJ16","v":0},{"$f":"'K90 - time schedule'!JK16","v":0},{"$f":"'K90 - time schedule'!JL16","v":0},{"$f":"'K90 - time schedule'!JM16","v":0},{"$f":"'K90 - time schedule'!JN16","v":0},{"$f":"'K90 - time schedule'!JO16","v":0},{"$f":"'K90 - time schedule'!JP16","v":0},{"$f":"'K90 - time schedule'!JQ16","v":0},{"$f":"'K90 - time schedule'!JR16","v":0},{"$f":"'K90 - time schedule'!JS16","v":0},{"$f":"'K90 - time schedule'!JT16","v":0},{"$f":"'K90 - time schedule'!JU16","v":0},{"$f":"'K90 - time schedule'!JV16","v":0},{"$f":"'K90 - time schedule'!JW16","v":0},{"$f":"'K90 - time schedule'!JX16","v":0},{"$f":"'K90 - time schedule'!JY16","v":0},{"$f":"'K90 - time schedule'!JZ16","v":0},{"$f":"'K90 - time schedule'!KA16","v":0},{"$f":"'K90 - time schedule'!KB16","v":0},{"$f":"'K90 - time schedule'!KC16","v":0},{"$f":"'K90 - time schedule'!KD16","v":0},{"$f":"'K90 - time schedule'!KE16","v":0},{"$f":"'K90 - time schedule'!KF16","v":0},{"$f":"'K90 - time schedule'!KG16","v":0},{"$f":"'K90 - time schedule'!KH16","v":0},{"$f":"'K90 - time schedule'!KI16","v":0},{"$f":"'K90 - time schedule'!KJ16","v":0},{"$f":"'K90 - time schedule'!KK16","v":0},{"$f":"'K90 - time schedule'!KL16","v":0},{"$f":"'K90 - time schedule'!KM16","v":0},{"$f":"'K90 - time schedule'!KN16","v":0},{"$f":"'K90 - time schedule'!KO16","v":0},{"$f":"'K90 - time schedule'!KP16","v":0},{"$f":"'K90 - time schedule'!KQ16","v":0},{"$f":"'K90 - time schedule'!KR16","v":0},{"$f":"'K90 - time schedule'!KS16","v":0},{"$f":"'K90 - time schedule'!KT16","v":0}]
["Boiler room K90 - handover and acceptance of construction site","K90",{"$f":"'K90 - time schedule'!G18","v":0},{"$f":"'K90 - time schedule'!H18","v":0},{"$f":"'K90 - time schedule'!I18","v":0},{"$f":"'K90 - time schedule'!J18","v":0},{"$f":"'K90 - time schedule'!K18","v":0},{"$f":"'K90 - time schedule'!L18","v":0},{"$f":"'K90 - time schedule'!M18","v":0},{"$f":"'K90 - time schedule'!N18","v":0},{"$f":"'K90 - time schedule'!O18","v":0},{"$f":"'K90 - time schedule'!P18","v":0},{"$f":"'K90 - time schedule'!Q18","v":0},{"$f":"'K90 - time schedule'!R18","v":0},{"$f":"'K90 - time schedule'!S18","v":0},{"$f":"'K90 - time schedule'!T18","v":0},{"$f":"'K90 - time schedule'!U18","v":0},{"$f":"'K90 - time schedule'!V18","v":0},{"$f":"'K90 - time schedule'!W18","v":0},{"$f":"'K90 - time schedule'!X18","v":0},{"$f":"'K90 - time schedule'!Y18","v":0},{"$f":"'K90 - time schedule'!Z18","v":0},{"$f":"'K90 - time schedule'!AA18","v":0},{"$f":"'K90 - time schedule'!AB18","v":0},{"$f":"'K90 - time schedule'!AC18","v":0},{"$f":"'K90 - time schedule'!AD18","v":0},{"$f":"'K90 - time schedule'!AE18","v":0},{"$f":"'K90 - time schedule'!AF18","v":0},{"$f":"'K90 - time schedule'!AG18","v":0},{"$f":"'K90 - time schedule'!AH18","v":0},{"$f":"'K90 - time schedule'!AI18","v":0},{"$f":"'K90 - time schedule'!AJ18","v":0},{"$f":"'K90 - time schedule'!AK18","v":0},{"$f":"'K90 - time schedule'!AL18","v":0},{"$f":"'K90 - time schedule'!AM18","v":0},{"$f":"'K90 - time schedule'!AN18","v":0},{"$f":"'K90 - time schedule'!AO18","v":0},{"$f":"'K90 - time schedule'!AP18","v":0},{"$f":"'K90 - time schedule'!AQ18","v":0},{"$f":"'K90 - time schedule'!AR18","v":0},{"$f":"'K90 - time schedule'!AS18","v":0},{"$f":"'K90 - time schedule'!AT18","v":0},{"$f":"'K90 - time schedule'!AU18","v":0},{"$f":"'K90 - time schedule'!AV18","v":0},{"$f":"'K90 - time schedule'!AW18","v":0},{"$f":"'K90 - time schedule'!AX18","v":0},{"$f":"'K90 - time schedule'!AY18","v":0},{"$f":"'K90 - time schedule'!AZ18","v":0},{"$f":"'K90 - time schedule'!BA18","v":0},{"$f":"'K90 - time schedule'!BB18","v":0},{"$f":"'K90 - time schedule'!BC18","v":0},{"$f":"'K90 - time schedule'!BD18","v":0},{"$f":"'K90 - time schedule'!BE18","v":0},{"$f":"'K90 - time schedule'!BF18","v":0},{"$f":"'K90 - time schedule'!BG18","v":0},{"$f":"'K90 - time schedule'!BH18","v":0},{"$f":"'K90 - time schedule'!BI18","v":0},{"$f":"'K90 - time schedule'!BJ18","v":0},{"$f":"'K90 - time schedule'!BK18","v":0},{"$f":"'K90 - time schedule'!BL18","v":0},{"$f":"'K90 - time schedule'!BM18","v":0},{"$f":"'K90 - time schedule'!BN18","v":0},{"$f":"'K90 - time schedule'!BO18","v":0},{"$f":"'K90 - time schedule'!BP18","v":0},{"$f":"'K90 - time schedule'!BQ18","v":0},{"$f":"'K90 - time schedule'!BR18","v":0},{"$f":"'K90 - time schedule'!BS18","v":0},{"$f":"'K90 - time schedule'!BT18","v":0},{"$f":"'K90 - time schedule'!BU18","v":0},{"$f":"'K90 - time schedule'!BV18","v":0},{"$f":"'K90 - time schedule'!BW18","v":0},{"$f":"'K90 - time schedule'!BX18","v":0},{"$f":"'K90 - time schedule'!BY18","v":0},{"$f":"'K90 - time schedule'!BZ18","v":0},{"$f":"'K90 - time schedule'!CA18","v":0},{"$f":"'K90 - time schedule'!CB18","v":0},{"$f":"'K90 - time schedule'!CC18","v":0},{"$f":"'K90 - time schedule'!CD18","v":0},{"$f":"'K90 - time schedule'!CE18","v":0},{"$f":"'K90 - time schedule'!CF18","v":0},{"$f":"'K90 - time schedule'!CG18","v":0},{"$f":"'K90 - time schedule'!CH18","v":0},{"$f":"'K90 - time schedule'!CI18","v":0},{"$f":"'K90 - time schedule'!CJ18","v":0},{"$f":"'K90 - time schedule'!CK18","v":0},{"$f":"'K90 - time schedule'!CL18","v":0},{"$f":"'K90 - time schedule'!CM18","v":0},{"$f":"'K90 - time schedule'!CN18","v":0},{"$f":"'K90 - time schedule'!CO18","v":0},{"$f":"'K90 - time schedule'!CP18","v":0},{"$f":"'K90 - time schedule'!CQ18","v":0},{"$f":"'K90 - time schedule'!CR18","v":0},{"$f":"'K90 - time schedule'!CS18","v":0},{"$f":"'K90 - time schedule'!CT18","v":0},{"$f":"'K90 - time schedule'!CU18","v":0},{"$f":"'K90 - time schedule'!CV18","v":0},{"$f":"'K90 - time schedule'!CW18","v":0},{"$f":"'K90 - time schedule'!CX18","v":0},{"$f":"'K90 - time schedule'!CY18","v":0},{"$f":"'K90 - time schedule'!CZ18","v":0},{"$f":"'K90 - time schedule'!DA18","v":0},{"$f":"'K90 - time schedule'!DB18","v":0},{"$f":"'K90 - time schedule'!DC18","v":0},{"$f":"'K90 - time schedule'!DD18","v":0},{"$f":"'K90 - time schedule'!DE18","v":0},{"$f":"'K90 - time schedule'!DF18","v":0},{"$f":"'K90 - time schedule'!DG18","v":0},{"$f":"'K90 - time schedule'!DH18","v":0},{"$f":"'K90 - time schedule'!DI18","v":0},{"$f":"'K90 - time schedule'!DJ18","v":0},{"$f":"'K90 - time schedule'!DK18","v":0},{"$f":"'K90 - time schedule'!DL18","v":0},{"$f":"'K90 - time schedule'!DM18","v":0},{"$f":"'K90 - time schedule'!DN18","v":0},{"$f":"'K90 - time schedule'!DO18","v":0},{"$f":"'K90 - time schedule'!DP18","v":0},{"$f":"'K90 - time schedule'!DQ18","v":0},{"$f":"'K90 - time schedule'!DR18","v":0},{"$f":"'K90 - time schedule'!DS18","v":0},{"$f":"'K90 - time schedule'!DT18","v":0},{"$f":"'K90 - time schedule'!DU18","v":0},{"$f":"'K90 - time schedule'!DV18","v":0},{"$f":"'K90 - time schedule'!DW18","v":0},{"$f":"'K90 - time schedule'!DX18","v":0},{"$f":"'K90 - time schedule'!DY18","v":0},{"$f":"'K90 - time schedule'!DZ18","v":0},{"$f":"'K90 - time schedule'!EA18","v":0},{"$f":"'K90 - time schedule'!EB18","v":0},{"$f":"'K90 - time schedule'!EC18","v":0},{"$f":"'K90 - time schedule'!ED18","v":0},{"$f":"'K90 - time schedule'!EE18","v":0},{"$f":"'K90 - time schedule'!EF18","v":0},{"$f":"'K90 - time schedule'!EG18","v":0},{"$f":"'K90 - time schedule'!EH18","v":0},{"$f":"'K90 - time schedule'!EI18","v":0},{"$f":"'K90 - time schedule'!EJ18","v":0},{"$f":"'K90 - time schedule'!EK18","v":0},{"$f":"'K90 - time schedule'!EL18","v":0},{"$f":"'K90 - time schedule'!EM18","v":0},{"$f":"'K90 - time schedule'!EN18","v":0},{"$f":"'K90 - time schedule'!EO18","v":0},{"$f":"'K90 - time schedule'!EP18","v":0},{"$f":"'K90 - time schedule'!EQ18","v":0},{"$f":"'K90 - time schedule'!ER18","v":0},{"$f":"'K90 - time schedule'!ES18","v":0},{"$f":"'K90 - time schedule'!ET18","v":0},{"$f":"'K90 - time schedule'!EU18","v":0},{"$f":"'K90 - time schedule'!EV18","v":0},{"$f":"'K90 - time schedule'!EW18","v":0},{"$f":"'K90 - time schedule'!EX18","v":0},{"$f":"'K90 - time schedule'!EY18","v":0},{"$f":"'K90 - time schedule'!EZ18","v":0},{"$f":"'K90 - time schedule'!FA18","v":0},{"$f":"'K90 - time schedule'!FB18","v":0},{"$f":"'K90 - time schedule'!FC18","v":0},{"$f":"'K90 - time schedule'!FD18","v":0},{"$f":"'K90 - time schedule'!FE18","v":0},{"$f":"'K90 - time schedule'!FF18","v":0},{"$f":"'K90 - time schedule'!FG18","v":0},{"$f":"'K90 - time schedule'!FH18","v":0},{"$f":"'K90 - time schedule'!FI18","v":0},{"$f":"'K90 - time schedule'!FJ18","v":0},{"$f":"'K90 - time schedule'!FK18","v":0},{"$f":"'K90 - time schedule'!FL18","v":0},{"$f":"'K90 - time schedule'!FM18","v":0},{"$f":"'K90 - time schedule'!FN18","v":0},{"$f":"'K90 - time schedule'!FO18","v":0},{"$f":"'K90 - time schedule'!FP18","v":0},{"$f":"'K90 - time schedule'!FQ18","v":0},{"$f":"'K90 - time schedule'!FR18","v":0},{"$f":"'K90 - time schedule'!FS18","v":0},{"$f":"'K90 - time schedule'!FT18","v":0},{"$f":"'K90 - time schedule'!FU18","v":0},{"$f":"'K90 - time schedule'!FV18","v":0},{"$f":"'K90 - time schedule'!FW18","v":0},{"$f":"'K90 - time schedule'!FX18","v":0},{"$f":"'K90 - time schedule'!FY18","v":0},{"$f":"'K90 - time schedule'!FZ18","v":0},{"$f":"'K90 - time schedule'!GA18","v":0},{"$f":"'K90 - time schedule'!GB18","v":0},{"$f":"'K90 - time schedule'!GC18","v":0},{"$f":"'K90 - time schedule'!GD18","v":0},{"$f":"'K90 - time schedule'!GE18","v":0},{"$f":"'K90 - time schedule'!GF18","v":0},{"$f":"'K90 - time schedule'!GG18","v":0},{"$f":"'K90 - time schedule'!GH18","v":0},{"$f":"'K90 - time schedule'!GI18","v":0},{"$f":"'K90 - time schedule'!GJ18","v":0},{"$f":"'K90 - time schedule'!GK18","v":0},{"$f":"'K90 - time schedule'!GL18","v":0},{"$f":"'K90 - time schedule'!GM18","v":0},{"$f":"'K90 - time schedule'!GN18","v":0},{"$f":"'K90 - time schedule'!GO18","v":0},{"$f":"'K90 - time schedule'!GP18","v":0},{"$f":"'K90 - time schedule'!GQ18","v":0},{"$f":"'K90 - time schedule'!GR18","v":0},{"$f":"'K90 - time schedule'!GS18","v":0},{"$f":"'K90 - time schedule'!GT18","v":0},{"$f":"'K90 - time schedule'!GU18","v":0},{"$f":"'K90 - time schedule'!GV18","v":0},{"$f":"'K90 - time schedule'!GW18","v":0},{"$f":"'K90 - time schedule'!GX18","v":0},{"$f":"'K90 - time schedule'!GY18","v":0},{"$f":"'K90 - time schedule'!GZ18","v":0},{"$f":"'K90 - time schedule'!HA18","v":0},{"$f":"'K90 - time schedule'!HB18","v":0},{"$f":"'K90 - time schedule'!HC18","v":0},{"$f":"'K90 - time schedule'!HD18","v":0},{"$f":"'K90 - time schedule'!HE18","v":0},{"$f":"'K90 - time schedule'!HF18","v":0},{"$f":"'K90 - time schedule'!HG18","v":0},{"$f":"'K90 - time schedule'!HH18","v":0},{"$f":"'K90 - time schedule'!HI18","v":0},{"$f":"'K90 - time schedule'!HJ18","v":0},{"$f":"'K90 - time schedule'!HK18","v":0},{"$f":"'K90 - time schedule'!HL18","v":0},{"$f":"'K90 - time schedule'!HM18","v":0},{"$f":"'K90 - time schedule'!HN18","v":0},{"$f":"'K90 - time schedule'!HO18","v":0},{"$f":"'K90 - time schedule'!HP18","v":0},{"$f":"'K90 - time schedule'!HQ18","v":0},{"$f":"'K90 - time schedule'!HR18","v":0},{"$f":"'K90 - time schedule'!HS18","v":0},{"$f":"'K90 - time schedule'!HT18","v":0},{"$f":"'K90 - time schedule'!HU18","v":0},{"$f":"'K90 - time schedule'!HV18","v":0},{"$f":"'K90 - time schedule'!HW18","v":0},{"$f":"'K90 - time schedule'!HX18","v":0},{"$f":"'K90 - time schedule'!HY18","v":0},{"$f":"'K90 - time schedule'!HZ18","v":0},{"$f":"'K90 - time schedule'!IA18","v":0},{"$f":"'K90 - time schedule'!IB18","v":0},{"$f":"'K90 - time schedule'!IC18","v":0},{"$f":"'K90 - time schedule'!ID18","v":0},{"$f":"'K90 - time schedule'!IE18","v":0},{"$f":"'K90 - time schedule'!IF18","v":0},{"$f":"'K90 - time schedule'!IG18","v":0},{"$f":"'K90 - time schedule'!IH18","v":0},{"$f":"'K90 - time schedule'!II18","v":0},{"$f":"'K90 - time schedule'!IJ18","v":0},{"$f":"'K90 - time schedule'!IK18","v":0},{"$f":"'K90 - time schedule'!IL18","v":0},{"$f":"'K90 - time schedule'!IM18","v":0},{"$f":"'K90 - time schedule'!IN18","v":0},{"$f":"'K90 - time schedule'!IO18","v":0},{"$f":"'K90 - time schedule'!IP18","v":0},{"$f":"'K90 - time schedule'!IQ18","v":0},{"$f":"'K90 - time schedule'!IR18","v":0},{"$f":"'K90 - time schedule'!IS18","v":0},{"$f":"'K90 - time schedule'!IT18","v":0},{"$f":"'K90 - time schedule'!IU18","v":0},{"$f":"'K90 - time schedule'!IV18","v":0},{"$f":"'K90 - time schedule'!IW18","v":0},{"$f":"'K90 - time schedule'!IX18","v":0},{"$f":"'K90 - time schedule'!IY18","v":0},{"$f":"'K90 - time schedule'!IZ18","v":0},{"$f":"'K90 - time schedule'!JA18","v":0},{"$f":"'K90 - time schedule'!JB18","v":0},{"$f":"'K90 - time schedule'!JC18","v":0},{"$f":"'K90 - time schedule'!JD18","v":0},{"$f":"'K90 - time schedule'!JE18","v":0},{"$f":"'K90 - time schedule'!JF18","v":0},{"$f":"'K90 - time schedule'!JG18","v":0},{"$f":"'K90 - time schedule'!JH18","v":0},{"$f":"'K90 - time schedule'!JI18","v":0},{"$f":"'K90 - time schedule'!JJ18","v":0},{"$f":"'K90 - time schedule'!JK18","v":0},{"$f":"'K90 - time schedule'!JL18","v":0},{"$f":"'K90 - time schedule'!JM18","v":0},{"$f":"'K90 - time schedule'!JN18","v":0},{"$f":"'K90 - time schedule'!JO18","v":0},{"$f":"'K90 - time schedule'!JP18","v":0},{"$f":"'K90 - time schedule'!JQ18","v":0},{"$f":"'K90 - time schedule'!JR18","v":0},{"$f":"'K90 - time schedule'!JS18","v":0},{"$f":"'K90 - time schedule'!JT18","v":0},{"$f":"'K90 - time schedule'!JU18","v":0},{"$f":"'K90 - time schedule'!JV18","v":0},{"$f":"'K90 - time schedule'!JW18","v":0},{"$f":"'K90 - time schedule'!JX18","v":0},{"$f":"'K90 - time schedule'!JY18","v":0},{"$f":"'K90 - time schedule'!JZ18","v":0},{"$f":"'K90 - time schedule'!KA18","v":0},{"$f":"'K90 - time schedule'!KB18","v":0},{"$f":"'K90 - time schedule'!KC18","v":0},{"$f":"'K90 - time schedule'!KD18","v":0},{"$f":"'K90 - time schedule'!KE18","v":0},{"$f":"'K90 - time schedule'!KF18","v":0},{"$f":"'K90 - time schedule'!KG18","v":0},{"$f":"'K90 - time schedule'!KH18","v":0},{"$f":"'K90 - time schedule'!KI18","v":0},{"$f":"'K90 - time schedule'!KJ18","v":0},{"$f":"'K90 - time schedule'!KK18","v":0},{"$f":"'K90 - time schedule'!KL18","v":0},{"$f":"'K90 - time schedule'!KM18","v":0},{"$f":"'K90 - time schedule'!KN18","v":0},{"$f":"'K90 - time schedule'!KO18","v":0},{"$f":"'K90 - time schedule'!KP18","v":0},{"$f":"'K90 - time schedule'!KQ18","v":0},{"$f":"'K90 - time schedule'!KR18","v":0},{"$f":"'K90 - time schedule'!KS18","v":0},{"$f":"'K90 - time schedule'!KT18","v":0}]
["Boiler room K90 - shutdown of boiler K90","K90",{"$f":"'K90 - time schedule'!G19","v":0},{"$f":"'K90 - time schedule'!H19","v":0},{"$f":"'K90 - time schedule'!I19","v":0},{"$f":"'K90 - time schedule'!J19","v":0},{"$f":"'K90 - time schedule'!K19","v":0},{"$f":"'K90 - time schedule'!L19","v":0},{"$f":"'K90 - time schedule'!M19","v":0},{"$f":"'K90 - time schedule'!N19","v":0},{"$f":"'K90 - time schedule'!O19","v":0},{"$f":"'K90 - time schedule'!P19","v":0},{"$f":"'K90 - time schedule'!Q19","v":0},{"$f":"'K90 - time schedule'!R19","v":0},{"$f":"'K90 - time schedule'!S19","v":0},{"$f":"'K90 - time schedule'!T19","v":0},{"$f":"'K90 - time schedule'!U19","v":0},{"$f":"'K90 - time schedule'!V19","v":0},{"$f":"'K90 - time schedule'!W19","v":0},{"$f":"'K90 - time schedule'!X19","v":0},{"$f":"'K90 - time schedule'!Y19","v":0},{"$f":"'K90 - time schedule'!Z19","v":0},{"$f":"'K90 - time schedule'!AA19","v":0},{"$f":"'K90 - time schedule'!AB19","v":0},{"$f":"'K90 - time schedule'!AC19","v":0},{"$f":"'K90 - time schedule'!AD19","v":0},{"$f":"'K90 - time schedule'!AE19","v":0},{"$f":"'K90 - time schedule'!AF19","v":0},{"$f":"'K90 - time schedule'!AG19","v":0},{"$f":"'K90 - time schedule'!AH19","v":0},{"$f":"'K90 - time schedule'!AI19","v":0},{"$f":"'K90 - time schedule'!AJ19","v":0},{"$f":"'K90 - time schedule'!AK19","v":0},{"$f":"'K90 - time schedule'!AL19","v":0},{"$f":"'K90 - time schedule'!AM19","v":0},{"$f":"'K90 - time schedule'!AN19","v":0},{"$f":"'K90 - time schedule'!AO19","v":0},{"$f":"'K90 - time schedule'!AP19","v":0},{"$f":"'K90 - time schedule'!AQ19","v":0},{"$f":"'K90 - time schedule'!AR19","v":0},{"$f":"'K90 - time schedule'!AS19","v":0},{"$f":"'K90 - time schedule'!AT19","v":0},{"$f":"'K90 - time schedule'!AU19","v":0},{"$f":"'K90 - time schedule'!AV19","v":0},{"$f":"'K90 - time schedule'!AW19","v":0},{"$f":"'K90 - time schedule'!AX19","v":0},{"$f":"'K90 - time schedule'!AY19","v":0},{"$f":"'K90 - time schedule'!AZ19","v":0},{"$f":"'K90 - time schedule'!BA19","v":0},{"$f":"'K90 - time schedule'!BB19","v":0},{"$f":"'K90 - time schedule'!BC19","v":0},{"$f":"'K90 - time schedule'!BD19","v":0},{"$f":"'K90 - time schedule'!BE19","v":0},{"$f":"'K90 - time schedule'!BF19","v":0},{"$f":"'K90 - time schedule'!BG19","v":0},{"$f":"'K90 - time schedule'!BH19","v":0},{"$f":"'K90 - time schedule'!BI19","v":0},{"$f":"'K90 - time schedule'!BJ19","v":0},{"$f":"'K90 - time schedule'!BK19","v":0},{"$f":"'K90 - time schedule'!BL19","v":0},{"$f":"'K90 - time schedule'!BM19","v":0},{"$f":"'K90 - time schedule'!BN19","v":0},{"$f":"'K90 - time schedule'!BO19","v":0},{"$f":"'K90 - time schedule'!BP19","v":0},{"$f":"'K90 - time schedule'!BQ19","v":0},{"$f":"'K90 - time schedule'!BR19","v":0},{"$f":"'K90 - time schedule'!BS19","v":0},{"$f":"'K90 - time schedule'!BT19","v":0},{"$f":"'K90 - time schedule'!BU19","v":0},{"$f":"'K90 - time schedule'!BV19","v":0},{"$f":"'K90 - time schedule'!BW19","v":0},{"$f":"'K90 - time schedule'!BX19","v":0},{"$f":"'K90 - time schedule'!BY19","v":0},{"$f":"'K90 - time schedule'!BZ19","v":0},{"$f":"'K90 - time schedule'!CA19","v":0},{"$f":"'K90 - time schedule'!CB19","v":0},{"$f":"'K90 - time schedule'!CC19","v":0},{"$f":"'K90 - time schedule'!CD19","v":0},{"$f":"'K90 - time schedule'!CE19","v":0},{"$f":"'K90 - time schedule'!CF19","v":0},{"$f":"'K90 - time schedule'!CG19","v":0},{"$f":"'K90 - time schedule'!CH19","v":0},{"$f":"'K90 - time schedule'!CI19","v":0},{"$f":"'K90 - time schedule'!CJ19","v":0},{"$f":"'K90 - time schedule'!CK19","v":0},{"$f":"'K90 - time schedule'!CL19","v":0},{"$f":"'K90 - time schedule'!CM19","v":0},{"$f":"'K90 - time schedule'!CN19","v":0},{"$f":"'K90 - time schedule'!CO19","v":0},{"$f":"'K90 - time schedule'!CP19","v":0},{"$f":"'K90 - time schedule'!CQ19","v":0},{"$f":"'K90 - time schedule'!CR19","v":0},{"$f":"'K90 - time schedule'!CS19","v":0},{"$f":"'K90 - time schedule'!CT19","v":0},{"$f":"'K90 - time schedule'!CU19","v":0},{"$f":"'K90 - time schedule'!CV19","v":0},{"$f":"'K90 - time schedule'!CW19","v":0},{"$f":"'K90 - time schedule'!CX19","v":0},{"$f":"'K90 - time schedule'!CY19","v":0},{"$f":"'K90 - time schedule'!CZ19","v":0},{"$f":"'K90 - time schedule'!DA19","v":0},{"$f":"'K90 - time schedule'!DB19","v":0},{"$f":"'K90 - time schedule'!DC19","v":0},{"$f":"'K90 - time schedule'!DD19","v":0},{"$f":"'K90 - time schedule'!DE19","v":0},{"$f":"'K90 - time schedule'!DF19","v":0},{"$f":"'K90 - time schedule'!DG19","v":0},{"$f":"'K90 - time schedule'!DH19","v":0},{"$f":"'K90 - time schedule'!DI19","v":0},{"$f":"'K90 - time schedule'!DJ19","v":0},{"$f":"'K90 - time schedule'!DK19","v":0},{"$f":"'K90 - time schedule'!DL19","v":0},{"$f":"'K90 - time schedule'!DM19","v":0},{"$f":"'K90 - time schedule'!DN19","v":0},{"$f":"'K90 - time schedule'!DO19","v":0},{"$f":"'K90 - time schedule'!DP19","v":0},{"$f":"'K90 - time schedule'!DQ19","v":0},{"$f":"'K90 - time schedule'!DR19","v":0},{"$f":"'K90 - time schedule'!DS19","v":0},{"$f":"'K90 - time schedule'!DT19","v":0},{"$f":"'K90 - time schedule'!DU19","v":0},{"$f":"'K90 - time schedule'!DV19","v":0},{"$f":"'K90 - time schedule'!DW19","v":0},{"$f":"'K90 - time schedule'!DX19","v":0},{"$f":"'K90 - time schedule'!DY19","v":0},{"$f":"'K90 - time schedule'!DZ19","v":0},{"$f":"'K90 - time schedule'!EA19","v":0},{"$f":"'K90 - time schedule'!EB19","v":0},{"$f":"'K90 - time schedule'!EC19","v":0},{"$f":"'K90 - time schedule'!ED19","v":0},{"$f":"'K90 - time schedule'!EE19","v":0},{"$f":"'K90 - time schedule'!EF19","v":0},{"$f":"'K90 - time schedule'!EG19","v":0},{"$f":"'K90 - time schedule'!EH19","v":0},{"$f":"'K90 - time schedule'!EI19","v":0},{"$f":"'K90 - time schedule'!EJ19","v":0},{"$f":"'K90 - time schedule'!EK19","v":0},{"$f":"'K90 - time schedule'!EL19","v":0},{"$f":"'K90 - time schedule'!EM19","v":0},{"$f":"'K90 - time schedule'!EN19","v":0},{"$f":"'K90 - time schedule'!EO19","v":0},{"$f":"'K90 - time schedule'!EP19","v":0},{"$f":"'K90 - time schedule'!EQ19","v":0},{"$f":"'K90 - time schedule'!ER19","v":0},{"$f":"'K90 - time schedule'!ES19","v":0},{"$f":"'K90 - time schedule'!ET19","v":0},{"$f":"'K90 - time schedule'!EU19","v":0},{"$f":"'K90 - time schedule'!EV19","v":0},{"$f":"'K90 - time schedule'!EW19","v":0},{"$f":"'K90 - time schedule'!EX19","v":0},{"$f":"'K90 - time schedule'!EY19","v":0},{"$f":"'K90 - time schedule'!EZ19","v":0},{"$f":"'K90 - time schedule'!FA19","v":0},{"$f":"'K90 - time schedule'!FB19","v":0},{"$f":"'K90 - time schedule'!FC19","v":0},{"$f":"'K90 - time schedule'!FD19","v":0},{"$f":"'K90 - time schedule'!FE19","v":0},{"$f":"'K90 - time schedule'!FF19","v":0},{"$f":"'K90 - time schedule'!FG19","v":0},{"$f":"'K90 - time schedule'!FH19","v":0},{"$f":"'K90 - time schedule'!FI19","v":0},{"$f":"'K90 - time schedule'!FJ19","v":0},{"$f":"'K90 - time schedule'!FK19","v":0},{"$f":"'K90 - time schedule'!FL19","v":0},{"$f":"'K90 - time schedule'!FM19","v":0},{"$f":"'K90 - time schedule'!FN19","v":0},{"$f":"'K90 - time schedule'!FO19","v":0},{"$f":"'K90 - time schedule'!FP19","v":0},{"$f":"'K90 - time schedule'!FQ19","v":0},{"$f":"'K90 - time schedule'!FR19","v":0},{"$f":"'K90 - time schedule'!FS19","v":0},{"$f":"'K90 - time schedule'!FT19","v":0},{"$f":"'K90 - time schedule'!FU19","v":0},{"$f":"'K90 - time schedule'!FV19","v":0},{"$f":"'K90 - time schedule'!FW19","v":0},{"$f":"'K90 - time schedule'!FX19","v":0},{"$f":"'K90 - time schedule'!FY19","v":0},{"$f":"'K90 - time schedule'!FZ19","v":0},{"$f":"'K90 - time schedule'!GA19","v":0},{"$f":"'K90 - time schedule'!GB19","v":0},{"$f":"'K90 - time schedule'!GC19","v":0},{"$f":"'K90 - time schedule'!GD19","v":0},{"$f":"'K90 - time schedule'!GE19","v":0},{"$f":"'K90 - time schedule'!GF19","v":0},{"$f":"'K90 - time schedule'!GG19","v":0},{"$f":"'K90 - time schedule'!GH19","v":0},{"$f":"'K90 - time schedule'!GI19","v":0},{"$f":"'K90 - time schedule'!GJ19","v":0},{"$f":"'K90 - time schedule'!GK19","v":0},{"$f":"'K90 - time schedule'!GL19","v":0},{"$f":"'K90 - time schedule'!GM19","v":0},{"$f":"'K90 - time schedule'!GN19","v":0},{"$f":"'K90 - time schedule'!GO19","v":0},{"$f":"'K90 - time schedule'!GP19","v":0},{"$f":"'K90 - time schedule'!GQ19","v":0},{"$f":"'K90 - time schedule'!GR19","v":0},{"$f":"'K90 - time schedule'!GS19","v":0},{"$f":"'K90 - time schedule'!GT19","v":0},{"$f":"'K90 - time schedule'!GU19","v":0},{"$f":"'K90 - time schedule'!GV19","v":0},{"$f":"'K90 - time schedule'!GW19","v":0},{"$f":"'K90 - time schedule'!GX19","v":0},{"$f":"'K90 - time schedule'!GY19","v":0},{"$f":"'K90 - time schedule'!GZ19","v":0},{"$f":"'K90 - time schedule'!HA19","v":0},{"$f":"'K90 - time schedule'!HB19","v":0},{"$f":"'K90 - time schedule'!HC19","v":0},{"$f":"'K90 - time schedule'!HD19","v":0},{"$f":"'K90 - time schedule'!HE19","v":0},{"$f":"'K90 - time schedule'!HF19","v":0},{"$f":"'K90 - time schedule'!HG19","v":0},{"$f":"'K90 - time schedule'!HH19","v":0},{"$f":"'K90 - time schedule'!HI19","v":0},{"$f":"'K90 - time schedule'!HJ19","v":0},{"$f":"'K90 - time schedule'!HK19","v":0},{"$f":"'K90 - time schedule'!HL19","v":0},{"$f":"'K90 - time schedule'!HM19","v":0},{"$f":"'K90 - time schedule'!HN19","v":0},{"$f":"'K90 - time schedule'!HO19","v":0},{"$f":"'K90 - time schedule'!HP19","v":0},{"$f":"'K90 - time schedule'!HQ19","v":0},{"$f":"'K90 - time schedule'!HR19","v":0},{"$f":"'K90 - time schedule'!HS19","v":0},{"$f":"'K90 - time schedule'!HT19","v":0},{"$f":"'K90 - time schedule'!HU19","v":0},{"$f":"'K90 - time schedule'!HV19","v":0},{"$f":"'K90 - time schedule'!HW19","v":0},{"$f":"'K90 - time schedule'!HX19","v":0},{"$f":"'K90 - time schedule'!HY19","v":0},{"$f":"'K90 - time schedule'!HZ19","v":0},{"$f":"'K90 - time schedule'!IA19","v":0},{"$f":"'K90 - time schedule'!IB19","v":0},{"$f":"'K90 - time schedule'!IC19","v":0},{"$f":"'K90 - time schedule'!ID19","v":0},{"$f":"'K90 - time schedule'!IE19","v":0},{"$f":"'K90 - time schedule'!IF19","v":0},{"$f":"'K90 - time schedule'!IG19","v":0},{"$f":"'K90 - time schedule'!IH19","v":0},{"$f":"'K90 - time schedule'!II19","v":0},{"$f":"'K90 - time schedule'!IJ19","v":0},{"$f":"'K90 - time schedule'!IK19","v":0},{"$f":"'K90 - time schedule'!IL19","v":0},{"$f":"'K90 - time schedule'!IM19","v":0},{"$f":"'K90 - time schedule'!IN19","v":0},{"$f":"'K90 - time schedule'!IO19","v":0},{"$f":"'K90 - time schedule'!IP19","v":0},{"$f":"'K90 - time schedule'!IQ19","v":0},{"$f":"'K90 - time schedule'!IR19","v":0},{"$f":"'K90 - time schedule'!IS19","v":0},{"$f":"'K90 - time schedule'!IT19","v":0},{"$f":"'K90 - time schedule'!IU19","v":0},{"$f":"'K90 - time schedule'!IV19","v":0},{"$f":"'K90 - time schedule'!IW19","v":0},{"$f":"'K90 - time schedule'!IX19","v":0},{"$f":"'K90 - time schedule'!IY19","v":0},{"$f":"'K90 - time schedule'!IZ19","v":0},{"$f":"'K90 - time schedule'!JA19","v":0},{"$f":"'K90 - time schedule'!JB19","v":0},{"$f":"'K90 - time schedule'!JC19","v":0},{"$f":"'K90 - time schedule'!JD19","v":0},{"$f":"'K90 - time schedule'!JE19","v":0},{"$f":"'K90 - time schedule'!JF19","v":0},{"$f":"'K90 - time schedule'!JG19","v":0},{"$f":"'K90 - time schedule'!JH19","v":0},{"$f":"'K90 - time schedule'!JI19","v":0},{"$f":"'K90 - time schedule'!JJ19","v":0},{"$f":"'K90 - time schedule'!JK19","v":0},{"$f":"'K90 - time schedule'!JL19","v":0},{"$f":"'K90 - time schedule'!JM19","v":0},{"$f":"'K90 - time schedule'!JN19","v":0},{"$f":"'K90 - time schedule'!JO19","v":0},{"$f":"'K90 - time schedule'!JP19","v":0},{"$f":"'K90 - time schedule'!JQ19","v":0},{"$f":"'K90 - time schedule'!JR19","v":0},{"$f":"'K90 - time schedule'!JS19","v":0},{"$f":"'K90 - time schedule'!JT19","v":0},{"$f":"'K90 - time schedule'!JU19","v":0},{"$f":"'K90 - time schedule'!JV19","v":0},{"$f":"'K90 - time schedule'!JW19","v":0},{"$f":"'K90 - time schedule'!JX19","v":0},{"$f":"'K90 - time schedule'!JY19","v":0},{"$f":"'K90 - time schedule'!JZ19","v":0},{"$f":"'K90 - time schedule'!KA19","v":0},{"$f":"'K90 - time schedule'!KB19","v":0},{"$f":"'K90 - time schedule'!KC19","v":0},{"$f":"'K90 - time schedule'!KD19","v":0},{"$f":"'K90 - time schedule'!KE19","v":0},{"$f":"'K90 - time schedule'!KF19","v":0},{"$f":"'K90 - time schedule'!KG19","v":0},{"$f":"'K90 - time schedule'!KH19","v":0},{"$f":"'K90 - time schedule'!KI19","v":0},{"$f":"'K90 - time schedule'!KJ19","v":0},{"$f":"'K90 - time schedule'!KK19","v":0},{"$f":"'K90 - time schedule'!KL19","v":0},{"$f":"'K90 - time schedule'!KM19","v":0},{"$f":"'K90 - time schedule'!KN19","v":0},{"$f":"'K90 - time schedule'!KO19","v":0},{"$f":"'K90 - time schedule'!KP19","v":0},{"$f":"'K90 - time schedule'!KQ19","v":0},{"$f":"'K90 - time schedule'!KR19","v":0},{"$f":"'K90 - time schedule'!KS19","v":0},{"$f":"'K90 - time schedule'!KT19","v":0}]
["Boiler room K90 - dismantling","K90",{"$f":"'K90 - time schedule'!G20","v":0},{"$f":"'K90 - time schedule'!H20","v":0},{"$f":"'K90 - time schedule'!I20","v":0},{"$f":"'K90 - time schedule'!J20","v":0},{"$f":"'K90 - time schedule'!K20","v":0},{"$f":"'K90 - time schedule'!L20","v":0},{"$f":"'K90 - time schedule'!M20","v":0},{"$f":"'K90 - time schedule'!N20","v":0},{"$f":"'K90 - time schedule'!O20","v":0},{"$f":"'K90 - time schedule'!P20","v":0},{"$f":"'K90 - time schedule'!Q20","v":0},{"$f":"'K90 - time schedule'!R20","v":0},{"$f":"'K90 - time schedule'!S20","v":0},{"$f":"'K90 - time schedule'!T20","v":0},{"$f":"'K90 - time schedule'!U20","v":0},{"$f":"'K90 - time schedule'!V20","v":0},{"$f":"'K90 - time schedule'!W20","v":0},{"$f":"'K90 - time schedule'!X20","v":0},{"$f":"'K90 - time schedule'!Y20","v":0},{"$f":"'K90 - time schedule'!Z20","v":0},{"$f":"'K90 - time schedule'!AA20","v":0},{"$f":"'K90 - time schedule'!AB20","v":0},{"$f":"'K90 - time schedule'!AC20","v":0},{"$f":"'K90 - time schedule'!AD20","v":0},{"$f":"'K90 - time schedule'!AE20","v":0},{"$f":"'K90 - time schedule'!AF20","v":0},{"$f":"'K90 - time schedule'!AG20","v":0},{"$f":"'K90 - time schedule'!AH20","v":0},{"$f":"'K90 - time schedule'!AI20","v":0},{"$f":"'K90 - time schedule'!AJ20","v":0},{"$f":"'K90 - time schedule'!AK20","v":0},{"$f":"'K90 - time schedule'!AL20","v":0},{"$f":"'K90 - time schedule'!AM20","v":0},{"$f":"'K90 - time schedule'!AN20","v":0},{"$f":"'K90 - time schedule'!AO20","v":0},{"$f":"'K90 - time schedule'!AP20","v":0},{"$f":"'K90 - time schedule'!AQ20","v":0},{"$f":"'K90 - time schedule'!AR20","v":0},{"$f":"'K90 - time schedule'!AS20","v":0},{"$f":"'K90 - time schedule'!AT20","v":0},{"$f":"'K90 - time schedule'!AU20","v":0},{"$f":"'K90 - time schedule'!AV20","v":0},{"$f":"'K90 - time schedule'!AW20","v":0},{"$f":"'K90 - time schedule'!AX20","v":0},{"$f":"'K90 - time schedule'!AY20","v":0},{"$f":"'K90 - time schedule'!AZ20","v":0},{"$f":"'K90 - time schedule'!BA20","v":0},{"$f":"'K90 - time schedule'!BB20","v":0},{"$f":"'K90 - time schedule'!BC20","v":0},{"$f":"'K90 - time schedule'!BD20","v":0},{"$f":"'K90 - time schedule'!BE20","v":0},{"$f":"'K90 - time schedule'!BF20","v":0},{"$f":"'K90 - time schedule'!BG20","v":0},{"$f":"'K90 - time schedule'!BH20","v":0},{"$f":"'K90 - time schedule'!BI20","v":0},{"$f":"'K90 - time schedule'!BJ20","v":0},{"$f":"'K90 - time schedule'!BK20","v":0},{"$f":"'K90 - time schedule'!BL20","v":0},{"$f":"'K90 - time schedule'!BM20","v":0},{"$f":"'K90 - time schedule'!BN20","v":0},{"$f":"'K90 - time schedule'!BO20","v":0},{"$f":"'K90 - time schedule'!BP20","v":0},{"$f":"'K90 - time schedule'!BQ20","v":0},{"$f":"'K90 - time schedule'!BR20","v":0},{"$f":"'K90 - time schedule'!BS20","v":0},{"$f":"'K90 - time schedule'!BT20","v":0},{"$f":"'K90 - time schedule'!BU20","v":0},{"$f":"'K90 - time schedule'!BV20","v":0},{"$f":"'K90 - time schedule'!BW20","v":0},{"$f":"'K90 - time schedule'!BX20","v":0},{"$f":"'K90 - time schedule'!BY20","v":0},{"$f":"'K90 - time schedule'!BZ20","v":0},{"$f":"'K90 - time schedule'!CA20","v":0},{"$f":"'K90 - time schedule'!CB20","v":0},{"$f":"'K90 - time schedule'!CC20","v":0},{"$f":"'K90 - time schedule'!CD20","v":0},{"$f":"'K90 - time schedule'!CE20","v":0},{"$f":"'K90 - time schedule'!CF20","v":0},{"$f":"'K90 - time schedule'!CG20","v":0},{"$f":"'K90 - time schedule'!CH20","v":0},{"$f":"'K90 - time schedule'!CI20","v":0},{"$f":"'K90 - time schedule'!CJ20","v":0},{"$f":"'K90 - time schedule'!CK20","v":0},{"$f":"'K90 - time schedule'!CL20","v":0},{"$f":"'K90 - time schedule'!CM20","v":0},{"$f":"'K90 - time schedule'!CN20","v":0},{"$f":"'K90 - time schedule'!CO20","v":0},{"$f":"'K90 - time schedule'!CP20","v":0},{"$f":"'K90 - time schedule'!CQ20","v":0},{"$f":"'K90 - time schedule'!CR20","v":0},{"$f":"'K90 - time schedule'!CS20","v":0},{"$f":"'K90 - time schedule'!CT20","v":0},{"$f":"'K90 - time schedule'!CU20","v":0},{"$f":"'K90 - time schedule'!CV20","v":0},{"$f":"'K90 - time schedule'!CW20","v":0},{"$f":"'K90 - time schedule'!CX20","v":0},{"$f":"'K90 - time schedule'!CY20","v":0},{"$f":"'K90 - time schedule'!CZ20","v":0},{"$f":"'K90 - time schedule'!DA20","v":0},{"$f":"'K90 - time schedule'!DB20","v":0},{"$f":"'K90 - time schedule'!DC20","v":0},{"$f":"'K90 - time schedule'!DD20","v":0},{"$f":"'K90 - time schedule'!DE20","v":0},{"$f":"'K90 - time schedule'!DF20","v":0},{"$f":"'K90 - time schedule'!DG20","v":0},{"$f":"'K90 - time schedule'!DH20","v":0},{"$f":"'K90 - time schedule'!DI20","v":0},{"$f":"'K90 - time schedule'!DJ20","v":0},{"$f":"'K90 - time schedule'!DK20","v":0},{"$f":"'K90 - time schedule'!DL20","v":0},{"$f":"'K90 - time schedule'!DM20","v":0},{"$f":"'K90 - time schedule'!DN20","v":0},{"$f":"'K90 - time schedule'!DO20","v":0},{"$f":"'K90 - time schedule'!DP20","v":0},{"$f":"'K90 - time schedule'!DQ20","v":0},{"$f":"'K90 - time schedule'!DR20","v":0},{"$f":"'K90 - time schedule'!DS20","v":0},{"$f":"'K90 - time schedule'!DT20","v":0},{"$f":"'K90 - time schedule'!DU20","v":0},{"$f":"'K90 - time schedule'!DV20","v":0},{"$f":"'K90 - time schedule'!DW20","v":0},{"$f":"'K90 - time schedule'!DX20","v":0},{"$f":"'K90 - time schedule'!DY20","v":0},{"$f":"'K90 - time schedule'!DZ20","v":0},{"$f":"'K90 - time schedule'!EA20","v":0},{"$f":"'K90 - time schedule'!EB20","v":0},{"$f":"'K90 - time schedule'!EC20","v":0},{"$f":"'K90 - time schedule'!ED20","v":0},{"$f":"'K90 - time schedule'!EE20","v":0},{"$f":"'K90 - time schedule'!EF20","v":0},{"$f":"'K90 - time schedule'!EG20","v":0},{"$f":"'K90 - time schedule'!EH20","v":0},{"$f":"'K90 - time schedule'!EI20","v":0},{"$f":"'K90 - time schedule'!EJ20","v":0},{"$f":"'K90 - time schedule'!EK20","v":0},{"$f":"'K90 - time schedule'!EL20","v":0},{"$f":"'K90 - time schedule'!EM20","v":0},{"$f":"'K90 - time schedule'!EN20","v":0},{"$f":"'K90 - time schedule'!EO20","v":0},{"$f":"'K90 - time schedule'!EP20","v":0},{"$f":"'K90 - time schedule'!EQ20","v":0},{"$f":"'K90 - time schedule'!ER20","v":0},{"$f":"'K90 - time schedule'!ES20","v":0},{"$f":"'K90 - time schedule'!ET20","v":0},{"$f":"'K90 - time schedule'!EU20","v":0},{"$f":"'K90 - time schedule'!EV20","v":0},{"$f":"'K90 - time schedule'!EW20","v":0},{"$f":"'K90 - time schedule'!EX20","v":0},{"$f":"'K90 - time schedule'!EY20","v":0},{"$f":"'K90 - time schedule'!EZ20","v":0},{"$f":"'K90 - time schedule'!FA20","v":0},{"$f":"'K90 - time schedule'!FB20","v":0},{"$f":"'K90 - time schedule'!FC20","v":0},{"$f":"'K90 - time schedule'!FD20","v":0},{"$f":"'K90 - time schedule'!FE20","v":0},{"$f":"'K90 - time schedule'!FF20","v":0},{"$f":"'K90 - time schedule'!FG20","v":0},{"$f":"'K90 - time schedule'!FH20","v":0},{"$f":"'K90 - time schedule'!FI20","v":0},{"$f":"'K90 - time schedule'!FJ20","v":0},{"$f":"'K90 - time schedule'!FK20","v":0},{"$f":"'K90 - time schedule'!FL20","v":0},{"$f":"'K90 - time schedule'!FM20","v":0},{"$f":"'K90 - time schedule'!FN20","v":0},{"$f":"'K90 - time schedule'!FO20","v":0},{"$f":"'K90 - time schedule'!FP20","v":0},{"$f":"'K90 - time schedule'!FQ20","v":0},{"$f":"'K90 - time schedule'!FR20","v":0},{"$f":"'K90 - time schedule'!FS20","v":0},{"$f":"'K90 - time schedule'!FT20","v":0},{"$f":"'K90 - time schedule'!FU20","v":0},{"$f":"'K90 - time schedule'!FV20","v":0},{"$f":"'K90 - time schedule'!FW20","v":0},{"$f":"'K90 - time schedule'!FX20","v":0},{"$f":"'K90 - time schedule'!FY20","v":0},{"$f":"'K90 - time schedule'!FZ20","v":0},{"$f":"'K90 - time schedule'!GA20","v":0},{"$f":"'K90 - time schedule'!GB20","v":0},{"$f":"'K90 - time schedule'!GC20","v":0},{"$f":"'K90 - time schedule'!GD20","v":0},{"$f":"'K90 - time schedule'!GE20","v":0},{"$f":"'K90 - time schedule'!GF20","v":0},{"$f":"'K90 - time schedule'!GG20","v":0},{"$f":"'K90 - time schedule'!GH20","v":0},{"$f":"'K90 - time schedule'!GI20","v":0},{"$f":"'K90 - time schedule'!GJ20","v":0},{"$f":"'K90 - time schedule'!GK20","v":0},{"$f":"'K90 - time schedule'!GL20","v":0},{"$f":"'K90 - time schedule'!GM20","v":0},{"$f":"'K90 - time schedule'!GN20","v":0},{"$f":"'K90 - time schedule'!GO20","v":0},{"$f":"'K90 - time schedule'!GP20","v":0},{"$f":"'K90 - time schedule'!GQ20","v":0},{"$f":"'K90 - time schedule'!GR20","v":0},{"$f":"'K90 - time schedule'!GS20","v":0},{"$f":"'K90 - time schedule'!GT20","v":0},{"$f":"'K90 - time schedule'!GU20","v":0},{"$f":"'K90 - time schedule'!GV20","v":0},{"$f":"'K90 - time schedule'!GW20","v":0},{"$f":"'K90 - time schedule'!GX20","v":0},{"$f":"'K90 - time schedule'!GY20","v":0},{"$f":"'K90 - time schedule'!GZ20","v":0},{"$f":"'K90 - time schedule'!HA20","v":0},{"$f":"'K90 - time schedule'!HB20","v":0},{"$f":"'K90 - time schedule'!HC20","v":0},{"$f":"'K90 - time schedule'!HD20","v":0},{"$f":"'K90 - time schedule'!HE20","v":0},{"$f":"'K90 - time schedule'!HF20","v":0},{"$f":"'K90 - time schedule'!HG20","v":0},{"$f":"'K90 - time schedule'!HH20","v":0},{"$f":"'K90 - time schedule'!HI20","v":0},{"$f":"'K90 - time schedule'!HJ20","v":0},{"$f":"'K90 - time schedule'!HK20","v":0},{"$f":"'K90 - time schedule'!HL20","v":0},{"$f":"'K90 - time schedule'!HM20","v":0},{"$f":"'K90 - time schedule'!HN20","v":0},{"$f":"'K90 - time schedule'!HO20","v":0},{"$f":"'K90 - time schedule'!HP20","v":0},{"$f":"'K90 - time schedule'!HQ20","v":0},{"$f":"'K90 - time schedule'!HR20","v":0},{"$f":"'K90 - time schedule'!HS20","v":0},{"$f":"'K90 - time schedule'!HT20","v":0},{"$f":"'K90 - time schedule'!HU20","v":0},{"$f":"'K90 - time schedule'!HV20","v":0},{"$f":"'K90 - time schedule'!HW20","v":0},{"$f":"'K90 - time schedule'!HX20","v":0},{"$f":"'K90 - time schedule'!HY20","v":0},{"$f":"'K90 - time schedule'!HZ20","v":0},{"$f":"'K90 - time schedule'!IA20","v":0},{"$f":"'K90 - time schedule'!IB20","v":0},{"$f":"'K90 - time schedule'!IC20","v":0},{"$f":"'K90 - time schedule'!ID20","v":0},{"$f":"'K90 - time schedule'!IE20","v":0},{"$f":"'K90 - time schedule'!IF20","v":0},{"$f":"'K90 - time schedule'!IG20","v":0},{"$f":"'K90 - time schedule'!IH20","v":0},{"$f":"'K90 - time schedule'!II20","v":0},{"$f":"'K90 - time schedule'!IJ20","v":0},{"$f":"'K90 - time schedule'!IK20","v":0},{"$f":"'K90 - time schedule'!IL20","v":0},{"$f":"'K90 - time schedule'!IM20","v":0},{"$f":"'K90 - time schedule'!IN20","v":0},{"$f":"'K90 - time schedule'!IO20","v":0},{"$f":"'K90 - time schedule'!IP20","v":0},{"$f":"'K90 - time schedule'!IQ20","v":0},{"$f":"'K90 - time schedule'!IR20","v":0},{"$f":"'K90 - time schedule'!IS20","v":0},{"$f":"'K90 - time schedule'!IT20","v":0},{"$f":"'K90 - time schedule'!IU20","v":0},{"$f":"'K90 - time schedule'!IV20","v":0},{"$f":"'K90 - time schedule'!IW20","v":0},{"$f":"'K90 - time schedule'!IX20","v":0},{"$f":"'K90 - time schedule'!IY20","v":0},{"$f":"'K90 - time schedule'!IZ20","v":0},{"$f":"'K90 - time schedule'!JA20","v":0},{"$f":"'K90 - time schedule'!JB20","v":0},{"$f":"'K90 - time schedule'!JC20","v":0},{"$f":"'K90 - time schedule'!JD20","v":0},{"$f":"'K90 - time schedule'!JE20","v":0},{"$f":"'K90 - time schedule'!JF20","v":0},{"$f":"'K90 - time schedule'!JG20","v":0},{"$f":"'K90 - time schedule'!JH20","v":0},{"$f":"'K90 - time schedule'!JI20","v":0},{"$f":"'K90 - time schedule'!JJ20","v":0},{"$f":"'K90 - time schedule'!JK20","v":0},{"$f":"'K90 - time schedule'!JL20","v":0},{"$f":"'K90 - time schedule'!JM20","v":0},{"$f":"'K90 - time schedule'!JN20","v":0},{"$f":"'K90 - time schedule'!JO20","v":0},{"$f":"'K90 - time schedule'!JP20","v":0},{"$f":"'K90 - time schedule'!JQ20","v":0},{"$f":"'K90 - time schedule'!JR20","v":0},{"$f":"'K90 - time schedule'!JS20","v":0},{"$f":"'K90 - time schedule'!JT20","v":0},{"$f":"'K90 - time schedule'!JU20","v":0},{"$f":"'K90 - time schedule'!JV20","v":0},{"$f":"'K90 - time schedule'!JW20","v":0},{"$f":"'K90 - time schedule'!JX20","v":0},{"$f":"'K90 - time schedule'!JY20","v":0},{"$f":"'K90 - time schedule'!JZ20","v":0},{"$f":"'K90 - time schedule'!KA20","v":0},{"$f":"'K90 - time schedule'!KB20","v":0},{"$f":"'K90 - time schedule'!KC20","v":0},{"$f":"'K90 - time schedule'!KD20","v":0},{"$f":"'K90 - time schedule'!KE20","v":0},{"$f":"'K90 - time schedule'!KF20","v":0},{"$f":"'K90 - time schedule'!KG20","v":0},{"$f":"'K90 - time schedule'!KH20","v":0},{"$f":"'K90 - time schedule'!KI20","v":0},{"$f":"'K90 - time schedule'!KJ20","v":0},{"$f":"'K90 - time schedule'!KK20","v":0},{"$f":"'K90 - time schedule'!KL20","v":0},{"$f":"'K90 - time schedule'!KM20","v":0},{"$f":"'K90 - time schedule'!KN20","v":0},{"$f":"'K90 - time schedule'!KO20","v":0},{"$f":"'K90 - time schedule'!KP20","v":0},{"$f":"'K90 - time schedule'!KQ20","v":0},{"$f":"'K90 - time schedule'!KR20","v":0},{"$f":"'K90 - time schedule'!KS20","v":0},{"$f":"'K90 - time schedule'!KT20","v":0}]
["Boiler room K90 - supply of combustion air","K90",{"$f":"'K90 - time schedule'!G22","v":0},{"$f":"'K90 - time schedule'!H22","v":0},{"$f":"'K90 - time schedule'!I22","v":0},{"$f":"'K90 - time schedule'!J22","v":0},{"$f":"'K90 - time schedule'!K22","v":0},{"$f":"'K90 - time schedule'!L22","v":0},{"$f":"'K90 - time schedule'!M22","v":0},{"$f":"'K90 - time schedule'!N22","v":0},{"$f":"'K90 - time schedule'!O22","v":0},{"$f":"'K90 - time schedule'!P22","v":0},{"$f":"'K90 - time schedule'!Q22","v":0},{"$f":"'K90 - time schedule'!R22","v":0},{"$f":"'K90 - time schedule'!S22","v":0},{"$f":"'K90 - time schedule'!T22","v":0},{"$f":"'K90 - time schedule'!U22","v":0},{"$f":"'K90 - time schedule'!V22","v":0},{"$f":"'K90 - time schedule'!W22","v":0},{"$f":"'K90 - time schedule'!X22","v":0},{"$f":"'K90 - time schedule'!Y22","v":0},{"$f":"'K90 - time schedule'!Z22","v":0},{"$f":"'K90 - time schedule'!AA22","v":0},{"$f":"'K90 - time schedule'!AB22","v":0},{"$f":"'K90 - time schedule'!AC22","v":0},{"$f":"'K90 - time schedule'!AD22","v":0},{"$f":"'K90 - time schedule'!AE22","v":0},{"$f":"'K90 - time schedule'!AF22","v":0},{"$f":"'K90 - time schedule'!AG22","v":0},{"$f":"'K90 - time schedule'!AH22","v":0},{"$f":"'K90 - time schedule'!AI22","v":0},{"$f":"'K90 - time schedule'!AJ22","v":0},{"$f":"'K90 - time schedule'!AK22","v":0},{"$f":"'K90 - time schedule'!AL22","v":0},{"$f":"'K90 - time schedule'!AM22","v":0},{"$f":"'K90 - time schedule'!AN22","v":0},{"$f":"'K90 - time schedule'!AO22","v":0},{"$f":"'K90 - time schedule'!AP22","v":0},{"$f":"'K90 - time schedule'!AQ22","v":0},{"$f":"'K90 - time schedule'!AR22","v":0},{"$f":"'K90 - time schedule'!AS22","v":0},{"$f":"'K90 - time schedule'!AT22","v":0},{"$f":"'K90 - time schedule'!AU22","v":0},{"$f":"'K90 - time schedule'!AV22","v":0},{"$f":"'K90 - time schedule'!AW22","v":0},{"$f":"'K90 - time schedule'!AX22","v":0},{"$f":"'K90 - time schedule'!AY22","v":0},{"$f":"'K90 - time schedule'!AZ22","v":0},{"$f":"'K90 - time schedule'!BA22","v":0},{"$f":"'K90 - time schedule'!BB22","v":0},{"$f":"'K90 - time schedule'!BC22","v":0},{"$f":"'K90 - time schedule'!BD22","v":0},{"$f":"'K90 - time schedule'!BE22","v":0},{"$f":"'K90 - time schedule'!BF22","v":0},{"$f":"'K90 - time schedule'!BG22","v":0},{"$f":"'K90 - time schedule'!BH22","v":0},{"$f":"'K90 - time schedule'!BI22","v":0},{"$f":"'K90 - time schedule'!BJ22","v":0},{"$f":"'K90 - time schedule'!BK22","v":0},{"$f":"'K90 - time schedule'!BL22","v":0},{"$f":"'K90 - time schedule'!BM22","v":0},{"$f":"'K90 - time schedule'!BN22","v":0},{"$f":"'K90 - time schedule'!BO22","v":0},{"$f":"'K90 - time schedule'!BP22","v":0},{"$f":"'K90 - time schedule'!BQ22","v":0},{"$f":"'K90 - time schedule'!BR22","v":0},{"$f":"'K90 - time schedule'!BS22","v":0},{"$f":"'K90 - time schedule'!BT22","v":0},{"$f":"'K90 - time schedule'!BU22","v":0},{"$f":"'K90 - time schedule'!BV22","v":0},{"$f":"'K90 - time schedule'!BW22","v":0},{"$f":"'K90 - time schedule'!BX22","v":0},{"$f":"'K90 - time schedule'!BY22","v":0},{"$f":"'K90 - time schedule'!BZ22","v":0},{"$f":"'K90 - time schedule'!CA22","v":0},{"$f":"'K90 - time schedule'!CB22","v":0},{"$f":"'K90 - time schedule'!CC22","v":0},{"$f":"'K90 - time schedule'!CD22","v":0},{"$f":"'K90 - time schedule'!CE22","v":0},{"$f":"'K90 - time schedule'!CF22","v":0},{"$f":"'K90 - time schedule'!CG22","v":0},{"$f":"'K90 - time schedule'!CH22","v":0},{"$f":"'K90 - time schedule'!CI22","v":0},{"$f":"'K90 - time schedule'!CJ22","v":0},{"$f":"'K90 - time schedule'!CK22","v":0},{"$f":"'K90 - time schedule'!CL22","v":0},{"$f":"'K90 - time schedule'!CM22","v":0},{"$f":"'K90 - time schedule'!CN22","v":0},{"$f":"'K90 - time schedule'!CO22","v":0},{"$f":"'K90 - time schedule'!CP22","v":0},{"$f":"'K90 - time schedule'!CQ22","v":0},{"$f":"'K90 - time schedule'!CR22","v":0},{"$f":"'K90 - time schedule'!CS22","v":0},{"$f":"'K90 - time schedule'!CT22","v":0},{"$f":"'K90 - time schedule'!CU22","v":0},{"$f":"'K90 - time schedule'!CV22","v":0},{"$f":"'K90 - time schedule'!CW22","v":0},{"$f":"'K90 - time schedule'!CX22","v":0},{"$f":"'K90 - time schedule'!CY22","v":0},{"$f":"'K90 - time schedule'!CZ22","v":0},{"$f":"'K90 - time schedule'!DA22","v":0},{"$f":"'K90 - time schedule'!DB22","v":0},{"$f":"'K90 - time schedule'!DC22","v":0},{"$f":"'K90 - time schedule'!DD22","v":0},{"$f":"'K90 - time schedule'!DE22","v":0},{"$f":"'K90 - time schedule'!DF22","v":0},{"$f":"'K90 - time schedule'!DG22","v":0},{"$f":"'K90 - time schedule'!DH22","v":0},{"$f":"'K90 - time schedule'!DI22","v":0},{"$f":"'K90 - time schedule'!DJ22","v":0},{"$f":"'K90 - time schedule'!DK22","v":0},{"$f":"'K90 - time schedule'!DL22","v":0},{"$f":"'K90 - time schedule'!DM22","v":0},{"$f":"'K90 - time schedule'!DN22","v":0},{"$f":"'K90 - time schedule'!DO22","v":0},{"$f":"'K90 - time schedule'!DP22","v":0},{"$f":"'K90 - time schedule'!DQ22","v":0},{"$f":"'K90 - time schedule'!DR22","v":0},{"$f":"'K90 - time schedule'!DS22","v":0},{"$f":"'K90 - time schedule'!DT22","v":0},{"$f":"'K90 - time schedule'!DU22","v":0},{"$f":"'K90 - time schedule'!DV22","v":0},{"$f":"'K90 - time schedule'!DW22","v":0},{"$f":"'K90 - time schedule'!DX22","v":0},{"$f":"'K90 - time schedule'!DY22","v":0},{"$f":"'K90 - time schedule'!DZ22","v":0},{"$f":"'K90 - time schedule'!EA22","v":0},{"$f":"'K90 - time schedule'!EB22","v":0},{"$f":"'K90 - time schedule'!EC22","v":0},{"$f":"'K90 - time schedule'!ED22","v":0},{"$f":"'K90 - time schedule'!EE22","v":0},{"$f":"'K90 - time schedule'!EF22","v":0},{"$f":"'K90 - time schedule'!EG22","v":0},{"$f":"'K90 - time schedule'!EH22","v":0},{"$f":"'K90 - time schedule'!EI22","v":0},{"$f":"'K90 - time schedule'!EJ22","v":0},{"$f":"'K90 - time schedule'!EK22","v":0},{"$f":"'K90 - time schedule'!EL22","v":0},{"$f":"'K90 - time schedule'!EM22","v":0},{"$f":"'K90 - time schedule'!EN22","v":0},{"$f":"'K90 - time schedule'!EO22","v":0},{"$f":"'K90 - time schedule'!EP22","v":0},{"$f":"'K90 - time schedule'!EQ22","v":0},{"$f":"'K90 - time schedule'!ER22","v":0},{"$f":"'K90 - time schedule'!ES22","v":0},{"$f":"'K90 - time schedule'!ET22","v":0},{"$f":"'K90 - time schedule'!EU22","v":0},{"$f":"'K90 - time schedule'!EV22","v":0},{"$f":"'K90 - time schedule'!EW22","v":0},{"$f":"'K90 - time schedule'!EX22","v":0},{"$f":"'K90 - time schedule'!EY22","v":0},{"$f":"'K90 - time schedule'!EZ22","v":0},{"$f":"'K90 - time schedule'!FA22","v":0},{"$f":"'K90 - time schedule'!FB22","v":0},{"$f":"'K90 - time schedule'!FC22","v":0},{"$f":"'K90 - time schedule'!FD22","v":0},{"$f":"'K90 - time schedule'!FE22","v":0},{"$f":"'K90 - time schedule'!FF22","v":0},{"$f":"'K90 - time schedule'!FG22","v":0},{"$f":"'K90 - time schedule'!FH22","v":0},{"$f":"'K90 - time schedule'!FI22","v":0},{"$f":"'K90 - time schedule'!FJ22","v":0},{"$f":"'K90 - time schedule'!FK22","v":0},{"$f":"'K90 - time schedule'!FL22","v":0},{"$f":"'K90 - time schedule'!FM22","v":0},{"$f":"'K90 - time schedule'!FN22","v":0},{"$f":"'K90 - time schedule'!FO22","v":0},{"$f":"'K90 - time schedule'!FP22","v":0},{"$f":"'K90 - time schedule'!FQ22","v":0},{"$f":"'K90 - time schedule'!FR22","v":0},{"$f":"'K90 - time schedule'!FS22","v":0},{"$f":"'K90 - time schedule'!FT22","v":0},{"$f":"'K90 - time schedule'!FU22","v":0},{"$f":"'K90 - time schedule'!FV22","v":0},{"$f":"'K90 - time schedule'!FW22","v":0},{"$f":"'K90 - time schedule'!FX22","v":0},{"$f":"'K90 - time schedule'!FY22","v":0},{"$f":"'K90 - time schedule'!FZ22","v":0},{"$f":"'K90 - time schedule'!GA22","v":0},{"$f":"'K90 - time schedule'!GB22","v":0},{"$f":"'K90 - time schedule'!GC22","v":0},{"$f":"'K90 - time schedule'!GD22","v":0},{"$f":"'K90 - time schedule'!GE22","v":0},{"$f":"'K90 - time schedule'!GF22","v":0},{"$f":"'K90 - time schedule'!GG22","v":0},{"$f":"'K90 - time schedule'!GH22","v":0},{"$f":"'K90 - time schedule'!GI22","v":0},{"$f":"'K90 - time schedule'!GJ22","v":0},{"$f":"'K90 - time schedule'!GK22","v":0},{"$f":"'K90 - time schedule'!GL22","v":0},{"$f":"'K90 - time schedule'!GM22","v":0},{"$f":"'K90 - time schedule'!GN22","v":0},{"$f":"'K90 - time schedule'!GO22","v":0},{"$f":"'K90 - time schedule'!GP22","v":0},{"$f":"'K90 - time schedule'!GQ22","v":0},{"$f":"'K90 - time schedule'!GR22","v":0},{"$f":"'K90 - time schedule'!GS22","v":0},{"$f":"'K90 - time schedule'!GT22","v":0},{"$f":"'K90 - time schedule'!GU22","v":0},{"$f":"'K90 - time schedule'!GV22","v":0},{"$f":"'K90 - time schedule'!GW22","v":0},{"$f":"'K90 - time schedule'!GX22","v":0},{"$f":"'K90 - time schedule'!GY22","v":0},{"$f":"'K90 - time schedule'!GZ22","v":0},{"$f":"'K90 - time schedule'!HA22","v":0},{"$f":"'K90 - time schedule'!HB22","v":0},{"$f":"'K90 - time schedule'!HC22","v":0},{"$f":"'K90 - time schedule'!HD22","v":0},{"$f":"'K90 - time schedule'!HE22","v":0},{"$f":"'K90 - time schedule'!HF22","v":0},{"$f":"'K90 - time schedule'!HG22","v":0},{"$f":"'K90 - time schedule'!HH22","v":0},{"$f":"'K90 - time schedule'!HI22","v":0},{"$f":"'K90 - time schedule'!HJ22","v":0},{"$f":"'K90 - time schedule'!HK22","v":0},{"$f":"'K90 - time schedule'!HL22","v":0},{"$f":"'K90 - time schedule'!HM22","v":0},{"$f":"'K90 - time schedule'!HN22","v":0},{"$f":"'K90 - time schedule'!HO22","v":0},{"$f":"'K90 - time schedule'!HP22","v":0},{"$f":"'K90 - time schedule'!HQ22","v":0},{"$f":"'K90 - time schedule'!HR22","v":0},{"$f":"'K90 - time schedule'!HS22","v":0},{"$f":"'K90 - time schedule'!HT22","v":0},{"$f":"'K90 - time schedule'!HU22","v":0},{"$f":"'K90 - time schedule'!HV22","v":0},{"$f":"'K90 - time schedule'!HW22","v":0},{"$f":"'K90 - time schedule'!HX22","v":0},{"$f":"'K90 - time schedule'!HY22","v":0},{"$f":"'K90 - time schedule'!HZ22","v":0},{"$f":"'K90 - time schedule'!IA22","v":0},{"$f":"'K90 - time schedule'!IB22","v":0},{"$f":"'K90 - time schedule'!IC22","v":0},{"$f":"'K90 - time schedule'!ID22","v":0},{"$f":"'K90 - time schedule'!IE22","v":0},{"$f":"'K90 - time schedule'!IF22","v":0},{"$f":"'K90 - time schedule'!IG22","v":0},{"$f":"'K90 - time schedule'!IH22","v":0},{"$f":"'K90 - time schedule'!II22","v":0},{"$f":"'K90 - time schedule'!IJ22","v":0},{"$f":"'K90 - time schedule'!IK22","v":0},{"$f":"'K90 - time schedule'!IL22","v":0},{"$f":"'K90 - time schedule'!IM22","v":0},{"$f":"'K90 - time schedule'!IN22","v":0},{"$f":"'K90 - time schedule'!IO22","v":0},{"$f":"'K90 - time schedule'!IP22","v":0},{"$f":"'K90 - time schedule'!IQ22","v":0},{"$f":"'K90 - time schedule'!IR22","v":0},{"$f":"'K90 - time schedule'!IS22","v":0},{"$f":"'K90 - time schedule'!IT22","v":0},{"$f":"'K90 - time schedule'!IU22","v":0},{"$f":"'K90 - time schedule'!IV22","v":0},{"$f":"'K90 - time schedule'!IW22","v":0},{"$f":"'K90 - time schedule'!IX22","v":0},{"$f":"'K90 - time schedule'!IY22","v":0},{"$f":"'K90 - time schedule'!IZ22","v":0},{"$f":"'K90 - time schedule'!JA22","v":0},{"$f":"'K90 - time schedule'!JB22","v":0},{"$f":"'K90 - time schedule'!JC22","v":0},{"$f":"'K90 - time schedule'!JD22","v":0},{"$f":"'K90 - time schedule'!JE22","v":0},{"$f":"'K90 - time schedule'!JF22","v":0},{"$f":"'K90 - time schedule'!JG22","v":0},{"$f":"'K90 - time schedule'!JH22","v":0},{"$f":"'K90 - time schedule'!JI22","v":0},{"$f":"'K90 - time schedule'!JJ22","v":0},{"$f":"'K90 - time schedule'!JK22","v":0},{"$f":"'K90 - time schedule'!JL22","v":0},{"$f":"'K90 - time schedule'!JM22","v":0},{"$f":"'K90 - time schedule'!JN22","v":0},{"$f":"'K90 - time schedule'!JO22","v":0},{"$f":"'K90 - time schedule'!JP22","v":0},{"$f":"'K90 - time schedule'!JQ22","v":0},{"$f":"'K90 - time schedule'!JR22","v":0},{"$f":"'K90 - time schedule'!JS22","v":0},{"$f":"'K90 - time schedule'!JT22","v":0},{"$f":"'K90 - time schedule'!JU22","v":0},{"$f":"'K90 - time schedule'!JV22","v":0},{"$f":"'K90 - time schedule'!JW22","v":0},{"$f":"'K90 - time schedule'!JX22","v":0},{"$f":"'K90 - time schedule'!JY22","v":0},{"$f":"'K90 - time schedule'!JZ22","v":0},{"$f":"'K90 - time schedule'!KA22","v":0},{"$f":"'K90 - time schedule'!KB22","v":0},{"$f":"'K90 - time schedule'!KC22","v":0},{"$f":"'K90 - time schedule'!KD22","v":0},{"$f":"'K90 - time schedule'!KE22","v":0},{"$f":"'K90 - time schedule'!KF22","v":0},{"$f":"'K90 - time schedule'!KG22","v":0},{"$f":"'K90 - time schedule'!KH22","v":0},{"$f":"'K90 - time schedule'!KI22","v":0},{"$f":"'K90 - time schedule'!KJ22","v":0},{"$f":"'K90 - time schedule'!KK22","v":0},{"$f":"'K90 - time schedule'!KL22","v":0},{"$f":"'K90 - time schedule'!KM22","v":0},{"$f":"'K90 - time schedule'!KN22","v":0},{"$f":"'K90 - time schedule'!KO22","v":0},{"$f":"'K90 - time schedule'!KP22","v":0},{"$f":"'K90 - time schedule'!KQ22","v":0},{"$f":"'K90 - time schedule'!KR22","v":0},{"$f":"'K90 - time schedule'!KS22","v":0},{"$f":"'K90 - time schedule'!KT22","v":0}]
["Boiler room K90 - fuel silos, including transport of fuel to the boiler","K90",{"$f":"'K90 - time schedule'!G24","v":0},{"$f":"'K90 - time schedule'!H24","v":0},{"$f":"'K90 - time schedule'!I24","v":0},{"$f":"'K90 - time schedule'!J24","v":0},{"$f":"'K90 - time schedule'!K24","v":0},{"$f":"'K90 - time schedule'!L24","v":0},{"$f":"'K90 - time schedule'!M24","v":0},{"$f":"'K90 - time schedule'!N24","v":0},{"$f":"'K90 - time schedule'!O24","v":0},{"$f":"'K90 - time schedule'!P24","v":0},{"$f":"'K90 - time schedule'!Q24","v":0},{"$f":"'K90 - time schedule'!R24","v":0},{"$f":"'K90 - time schedule'!S24","v":0},{"$f":"'K90 - time schedule'!T24","v":0},{"$f":"'K90 - time schedule'!U24","v":0},{"$f":"'K90 - time schedule'!V24","v":0},{"$f":"'K90 - time schedule'!W24","v":0},{"$f":"'K90 - time schedule'!X24","v":0},{"$f":"'K90 - time schedule'!Y24","v":0},{"$f":"'K90 - time schedule'!Z24","v":0},{"$f":"'K90 - time schedule'!AA24","v":0},{"$f":"'K90 - time schedule'!AB24","v":0},{"$f":"'K90 - time schedule'!AC24","v":0},{"$f":"'K90 - time schedule'!AD24","v":0},{"$f":"'K90 - time schedule'!AE24","v":0},{"$f":"'K90 - time schedule'!AF24","v":0},{"$f":"'K90 - time schedule'!AG24","v":0},{"$f":"'K90 - time schedule'!AH24","v":0},{"$f":"'K90 - time schedule'!AI24","v":0},{"$f":"'K90 - time schedule'!AJ24","v":0},{"$f":"'K90 - time schedule'!AK24","v":0},{"$f":"'K90 - time schedule'!AL24","v":0},{"$f":"'K90 - time schedule'!AM24","v":0},{"$f":"'K90 - time schedule'!AN24","v":0},{"$f":"'K90 - time schedule'!AO24","v":0},{"$f":"'K90 - time schedule'!AP24","v":0},{"$f":"'K90 - time schedule'!AQ24","v":0},{"$f":"'K90 - time schedule'!AR24","v":0},{"$f":"'K90 - time schedule'!AS24","v":0},{"$f":"'K90 - time schedule'!AT24","v":0},{"$f":"'K90 - time schedule'!AU24","v":0},{"$f":"'K90 - time schedule'!AV24","v":0},{"$f":"'K90 - time schedule'!AW24","v":0},{"$f":"'K90 - time schedule'!AX24","v":0},{"$f":"'K90 - time schedule'!AY24","v":0},{"$f":"'K90 - time schedule'!AZ24","v":0},{"$f":"'K90 - time schedule'!BA24","v":0},{"$f":"'K90 - time schedule'!BB24","v":0},{"$f":"'K90 - time schedule'!BC24","v":0},{"$f":"'K90 - time schedule'!BD24","v":0},{"$f":"'K90 - time schedule'!BE24","v":0},{"$f":"'K90 - time schedule'!BF24","v":0},{"$f":"'K90 - time schedule'!BG24","v":0},{"$f":"'K90 - time schedule'!BH24","v":0},{"$f":"'K90 - time schedule'!BI24","v":0},{"$f":"'K90 - time schedule'!BJ24","v":0},{"$f":"'K90 - time schedule'!BK24","v":0},{"$f":"'K90 - time schedule'!BL24","v":0},{"$f":"'K90 - time schedule'!BM24","v":0},{"$f":"'K90 - time schedule'!BN24","v":0},{"$f":"'K90 - time schedule'!BO24","v":0},{"$f":"'K90 - time schedule'!BP24","v":0},{"$f":"'K90 - time schedule'!BQ24","v":0},{"$f":"'K90 - time schedule'!BR24","v":0},{"$f":"'K90 - time schedule'!BS24","v":0},{"$f":"'K90 - time schedule'!BT24","v":0},{"$f":"'K90 - time schedule'!BU24","v":0},{"$f":"'K90 - time schedule'!BV24","v":0},{"$f":"'K90 - time schedule'!BW24","v":0},{"$f":"'K90 - time schedule'!BX24","v":0},{"$f":"'K90 - time schedule'!BY24","v":0},{"$f":"'K90 - time schedule'!BZ24","v":0},{"$f":"'K90 - time schedule'!CA24","v":0},{"$f":"'K90 - time schedule'!CB24","v":0},{"$f":"'K90 - time schedule'!CC24","v":0},{"$f":"'K90 - time schedule'!CD24","v":0},{"$f":"'K90 - time schedule'!CE24","v":0},{"$f":"'K90 - time schedule'!CF24","v":0},{"$f":"'K90 - time schedule'!CG24","v":0},{"$f":"'K90 - time schedule'!CH24","v":0},{"$f":"'K90 - time schedule'!CI24","v":0},{"$f":"'K90 - time schedule'!CJ24","v":0},{"$f":"'K90 - time schedule'!CK24","v":0},{"$f":"'K90 - time schedule'!CL24","v":0},{"$f":"'K90 - time schedule'!CM24","v":0},{"$f":"'K90 - time schedule'!CN24","v":0},{"$f":"'K90 - time schedule'!CO24","v":0},{"$f":"'K90 - time schedule'!CP24","v":0},{"$f":"'K90 - time schedule'!CQ24","v":0},{"$f":"'K90 - time schedule'!CR24","v":0},{"$f":"'K90 - time schedule'!CS24","v":0},{"$f":"'K90 - time schedule'!CT24","v":0},{"$f":"'K90 - time schedule'!CU24","v":0},{"$f":"'K90 - time schedule'!CV24","v":0},{"$f":"'K90 - time schedule'!CW24","v":0},{"$f":"'K90 - time schedule'!CX24","v":0},{"$f":"'K90 - time schedule'!CY24","v":0},{"$f":"'K90 - time schedule'!CZ24","v":0},{"$f":"'K90 - time schedule'!DA24","v":0},{"$f":"'K90 - time schedule'!DB24","v":0},{"$f":"'K90 - time schedule'!DC24","v":0},{"$f":"'K90 - time schedule'!DD24","v":0},{"$f":"'K90 - time schedule'!DE24","v":0},{"$f":"'K90 - time schedule'!DF24","v":0},{"$f":"'K90 - time schedule'!DG24","v":0},{"$f":"'K90 - time schedule'!DH24","v":0},{"$f":"'K90 - time schedule'!DI24","v":0},{"$f":"'K90 - time schedule'!DJ24","v":0},{"$f":"'K90 - time schedule'!DK24","v":0},{"$f":"'K90 - time schedule'!DL24","v":0},{"$f":"'K90 - time schedule'!DM24","v":0},{"$f":"'K90 - time schedule'!DN24","v":0},{"$f":"'K90 - time schedule'!DO24","v":0},{"$f":"'K90 - time schedule'!DP24","v":0},{"$f":"'K90 - time schedule'!DQ24","v":0},{"$f":"'K90 - time schedule'!DR24","v":0},{"$f":"'K90 - time schedule'!DS24","v":0},{"$f":"'K90 - time schedule'!DT24","v":0},{"$f":"'K90 - time schedule'!DU24","v":0},{"$f":"'K90 - time schedule'!DV24","v":0},{"$f":"'K90 - time schedule'!DW24","v":0},{"$f":"'K90 - time schedule'!DX24","v":0},{"$f":"'K90 - time schedule'!DY24","v":0},{"$f":"'K90 - time schedule'!DZ24","v":0},{"$f":"'K90 - time schedule'!EA24","v":0},{"$f":"'K90 - time schedule'!EB24","v":0},{"$f":"'K90 - time schedule'!EC24","v":0},{"$f":"'K90 - time schedule'!ED24","v":0},{"$f":"'K90 - time schedule'!EE24","v":0},{"$f":"'K90 - time schedule'!EF24","v":0},{"$f":"'K90 - time schedule'!EG24","v":0},{"$f":"'K90 - time schedule'!EH24","v":0},{"$f":"'K90 - time schedule'!EI24","v":0},{"$f":"'K90 - time schedule'!EJ24","v":0},{"$f":"'K90 - time schedule'!EK24","v":0},{"$f":"'K90 - time schedule'!EL24","v":0},{"$f":"'K90 - time schedule'!EM24","v":0},{"$f":"'K90 - time schedule'!EN24","v":0},{"$f":"'K90 - time schedule'!EO24","v":0},{"$f":"'K90 - time schedule'!EP24","v":0},{"$f":"'K90 - time schedule'!EQ24","v":0},{"$f":"'K90 - time schedule'!ER24","v":0},{"$f":"'K90 - time schedule'!ES24","v":0},{"$f":"'K90 - time schedule'!ET24","v":0},{"$f":"'K90 - time schedule'!EU24","v":0},{"$f":"'K90 - time schedule'!EV24","v":0},{"$f":"'K90 - time schedule'!EW24","v":0},{"$f":"'K90 - time schedule'!EX24","v":0},{"$f":"'K90 - time schedule'!EY24","v":0},{"$f":"'K90 - time schedule'!EZ24","v":0},{"$f":"'K90 - time schedule'!FA24","v":0},{"$f":"'K90 - time schedule'!FB24","v":0},{"$f":"'K90 - time schedule'!FC24","v":0},{"$f":"'K90 - time schedule'!FD24","v":0},{"$f":"'K90 - time schedule'!FE24","v":0},{"$f":"'K90 - time schedule'!FF24","v":0},{"$f":"'K90 - time schedule'!FG24","v":0},{"$f":"'K90 - time schedule'!FH24","v":0},{"$f":"'K90 - time schedule'!FI24","v":0},{"$f":"'K90 - time schedule'!FJ24","v":0},{"$f":"'K90 - time schedule'!FK24","v":0},{"$f":"'K90 - time schedule'!FL24","v":0},{"$f":"'K90 - time schedule'!FM24","v":0},{"$f":"'K90 - time schedule'!FN24","v":0},{"$f":"'K90 - time schedule'!FO24","v":0},{"$f":"'K90 - time schedule'!FP24","v":0},{"$f":"'K90 - time schedule'!FQ24","v":0},{"$f":"'K90 - time schedule'!FR24","v":0},{"$f":"'K90 - time schedule'!FS24","v":0},{"$f":"'K90 - time schedule'!FT24","v":0},{"$f":"'K90 - time schedule'!FU24","v":0},{"$f":"'K90 - time schedule'!FV24","v":0},{"$f":"'K90 - time schedule'!FW24","v":0},{"$f":"'K90 - time schedule'!FX24","v":0},{"$f":"'K90 - time schedule'!FY24","v":0},{"$f":"'K90 - time schedule'!FZ24","v":0},{"$f":"'K90 - time schedule'!GA24","v":0},{"$f":"'K90 - time schedule'!GB24","v":0},{"$f":"'K90 - time schedule'!GC24","v":0},{"$f":"'K90 - time schedule'!GD24","v":0},{"$f":"'K90 - time schedule'!GE24","v":0},{"$f":"'K90 - time schedule'!GF24","v":0},{"$f":"'K90 - time schedule'!GG24","v":0},{"$f":"'K90 - time schedule'!GH24","v":0},{"$f":"'K90 - time schedule'!GI24","v":0},{"$f":"'K90 - time schedule'!GJ24","v":0},{"$f":"'K90 - time schedule'!GK24","v":0},{"$f":"'K90 - time schedule'!GL24","v":0},{"$f":"'K90 - time schedule'!GM24","v":0},{"$f":"'K90 - time schedule'!GN24","v":0},{"$f":"'K90 - time schedule'!GO24","v":0},{"$f":"'K90 - time schedule'!GP24","v":0},{"$f":"'K90 - time schedule'!GQ24","v":0},{"$f":"'K90 - time schedule'!GR24","v":0},{"$f":"'K90 - time schedule'!GS24","v":0},{"$f":"'K90 - time schedule'!GT24","v":0},{"$f":"'K90 - time schedule'!GU24","v":0},{"$f":"'K90 - time schedule'!GV24","v":0},{"$f":"'K90 - time schedule'!GW24","v":0},{"$f":"'K90 - time schedule'!GX24","v":0},{"$f":"'K90 - time schedule'!GY24","v":0},{"$f":"'K90 - time schedule'!GZ24","v":0},{"$f":"'K90 - time schedule'!HA24","v":0},{"$f":"'K90 - time schedule'!HB24","v":0},{"$f":"'K90 - time schedule'!HC24","v":0},{"$f":"'K90 - time schedule'!HD24","v":0},{"$f":"'K90 - time schedule'!HE24","v":0},{"$f":"'K90 - time schedule'!HF24","v":0},{"$f":"'K90 - time schedule'!HG24","v":0},{"$f":"'K90 - time schedule'!HH24","v":0},{"$f":"'K90 - time schedule'!HI24","v":0},{"$f":"'K90 - time schedule'!HJ24","v":0},{"$f":"'K90 - time schedule'!HK24","v":0},{"$f":"'K90 - time schedule'!HL24","v":0},{"$f":"'K90 - time schedule'!HM24","v":0},{"$f":"'K90 - time schedule'!HN24","v":0},{"$f":"'K90 - time schedule'!HO24","v":0},{"$f":"'K90 - time schedule'!HP24","v":0},{"$f":"'K90 - time schedule'!HQ24","v":0},{"$f":"'K90 - time schedule'!HR24","v":0},{"$f":"'K90 - time schedule'!HS24","v":0},{"$f":"'K90 - time schedule'!HT24","v":0},{"$f":"'K90 - time schedule'!HU24","v":0},{"$f":"'K90 - time schedule'!HV24","v":0},{"$f":"'K90 - time schedule'!HW24","v":0},{"$f":"'K90 - time schedule'!HX24","v":0},{"$f":"'K90 - time schedule'!HY24","v":0},{"$f":"'K90 - time schedule'!HZ24","v":0},{"$f":"'K90 - time schedule'!IA24","v":0},{"$f":"'K90 - time schedule'!IB24","v":0},{"$f":"'K90 - time schedule'!IC24","v":0},{"$f":"'K90 - time schedule'!ID24","v":0},{"$f":"'K90 - time schedule'!IE24","v":0},{"$f":"'K90 - time schedule'!IF24","v":0},{"$f":"'K90 - time schedule'!IG24","v":0},{"$f":"'K90 - time schedule'!IH24","v":0},{"$f":"'K90 - time schedule'!II24","v":0},{"$f":"'K90 - time schedule'!IJ24","v":0},{"$f":"'K90 - time schedule'!IK24","v":0},{"$f":"'K90 - time schedule'!IL24","v":0},{"$f":"'K90 - time schedule'!IM24","v":0},{"$f":"'K90 - time schedule'!IN24","v":0},{"$f":"'K90 - time schedule'!IO24","v":0},{"$f":"'K90 - time schedule'!IP24","v":0},{"$f":"'K90 - time schedule'!IQ24","v":0},{"$f":"'K90 - time schedule'!IR24","v":0},{"$f":"'K90 - time schedule'!IS24","v":0},{"$f":"'K90 - time schedule'!IT24","v":0},{"$f":"'K90 - time schedule'!IU24","v":0},{"$f":"'K90 - time schedule'!IV24","v":0},{"$f":"'K90 - time schedule'!IW24","v":0},{"$f":"'K90 - time schedule'!IX24","v":0},{"$f":"'K90 - time schedule'!IY24","v":0},{"$f":"'K90 - time schedule'!IZ24","v":0},{"$f":"'K90 - time schedule'!JA24","v":0},{"$f":"'K90 - time schedule'!JB24","v":0},{"$f":"'K90 - time schedule'!JC24","v":0},{"$f":"'K90 - time schedule'!JD24","v":0},{"$f":"'K90 - time schedule'!JE24","v":0},{"$f":"'K90 - time schedule'!JF24","v":0},{"$f":"'K90 - time schedule'!JG24","v":0},{"$f":"'K90 - time schedule'!JH24","v":0},{"$f":"'K90 - time schedule'!JI24","v":0},{"$f":"'K90 - time schedule'!JJ24","v":0},{"$f":"'K90 - time schedule'!JK24","v":0},{"$f":"'K90 - time schedule'!JL24","v":0},{"$f":"'K90 - time schedule'!JM24","v":0},{"$f":"'K90 - time schedule'!JN24","v":0},{"$f":"'K90 - time schedule'!JO24","v":0},{"$f":"'K90 - time schedule'!JP24","v":0},{"$f":"'K90 - time schedule'!JQ24","v":0},{"$f":"'K90 - time schedule'!JR24","v":0},{"$f":"'K90 - time schedule'!JS24","v":0},{"$f":"'K90 - time schedule'!JT24","v":0},{"$f":"'K90 - time schedule'!JU24","v":0},{"$f":"'K90 - time schedule'!JV24","v":0},{"$f":"'K90 - time schedule'!JW24","v":0},{"$f":"'K90 - time schedule'!JX24","v":0},{"$f":"'K90 - time schedule'!JY24","v":0},{"$f":"'K90 - time schedule'!JZ24","v":0},{"$f":"'K90 - time schedule'!KA24","v":0},{"$f":"'K90 - time schedule'!KB24","v":0},{"$f":"'K90 - time schedule'!KC24","v":0},{"$f":"'K90 - time schedule'!KD24","v":0},{"$f":"'K90 - time schedule'!KE24","v":0},{"$f":"'K90 - time schedule'!KF24","v":0},{"$f":"'K90 - time schedule'!KG24","v":0},{"$f":"'K90 - time schedule'!KH24","v":0},{"$f":"'K90 - time schedule'!KI24","v":0},{"$f":"'K90 - time schedule'!KJ24","v":0},{"$f":"'K90 - time schedule'!KK24","v":0},{"$f":"'K90 - time schedule'!KL24","v":0},{"$f":"'K90 - time schedule'!KM24","v":0},{"$f":"'K90 - time schedule'!KN24","v":0},{"$f":"'K90 - time schedule'!KO24","v":0},{"$f":"'K90 - time schedule'!KP24","v":0},{"$f":"'K90 - time schedule'!KQ24","v":0},{"$f":"'K90 - time schedule'!KR24","v":0},{"$f":"'K90 - time schedule'!KS24","v":0},{"$f":"'K90 - time schedule'!KT24","v":0}]
["Boiler room K90 - air heating","K90",{"$f":"'K90 - time schedule'!G26","v":0},{"$f":"'K90 - time schedule'!H26","v":0},{"$f":"'K90 - time schedule'!I26","v":0},{"$f":"'K90 - time schedule'!J26","v":0},{"$f":"'K90 - time schedule'!K26","v":0},{"$f":"'K90 - time schedule'!L26","v":0},{"$f":"'K90 - time schedule'!M26","v":0},{"$f":"'K90 - time schedule'!N26","v":0},{"$f":"'K90 - time schedule'!O26","v":0},{"$f":"'K90 - time schedule'!P26","v":0},{"$f":"'K90 - time schedule'!Q26","v":0},{"$f":"'K90 - time schedule'!R26","v":0},{"$f":"'K90 - time schedule'!S26","v":0},{"$f":"'K90 - time schedule'!T26","v":0},{"$f":"'K90 - time schedule'!U26","v":0},{"$f":"'K90 - time schedule'!V26","v":0},{"$f":"'K90 - time schedule'!W26","v":0},{"$f":"'K90 - time schedule'!X26","v":0},{"$f":"'K90 - time schedule'!Y26","v":0},{"$f":"'K90 - time schedule'!Z26","v":0},{"$f":"'K90 - time schedule'!AA26","v":0},{"$f":"'K90 - time schedule'!AB26","v":0},{"$f":"'K90 - time schedule'!AC26","v":0},{"$f":"'K90 - time schedule'!AD26","v":0},{"$f":"'K90 - time schedule'!AE26","v":0},{"$f":"'K90 - time schedule'!AF26","v":0},{"$f":"'K90 - time schedule'!AG26","v":0},{"$f":"'K90 - time schedule'!AH26","v":0},{"$f":"'K90 - time schedule'!AI26","v":0},{"$f":"'K90 - time schedule'!AJ26","v":0},{"$f":"'K90 - time schedule'!AK26","v":0},{"$f":"'K90 - time schedule'!AL26","v":0},{"$f":"'K90 - time schedule'!AM26","v":0},{"$f":"'K90 - time schedule'!AN26","v":0},{"$f":"'K90 - time schedule'!AO26","v":0},{"$f":"'K90 - time schedule'!AP26","v":0},{"$f":"'K90 - time schedule'!AQ26","v":0},{"$f":"'K90 - time schedule'!AR26","v":0},{"$f":"'K90 - time schedule'!AS26","v":0},{"$f":"'K90 - time schedule'!AT26","v":0},{"$f":"'K90 - time schedule'!AU26","v":0},{"$f":"'K90 - time schedule'!AV26","v":0},{"$f":"'K90 - time schedule'!AW26","v":0},{"$f":"'K90 - time schedule'!AX26","v":0},{"$f":"'K90 - time schedule'!AY26","v":0},{"$f":"'K90 - time schedule'!AZ26","v":0},{"$f":"'K90 - time schedule'!BA26","v":0},{"$f":"'K90 - time schedule'!BB26","v":0},{"$f":"'K90 - time schedule'!BC26","v":0},{"$f":"'K90 - time schedule'!BD26","v":0},{"$f":"'K90 - time schedule'!BE26","v":0},{"$f":"'K90 - time schedule'!BF26","v":0},{"$f":"'K90 - time schedule'!BG26","v":0},{"$f":"'K90 - time schedule'!BH26","v":0},{"$f":"'K90 - time schedule'!BI26","v":0},{"$f":"'K90 - time schedule'!BJ26","v":0},{"$f":"'K90 - time schedule'!BK26","v":0},{"$f":"'K90 - time schedule'!BL26","v":0},{"$f":"'K90 - time schedule'!BM26","v":0},{"$f":"'K90 - time schedule'!BN26","v":0},{"$f":"'K90 - time schedule'!BO26","v":0},{"$f":"'K90 - time schedule'!BP26","v":0},{"$f":"'K90 - time schedule'!BQ26","v":0},{"$f":"'K90 - time schedule'!BR26","v":0},{"$f":"'K90 - time schedule'!BS26","v":0},{"$f":"'K90 - time schedule'!BT26","v":0},{"$f":"'K90 - time schedule'!BU26","v":0},{"$f":"'K90 - time schedule'!BV26","v":0},{"$f":"'K90 - time schedule'!BW26","v":0},{"$f":"'K90 - time schedule'!BX26","v":0},{"$f":"'K90 - time schedule'!BY26","v":0},{"$f":"'K90 - time schedule'!BZ26","v":0},{"$f":"'K90 - time schedule'!CA26","v":0},{"$f":"'K90 - time schedule'!CB26","v":0},{"$f":"'K90 - time schedule'!CC26","v":0},{"$f":"'K90 - time schedule'!CD26","v":0},{"$f":"'K90 - time schedule'!CE26","v":0},{"$f":"'K90 - time schedule'!CF26","v":0},{"$f":"'K90 - time schedule'!CG26","v":0},{"$f":"'K90 - time schedule'!CH26","v":0},{"$f":"'K90 - time schedule'!CI26","v":0},{"$f":"'K90 - time schedule'!CJ26","v":0},{"$f":"'K90 - time schedule'!CK26","v":0},{"$f":"'K90 - time schedule'!CL26","v":0},{"$f":"'K90 - time schedule'!CM26","v":0},{"$f":"'K90 - time schedule'!CN26","v":0},{"$f":"'K90 - time schedule'!CO26","v":0},{"$f":"'K90 - time schedule'!CP26","v":0},{"$f":"'K90 - time schedule'!CQ26","v":0},{"$f":"'K90 - time schedule'!CR26","v":0},{"$f":"'K90 - time schedule'!CS26","v":0},{"$f":"'K90 - time schedule'!CT26","v":0},{"$f":"'K90 - time schedule'!CU26","v":0},{"$f":"'K90 - time schedule'!CV26","v":0},{"$f":"'K90 - time schedule'!CW26","v":0},{"$f":"'K90 - time schedule'!CX26","v":0},{"$f":"'K90 - time schedule'!CY26","v":0},{"$f":"'K90 - time schedule'!CZ26","v":0},{"$f":"'K90 - time schedule'!DA26","v":0},{"$f":"'K90 - time schedule'!DB26","v":0},{"$f":"'K90 - time schedule'!DC26","v":0},{"$f":"'K90 - time schedule'!DD26","v":0},{"$f":"'K90 - time schedule'!DE26","v":0},{"$f":"'K90 - time schedule'!DF26","v":0},{"$f":"'K90 - time schedule'!DG26","v":0},{"$f":"'K90 - time schedule'!DH26","v":0},{"$f":"'K90 - time schedule'!DI26","v":0},{"$f":"'K90 - time schedule'!DJ26","v":0},{"$f":"'K90 - time schedule'!DK26","v":0},{"$f":"'K90 - time schedule'!DL26","v":0},{"$f":"'K90 - time schedule'!DM26","v":0},{"$f":"'K90 - time schedule'!DN26","v":0},{"$f":"'K90 - time schedule'!DO26","v":0},{"$f":"'K90 - time schedule'!DP26","v":0},{"$f":"'K90 - time schedule'!DQ26","v":0},{"$f":"'K90 - time schedule'!DR26","v":0},{"$f":"'K90 - time schedule'!DS26","v":0},{"$f":"'K90 - time schedule'!DT26","v":0},{"$f":"'K90 - time schedule'!DU26","v":0},{"$f":"'K90 - time schedule'!DV26","v":0},{"$f":"'K90 - time schedule'!DW26","v":0},{"$f":"'K90 - time schedule'!DX26","v":0},{"$f":"'K90 - time schedule'!DY26","v":0},{"$f":"'K90 - time schedule'!DZ26","v":0},{"$f":"'K90 - time schedule'!EA26","v":0},{"$f":"'K90 - time schedule'!EB26","v":0},{"$f":"'K90 - time schedule'!EC26","v":0},{"$f":"'K90 - time schedule'!ED26","v":0},{"$f":"'K90 - time schedule'!EE26","v":0},{"$f":"'K90 - time schedule'!EF26","v":0},{"$f":"'K90 - time schedule'!EG26","v":0},{"$f":"'K90 - time schedule'!EH26","v":0},{"$f":"'K90 - time schedule'!EI26","v":0},{"$f":"'K90 - time schedule'!EJ26","v":0},{"$f":"'K90 - time schedule'!EK26","v":0},{"$f":"'K90 - time schedule'!EL26","v":0},{"$f":"'K90 - time schedule'!EM26","v":0},{"$f":"'K90 - time schedule'!EN26","v":0},{"$f":"'K90 - time schedule'!EO26","v":0},{"$f":"'K90 - time schedule'!EP26","v":0},{"$f":"'K90 - time schedule'!EQ26","v":0},{"$f":"'K90 - time schedule'!ER26","v":0},{"$f":"'K90 - time schedule'!ES26","v":0},{"$f":"'K90 - time schedule'!ET26","v":0},{"$f":"'K90 - time schedule'!EU26","v":0},{"$f":"'K90 - time schedule'!EV26","v":0},{"$f":"'K90 - time schedule'!EW26","v":0},{"$f":"'K90 - time schedule'!EX26","v":0},{"$f":"'K90 - time schedule'!EY26","v":0},{"$f":"'K90 - time schedule'!EZ26","v":0},{"$f":"'K90 - time schedule'!FA26","v":0},{"$f":"'K90 - time schedule'!FB26","v":0},{"$f":"'K90 - time schedule'!FC26","v":0},{"$f":"'K90 - time schedule'!FD26","v":0},{"$f":"'K90 - time schedule'!FE26","v":0},{"$f":"'K90 - time schedule'!FF26","v":0},{"$f":"'K90 - time schedule'!FG26","v":0},{"$f":"'K90 - time schedule'!FH26","v":0},{"$f":"'K90 - time schedule'!FI26","v":0},{"$f":"'K90 - time schedule'!FJ26","v":0},{"$f":"'K90 - time schedule'!FK26","v":0},{"$f":"'K90 - time schedule'!FL26","v":0},{"$f":"'K90 - time schedule'!FM26","v":0},{"$f":"'K90 - time schedule'!FN26","v":0},{"$f":"'K90 - time schedule'!FO26","v":0},{"$f":"'K90 - time schedule'!FP26","v":0},{"$f":"'K90 - time schedule'!FQ26","v":0},{"$f":"'K90 - time schedule'!FR26","v":0},{"$f":"'K90 - time schedule'!FS26","v":0},{"$f":"'K90 - time schedule'!FT26","v":0},{"$f":"'K90 - time schedule'!FU26","v":0},{"$f":"'K90 - time schedule'!FV26","v":0},{"$f":"'K90 - time schedule'!FW26","v":0},{"$f":"'K90 - time schedule'!FX26","v":0},{"$f":"'K90 - time schedule'!FY26","v":0},{"$f":"'K90 - time schedule'!FZ26","v":0},{"$f":"'K90 - time schedule'!GA26","v":0},{"$f":"'K90 - time schedule'!GB26","v":0},{"$f":"'K90 - time schedule'!GC26","v":0},{"$f":"'K90 - time schedule'!GD26","v":0},{"$f":"'K90 - time schedule'!GE26","v":0},{"$f":"'K90 - time schedule'!GF26","v":0},{"$f":"'K90 - time schedule'!GG26","v":0},{"$f":"'K90 - time schedule'!GH26","v":0},{"$f":"'K90 - time schedule'!GI26","v":0},{"$f":"'K90 - time schedule'!GJ26","v":0},{"$f":"'K90 - time schedule'!GK26","v":0},{"$f":"'K90 - time schedule'!GL26","v":0},{"$f":"'K90 - time schedule'!GM26","v":0},{"$f":"'K90 - time schedule'!GN26","v":0},{"$f":"'K90 - time schedule'!GO26","v":0},{"$f":"'K90 - time schedule'!GP26","v":0},{"$f":"'K90 - time schedule'!GQ26","v":0},{"$f":"'K90 - time schedule'!GR26","v":0},{"$f":"'K90 - time schedule'!GS26","v":0},{"$f":"'K90 - time schedule'!GT26","v":0},{"$f":"'K90 - time schedule'!GU26","v":0},{"$f":"'K90 - time schedule'!GV26","v":0},{"$f":"'K90 - time schedule'!GW26","v":0},{"$f":"'K90 - time schedule'!GX26","v":0},{"$f":"'K90 - time schedule'!GY26","v":0},{"$f":"'K90 - time schedule'!GZ26","v":0},{"$f":"'K90 - time schedule'!HA26","v":0},{"$f":"'K90 - time schedule'!HB26","v":0},{"$f":"'K90 - time schedule'!HC26","v":0},{"$f":"'K90 - time schedule'!HD26","v":0},{"$f":"'K90 - time schedule'!HE26","v":0},{"$f":"'K90 - time schedule'!HF26","v":0},{"$f":"'K90 - time schedule'!HG26","v":0},{"$f":"'K90 - time schedule'!HH26","v":0},{"$f":"'K90 - time schedule'!HI26","v":0},{"$f":"'K90 - time schedule'!HJ26","v":0},{"$f":"'K90 - time schedule'!HK26","v":0},{"$f":"'K90 - time schedule'!HL26","v":0},{"$f":"'K90 - time schedule'!HM26","v":0},{"$f":"'K90 - time schedule'!HN26","v":0},{"$f":"'K90 - time schedule'!HO26","v":0},{"$f":"'K90 - time schedule'!HP26","v":0},{"$f":"'K90 - time schedule'!HQ26","v":0},{"$f":"'K90 - time schedule'!HR26","v":0},{"$f":"'K90 - time schedule'!HS26","v":0},{"$f":"'K90 - time schedule'!HT26","v":0},{"$f":"'K90 - time schedule'!HU26","v":0},{"$f":"'K90 - time schedule'!HV26","v":0},{"$f":"'K90 - time schedule'!HW26","v":0},{"$f":"'K90 - time schedule'!HX26","v":0},{"$f":"'K90 - time schedule'!HY26","v":0},{"$f":"'K90 - time schedule'!HZ26","v":0},{"$f":"'K90 - time schedule'!IA26","v":0},{"$f":"'K90 - time schedule'!IB26","v":0},{"$f":"'K90 - time schedule'!IC26","v":0},{"$f":"'K90 - time schedule'!ID26","v":0},{"$f":"'K90 - time schedule'!IE26","v":0},{"$f":"'K90 - time schedule'!IF26","v":0},{"$f":"'K90 - time schedule'!IG26","v":0},{"$f":"'K90 - time schedule'!IH26","v":0},{"$f":"'K90 - time schedule'!II26","v":0},{"$f":"'K90 - time schedule'!IJ26","v":0},{"$f":"'K90 - time schedule'!IK26","v":0},{"$f":"'K90 - time schedule'!IL26","v":0},{"$f":"'K90 - time schedule'!IM26","v":0},{"$f":"'K90 - time schedule'!IN26","v":0},{"$f":"'K90 - time schedule'!IO26","v":0},{"$f":"'K90 - time schedule'!IP26","v":0},{"$f":"'K90 - time schedule'!IQ26","v":0},{"$f":"'K90 - time schedule'!IR26","v":0},{"$f":"'K90 - time schedule'!IS26","v":0},{"$f":"'K90 - time schedule'!IT26","v":0},{"$f":"'K90 - time schedule'!IU26","v":0},{"$f":"'K90 - time schedule'!IV26","v":0},{"$f":"'K90 - time schedule'!IW26","v":0},{"$f":"'K90 - time schedule'!IX26","v":0},{"$f":"'K90 - time schedule'!IY26","v":0},{"$f":"'K90 - time schedule'!IZ26","v":0},{"$f":"'K90 - time schedule'!JA26","v":0},{"$f":"'K90 - time schedule'!JB26","v":0},{"$f":"'K90 - time schedule'!JC26","v":0},{"$f":"'K90 - time schedule'!JD26","v":0},{"$f":"'K90 - time schedule'!JE26","v":0},{"$f":"'K90 - time schedule'!JF26","v":0},{"$f":"'K90 - time schedule'!JG26","v":0},{"$f":"'K90 - time schedule'!JH26","v":0},{"$f":"'K90 - time schedule'!JI26","v":0},{"$f":"'K90 - time schedule'!JJ26","v":0},{"$f":"'K90 - time schedule'!JK26","v":0},{"$f":"'K90 - time schedule'!JL26","v":0},{"$f":"'K90 - time schedule'!JM26","v":0},{"$f":"'K90 - time schedule'!JN26","v":0},{"$f":"'K90 - time schedule'!JO26","v":0},{"$f":"'K90 - time schedule'!JP26","v":0},{"$f":"'K90 - time schedule'!JQ26","v":0},{"$f":"'K90 - time schedule'!JR26","v":0},{"$f":"'K90 - time schedule'!JS26","v":0},{"$f":"'K90 - time schedule'!JT26","v":0},{"$f":"'K90 - time schedule'!JU26","v":0},{"$f":"'K90 - time schedule'!JV26","v":0},{"$f":"'K90 - time schedule'!JW26","v":0},{"$f":"'K90 - time schedule'!JX26","v":0},{"$f":"'K90 - time schedule'!JY26","v":0},{"$f":"'K90 - time schedule'!JZ26","v":0},{"$f":"'K90 - time schedule'!KA26","v":0},{"$f":"'K90 - time schedule'!KB26","v":0},{"$f":"'K90 - time schedule'!KC26","v":0},{"$f":"'K90 - time schedule'!KD26","v":0},{"$f":"'K90 - time schedule'!KE26","v":0},{"$f":"'K90 - time schedule'!KF26","v":0},{"$f":"'K90 - time schedule'!KG26","v":0},{"$f":"'K90 - time schedule'!KH26","v":0},{"$f":"'K90 - time schedule'!KI26","v":0},{"$f":"'K90 - time schedule'!KJ26","v":0},{"$f":"'K90 - time schedule'!KK26","v":0},{"$f":"'K90 - time schedule'!KL26","v":0},{"$f":"'K90 - time schedule'!KM26","v":0},{"$f":"'K90 - time schedule'!KN26","v":0},{"$f":"'K90 - time schedule'!KO26","v":0},{"$f":"'K90 - time schedule'!KP26","v":0},{"$f":"'K90 - time schedule'!KQ26","v":0},{"$f":"'K90 - time schedule'!KR26","v":0},{"$f":"'K90 - time schedule'!KS26","v":0},{"$f":"'K90 - time schedule'!KT26","v":0}]
["Boiler room K90 - overheating","K90",{"$f":"'K90 - time schedule'!G28","v":0},{"$f":"'K90 - time schedule'!H28","v":0},{"$f":"'K90 - time schedule'!I28","v":0},{"$f":"'K90 - time schedule'!J28","v":0},{"$f":"'K90 - time schedule'!K28","v":0},{"$f":"'K90 - time schedule'!L28","v":0},{"$f":"'K90 - time schedule'!M28","v":0},{"$f":"'K90 - time schedule'!N28","v":0},{"$f":"'K90 - time schedule'!O28","v":0},{"$f":"'K90 - time schedule'!P28","v":0},{"$f":"'K90 - time schedule'!Q28","v":0},{"$f":"'K90 - time schedule'!R28","v":0},{"$f":"'K90 - time schedule'!S28","v":0},{"$f":"'K90 - time schedule'!T28","v":0},{"$f":"'K90 - time schedule'!U28","v":0},{"$f":"'K90 - time schedule'!V28","v":0},{"$f":"'K90 - time schedule'!W28","v":0},{"$f":"'K90 - time schedule'!X28","v":0},{"$f":"'K90 - time schedule'!Y28","v":0},{"$f":"'K90 - time schedule'!Z28","v":0},{"$f":"'K90 - time schedule'!AA28","v":0},{"$f":"'K90 - time schedule'!AB28","v":0},{"$f":"'K90 - time schedule'!AC28","v":0},{"$f":"'K90 - time schedule'!AD28","v":0},{"$f":"'K90 - time schedule'!AE28","v":0},{"$f":"'K90 - time schedule'!AF28","v":0},{"$f":"'K90 - time schedule'!AG28","v":0},{"$f":"'K90 - time schedule'!AH28","v":0},{"$f":"'K90 - time schedule'!AI28","v":0},{"$f":"'K90 - time schedule'!AJ28","v":0},{"$f":"'K90 - time schedule'!AK28","v":0},{"$f":"'K90 - time schedule'!AL28","v":0},{"$f":"'K90 - time schedule'!AM28","v":0},{"$f":"'K90 - time schedule'!AN28","v":0},{"$f":"'K90 - time schedule'!AO28","v":0},{"$f":"'K90 - time schedule'!AP28","v":0},{"$f":"'K90 - time schedule'!AQ28","v":0},{"$f":"'K90 - time schedule'!AR28","v":0},{"$f":"'K90 - time schedule'!AS28","v":0},{"$f":"'K90 - time schedule'!AT28","v":0},{"$f":"'K90 - time schedule'!AU28","v":0},{"$f":"'K90 - time schedule'!AV28","v":0},{"$f":"'K90 - time schedule'!AW28","v":0},{"$f":"'K90 - time schedule'!AX28","v":0},{"$f":"'K90 - time schedule'!AY28","v":0},{"$f":"'K90 - time schedule'!AZ28","v":0},{"$f":"'K90 - time schedule'!BA28","v":0},{"$f":"'K90 - time schedule'!BB28","v":0},{"$f":"'K90 - time schedule'!BC28","v":0},{"$f":"'K90 - time schedule'!BD28","v":0},{"$f":"'K90 - time schedule'!BE28","v":0},{"$f":"'K90 - time schedule'!BF28","v":0},{"$f":"'K90 - time schedule'!BG28","v":0},{"$f":"'K90 - time schedule'!BH28","v":0},{"$f":"'K90 - time schedule'!BI28","v":0},{"$f":"'K90 - time schedule'!BJ28","v":0},{"$f":"'K90 - time schedule'!BK28","v":0},{"$f":"'K90 - time schedule'!BL28","v":0},{"$f":"'K90 - time schedule'!BM28","v":0},{"$f":"'K90 - time schedule'!BN28","v":0},{"$f":"'K90 - time schedule'!BO28","v":0},{"$f":"'K90 - time schedule'!BP28","v":0},{"$f":"'K90 - time schedule'!BQ28","v":0},{"$f":"'K90 - time schedule'!BR28","v":0},{"$f":"'K90 - time schedule'!BS28","v":0},{"$f":"'K90 - time schedule'!BT28","v":0},{"$f":"'K90 - time schedule'!BU28","v":0},{"$f":"'K90 - time schedule'!BV28","v":0},{"$f":"'K90 - time schedule'!BW28","v":0},{"$f":"'K90 - time schedule'!BX28","v":0},{"$f":"'K90 - time schedule'!BY28","v":0},{"$f":"'K90 - time schedule'!BZ28","v":0},{"$f":"'K90 - time schedule'!CA28","v":0},{"$f":"'K90 - time schedule'!CB28","v":0},{"$f":"'K90 - time schedule'!CC28","v":0},{"$f":"'K90 - time schedule'!CD28","v":0},{"$f":"'K90 - time schedule'!CE28","v":0},{"$f":"'K90 - time schedule'!CF28","v":0},{"$f":"'K90 - time schedule'!CG28","v":0},{"$f":"'K90 - time schedule'!CH28","v":0},{"$f":"'K90 - time schedule'!CI28","v":0},{"$f":"'K90 - time schedule'!CJ28","v":0},{"$f":"'K90 - time schedule'!CK28","v":0},{"$f":"'K90 - time schedule'!CL28","v":0},{"$f":"'K90 - time schedule'!CM28","v":0},{"$f":"'K90 - time schedule'!CN28","v":0},{"$f":"'K90 - time schedule'!CO28","v":0},{"$f":"'K90 - time schedule'!CP28","v":0},{"$f":"'K90 - time schedule'!CQ28","v":0},{"$f":"'K90 - time schedule'!CR28","v":0},{"$f":"'K90 - time schedule'!CS28","v":0},{"$f":"'K90 - time schedule'!CT28","v":0},{"$f":"'K90 - time schedule'!CU28","v":0},{"$f":"'K90 - time schedule'!CV28","v":0},{"$f":"'K90 - time schedule'!CW28","v":0},{"$f":"'K90 - time schedule'!CX28","v":0},{"$f":"'K90 - time schedule'!CY28","v":0},{"$f":"'K90 - time schedule'!CZ28","v":0},{"$f":"'K90 - time schedule'!DA28","v":0},{"$f":"'K90 - time schedule'!DB28","v":0},{"$f":"'K90 - time schedule'!DC28","v":0},{"$f":"'K90 - time schedule'!DD28","v":0},{"$f":"'K90 - time schedule'!DE28","v":0},{"$f":"'K90 - time schedule'!DF28","v":0},{"$f":"'K90 - time schedule'!DG28","v":0},{"$f":"'K90 - time schedule'!DH28","v":0},{"$f":"'K90 - time schedule'!DI28","v":0},{"$f":"'K90 - time schedule'!DJ28","v":0},{"$f":"'K90 - time schedule'!DK28","v":0},{"$f":"'K90 - time schedule'!DL28","v":0},{"$f":"'K90 - time schedule'!DM28","v":0},{"$f":"'K90 - time schedule'!DN28","v":0},{"$f":"'K90 - time schedule'!DO28","v":0},{"$f":"'K90 - time schedule'!DP28","v":0},{"$f":"'K90 - time schedule'!DQ28","v":0},{"$f":"'K90 - time schedule'!DR28","v":0},{"$f":"'K90 - time schedule'!DS28","v":0},{"$f":"'K90 - time schedule'!DT28","v":0},{"$f":"'K90 - time schedule'!DU28","v":0},{"$f":"'K90 - time schedule'!DV28","v":0},{"$f":"'K90 - time schedule'!DW28","v":0},{"$f":"'K90 - time schedule'!DX28","v":0},{"$f":"'K90 - time schedule'!DY28","v":0},{"$f":"'K90 - time schedule'!DZ28","v":0},{"$f":"'K90 - time schedule'!EA28","v":0},{"$f":"'K90 - time schedule'!EB28","v":0},{"$f":"'K90 - time schedule'!EC28","v":0},{"$f":"'K90 - time schedule'!ED28","v":0},{"$f":"'K90 - time schedule'!EE28","v":0},{"$f":"'K90 - time schedule'!EF28","v":0},{"$f":"'K90 - time schedule'!EG28","v":0},{"$f":"'K90 - time schedule'!EH28","v":0},{"$f":"'K90 - time schedule'!EI28","v":0},{"$f":"'K90 - time schedule'!EJ28","v":0},{"$f":"'K90 - time schedule'!EK28","v":0},{"$f":"'K90 - time schedule'!EL28","v":0},{"$f":"'K90 - time schedule'!EM28","v":0},{"$f":"'K90 - time schedule'!EN28","v":0},{"$f":"'K90 - time schedule'!EO28","v":0},{"$f":"'K90 - time schedule'!EP28","v":0},{"$f":"'K90 - time schedule'!EQ28","v":0},{"$f":"'K90 - time schedule'!ER28","v":0},{"$f":"'K90 - time schedule'!ES28","v":0},{"$f":"'K90 - time schedule'!ET28","v":0},{"$f":"'K90 - time schedule'!EU28","v":0},{"$f":"'K90 - time schedule'!EV28","v":0},{"$f":"'K90 - time schedule'!EW28","v":0},{"$f":"'K90 - time schedule'!EX28","v":0},{"$f":"'K90 - time schedule'!EY28","v":0},{"$f":"'K90 - time schedule'!EZ28","v":0},{"$f":"'K90 - time schedule'!FA28","v":0},{"$f":"'K90 - time schedule'!FB28","v":0},{"$f":"'K90 - time schedule'!FC28","v":0},{"$f":"'K90 - time schedule'!FD28","v":0},{"$f":"'K90 - time schedule'!FE28","v":0},{"$f":"'K90 - time schedule'!FF28","v":0},{"$f":"'K90 - time schedule'!FG28","v":0},{"$f":"'K90 - time schedule'!FH28","v":0},{"$f":"'K90 - time schedule'!FI28","v":0},{"$f":"'K90 - time schedule'!FJ28","v":0},{"$f":"'K90 - time schedule'!FK28","v":0},{"$f":"'K90 - time schedule'!FL28","v":0},{"$f":"'K90 - time schedule'!FM28","v":0},{"$f":"'K90 - time schedule'!FN28","v":0},{"$f":"'K90 - time schedule'!FO28","v":0},{"$f":"'K90 - time schedule'!FP28","v":0},{"$f":"'K90 - time schedule'!FQ28","v":0},{"$f":"'K90 - time schedule'!FR28","v":0},{"$f":"'K90 - time schedule'!FS28","v":0},{"$f":"'K90 - time schedule'!FT28","v":0},{"$f":"'K90 - time schedule'!FU28","v":0},{"$f":"'K90 - time schedule'!FV28","v":0},{"$f":"'K90 - time schedule'!FW28","v":0},{"$f":"'K90 - time schedule'!FX28","v":0},{"$f":"'K90 - time schedule'!FY28","v":0},{"$f":"'K90 - time schedule'!FZ28","v":0},{"$f":"'K90 - time schedule'!GA28","v":0},{"$f":"'K90 - time schedule'!GB28","v":0},{"$f":"'K90 - time schedule'!GC28","v":0},{"$f":"'K90 - time schedule'!GD28","v":0},{"$f":"'K90 - time schedule'!GE28","v":0},{"$f":"'K90 - time schedule'!GF28","v":0},{"$f":"'K90 - time schedule'!GG28","v":0},{"$f":"'K90 - time schedule'!GH28","v":0},{"$f":"'K90 - time schedule'!GI28","v":0},{"$f":"'K90 - time schedule'!GJ28","v":0},{"$f":"'K90 - time schedule'!GK28","v":0},{"$f":"'K90 - time schedule'!GL28","v":0},{"$f":"'K90 - time schedule'!GM28","v":0},{"$f":"'K90 - time schedule'!GN28","v":0},{"$f":"'K90 - time schedule'!GO28","v":0},{"$f":"'K90 - time schedule'!GP28","v":0},{"$f":"'K90 - time schedule'!GQ28","v":0},{"$f":"'K90 - time schedule'!GR28","v":0},{"$f":"'K90 - time schedule'!GS28","v":0},{"$f":"'K90 - time schedule'!GT28","v":0},{"$f":"'K90 - time schedule'!GU28","v":0},{"$f":"'K90 - time schedule'!GV28","v":0},{"$f":"'K90 - time schedule'!GW28","v":0},{"$f":"'K90 - time schedule'!GX28","v":0},{"$f":"'K90 - time schedule'!GY28","v":0},{"$f":"'K90 - time schedule'!GZ28","v":0},{"$f":"'K90 - time schedule'!HA28","v":0},{"$f":"'K90 - time schedule'!HB28","v":0},{"$f":"'K90 - time schedule'!HC28","v":0},{"$f":"'K90 - time schedule'!HD28","v":0},{"$f":"'K90 - time schedule'!HE28","v":0},{"$f":"'K90 - time schedule'!HF28","v":0},{"$f":"'K90 - time schedule'!HG28","v":0},{"$f":"'K90 - time schedule'!HH28","v":0},{"$f":"'K90 - time schedule'!HI28","v":0},{"$f":"'K90 - time schedule'!HJ28","v":0},{"$f":"'K90 - time schedule'!HK28","v":0},{"$f":"'K90 - time schedule'!HL28","v":0},{"$f":"'K90 - time schedule'!HM28","v":0},{"$f":"'K90 - time schedule'!HN28","v":0},{"$f":"'K90 - time schedule'!HO28","v":0},{"$f":"'K90 - time schedule'!HP28","v":0},{"$f":"'K90 - time schedule'!HQ28","v":0},{"$f":"'K90 - time schedule'!HR28","v":0},{"$f":"'K90 - time schedule'!HS28","v":0},{"$f":"'K90 - time schedule'!HT28","v":0},{"$f":"'K90 - time schedule'!HU28","v":0},{"$f":"'K90 - time schedule'!HV28","v":0},{"$f":"'K90 - time schedule'!HW28","v":0},{"$f":"'K90 - time schedule'!HX28","v":0},{"$f":"'K90 - time schedule'!HY28","v":0},{"$f":"'K90 - time schedule'!HZ28","v":0},{"$f":"'K90 - time schedule'!IA28","v":0},{"$f":"'K90 - time schedule'!IB28","v":0},{"$f":"'K90 - time schedule'!IC28","v":0},{"$f":"'K90 - time schedule'!ID28","v":0},{"$f":"'K90 - time schedule'!IE28","v":0},{"$f":"'K90 - time schedule'!IF28","v":0},{"$f":"'K90 - time schedule'!IG28","v":0},{"$f":"'K90 - time schedule'!IH28","v":0},{"$f":"'K90 - time schedule'!II28","v":0},{"$f":"'K90 - time schedule'!IJ28","v":0},{"$f":"'K90 - time schedule'!IK28","v":0},{"$f":"'K90 - time schedule'!IL28","v":0},{"$f":"'K90 - time schedule'!IM28","v":0},{"$f":"'K90 - time schedule'!IN28","v":0},{"$f":"'K90 - time schedule'!IO28","v":0},{"$f":"'K90 - time schedule'!IP28","v":0},{"$f":"'K90 - time schedule'!IQ28","v":0},{"$f":"'K90 - time schedule'!IR28","v":0},{"$f":"'K90 - time schedule'!IS28","v":0},{"$f":"'K90 - time schedule'!IT28","v":0},{"$f":"'K90 - time schedule'!IU28","v":0},{"$f":"'K90 - time schedule'!IV28","v":0},{"$f":"'K90 - time schedule'!IW28","v":0},{"$f":"'K90 - time schedule'!IX28","v":0},{"$f":"'K90 - time schedule'!IY28","v":0},{"$f":"'K90 - time schedule'!IZ28","v":0},{"$f":"'K90 - time schedule'!JA28","v":0},{"$f":"'K90 - time schedule'!JB28","v":0},{"$f":"'K90 - time schedule'!JC28","v":0},{"$f":"'K90 - time schedule'!JD28","v":0},{"$f":"'K90 - time schedule'!JE28","v":0},{"$f":"'K90 - time schedule'!JF28","v":0},{"$f":"'K90 - time schedule'!JG28","v":0},{"$f":"'K90 - time schedule'!JH28","v":0},{"$f":"'K90 - time schedule'!JI28","v":0},{"$f":"'K90 - time schedule'!JJ28","v":0},{"$f":"'K90 - time schedule'!JK28","v":0},{"$f":"'K90 - time schedule'!JL28","v":0},{"$f":"'K90 - time schedule'!JM28","v":0},{"$f":"'K90 - time schedule'!JN28","v":0},{"$f":"'K90 - time schedule'!JO28","v":0},{"$f":"'K90 - time schedule'!JP28","v":0},{"$f":"'K90 - time schedule'!JQ28","v":0},{"$f":"'K90 - time schedule'!JR28","v":0},{"$f":"'K90 - time schedule'!JS28","v":0},{"$f":"'K90 - time schedule'!JT28","v":0},{"$f":"'K90 - time schedule'!JU28","v":0},{"$f":"'K90 - time schedule'!JV28","v":0},{"$f":"'K90 - time schedule'!JW28","v":0},{"$f":"'K90 - time schedule'!JX28","v":0},{"$f":"'K90 - time schedule'!JY28","v":0},{"$f":"'K90 - time schedule'!JZ28","v":0},{"$f":"'K90 - time schedule'!KA28","v":0},{"$f":"'K90 - time schedule'!KB28","v":0},{"$f":"'K90 - time schedule'!KC28","v":0},{"$f":"'K90 - time schedule'!KD28","v":0},{"$f":"'K90 - time schedule'!KE28","v":0},{"$f":"'K90 - time schedule'!KF28","v":0},{"$f":"'K90 - time schedule'!KG28","v":0},{"$f":"'K90 - time schedule'!KH28","v":0},{"$f":"'K90 - time schedule'!KI28","v":0},{"$f":"'K90 - time schedule'!KJ28","v":0},{"$f":"'K90 - time schedule'!KK28","v":0},{"$f":"'K90 - time schedule'!KL28","v":0},{"$f":"'K90 - time schedule'!KM28","v":0},{"$f":"'K90 - time schedule'!KN28","v":0},{"$f":"'K90 - time schedule'!KO28","v":0},{"$f":"'K90 - time schedule'!KP28","v":0},{"$f":"'K90 - time schedule'!KQ28","v":0},{"$f":"'K90 - time schedule'!KR28","v":0},{"$f":"'K90 - time schedule'!KS28","v":0},{"$f":"'K90 - time schedule'!KT28","v":0}]
["Boiler room K90 - economizer","K90",{"$f":"'K90 - time schedule'!G30","v":0},{"$f":"'K90 - time schedule'!H30","v":0},{"$f":"'K90 - time schedule'!I30","v":0},{"$f":"'K90 - time schedule'!J30","v":0},{"$f":"'K90 - time schedule'!K30","v":0},{"$f":"'K90 - time schedule'!L30","v":0},{"$f":"'K90 - time schedule'!M30","v":0},{"$f":"'K90 - time schedule'!N30","v":0},{"$f":"'K90 - time schedule'!O30","v":0},{"$f":"'K90 - time schedule'!P30","v":0},{"$f":"'K90 - time schedule'!Q30","v":0},{"$f":"'K90 - time schedule'!R30","v":0},{"$f":"'K90 - time schedule'!S30","v":0},{"$f":"'K90 - time schedule'!T30","v":0},{"$f":"'K90 - time schedule'!U30","v":0},{"$f":"'K90 - time schedule'!V30","v":0},{"$f":"'K90 - time schedule'!W30","v":0},{"$f":"'K90 - time schedule'!X30","v":0},{"$f":"'K90 - time schedule'!Y30","v":0},{"$f":"'K90 - time schedule'!Z30","v":0},{"$f":"'K90 - time schedule'!AA30","v":0},{"$f":"'K90 - time schedule'!AB30","v":0},{"$f":"'K90 - time schedule'!AC30","v":0},{"$f":"'K90 - time schedule'!AD30","v":0},{"$f":"'K90 - time schedule'!AE30","v":0},{"$f":"'K90 - time schedule'!AF30","v":0},{"$f":"'K90 - time schedule'!AG30","v":0},{"$f":"'K90 - time schedule'!AH30","v":0},{"$f":"'K90 - time schedule'!AI30","v":0},{"$f":"'K90 - time schedule'!AJ30","v":0},{"$f":"'K90 - time schedule'!AK30","v":0},{"$f":"'K90 - time schedule'!AL30","v":0},{"$f":"'K90 - time schedule'!AM30","v":0},{"$f":"'K90 - time schedule'!AN30","v":0},{"$f":"'K90 - time schedule'!AO30","v":0},{"$f":"'K90 - time schedule'!AP30","v":0},{"$f":"'K90 - time schedule'!AQ30","v":0},{"$f":"'K90 - time schedule'!AR30","v":0},{"$f":"'K90 - time schedule'!AS30","v":0},{"$f":"'K90 - time schedule'!AT30","v":0},{"$f":"'K90 - time schedule'!AU30","v":0},{"$f":"'K90 - time schedule'!AV30","v":0},{"$f":"'K90 - time schedule'!AW30","v":0},{"$f":"'K90 - time schedule'!AX30","v":0},{"$f":"'K90 - time schedule'!AY30","v":0},{"$f":"'K90 - time schedule'!AZ30","v":0},{"$f":"'K90 - time schedule'!BA30","v":0},{"$f":"'K90 - time schedule'!BB30","v":0},{"$f":"'K90 - time schedule'!BC30","v":0},{"$f":"'K90 - time schedule'!BD30","v":0},{"$f":"'K90 - time schedule'!BE30","v":0},{"$f":"'K90 - time schedule'!BF30","v":0},{"$f":"'K90 - time schedule'!BG30","v":0},{"$f":"'K90 - time schedule'!BH30","v":0},{"$f":"'K90 - time schedule'!BI30","v":0},{"$f":"'K90 - time schedule'!BJ30","v":0},{"$f":"'K90 - time schedule'!BK30","v":0},{"$f":"'K90 - time schedule'!BL30","v":0},{"$f":"'K90 - time schedule'!BM30","v":0},{"$f":"'K90 - time schedule'!BN30","v":0},{"$f":"'K90 - time schedule'!BO30","v":0},{"$f":"'K90 - time schedule'!BP30","v":0},{"$f":"'K90 - time schedule'!BQ30","v":0},{"$f":"'K90 - time schedule'!BR30","v":0},{"$f":"'K90 - time schedule'!BS30","v":0},{"$f":"'K90 - time schedule'!BT30","v":0},{"$f":"'K90 - time schedule'!BU30","v":0},{"$f":"'K90 - time schedule'!BV30","v":0},{"$f":"'K90 - time schedule'!BW30","v":0},{"$f":"'K90 - time schedule'!BX30","v":0},{"$f":"'K90 - time schedule'!BY30","v":0},{"$f":"'K90 - time schedule'!BZ30","v":0},{"$f":"'K90 - time schedule'!CA30","v":0},{"$f":"'K90 - time schedule'!CB30","v":0},{"$f":"'K90 - time schedule'!CC30","v":0},{"$f":"'K90 - time schedule'!CD30","v":0},{"$f":"'K90 - time schedule'!CE30","v":0},{"$f":"'K90 - time schedule'!CF30","v":0},{"$f":"'K90 - time schedule'!CG30","v":0},{"$f":"'K90 - time schedule'!CH30","v":0},{"$f":"'K90 - time schedule'!CI30","v":0},{"$f":"'K90 - time schedule'!CJ30","v":0},{"$f":"'K90 - time schedule'!CK30","v":0},{"$f":"'K90 - time schedule'!CL30","v":0},{"$f":"'K90 - time schedule'!CM30","v":0},{"$f":"'K90 - time schedule'!CN30","v":0},{"$f":"'K90 - time schedule'!CO30","v":0},{"$f":"'K90 - time schedule'!CP30","v":0},{"$f":"'K90 - time schedule'!CQ30","v":0},{"$f":"'K90 - time schedule'!CR30","v":0},{"$f":"'K90 - time schedule'!CS30","v":0},{"$f":"'K90 - time schedule'!CT30","v":0},{"$f":"'K90 - time schedule'!CU30","v":0},{"$f":"'K90 - time schedule'!CV30","v":0},{"$f":"'K90 - time schedule'!CW30","v":0},{"$f":"'K90 - time schedule'!CX30","v":0},{"$f":"'K90 - time schedule'!CY30","v":0},{"$f":"'K90 - time schedule'!CZ30","v":0},{"$f":"'K90 - time schedule'!DA30","v":0},{"$f":"'K90 - time schedule'!DB30","v":0},{"$f":"'K90 - time schedule'!DC30","v":0},{"$f":"'K90 - time schedule'!DD30","v":0},{"$f":"'K90 - time schedule'!DE30","v":0},{"$f":"'K90 - time schedule'!DF30","v":0},{"$f":"'K90 - time schedule'!DG30","v":0},{"$f":"'K90 - time schedule'!DH30","v":0},{"$f":"'K90 - time schedule'!DI30","v":0},{"$f":"'K90 - time schedule'!DJ30","v":0},{"$f":"'K90 - time schedule'!DK30","v":0},{"$f":"'K90 - time schedule'!DL30","v":0},{"$f":"'K90 - time schedule'!DM30","v":0},{"$f":"'K90 - time schedule'!DN30","v":0},{"$f":"'K90 - time schedule'!DO30","v":0},{"$f":"'K90 - time schedule'!DP30","v":0},{"$f":"'K90 - time schedule'!DQ30","v":0},{"$f":"'K90 - time schedule'!DR30","v":0},{"$f":"'K90 - time schedule'!DS30","v":0},{"$f":"'K90 - time schedule'!DT30","v":0},{"$f":"'K90 - time schedule'!DU30","v":0},{"$f":"'K90 - time schedule'!DV30","v":0},{"$f":"'K90 - time schedule'!DW30","v":0},{"$f":"'K90 - time schedule'!DX30","v":0},{"$f":"'K90 - time schedule'!DY30","v":0},{"$f":"'K90 - time schedule'!DZ30","v":0},{"$f":"'K90 - time schedule'!EA30","v":0},{"$f":"'K90 - time schedule'!EB30","v":0},{"$f":"'K90 - time schedule'!EC30","v":0},{"$f":"'K90 - time schedule'!ED30","v":0},{"$f":"'K90 - time schedule'!EE30","v":0},{"$f":"'K90 - time schedule'!EF30","v":0},{"$f":"'K90 - time schedule'!EG30","v":0},{"$f":"'K90 - time schedule'!EH30","v":0},{"$f":"'K90 - time schedule'!EI30","v":0},{"$f":"'K90 - time schedule'!EJ30","v":0},{"$f":"'K90 - time schedule'!EK30","v":0},{"$f":"'K90 - time schedule'!EL30","v":0},{"$f":"'K90 - time schedule'!EM30","v":0},{"$f":"'K90 - time schedule'!EN30","v":0},{"$f":"'K90 - time schedule'!EO30","v":0},{"$f":"'K90 - time schedule'!EP30","v":0},{"$f":"'K90 - time schedule'!EQ30","v":0},{"$f":"'K90 - time schedule'!ER30","v":0},{"$f":"'K90 - time schedule'!ES30","v":0},{"$f":"'K90 - time schedule'!ET30","v":0},{"$f":"'K90 - time schedule'!EU30","v":0},{"$f":"'K90 - time schedule'!EV30","v":0},{"$f":"'K90 - time schedule'!EW30","v":0},{"$f":"'K90 - time schedule'!EX30","v":0},{"$f":"'K90 - time schedule'!EY30","v":0},{"$f":"'K90 - time schedule'!EZ30","v":0},{"$f":"'K90 - time schedule'!FA30","v":0},{"$f":"'K90 - time schedule'!FB30","v":0},{"$f":"'K90 - time schedule'!FC30","v":0},{"$f":"'K90 - time schedule'!FD30","v":0},{"$f":"'K90 - time schedule'!FE30","v":0},{"$f":"'K90 - time schedule'!FF30","v":0},{"$f":"'K90 - time schedule'!FG30","v":0},{"$f":"'K90 - time schedule'!FH30","v":0},{"$f":"'K90 - time schedule'!FI30","v":0},{"$f":"'K90 - time schedule'!FJ30","v":0},{"$f":"'K90 - time schedule'!FK30","v":0},{"$f":"'K90 - time schedule'!FL30","v":0},{"$f":"'K90 - time schedule'!FM30","v":0},{"$f":"'K90 - time schedule'!FN30","v":0},{"$f":"'K90 - time schedule'!FO30","v":0},{"$f":"'K90 - time schedule'!FP30","v":0},{"$f":"'K90 - time schedule'!FQ30","v":0},{"$f":"'K90 - time schedule'!FR30","v":0},{"$f":"'K90 - time schedule'!FS30","v":0},{"$f":"'K90 - time schedule'!FT30","v":0},{"$f":"'K90 - time schedule'!FU30","v":0},{"$f":"'K90 - time schedule'!FV30","v":0},{"$f":"'K90 - time schedule'!FW30","v":0},{"$f":"'K90 - time schedule'!FX30","v":0},{"$f":"'K90 - time schedule'!FY30","v":0},{"$f":"'K90 - time schedule'!FZ30","v":0},{"$f":"'K90 - time schedule'!GA30","v":0},{"$f":"'K90 - time schedule'!GB30","v":0},{"$f":"'K90 - time schedule'!GC30","v":0},{"$f":"'K90 - time schedule'!GD30","v":0},{"$f":"'K90 - time schedule'!GE30","v":0},{"$f":"'K90 - time schedule'!GF30","v":0},{"$f":"'K90 - time schedule'!GG30","v":0},{"$f":"'K90 - time schedule'!GH30","v":0},{"$f":"'K90 - time schedule'!GI30","v":0},{"$f":"'K90 - time schedule'!GJ30","v":0},{"$f":"'K90 - time schedule'!GK30","v":0},{"$f":"'K90 - time schedule'!GL30","v":0},{"$f":"'K90 - time schedule'!GM30","v":0},{"$f":"'K90 - time schedule'!GN30","v":0},{"$f":"'K90 - time schedule'!GO30","v":0},{"$f":"'K90 - time schedule'!GP30","v":0},{"$f":"'K90 - time schedule'!GQ30","v":0},{"$f":"'K90 - time schedule'!GR30","v":0},{"$f":"'K90 - time schedule'!GS30","v":0},{"$f":"'K90 - time schedule'!GT30","v":0},{"$f":"'K90 - time schedule'!GU30","v":0},{"$f":"'K90 - time schedule'!GV30","v":0},{"$f":"'K90 - time schedule'!GW30","v":0},{"$f":"'K90 - time schedule'!GX30","v":0},{"$f":"'K90 - time schedule'!GY30","v":0},{"$f":"'K90 - time schedule'!GZ30","v":0},{"$f":"'K90 - time schedule'!HA30","v":0},{"$f":"'K90 - time schedule'!HB30","v":0},{"$f":"'K90 - time schedule'!HC30","v":0},{"$f":"'K90 - time schedule'!HD30","v":0},{"$f":"'K90 - time schedule'!HE30","v":0},{"$f":"'K90 - time schedule'!HF30","v":0},{"$f":"'K90 - time schedule'!HG30","v":0},{"$f":"'K90 - time schedule'!HH30","v":0},{"$f":"'K90 - time schedule'!HI30","v":0},{"$f":"'K90 - time schedule'!HJ30","v":0},{"$f":"'K90 - time schedule'!HK30","v":0},{"$f":"'K90 - time schedule'!HL30","v":0},{"$f":"'K90 - time schedule'!HM30","v":0},{"$f":"'K90 - time schedule'!HN30","v":0},{"$f":"'K90 - time schedule'!HO30","v":0},{"$f":"'K90 - time schedule'!HP30","v":0},{"$f":"'K90 - time schedule'!HQ30","v":0},{"$f":"'K90 - time schedule'!HR30","v":0},{"$f":"'K90 - time schedule'!HS30","v":0},{"$f":"'K90 - time schedule'!HT30","v":0},{"$f":"'K90 - time schedule'!HU30","v":0},{"$f":"'K90 - time schedule'!HV30","v":0},{"$f":"'K90 - time schedule'!HW30","v":0},{"$f":"'K90 - time schedule'!HX30","v":0},{"$f":"'K90 - time schedule'!HY30","v":0},{"$f":"'K90 - time schedule'!HZ30","v":0},{"$f":"'K90 - time schedule'!IA30","v":0},{"$f":"'K90 - time schedule'!IB30","v":0},{"$f":"'K90 - time schedule'!IC30","v":0},{"$f":"'K90 - time schedule'!ID30","v":0},{"$f":"'K90 - time schedule'!IE30","v":0},{"$f":"'K90 - time schedule'!IF30","v":0},{"$f":"'K90 - time schedule'!IG30","v":0},{"$f":"'K90 - time schedule'!IH30","v":0},{"$f":"'K90 - time schedule'!II30","v":0},{"$f":"'K90 - time schedule'!IJ30","v":0},{"$f":"'K90 - time schedule'!IK30","v":0},{"$f":"'K90 - time schedule'!IL30","v":0},{"$f":"'K90 - time schedule'!IM30","v":0},{"$f":"'K90 - time schedule'!IN30","v":0},{"$f":"'K90 - time schedule'!IO30","v":0},{"$f":"'K90 - time schedule'!IP30","v":0},{"$f":"'K90 - time schedule'!IQ30","v":0},{"$f":"'K90 - time schedule'!IR30","v":0},{"$f":"'K90 - time schedule'!IS30","v":0},{"$f":"'K90 - time schedule'!IT30","v":0},{"$f":"'K90 - time schedule'!IU30","v":0},{"$f":"'K90 - time schedule'!IV30","v":0},{"$f":"'K90 - time schedule'!IW30","v":0},{"$f":"'K90 - time schedule'!IX30","v":0},{"$f":"'K90 - time schedule'!IY30","v":0},{"$f":"'K90 - time schedule'!IZ30","v":0},{"$f":"'K90 - time schedule'!JA30","v":0},{"$f":"'K90 - time schedule'!JB30","v":0},{"$f":"'K90 - time schedule'!JC30","v":0},{"$f":"'K90 - time schedule'!JD30","v":0},{"$f":"'K90 - time schedule'!JE30","v":0},{"$f":"'K90 - time schedule'!JF30","v":0},{"$f":"'K90 - time schedule'!JG30","v":0},{"$f":"'K90 - time schedule'!JH30","v":0},{"$f":"'K90 - time schedule'!JI30","v":0},{"$f":"'K90 - time schedule'!JJ30","v":0},{"$f":"'K90 - time schedule'!JK30","v":0},{"$f":"'K90 - time schedule'!JL30","v":0},{"$f":"'K90 - time schedule'!JM30","v":0},{"$f":"'K90 - time schedule'!JN30","v":0},{"$f":"'K90 - time schedule'!JO30","v":0},{"$f":"'K90 - time schedule'!JP30","v":0},{"$f":"'K90 - time schedule'!JQ30","v":0},{"$f":"'K90 - time schedule'!JR30","v":0},{"$f":"'K90 - time schedule'!JS30","v":0},{"$f":"'K90 - time schedule'!JT30","v":0},{"$f":"'K90 - time schedule'!JU30","v":0},{"$f":"'K90 - time schedule'!JV30","v":0},{"$f":"'K90 - time schedule'!JW30","v":0},{"$f":"'K90 - time schedule'!JX30","v":0},{"$f":"'K90 - time schedule'!JY30","v":0},{"$f":"'K90 - time schedule'!JZ30","v":0},{"$f":"'K90 - time schedule'!KA30","v":0},{"$f":"'K90 - time schedule'!KB30","v":0},{"$f":"'K90 - time schedule'!KC30","v":0},{"$f":"'K90 - time schedule'!KD30","v":0},{"$f":"'K90 - time schedule'!KE30","v":0},{"$f":"'K90 - time schedule'!KF30","v":0},{"$f":"'K90 - time schedule'!KG30","v":0},{"$f":"'K90 - time schedule'!KH30","v":0},{"$f":"'K90 - time schedule'!KI30","v":0},{"$f":"'K90 - time schedule'!KJ30","v":0},{"$f":"'K90 - time schedule'!KK30","v":0},{"$f":"'K90 - time schedule'!KL30","v":0},{"$f":"'K90 - time schedule'!KM30","v":0},{"$f":"'K90 - time schedule'!KN30","v":0},{"$f":"'K90 - time schedule'!KO30","v":0},{"$f":"'K90 - time schedule'!KP30","v":0},{"$f":"'K90 - time schedule'!KQ30","v":0},{"$f":"'K90 - time schedule'!KR30","v":0},{"$f":"'K90 - time schedule'!KS30","v":0},{"$f":"'K90 - time schedule'!KT30","v":0}]
["Boiler room K90 - lining","K90",{"$f":"'K90 - time schedule'!G32","v":0},{"$f":"'K90 - time schedule'!H32","v":0},{"$f":"'K90 - time schedule'!I32","v":0},{"$f":"'K90 - time schedule'!J32","v":0},{"$f":"'K90 - time schedule'!K32","v":0},{"$f":"'K90 - time schedule'!L32","v":0},{"$f":"'K90 - time schedule'!M32","v":0},{"$f":"'K90 - time schedule'!N32","v":0},{"$f":"'K90 - time schedule'!O32","v":0},{"$f":"'K90 - time schedule'!P32","v":0},{"$f":"'K90 - time schedule'!Q32","v":0},{"$f":"'K90 - time schedule'!R32","v":0},{"$f":"'K90 - time schedule'!S32","v":0},{"$f":"'K90 - time schedule'!T32","v":0},{"$f":"'K90 - time schedule'!U32","v":0},{"$f":"'K90 - time schedule'!V32","v":0},{"$f":"'K90 - time schedule'!W32","v":0},{"$f":"'K90 - time schedule'!X32","v":0},{"$f":"'K90 - time schedule'!Y32","v":0},{"$f":"'K90 - time schedule'!Z32","v":0},{"$f":"'K90 - time schedule'!AA32","v":0},{"$f":"'K90 - time schedule'!AB32","v":0},{"$f":"'K90 - time schedule'!AC32","v":0},{"$f":"'K90 - time schedule'!AD32","v":0},{"$f":"'K90 - time schedule'!AE32","v":0},{"$f":"'K90 - time schedule'!AF32","v":0},{"$f":"'K90 - time schedule'!AG32","v":0},{"$f":"'K90 - time schedule'!AH32","v":0},{"$f":"'K90 - time schedule'!AI32","v":0},{"$f":"'K90 - time schedule'!AJ32","v":0},{"$f":"'K90 - time schedule'!AK32","v":0},{"$f":"'K90 - time schedule'!AL32","v":0},{"$f":"'K90 - time schedule'!AM32","v":0},{"$f":"'K90 - time schedule'!AN32","v":0},{"$f":"'K90 - time schedule'!AO32","v":0},{"$f":"'K90 - time schedule'!AP32","v":0},{"$f":"'K90 - time schedule'!AQ32","v":0},{"$f":"'K90 - time schedule'!AR32","v":0},{"$f":"'K90 - time schedule'!AS32","v":0},{"$f":"'K90 - time schedule'!AT32","v":0},{"$f":"'K90 - time schedule'!AU32","v":0},{"$f":"'K90 - time schedule'!AV32","v":0},{"$f":"'K90 - time schedule'!AW32","v":0},{"$f":"'K90 - time schedule'!AX32","v":0},{"$f":"'K90 - time schedule'!AY32","v":0},{"$f":"'K90 - time schedule'!AZ32","v":0},{"$f":"'K90 - time schedule'!BA32","v":0},{"$f":"'K90 - time schedule'!BB32","v":0},{"$f":"'K90 - time schedule'!BC32","v":0},{"$f":"'K90 - time schedule'!BD32","v":0},{"$f":"'K90 - time schedule'!BE32","v":0},{"$f":"'K90 - time schedule'!BF32","v":0},{"$f":"'K90 - time schedule'!BG32","v":0},{"$f":"'K90 - time schedule'!BH32","v":0},{"$f":"'K90 - time schedule'!BI32","v":0},{"$f":"'K90 - time schedule'!BJ32","v":0},{"$f":"'K90 - time schedule'!BK32","v":0},{"$f":"'K90 - time schedule'!BL32","v":0},{"$f":"'K90 - time schedule'!BM32","v":0},{"$f":"'K90 - time schedule'!BN32","v":0},{"$f":"'K90 - time schedule'!BO32","v":0},{"$f":"'K90 - time schedule'!BP32","v":0},{"$f":"'K90 - time schedule'!BQ32","v":0},{"$f":"'K90 - time schedule'!BR32","v":0},{"$f":"'K90 - time schedule'!BS32","v":0},{"$f":"'K90 - time schedule'!BT32","v":0},{"$f":"'K90 - time schedule'!BU32","v":0},{"$f":"'K90 - time schedule'!BV32","v":0},{"$f":"'K90 - time schedule'!BW32","v":0},{"$f":"'K90 - time schedule'!BX32","v":0},{"$f":"'K90 - time schedule'!BY32","v":0},{"$f":"'K90 - time schedule'!BZ32","v":0},{"$f":"'K90 - time schedule'!CA32","v":0},{"$f":"'K90 - time schedule'!CB32","v":0},{"$f":"'K90 - time schedule'!CC32","v":0},{"$f":"'K90 - time schedule'!CD32","v":0},{"$f":"'K90 - time schedule'!CE32","v":0},{"$f":"'K90 - time schedule'!CF32","v":0},{"$f":"'K90 - time schedule'!CG32","v":0},{"$f":"'K90 - time schedule'!CH32","v":0},{"$f":"'K90 - time schedule'!CI32","v":0},{"$f":"'K90 - time schedule'!CJ32","v":0},{"$f":"'K90 - time schedule'!CK32","v":0},{"$f":"'K90 - time schedule'!CL32","v":0},{"$f":"'K90 - time schedule'!CM32","v":0},{"$f":"'K90 - time schedule'!CN32","v":0},{"$f":"'K90 - time schedule'!CO32","v":0},{"$f":"'K90 - time schedule'!CP32","v":0},{"$f":"'K90 - time schedule'!CQ32","v":0},{"$f":"'K90 - time schedule'!CR32","v":0},{"$f":"'K90 - time schedule'!CS32","v":0},{"$f":"'K90 - time schedule'!CT32","v":0},{"$f":"'K90 - time schedule'!CU32","v":0},{"$f":"'K90 - time schedule'!CV32","v":0},{"$f":"'K90 - time schedule'!CW32","v":0},{"$f":"'K90 - time schedule'!CX32","v":0},{"$f":"'K90 - time schedule'!CY32","v":0},{"$f":"'K90 - time schedule'!CZ32","v":0},{"$f":"'K90 - time schedule'!DA32","v":0},{"$f":"'K90 - time schedule'!DB32","v":0},{"$f":"'K90 - time schedule'!DC32","v":0},{"$f":"'K90 - time schedule'!DD32","v":0},{"$f":"'K90 - time schedule'!DE32","v":0},{"$f":"'K90 - time schedule'!DF32","v":0},{"$f":"'K90 - time schedule'!DG32","v":0},{"$f":"'K90 - time schedule'!DH32","v":0},{"$f":"'K90 - time schedule'!DI32","v":0},{"$f":"'K90 - time schedule'!DJ32","v":0},{"$f":"'K90 - time schedule'!DK32","v":0},{"$f":"'K90 - time schedule'!DL32","v":0},{"$f":"'K90 - time schedule'!DM32","v":0},{"$f":"'K90 - time schedule'!DN32","v":0},{"$f":"'K90 - time schedule'!DO32","v":0},{"$f":"'K90 - time schedule'!DP32","v":0},{"$f":"'K90 - time schedule'!DQ32","v":0},{"$f":"'K90 - time schedule'!DR32","v":0},{"$f":"'K90 - time schedule'!DS32","v":0},{"$f":"'K90 - time schedule'!DT32","v":0},{"$f":"'K90 - time schedule'!DU32","v":0},{"$f":"'K90 - time schedule'!DV32","v":0},{"$f":"'K90 - time schedule'!DW32","v":0},{"$f":"'K90 - time schedule'!DX32","v":0},{"$f":"'K90 - time schedule'!DY32","v":0},{"$f":"'K90 - time schedule'!DZ32","v":0},{"$f":"'K90 - time schedule'!EA32","v":0},{"$f":"'K90 - time schedule'!EB32","v":0},{"$f":"'K90 - time schedule'!EC32","v":0},{"$f":"'K90 - time schedule'!ED32","v":0},{"$f":"'K90 - time schedule'!EE32","v":0},{"$f":"'K90 - time schedule'!EF32","v":0},{"$f":"'K90 - time schedule'!EG32","v":0},{"$f":"'K90 - time schedule'!EH32","v":0},{"$f":"'K90 - time schedule'!EI32","v":0},{"$f":"'K90 - time schedule'!EJ32","v":0},{"$f":"'K90 - time schedule'!EK32","v":0},{"$f":"'K90 - time schedule'!EL32","v":0},{"$f":"'K90 - time schedule'!EM32","v":0},{"$f":"'K90 - time schedule'!EN32","v":0},{"$f":"'K90 - time schedule'!EO32","v":0},{"$f":"'K90 - time schedule'!EP32","v":0},{"$f":"'K90 - time schedule'!EQ32","v":0},{"$f":"'K90 - time schedule'!ER32","v":0},{"$f":"'K90 - time schedule'!ES32","v":0},{"$f":"'K90 - time schedule'!ET32","v":0},{"$f":"'K90 - time schedule'!EU32","v":0},{"$f":"'K90 - time schedule'!EV32","v":0},{"$f":"'K90 - time schedule'!EW32","v":0},{"$f":"'K90 - time schedule'!EX32","v":0},{"$f":"'K90 - time schedule'!EY32","v":0},{"$f":"'K90 - time schedule'!EZ32","v":0},{"$f":"'K90 - time schedule'!FA32","v":0},{"$f":"'K90 - time schedule'!FB32","v":0},{"$f":"'K90 - time schedule'!FC32","v":0},{"$f":"'K90 - time schedule'!FD32","v":0},{"$f":"'K90 - time schedule'!FE32","v":0},{"$f":"'K90 - time schedule'!FF32","v":0},{"$f":"'K90 - time schedule'!FG32","v":0},{"$f":"'K90 - time schedule'!FH32","v":0},{"$f":"'K90 - time schedule'!FI32","v":0},{"$f":"'K90 - time schedule'!FJ32","v":0},{"$f":"'K90 - time schedule'!FK32","v":0},{"$f":"'K90 - time schedule'!FL32","v":0},{"$f":"'K90 - time schedule'!FM32","v":0},{"$f":"'K90 - time schedule'!FN32","v":0},{"$f":"'K90 - time schedule'!FO32","v":0},{"$f":"'K90 - time schedule'!FP32","v":0},{"$f":"'K90 - time schedule'!FQ32","v":0},{"$f":"'K90 - time schedule'!FR32","v":0},{"$f":"'K90 - time schedule'!FS32","v":0},{"$f":"'K90 - time schedule'!FT32","v":0},{"$f":"'K90 - time schedule'!FU32","v":0},{"$f":"'K90 - time schedule'!FV32","v":0},{"$f":"'K90 - time schedule'!FW32","v":0},{"$f":"'K90 - time schedule'!FX32","v":0},{"$f":"'K90 - time schedule'!FY32","v":0},{"$f":"'K90 - time schedule'!FZ32","v":0},{"$f":"'K90 - time schedule'!GA32","v":0},{"$f":"'K90 - time schedule'!GB32","v":0},{"$f":"'K90 - time schedule'!GC32","v":0},{"$f":"'K90 - time schedule'!GD32","v":0},{"$f":"'K90 - time schedule'!GE32","v":0},{"$f":"'K90 - time schedule'!GF32","v":0},{"$f":"'K90 - time schedule'!GG32","v":0},{"$f":"'K90 - time schedule'!GH32","v":0},{"$f":"'K90 - time schedule'!GI32","v":0},{"$f":"'K90 - time schedule'!GJ32","v":0},{"$f":"'K90 - time schedule'!GK32","v":0},{"$f":"'K90 - time schedule'!GL32","v":0},{"$f":"'K90 - time schedule'!GM32","v":0},{"$f":"'K90 - time schedule'!GN32","v":0},{"$f":"'K90 - time schedule'!GO32","v":0},{"$f":"'K90 - time schedule'!GP32","v":0},{"$f":"'K90 - time schedule'!GQ32","v":0},{"$f":"'K90 - time schedule'!GR32","v":0},{"$f":"'K90 - time schedule'!GS32","v":0},{"$f":"'K90 - time schedule'!GT32","v":0},{"$f":"'K90 - time schedule'!GU32","v":0},{"$f":"'K90 - time schedule'!GV32","v":0},{"$f":"'K90 - time schedule'!GW32","v":0},{"$f":"'K90 - time schedule'!GX32","v":0},{"$f":"'K90 - time schedule'!GY32","v":0},{"$f":"'K90 - time schedule'!GZ32","v":0},{"$f":"'K90 - time schedule'!HA32","v":0},{"$f":"'K90 - time schedule'!HB32","v":0},{"$f":"'K90 - time schedule'!HC32","v":0},{"$f":"'K90 - time schedule'!HD32","v":0},{"$f":"'K90 - time schedule'!HE32","v":0},{"$f":"'K90 - time schedule'!HF32","v":0},{"$f":"'K90 - time schedule'!HG32","v":0},{"$f":"'K90 - time schedule'!HH32","v":0},{"$f":"'K90 - time schedule'!HI32","v":0},{"$f":"'K90 - time schedule'!HJ32","v":0},{"$f":"'K90 - time schedule'!HK32","v":0},{"$f":"'K90 - time schedule'!HL32","v":0},{"$f":"'K90 - time schedule'!HM32","v":0},{"$f":"'K90 - time schedule'!HN32","v":0},{"$f":"'K90 - time schedule'!HO32","v":0},{"$f":"'K90 - time schedule'!HP32","v":0},{"$f":"'K90 - time schedule'!HQ32","v":0},{"$f":"'K90 - time schedule'!HR32","v":0},{"$f":"'K90 - time schedule'!HS32","v":0},{"$f":"'K90 - time schedule'!HT32","v":0},{"$f":"'K90 - time schedule'!HU32","v":0},{"$f":"'K90 - time schedule'!HV32","v":0},{"$f":"'K90 - time schedule'!HW32","v":0},{"$f":"'K90 - time schedule'!HX32","v":0},{"$f":"'K90 - time schedule'!HY32","v":0},{"$f":"'K90 - time schedule'!HZ32","v":0},{"$f":"'K90 - time schedule'!IA32","v":0},{"$f":"'K90 - time schedule'!IB32","v":0},{"$f":"'K90 - time schedule'!IC32","v":0},{"$f":"'K90 - time schedule'!ID32","v":0},{"$f":"'K90 - time schedule'!IE32","v":0},{"$f":"'K90 - time schedule'!IF32","v":0},{"$f":"'K90 - time schedule'!IG32","v":0},{"$f":"'K90 - time schedule'!IH32","v":0},{"$f":"'K90 - time schedule'!II32","v":0},{"$f":"'K90 - time schedule'!IJ32","v":0},{"$f":"'K90 - time schedule'!IK32","v":0},{"$f":"'K90 - time schedule'!IL32","v":0},{"$f":"'K90 - time schedule'!IM32","v":0},{"$f":"'K90 - time schedule'!IN32","v":0},{"$f":"'K90 - time schedule'!IO32","v":0},{"$f":"'K90 - time schedule'!IP32","v":0},{"$f":"'K90 - time schedule'!IQ32","v":0},{"$f":"'K90 - time schedule'!IR32","v":0},{"$f":"'K90 - time schedule'!IS32","v":0},{"$f":"'K90 - time schedule'!IT32","v":0},{"$f":"'K90 - time schedule'!IU32","v":0},{"$f":"'K90 - time schedule'!IV32","v":0},{"$f":"'K90 - time schedule'!IW32","v":0},{"$f":"'K90 - time schedule'!IX32","v":0},{"$f":"'K90 - time schedule'!IY32","v":0},{"$f":"'K90 - time schedule'!IZ32","v":0},{"$f":"'K90 - time schedule'!JA32","v":0},{"$f":"'K90 - time schedule'!JB32","v":0},{"$f":"'K90 - time schedule'!JC32","v":0},{"$f":"'K90 - time schedule'!JD32","v":0},{"$f":"'K90 - time schedule'!JE32","v":0},{"$f":"'K90 - time schedule'!JF32","v":0},{"$f":"'K90 - time schedule'!JG32","v":0},{"$f":"'K90 - time schedule'!JH32","v":0},{"$f":"'K90 - time schedule'!JI32","v":0},{"$f":"'K90 - time schedule'!JJ32","v":0},{"$f":"'K90 - time schedule'!JK32","v":0},{"$f":"'K90 - time schedule'!JL32","v":0},{"$f":"'K90 - time schedule'!JM32","v":0},{"$f":"'K90 - time schedule'!JN32","v":0},{"$f":"'K90 - time schedule'!JO32","v":0},{"$f":"'K90 - time schedule'!JP32","v":0},{"$f":"'K90 - time schedule'!JQ32","v":0},{"$f":"'K90 - time schedule'!JR32","v":0},{"$f":"'K90 - time schedule'!JS32","v":0},{"$f":"'K90 - time schedule'!JT32","v":0},{"$f":"'K90 - time schedule'!JU32","v":0},{"$f":"'K90 - time schedule'!JV32","v":0},{"$f":"'K90 - time schedule'!JW32","v":0},{"$f":"'K90 - time schedule'!JX32","v":0},{"$f":"'K90 - time schedule'!JY32","v":0},{"$f":"'K90 - time schedule'!JZ32","v":0},{"$f":"'K90 - time schedule'!KA32","v":0},{"$f":"'K90 - time schedule'!KB32","v":0},{"$f":"'K90 - time schedule'!KC32","v":0},{"$f":"'K90 - time schedule'!KD32","v":0},{"$f":"'K90 - time schedule'!KE32","v":0},{"$f":"'K90 - time schedule'!KF32","v":0},{"$f":"'K90 - time schedule'!KG32","v":0},{"$f":"'K90 - time schedule'!KH32","v":0},{"$f":"'K90 - time schedule'!KI32","v":0},{"$f":"'K90 - time schedule'!KJ32","v":0},{"$f":"'K90 - time schedule'!KK32","v":0},{"$f":"'K90 - time schedule'!KL32","v":0},{"$f":"'K90 - time schedule'!KM32","v":0},{"$f":"'K90 - time schedule'!KN32","v":0},{"$f":"'K90 - time schedule'!KO32","v":0},{"$f":"'K90 - time schedule'!KP32","v":0},{"$f":"'K90 - time schedule'!KQ32","v":0},{"$f":"'K90 - time schedule'!KR32","v":0},{"$f":"'K90 - time schedule'!KS32","v":0},{"$f":"'K90 - time schedule'!KT32","v":0}]
["Boiler room K90 - bottom of combustion chamber","K90",{"$f":"'K90 - time schedule'!G34","v":0},{"$f":"'K90 - time schedule'!H34","v":0},{"$f":"'K90 - time schedule'!I34","v":0},{"$f":"'K90 - time schedule'!J34","v":0},{"$f":"'K90 - time schedule'!K34","v":0},{"$f":"'K90 - time schedule'!L34","v":0},{"$f":"'K90 - time schedule'!M34","v":0},{"$f":"'K90 - time schedule'!N34","v":0},{"$f":"'K90 - time schedule'!O34","v":0},{"$f":"'K90 - time schedule'!P34","v":0},{"$f":"'K90 - time schedule'!Q34","v":0},{"$f":"'K90 - time schedule'!R34","v":0},{"$f":"'K90 - time schedule'!S34","v":0},{"$f":"'K90 - time schedule'!T34","v":0},{"$f":"'K90 - time schedule'!U34","v":0},{"$f":"'K90 - time schedule'!V34","v":0},{"$f":"'K90 - time schedule'!W34","v":0},{"$f":"'K90 - time schedule'!X34","v":0},{"$f":"'K90 - time schedule'!Y34","v":0},{"$f":"'K90 - time schedule'!Z34","v":0},{"$f":"'K90 - time schedule'!AA34","v":0},{"$f":"'K90 - time schedule'!AB34","v":0},{"$f":"'K90 - time schedule'!AC34","v":0},{"$f":"'K90 - time schedule'!AD34","v":0},{"$f":"'K90 - time schedule'!AE34","v":0},{"$f":"'K90 - time schedule'!AF34","v":0},{"$f":"'K90 - time schedule'!AG34","v":0},{"$f":"'K90 - time schedule'!AH34","v":0},{"$f":"'K90 - time schedule'!AI34","v":0},{"$f":"'K90 - time schedule'!AJ34","v":0},{"$f":"'K90 - time schedule'!AK34","v":0},{"$f":"'K90 - time schedule'!AL34","v":0},{"$f":"'K90 - time schedule'!AM34","v":0},{"$f":"'K90 - time schedule'!AN34","v":0},{"$f":"'K90 - time schedule'!AO34","v":0},{"$f":"'K90 - time schedule'!AP34","v":0},{"$f":"'K90 - time schedule'!AQ34","v":0},{"$f":"'K90 - time schedule'!AR34","v":0},{"$f":"'K90 - time schedule'!AS34","v":0},{"$f":"'K90 - time schedule'!AT34","v":0},{"$f":"'K90 - time schedule'!AU34","v":0},{"$f":"'K90 - time schedule'!AV34","v":0},{"$f":"'K90 - time schedule'!AW34","v":0},{"$f":"'K90 - time schedule'!AX34","v":0},{"$f":"'K90 - time schedule'!AY34","v":0},{"$f":"'K90 - time schedule'!AZ34","v":0},{"$f":"'K90 - time schedule'!BA34","v":0},{"$f":"'K90 - time schedule'!BB34","v":0},{"$f":"'K90 - time schedule'!BC34","v":0},{"$f":"'K90 - time schedule'!BD34","v":0},{"$f":"'K90 - time schedule'!BE34","v":0},{"$f":"'K90 - time schedule'!BF34","v":0},{"$f":"'K90 - time schedule'!BG34","v":0},{"$f":"'K90 - time schedule'!BH34","v":0},{"$f":"'K90 - time schedule'!BI34","v":0},{"$f":"'K90 - time schedule'!BJ34","v":0},{"$f":"'K90 - time schedule'!BK34","v":0},{"$f":"'K90 - time schedule'!BL34","v":0},{"$f":"'K90 - time schedule'!BM34","v":0},{"$f":"'K90 - time schedule'!BN34","v":0},{"$f":"'K90 - time schedule'!BO34","v":0},{"$f":"'K90 - time schedule'!BP34","v":0},{"$f":"'K90 - time schedule'!BQ34","v":0},{"$f":"'K90 - time schedule'!BR34","v":0},{"$f":"'K90 - time schedule'!BS34","v":0},{"$f":"'K90 - time schedule'!BT34","v":0},{"$f":"'K90 - time schedule'!BU34","v":0},{"$f":"'K90 - time schedule'!BV34","v":0},{"$f":"'K90 - time schedule'!BW34","v":0},{"$f":"'K90 - time schedule'!BX34","v":0},{"$f":"'K90 - time schedule'!BY34","v":0},{"$f":"'K90 - time schedule'!BZ34","v":0},{"$f":"'K90 - time schedule'!CA34","v":0},{"$f":"'K90 - time schedule'!CB34","v":0},{"$f":"'K90 - time schedule'!CC34","v":0},{"$f":"'K90 - time schedule'!CD34","v":0},{"$f":"'K90 - time schedule'!CE34","v":0},{"$f":"'K90 - time schedule'!CF34","v":0},{"$f":"'K90 - time schedule'!CG34","v":0},{"$f":"'K90 - time schedule'!CH34","v":0},{"$f":"'K90 - time schedule'!CI34","v":0},{"$f":"'K90 - time schedule'!CJ34","v":0},{"$f":"'K90 - time schedule'!CK34","v":0},{"$f":"'K90 - time schedule'!CL34","v":0},{"$f":"'K90 - time schedule'!CM34","v":0},{"$f":"'K90 - time schedule'!CN34","v":0},{"$f":"'K90 - time schedule'!CO34","v":0},{"$f":"'K90 - time schedule'!CP34","v":0},{"$f":"'K90 - time schedule'!CQ34","v":0},{"$f":"'K90 - time schedule'!CR34","v":0},{"$f":"'K90 - time schedule'!CS34","v":0},{"$f":"'K90 - time schedule'!CT34","v":0},{"$f":"'K90 - time schedule'!CU34","v":0},{"$f":"'K90 - time schedule'!CV34","v":0},{"$f":"'K90 - time schedule'!CW34","v":0},{"$f":"'K90 - time schedule'!CX34","v":0},{"$f":"'K90 - time schedule'!CY34","v":0},{"$f":"'K90 - time schedule'!CZ34","v":0},{"$f":"'K90 - time schedule'!DA34","v":0},{"$f":"'K90 - time schedule'!DB34","v":0},{"$f":"'K90 - time schedule'!DC34","v":0},{"$f":"'K90 - time schedule'!DD34","v":0},{"$f":"'K90 - time schedule'!DE34","v":0},{"$f":"'K90 - time schedule'!DF34","v":0},{"$f":"'K90 - time schedule'!DG34","v":0},{"$f":"'K90 - time schedule'!DH34","v":0},{"$f":"'K90 - time schedule'!DI34","v":0},{"$f":"'K90 - time schedule'!DJ34","v":0},{"$f":"'K90 - time schedule'!DK34","v":0},{"$f":"'K90 - time schedule'!DL34","v":0},{"$f":"'K90 - time schedule'!DM34","v":0},{"$f":"'K90 - time schedule'!DN34","v":0},{"$f":"'K90 - time schedule'!DO34","v":0},{"$f":"'K90 - time schedule'!DP34","v":0},{"$f":"'K90 - time schedule'!DQ34","v":0},{"$f":"'K90 - time schedule'!DR34","v":0},{"$f":"'K90 - time schedule'!DS34","v":0},{"$f":"'K90 - time schedule'!DT34","v":0},{"$f":"'K90 - time schedule'!DU34","v":0},{"$f":"'K90 - time schedule'!DV34","v":0},{"$f":"'K90 - time schedule'!DW34","v":0},{"$f":"'K90 - time schedule'!DX34","v":0},{"$f":"'K90 - time schedule'!DY34","v":0},{"$f":"'K90 - time schedule'!DZ34","v":0},{"$f":"'K90 - time schedule'!EA34","v":0},{"$f":"'K90 - time schedule'!EB34","v":0},{"$f":"'K90 - time schedule'!EC34","v":0},{"$f":"'K90 - time schedule'!ED34","v":0},{"$f":"'K90 - time schedule'!EE34","v":0},{"$f":"'K90 - time schedule'!EF34","v":0},{"$f":"'K90 - time schedule'!EG34","v":0},{"$f":"'K90 - time schedule'!EH34","v":0},{"$f":"'K90 - time schedule'!EI34","v":0},{"$f":"'K90 - time schedule'!EJ34","v":0},{"$f":"'K90 - time schedule'!EK34","v":0},{"$f":"'K90 - time schedule'!EL34","v":0},{"$f":"'K90 - time schedule'!EM34","v":0},{"$f":"'K90 - time schedule'!EN34","v":0},{"$f":"'K90 - time schedule'!EO34","v":0},{"$f":"'K90 - time schedule'!EP34","v":0},{"$f":"'K90 - time schedule'!EQ34","v":0},{"$f":"'K90 - time schedule'!ER34","v":0},{"$f":"'K90 - time schedule'!ES34","v":0},{"$f":"'K90 - time schedule'!ET34","v":0},{"$f":"'K90 - time schedule'!EU34","v":0},{"$f":"'K90 - time schedule'!EV34","v":0},{"$f":"'K90 - time schedule'!EW34","v":0},{"$f":"'K90 - time schedule'!EX34","v":0},{"$f":"'K90 - time schedule'!EY34","v":0},{"$f":"'K90 - time schedule'!EZ34","v":0},{"$f":"'K90 - time schedule'!FA34","v":0},{"$f":"'K90 - time schedule'!FB34","v":0},{"$f":"'K90 - time schedule'!FC34","v":0},{"$f":"'K90 - time schedule'!FD34","v":0},{"$f":"'K90 - time schedule'!FE34","v":0},{"$f":"'K90 - time schedule'!FF34","v":0},{"$f":"'K90 - time schedule'!FG34","v":0},{"$f":"'K90 - time schedule'!FH34","v":0},{"$f":"'K90 - time schedule'!FI34","v":0},{"$f":"'K90 - time schedule'!FJ34","v":0},{"$f":"'K90 - time schedule'!FK34","v":0},{"$f":"'K90 - time schedule'!FL34","v":0},{"$f":"'K90 - time schedule'!FM34","v":0},{"$f":"'K90 - time schedule'!FN34","v":0},{"$f":"'K90 - time schedule'!FO34","v":0},{"$f":"'K90 - time schedule'!FP34","v":0},{"$f":"'K90 - time schedule'!FQ34","v":0},{"$f":"'K90 - time schedule'!FR34","v":0},{"$f":"'K90 - time schedule'!FS34","v":0},{"$f":"'K90 - time schedule'!FT34","v":0},{"$f":"'K90 - time schedule'!FU34","v":0},{"$f":"'K90 - time schedule'!FV34","v":0},{"$f":"'K90 - time schedule'!FW34","v":0},{"$f":"'K90 - time schedule'!FX34","v":0},{"$f":"'K90 - time schedule'!FY34","v":0},{"$f":"'K90 - time schedule'!FZ34","v":0},{"$f":"'K90 - time schedule'!GA34","v":0},{"$f":"'K90 - time schedule'!GB34","v":0},{"$f":"'K90 - time schedule'!GC34","v":0},{"$f":"'K90 - time schedule'!GD34","v":0},{"$f":"'K90 - time schedule'!GE34","v":0},{"$f":"'K90 - time schedule'!GF34","v":0},{"$f":"'K90 - time schedule'!GG34","v":0},{"$f":"'K90 - time schedule'!GH34","v":0},{"$f":"'K90 - time schedule'!GI34","v":0},{"$f":"'K90 - time schedule'!GJ34","v":0},{"$f":"'K90 - time schedule'!GK34","v":0},{"$f":"'K90 - time schedule'!GL34","v":0},{"$f":"'K90 - time schedule'!GM34","v":0},{"$f":"'K90 - time schedule'!GN34","v":0},{"$f":"'K90 - time schedule'!GO34","v":0},{"$f":"'K90 - time schedule'!GP34","v":0},{"$f":"'K90 - time schedule'!GQ34","v":0},{"$f":"'K90 - time schedule'!GR34","v":0},{"$f":"'K90 - time schedule'!GS34","v":0},{"$f":"'K90 - time schedule'!GT34","v":0},{"$f":"'K90 - time schedule'!GU34","v":0},{"$f":"'K90 - time schedule'!GV34","v":0},{"$f":"'K90 - time schedule'!GW34","v":0},{"$f":"'K90 - time schedule'!GX34","v":0},{"$f":"'K90 - time schedule'!GY34","v":0},{"$f":"'K90 - time schedule'!GZ34","v":0},{"$f":"'K90 - time schedule'!HA34","v":0},{"$f":"'K90 - time schedule'!HB34","v":0},{"$f":"'K90 - time schedule'!HC34","v":0},{"$f":"'K90 - time schedule'!HD34","v":0},{"$f":"'K90 - time schedule'!HE34","v":0},{"$f":"'K90 - time schedule'!HF34","v":0},{"$f":"'K90 - time schedule'!HG34","v":0},{"$f":"'K90 - time schedule'!HH34","v":0},{"$f":"'K90 - time schedule'!HI34","v":0},{"$f":"'K90 - time schedule'!HJ34","v":0},{"$f":"'K90 - time schedule'!HK34","v":0},{"$f":"'K90 - time schedule'!HL34","v":0},{"$f":"'K90 - time schedule'!HM34","v":0},{"$f":"'K90 - time schedule'!HN34","v":0},{"$f":"'K90 - time schedule'!HO34","v":0},{"$f":"'K90 - time schedule'!HP34","v":0},{"$f":"'K90 - time schedule'!HQ34","v":0},{"$f":"'K90 - time schedule'!HR34","v":0},{"$f":"'K90 - time schedule'!HS34","v":0},{"$f":"'K90 - time schedule'!HT34","v":0},{"$f":"'K90 - time schedule'!HU34","v":0},{"$f":"'K90 - time schedule'!HV34","v":0},{"$f":"'K90 - time schedule'!HW34","v":0},{"$f":"'K90 - time schedule'!HX34","v":0},{"$f":"'K90 - time schedule'!HY34","v":0},{"$f":"'K90 - time schedule'!HZ34","v":0},{"$f":"'K90 - time schedule'!IA34","v":0},{"$f":"'K90 - time schedule'!IB34","v":0},{"$f":"'K90 - time schedule'!IC34","v":0},{"$f":"'K90 - time schedule'!ID34","v":0},{"$f":"'K90 - time schedule'!IE34","v":0},{"$f":"'K90 - time schedule'!IF34","v":0},{"$f":"'K90 - time schedule'!IG34","v":0},{"$f":"'K90 - time schedule'!IH34","v":0},{"$f":"'K90 - time schedule'!II34","v":0},{"$f":"'K90 - time schedule'!IJ34","v":0},{"$f":"'K90 - time schedule'!IK34","v":0},{"$f":"'K90 - time schedule'!IL34","v":0},{"$f":"'K90 - time schedule'!IM34","v":0},{"$f":"'K90 - time schedule'!IN34","v":0},{"$f":"'K90 - time schedule'!IO34","v":0},{"$f":"'K90 - time schedule'!IP34","v":0},{"$f":"'K90 - time schedule'!IQ34","v":0},{"$f":"'K90 - time schedule'!IR34","v":0},{"$f":"'K90 - time schedule'!IS34","v":0},{"$f":"'K90 - time schedule'!IT34","v":0},{"$f":"'K90 - time schedule'!IU34","v":0},{"$f":"'K90 - time schedule'!IV34","v":0},{"$f":"'K90 - time schedule'!IW34","v":0},{"$f":"'K90 - time schedule'!IX34","v":0},{"$f":"'K90 - time schedule'!IY34","v":0},{"$f":"'K90 - time schedule'!IZ34","v":0},{"$f":"'K90 - time schedule'!JA34","v":0},{"$f":"'K90 - time schedule'!JB34","v":0},{"$f":"'K90 - time schedule'!JC34","v":0},{"$f":"'K90 - time schedule'!JD34","v":0},{"$f":"'K90 - time schedule'!JE34","v":0},{"$f":"'K90 - time schedule'!JF34","v":0},{"$f":"'K90 - time schedule'!JG34","v":0},{"$f":"'K90 - time schedule'!JH34","v":0},{"$f":"'K90 - time schedule'!JI34","v":0},{"$f":"'K90 - time schedule'!JJ34","v":0},{"$f":"'K90 - time schedule'!JK34","v":0},{"$f":"'K90 - time schedule'!JL34","v":0},{"$f":"'K90 - time schedule'!JM34","v":0},{"$f":"'K90 - time schedule'!JN34","v":0},{"$f":"'K90 - time schedule'!JO34","v":0},{"$f":"'K90 - time schedule'!JP34","v":0},{"$f":"'K90 - time schedule'!JQ34","v":0},{"$f":"'K90 - time schedule'!JR34","v":0},{"$f":"'K90 - time schedule'!JS34","v":0},{"$f":"'K90 - time schedule'!JT34","v":0},{"$f":"'K90 - time schedule'!JU34","v":0},{"$f":"'K90 - time schedule'!JV34","v":0},{"$f":"'K90 - time schedule'!JW34","v":0},{"$f":"'K90 - time schedule'!JX34","v":0},{"$f":"'K90 - time schedule'!JY34","v":0},{"$f":"'K90 - time schedule'!JZ34","v":0},{"$f":"'K90 - time schedule'!KA34","v":0},{"$f":"'K90 - time schedule'!KB34","v":0},{"$f":"'K90 - time schedule'!KC34","v":0},{"$f":"'K90 - time schedule'!KD34","v":0},{"$f":"'K90 - time schedule'!KE34","v":0},{"$f":"'K90 - time schedule'!KF34","v":0},{"$f":"'K90 - time schedule'!KG34","v":0},{"$f":"'K90 - time schedule'!KH34","v":0},{"$f":"'K90 - time schedule'!KI34","v":0},{"$f":"'K90 - time schedule'!KJ34","v":0},{"$f":"'K90 - time schedule'!KK34","v":0},{"$f":"'K90 - time schedule'!KL34","v":0},{"$f":"'K90 - time schedule'!KM34","v":0},{"$f":"'K90 - time schedule'!KN34","v":0},{"$f":"'K90 - time schedule'!KO34","v":0},{"$f":"'K90 - time schedule'!KP34","v":0},{"$f":"'K90 - time schedule'!KQ34","v":0},{"$f":"'K90 - time schedule'!KR34","v":0},{"$f":"'K90 - time schedule'!KS34","v":0},{"$f":"'K90 - time schedule'!KT34","v":0}]
["Boiler room K90 - flue lines, including fabric filter","K90",{"$f":"'K90 - time schedule'!G36","v":0},{"$f":"'K90 - time schedule'!H36","v":0},{"$f":"'K90 - time schedule'!I36","v":0},{"$f":"'K90 - time schedule'!J36","v":0},{"$f":"'K90 - time schedule'!K36","v":0},{"$f":"'K90 - time schedule'!L36","v":0},{"$f":"'K90 - time schedule'!M36","v":0},{"$f":"'K90 - time schedule'!N36","v":0},{"$f":"'K90 - time schedule'!O36","v":0},{"$f":"'K90 - time schedule'!P36","v":0},{"$f":"'K90 - time schedule'!Q36","v":0},{"$f":"'K90 - time schedule'!R36","v":0},{"$f":"'K90 - time schedule'!S36","v":0},{"$f":"'K90 - time schedule'!T36","v":0},{"$f":"'K90 - time schedule'!U36","v":0},{"$f":"'K90 - time schedule'!V36","v":0},{"$f":"'K90 - time schedule'!W36","v":0},{"$f":"'K90 - time schedule'!X36","v":0},{"$f":"'K90 - time schedule'!Y36","v":0},{"$f":"'K90 - time schedule'!Z36","v":0},{"$f":"'K90 - time schedule'!AA36","v":0},{"$f":"'K90 - time schedule'!AB36","v":0},{"$f":"'K90 - time schedule'!AC36","v":0},{"$f":"'K90 - time schedule'!AD36","v":0},{"$f":"'K90 - time schedule'!AE36","v":0},{"$f":"'K90 - time schedule'!AF36","v":0},{"$f":"'K90 - time schedule'!AG36","v":0},{"$f":"'K90 - time schedule'!AH36","v":0},{"$f":"'K90 - time schedule'!AI36","v":0},{"$f":"'K90 - time schedule'!AJ36","v":0},{"$f":"'K90 - time schedule'!AK36","v":0},{"$f":"'K90 - time schedule'!AL36","v":0},{"$f":"'K90 - time schedule'!AM36","v":0},{"$f":"'K90 - time schedule'!AN36","v":0},{"$f":"'K90 - time schedule'!AO36","v":0},{"$f":"'K90 - time schedule'!AP36","v":0},{"$f":"'K90 - time schedule'!AQ36","v":0},{"$f":"'K90 - time schedule'!AR36","v":0},{"$f":"'K90 - time schedule'!AS36","v":0},{"$f":"'K90 - time schedule'!AT36","v":0},{"$f":"'K90 - time schedule'!AU36","v":0},{"$f":"'K90 - time schedule'!AV36","v":0},{"$f":"'K90 - time schedule'!AW36","v":0},{"$f":"'K90 - time schedule'!AX36","v":0},{"$f":"'K90 - time schedule'!AY36","v":0},{"$f":"'K90 - time schedule'!AZ36","v":0},{"$f":"'K90 - time schedule'!BA36","v":0},{"$f":"'K90 - time schedule'!BB36","v":0},{"$f":"'K90 - time schedule'!BC36","v":0},{"$f":"'K90 - time schedule'!BD36","v":0},{"$f":"'K90 - time schedule'!BE36","v":0},{"$f":"'K90 - time schedule'!BF36","v":0},{"$f":"'K90 - time schedule'!BG36","v":0},{"$f":"'K90 - time schedule'!BH36","v":0},{"$f":"'K90 - time schedule'!BI36","v":0},{"$f":"'K90 - time schedule'!BJ36","v":0},{"$f":"'K90 - time schedule'!BK36","v":0},{"$f":"'K90 - time schedule'!BL36","v":0},{"$f":"'K90 - time schedule'!BM36","v":0},{"$f":"'K90 - time schedule'!BN36","v":0},{"$f":"'K90 - time schedule'!BO36","v":0},{"$f":"'K90 - time schedule'!BP36","v":0},{"$f":"'K90 - time schedule'!BQ36","v":0},{"$f":"'K90 - time schedule'!BR36","v":0},{"$f":"'K90 - time schedule'!BS36","v":0},{"$f":"'K90 - time schedule'!BT36","v":0},{"$f":"'K90 - time schedule'!BU36","v":0},{"$f":"'K90 - time schedule'!BV36","v":0},{"$f":"'K90 - time schedule'!BW36","v":0},{"$f":"'K90 - time schedule'!BX36","v":0},{"$f":"'K90 - time schedule'!BY36","v":0},{"$f":"'K90 - time schedule'!BZ36","v":0},{"$f":"'K90 - time schedule'!CA36","v":0},{"$f":"'K90 - time schedule'!CB36","v":0},{"$f":"'K90 - time schedule'!CC36","v":0},{"$f":"'K90 - time schedule'!CD36","v":0},{"$f":"'K90 - time schedule'!CE36","v":0},{"$f":"'K90 - time schedule'!CF36","v":0},{"$f":"'K90 - time schedule'!CG36","v":0},{"$f":"'K90 - time schedule'!CH36","v":0},{"$f":"'K90 - time schedule'!CI36","v":0},{"$f":"'K90 - time schedule'!CJ36","v":0},{"$f":"'K90 - time schedule'!CK36","v":0},{"$f":"'K90 - time schedule'!CL36","v":0},{"$f":"'K90 - time schedule'!CM36","v":0},{"$f":"'K90 - time schedule'!CN36","v":0},{"$f":"'K90 - time schedule'!CO36","v":0},{"$f":"'K90 - time schedule'!CP36","v":0},{"$f":"'K90 - time schedule'!CQ36","v":0},{"$f":"'K90 - time schedule'!CR36","v":0},{"$f":"'K90 - time schedule'!CS36","v":0},{"$f":"'K90 - time schedule'!CT36","v":0},{"$f":"'K90 - time schedule'!CU36","v":0},{"$f":"'K90 - time schedule'!CV36","v":0},{"$f":"'K90 - time schedule'!CW36","v":0},{"$f":"'K90 - time schedule'!CX36","v":0},{"$f":"'K90 - time schedule'!CY36","v":0},{"$f":"'K90 - time schedule'!CZ36","v":0},{"$f":"'K90 - time schedule'!DA36","v":0},{"$f":"'K90 - time schedule'!DB36","v":0},{"$f":"'K90 - time schedule'!DC36","v":0},{"$f":"'K90 - time schedule'!DD36","v":0},{"$f":"'K90 - time schedule'!DE36","v":0},{"$f":"'K90 - time schedule'!DF36","v":0},{"$f":"'K90 - time schedule'!DG36","v":0},{"$f":"'K90 - time schedule'!DH36","v":0},{"$f":"'K90 - time schedule'!DI36","v":0},{"$f":"'K90 - time schedule'!DJ36","v":0},{"$f":"'K90 - time schedule'!DK36","v":0},{"$f":"'K90 - time schedule'!DL36","v":0},{"$f":"'K90 - time schedule'!DM36","v":0},{"$f":"'K90 - time schedule'!DN36","v":0},{"$f":"'K90 - time schedule'!DO36","v":0},{"$f":"'K90 - time schedule'!DP36","v":0},{"$f":"'K90 - time schedule'!DQ36","v":0},{"$f":"'K90 - time schedule'!DR36","v":0},{"$f":"'K90 - time schedule'!DS36","v":0},{"$f":"'K90 - time schedule'!DT36","v":0},{"$f":"'K90 - time schedule'!DU36","v":0},{"$f":"'K90 - time schedule'!DV36","v":0},{"$f":"'K90 - time schedule'!DW36","v":0},{"$f":"'K90 - time schedule'!DX36","v":0},{"$f":"'K90 - time schedule'!DY36","v":0},{"$f":"'K90 - time schedule'!DZ36","v":0},{"$f":"'K90 - time schedule'!EA36","v":0},{"$f":"'K90 - time schedule'!EB36","v":0},{"$f":"'K90 - time schedule'!EC36","v":0},{"$f":"'K90 - time schedule'!ED36","v":0},{"$f":"'K90 - time schedule'!EE36","v":0},{"$f":"'K90 - time schedule'!EF36","v":0},{"$f":"'K90 - time schedule'!EG36","v":0},{"$f":"'K90 - time schedule'!EH36","v":0},{"$f":"'K90 - time schedule'!EI36","v":0},{"$f":"'K90 - time schedule'!EJ36","v":0},{"$f":"'K90 - time schedule'!EK36","v":0},{"$f":"'K90 - time schedule'!EL36","v":0},{"$f":"'K90 - time schedule'!EM36","v":0},{"$f":"'K90 - time schedule'!EN36","v":0},{"$f":"'K90 - time schedule'!EO36","v":0},{"$f":"'K90 - time schedule'!EP36","v":0},{"$f":"'K90 - time schedule'!EQ36","v":0},{"$f":"'K90 - time schedule'!ER36","v":0},{"$f":"'K90 - time schedule'!ES36","v":0},{"$f":"'K90 - time schedule'!ET36","v":0},{"$f":"'K90 - time schedule'!EU36","v":0},{"$f":"'K90 - time schedule'!EV36","v":0},{"$f":"'K90 - time schedule'!EW36","v":0},{"$f":"'K90 - time schedule'!EX36","v":0},{"$f":"'K90 - time schedule'!EY36","v":0},{"$f":"'K90 - time schedule'!EZ36","v":0},{"$f":"'K90 - time schedule'!FA36","v":0},{"$f":"'K90 - time schedule'!FB36","v":0},{"$f":"'K90 - time schedule'!FC36","v":0},{"$f":"'K90 - time schedule'!FD36","v":0},{"$f":"'K90 - time schedule'!FE36","v":0},{"$f":"'K90 - time schedule'!FF36","v":0},{"$f":"'K90 - time schedule'!FG36","v":0},{"$f":"'K90 - time schedule'!FH36","v":0},{"$f":"'K90 - time schedule'!FI36","v":0},{"$f":"'K90 - time schedule'!FJ36","v":0},{"$f":"'K90 - time schedule'!FK36","v":0},{"$f":"'K90 - time schedule'!FL36","v":0},{"$f":"'K90 - time schedule'!FM36","v":0},{"$f":"'K90 - time schedule'!FN36","v":0},{"$f":"'K90 - time schedule'!FO36","v":0},{"$f":"'K90 - time schedule'!FP36","v":0},{"$f":"'K90 - time schedule'!FQ36","v":0},{"$f":"'K90 - time schedule'!FR36","v":0},{"$f":"'K90 - time schedule'!FS36","v":0},{"$f":"'K90 - time schedule'!FT36","v":0},{"$f":"'K90 - time schedule'!FU36","v":0},{"$f":"'K90 - time schedule'!FV36","v":0},{"$f":"'K90 - time schedule'!FW36","v":0},{"$f":"'K90 - time schedule'!FX36","v":0},{"$f":"'K90 - time schedule'!FY36","v":0},{"$f":"'K90 - time schedule'!FZ36","v":0},{"$f":"'K90 - time schedule'!GA36","v":0},{"$f":"'K90 - time schedule'!GB36","v":0},{"$f":"'K90 - time schedule'!GC36","v":0},{"$f":"'K90 - time schedule'!GD36","v":0},{"$f":"'K90 - time schedule'!GE36","v":0},{"$f":"'K90 - time schedule'!GF36","v":0},{"$f":"'K90 - time schedule'!GG36","v":0},{"$f":"'K90 - time schedule'!GH36","v":0},{"$f":"'K90 - time schedule'!GI36","v":0},{"$f":"'K90 - time schedule'!GJ36","v":0},{"$f":"'K90 - time schedule'!GK36","v":0},{"$f":"'K90 - time schedule'!GL36","v":0},{"$f":"'K90 - time schedule'!GM36","v":0},{"$f":"'K90 - time schedule'!GN36","v":0},{"$f":"'K90 - time schedule'!GO36","v":0},{"$f":"'K90 - time schedule'!GP36","v":0},{"$f":"'K90 - time schedule'!GQ36","v":0},{"$f":"'K90 - time schedule'!GR36","v":0},{"$f":"'K90 - time schedule'!GS36","v":0},{"$f":"'K90 - time schedule'!GT36","v":0},{"$f":"'K90 - time schedule'!GU36","v":0},{"$f":"'K90 - time schedule'!GV36","v":0},{"$f":"'K90 - time schedule'!GW36","v":0},{"$f":"'K90 - time schedule'!GX36","v":0},{"$f":"'K90 - time schedule'!GY36","v":0},{"$f":"'K90 - time schedule'!GZ36","v":0},{"$f":"'K90 - time schedule'!HA36","v":0},{"$f":"'K90 - time schedule'!HB36","v":0},{"$f":"'K90 - time schedule'!HC36","v":0},{"$f":"'K90 - time schedule'!HD36","v":0},{"$f":"'K90 - time schedule'!HE36","v":0},{"$f":"'K90 - time schedule'!HF36","v":0},{"$f":"'K90 - time schedule'!HG36","v":0},{"$f":"'K90 - time schedule'!HH36","v":0},{"$f":"'K90 - time schedule'!HI36","v":0},{"$f":"'K90 - time schedule'!HJ36","v":0},{"$f":"'K90 - time schedule'!HK36","v":0},{"$f":"'K90 - time schedule'!HL36","v":0},{"$f":"'K90 - time schedule'!HM36","v":0},{"$f":"'K90 - time schedule'!HN36","v":0},{"$f":"'K90 - time schedule'!HO36","v":0},{"$f":"'K90 - time schedule'!HP36","v":0},{"$f":"'K90 - time schedule'!HQ36","v":0},{"$f":"'K90 - time schedule'!HR36","v":0},{"$f":"'K90 - time schedule'!HS36","v":0},{"$f":"'K90 - time schedule'!HT36","v":0},{"$f":"'K90 - time schedule'!HU36","v":0},{"$f":"'K90 - time schedule'!HV36","v":0},{"$f":"'K90 - time schedule'!HW36","v":0},{"$f":"'K90 - time schedule'!HX36","v":0},{"$f":"'K90 - time schedule'!HY36","v":0},{"$f":"'K90 - time schedule'!HZ36","v":0},{"$f":"'K90 - time schedule'!IA36","v":0},{"$f":"'K90 - time schedule'!IB36","v":0},{"$f":"'K90 - time schedule'!IC36","v":0},{"$f":"'K90 - time schedule'!ID36","v":0},{"$f":"'K90 - time schedule'!IE36","v":0},{"$f":"'K90 - time schedule'!IF36","v":0},{"$f":"'K90 - time schedule'!IG36","v":0},{"$f":"'K90 - time schedule'!IH36","v":0},{"$f":"'K90 - time schedule'!II36","v":0},{"$f":"'K90 - time schedule'!IJ36","v":0},{"$f":"'K90 - time schedule'!IK36","v":0},{"$f":"'K90 - time schedule'!IL36","v":0},{"$f":"'K90 - time schedule'!IM36","v":0},{"$f":"'K90 - time schedule'!IN36","v":0},{"$f":"'K90 - time schedule'!IO36","v":0},{"$f":"'K90 - time schedule'!IP36","v":0},{"$f":"'K90 - time schedule'!IQ36","v":0},{"$f":"'K90 - time schedule'!IR36","v":0},{"$f":"'K90 - time schedule'!IS36","v":0},{"$f":"'K90 - time schedule'!IT36","v":0},{"$f":"'K90 - time schedule'!IU36","v":0},{"$f":"'K90 - time schedule'!IV36","v":0},{"$f":"'K90 - time schedule'!IW36","v":0},{"$f":"'K90 - time schedule'!IX36","v":0},{"$f":"'K90 - time schedule'!IY36","v":0},{"$f":"'K90 - time schedule'!IZ36","v":0},{"$f":"'K90 - time schedule'!JA36","v":0},{"$f":"'K90 - time schedule'!JB36","v":0},{"$f":"'K90 - time schedule'!JC36","v":0},{"$f":"'K90 - time schedule'!JD36","v":0},{"$f":"'K90 - time schedule'!JE36","v":0},{"$f":"'K90 - time schedule'!JF36","v":0},{"$f":"'K90 - time schedule'!JG36","v":0},{"$f":"'K90 - time schedule'!JH36","v":0},{"$f":"'K90 - time schedule'!JI36","v":0},{"$f":"'K90 - time schedule'!JJ36","v":0},{"$f":"'K90 - time schedule'!JK36","v":0},{"$f":"'K90 - time schedule'!JL36","v":0},{"$f":"'K90 - time schedule'!JM36","v":0},{"$f":"'K90 - time schedule'!JN36","v":0},{"$f":"'K90 - time schedule'!JO36","v":0},{"$f":"'K90 - time schedule'!JP36","v":0},{"$f":"'K90 - time schedule'!JQ36","v":0},{"$f":"'K90 - time schedule'!JR36","v":0},{"$f":"'K90 - time schedule'!JS36","v":0},{"$f":"'K90 - time schedule'!JT36","v":0},{"$f":"'K90 - time schedule'!JU36","v":0},{"$f":"'K90 - time schedule'!JV36","v":0},{"$f":"'K90 - time schedule'!JW36","v":0},{"$f":"'K90 - time schedule'!JX36","v":0},{"$f":"'K90 - time schedule'!JY36","v":0},{"$f":"'K90 - time schedule'!JZ36","v":0},{"$f":"'K90 - time schedule'!KA36","v":0},{"$f":"'K90 - time schedule'!KB36","v":0},{"$f":"'K90 - time schedule'!KC36","v":0},{"$f":"'K90 - time schedule'!KD36","v":0},{"$f":"'K90 - time schedule'!KE36","v":0},{"$f":"'K90 - time schedule'!KF36","v":0},{"$f":"'K90 - time schedule'!KG36","v":0},{"$f":"'K90 - time schedule'!KH36","v":0},{"$f":"'K90 - time schedule'!KI36","v":0},{"$f":"'K90 - time schedule'!KJ36","v":0},{"$f":"'K90 - time schedule'!KK36","v":0},{"$f":"'K90 - time schedule'!KL36","v":0},{"$f":"'K90 - time schedule'!KM36","v":0},{"$f":"'K90 - time schedule'!KN36","v":0},{"$f":"'K90 - time schedule'!KO36","v":0},{"$f":"'K90 - time schedule'!KP36","v":0},{"$f":"'K90 - time schedule'!KQ36","v":0},{"$f":"'K90 - time schedule'!KR36","v":0},{"$f":"'K90 - time schedule'!KS36","v":0},{"$f":"'K90 - time schedule'!KT36","v":0}]
["Boiler room K90 - electrical installation","K90",{"$f":"'K90 - time schedule'!G38","v":0},{"$f":"'K90 - time schedule'!H38","v":0},{"$f":"'K90 - time schedule'!I38","v":0},{"$f":"'K90 - time schedule'!J38","v":0},{"$f":"'K90 - time schedule'!K38","v":0},{"$f":"'K90 - time schedule'!L38","v":0},{"$f":"'K90 - time schedule'!M38","v":0},{"$f":"'K90 - time schedule'!N38","v":0},{"$f":"'K90 - time schedule'!O38","v":0},{"$f":"'K90 - time schedule'!P38","v":0},{"$f":"'K90 - time schedule'!Q38","v":0},{"$f":"'K90 - time schedule'!R38","v":0},{"$f":"'K90 - time schedule'!S38","v":0},{"$f":"'K90 - time schedule'!T38","v":0},{"$f":"'K90 - time schedule'!U38","v":0},{"$f":"'K90 - time schedule'!V38","v":0},{"$f":"'K90 - time schedule'!W38","v":0},{"$f":"'K90 - time schedule'!X38","v":0},{"$f":"'K90 - time schedule'!Y38","v":0},{"$f":"'K90 - time schedule'!Z38","v":0},{"$f":"'K90 - time schedule'!AA38","v":0},{"$f":"'K90 - time schedule'!AB38","v":0},{"$f":"'K90 - time schedule'!AC38","v":0},{"$f":"'K90 - time schedule'!AD38","v":0},{"$f":"'K90 - time schedule'!AE38","v":0},{"$f":"'K90 - time schedule'!AF38","v":0},{"$f":"'K90 - time schedule'!AG38","v":0},{"$f":"'K90 - time schedule'!AH38","v":0},{"$f":"'K90 - time schedule'!AI38","v":0},{"$f":"'K90 - time schedule'!AJ38","v":0},{"$f":"'K90 - time schedule'!AK38","v":0},{"$f":"'K90 - time schedule'!AL38","v":0},{"$f":"'K90 - time schedule'!AM38","v":0},{"$f":"'K90 - time schedule'!AN38","v":0},{"$f":"'K90 - time schedule'!AO38","v":0},{"$f":"'K90 - time schedule'!AP38","v":0},{"$f":"'K90 - time schedule'!AQ38","v":0},{"$f":"'K90 - time schedule'!AR38","v":0},{"$f":"'K90 - time schedule'!AS38","v":0},{"$f":"'K90 - time schedule'!AT38","v":0},{"$f":"'K90 - time schedule'!AU38","v":0},{"$f":"'K90 - time schedule'!AV38","v":0},{"$f":"'K90 - time schedule'!AW38","v":0},{"$f":"'K90 - time schedule'!AX38","v":0},{"$f":"'K90 - time schedule'!AY38","v":0},{"$f":"'K90 - time schedule'!AZ38","v":0},{"$f":"'K90 - time schedule'!BA38","v":0},{"$f":"'K90 - time schedule'!BB38","v":0},{"$f":"'K90 - time schedule'!BC38","v":0},{"$f":"'K90 - time schedule'!BD38","v":0},{"$f":"'K90 - time schedule'!BE38","v":0},{"$f":"'K90 - time schedule'!BF38","v":0},{"$f":"'K90 - time schedule'!BG38","v":0},{"$f":"'K90 - time schedule'!BH38","v":0},{"$f":"'K90 - time schedule'!BI38","v":0},{"$f":"'K90 - time schedule'!BJ38","v":0},{"$f":"'K90 - time schedule'!BK38","v":0},{"$f":"'K90 - time schedule'!BL38","v":0},{"$f":"'K90 - time schedule'!BM38","v":0},{"$f":"'K90 - time schedule'!BN38","v":0},{"$f":"'K90 - time schedule'!BO38","v":0},{"$f":"'K90 - time schedule'!BP38","v":0},{"$f":"'K90 - time schedule'!BQ38","v":0},{"$f":"'K90 - time schedule'!BR38","v":0},{"$f":"'K90 - time schedule'!BS38","v":0},{"$f":"'K90 - time schedule'!BT38","v":0},{"$f":"'K90 - time schedule'!BU38","v":0},{"$f":"'K90 - time schedule'!BV38","v":0},{"$f":"'K90 - time schedule'!BW38","v":0},{"$f":"'K90 - time schedule'!BX38","v":0},{"$f":"'K90 - time schedule'!BY38","v":0},{"$f":"'K90 - time schedule'!BZ38","v":0},{"$f":"'K90 - time schedule'!CA38","v":0},{"$f":"'K90 - time schedule'!CB38","v":0},{"$f":"'K90 - time schedule'!CC38","v":0},{"$f":"'K90 - time schedule'!CD38","v":0},{"$f":"'K90 - time schedule'!CE38","v":0},{"$f":"'K90 - time schedule'!CF38","v":0},{"$f":"'K90 - time schedule'!CG38","v":0},{"$f":"'K90 - time schedule'!CH38","v":0},{"$f":"'K90 - time schedule'!CI38","v":0},{"$f":"'K90 - time schedule'!CJ38","v":0},{"$f":"'K90 - time schedule'!CK38","v":0},{"$f":"'K90 - time schedule'!CL38","v":0},{"$f":"'K90 - time schedule'!CM38","v":0},{"$f":"'K90 - time schedule'!CN38","v":0},{"$f":"'K90 - time schedule'!CO38","v":0},{"$f":"'K90 - time schedule'!CP38","v":0},{"$f":"'K90 - time schedule'!CQ38","v":0},{"$f":"'K90 - time schedule'!CR38","v":0},{"$f":"'K90 - time schedule'!CS38","v":0},{"$f":"'K90 - time schedule'!CT38","v":0},{"$f":"'K90 - time schedule'!CU38","v":0},{"$f":"'K90 - time schedule'!CV38","v":0},{"$f":"'K90 - time schedule'!CW38","v":0},{"$f":"'K90 - time schedule'!CX38","v":0},{"$f":"'K90 - time schedule'!CY38","v":0},{"$f":"'K90 - time schedule'!CZ38","v":0},{"$f":"'K90 - time schedule'!DA38","v":0},{"$f":"'K90 - time schedule'!DB38","v":0},{"$f":"'K90 - time schedule'!DC38","v":0},{"$f":"'K90 - time schedule'!DD38","v":0},{"$f":"'K90 - time schedule'!DE38","v":0},{"$f":"'K90 - time schedule'!DF38","v":0},{"$f":"'K90 - time schedule'!DG38","v":0},{"$f":"'K90 - time schedule'!DH38","v":0},{"$f":"'K90 - time schedule'!DI38","v":0},{"$f":"'K90 - time schedule'!DJ38","v":0},{"$f":"'K90 - time schedule'!DK38","v":0},{"$f":"'K90 - time schedule'!DL38","v":0},{"$f":"'K90 - time schedule'!DM38","v":0},{"$f":"'K90 - time schedule'!DN38","v":0},{"$f":"'K90 - time schedule'!DO38","v":0},{"$f":"'K90 - time schedule'!DP38","v":0},{"$f":"'K90 - time schedule'!DQ38","v":0},{"$f":"'K90 - time schedule'!DR38","v":0},{"$f":"'K90 - time schedule'!DS38","v":0},{"$f":"'K90 - time schedule'!DT38","v":0},{"$f":"'K90 - time schedule'!DU38","v":0},{"$f":"'K90 - time schedule'!DV38","v":0},{"$f":"'K90 - time schedule'!DW38","v":0},{"$f":"'K90 - time schedule'!DX38","v":0},{"$f":"'K90 - time schedule'!DY38","v":0},{"$f":"'K90 - time schedule'!DZ38","v":0},{"$f":"'K90 - time schedule'!EA38","v":0},{"$f":"'K90 - time schedule'!EB38","v":0},{"$f":"'K90 - time schedule'!EC38","v":0},{"$f":"'K90 - time schedule'!ED38","v":0},{"$f":"'K90 - time schedule'!EE38","v":0},{"$f":"'K90 - time schedule'!EF38","v":0},{"$f":"'K90 - time schedule'!EG38","v":0},{"$f":"'K90 - time schedule'!EH38","v":0},{"$f":"'K90 - time schedule'!EI38","v":0},{"$f":"'K90 - time schedule'!EJ38","v":0},{"$f":"'K90 - time schedule'!EK38","v":0},{"$f":"'K90 - time schedule'!EL38","v":0},{"$f":"'K90 - time schedule'!EM38","v":0},{"$f":"'K90 - time schedule'!EN38","v":0},{"$f":"'K90 - time schedule'!EO38","v":0},{"$f":"'K90 - time schedule'!EP38","v":0},{"$f":"'K90 - time schedule'!EQ38","v":0},{"$f":"'K90 - time schedule'!ER38","v":0},{"$f":"'K90 - time schedule'!ES38","v":0},{"$f":"'K90 - time schedule'!ET38","v":0},{"$f":"'K90 - time schedule'!EU38","v":0},{"$f":"'K90 - time schedule'!EV38","v":0},{"$f":"'K90 - time schedule'!EW38","v":0},{"$f":"'K90 - time schedule'!EX38","v":0},{"$f":"'K90 - time schedule'!EY38","v":0},{"$f":"'K90 - time schedule'!EZ38","v":0},{"$f":"'K90 - time schedule'!FA38","v":0},{"$f":"'K90 - time schedule'!FB38","v":0},{"$f":"'K90 - time schedule'!FC38","v":0},{"$f":"'K90 - time schedule'!FD38","v":0},{"$f":"'K90 - time schedule'!FE38","v":0},{"$f":"'K90 - time schedule'!FF38","v":0},{"$f":"'K90 - time schedule'!FG38","v":0},{"$f":"'K90 - time schedule'!FH38","v":0},{"$f":"'K90 - time schedule'!FI38","v":0},{"$f":"'K90 - time schedule'!FJ38","v":0},{"$f":"'K90 - time schedule'!FK38","v":0},{"$f":"'K90 - time schedule'!FL38","v":0},{"$f":"'K90 - time schedule'!FM38","v":0},{"$f":"'K90 - time schedule'!FN38","v":0},{"$f":"'K90 - time schedule'!FO38","v":0},{"$f":"'K90 - time schedule'!FP38","v":0},{"$f":"'K90 - time schedule'!FQ38","v":0},{"$f":"'K90 - time schedule'!FR38","v":0},{"$f":"'K90 - time schedule'!FS38","v":0},{"$f":"'K90 - time schedule'!FT38","v":0},{"$f":"'K90 - time schedule'!FU38","v":0},{"$f":"'K90 - time schedule'!FV38","v":0},{"$f":"'K90 - time schedule'!FW38","v":0},{"$f":"'K90 - time schedule'!FX38","v":0},{"$f":"'K90 - time schedule'!FY38","v":0},{"$f":"'K90 - time schedule'!FZ38","v":0},{"$f":"'K90 - time schedule'!GA38","v":0},{"$f":"'K90 - time schedule'!GB38","v":0},{"$f":"'K90 - time schedule'!GC38","v":0},{"$f":"'K90 - time schedule'!GD38","v":0},{"$f":"'K90 - time schedule'!GE38","v":0},{"$f":"'K90 - time schedule'!GF38","v":0},{"$f":"'K90 - time schedule'!GG38","v":0},{"$f":"'K90 - time schedule'!GH38","v":0},{"$f":"'K90 - time schedule'!GI38","v":0},{"$f":"'K90 - time schedule'!GJ38","v":0},{"$f":"'K90 - time schedule'!GK38","v":0},{"$f":"'K90 - time schedule'!GL38","v":0},{"$f":"'K90 - time schedule'!GM38","v":0},{"$f":"'K90 - time schedule'!GN38","v":0},{"$f":"'K90 - time schedule'!GO38","v":0},{"$f":"'K90 - time schedule'!GP38","v":0},{"$f":"'K90 - time schedule'!GQ38","v":0},{"$f":"'K90 - time schedule'!GR38","v":0},{"$f":"'K90 - time schedule'!GS38","v":0},{"$f":"'K90 - time schedule'!GT38","v":0},{"$f":"'K90 - time schedule'!GU38","v":0},{"$f":"'K90 - time schedule'!GV38","v":0},{"$f":"'K90 - time schedule'!GW38","v":0},{"$f":"'K90 - time schedule'!GX38","v":0},{"$f":"'K90 - time schedule'!GY38","v":0},{"$f":"'K90 - time schedule'!GZ38","v":0},{"$f":"'K90 - time schedule'!HA38","v":0},{"$f":"'K90 - time schedule'!HB38","v":0},{"$f":"'K90 - time schedule'!HC38","v":0},{"$f":"'K90 - time schedule'!HD38","v":0},{"$f":"'K90 - time schedule'!HE38","v":0},{"$f":"'K90 - time schedule'!HF38","v":0},{"$f":"'K90 - time schedule'!HG38","v":0},{"$f":"'K90 - time schedule'!HH38","v":0},{"$f":"'K90 - time schedule'!HI38","v":0},{"$f":"'K90 - time schedule'!HJ38","v":0},{"$f":"'K90 - time schedule'!HK38","v":0},{"$f":"'K90 - time schedule'!HL38","v":0},{"$f":"'K90 - time schedule'!HM38","v":0},{"$f":"'K90 - time schedule'!HN38","v":0},{"$f":"'K90 - time schedule'!HO38","v":0},{"$f":"'K90 - time schedule'!HP38","v":0},{"$f":"'K90 - time schedule'!HQ38","v":0},{"$f":"'K90 - time schedule'!HR38","v":0},{"$f":"'K90 - time schedule'!HS38","v":0},{"$f":"'K90 - time schedule'!HT38","v":0},{"$f":"'K90 - time schedule'!HU38","v":0},{"$f":"'K90 - time schedule'!HV38","v":0},{"$f":"'K90 - time schedule'!HW38","v":0},{"$f":"'K90 - time schedule'!HX38","v":0},{"$f":"'K90 - time schedule'!HY38","v":0},{"$f":"'K90 - time schedule'!HZ38","v":0},{"$f":"'K90 - time schedule'!IA38","v":0},{"$f":"'K90 - time schedule'!IB38","v":0},{"$f":"'K90 - time schedule'!IC38","v":0},{"$f":"'K90 - time schedule'!ID38","v":0},{"$f":"'K90 - time schedule'!IE38","v":0},{"$f":"'K90 - time schedule'!IF38","v":0},{"$f":"'K90 - time schedule'!IG38","v":0},{"$f":"'K90 - time schedule'!IH38","v":0},{"$f":"'K90 - time schedule'!II38","v":0},{"$f":"'K90 - time schedule'!IJ38","v":0},{"$f":"'K90 - time schedule'!IK38","v":0},{"$f":"'K90 - time schedule'!IL38","v":0},{"$f":"'K90 - time schedule'!IM38","v":0},{"$f":"'K90 - time schedule'!IN38","v":0},{"$f":"'K90 - time schedule'!IO38","v":0},{"$f":"'K90 - time schedule'!IP38","v":0},{"$f":"'K90 - time schedule'!IQ38","v":0},{"$f":"'K90 - time schedule'!IR38","v":0},{"$f":"'K90 - time schedule'!IS38","v":0},{"$f":"'K90 - time schedule'!IT38","v":0},{"$f":"'K90 - time schedule'!IU38","v":0},{"$f":"'K90 - time schedule'!IV38","v":0},{"$f":"'K90 - time schedule'!IW38","v":0},{"$f":"'K90 - time schedule'!IX38","v":0},{"$f":"'K90 - time schedule'!IY38","v":0},{"$f":"'K90 - time schedule'!IZ38","v":0},{"$f":"'K90 - time schedule'!JA38","v":0},{"$f":"'K90 - time schedule'!JB38","v":0},{"$f":"'K90 - time schedule'!JC38","v":0},{"$f":"'K90 - time schedule'!JD38","v":0},{"$f":"'K90 - time schedule'!JE38","v":0},{"$f":"'K90 - time schedule'!JF38","v":0},{"$f":"'K90 - time schedule'!JG38","v":0},{"$f":"'K90 - time schedule'!JH38","v":0},{"$f":"'K90 - time schedule'!JI38","v":0},{"$f":"'K90 - time schedule'!JJ38","v":0},{"$f":"'K90 - time schedule'!JK38","v":0},{"$f":"'K90 - time schedule'!JL38","v":0},{"$f":"'K90 - time schedule'!JM38","v":0},{"$f":"'K90 - time schedule'!JN38","v":0},{"$f":"'K90 - time schedule'!JO38","v":0},{"$f":"'K90 - time schedule'!JP38","v":0},{"$f":"'K90 - time schedule'!JQ38","v":0},{"$f":"'K90 - time schedule'!JR38","v":0},{"$f":"'K90 - time schedule'!JS38","v":0},{"$f":"'K90 - time schedule'!JT38","v":0},{"$f":"'K90 - time schedule'!JU38","v":0},{"$f":"'K90 - time schedule'!JV38","v":0},{"$f":"'K90 - time schedule'!JW38","v":0},{"$f":"'K90 - time schedule'!JX38","v":0},{"$f":"'K90 - time schedule'!JY38","v":0},{"$f":"'K90 - time schedule'!JZ38","v":0},{"$f":"'K90 - time schedule'!KA38","v":0},{"$f":"'K90 - time schedule'!KB38","v":0},{"$f":"'K90 - time schedule'!KC38","v":0},{"$f":"'K90 - time schedule'!KD38","v":0},{"$f":"'K90 - time schedule'!KE38","v":0},{"$f":"'K90 - time schedule'!KF38","v":0},{"$f":"'K90 - time schedule'!KG38","v":0},{"$f":"'K90 - time schedule'!KH38","v":0},{"$f":"'K90 - time schedule'!KI38","v":0},{"$f":"'K90 - time schedule'!KJ38","v":0},{"$f":"'K90 - time schedule'!KK38","v":0},{"$f":"'K90 - time schedule'!KL38","v":0},{"$f":"'K90 - time schedule'!KM38","v":0},{"$f":"'K90 - time schedule'!KN38","v":0},{"$f":"'K90 - time schedule'!KO38","v":0},{"$f":"'K90 - time schedule'!KP38","v":0},{"$f":"'K90 - time schedule'!KQ38","v":0},{"$f":"'K90 - time schedule'!KR38","v":0},{"$f":"'K90 - time schedule'!KS38","v":0},{"$f":"'K90 - time schedule'!KT38","v":0}]
["Boiler room K90 - management of automatic control system","K90",{"$f":"'K90 - time schedule'!G40","v":0},{"$f":"'K90 - time schedule'!H40","v":0},{"$f":"'K90 - time schedule'!I40","v":0},{"$f":"'K90 - time schedule'!J40","v":0},{"$f":"'K90 - time schedule'!K40","v":0},{"$f":"'K90 - time schedule'!L40","v":0},{"$f":"'K90 - time schedule'!M40","v":0},{"$f":"'K90 - time schedule'!N40","v":0},{"$f":"'K90 - time schedule'!O40","v":0},{"$f":"'K90 - time schedule'!P40","v":0},{"$f":"'K90 - time schedule'!Q40","v":0},{"$f":"'K90 - time schedule'!R40","v":0},{"$f":"'K90 - time schedule'!S40","v":0},{"$f":"'K90 - time schedule'!T40","v":0},{"$f":"'K90 - time schedule'!U40","v":0},{"$f":"'K90 - time schedule'!V40","v":0},{"$f":"'K90 - time schedule'!W40","v":0},{"$f":"'K90 - time schedule'!X40","v":0},{"$f":"'K90 - time schedule'!Y40","v":0},{"$f":"'K90 - time schedule'!Z40","v":0},{"$f":"'K90 - time schedule'!AA40","v":0},{"$f":"'K90 - time schedule'!AB40","v":0},{"$f":"'K90 - time schedule'!AC40","v":0},{"$f":"'K90 - time schedule'!AD40","v":0},{"$f":"'K90 - time schedule'!AE40","v":0},{"$f":"'K90 - time schedule'!AF40","v":0},{"$f":"'K90 - time schedule'!AG40","v":0},{"$f":"'K90 - time schedule'!AH40","v":0},{"$f":"'K90 - time schedule'!AI40","v":0},{"$f":"'K90 - time schedule'!AJ40","v":0},{"$f":"'K90 - time schedule'!AK40","v":0},{"$f":"'K90 - time schedule'!AL40","v":0},{"$f":"'K90 - time schedule'!AM40","v":0},{"$f":"'K90 - time schedule'!AN40","v":0},{"$f":"'K90 - time schedule'!AO40","v":0},{"$f":"'K90 - time schedule'!AP40","v":0},{"$f":"'K90 - time schedule'!AQ40","v":0},{"$f":"'K90 - time schedule'!AR40","v":0},{"$f":"'K90 - time schedule'!AS40","v":0},{"$f":"'K90 - time schedule'!AT40","v":0},{"$f":"'K90 - time schedule'!AU40","v":0},{"$f":"'K90 - time schedule'!AV40","v":0},{"$f":"'K90 - time schedule'!AW40","v":0},{"$f":"'K90 - time schedule'!AX40","v":0},{"$f":"'K90 - time schedule'!AY40","v":0},{"$f":"'K90 - time schedule'!AZ40","v":0},{"$f":"'K90 - time schedule'!BA40","v":0},{"$f":"'K90 - time schedule'!BB40","v":0},{"$f":"'K90 - time schedule'!BC40","v":0},{"$f":"'K90 - time schedule'!BD40","v":0},{"$f":"'K90 - time schedule'!BE40","v":0},{"$f":"'K90 - time schedule'!BF40","v":0},{"$f":"'K90 - time schedule'!BG40","v":0},{"$f":"'K90 - time schedule'!BH40","v":0},{"$f":"'K90 - time schedule'!BI40","v":0},{"$f":"'K90 - time schedule'!BJ40","v":0},{"$f":"'K90 - time schedule'!BK40","v":0},{"$f":"'K90 - time schedule'!BL40","v":0},{"$f":"'K90 - time schedule'!BM40","v":0},{"$f":"'K90 - time schedule'!BN40","v":0},{"$f":"'K90 - time schedule'!BO40","v":0},{"$f":"'K90 - time schedule'!BP40","v":0},{"$f":"'K90 - time schedule'!BQ40","v":0},{"$f":"'K90 - time schedule'!BR40","v":0},{"$f":"'K90 - time schedule'!BS40","v":0},{"$f":"'K90 - time schedule'!BT40","v":0},{"$f":"'K90 - time schedule'!BU40","v":0},{"$f":"'K90 - time schedule'!BV40","v":0},{"$f":"'K90 - time schedule'!BW40","v":0},{"$f":"'K90 - time schedule'!BX40","v":0},{"$f":"'K90 - time schedule'!BY40","v":0},{"$f":"'K90 - time schedule'!BZ40","v":0},{"$f":"'K90 - time schedule'!CA40","v":0},{"$f":"'K90 - time schedule'!CB40","v":0},{"$f":"'K90 - time schedule'!CC40","v":0},{"$f":"'K90 - time schedule'!CD40","v":0},{"$f":"'K90 - time schedule'!CE40","v":0},{"$f":"'K90 - time schedule'!CF40","v":0},{"$f":"'K90 - time schedule'!CG40","v":0},{"$f":"'K90 - time schedule'!CH40","v":0},{"$f":"'K90 - time schedule'!CI40","v":0},{"$f":"'K90 - time schedule'!CJ40","v":0},{"$f":"'K90 - time schedule'!CK40","v":0},{"$f":"'K90 - time schedule'!CL40","v":0},{"$f":"'K90 - time schedule'!CM40","v":0},{"$f":"'K90 - time schedule'!CN40","v":0},{"$f":"'K90 - time schedule'!CO40","v":0},{"$f":"'K90 - time schedule'!CP40","v":0},{"$f":"'K90 - time schedule'!CQ40","v":0},{"$f":"'K90 - time schedule'!CR40","v":0},{"$f":"'K90 - time schedule'!CS40","v":0},{"$f":"'K90 - time schedule'!CT40","v":0},{"$f":"'K90 - time schedule'!CU40","v":0},{"$f":"'K90 - time schedule'!CV40","v":0},{"$f":"'K90 - time schedule'!CW40","v":0},{"$f":"'K90 - time schedule'!CX40","v":0},{"$f":"'K90 - time schedule'!CY40","v":0},{"$f":"'K90 - time schedule'!CZ40","v":0},{"$f":"'K90 - time schedule'!DA40","v":0},{"$f":"'K90 - time schedule'!DB40","v":0},{"$f":"'K90 - time schedule'!DC40","v":0},{"$f":"'K90 - time schedule'!DD40","v":0},{"$f":"'K90 - time schedule'!DE40","v":0},{"$f":"'K90 - time schedule'!DF40","v":0},{"$f":"'K90 - time schedule'!DG40","v":0},{"$f":"'K90 - time schedule'!DH40","v":0},{"$f":"'K90 - time schedule'!DI40","v":0},{"$f":"'K90 - time schedule'!DJ40","v":0},{"$f":"'K90 - time schedule'!DK40","v":0},{"$f":"'K90 - time schedule'!DL40","v":0},{"$f":"'K90 - time schedule'!DM40","v":0},{"$f":"'K90 - time schedule'!DN40","v":0},{"$f":"'K90 - time schedule'!DO40","v":0},{"$f":"'K90 - time schedule'!DP40","v":0},{"$f":"'K90 - time schedule'!DQ40","v":0},{"$f":"'K90 - time schedule'!DR40","v":0},{"$f":"'K90 - time schedule'!DS40","v":0},{"$f":"'K90 - time schedule'!DT40","v":0},{"$f":"'K90 - time schedule'!DU40","v":0},{"$f":"'K90 - time schedule'!DV40","v":0},{"$f":"'K90 - time schedule'!DW40","v":0},{"$f":"'K90 - time schedule'!DX40","v":0},{"$f":"'K90 - time schedule'!DY40","v":0},{"$f":"'K90 - time schedule'!DZ40","v":0},{"$f":"'K90 - time schedule'!EA40","v":0},{"$f":"'K90 - time schedule'!EB40","v":0},{"$f":"'K90 - time schedule'!EC40","v":0},{"$f":"'K90 - time schedule'!ED40","v":0},{"$f":"'K90 - time schedule'!EE40","v":0},{"$f":"'K90 - time schedule'!EF40","v":0},{"$f":"'K90 - time schedule'!EG40","v":0},{"$f":"'K90 - time schedule'!EH40","v":0},{"$f":"'K90 - time schedule'!EI40","v":0},{"$f":"'K90 - time schedule'!EJ40","v":0},{"$f":"'K90 - time schedule'!EK40","v":0},{"$f":"'K90 - time schedule'!EL40","v":0},{"$f":"'K90 - time schedule'!EM40","v":0},{"$f":"'K90 - time schedule'!EN40","v":0},{"$f":"'K90 - time schedule'!EO40","v":0},{"$f":"'K90 - time schedule'!EP40","v":0},{"$f":"'K90 - time schedule'!EQ40","v":0},{"$f":"'K90 - time schedule'!ER40","v":0},{"$f":"'K90 - time schedule'!ES40","v":0},{"$f":"'K90 - time schedule'!ET40","v":0},{"$f":"'K90 - time schedule'!EU40","v":0},{"$f":"'K90 - time schedule'!EV40","v":0},{"$f":"'K90 - time schedule'!EW40","v":0},{"$f":"'K90 - time schedule'!EX40","v":0},{"$f":"'K90 - time schedule'!EY40","v":0},{"$f":"'K90 - time schedule'!EZ40","v":0},{"$f":"'K90 - time schedule'!FA40","v":0},{"$f":"'K90 - time schedule'!FB40","v":0},{"$f":"'K90 - time schedule'!FC40","v":0},{"$f":"'K90 - time schedule'!FD40","v":0},{"$f":"'K90 - time schedule'!FE40","v":0},{"$f":"'K90 - time schedule'!FF40","v":0},{"$f":"'K90 - time schedule'!FG40","v":0},{"$f":"'K90 - time schedule'!FH40","v":0},{"$f":"'K90 - time schedule'!FI40","v":0},{"$f":"'K90 - time schedule'!FJ40","v":0},{"$f":"'K90 - time schedule'!FK40","v":0},{"$f":"'K90 - time schedule'!FL40","v":0},{"$f":"'K90 - time schedule'!FM40","v":0},{"$f":"'K90 - time schedule'!FN40","v":0},{"$f":"'K90 - time schedule'!FO40","v":0},{"$f":"'K90 - time schedule'!FP40","v":0},{"$f":"'K90 - time schedule'!FQ40","v":0},{"$f":"'K90 - time schedule'!FR40","v":0},{"$f":"'K90 - time schedule'!FS40","v":0},{"$f":"'K90 - time schedule'!FT40","v":0},{"$f":"'K90 - time schedule'!FU40","v":0},{"$f":"'K90 - time schedule'!FV40","v":0},{"$f":"'K90 - time schedule'!FW40","v":0},{"$f":"'K90 - time schedule'!FX40","v":0},{"$f":"'K90 - time schedule'!FY40","v":0},{"$f":"'K90 - time schedule'!FZ40","v":0},{"$f":"'K90 - time schedule'!GA40","v":0},{"$f":"'K90 - time schedule'!GB40","v":0},{"$f":"'K90 - time schedule'!GC40","v":0},{"$f":"'K90 - time schedule'!GD40","v":0},{"$f":"'K90 - time schedule'!GE40","v":0},{"$f":"'K90 - time schedule'!GF40","v":0},{"$f":"'K90 - time schedule'!GG40","v":0},{"$f":"'K90 - time schedule'!GH40","v":0},{"$f":"'K90 - time schedule'!GI40","v":0},{"$f":"'K90 - time schedule'!GJ40","v":0},{"$f":"'K90 - time schedule'!GK40","v":0},{"$f":"'K90 - time schedule'!GL40","v":0},{"$f":"'K90 - time schedule'!GM40","v":0},{"$f":"'K90 - time schedule'!GN40","v":0},{"$f":"'K90 - time schedule'!GO40","v":0},{"$f":"'K90 - time schedule'!GP40","v":0},{"$f":"'K90 - time schedule'!GQ40","v":0},{"$f":"'K90 - time schedule'!GR40","v":0},{"$f":"'K90 - time schedule'!GS40","v":0},{"$f":"'K90 - time schedule'!GT40","v":0},{"$f":"'K90 - time schedule'!GU40","v":0},{"$f":"'K90 - time schedule'!GV40","v":0},{"$f":"'K90 - time schedule'!GW40","v":0},{"$f":"'K90 - time schedule'!GX40","v":0},{"$f":"'K90 - time schedule'!GY40","v":0},{"$f":"'K90 - time schedule'!GZ40","v":0},{"$f":"'K90 - time schedule'!HA40","v":0},{"$f":"'K90 - time schedule'!HB40","v":0},{"$f":"'K90 - time schedule'!HC40","v":0},{"$f":"'K90 - time schedule'!HD40","v":0},{"$f":"'K90 - time schedule'!HE40","v":0},{"$f":"'K90 - time schedule'!HF40","v":0},{"$f":"'K90 - time schedule'!HG40","v":0},{"$f":"'K90 - time schedule'!HH40","v":0},{"$f":"'K90 - time schedule'!HI40","v":0},{"$f":"'K90 - time schedule'!HJ40","v":0},{"$f":"'K90 - time schedule'!HK40","v":0},{"$f":"'K90 - time schedule'!HL40","v":0},{"$f":"'K90 - time schedule'!HM40","v":0},{"$f":"'K90 - time schedule'!HN40","v":0},{"$f":"'K90 - time schedule'!HO40","v":0},{"$f":"'K90 - time schedule'!HP40","v":0},{"$f":"'K90 - time schedule'!HQ40","v":0},{"$f":"'K90 - time schedule'!HR40","v":0},{"$f":"'K90 - time schedule'!HS40","v":0},{"$f":"'K90 - time schedule'!HT40","v":0},{"$f":"'K90 - time schedule'!HU40","v":0},{"$f":"'K90 - time schedule'!HV40","v":0},{"$f":"'K90 - time schedule'!HW40","v":0},{"$f":"'K90 - time schedule'!HX40","v":0},{"$f":"'K90 - time schedule'!HY40","v":0},{"$f":"'K90 - time schedule'!HZ40","v":0},{"$f":"'K90 - time schedule'!IA40","v":0},{"$f":"'K90 - time schedule'!IB40","v":0},{"$f":"'K90 - time schedule'!IC40","v":0},{"$f":"'K90 - time schedule'!ID40","v":0},{"$f":"'K90 - time schedule'!IE40","v":0},{"$f":"'K90 - time schedule'!IF40","v":0},{"$f":"'K90 - time schedule'!IG40","v":0},{"$f":"'K90 - time schedule'!IH40","v":0},{"$f":"'K90 - time schedule'!II40","v":0},{"$f":"'K90 - time schedule'!IJ40","v":0},{"$f":"'K90 - time schedule'!IK40","v":0},{"$f":"'K90 - time schedule'!IL40","v":0},{"$f":"'K90 - time schedule'!IM40","v":0},{"$f":"'K90 - time schedule'!IN40","v":0},{"$f":"'K90 - time schedule'!IO40","v":0},{"$f":"'K90 - time schedule'!IP40","v":0},{"$f":"'K90 - time schedule'!IQ40","v":0},{"$f":"'K90 - time schedule'!IR40","v":0},{"$f":"'K90 - time schedule'!IS40","v":0},{"$f":"'K90 - time schedule'!IT40","v":0},{"$f":"'K90 - time schedule'!IU40","v":0},{"$f":"'K90 - time schedule'!IV40","v":0},{"$f":"'K90 - time schedule'!IW40","v":0},{"$f":"'K90 - time schedule'!IX40","v":0},{"$f":"'K90 - time schedule'!IY40","v":0},{"$f":"'K90 - time schedule'!IZ40","v":0},{"$f":"'K90 - time schedule'!JA40","v":0},{"$f":"'K90 - time schedule'!JB40","v":0},{"$f":"'K90 - time schedule'!JC40","v":0},{"$f":"'K90 - time schedule'!JD40","v":0},{"$f":"'K90 - time schedule'!JE40","v":0},{"$f":"'K90 - time schedule'!JF40","v":0},{"$f":"'K90 - time schedule'!JG40","v":0},{"$f":"'K90 - time schedule'!JH40","v":0},{"$f":"'K90 - time schedule'!JI40","v":0},{"$f":"'K90 - time schedule'!JJ40","v":0},{"$f":"'K90 - time schedule'!JK40","v":0},{"$f":"'K90 - time schedule'!JL40","v":0},{"$f":"'K90 - time schedule'!JM40","v":0},{"$f":"'K90 - time schedule'!JN40","v":0},{"$f":"'K90 - time schedule'!JO40","v":0},{"$f":"'K90 - time schedule'!JP40","v":0},{"$f":"'K90 - time schedule'!JQ40","v":0},{"$f":"'K90 - time schedule'!JR40","v":0},{"$f":"'K90 - time schedule'!JS40","v":0},{"$f":"'K90 - time schedule'!JT40","v":0},{"$f":"'K90 - time schedule'!JU40","v":0},{"$f":"'K90 - time schedule'!JV40","v":0},{"$f":"'K90 - time schedule'!JW40","v":0},{"$f":"'K90 - time schedule'!JX40","v":0},{"$f":"'K90 - time schedule'!JY40","v":0},{"$f":"'K90 - time schedule'!JZ40","v":0},{"$f":"'K90 - time schedule'!KA40","v":0},{"$f":"'K90 - time schedule'!KB40","v":0},{"$f":"'K90 - time schedule'!KC40","v":0},{"$f":"'K90 - time schedule'!KD40","v":0},{"$f":"'K90 - time schedule'!KE40","v":0},{"$f":"'K90 - time schedule'!KF40","v":0},{"$f":"'K90 - time schedule'!KG40","v":0},{"$f":"'K90 - time schedule'!KH40","v":0},{"$f":"'K90 - time schedule'!KI40","v":0},{"$f":"'K90 - time schedule'!KJ40","v":0},{"$f":"'K90 - time schedule'!KK40","v":0},{"$f":"'K90 - time schedule'!KL40","v":0},{"$f":"'K90 - time schedule'!KM40","v":0},{"$f":"'K90 - time schedule'!KN40","v":0},{"$f":"'K90 - time schedule'!KO40","v":0},{"$f":"'K90 - time schedule'!KP40","v":0},{"$f":"'K90 - time schedule'!KQ40","v":0},{"$f":"'K90 - time schedule'!KR40","v":0},{"$f":"'K90 - time schedule'!KS40","v":0},{"$f":"'K90 - time schedule'!KT40","v":0}]
["Boiler room K90 - construction structures","K90",{"$f":"'K90 - time schedule'!G42","v":0},{"$f":"'K90 - time schedule'!H42","v":0},{"$f":"'K90 - time schedule'!I42","v":0},{"$f":"'K90 - time schedule'!J42","v":0},{"$f":"'K90 - time schedule'!K42","v":0},{"$f":"'K90 - time schedule'!L42","v":0},{"$f":"'K90 - time schedule'!M42","v":0},{"$f":"'K90 - time schedule'!N42","v":0},{"$f":"'K90 - time schedule'!O42","v":0},{"$f":"'K90 - time schedule'!P42","v":0},{"$f":"'K90 - time schedule'!Q42","v":0},{"$f":"'K90 - time schedule'!R42","v":0},{"$f":"'K90 - time schedule'!S42","v":0},{"$f":"'K90 - time schedule'!T42","v":0},{"$f":"'K90 - time schedule'!U42","v":0},{"$f":"'K90 - time schedule'!V42","v":0},{"$f":"'K90 - time schedule'!W42","v":0},{"$f":"'K90 - time schedule'!X42","v":0},{"$f":"'K90 - time schedule'!Y42","v":0},{"$f":"'K90 - time schedule'!Z42","v":0},{"$f":"'K90 - time schedule'!AA42","v":0},{"$f":"'K90 - time schedule'!AB42","v":0},{"$f":"'K90 - time schedule'!AC42","v":0},{"$f":"'K90 - time schedule'!AD42","v":0},{"$f":"'K90 - time schedule'!AE42","v":0},{"$f":"'K90 - time schedule'!AF42","v":0},{"$f":"'K90 - time schedule'!AG42","v":0},{"$f":"'K90 - time schedule'!AH42","v":0},{"$f":"'K90 - time schedule'!AI42","v":0},{"$f":"'K90 - time schedule'!AJ42","v":0},{"$f":"'K90 - time schedule'!AK42","v":0},{"$f":"'K90 - time schedule'!AL42","v":0},{"$f":"'K90 - time schedule'!AM42","v":0},{"$f":"'K90 - time schedule'!AN42","v":0},{"$f":"'K90 - time schedule'!AO42","v":0},{"$f":"'K90 - time schedule'!AP42","v":0},{"$f":"'K90 - time schedule'!AQ42","v":0},{"$f":"'K90 - time schedule'!AR42","v":0},{"$f":"'K90 - time schedule'!AS42","v":0},{"$f":"'K90 - time schedule'!AT42","v":0},{"$f":"'K90 - time schedule'!AU42","v":0},{"$f":"'K90 - time schedule'!AV42","v":0},{"$f":"'K90 - time schedule'!AW42","v":0},{"$f":"'K90 - time schedule'!AX42","v":0},{"$f":"'K90 - time schedule'!AY42","v":0},{"$f":"'K90 - time schedule'!AZ42","v":0},{"$f":"'K90 - time schedule'!BA42","v":0},{"$f":"'K90 - time schedule'!BB42","v":0},{"$f":"'K90 - time schedule'!BC42","v":0},{"$f":"'K90 - time schedule'!BD42","v":0},{"$f":"'K90 - time schedule'!BE42","v":0},{"$f":"'K90 - time schedule'!BF42","v":0},{"$f":"'K90 - time schedule'!BG42","v":0},{"$f":"'K90 - time schedule'!BH42","v":0},{"$f":"'K90 - time schedule'!BI42","v":0},{"$f":"'K90 - time schedule'!BJ42","v":0},{"$f":"'K90 - time schedule'!BK42","v":0},{"$f":"'K90 - time schedule'!BL42","v":0},{"$f":"'K90 - time schedule'!BM42","v":0},{"$f":"'K90 - time schedule'!BN42","v":0},{"$f":"'K90 - time schedule'!BO42","v":0},{"$f":"'K90 - time schedule'!BP42","v":0},{"$f":"'K90 - time schedule'!BQ42","v":0},{"$f":"'K90 - time schedule'!BR42","v":0},{"$f":"'K90 - time schedule'!BS42","v":0},{"$f":"'K90 - time schedule'!BT42","v":0},{"$f":"'K90 - time schedule'!BU42","v":0},{"$f":"'K90 - time schedule'!BV42","v":0},{"$f":"'K90 - time schedule'!BW42","v":0},{"$f":"'K90 - time schedule'!BX42","v":0},{"$f":"'K90 - time schedule'!BY42","v":0},{"$f":"'K90 - time schedule'!BZ42","v":0},{"$f":"'K90 - time schedule'!CA42","v":0},{"$f":"'K90 - time schedule'!CB42","v":0},{"$f":"'K90 - time schedule'!CC42","v":0},{"$f":"'K90 - time schedule'!CD42","v":0},{"$f":"'K90 - time schedule'!CE42","v":0},{"$f":"'K90 - time schedule'!CF42","v":0},{"$f":"'K90 - time schedule'!CG42","v":0},{"$f":"'K90 - time schedule'!CH42","v":0},{"$f":"'K90 - time schedule'!CI42","v":0},{"$f":"'K90 - time schedule'!CJ42","v":0},{"$f":"'K90 - time schedule'!CK42","v":0},{"$f":"'K90 - time schedule'!CL42","v":0},{"$f":"'K90 - time schedule'!CM42","v":0},{"$f":"'K90 - time schedule'!CN42","v":0},{"$f":"'K90 - time schedule'!CO42","v":0},{"$f":"'K90 - time schedule'!CP42","v":0},{"$f":"'K90 - time schedule'!CQ42","v":0},{"$f":"'K90 - time schedule'!CR42","v":0},{"$f":"'K90 - time schedule'!CS42","v":0},{"$f":"'K90 - time schedule'!CT42","v":0},{"$f":"'K90 - time schedule'!CU42","v":0},{"$f":"'K90 - time schedule'!CV42","v":0},{"$f":"'K90 - time schedule'!CW42","v":0},{"$f":"'K90 - time schedule'!CX42","v":0},{"$f":"'K90 - time schedule'!CY42","v":0},{"$f":"'K90 - time schedule'!CZ42","v":0},{"$f":"'K90 - time schedule'!DA42","v":0},{"$f":"'K90 - time schedule'!DB42","v":0},{"$f":"'K90 - time schedule'!DC42","v":0},{"$f":"'K90 - time schedule'!DD42","v":0},{"$f":"'K90 - time schedule'!DE42","v":0},{"$f":"'K90 - time schedule'!DF42","v":0},{"$f":"'K90 - time schedule'!DG42","v":0},{"$f":"'K90 - time schedule'!DH42","v":0},{"$f":"'K90 - time schedule'!DI42","v":0},{"$f":"'K90 - time schedule'!DJ42","v":0},{"$f":"'K90 - time schedule'!DK42","v":0},{"$f":"'K90 - time schedule'!DL42","v":0},{"$f":"'K90 - time schedule'!DM42","v":0},{"$f":"'K90 - time schedule'!DN42","v":0},{"$f":"'K90 - time schedule'!DO42","v":0},{"$f":"'K90 - time schedule'!DP42","v":0},{"$f":"'K90 - time schedule'!DQ42","v":0},{"$f":"'K90 - time schedule'!DR42","v":0},{"$f":"'K90 - time schedule'!DS42","v":0},{"$f":"'K90 - time schedule'!DT42","v":0},{"$f":"'K90 - time schedule'!DU42","v":0},{"$f":"'K90 - time schedule'!DV42","v":0},{"$f":"'K90 - time schedule'!DW42","v":0},{"$f":"'K90 - time schedule'!DX42","v":0},{"$f":"'K90 - time schedule'!DY42","v":0},{"$f":"'K90 - time schedule'!DZ42","v":0},{"$f":"'K90 - time schedule'!EA42","v":0},{"$f":"'K90 - time schedule'!EB42","v":0},{"$f":"'K90 - time schedule'!EC42","v":0},{"$f":"'K90 - time schedule'!ED42","v":0},{"$f":"'K90 - time schedule'!EE42","v":0},{"$f":"'K90 - time schedule'!EF42","v":0},{"$f":"'K90 - time schedule'!EG42","v":0},{"$f":"'K90 - time schedule'!EH42","v":0},{"$f":"'K90 - time schedule'!EI42","v":0},{"$f":"'K90 - time schedule'!EJ42","v":0},{"$f":"'K90 - time schedule'!EK42","v":0},{"$f":"'K90 - time schedule'!EL42","v":0},{"$f":"'K90 - time schedule'!EM42","v":0},{"$f":"'K90 - time schedule'!EN42","v":0},{"$f":"'K90 - time schedule'!EO42","v":0},{"$f":"'K90 - time schedule'!EP42","v":0},{"$f":"'K90 - time schedule'!EQ42","v":0},{"$f":"'K90 - time schedule'!ER42","v":0},{"$f":"'K90 - time schedule'!ES42","v":0},{"$f":"'K90 - time schedule'!ET42","v":0},{"$f":"'K90 - time schedule'!EU42","v":0},{"$f":"'K90 - time schedule'!EV42","v":0},{"$f":"'K90 - time schedule'!EW42","v":0},{"$f":"'K90 - time schedule'!EX42","v":0},{"$f":"'K90 - time schedule'!EY42","v":0},{"$f":"'K90 - time schedule'!EZ42","v":0},{"$f":"'K90 - time schedule'!FA42","v":0},{"$f":"'K90 - time schedule'!FB42","v":0},{"$f":"'K90 - time schedule'!FC42","v":0},{"$f":"'K90 - time schedule'!FD42","v":0},{"$f":"'K90 - time schedule'!FE42","v":0},{"$f":"'K90 - time schedule'!FF42","v":0},{"$f":"'K90 - time schedule'!FG42","v":0},{"$f":"'K90 - time schedule'!FH42","v":0},{"$f":"'K90 - time schedule'!FI42","v":0},{"$f":"'K90 - time schedule'!FJ42","v":0},{"$f":"'K90 - time schedule'!FK42","v":0},{"$f":"'K90 - time schedule'!FL42","v":0},{"$f":"'K90 - time schedule'!FM42","v":0},{"$f":"'K90 - time schedule'!FN42","v":0},{"$f":"'K90 - time schedule'!FO42","v":0},{"$f":"'K90 - time schedule'!FP42","v":0},{"$f":"'K90 - time schedule'!FQ42","v":0},{"$f":"'K90 - time schedule'!FR42","v":0},{"$f":"'K90 - time schedule'!FS42","v":0},{"$f":"'K90 - time schedule'!FT42","v":0},{"$f":"'K90 - time schedule'!FU42","v":0},{"$f":"'K90 - time schedule'!FV42","v":0},{"$f":"'K90 - time schedule'!FW42","v":0},{"$f":"'K90 - time schedule'!FX42","v":0},{"$f":"'K90 - time schedule'!FY42","v":0},{"$f":"'K90 - time schedule'!FZ42","v":0},{"$f":"'K90 - time schedule'!GA42","v":0},{"$f":"'K90 - time schedule'!GB42","v":0},{"$f":"'K90 - time schedule'!GC42","v":0},{"$f":"'K90 - time schedule'!GD42","v":0},{"$f":"'K90 - time schedule'!GE42","v":0},{"$f":"'K90 - time schedule'!GF42","v":0},{"$f":"'K90 - time schedule'!GG42","v":0},{"$f":"'K90 - time schedule'!GH42","v":0},{"$f":"'K90 - time schedule'!GI42","v":0},{"$f":"'K90 - time schedule'!GJ42","v":0},{"$f":"'K90 - time schedule'!GK42","v":0},{"$f":"'K90 - time schedule'!GL42","v":0},{"$f":"'K90 - time schedule'!GM42","v":0},{"$f":"'K90 - time schedule'!GN42","v":0},{"$f":"'K90 - time schedule'!GO42","v":0},{"$f":"'K90 - time schedule'!GP42","v":0},{"$f":"'K90 - time schedule'!GQ42","v":0},{"$f":"'K90 - time schedule'!GR42","v":0},{"$f":"'K90 - time schedule'!GS42","v":0},{"$f":"'K90 - time schedule'!GT42","v":0},{"$f":"'K90 - time schedule'!GU42","v":0},{"$f":"'K90 - time schedule'!GV42","v":0},{"$f":"'K90 - time schedule'!GW42","v":0},{"$f":"'K90 - time schedule'!GX42","v":0},{"$f":"'K90 - time schedule'!GY42","v":0},{"$f":"'K90 - time schedule'!GZ42","v":0},{"$f":"'K90 - time schedule'!HA42","v":0},{"$f":"'K90 - time schedule'!HB42","v":0},{"$f":"'K90 - time schedule'!HC42","v":0},{"$f":"'K90 - time schedule'!HD42","v":0},{"$f":"'K90 - time schedule'!HE42","v":0},{"$f":"'K90 - time schedule'!HF42","v":0},{"$f":"'K90 - time schedule'!HG42","v":0},{"$f":"'K90 - time schedule'!HH42","v":0},{"$f":"'K90 - time schedule'!HI42","v":0},{"$f":"'K90 - time schedule'!HJ42","v":0},{"$f":"'K90 - time schedule'!HK42","v":0},{"$f":"'K90 - time schedule'!HL42","v":0},{"$f":"'K90 - time schedule'!HM42","v":0},{"$f":"'K90 - time schedule'!HN42","v":0},{"$f":"'K90 - time schedule'!HO42","v":0},{"$f":"'K90 - time schedule'!HP42","v":0},{"$f":"'K90 - time schedule'!HQ42","v":0},{"$f":"'K90 - time schedule'!HR42","v":0},{"$f":"'K90 - time schedule'!HS42","v":0},{"$f":"'K90 - time schedule'!HT42","v":0},{"$f":"'K90 - time schedule'!HU42","v":0},{"$f":"'K90 - time schedule'!HV42","v":0},{"$f":"'K90 - time schedule'!HW42","v":0},{"$f":"'K90 - time schedule'!HX42","v":0},{"$f":"'K90 - time schedule'!HY42","v":0},{"$f":"'K90 - time schedule'!HZ42","v":0},{"$f":"'K90 - time schedule'!IA42","v":0},{"$f":"'K90 - time schedule'!IB42","v":0},{"$f":"'K90 - time schedule'!IC42","v":0},{"$f":"'K90 - time schedule'!ID42","v":0},{"$f":"'K90 - time schedule'!IE42","v":0},{"$f":"'K90 - time schedule'!IF42","v":0},{"$f":"'K90 - time schedule'!IG42","v":0},{"$f":"'K90 - time schedule'!IH42","v":0},{"$f":"'K90 - time schedule'!II42","v":0},{"$f":"'K90 - time schedule'!IJ42","v":0},{"$f":"'K90 - time schedule'!IK42","v":0},{"$f":"'K90 - time schedule'!IL42","v":0},{"$f":"'K90 - time schedule'!IM42","v":0},{"$f":"'K90 - time schedule'!IN42","v":0},{"$f":"'K90 - time schedule'!IO42","v":0},{"$f":"'K90 - time schedule'!IP42","v":0},{"$f":"'K90 - time schedule'!IQ42","v":0},{"$f":"'K90 - time schedule'!IR42","v":0},{"$f":"'K90 - time schedule'!IS42","v":0},{"$f":"'K90 - time schedule'!IT42","v":0},{"$f":"'K90 - time schedule'!IU42","v":0},{"$f":"'K90 - time schedule'!IV42","v":0},{"$f":"'K90 - time schedule'!IW42","v":0},{"$f":"'K90 - time schedule'!IX42","v":0},{"$f":"'K90 - time schedule'!IY42","v":0},{"$f":"'K90 - time schedule'!IZ42","v":0},{"$f":"'K90 - time schedule'!JA42","v":0},{"$f":"'K90 - time schedule'!JB42","v":0},{"$f":"'K90 - time schedule'!JC42","v":0},{"$f":"'K90 - time schedule'!JD42","v":0},{"$f":"'K90 - time schedule'!JE42","v":0},{"$f":"'K90 - time schedule'!JF42","v":0},{"$f":"'K90 - time schedule'!JG42","v":0},{"$f":"'K90 - time schedule'!JH42","v":0},{"$f":"'K90 - time schedule'!JI42","v":0},{"$f":"'K90 - time schedule'!JJ42","v":0},{"$f":"'K90 - time schedule'!JK42","v":0},{"$f":"'K90 - time schedule'!JL42","v":0},{"$f":"'K90 - time schedule'!JM42","v":0},{"$f":"'K90 - time schedule'!JN42","v":0},{"$f":"'K90 - time schedule'!JO42","v":0},{"$f":"'K90 - time schedule'!JP42","v":0},{"$f":"'K90 - time schedule'!JQ42","v":0},{"$f":"'K90 - time schedule'!JR42","v":0},{"$f":"'K90 - time schedule'!JS42","v":0},{"$f":"'K90 - time schedule'!JT42","v":0},{"$f":"'K90 - time schedule'!JU42","v":0},{"$f":"'K90 - time schedule'!JV42","v":0},{"$f":"'K90 - time schedule'!JW42","v":0},{"$f":"'K90 - time schedule'!JX42","v":0},{"$f":"'K90 - time schedule'!JY42","v":0},{"$f":"'K90 - time schedule'!JZ42","v":0},{"$f":"'K90 - time schedule'!KA42","v":0},{"$f":"'K90 - time schedule'!KB42","v":0},{"$f":"'K90 - time schedule'!KC42","v":0},{"$f":"'K90 - time schedule'!KD42","v":0},{"$f":"'K90 - time schedule'!KE42","v":0},{"$f":"'K90 - time schedule'!KF42","v":0},{"$f":"'K90 - time schedule'!KG42","v":0},{"$f":"'K90 - time schedule'!KH42","v":0},{"$f":"'K90 - time schedule'!KI42","v":0},{"$f":"'K90 - time schedule'!KJ42","v":0},{"$f":"'K90 - time schedule'!KK42","v":0},{"$f":"'K90 - time schedule'!KL42","v":0},{"$f":"'K90 - time schedule'!KM42","v":0},{"$f":"'K90 - time schedule'!KN42","v":0},{"$f":"'K90 - time schedule'!KO42","v":0},{"$f":"'K90 - time schedule'!KP42","v":0},{"$f":"'K90 - time schedule'!KQ42","v":0},{"$f":"'K90 - time schedule'!KR42","v":0},{"$f":"'K90 - time schedule'!KS42","v":0},{"$f":"'K90 - time schedule'!KT42","v":0}]
["Boiler room K90 - ash management (transport piping, silos)","K90",{"$f":"'K90 - time schedule'!G44","v":0},{"$f":"'K90 - time schedule'!H44","v":0},{"$f":"'K90 - time schedule'!I44","v":0},{"$f":"'K90 - time schedule'!J44","v":0},{"$f":"'K90 - time schedule'!K44","v":0},{"$f":"'K90 - time schedule'!L44","v":0},{"$f":"'K90 - time schedule'!M44","v":0},{"$f":"'K90 - time schedule'!N44","v":0},{"$f":"'K90 - time schedule'!O44","v":0},{"$f":"'K90 - time schedule'!P44","v":0},{"$f":"'K90 - time schedule'!Q44","v":0},{"$f":"'K90 - time schedule'!R44","v":0},{"$f":"'K90 - time schedule'!S44","v":0},{"$f":"'K90 - time schedule'!T44","v":0},{"$f":"'K90 - time schedule'!U44","v":0},{"$f":"'K90 - time schedule'!V44","v":0},{"$f":"'K90 - time schedule'!W44","v":0},{"$f":"'K90 - time schedule'!X44","v":0},{"$f":"'K90 - time schedule'!Y44","v":0},{"$f":"'K90 - time schedule'!Z44","v":0},{"$f":"'K90 - time schedule'!AA44","v":0},{"$f":"'K90 - time schedule'!AB44","v":0},{"$f":"'K90 - time schedule'!AC44","v":0},{"$f":"'K90 - time schedule'!AD44","v":0},{"$f":"'K90 - time schedule'!AE44","v":0},{"$f":"'K90 - time schedule'!AF44","v":0},{"$f":"'K90 - time schedule'!AG44","v":0},{"$f":"'K90 - time schedule'!AH44","v":0},{"$f":"'K90 - time schedule'!AI44","v":0},{"$f":"'K90 - time schedule'!AJ44","v":0},{"$f":"'K90 - time schedule'!AK44","v":0},{"$f":"'K90 - time schedule'!AL44","v":0},{"$f":"'K90 - time schedule'!AM44","v":0},{"$f":"'K90 - time schedule'!AN44","v":0},{"$f":"'K90 - time schedule'!AO44","v":0},{"$f":"'K90 - time schedule'!AP44","v":0},{"$f":"'K90 - time schedule'!AQ44","v":0},{"$f":"'K90 - time schedule'!AR44","v":0},{"$f":"'K90 - time schedule'!AS44","v":0},{"$f":"'K90 - time schedule'!AT44","v":0},{"$f":"'K90 - time schedule'!AU44","v":0},{"$f":"'K90 - time schedule'!AV44","v":0},{"$f":"'K90 - time schedule'!AW44","v":0},{"$f":"'K90 - time schedule'!AX44","v":0},{"$f":"'K90 - time schedule'!AY44","v":0},{"$f":"'K90 - time schedule'!AZ44","v":0},{"$f":"'K90 - time schedule'!BA44","v":0},{"$f":"'K90 - time schedule'!BB44","v":0},{"$f":"'K90 - time schedule'!BC44","v":0},{"$f":"'K90 - time schedule'!BD44","v":0},{"$f":"'K90 - time schedule'!BE44","v":0},{"$f":"'K90 - time schedule'!BF44","v":0},{"$f":"'K90 - time schedule'!BG44","v":0},{"$f":"'K90 - time schedule'!BH44","v":0},{"$f":"'K90 - time schedule'!BI44","v":0},{"$f":"'K90 - time schedule'!BJ44","v":0},{"$f":"'K90 - time schedule'!BK44","v":0},{"$f":"'K90 - time schedule'!BL44","v":0},{"$f":"'K90 - time schedule'!BM44","v":0},{"$f":"'K90 - time schedule'!BN44","v":0},{"$f":"'K90 - time schedule'!BO44","v":0},{"$f":"'K90 - time schedule'!BP44","v":0},{"$f":"'K90 - time schedule'!BQ44","v":0},{"$f":"'K90 - time schedule'!BR44","v":0},{"$f":"'K90 - time schedule'!BS44","v":0},{"$f":"'K90 - time schedule'!BT44","v":0},{"$f":"'K90 - time schedule'!BU44","v":0},{"$f":"'K90 - time schedule'!BV44","v":0},{"$f":"'K90 - time schedule'!BW44","v":0},{"$f":"'K90 - time schedule'!BX44","v":0},{"$f":"'K90 - time schedule'!BY44","v":0},{"$f":"'K90 - time schedule'!BZ44","v":0},{"$f":"'K90 - time schedule'!CA44","v":0},{"$f":"'K90 - time schedule'!CB44","v":0},{"$f":"'K90 - time schedule'!CC44","v":0},{"$f":"'K90 - time schedule'!CD44","v":0},{"$f":"'K90 - time schedule'!CE44","v":0},{"$f":"'K90 - time schedule'!CF44","v":0},{"$f":"'K90 - time schedule'!CG44","v":0},{"$f":"'K90 - time schedule'!CH44","v":0},{"$f":"'K90 - time schedule'!CI44","v":0},{"$f":"'K90 - time schedule'!CJ44","v":0},{"$f":"'K90 - time schedule'!CK44","v":0},{"$f":"'K90 - time schedule'!CL44","v":0},{"$f":"'K90 - time schedule'!CM44","v":0},{"$f":"'K90 - time schedule'!CN44","v":0},{"$f":"'K90 - time schedule'!CO44","v":0},{"$f":"'K90 - time schedule'!CP44","v":0},{"$f":"'K90 - time schedule'!CQ44","v":0},{"$f":"'K90 - time schedule'!CR44","v":0},{"$f":"'K90 - time schedule'!CS44","v":0},{"$f":"'K90 - time schedule'!CT44","v":0},{"$f":"'K90 - time schedule'!CU44","v":0},{"$f":"'K90 - time schedule'!CV44","v":0},{"$f":"'K90 - time schedule'!CW44","v":0},{"$f":"'K90 - time schedule'!CX44","v":0},{"$f":"'K90 - time schedule'!CY44","v":0},{"$f":"'K90 - time schedule'!CZ44","v":0},{"$f":"'K90 - time schedule'!DA44","v":0},{"$f":"'K90 - time schedule'!DB44","v":0},{"$f":"'K90 - time schedule'!DC44","v":0},{"$f":"'K90 - time schedule'!DD44","v":0},{"$f":"'K90 - time schedule'!DE44","v":0},{"$f":"'K90 - time schedule'!DF44","v":0},{"$f":"'K90 - time schedule'!DG44","v":0},{"$f":"'K90 - time schedule'!DH44","v":0},{"$f":"'K90 - time schedule'!DI44","v":0},{"$f":"'K90 - time schedule'!DJ44","v":0},{"$f":"'K90 - time schedule'!DK44","v":0},{"$f":"'K90 - time schedule'!DL44","v":0},{"$f":"'K90 - time schedule'!DM44","v":0},{"$f":"'K90 - time schedule'!DN44","v":0},{"$f":"'K90 - time schedule'!DO44","v":0},{"$f":"'K90 - time schedule'!DP44","v":0},{"$f":"'K90 - time schedule'!DQ44","v":0},{"$f":"'K90 - time schedule'!DR44","v":0},{"$f":"'K90 - time schedule'!DS44","v":0},{"$f":"'K90 - time schedule'!DT44","v":0},{"$f":"'K90 - time schedule'!DU44","v":0},{"$f":"'K90 - time schedule'!DV44","v":0},{"$f":"'K90 - time schedule'!DW44","v":0},{"$f":"'K90 - time schedule'!DX44","v":0},{"$f":"'K90 - time schedule'!DY44","v":0},{"$f":"'K90 - time schedule'!DZ44","v":0},{"$f":"'K90 - time schedule'!EA44","v":0},{"$f":"'K90 - time schedule'!EB44","v":0},{"$f":"'K90 - time schedule'!EC44","v":0},{"$f":"'K90 - time schedule'!ED44","v":0},{"$f":"'K90 - time schedule'!EE44","v":0},{"$f":"'K90 - time schedule'!EF44","v":0},{"$f":"'K90 - time schedule'!EG44","v":0},{"$f":"'K90 - time schedule'!EH44","v":0},{"$f":"'K90 - time schedule'!EI44","v":0},{"$f":"'K90 - time schedule'!EJ44","v":0},{"$f":"'K90 - time schedule'!EK44","v":0},{"$f":"'K90 - time schedule'!EL44","v":0},{"$f":"'K90 - time schedule'!EM44","v":0},{"$f":"'K90 - time schedule'!EN44","v":0},{"$f":"'K90 - time schedule'!EO44","v":0},{"$f":"'K90 - time schedule'!EP44","v":0},{"$f":"'K90 - time schedule'!EQ44","v":0},{"$f":"'K90 - time schedule'!ER44","v":0},{"$f":"'K90 - time schedule'!ES44","v":0},{"$f":"'K90 - time schedule'!ET44","v":0},{"$f":"'K90 - time schedule'!EU44","v":0},{"$f":"'K90 - time schedule'!EV44","v":0},{"$f":"'K90 - time schedule'!EW44","v":0},{"$f":"'K90 - time schedule'!EX44","v":0},{"$f":"'K90 - time schedule'!EY44","v":0},{"$f":"'K90 - time schedule'!EZ44","v":0},{"$f":"'K90 - time schedule'!FA44","v":0},{"$f":"'K90 - time schedule'!FB44","v":0},{"$f":"'K90 - time schedule'!FC44","v":0},{"$f":"'K90 - time schedule'!FD44","v":0},{"$f":"'K90 - time schedule'!FE44","v":0},{"$f":"'K90 - time schedule'!FF44","v":0},{"$f":"'K90 - time schedule'!FG44","v":0},{"$f":"'K90 - time schedule'!FH44","v":0},{"$f":"'K90 - time schedule'!FI44","v":0},{"$f":"'K90 - time schedule'!FJ44","v":0},{"$f":"'K90 - time schedule'!FK44","v":0},{"$f":"'K90 - time schedule'!FL44","v":0},{"$f":"'K90 - time schedule'!FM44","v":0},{"$f":"'K90 - time schedule'!FN44","v":0},{"$f":"'K90 - time schedule'!FO44","v":0},{"$f":"'K90 - time schedule'!FP44","v":0},{"$f":"'K90 - time schedule'!FQ44","v":0},{"$f":"'K90 - time schedule'!FR44","v":0},{"$f":"'K90 - time schedule'!FS44","v":0},{"$f":"'K90 - time schedule'!FT44","v":0},{"$f":"'K90 - time schedule'!FU44","v":0},{"$f":"'K90 - time schedule'!FV44","v":0},{"$f":"'K90 - time schedule'!FW44","v":0},{"$f":"'K90 - time schedule'!FX44","v":0},{"$f":"'K90 - time schedule'!FY44","v":0},{"$f":"'K90 - time schedule'!FZ44","v":0},{"$f":"'K90 - time schedule'!GA44","v":0},{"$f":"'K90 - time schedule'!GB44","v":0},{"$f":"'K90 - time schedule'!GC44","v":0},{"$f":"'K90 - time schedule'!GD44","v":0},{"$f":"'K90 - time schedule'!GE44","v":0},{"$f":"'K90 - time schedule'!GF44","v":0},{"$f":"'K90 - time schedule'!GG44","v":0},{"$f":"'K90 - time schedule'!GH44","v":0},{"$f":"'K90 - time schedule'!GI44","v":0},{"$f":"'K90 - time schedule'!GJ44","v":0},{"$f":"'K90 - time schedule'!GK44","v":0},{"$f":"'K90 - time schedule'!GL44","v":0},{"$f":"'K90 - time schedule'!GM44","v":0},{"$f":"'K90 - time schedule'!GN44","v":0},{"$f":"'K90 - time schedule'!GO44","v":0},{"$f":"'K90 - time schedule'!GP44","v":0},{"$f":"'K90 - time schedule'!GQ44","v":0},{"$f":"'K90 - time schedule'!GR44","v":0},{"$f":"'K90 - time schedule'!GS44","v":0},{"$f":"'K90 - time schedule'!GT44","v":0},{"$f":"'K90 - time schedule'!GU44","v":0},{"$f":"'K90 - time schedule'!GV44","v":0},{"$f":"'K90 - time schedule'!GW44","v":0},{"$f":"'K90 - time schedule'!GX44","v":0},{"$f":"'K90 - time schedule'!GY44","v":0},{"$f":"'K90 - time schedule'!GZ44","v":0},{"$f":"'K90 - time schedule'!HA44","v":0},{"$f":"'K90 - time schedule'!HB44","v":0},{"$f":"'K90 - time schedule'!HC44","v":0},{"$f":"'K90 - time schedule'!HD44","v":0},{"$f":"'K90 - time schedule'!HE44","v":0},{"$f":"'K90 - time schedule'!HF44","v":0},{"$f":"'K90 - time schedule'!HG44","v":0},{"$f":"'K90 - time schedule'!HH44","v":0},{"$f":"'K90 - time schedule'!HI44","v":0},{"$f":"'K90 - time schedule'!HJ44","v":0},{"$f":"'K90 - time schedule'!HK44","v":0},{"$f":"'K90 - time schedule'!HL44","v":0},{"$f":"'K90 - time schedule'!HM44","v":0},{"$f":"'K90 - time schedule'!HN44","v":0},{"$f":"'K90 - time schedule'!HO44","v":0},{"$f":"'K90 - time schedule'!HP44","v":0},{"$f":"'K90 - time schedule'!HQ44","v":0},{"$f":"'K90 - time schedule'!HR44","v":0},{"$f":"'K90 - time schedule'!HS44","v":0},{"$f":"'K90 - time schedule'!HT44","v":0},{"$f":"'K90 - time schedule'!HU44","v":0},{"$f":"'K90 - time schedule'!HV44","v":0},{"$f":"'K90 - time schedule'!HW44","v":0},{"$f":"'K90 - time schedule'!HX44","v":0},{"$f":"'K90 - time schedule'!HY44","v":0},{"$f":"'K90 - time schedule'!HZ44","v":0},{"$f":"'K90 - time schedule'!IA44","v":0},{"$f":"'K90 - time schedule'!IB44","v":0},{"$f":"'K90 - time schedule'!IC44","v":0},{"$f":"'K90 - time schedule'!ID44","v":0},{"$f":"'K90 - time schedule'!IE44","v":0},{"$f":"'K90 - time schedule'!IF44","v":0},{"$f":"'K90 - time schedule'!IG44","v":0},{"$f":"'K90 - time schedule'!IH44","v":0},{"$f":"'K90 - time schedule'!II44","v":0},{"$f":"'K90 - time schedule'!IJ44","v":0},{"$f":"'K90 - time schedule'!IK44","v":0},{"$f":"'K90 - time schedule'!IL44","v":0},{"$f":"'K90 - time schedule'!IM44","v":0},{"$f":"'K90 - time schedule'!IN44","v":0},{"$f":"'K90 - time schedule'!IO44","v":0},{"$f":"'K90 - time schedule'!IP44","v":0},{"$f":"'K90 - time schedule'!IQ44","v":0},{"$f":"'K90 - time schedule'!IR44","v":0},{"$f":"'K90 - time schedule'!IS44","v":0},{"$f":"'K90 - time schedule'!IT44","v":0},{"$f":"'K90 - time schedule'!IU44","v":0},{"$f":"'K90 - time schedule'!IV44","v":0},{"$f":"'K90 - time schedule'!IW44","v":0},{"$f":"'K90 - time schedule'!IX44","v":0},{"$f":"'K90 - time schedule'!IY44","v":0},{"$f":"'K90 - time schedule'!IZ44","v":0},{"$f":"'K90 - time schedule'!JA44","v":0},{"$f":"'K90 - time schedule'!JB44","v":0},{"$f":"'K90 - time schedule'!JC44","v":0},{"$f":"'K90 - time schedule'!JD44","v":0},{"$f":"'K90 - time schedule'!JE44","v":0},{"$f":"'K90 - time schedule'!JF44","v":0},{"$f":"'K90 - time schedule'!JG44","v":0},{"$f":"'K90 - time schedule'!JH44","v":0},{"$f":"'K90 - time schedule'!JI44","v":0},{"$f":"'K90 - time schedule'!JJ44","v":0},{"$f":"'K90 - time schedule'!JK44","v":0},{"$f":"'K90 - time schedule'!JL44","v":0},{"$f":"'K90 - time schedule'!JM44","v":0},{"$f":"'K90 - time schedule'!JN44","v":0},{"$f":"'K90 - time schedule'!JO44","v":0},{"$f":"'K90 - time schedule'!JP44","v":0},{"$f":"'K90 - time schedule'!JQ44","v":0},{"$f":"'K90 - time schedule'!JR44","v":0},{"$f":"'K90 - time schedule'!JS44","v":0},{"$f":"'K90 - time schedule'!JT44","v":0},{"$f":"'K90 - time schedule'!JU44","v":0},{"$f":"'K90 - time schedule'!JV44","v":0},{"$f":"'K90 - time schedule'!JW44","v":0},{"$f":"'K90 - time schedule'!JX44","v":0},{"$f":"'K90 - time schedule'!JY44","v":0},{"$f":"'K90 - time schedule'!JZ44","v":0},{"$f":"'K90 - time schedule'!KA44","v":0},{"$f":"'K90 - time schedule'!KB44","v":0},{"$f":"'K90 - time schedule'!KC44","v":0},{"$f":"'K90 - time schedule'!KD44","v":0},{"$f":"'K90 - time schedule'!KE44","v":0},{"$f":"'K90 - time schedule'!KF44","v":0},{"$f":"'K90 - time schedule'!KG44","v":0},{"$f":"'K90 - time schedule'!KH44","v":0},{"$f":"'K90 - time schedule'!KI44","v":0},{"$f":"'K90 - time schedule'!KJ44","v":0},{"$f":"'K90 - time schedule'!KK44","v":0},{"$f":"'K90 - time schedule'!KL44","v":0},{"$f":"'K90 - time schedule'!KM44","v":0},{"$f":"'K90 - time schedule'!KN44","v":0},{"$f":"'K90 - time schedule'!KO44","v":0},{"$f":"'K90 - time schedule'!KP44","v":0},{"$f":"'K90 - time schedule'!KQ44","v":0},{"$f":"'K90 - time schedule'!KR44","v":0},{"$f":"'K90 - time schedule'!KS44","v":0},{"$f":"'K90 - time schedule'!KT44","v":0}]
["Boiler room K90 - other above not specified items","K90",{"$f":"'K90 - time schedule'!G46","v":0},{"$f":"'K90 - time schedule'!H46","v":0},{"$f":"'K90 - time schedule'!I46","v":0},{"$f":"'K90 - time schedule'!J46","v":0},{"$f":"'K90 - time schedule'!K46","v":0},{"$f":"'K90 - time schedule'!L46","v":0},{"$f":"'K90 - time schedule'!M46","v":0},{"$f":"'K90 - time schedule'!N46","v":0},{"$f":"'K90 - time schedule'!O46","v":0},{"$f":"'K90 - time schedule'!P46","v":0},{"$f":"'K90 - time schedule'!Q46","v":0},{"$f":"'K90 - time schedule'!R46","v":0},{"$f":"'K90 - time schedule'!S46","v":0},{"$f":"'K90 - time schedule'!T46","v":0},{"$f":"'K90 - time schedule'!U46","v":0},{"$f":"'K90 - time schedule'!V46","v":0},{"$f":"'K90 - time schedule'!W46","v":0},{"$f":"'K90 - time schedule'!X46","v":0},{"$f":"'K90 - time schedule'!Y46","v":0},{"$f":"'K90 - time schedule'!Z46","v":0},{"$f":"'K90 - time schedule'!AA46","v":0},{"$f":"'K90 - time schedule'!AB46","v":0},{"$f":"'K90 - time schedule'!AC46","v":0},{"$f":"'K90 - time schedule'!AD46","v":0},{"$f":"'K90 - time schedule'!AE46","v":0},{"$f":"'K90 - time schedule'!AF46","v":0},{"$f":"'K90 - time schedule'!AG46","v":0},{"$f":"'K90 - time schedule'!AH46","v":0},{"$f":"'K90 - time schedule'!AI46","v":0},{"$f":"'K90 - time schedule'!AJ46","v":0},{"$f":"'K90 - time schedule'!AK46","v":0},{"$f":"'K90 - time schedule'!AL46","v":0},{"$f":"'K90 - time schedule'!AM46","v":0},{"$f":"'K90 - time schedule'!AN46","v":0},{"$f":"'K90 - time schedule'!AO46","v":0},{"$f":"'K90 - time schedule'!AP46","v":0},{"$f":"'K90 - time schedule'!AQ46","v":0},{"$f":"'K90 - time schedule'!AR46","v":0},{"$f":"'K90 - time schedule'!AS46","v":0},{"$f":"'K90 - time schedule'!AT46","v":0},{"$f":"'K90 - time schedule'!AU46","v":0},{"$f":"'K90 - time schedule'!AV46","v":0},{"$f":"'K90 - time schedule'!AW46","v":0},{"$f":"'K90 - time schedule'!AX46","v":0},{"$f":"'K90 - time schedule'!AY46","v":0},{"$f":"'K90 - time schedule'!AZ46","v":0},{"$f":"'K90 - time schedule'!BA46","v":0},{"$f":"'K90 - time schedule'!BB46","v":0},{"$f":"'K90 - time schedule'!BC46","v":0},{"$f":"'K90 - time schedule'!BD46","v":0},{"$f":"'K90 - time schedule'!BE46","v":0},{"$f":"'K90 - time schedule'!BF46","v":0},{"$f":"'K90 - time schedule'!BG46","v":0},{"$f":"'K90 - time schedule'!BH46","v":0},{"$f":"'K90 - time schedule'!BI46","v":0},{"$f":"'K90 - time schedule'!BJ46","v":0},{"$f":"'K90 - time schedule'!BK46","v":0},{"$f":"'K90 - time schedule'!BL46","v":0},{"$f":"'K90 - time schedule'!BM46","v":0},{"$f":"'K90 - time schedule'!BN46","v":0},{"$f":"'K90 - time schedule'!BO46","v":0},{"$f":"'K90 - time schedule'!BP46","v":0},{"$f":"'K90 - time schedule'!BQ46","v":0},{"$f":"'K90 - time schedule'!BR46","v":0},{"$f":"'K90 - time schedule'!BS46","v":0},{"$f":"'K90 - time schedule'!BT46","v":0},{"$f":"'K90 - time schedule'!BU46","v":0},{"$f":"'K90 - time schedule'!BV46","v":0},{"$f":"'K90 - time schedule'!BW46","v":0},{"$f":"'K90 - time schedule'!BX46","v":0},{"$f":"'K90 - time schedule'!BY46","v":0},{"$f":"'K90 - time schedule'!BZ46","v":0},{"$f":"'K90 - time schedule'!CA46","v":0},{"$f":"'K90 - time schedule'!CB46","v":0},{"$f":"'K90 - time schedule'!CC46","v":0},{"$f":"'K90 - time schedule'!CD46","v":0},{"$f":"'K90 - time schedule'!CE46","v":0},{"$f":"'K90 - time schedule'!CF46","v":0},{"$f":"'K90 - time schedule'!CG46","v":0},{"$f":"'K90 - time schedule'!CH46","v":0},{"$f":"'K90 - time schedule'!CI46","v":0},{"$f":"'K90 - time schedule'!CJ46","v":0},{"$f":"'K90 - time schedule'!CK46","v":0},{"$f":"'K90 - time schedule'!CL46","v":0},{"$f":"'K90 - time schedule'!CM46","v":0},{"$f":"'K90 - time schedule'!CN46","v":0},{"$f":"'K90 - time schedule'!CO46","v":0},{"$f":"'K90 - time schedule'!CP46","v":0},{"$f":"'K90 - time schedule'!CQ46","v":0},{"$f":"'K90 - time schedule'!CR46","v":0},{"$f":"'K90 - time schedule'!CS46","v":0},{"$f":"'K90 - time schedule'!CT46","v":0},{"$f":"'K90 - time schedule'!CU46","v":0},{"$f":"'K90 - time schedule'!CV46","v":0},{"$f":"'K90 - time schedule'!CW46","v":0},{"$f":"'K90 - time schedule'!CX46","v":0},{"$f":"'K90 - time schedule'!CY46","v":0},{"$f":"'K90 - time schedule'!CZ46","v":0},{"$f":"'K90 - time schedule'!DA46","v":0},{"$f":"'K90 - time schedule'!DB46","v":0},{"$f":"'K90 - time schedule'!DC46","v":0},{"$f":"'K90 - time schedule'!DD46","v":0},{"$f":"'K90 - time schedule'!DE46","v":0},{"$f":"'K90 - time schedule'!DF46","v":0},{"$f":"'K90 - time schedule'!DG46","v":0},{"$f":"'K90 - time schedule'!DH46","v":0},{"$f":"'K90 - time schedule'!DI46","v":0},{"$f":"'K90 - time schedule'!DJ46","v":0},{"$f":"'K90 - time schedule'!DK46","v":0},{"$f":"'K90 - time schedule'!DL46","v":0},{"$f":"'K90 - time schedule'!DM46","v":0},{"$f":"'K90 - time schedule'!DN46","v":0},{"$f":"'K90 - time schedule'!DO46","v":0},{"$f":"'K90 - time schedule'!DP46","v":0},{"$f":"'K90 - time schedule'!DQ46","v":0},{"$f":"'K90 - time schedule'!DR46","v":0},{"$f":"'K90 - time schedule'!DS46","v":0},{"$f":"'K90 - time schedule'!DT46","v":0},{"$f":"'K90 - time schedule'!DU46","v":0},{"$f":"'K90 - time schedule'!DV46","v":0},{"$f":"'K90 - time schedule'!DW46","v":0},{"$f":"'K90 - time schedule'!DX46","v":0},{"$f":"'K90 - time schedule'!DY46","v":0},{"$f":"'K90 - time schedule'!DZ46","v":0},{"$f":"'K90 - time schedule'!EA46","v":0},{"$f":"'K90 - time schedule'!EB46","v":0},{"$f":"'K90 - time schedule'!EC46","v":0},{"$f":"'K90 - time schedule'!ED46","v":0},{"$f":"'K90 - time schedule'!EE46","v":0},{"$f":"'K90 - time schedule'!EF46","v":0},{"$f":"'K90 - time schedule'!EG46","v":0},{"$f":"'K90 - time schedule'!EH46","v":0},{"$f":"'K90 - time schedule'!EI46","v":0},{"$f":"'K90 - time schedule'!EJ46","v":0},{"$f":"'K90 - time schedule'!EK46","v":0},{"$f":"'K90 - time schedule'!EL46","v":0},{"$f":"'K90 - time schedule'!EM46","v":0},{"$f":"'K90 - time schedule'!EN46","v":0},{"$f":"'K90 - time schedule'!EO46","v":0},{"$f":"'K90 - time schedule'!EP46","v":0},{"$f":"'K90 - time schedule'!EQ46","v":0},{"$f":"'K90 - time schedule'!ER46","v":0},{"$f":"'K90 - time schedule'!ES46","v":0},{"$f":"'K90 - time schedule'!ET46","v":0},{"$f":"'K90 - time schedule'!EU46","v":0},{"$f":"'K90 - time schedule'!EV46","v":0},{"$f":"'K90 - time schedule'!EW46","v":0},{"$f":"'K90 - time schedule'!EX46","v":0},{"$f":"'K90 - time schedule'!EY46","v":0},{"$f":"'K90 - time schedule'!EZ46","v":0},{"$f":"'K90 - time schedule'!FA46","v":0},{"$f":"'K90 - time schedule'!FB46","v":0},{"$f":"'K90 - time schedule'!FC46","v":0},{"$f":"'K90 - time schedule'!FD46","v":0},{"$f":"'K90 - time schedule'!FE46","v":0},{"$f":"'K90 - time schedule'!FF46","v":0},{"$f":"'K90 - time schedule'!FG46","v":0},{"$f":"'K90 - time schedule'!FH46","v":0},{"$f":"'K90 - time schedule'!FI46","v":0},{"$f":"'K90 - time schedule'!FJ46","v":0},{"$f":"'K90 - time schedule'!FK46","v":0},{"$f":"'K90 - time schedule'!FL46","v":0},{"$f":"'K90 - time schedule'!FM46","v":0},{"$f":"'K90 - time schedule'!FN46","v":0},{"$f":"'K90 - time schedule'!FO46","v":0},{"$f":"'K90 - time schedule'!FP46","v":0},{"$f":"'K90 - time schedule'!FQ46","v":0},{"$f":"'K90 - time schedule'!FR46","v":0},{"$f":"'K90 - time schedule'!FS46","v":0},{"$f":"'K90 - time schedule'!FT46","v":0},{"$f":"'K90 - time schedule'!FU46","v":0},{"$f":"'K90 - time schedule'!FV46","v":0},{"$f":"'K90 - time schedule'!FW46","v":0},{"$f":"'K90 - time schedule'!FX46","v":0},{"$f":"'K90 - time schedule'!FY46","v":0},{"$f":"'K90 - time schedule'!FZ46","v":0},{"$f":"'K90 - time schedule'!GA46","v":0},{"$f":"'K90 - time schedule'!GB46","v":0},{"$f":"'K90 - time schedule'!GC46","v":0},{"$f":"'K90 - time schedule'!GD46","v":0},{"$f":"'K90 - time schedule'!GE46","v":0},{"$f":"'K90 - time schedule'!GF46","v":0},{"$f":"'K90 - time schedule'!GG46","v":0},{"$f":"'K90 - time schedule'!GH46","v":0},{"$f":"'K90 - time schedule'!GI46","v":0},{"$f":"'K90 - time schedule'!GJ46","v":0},{"$f":"'K90 - time schedule'!GK46","v":0},{"$f":"'K90 - time schedule'!GL46","v":0},{"$f":"'K90 - time schedule'!GM46","v":0},{"$f":"'K90 - time schedule'!GN46","v":0},{"$f":"'K90 - time schedule'!GO46","v":0},{"$f":"'K90 - time schedule'!GP46","v":0},{"$f":"'K90 - time schedule'!GQ46","v":0},{"$f":"'K90 - time schedule'!GR46","v":0},{"$f":"'K90 - time schedule'!GS46","v":0},{"$f":"'K90 - time schedule'!GT46","v":0},{"$f":"'K90 - time schedule'!GU46","v":0},{"$f":"'K90 - time schedule'!GV46","v":0},{"$f":"'K90 - time schedule'!GW46","v":0},{"$f":"'K90 - time schedule'!GX46","v":0},{"$f":"'K90 - time schedule'!GY46","v":0},{"$f":"'K90 - time schedule'!GZ46","v":0},{"$f":"'K90 - time schedule'!HA46","v":0},{"$f":"'K90 - time schedule'!HB46","v":0},{"$f":"'K90 - time schedule'!HC46","v":0},{"$f":"'K90 - time schedule'!HD46","v":0},{"$f":"'K90 - time schedule'!HE46","v":0},{"$f":"'K90 - time schedule'!HF46","v":0},{"$f":"'K90 - time schedule'!HG46","v":0},{"$f":"'K90 - time schedule'!HH46","v":0},{"$f":"'K90 - time schedule'!HI46","v":0},{"$f":"'K90 - time schedule'!HJ46","v":0},{"$f":"'K90 - time schedule'!HK46","v":0},{"$f":"'K90 - time schedule'!HL46","v":0},{"$f":"'K90 - time schedule'!HM46","v":0},{"$f":"'K90 - time schedule'!HN46","v":0},{"$f":"'K90 - time schedule'!HO46","v":0},{"$f":"'K90 - time schedule'!HP46","v":0},{"$f":"'K90 - time schedule'!HQ46","v":0},{"$f":"'K90 - time schedule'!HR46","v":0},{"$f":"'K90 - time schedule'!HS46","v":0},{"$f":"'K90 - time schedule'!HT46","v":0},{"$f":"'K90 - time schedule'!HU46","v":0},{"$f":"'K90 - time schedule'!HV46","v":0},{"$f":"'K90 - time schedule'!HW46","v":0},{"$f":"'K90 - time schedule'!HX46","v":0},{"$f":"'K90 - time schedule'!HY46","v":0},{"$f":"'K90 - time schedule'!HZ46","v":0},{"$f":"'K90 - time schedule'!IA46","v":0},{"$f":"'K90 - time schedule'!IB46","v":0},{"$f":"'K90 - time schedule'!IC46","v":0},{"$f":"'K90 - time schedule'!ID46","v":0},{"$f":"'K90 - time schedule'!IE46","v":0},{"$f":"'K90 - time schedule'!IF46","v":0},{"$f":"'K90 - time schedule'!IG46","v":0},{"$f":"'K90 - time schedule'!IH46","v":0},{"$f":"'K90 - time schedule'!II46","v":0},{"$f":"'K90 - time schedule'!IJ46","v":0},{"$f":"'K90 - time schedule'!IK46","v":0},{"$f":"'K90 - time schedule'!IL46","v":0},{"$f":"'K90 - time schedule'!IM46","v":0},{"$f":"'K90 - time schedule'!IN46","v":0},{"$f":"'K90 - time schedule'!IO46","v":0},{"$f":"'K90 - time schedule'!IP46","v":0},{"$f":"'K90 - time schedule'!IQ46","v":0},{"$f":"'K90 - time schedule'!IR46","v":0},{"$f":"'K90 - time schedule'!IS46","v":0},{"$f":"'K90 - time schedule'!IT46","v":0},{"$f":"'K90 - time schedule'!IU46","v":0},{"$f":"'K90 - time schedule'!IV46","v":0},{"$f":"'K90 - time schedule'!IW46","v":0},{"$f":"'K90 - time schedule'!IX46","v":0},{"$f":"'K90 - time schedule'!IY46","v":0},{"$f":"'K90 - time schedule'!IZ46","v":0},{"$f":"'K90 - time schedule'!JA46","v":0},{"$f":"'K90 - time schedule'!JB46","v":0},{"$f":"'K90 - time schedule'!JC46","v":0},{"$f":"'K90 - time schedule'!JD46","v":0},{"$f":"'K90 - time schedule'!JE46","v":0},{"$f":"'K90 - time schedule'!JF46","v":0},{"$f":"'K90 - time schedule'!JG46","v":0},{"$f":"'K90 - time schedule'!JH46","v":0},{"$f":"'K90 - time schedule'!JI46","v":0},{"$f":"'K90 - time schedule'!JJ46","v":0},{"$f":"'K90 - time schedule'!JK46","v":0},{"$f":"'K90 - time schedule'!JL46","v":0},{"$f":"'K90 - time schedule'!JM46","v":0},{"$f":"'K90 - time schedule'!JN46","v":0},{"$f":"'K90 - time schedule'!JO46","v":0},{"$f":"'K90 - time schedule'!JP46","v":0},{"$f":"'K90 - time schedule'!JQ46","v":0},{"$f":"'K90 - time schedule'!JR46","v":0},{"$f":"'K90 - time schedule'!JS46","v":0},{"$f":"'K90 - time schedule'!JT46","v":0},{"$f":"'K90 - time schedule'!JU46","v":0},{"$f":"'K90 - time schedule'!JV46","v":0},{"$f":"'K90 - time schedule'!JW46","v":0},{"$f":"'K90 - time schedule'!JX46","v":0},{"$f":"'K90 - time schedule'!JY46","v":0},{"$f":"'K90 - time schedule'!JZ46","v":0},{"$f":"'K90 - time schedule'!KA46","v":0},{"$f":"'K90 - time schedule'!KB46","v":0},{"$f":"'K90 - time schedule'!KC46","v":0},{"$f":"'K90 - time schedule'!KD46","v":0},{"$f":"'K90 - time schedule'!KE46","v":0},{"$f":"'K90 - time schedule'!KF46","v":0},{"$f":"'K90 - time schedule'!KG46","v":0},{"$f":"'K90 - time schedule'!KH46","v":0},{"$f":"'K90 - time schedule'!KI46","v":0},{"$f":"'K90 - time schedule'!KJ46","v":0},{"$f":"'K90 - time schedule'!KK46","v":0},{"$f":"'K90 - time schedule'!KL46","v":0},{"$f":"'K90 - time schedule'!KM46","v":0},{"$f":"'K90 - time schedule'!KN46","v":0},{"$f":"'K90 - time schedule'!KO46","v":0},{"$f":"'K90 - time schedule'!KP46","v":0},{"$f":"'K90 - time schedule'!KQ46","v":0},{"$f":"'K90 - time schedule'!KR46","v":0},{"$f":"'K90 - time schedule'!KS46","v":0},{"$f":"'K90 - time schedule'!KT46","v":0}]
["Boiler room K90 - completion of construction works","K90",{"$f":"'K90 - time schedule'!G48","v":0},{"$f":"'K90 - time schedule'!H48","v":0},{"$f":"'K90 - time schedule'!I48","v":0},{"$f":"'K90 - time schedule'!J48","v":0},{"$f":"'K90 - time schedule'!K48","v":0},{"$f":"'K90 - time schedule'!L48","v":0},{"$f":"'K90 - time schedule'!M48","v":0},{"$f":"'K90 - time schedule'!N48","v":0},{"$f":"'K90 - time schedule'!O48","v":0},{"$f":"'K90 - time schedule'!P48","v":0},{"$f":"'K90 - time schedule'!Q48","v":0},{"$f":"'K90 - time schedule'!R48","v":0},{"$f":"'K90 - time schedule'!S48","v":0},{"$f":"'K90 - time schedule'!T48","v":0},{"$f":"'K90 - time schedule'!U48","v":0},{"$f":"'K90 - time schedule'!V48","v":0},{"$f":"'K90 - time schedule'!W48","v":0},{"$f":"'K90 - time schedule'!X48","v":0},{"$f":"'K90 - time schedule'!Y48","v":0},{"$f":"'K90 - time schedule'!Z48","v":0},{"$f":"'K90 - time schedule'!AA48","v":0},{"$f":"'K90 - time schedule'!AB48","v":0},{"$f":"'K90 - time schedule'!AC48","v":0},{"$f":"'K90 - time schedule'!AD48","v":0},{"$f":"'K90 - time schedule'!AE48","v":0},{"$f":"'K90 - time schedule'!AF48","v":0},{"$f":"'K90 - time schedule'!AG48","v":0},{"$f":"'K90 - time schedule'!AH48","v":0},{"$f":"'K90 - time schedule'!AI48","v":0},{"$f":"'K90 - time schedule'!AJ48","v":0},{"$f":"'K90 - time schedule'!AK48","v":0},{"$f":"'K90 - time schedule'!AL48","v":0},{"$f":"'K90 - time schedule'!AM48","v":0},{"$f":"'K90 - time schedule'!AN48","v":0},{"$f":"'K90 - time schedule'!AO48","v":0},{"$f":"'K90 - time schedule'!AP48","v":0},{"$f":"'K90 - time schedule'!AQ48","v":0},{"$f":"'K90 - time schedule'!AR48","v":0},{"$f":"'K90 - time schedule'!AS48","v":0},{"$f":"'K90 - time schedule'!AT48","v":0},{"$f":"'K90 - time schedule'!AU48","v":0},{"$f":"'K90 - time schedule'!AV48","v":0},{"$f":"'K90 - time schedule'!AW48","v":0},{"$f":"'K90 - time schedule'!AX48","v":0},{"$f":"'K90 - time schedule'!AY48","v":0},{"$f":"'K90 - time schedule'!AZ48","v":0},{"$f":"'K90 - time schedule'!BA48","v":0},{"$f":"'K90 - time schedule'!BB48","v":0},{"$f":"'K90 - time schedule'!BC48","v":0},{"$f":"'K90 - time schedule'!BD48","v":0},{"$f":"'K90 - time schedule'!BE48","v":0},{"$f":"'K90 - time schedule'!BF48","v":0},{"$f":"'K90 - time schedule'!BG48","v":0},{"$f":"'K90 - time schedule'!BH48","v":0},{"$f":"'K90 - time schedule'!BI48","v":0},{"$f":"'K90 - time schedule'!BJ48","v":0},{"$f":"'K90 - time schedule'!BK48","v":0},{"$f":"'K90 - time schedule'!BL48","v":0},{"$f":"'K90 - time schedule'!BM48","v":0},{"$f":"'K90 - time schedule'!BN48","v":0},{"$f":"'K90 - time schedule'!BO48","v":0},{"$f":"'K90 - time schedule'!BP48","v":0},{"$f":"'K90 - time schedule'!BQ48","v":0},{"$f":"'K90 - time schedule'!BR48","v":0},{"$f":"'K90 - time schedule'!BS48","v":0},{"$f":"'K90 - time schedule'!BT48","v":0},{"$f":"'K90 - time schedule'!BU48","v":0},{"$f":"'K90 - time schedule'!BV48","v":0},{"$f":"'K90 - time schedule'!BW48","v":0},{"$f":"'K90 - time schedule'!BX48","v":0},{"$f":"'K90 - time schedule'!BY48","v":0},{"$f":"'K90 - time schedule'!BZ48","v":0},{"$f":"'K90 - time schedule'!CA48","v":0},{"$f":"'K90 - time schedule'!CB48","v":0},{"$f":"'K90 - time schedule'!CC48","v":0},{"$f":"'K90 - time schedule'!CD48","v":0},{"$f":"'K90 - time schedule'!CE48","v":0},{"$f":"'K90 - time schedule'!CF48","v":0},{"$f":"'K90 - time schedule'!CG48","v":0},{"$f":"'K90 - time schedule'!CH48","v":0},{"$f":"'K90 - time schedule'!CI48","v":0},{"$f":"'K90 - time schedule'!CJ48","v":0},{"$f":"'K90 - time schedule'!CK48","v":0},{"$f":"'K90 - time schedule'!CL48","v":0},{"$f":"'K90 - time schedule'!CM48","v":0},{"$f":"'K90 - time schedule'!CN48","v":0},{"$f":"'K90 - time schedule'!CO48","v":0},{"$f":"'K90 - time schedule'!CP48","v":0},{"$f":"'K90 - time schedule'!CQ48","v":0},{"$f":"'K90 - time schedule'!CR48","v":0},{"$f":"'K90 - time schedule'!CS48","v":0},{"$f":"'K90 - time schedule'!CT48","v":0},{"$f":"'K90 - time schedule'!CU48","v":0},{"$f":"'K90 - time schedule'!CV48","v":0},{"$f":"'K90 - time schedule'!CW48","v":0},{"$f":"'K90 - time schedule'!CX48","v":0},{"$f":"'K90 - time schedule'!CY48","v":0},{"$f":"'K90 - time schedule'!CZ48","v":0},{"$f":"'K90 - time schedule'!DA48","v":0},{"$f":"'K90 - time schedule'!DB48","v":0},{"$f":"'K90 - time schedule'!DC48","v":0},{"$f":"'K90 - time schedule'!DD48","v":0},{"$f":"'K90 - time schedule'!DE48","v":0},{"$f":"'K90 - time schedule'!DF48","v":0},{"$f":"'K90 - time schedule'!DG48","v":0},{"$f":"'K90 - time schedule'!DH48","v":0},{"$f":"'K90 - time schedule'!DI48","v":0},{"$f":"'K90 - time schedule'!DJ48","v":0},{"$f":"'K90 - time schedule'!DK48","v":0},{"$f":"'K90 - time schedule'!DL48","v":0},{"$f":"'K90 - time schedule'!DM48","v":0},{"$f":"'K90 - time schedule'!DN48","v":0},{"$f":"'K90 - time schedule'!DO48","v":0},{"$f":"'K90 - time schedule'!DP48","v":0},{"$f":"'K90 - time schedule'!DQ48","v":0},{"$f":"'K90 - time schedule'!DR48","v":0},{"$f":"'K90 - time schedule'!DS48","v":0},{"$f":"'K90 - time schedule'!DT48","v":0},{"$f":"'K90 - time schedule'!DU48","v":0},{"$f":"'K90 - time schedule'!DV48","v":0},{"$f":"'K90 - time schedule'!DW48","v":0},{"$f":"'K90 - time schedule'!DX48","v":0},{"$f":"'K90 - time schedule'!DY48","v":0},{"$f":"'K90 - time schedule'!DZ48","v":0},{"$f":"'K90 - time schedule'!EA48","v":0},{"$f":"'K90 - time schedule'!EB48","v":0},{"$f":"'K90 - time schedule'!EC48","v":0},{"$f":"'K90 - time schedule'!ED48","v":0},{"$f":"'K90 - time schedule'!EE48","v":0},{"$f":"'K90 - time schedule'!EF48","v":0},{"$f":"'K90 - time schedule'!EG48","v":0},{"$f":"'K90 - time schedule'!EH48","v":0},{"$f":"'K90 - time schedule'!EI48","v":0},{"$f":"'K90 - time schedule'!EJ48","v":0},{"$f":"'K90 - time schedule'!EK48","v":0},{"$f":"'K90 - time schedule'!EL48","v":0},{"$f":"'K90 - time schedule'!EM48","v":0},{"$f":"'K90 - time schedule'!EN48","v":0},{"$f":"'K90 - time schedule'!EO48","v":0},{"$f":"'K90 - time schedule'!EP48","v":0},{"$f":"'K90 - time schedule'!EQ48","v":0},{"$f":"'K90 - time schedule'!ER48","v":0},{"$f":"'K90 - time schedule'!ES48","v":0},{"$f":"'K90 - time schedule'!ET48","v":0},{"$f":"'K90 - time schedule'!EU48","v":0},{"$f":"'K90 - time schedule'!EV48","v":0},{"$f":"'K90 - time schedule'!EW48","v":0},{"$f":"'K90 - time schedule'!EX48","v":0},{"$f":"'K90 - time schedule'!EY48","v":0},{"$f":"'K90 - time schedule'!EZ48","v":0},{"$f":"'K90 - time schedule'!FA48","v":0},{"$f":"'K90 - time schedule'!FB48","v":0},{"$f":"'K90 - time schedule'!FC48","v":0},{"$f":"'K90 - time schedule'!FD48","v":0},{"$f":"'K90 - time schedule'!FE48","v":0},{"$f":"'K90 - time schedule'!FF48","v":0},{"$f":"'K90 - time schedule'!FG48","v":0},{"$f":"'K90 - time schedule'!FH48","v":0},{"$f":"'K90 - time schedule'!FI48","v":0},{"$f":"'K90 - time schedule'!FJ48","v":0},{"$f":"'K90 - time schedule'!FK48","v":0},{"$f":"'K90 - time schedule'!FL48","v":0},{"$f":"'K90 - time schedule'!FM48","v":0},{"$f":"'K90 - time schedule'!FN48","v":0},{"$f":"'K90 - time schedule'!FO48","v":0},{"$f":"'K90 - time schedule'!FP48","v":0},{"$f":"'K90 - time schedule'!FQ48","v":0},{"$f":"'K90 - time schedule'!FR48","v":0},{"$f":"'K90 - time schedule'!FS48","v":0},{"$f":"'K90 - time schedule'!FT48","v":0},{"$f":"'K90 - time schedule'!FU48","v":0},{"$f":"'K90 - time schedule'!FV48","v":0},{"$f":"'K90 - time schedule'!FW48","v":0},{"$f":"'K90 - time schedule'!FX48","v":0},{"$f":"'K90 - time schedule'!FY48","v":0},{"$f":"'K90 - time schedule'!FZ48","v":0},{"$f":"'K90 - time schedule'!GA48","v":0},{"$f":"'K90 - time schedule'!GB48","v":0},{"$f":"'K90 - time schedule'!GC48","v":0},{"$f":"'K90 - time schedule'!GD48","v":0},{"$f":"'K90 - time schedule'!GE48","v":0},{"$f":"'K90 - time schedule'!GF48","v":0},{"$f":"'K90 - time schedule'!GG48","v":0},{"$f":"'K90 - time schedule'!GH48","v":0},{"$f":"'K90 - time schedule'!GI48","v":0},{"$f":"'K90 - time schedule'!GJ48","v":0},{"$f":"'K90 - time schedule'!GK48","v":0},{"$f":"'K90 - time schedule'!GL48","v":0},{"$f":"'K90 - time schedule'!GM48","v":0},{"$f":"'K90 - time schedule'!GN48","v":0},{"$f":"'K90 - time schedule'!GO48","v":0},{"$f":"'K90 - time schedule'!GP48","v":0},{"$f":"'K90 - time schedule'!GQ48","v":0},{"$f":"'K90 - time schedule'!GR48","v":0},{"$f":"'K90 - time schedule'!GS48","v":0},{"$f":"'K90 - time schedule'!GT48","v":0},{"$f":"'K90 - time schedule'!GU48","v":0},{"$f":"'K90 - time schedule'!GV48","v":0},{"$f":"'K90 - time schedule'!GW48","v":0},{"$f":"'K90 - time schedule'!GX48","v":0},{"$f":"'K90 - time schedule'!GY48","v":0},{"$f":"'K90 - time schedule'!GZ48","v":0},{"$f":"'K90 - time schedule'!HA48","v":0},{"$f":"'K90 - time schedule'!HB48","v":0},{"$f":"'K90 - time schedule'!HC48","v":0},{"$f":"'K90 - time schedule'!HD48","v":0},{"$f":"'K90 - time schedule'!HE48","v":0},{"$f":"'K90 - time schedule'!HF48","v":0},{"$f":"'K90 - time schedule'!HG48","v":0},{"$f":"'K90 - time schedule'!HH48","v":0},{"$f":"'K90 - time schedule'!HI48","v":0},{"$f":"'K90 - time schedule'!HJ48","v":0},{"$f":"'K90 - time schedule'!HK48","v":0},{"$f":"'K90 - time schedule'!HL48","v":0},{"$f":"'K90 - time schedule'!HM48","v":0},{"$f":"'K90 - time schedule'!HN48","v":0},{"$f":"'K90 - time schedule'!HO48","v":0},{"$f":"'K90 - time schedule'!HP48","v":0},{"$f":"'K90 - time schedule'!HQ48","v":0},{"$f":"'K90 - time schedule'!HR48","v":0},{"$f":"'K90 - time schedule'!HS48","v":0},{"$f":"'K90 - time schedule'!HT48","v":0},{"$f":"'K90 - time schedule'!HU48","v":0},{"$f":"'K90 - time schedule'!HV48","v":0},{"$f":"'K90 - time schedule'!HW48","v":0},{"$f":"'K90 - time schedule'!HX48","v":0},{"$f":"'K90 - time schedule'!HY48","v":0},{"$f":"'K90 - time schedule'!HZ48","v":0},{"$f":"'K90 - time schedule'!IA48","v":0},{"$f":"'K90 - time schedule'!IB48","v":0},{"$f":"'K90 - time schedule'!IC48","v":0},{"$f":"'K90 - time schedule'!ID48","v":0},{"$f":"'K90 - time schedule'!IE48","v":0},{"$f":"'K90 - time schedule'!IF48","v":0},{"$f":"'K90 - time schedule'!IG48","v":0},{"$f":"'K90 - time schedule'!IH48","v":0},{"$f":"'K90 - time schedule'!II48","v":0},{"$f":"'K90 - time schedule'!IJ48","v":0},{"$f":"'K90 - time schedule'!IK48","v":0},{"$f":"'K90 - time schedule'!IL48","v":0},{"$f":"'K90 - time schedule'!IM48","v":0},{"$f":"'K90 - time schedule'!IN48","v":0},{"$f":"'K90 - time schedule'!IO48","v":0},{"$f":"'K90 - time schedule'!IP48","v":0},{"$f":"'K90 - time schedule'!IQ48","v":0},{"$f":"'K90 - time schedule'!IR48","v":0},{"$f":"'K90 - time schedule'!IS48","v":0},{"$f":"'K90 - time schedule'!IT48","v":0},{"$f":"'K90 - time schedule'!IU48","v":0},{"$f":"'K90 - time schedule'!IV48","v":0},{"$f":"'K90 - time schedule'!IW48","v":0},{"$f":"'K90 - time schedule'!IX48","v":0},{"$f":"'K90 - time schedule'!IY48","v":0},{"$f":"'K90 - time schedule'!IZ48","v":0},{"$f":"'K90 - time schedule'!JA48","v":0},{"$f":"'K90 - time schedule'!JB48","v":0},{"$f":"'K90 - time schedule'!JC48","v":0},{"$f":"'K90 - time schedule'!JD48","v":0},{"$f":"'K90 - time schedule'!JE48","v":0},{"$f":"'K90 - time schedule'!JF48","v":0},{"$f":"'K90 - time schedule'!JG48","v":0},{"$f":"'K90 - time schedule'!JH48","v":0},{"$f":"'K90 - time schedule'!JI48","v":0},{"$f":"'K90 - time schedule'!JJ48","v":0},{"$f":"'K90 - time schedule'!JK48","v":0},{"$f":"'K90 - time schedule'!JL48","v":0},{"$f":"'K90 - time schedule'!JM48","v":0},{"$f":"'K90 - time schedule'!JN48","v":0},{"$f":"'K90 - time schedule'!JO48","v":0},{"$f":"'K90 - time schedule'!JP48","v":0},{"$f":"'K90 - time schedule'!JQ48","v":0},{"$f":"'K90 - time schedule'!JR48","v":0},{"$f":"'K90 - time schedule'!JS48","v":0},{"$f":"'K90 - time schedule'!JT48","v":0},{"$f":"'K90 - time schedule'!JU48","v":0},{"$f":"'K90 - time schedule'!JV48","v":0},{"$f":"'K90 - time schedule'!JW48","v":0},{"$f":"'K90 - time schedule'!JX48","v":0},{"$f":"'K90 - time schedule'!JY48","v":0},{"$f":"'K90 - time schedule'!JZ48","v":0},{"$f":"'K90 - time schedule'!KA48","v":0},{"$f":"'K90 - time schedule'!KB48","v":0},{"$f":"'K90 - time schedule'!KC48","v":0},{"$f":"'K90 - time schedule'!KD48","v":0},{"$f":"'K90 - time schedule'!KE48","v":0},{"$f":"'K90 - time schedule'!KF48","v":0},{"$f":"'K90 - time schedule'!KG48","v":0},{"$f":"'K90 - time schedule'!KH48","v":0},{"$f":"'K90 - time schedule'!KI48","v":0},{"$f":"'K90 - time schedule'!KJ48","v":0},{"$f":"'K90 - time schedule'!KK48","v":0},{"$f":"'K90 - time schedule'!KL48","v":0},{"$f":"'K90 - time schedule'!KM48","v":0},{"$f":"'K90 - time schedule'!KN48","v":0},{"$f":"'K90 - time schedule'!KO48","v":0},{"$f":"'K90 - time schedule'!KP48","v":0},{"$f":"'K90 - time schedule'!KQ48","v":0},{"$f":"'K90 - time schedule'!KR48","v":0},{"$f":"'K90 - time schedule'!KS48","v":0},{"$f":"'K90 - time schedule'!KT48","v":0}]
["Boiler room K90 - completion of installation works","K90",{"$f":"'K90 - time schedule'!G49","v":0},{"$f":"'K90 - time schedule'!H49","v":0},{"$f":"'K90 - time schedule'!I49","v":0},{"$f":"'K90 - time schedule'!J49","v":0},{"$f":"'K90 - time schedule'!K49","v":0},{"$f":"'K90 - time schedule'!L49","v":0},{"$f":"'K90 - time schedule'!M49","v":0},{"$f":"'K90 - time schedule'!N49","v":0},{"$f":"'K90 - time schedule'!O49","v":0},{"$f":"'K90 - time schedule'!P49","v":0},{"$f":"'K90 - time schedule'!Q49","v":0},{"$f":"'K90 - time schedule'!R49","v":0},{"$f":"'K90 - time schedule'!S49","v":0},{"$f":"'K90 - time schedule'!T49","v":0},{"$f":"'K90 - time schedule'!U49","v":0},{"$f":"'K90 - time schedule'!V49","v":0},{"$f":"'K90 - time schedule'!W49","v":0},{"$f":"'K90 - time schedule'!X49","v":0},{"$f":"'K90 - time schedule'!Y49","v":0},{"$f":"'K90 - time schedule'!Z49","v":0},{"$f":"'K90 - time schedule'!AA49","v":0},{"$f":"'K90 - time schedule'!AB49","v":0},{"$f":"'K90 - time schedule'!AC49","v":0},{"$f":"'K90 - time schedule'!AD49","v":0},{"$f":"'K90 - time schedule'!AE49","v":0},{"$f":"'K90 - time schedule'!AF49","v":0},{"$f":"'K90 - time schedule'!AG49","v":0},{"$f":"'K90 - time schedule'!AH49","v":0},{"$f":"'K90 - time schedule'!AI49","v":0},{"$f":"'K90 - time schedule'!AJ49","v":0},{"$f":"'K90 - time schedule'!AK49","v":0},{"$f":"'K90 - time schedule'!AL49","v":0},{"$f":"'K90 - time schedule'!AM49","v":0},{"$f":"'K90 - time schedule'!AN49","v":0},{"$f":"'K90 - time schedule'!AO49","v":0},{"$f":"'K90 - time schedule'!AP49","v":0},{"$f":"'K90 - time schedule'!AQ49","v":0},{"$f":"'K90 - time schedule'!AR49","v":0},{"$f":"'K90 - time schedule'!AS49","v":0},{"$f":"'K90 - time schedule'!AT49","v":0},{"$f":"'K90 - time schedule'!AU49","v":0},{"$f":"'K90 - time schedule'!AV49","v":0},{"$f":"'K90 - time schedule'!AW49","v":0},{"$f":"'K90 - time schedule'!AX49","v":0},{"$f":"'K90 - time schedule'!AY49","v":0},{"$f":"'K90 - time schedule'!AZ49","v":0},{"$f":"'K90 - time schedule'!BA49","v":0},{"$f":"'K90 - time schedule'!BB49","v":0},{"$f":"'K90 - time schedule'!BC49","v":0},{"$f":"'K90 - time schedule'!BD49","v":0},{"$f":"'K90 - time schedule'!BE49","v":0},{"$f":"'K90 - time schedule'!BF49","v":0},{"$f":"'K90 - time schedule'!BG49","v":0},{"$f":"'K90 - time schedule'!BH49","v":0},{"$f":"'K90 - time schedule'!BI49","v":0},{"$f":"'K90 - time schedule'!BJ49","v":0},{"$f":"'K90 - time schedule'!BK49","v":0},{"$f":"'K90 - time schedule'!BL49","v":0},{"$f":"'K90 - time schedule'!BM49","v":0},{"$f":"'K90 - time schedule'!BN49","v":0},{"$f":"'K90 - time schedule'!BO49","v":0},{"$f":"'K90 - time schedule'!BP49","v":0},{"$f":"'K90 - time schedule'!BQ49","v":0},{"$f":"'K90 - time schedule'!BR49","v":0},{"$f":"'K90 - time schedule'!BS49","v":0},{"$f":"'K90 - time schedule'!BT49","v":0},{"$f":"'K90 - time schedule'!BU49","v":0},{"$f":"'K90 - time schedule'!BV49","v":0},{"$f":"'K90 - time schedule'!BW49","v":0},{"$f":"'K90 - time schedule'!BX49","v":0},{"$f":"'K90 - time schedule'!BY49","v":0},{"$f":"'K90 - time schedule'!BZ49","v":0},{"$f":"'K90 - time schedule'!CA49","v":0},{"$f":"'K90 - time schedule'!CB49","v":0},{"$f":"'K90 - time schedule'!CC49","v":0},{"$f":"'K90 - time schedule'!CD49","v":0},{"$f":"'K90 - time schedule'!CE49","v":0},{"$f":"'K90 - time schedule'!CF49","v":0},{"$f":"'K90 - time schedule'!CG49","v":0},{"$f":"'K90 - time schedule'!CH49","v":0},{"$f":"'K90 - time schedule'!CI49","v":0},{"$f":"'K90 - time schedule'!CJ49","v":0},{"$f":"'K90 - time schedule'!CK49","v":0},{"$f":"'K90 - time schedule'!CL49","v":0},{"$f":"'K90 - time schedule'!CM49","v":0},{"$f":"'K90 - time schedule'!CN49","v":0},{"$f":"'K90 - time schedule'!CO49","v":0},{"$f":"'K90 - time schedule'!CP49","v":0},{"$f":"'K90 - time schedule'!CQ49","v":0},{"$f":"'K90 - time schedule'!CR49","v":0},{"$f":"'K90 - time schedule'!CS49","v":0},{"$f":"'K90 - time schedule'!CT49","v":0},{"$f":"'K90 - time schedule'!CU49","v":0},{"$f":"'K90 - time schedule'!CV49","v":0},{"$f":"'K90 - time schedule'!CW49","v":0},{"$f":"'K90 - time schedule'!CX49","v":0},{"$f":"'K90 - time schedule'!CY49","v":0},{"$f":"'K90 - time schedule'!CZ49","v":0},{"$f":"'K90 - time schedule'!DA49","v":0},{"$f":"'K90 - time schedule'!DB49","v":0},{"$f":"'K90 - time schedule'!DC49","v":0},{"$f":"'K90 - time schedule'!DD49","v":0},{"$f":"'K90 - time schedule'!DE49","v":0},{"$f":"'K90 - time schedule'!DF49","v":0},{"$f":"'K90 - time schedule'!DG49","v":0},{"$f":"'K90 - time schedule'!DH49","v":0},{"$f":"'K90 - time schedule'!DI49","v":0},{"$f":"'K90 - time schedule'!DJ49","v":0},{"$f":"'K90 - time schedule'!DK49","v":0},{"$f":"'K90 - time schedule'!DL49","v":0},{"$f":"'K90 - time schedule'!DM49","v":0},{"$f":"'K90 - time schedule'!DN49","v":0},{"$f":"'K90 - time schedule'!DO49","v":0},{"$f":"'K90 - time schedule'!DP49","v":0},{"$f":"'K90 - time schedule'!DQ49","v":0},{"$f":"'K90 - time schedule'!DR49","v":0},{"$f":"'K90 - time schedule'!DS49","v":0},{"$f":"'K90 - time schedule'!DT49","v":0},{"$f":"'K90 - time schedule'!DU49","v":0},{"$f":"'K90 - time schedule'!DV49","v":0},{"$f":"'K90 - time schedule'!DW49","v":0},{"$f":"'K90 - time schedule'!DX49","v":0},{"$f":"'K90 - time schedule'!DY49","v":0},{"$f":"'K90 - time schedule'!DZ49","v":0},{"$f":"'K90 - time schedule'!EA49","v":0},{"$f":"'K90 - time schedule'!EB49","v":0},{"$f":"'K90 - time schedule'!EC49","v":0},{"$f":"'K90 - time schedule'!ED49","v":0},{"$f":"'K90 - time schedule'!EE49","v":0},{"$f":"'K90 - time schedule'!EF49","v":0},{"$f":"'K90 - time schedule'!EG49","v":0},{"$f":"'K90 - time schedule'!EH49","v":0},{"$f":"'K90 - time schedule'!EI49","v":0},{"$f":"'K90 - time schedule'!EJ49","v":0},{"$f":"'K90 - time schedule'!EK49","v":0},{"$f":"'K90 - time schedule'!EL49","v":0},{"$f":"'K90 - time schedule'!EM49","v":0},{"$f":"'K90 - time schedule'!EN49","v":0},{"$f":"'K90 - time schedule'!EO49","v":0},{"$f":"'K90 - time schedule'!EP49","v":0},{"$f":"'K90 - time schedule'!EQ49","v":0},{"$f":"'K90 - time schedule'!ER49","v":0},{"$f":"'K90 - time schedule'!ES49","v":0},{"$f":"'K90 - time schedule'!ET49","v":0},{"$f":"'K90 - time schedule'!EU49","v":0},{"$f":"'K90 - time schedule'!EV49","v":0},{"$f":"'K90 - time schedule'!EW49","v":0},{"$f":"'K90 - time schedule'!EX49","v":0},{"$f":"'K90 - time schedule'!EY49","v":0},{"$f":"'K90 - time schedule'!EZ49","v":0},{"$f":"'K90 - time schedule'!FA49","v":0},{"$f":"'K90 - time schedule'!FB49","v":0},{"$f":"'K90 - time schedule'!FC49","v":0},{"$f":"'K90 - time schedule'!FD49","v":0},{"$f":"'K90 - time schedule'!FE49","v":0},{"$f":"'K90 - time schedule'!FF49","v":0},{"$f":"'K90 - time schedule'!FG49","v":0},{"$f":"'K90 - time schedule'!FH49","v":0},{"$f":"'K90 - time schedule'!FI49","v":0},{"$f":"'K90 - time schedule'!FJ49","v":0},{"$f":"'K90 - time schedule'!FK49","v":0},{"$f":"'K90 - time schedule'!FL49","v":0},{"$f":"'K90 - time schedule'!FM49","v":0},{"$f":"'K90 - time schedule'!FN49","v":0},{"$f":"'K90 - time schedule'!FO49","v":0},{"$f":"'K90 - time schedule'!FP49","v":0},{"$f":"'K90 - time schedule'!FQ49","v":0},{"$f":"'K90 - time schedule'!FR49","v":0},{"$f":"'K90 - time schedule'!FS49","v":0},{"$f":"'K90 - time schedule'!FT49","v":0},{"$f":"'K90 - time schedule'!FU49","v":0},{"$f":"'K90 - time schedule'!FV49","v":0},{"$f":"'K90 - time schedule'!FW49","v":0},{"$f":"'K90 - time schedule'!FX49","v":0},{"$f":"'K90 - time schedule'!FY49","v":0},{"$f":"'K90 - time schedule'!FZ49","v":0},{"$f":"'K90 - time schedule'!GA49","v":0},{"$f":"'K90 - time schedule'!GB49","v":0},{"$f":"'K90 - time schedule'!GC49","v":0},{"$f":"'K90 - time schedule'!GD49","v":0},{"$f":"'K90 - time schedule'!GE49","v":0},{"$f":"'K90 - time schedule'!GF49","v":0},{"$f":"'K90 - time schedule'!GG49","v":0},{"$f":"'K90 - time schedule'!GH49","v":0},{"$f":"'K90 - time schedule'!GI49","v":0},{"$f":"'K90 - time schedule'!GJ49","v":0},{"$f":"'K90 - time schedule'!GK49","v":0},{"$f":"'K90 - time schedule'!GL49","v":0},{"$f":"'K90 - time schedule'!GM49","v":0},{"$f":"'K90 - time schedule'!GN49","v":0},{"$f":"'K90 - time schedule'!GO49","v":0},{"$f":"'K90 - time schedule'!GP49","v":0},{"$f":"'K90 - time schedule'!GQ49","v":0},{"$f":"'K90 - time schedule'!GR49","v":0},{"$f":"'K90 - time schedule'!GS49","v":0},{"$f":"'K90 - time schedule'!GT49","v":0},{"$f":"'K90 - time schedule'!GU49","v":0},{"$f":"'K90 - time schedule'!GV49","v":0},{"$f":"'K90 - time schedule'!GW49","v":0},{"$f":"'K90 - time schedule'!GX49","v":0},{"$f":"'K90 - time schedule'!GY49","v":0},{"$f":"'K90 - time schedule'!GZ49","v":0},{"$f":"'K90 - time schedule'!HA49","v":0},{"$f":"'K90 - time schedule'!HB49","v":0},{"$f":"'K90 - time schedule'!HC49","v":0},{"$f":"'K90 - time schedule'!HD49","v":0},{"$f":"'K90 - time schedule'!HE49","v":0},{"$f":"'K90 - time schedule'!HF49","v":0},{"$f":"'K90 - time schedule'!HG49","v":0},{"$f":"'K90 - time schedule'!HH49","v":0},{"$f":"'K90 - time schedule'!HI49","v":0},{"$f":"'K90 - time schedule'!HJ49","v":0},{"$f":"'K90 - time schedule'!HK49","v":0},{"$f":"'K90 - time schedule'!HL49","v":0},{"$f":"'K90 - time schedule'!HM49","v":0},{"$f":"'K90 - time schedule'!HN49","v":0},{"$f":"'K90 - time schedule'!HO49","v":0},{"$f":"'K90 - time schedule'!HP49","v":0},{"$f":"'K90 - time schedule'!HQ49","v":0},{"$f":"'K90 - time schedule'!HR49","v":0},{"$f":"'K90 - time schedule'!HS49","v":0},{"$f":"'K90 - time schedule'!HT49","v":0},{"$f":"'K90 - time schedule'!HU49","v":0},{"$f":"'K90 - time schedule'!HV49","v":0},{"$f":"'K90 - time schedule'!HW49","v":0},{"$f":"'K90 - time schedule'!HX49","v":0},{"$f":"'K90 - time schedule'!HY49","v":0},{"$f":"'K90 - time schedule'!HZ49","v":0},{"$f":"'K90 - time schedule'!IA49","v":0},{"$f":"'K90 - time schedule'!IB49","v":0},{"$f":"'K90 - time schedule'!IC49","v":0},{"$f":"'K90 - time schedule'!ID49","v":0},{"$f":"'K90 - time schedule'!IE49","v":0},{"$f":"'K90 - time schedule'!IF49","v":0},{"$f":"'K90 - time schedule'!IG49","v":0},{"$f":"'K90 - time schedule'!IH49","v":0},{"$f":"'K90 - time schedule'!II49","v":0},{"$f":"'K90 - time schedule'!IJ49","v":0},{"$f":"'K90 - time schedule'!IK49","v":0},{"$f":"'K90 - time schedule'!IL49","v":0},{"$f":"'K90 - time schedule'!IM49","v":0},{"$f":"'K90 - time schedule'!IN49","v":0},{"$f":"'K90 - time schedule'!IO49","v":0},{"$f":"'K90 - time schedule'!IP49","v":0},{"$f":"'K90 - time schedule'!IQ49","v":0},{"$f":"'K90 - time schedule'!IR49","v":0},{"$f":"'K90 - time schedule'!IS49","v":0},{"$f":"'K90 - time schedule'!IT49","v":0},{"$f":"'K90 - time schedule'!IU49","v":0},{"$f":"'K90 - time schedule'!IV49","v":0},{"$f":"'K90 - time schedule'!IW49","v":0},{"$f":"'K90 - time schedule'!IX49","v":0},{"$f":"'K90 - time schedule'!IY49","v":0},{"$f":"'K90 - time schedule'!IZ49","v":0},{"$f":"'K90 - time schedule'!JA49","v":0},{"$f":"'K90 - time schedule'!JB49","v":0},{"$f":"'K90 - time schedule'!JC49","v":0},{"$f":"'K90 - time schedule'!JD49","v":0},{"$f":"'K90 - time schedule'!JE49","v":0},{"$f":"'K90 - time schedule'!JF49","v":0},{"$f":"'K90 - time schedule'!JG49","v":0},{"$f":"'K90 - time schedule'!JH49","v":0},{"$f":"'K90 - time schedule'!JI49","v":0},{"$f":"'K90 - time schedule'!JJ49","v":0},{"$f":"'K90 - time schedule'!JK49","v":0},{"$f":"'K90 - time schedule'!JL49","v":0},{"$f":"'K90 - time schedule'!JM49","v":0},{"$f":"'K90 - time schedule'!JN49","v":0},{"$f":"'K90 - time schedule'!JO49","v":0},{"$f":"'K90 - time schedule'!JP49","v":0},{"$f":"'K90 - time schedule'!JQ49","v":0},{"$f":"'K90 - time schedule'!JR49","v":0},{"$f":"'K90 - time schedule'!JS49","v":0},{"$f":"'K90 - time schedule'!JT49","v":0},{"$f":"'K90 - time schedule'!JU49","v":0},{"$f":"'K90 - time schedule'!JV49","v":0},{"$f":"'K90 - time schedule'!JW49","v":0},{"$f":"'K90 - time schedule'!JX49","v":0},{"$f":"'K90 - time schedule'!JY49","v":0},{"$f":"'K90 - time schedule'!JZ49","v":0},{"$f":"'K90 - time schedule'!KA49","v":0},{"$f":"'K90 - time schedule'!KB49","v":0},{"$f":"'K90 - time schedule'!KC49","v":0},{"$f":"'K90 - time schedule'!KD49","v":0},{"$f":"'K90 - time schedule'!KE49","v":0},{"$f":"'K90 - time schedule'!KF49","v":0},{"$f":"'K90 - time schedule'!KG49","v":0},{"$f":"'K90 - time schedule'!KH49","v":0},{"$f":"'K90 - time schedule'!KI49","v":0},{"$f":"'K90 - time schedule'!KJ49","v":0},{"$f":"'K90 - time schedule'!KK49","v":0},{"$f":"'K90 - time schedule'!KL49","v":0},{"$f":"'K90 - time schedule'!KM49","v":0},{"$f":"'K90 - time schedule'!KN49","v":0},{"$f":"'K90 - time schedule'!KO49","v":0},{"$f":"'K90 - time schedule'!KP49","v":0},{"$f":"'K90 - time schedule'!KQ49","v":0},{"$f":"'K90 - time schedule'!KR49","v":0},{"$f":"'K90 - time schedule'!KS49","v":0},{"$f":"'K90 - time schedule'!KT49","v":0}]
["Boiler room K90 - operating staff training","K90",{"$f":"'K90 - time schedule'!G50","v":0},{"$f":"'K90 - time schedule'!H50","v":0},{"$f":"'K90 - time schedule'!I50","v":0},{"$f":"'K90 - time schedule'!J50","v":0},{"$f":"'K90 - time schedule'!K50","v":0},{"$f":"'K90 - time schedule'!L50","v":0},{"$f":"'K90 - time schedule'!M50","v":0},{"$f":"'K90 - time schedule'!N50","v":0},{"$f":"'K90 - time schedule'!O50","v":0},{"$f":"'K90 - time schedule'!P50","v":0},{"$f":"'K90 - time schedule'!Q50","v":0},{"$f":"'K90 - time schedule'!R50","v":0},{"$f":"'K90 - time schedule'!S50","v":0},{"$f":"'K90 - time schedule'!T50","v":0},{"$f":"'K90 - time schedule'!U50","v":0},{"$f":"'K90 - time schedule'!V50","v":0},{"$f":"'K90 - time schedule'!W50","v":0},{"$f":"'K90 - time schedule'!X50","v":0},{"$f":"'K90 - time schedule'!Y50","v":0},{"$f":"'K90 - time schedule'!Z50","v":0},{"$f":"'K90 - time schedule'!AA50","v":0},{"$f":"'K90 - time schedule'!AB50","v":0},{"$f":"'K90 - time schedule'!AC50","v":0},{"$f":"'K90 - time schedule'!AD50","v":0},{"$f":"'K90 - time schedule'!AE50","v":0},{"$f":"'K90 - time schedule'!AF50","v":0},{"$f":"'K90 - time schedule'!AG50","v":0},{"$f":"'K90 - time schedule'!AH50","v":0},{"$f":"'K90 - time schedule'!AI50","v":0},{"$f":"'K90 - time schedule'!AJ50","v":0},{"$f":"'K90 - time schedule'!AK50","v":0},{"$f":"'K90 - time schedule'!AL50","v":0},{"$f":"'K90 - time schedule'!AM50","v":0},{"$f":"'K90 - time schedule'!AN50","v":0},{"$f":"'K90 - time schedule'!AO50","v":0},{"$f":"'K90 - time schedule'!AP50","v":0},{"$f":"'K90 - time schedule'!AQ50","v":0},{"$f":"'K90 - time schedule'!AR50","v":0},{"$f":"'K90 - time schedule'!AS50","v":0},{"$f":"'K90 - time schedule'!AT50","v":0},{"$f":"'K90 - time schedule'!AU50","v":0},{"$f":"'K90 - time schedule'!AV50","v":0},{"$f":"'K90 - time schedule'!AW50","v":0},{"$f":"'K90 - time schedule'!AX50","v":0},{"$f":"'K90 - time schedule'!AY50","v":0},{"$f":"'K90 - time schedule'!AZ50","v":0},{"$f":"'K90 - time schedule'!BA50","v":0},{"$f":"'K90 - time schedule'!BB50","v":0},{"$f":"'K90 - time schedule'!BC50","v":0},{"$f":"'K90 - time schedule'!BD50","v":0},{"$f":"'K90 - time schedule'!BE50","v":0},{"$f":"'K90 - time schedule'!BF50","v":0},{"$f":"'K90 - time schedule'!BG50","v":0},{"$f":"'K90 - time schedule'!BH50","v":0},{"$f":"'K90 - time schedule'!BI50","v":0},{"$f":"'K90 - time schedule'!BJ50","v":0},{"$f":"'K90 - time schedule'!BK50","v":0},{"$f":"'K90 - time schedule'!BL50","v":0},{"$f":"'K90 - time schedule'!BM50","v":0},{"$f":"'K90 - time schedule'!BN50","v":0},{"$f":"'K90 - time schedule'!BO50","v":0},{"$f":"'K90 - time schedule'!BP50","v":0},{"$f":"'K90 - time schedule'!BQ50","v":0},{"$f":"'K90 - time schedule'!BR50","v":0},{"$f":"'K90 - time schedule'!BS50","v":0},{"$f":"'K90 - time schedule'!BT50","v":0},{"$f":"'K90 - time schedule'!BU50","v":0},{"$f":"'K90 - time schedule'!BV50","v":0},{"$f":"'K90 - time schedule'!BW50","v":0},{"$f":"'K90 - time schedule'!BX50","v":0},{"$f":"'K90 - time schedule'!BY50","v":0},{"$f":"'K90 - time schedule'!BZ50","v":0},{"$f":"'K90 - time schedule'!CA50","v":0},{"$f":"'K90 - time schedule'!CB50","v":0},{"$f":"'K90 - time schedule'!CC50","v":0},{"$f":"'K90 - time schedule'!CD50","v":0},{"$f":"'K90 - time schedule'!CE50","v":0},{"$f":"'K90 - time schedule'!CF50","v":0},{"$f":"'K90 - time schedule'!CG50","v":0},{"$f":"'K90 - time schedule'!CH50","v":0},{"$f":"'K90 - time schedule'!CI50","v":0},{"$f":"'K90 - time schedule'!CJ50","v":0},{"$f":"'K90 - time schedule'!CK50","v":0},{"$f":"'K90 - time schedule'!CL50","v":0},{"$f":"'K90 - time schedule'!CM50","v":0},{"$f":"'K90 - time schedule'!CN50","v":0},{"$f":"'K90 - time schedule'!CO50","v":0},{"$f":"'K90 - time schedule'!CP50","v":0},{"$f":"'K90 - time schedule'!CQ50","v":0},{"$f":"'K90 - time schedule'!CR50","v":0},{"$f":"'K90 - time schedule'!CS50","v":0},{"$f":"'K90 - time schedule'!CT50","v":0},{"$f":"'K90 - time schedule'!CU50","v":0},{"$f":"'K90 - time schedule'!CV50","v":0},{"$f":"'K90 - time schedule'!CW50","v":0},{"$f":"'K90 - time schedule'!CX50","v":0},{"$f":"'K90 - time schedule'!CY50","v":0},{"$f":"'K90 - time schedule'!CZ50","v":0},{"$f":"'K90 - time schedule'!DA50","v":0},{"$f":"'K90 - time schedule'!DB50","v":0},{"$f":"'K90 - time schedule'!DC50","v":0},{"$f":"'K90 - time schedule'!DD50","v":0},{"$f":"'K90 - time schedule'!DE50","v":0},{"$f":"'K90 - time schedule'!DF50","v":0},{"$f":"'K90 - time schedule'!DG50","v":0},{"$f":"'K90 - time schedule'!DH50","v":0},{"$f":"'K90 - time schedule'!DI50","v":0},{"$f":"'K90 - time schedule'!DJ50","v":0},{"$f":"'K90 - time schedule'!DK50","v":0},{"$f":"'K90 - time schedule'!DL50","v":0},{"$f":"'K90 - time schedule'!DM50","v":0},{"$f":"'K90 - time schedule'!DN50","v":0},{"$f":"'K90 - time schedule'!DO50","v":0},{"$f":"'K90 - time schedule'!DP50","v":0},{"$f":"'K90 - time schedule'!DQ50","v":0},{"$f":"'K90 - time schedule'!DR50","v":0},{"$f":"'K90 - time schedule'!DS50","v":0},{"$f":"'K90 - time schedule'!DT50","v":0},{"$f":"'K90 - time schedule'!DU50","v":0},{"$f":"'K90 - time schedule'!DV50","v":0},{"$f":"'K90 - time schedule'!DW50","v":0},{"$f":"'K90 - time schedule'!DX50","v":0},{"$f":"'K90 - time schedule'!DY50","v":0},{"$f":"'K90 - time schedule'!DZ50","v":0},{"$f":"'K90 - time schedule'!EA50","v":0},{"$f":"'K90 - time schedule'!EB50","v":0},{"$f":"'K90 - time schedule'!EC50","v":0},{"$f":"'K90 - time schedule'!ED50","v":0},{"$f":"'K90 - time schedule'!EE50","v":0},{"$f":"'K90 - time schedule'!EF50","v":0},{"$f":"'K90 - time schedule'!EG50","v":0},{"$f":"'K90 - time schedule'!EH50","v":0},{"$f":"'K90 - time schedule'!EI50","v":0},{"$f":"'K90 - time schedule'!EJ50","v":0},{"$f":"'K90 - time schedule'!EK50","v":0},{"$f":"'K90 - time schedule'!EL50","v":0},{"$f":"'K90 - time schedule'!EM50","v":0},{"$f":"'K90 - time schedule'!EN50","v":0},{"$f":"'K90 - time schedule'!EO50","v":0},{"$f":"'K90 - time schedule'!EP50","v":0},{"$f":"'K90 - time schedule'!EQ50","v":0},{"$f":"'K90 - time schedule'!ER50","v":0},{"$f":"'K90 - time schedule'!ES50","v":0},{"$f":"'K90 - time schedule'!ET50","v":0},{"$f":"'K90 - time schedule'!EU50","v":0},{"$f":"'K90 - time schedule'!EV50","v":0},{"$f":"'K90 - time schedule'!EW50","v":0},{"$f":"'K90 - time schedule'!EX50","v":0},{"$f":"'K90 - time schedule'!EY50","v":0},{"$f":"'K90 - time schedule'!EZ50","v":0},{"$f":"'K90 - time schedule'!FA50","v":0},{"$f":"'K90 - time schedule'!FB50","v":0},{"$f":"'K90 - time schedule'!FC50","v":0},{"$f":"'K90 - time schedule'!FD50","v":0},{"$f":"'K90 - time schedule'!FE50","v":0},{"$f":"'K90 - time schedule'!FF50","v":0},{"$f":"'K90 - time schedule'!FG50","v":0},{"$f":"'K90 - time schedule'!FH50","v":0},{"$f":"'K90 - time schedule'!FI50","v":0},{"$f":"'K90 - time schedule'!FJ50","v":0},{"$f":"'K90 - time schedule'!FK50","v":0},{"$f":"'K90 - time schedule'!FL50","v":0},{"$f":"'K90 - time schedule'!FM50","v":0},{"$f":"'K90 - time schedule'!FN50","v":0},{"$f":"'K90 - time schedule'!FO50","v":0},{"$f":"'K90 - time schedule'!FP50","v":0},{"$f":"'K90 - time schedule'!FQ50","v":0},{"$f":"'K90 - time schedule'!FR50","v":0},{"$f":"'K90 - time schedule'!FS50","v":0},{"$f":"'K90 - time schedule'!FT50","v":0},{"$f":"'K90 - time schedule'!FU50","v":0},{"$f":"'K90 - time schedule'!FV50","v":0},{"$f":"'K90 - time schedule'!FW50","v":0},{"$f":"'K90 - time schedule'!FX50","v":0},{"$f":"'K90 - time schedule'!FY50","v":0},{"$f":"'K90 - time schedule'!FZ50","v":0},{"$f":"'K90 - time schedule'!GA50","v":0},{"$f":"'K90 - time schedule'!GB50","v":0},{"$f":"'K90 - time schedule'!GC50","v":0},{"$f":"'K90 - time schedule'!GD50","v":0},{"$f":"'K90 - time schedule'!GE50","v":0},{"$f":"'K90 - time schedule'!GF50","v":0},{"$f":"'K90 - time schedule'!GG50","v":0},{"$f":"'K90 - time schedule'!GH50","v":0},{"$f":"'K90 - time schedule'!GI50","v":0},{"$f":"'K90 - time schedule'!GJ50","v":0},{"$f":"'K90 - time schedule'!GK50","v":0},{"$f":"'K90 - time schedule'!GL50","v":0},{"$f":"'K90 - time schedule'!GM50","v":0},{"$f":"'K90 - time schedule'!GN50","v":0},{"$f":"'K90 - time schedule'!GO50","v":0},{"$f":"'K90 - time schedule'!GP50","v":0},{"$f":"'K90 - time schedule'!GQ50","v":0},{"$f":"'K90 - time schedule'!GR50","v":0},{"$f":"'K90 - time schedule'!GS50","v":0},{"$f":"'K90 - time schedule'!GT50","v":0},{"$f":"'K90 - time schedule'!GU50","v":0},{"$f":"'K90 - time schedule'!GV50","v":0},{"$f":"'K90 - time schedule'!GW50","v":0},{"$f":"'K90 - time schedule'!GX50","v":0},{"$f":"'K90 - time schedule'!GY50","v":0},{"$f":"'K90 - time schedule'!GZ50","v":0},{"$f":"'K90 - time schedule'!HA50","v":0},{"$f":"'K90 - time schedule'!HB50","v":0},{"$f":"'K90 - time schedule'!HC50","v":0},{"$f":"'K90 - time schedule'!HD50","v":0},{"$f":"'K90 - time schedule'!HE50","v":0},{"$f":"'K90 - time schedule'!HF50","v":0},{"$f":"'K90 - time schedule'!HG50","v":0},{"$f":"'K90 - time schedule'!HH50","v":0},{"$f":"'K90 - time schedule'!HI50","v":0},{"$f":"'K90 - time schedule'!HJ50","v":0},{"$f":"'K90 - time schedule'!HK50","v":0},{"$f":"'K90 - time schedule'!HL50","v":0},{"$f":"'K90 - time schedule'!HM50","v":0},{"$f":"'K90 - time schedule'!HN50","v":0},{"$f":"'K90 - time schedule'!HO50","v":0},{"$f":"'K90 - time schedule'!HP50","v":0},{"$f":"'K90 - time schedule'!HQ50","v":0},{"$f":"'K90 - time schedule'!HR50","v":0},{"$f":"'K90 - time schedule'!HS50","v":0},{"$f":"'K90 - time schedule'!HT50","v":0},{"$f":"'K90 - time schedule'!HU50","v":0},{"$f":"'K90 - time schedule'!HV50","v":0},{"$f":"'K90 - time schedule'!HW50","v":0},{"$f":"'K90 - time schedule'!HX50","v":0},{"$f":"'K90 - time schedule'!HY50","v":0},{"$f":"'K90 - time schedule'!HZ50","v":0},{"$f":"'K90 - time schedule'!IA50","v":0},{"$f":"'K90 - time schedule'!IB50","v":0},{"$f":"'K90 - time schedule'!IC50","v":0},{"$f":"'K90 - time schedule'!ID50","v":0},{"$f":"'K90 - time schedule'!IE50","v":0},{"$f":"'K90 - time schedule'!IF50","v":0},{"$f":"'K90 - time schedule'!IG50","v":0},{"$f":"'K90 - time schedule'!IH50","v":0},{"$f":"'K90 - time schedule'!II50","v":0},{"$f":"'K90 - time schedule'!IJ50","v":0},{"$f":"'K90 - time schedule'!IK50","v":0},{"$f":"'K90 - time schedule'!IL50","v":0},{"$f":"'K90 - time schedule'!IM50","v":0},{"$f":"'K90 - time schedule'!IN50","v":0},{"$f":"'K90 - time schedule'!IO50","v":0},{"$f":"'K90 - time schedule'!IP50","v":0},{"$f":"'K90 - time schedule'!IQ50","v":0},{"$f":"'K90 - time schedule'!IR50","v":0},{"$f":"'K90 - time schedule'!IS50","v":0},{"$f":"'K90 - time schedule'!IT50","v":0},{"$f":"'K90 - time schedule'!IU50","v":0},{"$f":"'K90 - time schedule'!IV50","v":0},{"$f":"'K90 - time schedule'!IW50","v":0},{"$f":"'K90 - time schedule'!IX50","v":0},{"$f":"'K90 - time schedule'!IY50","v":0},{"$f":"'K90 - time schedule'!IZ50","v":0},{"$f":"'K90 - time schedule'!JA50","v":0},{"$f":"'K90 - time schedule'!JB50","v":0},{"$f":"'K90 - time schedule'!JC50","v":0},{"$f":"'K90 - time schedule'!JD50","v":0},{"$f":"'K90 - time schedule'!JE50","v":0},{"$f":"'K90 - time schedule'!JF50","v":0},{"$f":"'K90 - time schedule'!JG50","v":0},{"$f":"'K90 - time schedule'!JH50","v":0},{"$f":"'K90 - time schedule'!JI50","v":0},{"$f":"'K90 - time schedule'!JJ50","v":0},{"$f":"'K90 - time schedule'!JK50","v":0},{"$f":"'K90 - time schedule'!JL50","v":0},{"$f":"'K90 - time schedule'!JM50","v":0},{"$f":"'K90 - time schedule'!JN50","v":0},{"$f":"'K90 - time schedule'!JO50","v":0},{"$f":"'K90 - time schedule'!JP50","v":0},{"$f":"'K90 - time schedule'!JQ50","v":0},{"$f":"'K90 - time schedule'!JR50","v":0},{"$f":"'K90 - time schedule'!JS50","v":0},{"$f":"'K90 - time schedule'!JT50","v":0},{"$f":"'K90 - time schedule'!JU50","v":0},{"$f":"'K90 - time schedule'!JV50","v":0},{"$f":"'K90 - time schedule'!JW50","v":0},{"$f":"'K90 - time schedule'!JX50","v":0},{"$f":"'K90 - time schedule'!JY50","v":0},{"$f":"'K90 - time schedule'!JZ50","v":0},{"$f":"'K90 - time schedule'!KA50","v":0},{"$f":"'K90 - time schedule'!KB50","v":0},{"$f":"'K90 - time schedule'!KC50","v":0},{"$f":"'K90 - time schedule'!KD50","v":0},{"$f":"'K90 - time schedule'!KE50","v":0},{"$f":"'K90 - time schedule'!KF50","v":0},{"$f":"'K90 - time schedule'!KG50","v":0},{"$f":"'K90 - time schedule'!KH50","v":0},{"$f":"'K90 - time schedule'!KI50","v":0},{"$f":"'K90 - time schedule'!KJ50","v":0},{"$f":"'K90 - time schedule'!KK50","v":0},{"$f":"'K90 - time schedule'!KL50","v":0},{"$f":"'K90 - time schedule'!KM50","v":0},{"$f":"'K90 - time schedule'!KN50","v":0},{"$f":"'K90 - time schedule'!KO50","v":0},{"$f":"'K90 - time schedule'!KP50","v":0},{"$f":"'K90 - time schedule'!KQ50","v":0},{"$f":"'K90 - time schedule'!KR50","v":0},{"$f":"'K90 - time schedule'!KS50","v":0},{"$f":"'K90 - time schedule'!KT50","v":0}]
["Boiler room K90 - preparation for comprehensive testing","K90",{"$f":"'K90 - time schedule'!G52","v":0},{"$f":"'K90 - time schedule'!H52","v":0},{"$f":"'K90 - time schedule'!I52","v":0},{"$f":"'K90 - time schedule'!J52","v":0},{"$f":"'K90 - time schedule'!K52","v":0},{"$f":"'K90 - time schedule'!L52","v":0},{"$f":"'K90 - time schedule'!M52","v":0},{"$f":"'K90 - time schedule'!N52","v":0},{"$f":"'K90 - time schedule'!O52","v":0},{"$f":"'K90 - time schedule'!P52","v":0},{"$f":"'K90 - time schedule'!Q52","v":0},{"$f":"'K90 - time schedule'!R52","v":0},{"$f":"'K90 - time schedule'!S52","v":0},{"$f":"'K90 - time schedule'!T52","v":0},{"$f":"'K90 - time schedule'!U52","v":0},{"$f":"'K90 - time schedule'!V52","v":0},{"$f":"'K90 - time schedule'!W52","v":0},{"$f":"'K90 - time schedule'!X52","v":0},{"$f":"'K90 - time schedule'!Y52","v":0},{"$f":"'K90 - time schedule'!Z52","v":0},{"$f":"'K90 - time schedule'!AA52","v":0},{"$f":"'K90 - time schedule'!AB52","v":0},{"$f":"'K90 - time schedule'!AC52","v":0},{"$f":"'K90 - time schedule'!AD52","v":0},{"$f":"'K90 - time schedule'!AE52","v":0},{"$f":"'K90 - time schedule'!AF52","v":0},{"$f":"'K90 - time schedule'!AG52","v":0},{"$f":"'K90 - time schedule'!AH52","v":0},{"$f":"'K90 - time schedule'!AI52","v":0},{"$f":"'K90 - time schedule'!AJ52","v":0},{"$f":"'K90 - time schedule'!AK52","v":0},{"$f":"'K90 - time schedule'!AL52","v":0},{"$f":"'K90 - time schedule'!AM52","v":0},{"$f":"'K90 - time schedule'!AN52","v":0},{"$f":"'K90 - time schedule'!AO52","v":0},{"$f":"'K90 - time schedule'!AP52","v":0},{"$f":"'K90 - time schedule'!AQ52","v":0},{"$f":"'K90 - time schedule'!AR52","v":0},{"$f":"'K90 - time schedule'!AS52","v":0},{"$f":"'K90 - time schedule'!AT52","v":0},{"$f":"'K90 - time schedule'!AU52","v":0},{"$f":"'K90 - time schedule'!AV52","v":0},{"$f":"'K90 - time schedule'!AW52","v":0},{"$f":"'K90 - time schedule'!AX52","v":0},{"$f":"'K90 - time schedule'!AY52","v":0},{"$f":"'K90 - time schedule'!AZ52","v":0},{"$f":"'K90 - time schedule'!BA52","v":0},{"$f":"'K90 - time schedule'!BB52","v":0},{"$f":"'K90 - time schedule'!BC52","v":0},{"$f":"'K90 - time schedule'!BD52","v":0},{"$f":"'K90 - time schedule'!BE52","v":0},{"$f":"'K90 - time schedule'!BF52","v":0},{"$f":"'K90 - time schedule'!BG52","v":0},{"$f":"'K90 - time schedule'!BH52","v":0},{"$f":"'K90 - time schedule'!BI52","v":0},{"$f":"'K90 - time schedule'!BJ52","v":0},{"$f":"'K90 - time schedule'!BK52","v":0},{"$f":"'K90 - time schedule'!BL52","v":0},{"$f":"'K90 - time schedule'!BM52","v":0},{"$f":"'K90 - time schedule'!BN52","v":0},{"$f":"'K90 - time schedule'!BO52","v":0},{"$f":"'K90 - time schedule'!BP52","v":0},{"$f":"'K90 - time schedule'!BQ52","v":0},{"$f":"'K90 - time schedule'!BR52","v":0},{"$f":"'K90 - time schedule'!BS52","v":0},{"$f":"'K90 - time schedule'!BT52","v":0},{"$f":"'K90 - time schedule'!BU52","v":0},{"$f":"'K90 - time schedule'!BV52","v":0},{"$f":"'K90 - time schedule'!BW52","v":0},{"$f":"'K90 - time schedule'!BX52","v":0},{"$f":"'K90 - time schedule'!BY52","v":0},{"$f":"'K90 - time schedule'!BZ52","v":0},{"$f":"'K90 - time schedule'!CA52","v":0},{"$f":"'K90 - time schedule'!CB52","v":0},{"$f":"'K90 - time schedule'!CC52","v":0},{"$f":"'K90 - time schedule'!CD52","v":0},{"$f":"'K90 - time schedule'!CE52","v":0},{"$f":"'K90 - time schedule'!CF52","v":0},{"$f":"'K90 - time schedule'!CG52","v":0},{"$f":"'K90 - time schedule'!CH52","v":0},{"$f":"'K90 - time schedule'!CI52","v":0},{"$f":"'K90 - time schedule'!CJ52","v":0},{"$f":"'K90 - time schedule'!CK52","v":0},{"$f":"'K90 - time schedule'!CL52","v":0},{"$f":"'K90 - time schedule'!CM52","v":0},{"$f":"'K90 - time schedule'!CN52","v":0},{"$f":"'K90 - time schedule'!CO52","v":0},{"$f":"'K90 - time schedule'!CP52","v":0},{"$f":"'K90 - time schedule'!CQ52","v":0},{"$f":"'K90 - time schedule'!CR52","v":0},{"$f":"'K90 - time schedule'!CS52","v":0},{"$f":"'K90 - time schedule'!CT52","v":0},{"$f":"'K90 - time schedule'!CU52","v":0},{"$f":"'K90 - time schedule'!CV52","v":0},{"$f":"'K90 - time schedule'!CW52","v":0},{"$f":"'K90 - time schedule'!CX52","v":0},{"$f":"'K90 - time schedule'!CY52","v":0},{"$f":"'K90 - time schedule'!CZ52","v":0},{"$f":"'K90 - time schedule'!DA52","v":0},{"$f":"'K90 - time schedule'!DB52","v":0},{"$f":"'K90 - time schedule'!DC52","v":0},{"$f":"'K90 - time schedule'!DD52","v":0},{"$f":"'K90 - time schedule'!DE52","v":0},{"$f":"'K90 - time schedule'!DF52","v":0},{"$f":"'K90 - time schedule'!DG52","v":0},{"$f":"'K90 - time schedule'!DH52","v":0},{"$f":"'K90 - time schedule'!DI52","v":0},{"$f":"'K90 - time schedule'!DJ52","v":0},{"$f":"'K90 - time schedule'!DK52","v":0},{"$f":"'K90 - time schedule'!DL52","v":0},{"$f":"'K90 - time schedule'!DM52","v":0},{"$f":"'K90 - time schedule'!DN52","v":0},{"$f":"'K90 - time schedule'!DO52","v":0},{"$f":"'K90 - time schedule'!DP52","v":0},{"$f":"'K90 - time schedule'!DQ52","v":0},{"$f":"'K90 - time schedule'!DR52","v":0},{"$f":"'K90 - time schedule'!DS52","v":0},{"$f":"'K90 - time schedule'!DT52","v":0},{"$f":"'K90 - time schedule'!DU52","v":0},{"$f":"'K90 - time schedule'!DV52","v":0},{"$f":"'K90 - time schedule'!DW52","v":0},{"$f":"'K90 - time schedule'!DX52","v":0},{"$f":"'K90 - time schedule'!DY52","v":0},{"$f":"'K90 - time schedule'!DZ52","v":0},{"$f":"'K90 - time schedule'!EA52","v":0},{"$f":"'K90 - time schedule'!EB52","v":0},{"$f":"'K90 - time schedule'!EC52","v":0},{"$f":"'K90 - time schedule'!ED52","v":0},{"$f":"'K90 - time schedule'!EE52","v":0},{"$f":"'K90 - time schedule'!EF52","v":0},{"$f":"'K90 - time schedule'!EG52","v":0},{"$f":"'K90 - time schedule'!EH52","v":0},{"$f":"'K90 - time schedule'!EI52","v":0},{"$f":"'K90 - time schedule'!EJ52","v":0},{"$f":"'K90 - time schedule'!EK52","v":0},{"$f":"'K90 - time schedule'!EL52","v":0},{"$f":"'K90 - time schedule'!EM52","v":0},{"$f":"'K90 - time schedule'!EN52","v":0},{"$f":"'K90 - time schedule'!EO52","v":0},{"$f":"'K90 - time schedule'!EP52","v":0},{"$f":"'K90 - time schedule'!EQ52","v":0},{"$f":"'K90 - time schedule'!ER52","v":0},{"$f":"'K90 - time schedule'!ES52","v":0},{"$f":"'K90 - time schedule'!ET52","v":0},{"$f":"'K90 - time schedule'!EU52","v":0},{"$f":"'K90 - time schedule'!EV52","v":0},{"$f":"'K90 - time schedule'!EW52","v":0},{"$f":"'K90 - time schedule'!EX52","v":0},{"$f":"'K90 - time schedule'!EY52","v":0},{"$f":"'K90 - time schedule'!EZ52","v":0},{"$f":"'K90 - time schedule'!FA52","v":0},{"$f":"'K90 - time schedule'!FB52","v":0},{"$f":"'K90 - time schedule'!FC52","v":0},{"$f":"'K90 - time schedule'!FD52","v":0},{"$f":"'K90 - time schedule'!FE52","v":0},{"$f":"'K90 - time schedule'!FF52","v":0},{"$f":"'K90 - time schedule'!FG52","v":0},{"$f":"'K90 - time schedule'!FH52","v":0},{"$f":"'K90 - time schedule'!FI52","v":0},{"$f":"'K90 - time schedule'!FJ52","v":0},{"$f":"'K90 - time schedule'!FK52","v":0},{"$f":"'K90 - time schedule'!FL52","v":0},{"$f":"'K90 - time schedule'!FM52","v":0},{"$f":"'K90 - time schedule'!FN52","v":0},{"$f":"'K90 - time schedule'!FO52","v":0},{"$f":"'K90 - time schedule'!FP52","v":0},{"$f":"'K90 - time schedule'!FQ52","v":0},{"$f":"'K90 - time schedule'!FR52","v":0},{"$f":"'K90 - time schedule'!FS52","v":0},{"$f":"'K90 - time schedule'!FT52","v":0},{"$f":"'K90 - time schedule'!FU52","v":0},{"$f":"'K90 - time schedule'!FV52","v":0},{"$f":"'K90 - time schedule'!FW52","v":0},{"$f":"'K90 - time schedule'!FX52","v":0},{"$f":"'K90 - time schedule'!FY52","v":0},{"$f":"'K90 - time schedule'!FZ52","v":0},{"$f":"'K90 - time schedule'!GA52","v":0},{"$f":"'K90 - time schedule'!GB52","v":0},{"$f":"'K90 - time schedule'!GC52","v":0},{"$f":"'K90 - time schedule'!GD52","v":0},{"$f":"'K90 - time schedule'!GE52","v":0},{"$f":"'K90 - time schedule'!GF52","v":0},{"$f":"'K90 - time schedule'!GG52","v":0},{"$f":"'K90 - time schedule'!GH52","v":0},{"$f":"'K90 - time schedule'!GI52","v":0},{"$f":"'K90 - time schedule'!GJ52","v":0},{"$f":"'K90 - time schedule'!GK52","v":0},{"$f":"'K90 - time schedule'!GL52","v":0},{"$f":"'K90 - time schedule'!GM52","v":0},{"$f":"'K90 - time schedule'!GN52","v":0},{"$f":"'K90 - time schedule'!GO52","v":0},{"$f":"'K90 - time schedule'!GP52","v":0},{"$f":"'K90 - time schedule'!GQ52","v":0},{"$f":"'K90 - time schedule'!GR52","v":0},{"$f":"'K90 - time schedule'!GS52","v":0},{"$f":"'K90 - time schedule'!GT52","v":0},{"$f":"'K90 - time schedule'!GU52","v":0},{"$f":"'K90 - time schedule'!GV52","v":0},{"$f":"'K90 - time schedule'!GW52","v":0},{"$f":"'K90 - time schedule'!GX52","v":0},{"$f":"'K90 - time schedule'!GY52","v":0},{"$f":"'K90 - time schedule'!GZ52","v":0},{"$f":"'K90 - time schedule'!HA52","v":0},{"$f":"'K90 - time schedule'!HB52","v":0},{"$f":"'K90 - time schedule'!HC52","v":0},{"$f":"'K90 - time schedule'!HD52","v":0},{"$f":"'K90 - time schedule'!HE52","v":0},{"$f":"'K90 - time schedule'!HF52","v":0},{"$f":"'K90 - time schedule'!HG52","v":0},{"$f":"'K90 - time schedule'!HH52","v":0},{"$f":"'K90 - time schedule'!HI52","v":0},{"$f":"'K90 - time schedule'!HJ52","v":0},{"$f":"'K90 - time schedule'!HK52","v":0},{"$f":"'K90 - time schedule'!HL52","v":0},{"$f":"'K90 - time schedule'!HM52","v":0},{"$f":"'K90 - time schedule'!HN52","v":0},{"$f":"'K90 - time schedule'!HO52","v":0},{"$f":"'K90 - time schedule'!HP52","v":0},{"$f":"'K90 - time schedule'!HQ52","v":0},{"$f":"'K90 - time schedule'!HR52","v":0},{"$f":"'K90 - time schedule'!HS52","v":0},{"$f":"'K90 - time schedule'!HT52","v":0},{"$f":"'K90 - time schedule'!HU52","v":0},{"$f":"'K90 - time schedule'!HV52","v":0},{"$f":"'K90 - time schedule'!HW52","v":0},{"$f":"'K90 - time schedule'!HX52","v":0},{"$f":"'K90 - time schedule'!HY52","v":0},{"$f":"'K90 - time schedule'!HZ52","v":0},{"$f":"'K90 - time schedule'!IA52","v":0},{"$f":"'K90 - time schedule'!IB52","v":0},{"$f":"'K90 - time schedule'!IC52","v":0},{"$f":"'K90 - time schedule'!ID52","v":0},{"$f":"'K90 - time schedule'!IE52","v":0},{"$f":"'K90 - time schedule'!IF52","v":0},{"$f":"'K90 - time schedule'!IG52","v":0},{"$f":"'K90 - time schedule'!IH52","v":0},{"$f":"'K90 - time schedule'!II52","v":0},{"$f":"'K90 - time schedule'!IJ52","v":0},{"$f":"'K90 - time schedule'!IK52","v":0},{"$f":"'K90 - time schedule'!IL52","v":0},{"$f":"'K90 - time schedule'!IM52","v":0},{"$f":"'K90 - time schedule'!IN52","v":0},{"$f":"'K90 - time schedule'!IO52","v":0},{"$f":"'K90 - time schedule'!IP52","v":0},{"$f":"'K90 - time schedule'!IQ52","v":0},{"$f":"'K90 - time schedule'!IR52","v":0},{"$f":"'K90 - time schedule'!IS52","v":0},{"$f":"'K90 - time schedule'!IT52","v":0},{"$f":"'K90 - time schedule'!IU52","v":0},{"$f":"'K90 - time schedule'!IV52","v":0},{"$f":"'K90 - time schedule'!IW52","v":0},{"$f":"'K90 - time schedule'!IX52","v":0},{"$f":"'K90 - time schedule'!IY52","v":0},{"$f":"'K90 - time schedule'!IZ52","v":0},{"$f":"'K90 - time schedule'!JA52","v":0},{"$f":"'K90 - time schedule'!JB52","v":0},{"$f":"'K90 - time schedule'!JC52","v":0},{"$f":"'K90 - time schedule'!JD52","v":0},{"$f":"'K90 - time schedule'!JE52","v":0},{"$f":"'K90 - time schedule'!JF52","v":0},{"$f":"'K90 - time schedule'!JG52","v":0},{"$f":"'K90 - time schedule'!JH52","v":0},{"$f":"'K90 - time schedule'!JI52","v":0},{"$f":"'K90 - time schedule'!JJ52","v":0},{"$f":"'K90 - time schedule'!JK52","v":0},{"$f":"'K90 - time schedule'!JL52","v":0},{"$f":"'K90 - time schedule'!JM52","v":0},{"$f":"'K90 - time schedule'!JN52","v":0},{"$f":"'K90 - time schedule'!JO52","v":0},{"$f":"'K90 - time schedule'!JP52","v":0},{"$f":"'K90 - time schedule'!JQ52","v":0},{"$f":"'K90 - time schedule'!JR52","v":0},{"$f":"'K90 - time schedule'!JS52","v":0},{"$f":"'K90 - time schedule'!JT52","v":0},{"$f":"'K90 - time schedule'!JU52","v":0},{"$f":"'K90 - time schedule'!JV52","v":0},{"$f":"'K90 - time schedule'!JW52","v":0},{"$f":"'K90 - time schedule'!JX52","v":0},{"$f":"'K90 - time schedule'!JY52","v":0},{"$f":"'K90 - time schedule'!JZ52","v":0},{"$f":"'K90 - time schedule'!KA52","v":0},{"$f":"'K90 - time schedule'!KB52","v":0},{"$f":"'K90 - time schedule'!KC52","v":0},{"$f":"'K90 - time schedule'!KD52","v":0},{"$f":"'K90 - time schedule'!KE52","v":0},{"$f":"'K90 - time schedule'!KF52","v":0},{"$f":"'K90 - time schedule'!KG52","v":0},{"$f":"'K90 - time schedule'!KH52","v":0},{"$f":"'K90 - time schedule'!KI52","v":0},{"$f":"'K90 - time schedule'!KJ52","v":0},{"$f":"'K90 - time schedule'!KK52","v":0},{"$f":"'K90 - time schedule'!KL52","v":0},{"$f":"'K90 - time schedule'!KM52","v":0},{"$f":"'K90 - time schedule'!KN52","v":0},{"$f":"'K90 - time schedule'!KO52","v":0},{"$f":"'K90 - time schedule'!KP52","v":0},{"$f":"'K90 - time schedule'!KQ52","v":0},{"$f":"'K90 - time schedule'!KR52","v":0},{"$f":"'K90 - time schedule'!KS52","v":0},{"$f":"'K90 - time schedule'!KT52","v":0}]
["Boiler room K90 - comprehensive testing","K90",{"$f":"'K90 - time schedule'!G53","v":0},{"$f":"'K90 - time schedule'!H53","v":0},{"$f":"'K90 - time schedule'!I53","v":0},{"$f":"'K90 - time schedule'!J53","v":0},{"$f":"'K90 - time schedule'!K53","v":0},{"$f":"'K90 - time schedule'!L53","v":0},{"$f":"'K90 - time schedule'!M53","v":0},{"$f":"'K90 - time schedule'!N53","v":0},{"$f":"'K90 - time schedule'!O53","v":0},{"$f":"'K90 - time schedule'!P53","v":0},{"$f":"'K90 - time schedule'!Q53","v":0},{"$f":"'K90 - time schedule'!R53","v":0},{"$f":"'K90 - time schedule'!S53","v":0},{"$f":"'K90 - time schedule'!T53","v":0},{"$f":"'K90 - time schedule'!U53","v":0},{"$f":"'K90 - time schedule'!V53","v":0},{"$f":"'K90 - time schedule'!W53","v":0},{"$f":"'K90 - time schedule'!X53","v":0},{"$f":"'K90 - time schedule'!Y53","v":0},{"$f":"'K90 - time schedule'!Z53","v":0},{"$f":"'K90 - time schedule'!AA53","v":0},{"$f":"'K90 - time schedule'!AB53","v":0},{"$f":"'K90 - time schedule'!AC53","v":0},{"$f":"'K90 - time schedule'!AD53","v":0},{"$f":"'K90 - time schedule'!AE53","v":0},{"$f":"'K90 - time schedule'!AF53","v":0},{"$f":"'K90 - time schedule'!AG53","v":0},{"$f":"'K90 - time schedule'!AH53","v":0},{"$f":"'K90 - time schedule'!AI53","v":0},{"$f":"'K90 - time schedule'!AJ53","v":0},{"$f":"'K90 - time schedule'!AK53","v":0},{"$f":"'K90 - time schedule'!AL53","v":0},{"$f":"'K90 - time schedule'!AM53","v":0},{"$f":"'K90 - time schedule'!AN53","v":0},{"$f":"'K90 - time schedule'!AO53","v":0},{"$f":"'K90 - time schedule'!AP53","v":0},{"$f":"'K90 - time schedule'!AQ53","v":0},{"$f":"'K90 - time schedule'!AR53","v":0},{"$f":"'K90 - time schedule'!AS53","v":0},{"$f":"'K90 - time schedule'!AT53","v":0},{"$f":"'K90 - time schedule'!AU53","v":0},{"$f":"'K90 - time schedule'!AV53","v":0},{"$f":"'K90 - time schedule'!AW53","v":0},{"$f":"'K90 - time schedule'!AX53","v":0},{"$f":"'K90 - time schedule'!AY53","v":0},{"$f":"'K90 - time schedule'!AZ53","v":0},{"$f":"'K90 - time schedule'!BA53","v":0},{"$f":"'K90 - time schedule'!BB53","v":0},{"$f":"'K90 - time schedule'!BC53","v":0},{"$f":"'K90 - time schedule'!BD53","v":0},{"$f":"'K90 - time schedule'!BE53","v":0},{"$f":"'K90 - time schedule'!BF53","v":0},{"$f":"'K90 - time schedule'!BG53","v":0},{"$f":"'K90 - time schedule'!BH53","v":0},{"$f":"'K90 - time schedule'!BI53","v":0},{"$f":"'K90 - time schedule'!BJ53","v":0},{"$f":"'K90 - time schedule'!BK53","v":0},{"$f":"'K90 - time schedule'!BL53","v":0},{"$f":"'K90 - time schedule'!BM53","v":0},{"$f":"'K90 - time schedule'!BN53","v":0},{"$f":"'K90 - time schedule'!BO53","v":0},{"$f":"'K90 - time schedule'!BP53","v":0},{"$f":"'K90 - time schedule'!BQ53","v":0},{"$f":"'K90 - time schedule'!BR53","v":0},{"$f":"'K90 - time schedule'!BS53","v":0},{"$f":"'K90 - time schedule'!BT53","v":0},{"$f":"'K90 - time schedule'!BU53","v":0},{"$f":"'K90 - time schedule'!BV53","v":0},{"$f":"'K90 - time schedule'!BW53","v":0},{"$f":"'K90 - time schedule'!BX53","v":0},{"$f":"'K90 - time schedule'!BY53","v":0},{"$f":"'K90 - time schedule'!BZ53","v":0},{"$f":"'K90 - time schedule'!CA53","v":0},{"$f":"'K90 - time schedule'!CB53","v":0},{"$f":"'K90 - time schedule'!CC53","v":0},{"$f":"'K90 - time schedule'!CD53","v":0},{"$f":"'K90 - time schedule'!CE53","v":0},{"$f":"'K90 - time schedule'!CF53","v":0},{"$f":"'K90 - time schedule'!CG53","v":0},{"$f":"'K90 - time schedule'!CH53","v":0},{"$f":"'K90 - time schedule'!CI53","v":0},{"$f":"'K90 - time schedule'!CJ53","v":0},{"$f":"'K90 - time schedule'!CK53","v":0},{"$f":"'K90 - time schedule'!CL53","v":0},{"$f":"'K90 - time schedule'!CM53","v":0},{"$f":"'K90 - time schedule'!CN53","v":0},{"$f":"'K90 - time schedule'!CO53","v":0},{"$f":"'K90 - time schedule'!CP53","v":0},{"$f":"'K90 - time schedule'!CQ53","v":0},{"$f":"'K90 - time schedule'!CR53","v":0},{"$f":"'K90 - time schedule'!CS53","v":0},{"$f":"'K90 - time schedule'!CT53","v":0},{"$f":"'K90 - time schedule'!CU53","v":0},{"$f":"'K90 - time schedule'!CV53","v":0},{"$f":"'K90 - time schedule'!CW53","v":0},{"$f":"'K90 - time schedule'!CX53","v":0},{"$f":"'K90 - time schedule'!CY53","v":0},{"$f":"'K90 - time schedule'!CZ53","v":0},{"$f":"'K90 - time schedule'!DA53","v":0},{"$f":"'K90 - time schedule'!DB53","v":0},{"$f":"'K90 - time schedule'!DC53","v":0},{"$f":"'K90 - time schedule'!DD53","v":0},{"$f":"'K90 - time schedule'!DE53","v":0},{"$f":"'K90 - time schedule'!DF53","v":0},{"$f":"'K90 - time schedule'!DG53","v":0},{"$f":"'K90 - time schedule'!DH53","v":0},{"$f":"'K90 - time schedule'!DI53","v":0},{"$f":"'K90 - time schedule'!DJ53","v":0},{"$f":"'K90 - time schedule'!DK53","v":0},{"$f":"'K90 - time schedule'!DL53","v":0},{"$f":"'K90 - time schedule'!DM53","v":0},{"$f":"'K90 - time schedule'!DN53","v":0},{"$f":"'K90 - time schedule'!DO53","v":0},{"$f":"'K90 - time schedule'!DP53","v":0},{"$f":"'K90 - time schedule'!DQ53","v":0},{"$f":"'K90 - time schedule'!DR53","v":0},{"$f":"'K90 - time schedule'!DS53","v":0},{"$f":"'K90 - time schedule'!DT53","v":0},{"$f":"'K90 - time schedule'!DU53","v":0},{"$f":"'K90 - time schedule'!DV53","v":0},{"$f":"'K90 - time schedule'!DW53","v":0},{"$f":"'K90 - time schedule'!DX53","v":0},{"$f":"'K90 - time schedule'!DY53","v":0},{"$f":"'K90 - time schedule'!DZ53","v":0},{"$f":"'K90 - time schedule'!EA53","v":0},{"$f":"'K90 - time schedule'!EB53","v":0},{"$f":"'K90 - time schedule'!EC53","v":0},{"$f":"'K90 - time schedule'!ED53","v":0},{"$f":"'K90 - time schedule'!EE53","v":0},{"$f":"'K90 - time schedule'!EF53","v":0},{"$f":"'K90 - time schedule'!EG53","v":0},{"$f":"'K90 - time schedule'!EH53","v":0},{"$f":"'K90 - time schedule'!EI53","v":0},{"$f":"'K90 - time schedule'!EJ53","v":0},{"$f":"'K90 - time schedule'!EK53","v":0},{"$f":"'K90 - time schedule'!EL53","v":0},{"$f":"'K90 - time schedule'!EM53","v":0},{"$f":"'K90 - time schedule'!EN53","v":0},{"$f":"'K90 - time schedule'!EO53","v":0},{"$f":"'K90 - time schedule'!EP53","v":0},{"$f":"'K90 - time schedule'!EQ53","v":0},{"$f":"'K90 - time schedule'!ER53","v":0},{"$f":"'K90 - time schedule'!ES53","v":0},{"$f":"'K90 - time schedule'!ET53","v":0},{"$f":"'K90 - time schedule'!EU53","v":0},{"$f":"'K90 - time schedule'!EV53","v":0},{"$f":"'K90 - time schedule'!EW53","v":0},{"$f":"'K90 - time schedule'!EX53","v":0},{"$f":"'K90 - time schedule'!EY53","v":0},{"$f":"'K90 - time schedule'!EZ53","v":0},{"$f":"'K90 - time schedule'!FA53","v":0},{"$f":"'K90 - time schedule'!FB53","v":0},{"$f":"'K90 - time schedule'!FC53","v":0},{"$f":"'K90 - time schedule'!FD53","v":0},{"$f":"'K90 - time schedule'!FE53","v":0},{"$f":"'K90 - time schedule'!FF53","v":0},{"$f":"'K90 - time schedule'!FG53","v":0},{"$f":"'K90 - time schedule'!FH53","v":0},{"$f":"'K90 - time schedule'!FI53","v":0},{"$f":"'K90 - time schedule'!FJ53","v":0},{"$f":"'K90 - time schedule'!FK53","v":0},{"$f":"'K90 - time schedule'!FL53","v":0},{"$f":"'K90 - time schedule'!FM53","v":0},{"$f":"'K90 - time schedule'!FN53","v":0},{"$f":"'K90 - time schedule'!FO53","v":0},{"$f":"'K90 - time schedule'!FP53","v":0},{"$f":"'K90 - time schedule'!FQ53","v":0},{"$f":"'K90 - time schedule'!FR53","v":0},{"$f":"'K90 - time schedule'!FS53","v":0},{"$f":"'K90 - time schedule'!FT53","v":0},{"$f":"'K90 - time schedule'!FU53","v":0},{"$f":"'K90 - time schedule'!FV53","v":0},{"$f":"'K90 - time schedule'!FW53","v":0},{"$f":"'K90 - time schedule'!FX53","v":0},{"$f":"'K90 - time schedule'!FY53","v":0},{"$f":"'K90 - time schedule'!FZ53","v":0},{"$f":"'K90 - time schedule'!GA53","v":0},{"$f":"'K90 - time schedule'!GB53","v":0},{"$f":"'K90 - time schedule'!GC53","v":0},{"$f":"'K90 - time schedule'!GD53","v":0},{"$f":"'K90 - time schedule'!GE53","v":0},{"$f":"'K90 - time schedule'!GF53","v":0},{"$f":"'K90 - time schedule'!GG53","v":0},{"$f":"'K90 - time schedule'!GH53","v":0},{"$f":"'K90 - time schedule'!GI53","v":0},{"$f":"'K90 - time schedule'!GJ53","v":0},{"$f":"'K90 - time schedule'!GK53","v":0},{"$f":"'K90 - time schedule'!GL53","v":0},{"$f":"'K90 - time schedule'!GM53","v":0},{"$f":"'K90 - time schedule'!GN53","v":0},{"$f":"'K90 - time schedule'!GO53","v":0},{"$f":"'K90 - time schedule'!GP53","v":0},{"$f":"'K90 - time schedule'!GQ53","v":0},{"$f":"'K90 - time schedule'!GR53","v":0},{"$f":"'K90 - time schedule'!GS53","v":0},{"$f":"'K90 - time schedule'!GT53","v":0},{"$f":"'K90 - time schedule'!GU53","v":0},{"$f":"'K90 - time schedule'!GV53","v":0},{"$f":"'K90 - time schedule'!GW53","v":0},{"$f":"'K90 - time schedule'!GX53","v":0},{"$f":"'K90 - time schedule'!GY53","v":0},{"$f":"'K90 - time schedule'!GZ53","v":0},{"$f":"'K90 - time schedule'!HA53","v":0},{"$f":"'K90 - time schedule'!HB53","v":0},{"$f":"'K90 - time schedule'!HC53","v":0},{"$f":"'K90 - time schedule'!HD53","v":0},{"$f":"'K90 - time schedule'!HE53","v":0},{"$f":"'K90 - time schedule'!HF53","v":0},{"$f":"'K90 - time schedule'!HG53","v":0},{"$f":"'K90 - time schedule'!HH53","v":0},{"$f":"'K90 - time schedule'!HI53","v":0},{"$f":"'K90 - time schedule'!HJ53","v":0},{"$f":"'K90 - time schedule'!HK53","v":0},{"$f":"'K90 - time schedule'!HL53","v":0},{"$f":"'K90 - time schedule'!HM53","v":0},{"$f":"'K90 - time schedule'!HN53","v":0},{"$f":"'K90 - time schedule'!HO53","v":0},{"$f":"'K90 - time schedule'!HP53","v":0},{"$f":"'K90 - time schedule'!HQ53","v":0},{"$f":"'K90 - time schedule'!HR53","v":0},{"$f":"'K90 - time schedule'!HS53","v":0},{"$f":"'K90 - time schedule'!HT53","v":0},{"$f":"'K90 - time schedule'!HU53","v":0},{"$f":"'K90 - time schedule'!HV53","v":0},{"$f":"'K90 - time schedule'!HW53","v":0},{"$f":"'K90 - time schedule'!HX53","v":0},{"$f":"'K90 - time schedule'!HY53","v":0},{"$f":"'K90 - time schedule'!HZ53","v":0},{"$f":"'K90 - time schedule'!IA53","v":0},{"$f":"'K90 - time schedule'!IB53","v":0},{"$f":"'K90 - time schedule'!IC53","v":0},{"$f":"'K90 - time schedule'!ID53","v":0},{"$f":"'K90 - time schedule'!IE53","v":0},{"$f":"'K90 - time schedule'!IF53","v":0},{"$f":"'K90 - time schedule'!IG53","v":0},{"$f":"'K90 - time schedule'!IH53","v":0},{"$f":"'K90 - time schedule'!II53","v":0},{"$f":"'K90 - time schedule'!IJ53","v":0},{"$f":"'K90 - time schedule'!IK53","v":0},{"$f":"'K90 - time schedule'!IL53","v":0},{"$f":"'K90 - time schedule'!IM53","v":0},{"$f":"'K90 - time schedule'!IN53","v":0},{"$f":"'K90 - time schedule'!IO53","v":0},{"$f":"'K90 - time schedule'!IP53","v":0},{"$f":"'K90 - time schedule'!IQ53","v":0},{"$f":"'K90 - time schedule'!IR53","v":0},{"$f":"'K90 - time schedule'!IS53","v":0},{"$f":"'K90 - time schedule'!IT53","v":0},{"$f":"'K90 - time schedule'!IU53","v":0},{"$f":"'K90 - time schedule'!IV53","v":0},{"$f":"'K90 - time schedule'!IW53","v":0},{"$f":"'K90 - time schedule'!IX53","v":0},{"$f":"'K90 - time schedule'!IY53","v":0},{"$f":"'K90 - time schedule'!IZ53","v":0},{"$f":"'K90 - time schedule'!JA53","v":0},{"$f":"'K90 - time schedule'!JB53","v":0},{"$f":"'K90 - time schedule'!JC53","v":0},{"$f":"'K90 - time schedule'!JD53","v":0},{"$f":"'K90 - time schedule'!JE53","v":0},{"$f":"'K90 - time schedule'!JF53","v":0},{"$f":"'K90 - time schedule'!JG53","v":0},{"$f":"'K90 - time schedule'!JH53","v":0},{"$f":"'K90 - time schedule'!JI53","v":0},{"$f":"'K90 - time schedule'!JJ53","v":0},{"$f":"'K90 - time schedule'!JK53","v":0},{"$f":"'K90 - time schedule'!JL53","v":0},{"$f":"'K90 - time schedule'!JM53","v":0},{"$f":"'K90 - time schedule'!JN53","v":0},{"$f":"'K90 - time schedule'!JO53","v":0},{"$f":"'K90 - time schedule'!JP53","v":0},{"$f":"'K90 - time schedule'!JQ53","v":0},{"$f":"'K90 - time schedule'!JR53","v":0},{"$f":"'K90 - time schedule'!JS53","v":0},{"$f":"'K90 - time schedule'!JT53","v":0},{"$f":"'K90 - time schedule'!JU53","v":0},{"$f":"'K90 - time schedule'!JV53","v":0},{"$f":"'K90 - time schedule'!JW53","v":0},{"$f":"'K90 - time schedule'!JX53","v":0},{"$f":"'K90 - time schedule'!JY53","v":0},{"$f":"'K90 - time schedule'!JZ53","v":0},{"$f":"'K90 - time schedule'!KA53","v":0},{"$f":"'K90 - time schedule'!KB53","v":0},{"$f":"'K90 - time schedule'!KC53","v":0},{"$f":"'K90 - time schedule'!KD53","v":0},{"$f":"'K90 - time schedule'!KE53","v":0},{"$f":"'K90 - time schedule'!KF53","v":0},{"$f":"'K90 - time schedule'!KG53","v":0},{"$f":"'K90 - time schedule'!KH53","v":0},{"$f":"'K90 - time schedule'!KI53","v":0},{"$f":"'K90 - time schedule'!KJ53","v":0},{"$f":"'K90 - time schedule'!KK53","v":0},{"$f":"'K90 - time schedule'!KL53","v":0},{"$f":"'K90 - time schedule'!KM53","v":0},{"$f":"'K90 - time schedule'!KN53","v":0},{"$f":"'K90 - time schedule'!KO53","v":0},{"$f":"'K90 - time schedule'!KP53","v":0},{"$f":"'K90 - time schedule'!KQ53","v":0},{"$f":"'K90 - time schedule'!KR53","v":0},{"$f":"'K90 - time schedule'!KS53","v":0},{"$f":"'K90 - time schedule'!KT53","v":0}]
["Boiler room K90 - trial operation","K90",{"$f":"'K90 - time schedule'!G55","v":0},{"$f":"'K90 - time schedule'!H55","v":0},{"$f":"'K90 - time schedule'!I55","v":0},{"$f":"'K90 - time schedule'!J55","v":0},{"$f":"'K90 - time schedule'!K55","v":0},{"$f":"'K90 - time schedule'!L55","v":0},{"$f":"'K90 - time schedule'!M55","v":0},{"$f":"'K90 - time schedule'!N55","v":0},{"$f":"'K90 - time schedule'!O55","v":0},{"$f":"'K90 - time schedule'!P55","v":0},{"$f":"'K90 - time schedule'!Q55","v":0},{"$f":"'K90 - time schedule'!R55","v":0},{"$f":"'K90 - time schedule'!S55","v":0},{"$f":"'K90 - time schedule'!T55","v":0},{"$f":"'K90 - time schedule'!U55","v":0},{"$f":"'K90 - time schedule'!V55","v":0},{"$f":"'K90 - time schedule'!W55","v":0},{"$f":"'K90 - time schedule'!X55","v":0},{"$f":"'K90 - time schedule'!Y55","v":0},{"$f":"'K90 - time schedule'!Z55","v":0},{"$f":"'K90 - time schedule'!AA55","v":0},{"$f":"'K90 - time schedule'!AB55","v":0},{"$f":"'K90 - time schedule'!AC55","v":0},{"$f":"'K90 - time schedule'!AD55","v":0},{"$f":"'K90 - time schedule'!AE55","v":0},{"$f":"'K90 - time schedule'!AF55","v":0},{"$f":"'K90 - time schedule'!AG55","v":0},{"$f":"'K90 - time schedule'!AH55","v":0},{"$f":"'K90 - time schedule'!AI55","v":0},{"$f":"'K90 - time schedule'!AJ55","v":0},{"$f":"'K90 - time schedule'!AK55","v":0},{"$f":"'K90 - time schedule'!AL55","v":0},{"$f":"'K90 - time schedule'!AM55","v":0},{"$f":"'K90 - time schedule'!AN55","v":0},{"$f":"'K90 - time schedule'!AO55","v":0},{"$f":"'K90 - time schedule'!AP55","v":0},{"$f":"'K90 - time schedule'!AQ55","v":0},{"$f":"'K90 - time schedule'!AR55","v":0},{"$f":"'K90 - time schedule'!AS55","v":0},{"$f":"'K90 - time schedule'!AT55","v":0},{"$f":"'K90 - time schedule'!AU55","v":0},{"$f":"'K90 - time schedule'!AV55","v":0},{"$f":"'K90 - time schedule'!AW55","v":0},{"$f":"'K90 - time schedule'!AX55","v":0},{"$f":"'K90 - time schedule'!AY55","v":0},{"$f":"'K90 - time schedule'!AZ55","v":0},{"$f":"'K90 - time schedule'!BA55","v":0},{"$f":"'K90 - time schedule'!BB55","v":0},{"$f":"'K90 - time schedule'!BC55","v":0},{"$f":"'K90 - time schedule'!BD55","v":0},{"$f":"'K90 - time schedule'!BE55","v":0},{"$f":"'K90 - time schedule'!BF55","v":0},{"$f":"'K90 - time schedule'!BG55","v":0},{"$f":"'K90 - time schedule'!BH55","v":0},{"$f":"'K90 - time schedule'!BI55","v":0},{"$f":"'K90 - time schedule'!BJ55","v":0},{"$f":"'K90 - time schedule'!BK55","v":0},{"$f":"'K90 - time schedule'!BL55","v":0},{"$f":"'K90 - time schedule'!BM55","v":0},{"$f":"'K90 - time schedule'!BN55","v":0},{"$f":"'K90 - time schedule'!BO55","v":0},{"$f":"'K90 - time schedule'!BP55","v":0},{"$f":"'K90 - time schedule'!BQ55","v":0},{"$f":"'K90 - time schedule'!BR55","v":0},{"$f":"'K90 - time schedule'!BS55","v":0},{"$f":"'K90 - time schedule'!BT55","v":0},{"$f":"'K90 - time schedule'!BU55","v":0},{"$f":"'K90 - time schedule'!BV55","v":0},{"$f":"'K90 - time schedule'!BW55","v":0},{"$f":"'K90 - time schedule'!BX55","v":0},{"$f":"'K90 - time schedule'!BY55","v":0},{"$f":"'K90 - time schedule'!BZ55","v":0},{"$f":"'K90 - time schedule'!CA55","v":0},{"$f":"'K90 - time schedule'!CB55","v":0},{"$f":"'K90 - time schedule'!CC55","v":0},{"$f":"'K90 - time schedule'!CD55","v":0},{"$f":"'K90 - time schedule'!CE55","v":0},{"$f":"'K90 - time schedule'!CF55","v":0},{"$f":"'K90 - time schedule'!CG55","v":0},{"$f":"'K90 - time schedule'!CH55","v":0},{"$f":"'K90 - time schedule'!CI55","v":0},{"$f":"'K90 - time schedule'!CJ55","v":0},{"$f":"'K90 - time schedule'!CK55","v":0},{"$f":"'K90 - time schedule'!CL55","v":0},{"$f":"'K90 - time schedule'!CM55","v":0},{"$f":"'K90 - time schedule'!CN55","v":0},{"$f":"'K90 - time schedule'!CO55","v":0},{"$f":"'K90 - time schedule'!CP55","v":0},{"$f":"'K90 - time schedule'!CQ55","v":0},{"$f":"'K90 - time schedule'!CR55","v":0},{"$f":"'K90 - time schedule'!CS55","v":0},{"$f":"'K90 - time schedule'!CT55","v":0},{"$f":"'K90 - time schedule'!CU55","v":0},{"$f":"'K90 - time schedule'!CV55","v":0},{"$f":"'K90 - time schedule'!CW55","v":0},{"$f":"'K90 - time schedule'!CX55","v":0},{"$f":"'K90 - time schedule'!CY55","v":0},{"$f":"'K90 - time schedule'!CZ55","v":0},{"$f":"'K90 - time schedule'!DA55","v":0},{"$f":"'K90 - time schedule'!DB55","v":0},{"$f":"'K90 - time schedule'!DC55","v":0},{"$f":"'K90 - time schedule'!DD55","v":0},{"$f":"'K90 - time schedule'!DE55","v":0},{"$f":"'K90 - time schedule'!DF55","v":0},{"$f":"'K90 - time schedule'!DG55","v":0},{"$f":"'K90 - time schedule'!DH55","v":0},{"$f":"'K90 - time schedule'!DI55","v":0},{"$f":"'K90 - time schedule'!DJ55","v":0},{"$f":"'K90 - time schedule'!DK55","v":0},{"$f":"'K90 - time schedule'!DL55","v":0},{"$f":"'K90 - time schedule'!DM55","v":0},{"$f":"'K90 - time schedule'!DN55","v":0},{"$f":"'K90 - time schedule'!DO55","v":0},{"$f":"'K90 - time schedule'!DP55","v":0},{"$f":"'K90 - time schedule'!DQ55","v":0},{"$f":"'K90 - time schedule'!DR55","v":0},{"$f":"'K90 - time schedule'!DS55","v":0},{"$f":"'K90 - time schedule'!DT55","v":0},{"$f":"'K90 - time schedule'!DU55","v":0},{"$f":"'K90 - time schedule'!DV55","v":0},{"$f":"'K90 - time schedule'!DW55","v":0},{"$f":"'K90 - time schedule'!DX55","v":0},{"$f":"'K90 - time schedule'!DY55","v":0},{"$f":"'K90 - time schedule'!DZ55","v":0},{"$f":"'K90 - time schedule'!EA55","v":0},{"$f":"'K90 - time schedule'!EB55","v":0},{"$f":"'K90 - time schedule'!EC55","v":0},{"$f":"'K90 - time schedule'!ED55","v":0},{"$f":"'K90 - time schedule'!EE55","v":0},{"$f":"'K90 - time schedule'!EF55","v":0},{"$f":"'K90 - time schedule'!EG55","v":0},{"$f":"'K90 - time schedule'!EH55","v":0},{"$f":"'K90 - time schedule'!EI55","v":0},{"$f":"'K90 - time schedule'!EJ55","v":0},{"$f":"'K90 - time schedule'!EK55","v":0},{"$f":"'K90 - time schedule'!EL55","v":0},{"$f":"'K90 - time schedule'!EM55","v":0},{"$f":"'K90 - time schedule'!EN55","v":0},{"$f":"'K90 - time schedule'!EO55","v":0},{"$f":"'K90 - time schedule'!EP55","v":0},{"$f":"'K90 - time schedule'!EQ55","v":0},{"$f":"'K90 - time schedule'!ER55","v":0},{"$f":"'K90 - time schedule'!ES55","v":0},{"$f":"'K90 - time schedule'!ET55","v":0},{"$f":"'K90 - time schedule'!EU55","v":0},{"$f":"'K90 - time schedule'!EV55","v":0},{"$f":"'K90 - time schedule'!EW55","v":0},{"$f":"'K90 - time schedule'!EX55","v":0},{"$f":"'K90 - time schedule'!EY55","v":0},{"$f":"'K90 - time schedule'!EZ55","v":0},{"$f":"'K90 - time schedule'!FA55","v":0},{"$f":"'K90 - time schedule'!FB55","v":0},{"$f":"'K90 - time schedule'!FC55","v":0},{"$f":"'K90 - time schedule'!FD55","v":0},{"$f":"'K90 - time schedule'!FE55","v":0},{"$f":"'K90 - time schedule'!FF55","v":0},{"$f":"'K90 - time schedule'!FG55","v":0},{"$f":"'K90 - time schedule'!FH55","v":0},{"$f":"'K90 - time schedule'!FI55","v":0},{"$f":"'K90 - time schedule'!FJ55","v":0},{"$f":"'K90 - time schedule'!FK55","v":0},{"$f":"'K90 - time schedule'!FL55","v":0},{"$f":"'K90 - time schedule'!FM55","v":0},{"$f":"'K90 - time schedule'!FN55","v":0},{"$f":"'K90 - time schedule'!FO55","v":0},{"$f":"'K90 - time schedule'!FP55","v":0},{"$f":"'K90 - time schedule'!FQ55","v":0},{"$f":"'K90 - time schedule'!FR55","v":0},{"$f":"'K90 - time schedule'!FS55","v":0},{"$f":"'K90 - time schedule'!FT55","v":0},{"$f":"'K90 - time schedule'!FU55","v":0},{"$f":"'K90 - time schedule'!FV55","v":0},{"$f":"'K90 - time schedule'!FW55","v":0},{"$f":"'K90 - time schedule'!FX55","v":0},{"$f":"'K90 - time schedule'!FY55","v":0},{"$f":"'K90 - time schedule'!FZ55","v":0},{"$f":"'K90 - time schedule'!GA55","v":0},{"$f":"'K90 - time schedule'!GB55","v":0},{"$f":"'K90 - time schedule'!GC55","v":0},{"$f":"'K90 - time schedule'!GD55","v":0},{"$f":"'K90 - time schedule'!GE55","v":0},{"$f":"'K90 - time schedule'!GF55","v":0},{"$f":"'K90 - time schedule'!GG55","v":0},{"$f":"'K90 - time schedule'!GH55","v":0},{"$f":"'K90 - time schedule'!GI55","v":0},{"$f":"'K90 - time schedule'!GJ55","v":0},{"$f":"'K90 - time schedule'!GK55","v":0},{"$f":"'K90 - time schedule'!GL55","v":0},{"$f":"'K90 - time schedule'!GM55","v":0},{"$f":"'K90 - time schedule'!GN55","v":0},{"$f":"'K90 - time schedule'!GO55","v":0},{"$f":"'K90 - time schedule'!GP55","v":0},{"$f":"'K90 - time schedule'!GQ55","v":0},{"$f":"'K90 - time schedule'!GR55","v":0},{"$f":"'K90 - time schedule'!GS55","v":0},{"$f":"'K90 - time schedule'!GT55","v":0},{"$f":"'K90 - time schedule'!GU55","v":0},{"$f":"'K90 - time schedule'!GV55","v":0},{"$f":"'K90 - time schedule'!GW55","v":0},{"$f":"'K90 - time schedule'!GX55","v":0},{"$f":"'K90 - time schedule'!GY55","v":0},{"$f":"'K90 - time schedule'!GZ55","v":0},{"$f":"'K90 - time schedule'!HA55","v":0},{"$f":"'K90 - time schedule'!HB55","v":0},{"$f":"'K90 - time schedule'!HC55","v":0},{"$f":"'K90 - time schedule'!HD55","v":0},{"$f":"'K90 - time schedule'!HE55","v":0},{"$f":"'K90 - time schedule'!HF55","v":0},{"$f":"'K90 - time schedule'!HG55","v":0},{"$f":"'K90 - time schedule'!HH55","v":0},{"$f":"'K90 - time schedule'!HI55","v":0},{"$f":"'K90 - time schedule'!HJ55","v":0},{"$f":"'K90 - time schedule'!HK55","v":0},{"$f":"'K90 - time schedule'!HL55","v":0},{"$f":"'K90 - time schedule'!HM55","v":0},{"$f":"'K90 - time schedule'!HN55","v":0},{"$f":"'K90 - time schedule'!HO55","v":0},{"$f":"'K90 - time schedule'!HP55","v":0},{"$f":"'K90 - time schedule'!HQ55","v":0},{"$f":"'K90 - time schedule'!HR55","v":0},{"$f":"'K90 - time schedule'!HS55","v":0},{"$f":"'K90 - time schedule'!HT55","v":0},{"$f":"'K90 - time schedule'!HU55","v":0},{"$f":"'K90 - time schedule'!HV55","v":0},{"$f":"'K90 - time schedule'!HW55","v":0},{"$f":"'K90 - time schedule'!HX55","v":0},{"$f":"'K90 - time schedule'!HY55","v":0},{"$f":"'K90 - time schedule'!HZ55","v":0},{"$f":"'K90 - time schedule'!IA55","v":0},{"$f":"'K90 - time schedule'!IB55","v":0},{"$f":"'K90 - time schedule'!IC55","v":0},{"$f":"'K90 - time schedule'!ID55","v":0},{"$f":"'K90 - time schedule'!IE55","v":0},{"$f":"'K90 - time schedule'!IF55","v":0},{"$f":"'K90 - time schedule'!IG55","v":0},{"$f":"'K90 - time schedule'!IH55","v":0},{"$f":"'K90 - time schedule'!II55","v":0},{"$f":"'K90 - time schedule'!IJ55","v":0},{"$f":"'K90 - time schedule'!IK55","v":0},{"$f":"'K90 - time schedule'!IL55","v":0},{"$f":"'K90 - time schedule'!IM55","v":0},{"$f":"'K90 - time schedule'!IN55","v":0},{"$f":"'K90 - time schedule'!IO55","v":0},{"$f":"'K90 - time schedule'!IP55","v":0},{"$f":"'K90 - time schedule'!IQ55","v":0},{"$f":"'K90 - time schedule'!IR55","v":0},{"$f":"'K90 - time schedule'!IS55","v":0},{"$f":"'K90 - time schedule'!IT55","v":0},{"$f":"'K90 - time schedule'!IU55","v":0},{"$f":"'K90 - time schedule'!IV55","v":0},{"$f":"'K90 - time schedule'!IW55","v":0},{"$f":"'K90 - time schedule'!IX55","v":0},{"$f":"'K90 - time schedule'!IY55","v":0},{"$f":"'K90 - time schedule'!IZ55","v":0},{"$f":"'K90 - time schedule'!JA55","v":0},{"$f":"'K90 - time schedule'!JB55","v":0},{"$f":"'K90 - time schedule'!JC55","v":0},{"$f":"'K90 - time schedule'!JD55","v":0},{"$f":"'K90 - time schedule'!JE55","v":0},{"$f":"'K90 - time schedule'!JF55","v":0},{"$f":"'K90 - time schedule'!JG55","v":0},{"$f":"'K90 - time schedule'!JH55","v":0},{"$f":"'K90 - time schedule'!JI55","v":0},{"$f":"'K90 - time schedule'!JJ55","v":0},{"$f":"'K90 - time schedule'!JK55","v":0},{"$f":"'K90 - time schedule'!JL55","v":0},{"$f":"'K90 - time schedule'!JM55","v":0},{"$f":"'K90 - time schedule'!JN55","v":0},{"$f":"'K90 - time schedule'!JO55","v":0},{"$f":"'K90 - time schedule'!JP55","v":0},{"$f":"'K90 - time schedule'!JQ55","v":0},{"$f":"'K90 - time schedule'!JR55","v":0},{"$f":"'K90 - time schedule'!JS55","v":0},{"$f":"'K90 - time schedule'!JT55","v":0},{"$f":"'K90 - time schedule'!JU55","v":0},{"$f":"'K90 - time schedule'!JV55","v":0},{"$f":"'K90 - time schedule'!JW55","v":0},{"$f":"'K90 - time schedule'!JX55","v":0},{"$f":"'K90 - time schedule'!JY55","v":0},{"$f":"'K90 - time schedule'!JZ55","v":0},{"$f":"'K90 - time schedule'!KA55","v":0},{"$f":"'K90 - time schedule'!KB55","v":0},{"$f":"'K90 - time schedule'!KC55","v":0},{"$f":"'K90 - time schedule'!KD55","v":0},{"$f":"'K90 - time schedule'!KE55","v":0},{"$f":"'K90 - time schedule'!KF55","v":0},{"$f":"'K90 - time schedule'!KG55","v":0},{"$f":"'K90 - time schedule'!KH55","v":0},{"$f":"'K90 - time schedule'!KI55","v":0},{"$f":"'K90 - time schedule'!KJ55","v":0},{"$f":"'K90 - time schedule'!KK55","v":0},{"$f":"'K90 - time schedule'!KL55","v":0},{"$f":"'K90 - time schedule'!KM55","v":0},{"$f":"'K90 - time schedule'!KN55","v":0},{"$f":"'K90 - time schedule'!KO55","v":0},{"$f":"'K90 - time schedule'!KP55","v":0},{"$f":"'K90 - time schedule'!KQ55","v":0},{"$f":"'K90 - time schedule'!KR55","v":0},{"$f":"'K90 - time schedule'!KS55","v":0},{"$f":"'K90 - time schedule'!KT55","v":0}]
["Boiler room K90 - guarantee test A","K90",{"$f":"'K90 - time schedule'!G57","v":0},{"$f":"'K90 - time schedule'!H57","v":0},{"$f":"'K90 - time schedule'!I57","v":0},{"$f":"'K90 - time schedule'!J57","v":0},{"$f":"'K90 - time schedule'!K57","v":0},{"$f":"'K90 - time schedule'!L57","v":0},{"$f":"'K90 - time schedule'!M57","v":0},{"$f":"'K90 - time schedule'!N57","v":0},{"$f":"'K90 - time schedule'!O57","v":0},{"$f":"'K90 - time schedule'!P57","v":0},{"$f":"'K90 - time schedule'!Q57","v":0},{"$f":"'K90 - time schedule'!R57","v":0},{"$f":"'K90 - time schedule'!S57","v":0},{"$f":"'K90 - time schedule'!T57","v":0},{"$f":"'K90 - time schedule'!U57","v":0},{"$f":"'K90 - time schedule'!V57","v":0},{"$f":"'K90 - time schedule'!W57","v":0},{"$f":"'K90 - time schedule'!X57","v":0},{"$f":"'K90 - time schedule'!Y57","v":0},{"$f":"'K90 - time schedule'!Z57","v":0},{"$f":"'K90 - time schedule'!AA57","v":0},{"$f":"'K90 - time schedule'!AB57","v":0},{"$f":"'K90 - time schedule'!AC57","v":0},{"$f":"'K90 - time schedule'!AD57","v":0},{"$f":"'K90 - time schedule'!AE57","v":0},{"$f":"'K90 - time schedule'!AF57","v":0},{"$f":"'K90 - time schedule'!AG57","v":0},{"$f":"'K90 - time schedule'!AH57","v":0},{"$f":"'K90 - time schedule'!AI57","v":0},{"$f":"'K90 - time schedule'!AJ57","v":0},{"$f":"'K90 - time schedule'!AK57","v":0},{"$f":"'K90 - time schedule'!AL57","v":0},{"$f":"'K90 - time schedule'!AM57","v":0},{"$f":"'K90 - time schedule'!AN57","v":0},{"$f":"'K90 - time schedule'!AO57","v":0},{"$f":"'K90 - time schedule'!AP57","v":0},{"$f":"'K90 - time schedule'!AQ57","v":0},{"$f":"'K90 - time schedule'!AR57","v":0},{"$f":"'K90 - time schedule'!AS57","v":0},{"$f":"'K90 - time schedule'!AT57","v":0},{"$f":"'K90 - time schedule'!AU57","v":0},{"$f":"'K90 - time schedule'!AV57","v":0},{"$f":"'K90 - time schedule'!AW57","v":0},{"$f":"'K90 - time schedule'!AX57","v":0},{"$f":"'K90 - time schedule'!AY57","v":0},{"$f":"'K90 - time schedule'!AZ57","v":0},{"$f":"'K90 - time schedule'!BA57","v":0},{"$f":"'K90 - time schedule'!BB57","v":0},{"$f":"'K90 - time schedule'!BC57","v":0},{"$f":"'K90 - time schedule'!BD57","v":0},{"$f":"'K90 - time schedule'!BE57","v":0},{"$f":"'K90 - time schedule'!BF57","v":0},{"$f":"'K90 - time schedule'!BG57","v":0},{"$f":"'K90 - time schedule'!BH57","v":0},{"$f":"'K90 - time schedule'!BI57","v":0},{"$f":"'K90 - time schedule'!BJ57","v":0},{"$f":"'K90 - time schedule'!BK57","v":0},{"$f":"'K90 - time schedule'!BL57","v":0},{"$f":"'K90 - time schedule'!BM57","v":0},{"$f":"'K90 - time schedule'!BN57","v":0},{"$f":"'K90 - time schedule'!BO57","v":0},{"$f":"'K90 - time schedule'!BP57","v":0},{"$f":"'K90 - time schedule'!BQ57","v":0},{"$f":"'K90 - time schedule'!BR57","v":0},{"$f":"'K90 - time schedule'!BS57","v":0},{"$f":"'K90 - time schedule'!BT57","v":0},{"$f":"'K90 - time schedule'!BU57","v":0},{"$f":"'K90 - time schedule'!BV57","v":0},{"$f":"'K90 - time schedule'!BW57","v":0},{"$f":"'K90 - time schedule'!BX57","v":0},{"$f":"'K90 - time schedule'!BY57","v":0},{"$f":"'K90 - time schedule'!BZ57","v":0},{"$f":"'K90 - time schedule'!CA57","v":0},{"$f":"'K90 - time schedule'!CB57","v":0},{"$f":"'K90 - time schedule'!CC57","v":0},{"$f":"'K90 - time schedule'!CD57","v":0},{"$f":"'K90 - time schedule'!CE57","v":0},{"$f":"'K90 - time schedule'!CF57","v":0},{"$f":"'K90 - time schedule'!CG57","v":0},{"$f":"'K90 - time schedule'!CH57","v":0},{"$f":"'K90 - time schedule'!CI57","v":0},{"$f":"'K90 - time schedule'!CJ57","v":0},{"$f":"'K90 - time schedule'!CK57","v":0},{"$f":"'K90 - time schedule'!CL57","v":0},{"$f":"'K90 - time schedule'!CM57","v":0},{"$f":"'K90 - time schedule'!CN57","v":0},{"$f":"'K90 - time schedule'!CO57","v":0},{"$f":"'K90 - time schedule'!CP57","v":0},{"$f":"'K90 - time schedule'!CQ57","v":0},{"$f":"'K90 - time schedule'!CR57","v":0},{"$f":"'K90 - time schedule'!CS57","v":0},{"$f":"'K90 - time schedule'!CT57","v":0},{"$f":"'K90 - time schedule'!CU57","v":0},{"$f":"'K90 - time schedule'!CV57","v":0},{"$f":"'K90 - time schedule'!CW57","v":0},{"$f":"'K90 - time schedule'!CX57","v":0},{"$f":"'K90 - time schedule'!CY57","v":0},{"$f":"'K90 - time schedule'!CZ57","v":0},{"$f":"'K90 - time schedule'!DA57","v":0},{"$f":"'K90 - time schedule'!DB57","v":0},{"$f":"'K90 - time schedule'!DC57","v":0},{"$f":"'K90 - time schedule'!DD57","v":0},{"$f":"'K90 - time schedule'!DE57","v":0},{"$f":"'K90 - time schedule'!DF57","v":0},{"$f":"'K90 - time schedule'!DG57","v":0},{"$f":"'K90 - time schedule'!DH57","v":0},{"$f":"'K90 - time schedule'!DI57","v":0},{"$f":"'K90 - time schedule'!DJ57","v":0},{"$f":"'K90 - time schedule'!DK57","v":0},{"$f":"'K90 - time schedule'!DL57","v":0},{"$f":"'K90 - time schedule'!DM57","v":0},{"$f":"'K90 - time schedule'!DN57","v":0},{"$f":"'K90 - time schedule'!DO57","v":0},{"$f":"'K90 - time schedule'!DP57","v":0},{"$f":"'K90 - time schedule'!DQ57","v":0},{"$f":"'K90 - time schedule'!DR57","v":0},{"$f":"'K90 - time schedule'!DS57","v":0},{"$f":"'K90 - time schedule'!DT57","v":0},{"$f":"'K90 - time schedule'!DU57","v":0},{"$f":"'K90 - time schedule'!DV57","v":0},{"$f":"'K90 - time schedule'!DW57","v":0},{"$f":"'K90 - time schedule'!DX57","v":0},{"$f":"'K90 - time schedule'!DY57","v":0},{"$f":"'K90 - time schedule'!DZ57","v":0},{"$f":"'K90 - time schedule'!EA57","v":0},{"$f":"'K90 - time schedule'!EB57","v":0},{"$f":"'K90 - time schedule'!EC57","v":0},{"$f":"'K90 - time schedule'!ED57","v":0},{"$f":"'K90 - time schedule'!EE57","v":0},{"$f":"'K90 - time schedule'!EF57","v":0},{"$f":"'K90 - time schedule'!EG57","v":0},{"$f":"'K90 - time schedule'!EH57","v":0},{"$f":"'K90 - time schedule'!EI57","v":0},{"$f":"'K90 - time schedule'!EJ57","v":0},{"$f":"'K90 - time schedule'!EK57","v":0},{"$f":"'K90 - time schedule'!EL57","v":0},{"$f":"'K90 - time schedule'!EM57","v":0},{"$f":"'K90 - time schedule'!EN57","v":0},{"$f":"'K90 - time schedule'!EO57","v":0},{"$f":"'K90 - time schedule'!EP57","v":0},{"$f":"'K90 - time schedule'!EQ57","v":0},{"$f":"'K90 - time schedule'!ER57","v":0},{"$f":"'K90 - time schedule'!ES57","v":0},{"$f":"'K90 - time schedule'!ET57","v":0},{"$f":"'K90 - time schedule'!EU57","v":0},{"$f":"'K90 - time schedule'!EV57","v":0},{"$f":"'K90 - time schedule'!EW57","v":0},{"$f":"'K90 - time schedule'!EX57","v":0},{"$f":"'K90 - time schedule'!EY57","v":0},{"$f":"'K90 - time schedule'!EZ57","v":0},{"$f":"'K90 - time schedule'!FA57","v":0},{"$f":"'K90 - time schedule'!FB57","v":0},{"$f":"'K90 - time schedule'!FC57","v":0},{"$f":"'K90 - time schedule'!FD57","v":0},{"$f":"'K90 - time schedule'!FE57","v":0},{"$f":"'K90 - time schedule'!FF57","v":0},{"$f":"'K90 - time schedule'!FG57","v":0},{"$f":"'K90 - time schedule'!FH57","v":0},{"$f":"'K90 - time schedule'!FI57","v":0},{"$f":"'K90 - time schedule'!FJ57","v":0},{"$f":"'K90 - time schedule'!FK57","v":0},{"$f":"'K90 - time schedule'!FL57","v":0},{"$f":"'K90 - time schedule'!FM57","v":0},{"$f":"'K90 - time schedule'!FN57","v":0},{"$f":"'K90 - time schedule'!FO57","v":0},{"$f":"'K90 - time schedule'!FP57","v":0},{"$f":"'K90 - time schedule'!FQ57","v":0},{"$f":"'K90 - time schedule'!FR57","v":0},{"$f":"'K90 - time schedule'!FS57","v":0},{"$f":"'K90 - time schedule'!FT57","v":0},{"$f":"'K90 - time schedule'!FU57","v":0},{"$f":"'K90 - time schedule'!FV57","v":0},{"$f":"'K90 - time schedule'!FW57","v":0},{"$f":"'K90 - time schedule'!FX57","v":0},{"$f":"'K90 - time schedule'!FY57","v":0},{"$f":"'K90 - time schedule'!FZ57","v":0},{"$f":"'K90 - time schedule'!GA57","v":0},{"$f":"'K90 - time schedule'!GB57","v":0},{"$f":"'K90 - time schedule'!GC57","v":0},{"$f":"'K90 - time schedule'!GD57","v":0},{"$f":"'K90 - time schedule'!GE57","v":0},{"$f":"'K90 - time schedule'!GF57","v":0},{"$f":"'K90 - time schedule'!GG57","v":0},{"$f":"'K90 - time schedule'!GH57","v":0},{"$f":"'K90 - time schedule'!GI57","v":0},{"$f":"'K90 - time schedule'!GJ57","v":0},{"$f":"'K90 - time schedule'!GK57","v":0},{"$f":"'K90 - time schedule'!GL57","v":0},{"$f":"'K90 - time schedule'!GM57","v":0},{"$f":"'K90 - time schedule'!GN57","v":0},{"$f":"'K90 - time schedule'!GO57","v":0},{"$f":"'K90 - time schedule'!GP57","v":0},{"$f":"'K90 - time schedule'!GQ57","v":0},{"$f":"'K90 - time schedule'!GR57","v":0},{"$f":"'K90 - time schedule'!GS57","v":0},{"$f":"'K90 - time schedule'!GT57","v":0},{"$f":"'K90 - time schedule'!GU57","v":0},{"$f":"'K90 - time schedule'!GV57","v":0},{"$f":"'K90 - time schedule'!GW57","v":0},{"$f":"'K90 - time schedule'!GX57","v":0},{"$f":"'K90 - time schedule'!GY57","v":0},{"$f":"'K90 - time schedule'!GZ57","v":0},{"$f":"'K90 - time schedule'!HA57","v":0},{"$f":"'K90 - time schedule'!HB57","v":0},{"$f":"'K90 - time schedule'!HC57","v":0},{"$f":"'K90 - time schedule'!HD57","v":0},{"$f":"'K90 - time schedule'!HE57","v":0},{"$f":"'K90 - time schedule'!HF57","v":0},{"$f":"'K90 - time schedule'!HG57","v":0},{"$f":"'K90 - time schedule'!HH57","v":0},{"$f":"'K90 - time schedule'!HI57","v":0},{"$f":"'K90 - time schedule'!HJ57","v":0},{"$f":"'K90 - time schedule'!HK57","v":0},{"$f":"'K90 - time schedule'!HL57","v":0},{"$f":"'K90 - time schedule'!HM57","v":0},{"$f":"'K90 - time schedule'!HN57","v":0},{"$f":"'K90 - time schedule'!HO57","v":0},{"$f":"'K90 - time schedule'!HP57","v":0},{"$f":"'K90 - time schedule'!HQ57","v":0},{"$f":"'K90 - time schedule'!HR57","v":0},{"$f":"'K90 - time schedule'!HS57","v":0},{"$f":"'K90 - time schedule'!HT57","v":0},{"$f":"'K90 - time schedule'!HU57","v":0},{"$f":"'K90 - time schedule'!HV57","v":0},{"$f":"'K90 - time schedule'!HW57","v":0},{"$f":"'K90 - time schedule'!HX57","v":0},{"$f":"'K90 - time schedule'!HY57","v":0},{"$f":"'K90 - time schedule'!HZ57","v":0},{"$f":"'K90 - time schedule'!IA57","v":0},{"$f":"'K90 - time schedule'!IB57","v":0},{"$f":"'K90 - time schedule'!IC57","v":0},{"$f":"'K90 - time schedule'!ID57","v":0},{"$f":"'K90 - time schedule'!IE57","v":0},{"$f":"'K90 - time schedule'!IF57","v":0},{"$f":"'K90 - time schedule'!IG57","v":0},{"$f":"'K90 - time schedule'!IH57","v":0},{"$f":"'K90 - time schedule'!II57","v":0},{"$f":"'K90 - time schedule'!IJ57","v":0},{"$f":"'K90 - time schedule'!IK57","v":0},{"$f":"'K90 - time schedule'!IL57","v":0},{"$f":"'K90 - time schedule'!IM57","v":0},{"$f":"'K90 - time schedule'!IN57","v":0},{"$f":"'K90 - time schedule'!IO57","v":0},{"$f":"'K90 - time schedule'!IP57","v":0},{"$f":"'K90 - time schedule'!IQ57","v":0},{"$f":"'K90 - time schedule'!IR57","v":0},{"$f":"'K90 - time schedule'!IS57","v":0},{"$f":"'K90 - time schedule'!IT57","v":0},{"$f":"'K90 - time schedule'!IU57","v":0},{"$f":"'K90 - time schedule'!IV57","v":0},{"$f":"'K90 - time schedule'!IW57","v":0},{"$f":"'K90 - time schedule'!IX57","v":0},{"$f":"'K90 - time schedule'!IY57","v":0},{"$f":"'K90 - time schedule'!IZ57","v":0},{"$f":"'K90 - time schedule'!JA57","v":0},{"$f":"'K90 - time schedule'!JB57","v":0},{"$f":"'K90 - time schedule'!JC57","v":0},{"$f":"'K90 - time schedule'!JD57","v":0},{"$f":"'K90 - time schedule'!JE57","v":0},{"$f":"'K90 - time schedule'!JF57","v":0},{"$f":"'K90 - time schedule'!JG57","v":0},{"$f":"'K90 - time schedule'!JH57","v":0},{"$f":"'K90 - time schedule'!JI57","v":0},{"$f":"'K90 - time schedule'!JJ57","v":0},{"$f":"'K90 - time schedule'!JK57","v":0},{"$f":"'K90 - time schedule'!JL57","v":0},{"$f":"'K90 - time schedule'!JM57","v":0},{"$f":"'K90 - time schedule'!JN57","v":0},{"$f":"'K90 - time schedule'!JO57","v":0},{"$f":"'K90 - time schedule'!JP57","v":0},{"$f":"'K90 - time schedule'!JQ57","v":0},{"$f":"'K90 - time schedule'!JR57","v":0},{"$f":"'K90 - time schedule'!JS57","v":0},{"$f":"'K90 - time schedule'!JT57","v":0},{"$f":"'K90 - time schedule'!JU57","v":0},{"$f":"'K90 - time schedule'!JV57","v":0},{"$f":"'K90 - time schedule'!JW57","v":0},{"$f":"'K90 - time schedule'!JX57","v":0},{"$f":"'K90 - time schedule'!JY57","v":0},{"$f":"'K90 - time schedule'!JZ57","v":0},{"$f":"'K90 - time schedule'!KA57","v":0},{"$f":"'K90 - time schedule'!KB57","v":0},{"$f":"'K90 - time schedule'!KC57","v":0},{"$f":"'K90 - time schedule'!KD57","v":0},{"$f":"'K90 - time schedule'!KE57","v":0},{"$f":"'K90 - time schedule'!KF57","v":0},{"$f":"'K90 - time schedule'!KG57","v":0},{"$f":"'K90 - time schedule'!KH57","v":0},{"$f":"'K90 - time schedule'!KI57","v":0},{"$f":"'K90 - time schedule'!KJ57","v":0},{"$f":"'K90 - time schedule'!KK57","v":0},{"$f":"'K90 - time schedule'!KL57","v":0},{"$f":"'K90 - time schedule'!KM57","v":0},{"$f":"'K90 - time schedule'!KN57","v":0},{"$f":"'K90 - time schedule'!KO57","v":0},{"$f":"'K90 - time schedule'!KP57","v":0},{"$f":"'K90 - time schedule'!KQ57","v":0},{"$f":"'K90 - time schedule'!KR57","v":0},{"$f":"'K90 - time schedule'!KS57","v":0},{"$f":"'K90 - time schedule'!KT57","v":0}]
["Boiler room K90 - preliminary acceptance of the Work PAC","K90",{"$f":"'K90 - time schedule'!G59","v":0},{"$f":"'K90 - time schedule'!H59","v":0},{"$f":"'K90 - time schedule'!I59","v":0},{"$f":"'K90 - time schedule'!J59","v":0},{"$f":"'K90 - time schedule'!K59","v":0},{"$f":"'K90 - time schedule'!L59","v":0},{"$f":"'K90 - time schedule'!M59","v":0},{"$f":"'K90 - time schedule'!N59","v":0},{"$f":"'K90 - time schedule'!O59","v":0},{"$f":"'K90 - time schedule'!P59","v":0},{"$f":"'K90 - time schedule'!Q59","v":0},{"$f":"'K90 - time schedule'!R59","v":0},{"$f":"'K90 - time schedule'!S59","v":0},{"$f":"'K90 - time schedule'!T59","v":0},{"$f":"'K90 - time schedule'!U59","v":0},{"$f":"'K90 - time schedule'!V59","v":0},{"$f":"'K90 - time schedule'!W59","v":0},{"$f":"'K90 - time schedule'!X59","v":0},{"$f":"'K90 - time schedule'!Y59","v":0},{"$f":"'K90 - time schedule'!Z59","v":0},{"$f":"'K90 - time schedule'!AA59","v":0},{"$f":"'K90 - time schedule'!AB59","v":0},{"$f":"'K90 - time schedule'!AC59","v":0},{"$f":"'K90 - time schedule'!AD59","v":0},{"$f":"'K90 - time schedule'!AE59","v":0},{"$f":"'K90 - time schedule'!AF59","v":0},{"$f":"'K90 - time schedule'!AG59","v":0},{"$f":"'K90 - time schedule'!AH59","v":0},{"$f":"'K90 - time schedule'!AI59","v":0},{"$f":"'K90 - time schedule'!AJ59","v":0},{"$f":"'K90 - time schedule'!AK59","v":0},{"$f":"'K90 - time schedule'!AL59","v":0},{"$f":"'K90 - time schedule'!AM59","v":0},{"$f":"'K90 - time schedule'!AN59","v":0},{"$f":"'K90 - time schedule'!AO59","v":0},{"$f":"'K90 - time schedule'!AP59","v":0},{"$f":"'K90 - time schedule'!AQ59","v":0},{"$f":"'K90 - time schedule'!AR59","v":0},{"$f":"'K90 - time schedule'!AS59","v":0},{"$f":"'K90 - time schedule'!AT59","v":0},{"$f":"'K90 - time schedule'!AU59","v":0},{"$f":"'K90 - time schedule'!AV59","v":0},{"$f":"'K90 - time schedule'!AW59","v":0},{"$f":"'K90 - time schedule'!AX59","v":0},{"$f":"'K90 - time schedule'!AY59","v":0},{"$f":"'K90 - time schedule'!AZ59","v":0},{"$f":"'K90 - time schedule'!BA59","v":0},{"$f":"'K90 - time schedule'!BB59","v":0},{"$f":"'K90 - time schedule'!BC59","v":0},{"$f":"'K90 - time schedule'!BD59","v":0},{"$f":"'K90 - time schedule'!BE59","v":0},{"$f":"'K90 - time schedule'!BF59","v":0},{"$f":"'K90 - time schedule'!BG59","v":0},{"$f":"'K90 - time schedule'!BH59","v":0},{"$f":"'K90 - time schedule'!BI59","v":0},{"$f":"'K90 - time schedule'!BJ59","v":0},{"$f":"'K90 - time schedule'!BK59","v":0},{"$f":"'K90 - time schedule'!BL59","v":0},{"$f":"'K90 - time schedule'!BM59","v":0},{"$f":"'K90 - time schedule'!BN59","v":0},{"$f":"'K90 - time schedule'!BO59","v":0},{"$f":"'K90 - time schedule'!BP59","v":0},{"$f":"'K90 - time schedule'!BQ59","v":0},{"$f":"'K90 - time schedule'!BR59","v":0},{"$f":"'K90 - time schedule'!BS59","v":0},{"$f":"'K90 - time schedule'!BT59","v":0},{"$f":"'K90 - time schedule'!BU59","v":0},{"$f":"'K90 - time schedule'!BV59","v":0},{"$f":"'K90 - time schedule'!BW59","v":0},{"$f":"'K90 - time schedule'!BX59","v":0},{"$f":"'K90 - time schedule'!BY59","v":0},{"$f":"'K90 - time schedule'!BZ59","v":0},{"$f":"'K90 - time schedule'!CA59","v":0},{"$f":"'K90 - time schedule'!CB59","v":0},{"$f":"'K90 - time schedule'!CC59","v":0},{"$f":"'K90 - time schedule'!CD59","v":0},{"$f":"'K90 - time schedule'!CE59","v":0},{"$f":"'K90 - time schedule'!CF59","v":0},{"$f":"'K90 - time schedule'!CG59","v":0},{"$f":"'K90 - time schedule'!CH59","v":0},{"$f":"'K90 - time schedule'!CI59","v":0},{"$f":"'K90 - time schedule'!CJ59","v":0},{"$f":"'K90 - time schedule'!CK59","v":0},{"$f":"'K90 - time schedule'!CL59","v":0},{"$f":"'K90 - time schedule'!CM59","v":0},{"$f":"'K90 - time schedule'!CN59","v":0},{"$f":"'K90 - time schedule'!CO59","v":0},{"$f":"'K90 - time schedule'!CP59","v":0},{"$f":"'K90 - time schedule'!CQ59","v":0},{"$f":"'K90 - time schedule'!CR59","v":0},{"$f":"'K90 - time schedule'!CS59","v":0},{"$f":"'K90 - time schedule'!CT59","v":0},{"$f":"'K90 - time schedule'!CU59","v":0},{"$f":"'K90 - time schedule'!CV59","v":0},{"$f":"'K90 - time schedule'!CW59","v":0},{"$f":"'K90 - time schedule'!CX59","v":0},{"$f":"'K90 - time schedule'!CY59","v":0},{"$f":"'K90 - time schedule'!CZ59","v":0},{"$f":"'K90 - time schedule'!DA59","v":0},{"$f":"'K90 - time schedule'!DB59","v":0},{"$f":"'K90 - time schedule'!DC59","v":0},{"$f":"'K90 - time schedule'!DD59","v":0},{"$f":"'K90 - time schedule'!DE59","v":0},{"$f":"'K90 - time schedule'!DF59","v":0},{"$f":"'K90 - time schedule'!DG59","v":0},{"$f":"'K90 - time schedule'!DH59","v":0},{"$f":"'K90 - time schedule'!DI59","v":0},{"$f":"'K90 - time schedule'!DJ59","v":0},{"$f":"'K90 - time schedule'!DK59","v":0},{"$f":"'K90 - time schedule'!DL59","v":0},{"$f":"'K90 - time schedule'!DM59","v":0},{"$f":"'K90 - time schedule'!DN59","v":0},{"$f":"'K90 - time schedule'!DO59","v":0},{"$f":"'K90 - time schedule'!DP59","v":0},{"$f":"'K90 - time schedule'!DQ59","v":0},{"$f":"'K90 - time schedule'!DR59","v":0},{"$f":"'K90 - time schedule'!DS59","v":0},{"$f":"'K90 - time schedule'!DT59","v":0},{"$f":"'K90 - time schedule'!DU59","v":0},{"$f":"'K90 - time schedule'!DV59","v":0},{"$f":"'K90 - time schedule'!DW59","v":0},{"$f":"'K90 - time schedule'!DX59","v":0},{"$f":"'K90 - time schedule'!DY59","v":0},{"$f":"'K90 - time schedule'!DZ59","v":0},{"$f":"'K90 - time schedule'!EA59","v":0},{"$f":"'K90 - time schedule'!EB59","v":0},{"$f":"'K90 - time schedule'!EC59","v":0},{"$f":"'K90 - time schedule'!ED59","v":0},{"$f":"'K90 - time schedule'!EE59","v":0},{"$f":"'K90 - time schedule'!EF59","v":0},{"$f":"'K90 - time schedule'!EG59","v":0},{"$f":"'K90 - time schedule'!EH59","v":0},{"$f":"'K90 - time schedule'!EI59","v":0},{"$f":"'K90 - time schedule'!EJ59","v":0},{"$f":"'K90 - time schedule'!EK59","v":0},{"$f":"'K90 - time schedule'!EL59","v":0},{"$f":"'K90 - time schedule'!EM59","v":0},{"$f":"'K90 - time schedule'!EN59","v":0},{"$f":"'K90 - time schedule'!EO59","v":0},{"$f":"'K90 - time schedule'!EP59","v":0},{"$f":"'K90 - time schedule'!EQ59","v":0},{"$f":"'K90 - time schedule'!ER59","v":0},{"$f":"'K90 - time schedule'!ES59","v":0},{"$f":"'K90 - time schedule'!ET59","v":0},{"$f":"'K90 - time schedule'!EU59","v":0},{"$f":"'K90 - time schedule'!EV59","v":0},{"$f":"'K90 - time schedule'!EW59","v":0},{"$f":"'K90 - time schedule'!EX59","v":0},{"$f":"'K90 - time schedule'!EY59","v":0},{"$f":"'K90 - time schedule'!EZ59","v":0},{"$f":"'K90 - time schedule'!FA59","v":0},{"$f":"'K90 - time schedule'!FB59","v":0},{"$f":"'K90 - time schedule'!FC59","v":0},{"$f":"'K90 - time schedule'!FD59","v":0},{"$f":"'K90 - time schedule'!FE59","v":0},{"$f":"'K90 - time schedule'!FF59","v":0},{"$f":"'K90 - time schedule'!FG59","v":0},{"$f":"'K90 - time schedule'!FH59","v":0},{"$f":"'K90 - time schedule'!FI59","v":0},{"$f":"'K90 - time schedule'!FJ59","v":0},{"$f":"'K90 - time schedule'!FK59","v":0},{"$f":"'K90 - time schedule'!FL59","v":0},{"$f":"'K90 - time schedule'!FM59","v":0},{"$f":"'K90 - time schedule'!FN59","v":0},{"$f":"'K90 - time schedule'!FO59","v":0},{"$f":"'K90 - time schedule'!FP59","v":0},{"$f":"'K90 - time schedule'!FQ59","v":0},{"$f":"'K90 - time schedule'!FR59","v":0},{"$f":"'K90 - time schedule'!FS59","v":0},{"$f":"'K90 - time schedule'!FT59","v":0},{"$f":"'K90 - time schedule'!FU59","v":0},{"$f":"'K90 - time schedule'!FV59","v":0},{"$f":"'K90 - time schedule'!FW59","v":0},{"$f":"'K90 - time schedule'!FX59","v":0},{"$f":"'K90 - time schedule'!FY59","v":0},{"$f":"'K90 - time schedule'!FZ59","v":0},{"$f":"'K90 - time schedule'!GA59","v":0},{"$f":"'K90 - time schedule'!GB59","v":0},{"$f":"'K90 - time schedule'!GC59","v":0},{"$f":"'K90 - time schedule'!GD59","v":0},{"$f":"'K90 - time schedule'!GE59","v":0},{"$f":"'K90 - time schedule'!GF59","v":0},{"$f":"'K90 - time schedule'!GG59","v":0},{"$f":"'K90 - time schedule'!GH59","v":0},{"$f":"'K90 - time schedule'!GI59","v":0},{"$f":"'K90 - time schedule'!GJ59","v":0},{"$f":"'K90 - time schedule'!GK59","v":0},{"$f":"'K90 - time schedule'!GL59","v":0},{"$f":"'K90 - time schedule'!GM59","v":0},{"$f":"'K90 - time schedule'!GN59","v":0},{"$f":"'K90 - time schedule'!GO59","v":0},{"$f":"'K90 - time schedule'!GP59","v":0},{"$f":"'K90 - time schedule'!GQ59","v":0},{"$f":"'K90 - time schedule'!GR59","v":0},{"$f":"'K90 - time schedule'!GS59","v":0},{"$f":"'K90 - time schedule'!GT59","v":0},{"$f":"'K90 - time schedule'!GU59","v":0},{"$f":"'K90 - time schedule'!GV59","v":0},{"$f":"'K90 - time schedule'!GW59","v":0},{"$f":"'K90 - time schedule'!GX59","v":0},{"$f":"'K90 - time schedule'!GY59","v":0},{"$f":"'K90 - time schedule'!GZ59","v":0},{"$f":"'K90 - time schedule'!HA59","v":0},{"$f":"'K90 - time schedule'!HB59","v":0},{"$f":"'K90 - time schedule'!HC59","v":0},{"$f":"'K90 - time schedule'!HD59","v":0},{"$f":"'K90 - time schedule'!HE59","v":0},{"$f":"'K90 - time schedule'!HF59","v":0},{"$f":"'K90 - time schedule'!HG59","v":0},{"$f":"'K90 - time schedule'!HH59","v":0},{"$f":"'K90 - time schedule'!HI59","v":0},{"$f":"'K90 - time schedule'!HJ59","v":0},{"$f":"'K90 - time schedule'!HK59","v":0},{"$f":"'K90 - time schedule'!HL59","v":0},{"$f":"'K90 - time schedule'!HM59","v":0},{"$f":"'K90 - time schedule'!HN59","v":0},{"$f":"'K90 - time schedule'!HO59","v":0},{"$f":"'K90 - time schedule'!HP59","v":0},{"$f":"'K90 - time schedule'!HQ59","v":0},{"$f":"'K90 - time schedule'!HR59","v":0},{"$f":"'K90 - time schedule'!HS59","v":0},{"$f":"'K90 - time schedule'!HT59","v":0},{"$f":"'K90 - time schedule'!HU59","v":0},{"$f":"'K90 - time schedule'!HV59","v":0},{"$f":"'K90 - time schedule'!HW59","v":0},{"$f":"'K90 - time schedule'!HX59","v":0},{"$f":"'K90 - time schedule'!HY59","v":0},{"$f":"'K90 - time schedule'!HZ59","v":0},{"$f":"'K90 - time schedule'!IA59","v":0},{"$f":"'K90 - time schedule'!IB59","v":0},{"$f":"'K90 - time schedule'!IC59","v":0},{"$f":"'K90 - time schedule'!ID59","v":0},{"$f":"'K90 - time schedule'!IE59","v":0},{"$f":"'K90 - time schedule'!IF59","v":0},{"$f":"'K90 - time schedule'!IG59","v":0},{"$f":"'K90 - time schedule'!IH59","v":0},{"$f":"'K90 - time schedule'!II59","v":0},{"$f":"'K90 - time schedule'!IJ59","v":0},{"$f":"'K90 - time schedule'!IK59","v":0},{"$f":"'K90 - time schedule'!IL59","v":0},{"$f":"'K90 - time schedule'!IM59","v":0},{"$f":"'K90 - time schedule'!IN59","v":0},{"$f":"'K90 - time schedule'!IO59","v":0},{"$f":"'K90 - time schedule'!IP59","v":0},{"$f":"'K90 - time schedule'!IQ59","v":0},{"$f":"'K90 - time schedule'!IR59","v":0},{"$f":"'K90 - time schedule'!IS59","v":0},{"$f":"'K90 - time schedule'!IT59","v":0},{"$f":"'K90 - time schedule'!IU59","v":0},{"$f":"'K90 - time schedule'!IV59","v":0},{"$f":"'K90 - time schedule'!IW59","v":0},{"$f":"'K90 - time schedule'!IX59","v":0},{"$f":"'K90 - time schedule'!IY59","v":0},{"$f":"'K90 - time schedule'!IZ59","v":0},{"$f":"'K90 - time schedule'!JA59","v":0},{"$f":"'K90 - time schedule'!JB59","v":0},{"$f":"'K90 - time schedule'!JC59","v":0},{"$f":"'K90 - time schedule'!JD59","v":0},{"$f":"'K90 - time schedule'!JE59","v":0},{"$f":"'K90 - time schedule'!JF59","v":0},{"$f":"'K90 - time schedule'!JG59","v":0},{"$f":"'K90 - time schedule'!JH59","v":0},{"$f":"'K90 - time schedule'!JI59","v":0},{"$f":"'K90 - time schedule'!JJ59","v":0},{"$f":"'K90 - time schedule'!JK59","v":0},{"$f":"'K90 - time schedule'!JL59","v":0},{"$f":"'K90 - time schedule'!JM59","v":0},{"$f":"'K90 - time schedule'!JN59","v":0},{"$f":"'K90 - time schedule'!JO59","v":0},{"$f":"'K90 - time schedule'!JP59","v":0},{"$f":"'K90 - time schedule'!JQ59","v":0},{"$f":"'K90 - time schedule'!JR59","v":0},{"$f":"'K90 - time schedule'!JS59","v":0},{"$f":"'K90 - time schedule'!JT59","v":0},{"$f":"'K90 - time schedule'!JU59","v":0},{"$f":"'K90 - time schedule'!JV59","v":0},{"$f":"'K90 - time schedule'!JW59","v":0},{"$f":"'K90 - time schedule'!JX59","v":0},{"$f":"'K90 - time schedule'!JY59","v":0},{"$f":"'K90 - time schedule'!JZ59","v":0},{"$f":"'K90 - time schedule'!KA59","v":0},{"$f":"'K90 - time schedule'!KB59","v":0},{"$f":"'K90 - time schedule'!KC59","v":0},{"$f":"'K90 - time schedule'!KD59","v":0},{"$f":"'K90 - time schedule'!KE59","v":0},{"$f":"'K90 - time schedule'!KF59","v":0},{"$f":"'K90 - time schedule'!KG59","v":0},{"$f":"'K90 - time schedule'!KH59","v":0},{"$f":"'K90 - time schedule'!KI59","v":0},{"$f":"'K90 - time schedule'!KJ59","v":0},{"$f":"'K90 - time schedule'!KK59","v":0},{"$f":"'K90 - time schedule'!KL59","v":0},{"$f":"'K90 - time schedule'!KM59","v":0},{"$f":"'K90 - time schedule'!KN59","v":0},{"$f":"'K90 - time schedule'!KO59","v":0},{"$f":"'K90 - time schedule'!KP59","v":0},{"$f":"'K90 - time schedule'!KQ59","v":0},{"$f":"'K90 - time schedule'!KR59","v":0},{"$f":"'K90 - time schedule'!KS59","v":0},{"$f":"'K90 - time schedule'!KT59","v":0}]
["Boiler room K90 - guarantee test B","K90",{"$f":"'K90 - time schedule'!G61","v":0},{"$f":"'K90 - time schedule'!H61","v":0},{"$f":"'K90 - time schedule'!I61","v":0},{"$f":"'K90 - time schedule'!J61","v":0},{"$f":"'K90 - time schedule'!K61","v":0},{"$f":"'K90 - time schedule'!L61","v":0},{"$f":"'K90 - time schedule'!M61","v":0},{"$f":"'K90 - time schedule'!N61","v":0},{"$f":"'K90 - time schedule'!O61","v":0},{"$f":"'K90 - time schedule'!P61","v":0},{"$f":"'K90 - time schedule'!Q61","v":0},{"$f":"'K90 - time schedule'!R61","v":0},{"$f":"'K90 - time schedule'!S61","v":0},{"$f":"'K90 - time schedule'!T61","v":0},{"$f":"'K90 - time schedule'!U61","v":0},{"$f":"'K90 - time schedule'!V61","v":0},{"$f":"'K90 - time schedule'!W61","v":0},{"$f":"'K90 - time schedule'!X61","v":0},{"$f":"'K90 - time schedule'!Y61","v":0},{"$f":"'K90 - time schedule'!Z61","v":0},{"$f":"'K90 - time schedule'!AA61","v":0},{"$f":"'K90 - time schedule'!AB61","v":0},{"$f":"'K90 - time schedule'!AC61","v":0},{"$f":"'K90 - time schedule'!AD61","v":0},{"$f":"'K90 - time schedule'!AE61","v":0},{"$f":"'K90 - time schedule'!AF61","v":0},{"$f":"'K90 - time schedule'!AG61","v":0},{"$f":"'K90 - time schedule'!AH61","v":0},{"$f":"'K90 - time schedule'!AI61","v":0},{"$f":"'K90 - time schedule'!AJ61","v":0},{"$f":"'K90 - time schedule'!AK61","v":0},{"$f":"'K90 - time schedule'!AL61","v":0},{"$f":"'K90 - time schedule'!AM61","v":0},{"$f":"'K90 - time schedule'!AN61","v":0},{"$f":"'K90 - time schedule'!AO61","v":0},{"$f":"'K90 - time schedule'!AP61","v":0},{"$f":"'K90 - time schedule'!AQ61","v":0},{"$f":"'K90 - time schedule'!AR61","v":0},{"$f":"'K90 - time schedule'!AS61","v":0},{"$f":"'K90 - time schedule'!AT61","v":0},{"$f":"'K90 - time schedule'!AU61","v":0},{"$f":"'K90 - time schedule'!AV61","v":0},{"$f":"'K90 - time schedule'!AW61","v":0},{"$f":"'K90 - time schedule'!AX61","v":0},{"$f":"'K90 - time schedule'!AY61","v":0},{"$f":"'K90 - time schedule'!AZ61","v":0},{"$f":"'K90 - time schedule'!BA61","v":0},{"$f":"'K90 - time schedule'!BB61","v":0},{"$f":"'K90 - time schedule'!BC61","v":0},{"$f":"'K90 - time schedule'!BD61","v":0},{"$f":"'K90 - time schedule'!BE61","v":0},{"$f":"'K90 - time schedule'!BF61","v":0},{"$f":"'K90 - time schedule'!BG61","v":0},{"$f":"'K90 - time schedule'!BH61","v":0},{"$f":"'K90 - time schedule'!BI61","v":0},{"$f":"'K90 - time schedule'!BJ61","v":0},{"$f":"'K90 - time schedule'!BK61","v":0},{"$f":"'K90 - time schedule'!BL61","v":0},{"$f":"'K90 - time schedule'!BM61","v":0},{"$f":"'K90 - time schedule'!BN61","v":0},{"$f":"'K90 - time schedule'!BO61","v":0},{"$f":"'K90 - time schedule'!BP61","v":0},{"$f":"'K90 - time schedule'!BQ61","v":0},{"$f":"'K90 - time schedule'!BR61","v":0},{"$f":"'K90 - time schedule'!BS61","v":0},{"$f":"'K90 - time schedule'!BT61","v":0},{"$f":"'K90 - time schedule'!BU61","v":0},{"$f":"'K90 - time schedule'!BV61","v":0},{"$f":"'K90 - time schedule'!BW61","v":0},{"$f":"'K90 - time schedule'!BX61","v":0},{"$f":"'K90 - time schedule'!BY61","v":0},{"$f":"'K90 - time schedule'!BZ61","v":0},{"$f":"'K90 - time schedule'!CA61","v":0},{"$f":"'K90 - time schedule'!CB61","v":0},{"$f":"'K90 - time schedule'!CC61","v":0},{"$f":"'K90 - time schedule'!CD61","v":0},{"$f":"'K90 - time schedule'!CE61","v":0},{"$f":"'K90 - time schedule'!CF61","v":0},{"$f":"'K90 - time schedule'!CG61","v":0},{"$f":"'K90 - time schedule'!CH61","v":0},{"$f":"'K90 - time schedule'!CI61","v":0},{"$f":"'K90 - time schedule'!CJ61","v":0},{"$f":"'K90 - time schedule'!CK61","v":0},{"$f":"'K90 - time schedule'!CL61","v":0},{"$f":"'K90 - time schedule'!CM61","v":0},{"$f":"'K90 - time schedule'!CN61","v":0},{"$f":"'K90 - time schedule'!CO61","v":0},{"$f":"'K90 - time schedule'!CP61","v":0},{"$f":"'K90 - time schedule'!CQ61","v":0},{"$f":"'K90 - time schedule'!CR61","v":0},{"$f":"'K90 - time schedule'!CS61","v":0},{"$f":"'K90 - time schedule'!CT61","v":0},{"$f":"'K90 - time schedule'!CU61","v":0},{"$f":"'K90 - time schedule'!CV61","v":0},{"$f":"'K90 - time schedule'!CW61","v":0},{"$f":"'K90 - time schedule'!CX61","v":0},{"$f":"'K90 - time schedule'!CY61","v":0},{"$f":"'K90 - time schedule'!CZ61","v":0},{"$f":"'K90 - time schedule'!DA61","v":0},{"$f":"'K90 - time schedule'!DB61","v":0},{"$f":"'K90 - time schedule'!DC61","v":0},{"$f":"'K90 - time schedule'!DD61","v":0},{"$f":"'K90 - time schedule'!DE61","v":0},{"$f":"'K90 - time schedule'!DF61","v":0},{"$f":"'K90 - time schedule'!DG61","v":0},{"$f":"'K90 - time schedule'!DH61","v":0},{"$f":"'K90 - time schedule'!DI61","v":0},{"$f":"'K90 - time schedule'!DJ61","v":0},{"$f":"'K90 - time schedule'!DK61","v":0},{"$f":"'K90 - time schedule'!DL61","v":0},{"$f":"'K90 - time schedule'!DM61","v":0},{"$f":"'K90 - time schedule'!DN61","v":0},{"$f":"'K90 - time schedule'!DO61","v":0},{"$f":"'K90 - time schedule'!DP61","v":0},{"$f":"'K90 - time schedule'!DQ61","v":0},{"$f":"'K90 - time schedule'!DR61","v":0},{"$f":"'K90 - time schedule'!DS61","v":0},{"$f":"'K90 - time schedule'!DT61","v":0},{"$f":"'K90 - time schedule'!DU61","v":0},{"$f":"'K90 - time schedule'!DV61","v":0},{"$f":"'K90 - time schedule'!DW61","v":0},{"$f":"'K90 - time schedule'!DX61","v":0},{"$f":"'K90 - time schedule'!DY61","v":0},{"$f":"'K90 - time schedule'!DZ61","v":0},{"$f":"'K90 - time schedule'!EA61","v":0},{"$f":"'K90 - time schedule'!EB61","v":0},{"$f":"'K90 - time schedule'!EC61","v":0},{"$f":"'K90 - time schedule'!ED61","v":0},{"$f":"'K90 - time schedule'!EE61","v":0},{"$f":"'K90 - time schedule'!EF61","v":0},{"$f":"'K90 - time schedule'!EG61","v":0},{"$f":"'K90 - time schedule'!EH61","v":0},{"$f":"'K90 - time schedule'!EI61","v":0},{"$f":"'K90 - time schedule'!EJ61","v":0},{"$f":"'K90 - time schedule'!EK61","v":0},{"$f":"'K90 - time schedule'!EL61","v":0},{"$f":"'K90 - time schedule'!EM61","v":0},{"$f":"'K90 - time schedule'!EN61","v":0},{"$f":"'K90 - time schedule'!EO61","v":0},{"$f":"'K90 - time schedule'!EP61","v":0},{"$f":"'K90 - time schedule'!EQ61","v":0},{"$f":"'K90 - time schedule'!ER61","v":0},{"$f":"'K90 - time schedule'!ES61","v":0},{"$f":"'K90 - time schedule'!ET61","v":0},{"$f":"'K90 - time schedule'!EU61","v":0},{"$f":"'K90 - time schedule'!EV61","v":0},{"$f":"'K90 - time schedule'!EW61","v":0},{"$f":"'K90 - time schedule'!EX61","v":0},{"$f":"'K90 - time schedule'!EY61","v":0},{"$f":"'K90 - time schedule'!EZ61","v":0},{"$f":"'K90 - time schedule'!FA61","v":0},{"$f":"'K90 - time schedule'!FB61","v":0},{"$f":"'K90 - time schedule'!FC61","v":0},{"$f":"'K90 - time schedule'!FD61","v":0},{"$f":"'K90 - time schedule'!FE61","v":0},{"$f":"'K90 - time schedule'!FF61","v":0},{"$f":"'K90 - time schedule'!FG61","v":0},{"$f":"'K90 - time schedule'!FH61","v":0},{"$f":"'K90 - time schedule'!FI61","v":0},{"$f":"'K90 - time schedule'!FJ61","v":0},{"$f":"'K90 - time schedule'!FK61","v":0},{"$f":"'K90 - time schedule'!FL61","v":0},{"$f":"'K90 - time schedule'!FM61","v":0},{"$f":"'K90 - time schedule'!FN61","v":0},{"$f":"'K90 - time schedule'!FO61","v":0},{"$f":"'K90 - time schedule'!FP61","v":0},{"$f":"'K90 - time schedule'!FQ61","v":0},{"$f":"'K90 - time schedule'!FR61","v":0},{"$f":"'K90 - time schedule'!FS61","v":0},{"$f":"'K90 - time schedule'!FT61","v":0},{"$f":"'K90 - time schedule'!FU61","v":0},{"$f":"'K90 - time schedule'!FV61","v":0},{"$f":"'K90 - time schedule'!FW61","v":0},{"$f":"'K90 - time schedule'!FX61","v":0},{"$f":"'K90 - time schedule'!FY61","v":0},{"$f":"'K90 - time schedule'!FZ61","v":0},{"$f":"'K90 - time schedule'!GA61","v":0},{"$f":"'K90 - time schedule'!GB61","v":0},{"$f":"'K90 - time schedule'!GC61","v":0},{"$f":"'K90 - time schedule'!GD61","v":0},{"$f":"'K90 - time schedule'!GE61","v":0},{"$f":"'K90 - time schedule'!GF61","v":0},{"$f":"'K90 - time schedule'!GG61","v":0},{"$f":"'K90 - time schedule'!GH61","v":0},{"$f":"'K90 - time schedule'!GI61","v":0},{"$f":"'K90 - time schedule'!GJ61","v":0},{"$f":"'K90 - time schedule'!GK61","v":0},{"$f":"'K90 - time schedule'!GL61","v":0},{"$f":"'K90 - time schedule'!GM61","v":0},{"$f":"'K90 - time schedule'!GN61","v":0},{"$f":"'K90 - time schedule'!GO61","v":0},{"$f":"'K90 - time schedule'!GP61","v":0},{"$f":"'K90 - time schedule'!GQ61","v":0},{"$f":"'K90 - time schedule'!GR61","v":0},{"$f":"'K90 - time schedule'!GS61","v":0},{"$f":"'K90 - time schedule'!GT61","v":0},{"$f":"'K90 - time schedule'!GU61","v":0},{"$f":"'K90 - time schedule'!GV61","v":0},{"$f":"'K90 - time schedule'!GW61","v":0},{"$f":"'K90 - time schedule'!GX61","v":0},{"$f":"'K90 - time schedule'!GY61","v":0},{"$f":"'K90 - time schedule'!GZ61","v":0},{"$f":"'K90 - time schedule'!HA61","v":0},{"$f":"'K90 - time schedule'!HB61","v":0},{"$f":"'K90 - time schedule'!HC61","v":0},{"$f":"'K90 - time schedule'!HD61","v":0},{"$f":"'K90 - time schedule'!HE61","v":0},{"$f":"'K90 - time schedule'!HF61","v":0},{"$f":"'K90 - time schedule'!HG61","v":0},{"$f":"'K90 - time schedule'!HH61","v":0},{"$f":"'K90 - time schedule'!HI61","v":0},{"$f":"'K90 - time schedule'!HJ61","v":0},{"$f":"'K90 - time schedule'!HK61","v":0},{"$f":"'K90 - time schedule'!HL61","v":0},{"$f":"'K90 - time schedule'!HM61","v":0},{"$f":"'K90 - time schedule'!HN61","v":0},{"$f":"'K90 - time schedule'!HO61","v":0},{"$f":"'K90 - time schedule'!HP61","v":0},{"$f":"'K90 - time schedule'!HQ61","v":0},{"$f":"'K90 - time schedule'!HR61","v":0},{"$f":"'K90 - time schedule'!HS61","v":0},{"$f":"'K90 - time schedule'!HT61","v":0},{"$f":"'K90 - time schedule'!HU61","v":0},{"$f":"'K90 - time schedule'!HV61","v":0},{"$f":"'K90 - time schedule'!HW61","v":0},{"$f":"'K90 - time schedule'!HX61","v":0},{"$f":"'K90 - time schedule'!HY61","v":0},{"$f":"'K90 - time schedule'!HZ61","v":0},{"$f":"'K90 - time schedule'!IA61","v":0},{"$f":"'K90 - time schedule'!IB61","v":0},{"$f":"'K90 - time schedule'!IC61","v":0},{"$f":"'K90 - time schedule'!ID61","v":0},{"$f":"'K90 - time schedule'!IE61","v":0},{"$f":"'K90 - time schedule'!IF61","v":0},{"$f":"'K90 - time schedule'!IG61","v":0},{"$f":"'K90 - time schedule'!IH61","v":0},{"$f":"'K90 - time schedule'!II61","v":0},{"$f":"'K90 - time schedule'!IJ61","v":0},{"$f":"'K90 - time schedule'!IK61","v":0},{"$f":"'K90 - time schedule'!IL61","v":0},{"$f":"'K90 - time schedule'!IM61","v":0},{"$f":"'K90 - time schedule'!IN61","v":0},{"$f":"'K90 - time schedule'!IO61","v":0},{"$f":"'K90 - time schedule'!IP61","v":0},{"$f":"'K90 - time schedule'!IQ61","v":0},{"$f":"'K90 - time schedule'!IR61","v":0},{"$f":"'K90 - time schedule'!IS61","v":0},{"$f":"'K90 - time schedule'!IT61","v":0},{"$f":"'K90 - time schedule'!IU61","v":0},{"$f":"'K90 - time schedule'!IV61","v":0},{"$f":"'K90 - time schedule'!IW61","v":0},{"$f":"'K90 - time schedule'!IX61","v":0},{"$f":"'K90 - time schedule'!IY61","v":0},{"$f":"'K90 - time schedule'!IZ61","v":0},{"$f":"'K90 - time schedule'!JA61","v":0},{"$f":"'K90 - time schedule'!JB61","v":0},{"$f":"'K90 - time schedule'!JC61","v":0},{"$f":"'K90 - time schedule'!JD61","v":0},{"$f":"'K90 - time schedule'!JE61","v":0},{"$f":"'K90 - time schedule'!JF61","v":0},{"$f":"'K90 - time schedule'!JG61","v":0},{"$f":"'K90 - time schedule'!JH61","v":0},{"$f":"'K90 - time schedule'!JI61","v":0},{"$f":"'K90 - time schedule'!JJ61","v":0},{"$f":"'K90 - time schedule'!JK61","v":0},{"$f":"'K90 - time schedule'!JL61","v":0},{"$f":"'K90 - time schedule'!JM61","v":0},{"$f":"'K90 - time schedule'!JN61","v":0},{"$f":"'K90 - time schedule'!JO61","v":0},{"$f":"'K90 - time schedule'!JP61","v":0},{"$f":"'K90 - time schedule'!JQ61","v":0},{"$f":"'K90 - time schedule'!JR61","v":0},{"$f":"'K90 - time schedule'!JS61","v":0},{"$f":"'K90 - time schedule'!JT61","v":0},{"$f":"'K90 - time schedule'!JU61","v":0},{"$f":"'K90 - time schedule'!JV61","v":0},{"$f":"'K90 - time schedule'!JW61","v":0},{"$f":"'K90 - time schedule'!JX61","v":0},{"$f":"'K90 - time schedule'!JY61","v":0},{"$f":"'K90 - time schedule'!JZ61","v":0},{"$f":"'K90 - time schedule'!KA61","v":0},{"$f":"'K90 - time schedule'!KB61","v":0},{"$f":"'K90 - time schedule'!KC61","v":0},{"$f":"'K90 - time schedule'!KD61","v":0},{"$f":"'K90 - time schedule'!KE61","v":0},{"$f":"'K90 - time schedule'!KF61","v":0},{"$f":"'K90 - time schedule'!KG61","v":0},{"$f":"'K90 - time schedule'!KH61","v":0},{"$f":"'K90 - time schedule'!KI61","v":0},{"$f":"'K90 - time schedule'!KJ61","v":0},{"$f":"'K90 - time schedule'!KK61","v":0},{"$f":"'K90 - time schedule'!KL61","v":0},{"$f":"'K90 - time schedule'!KM61","v":0},{"$f":"'K90 - time schedule'!KN61","v":0},{"$f":"'K90 - time schedule'!KO61","v":0},{"$f":"'K90 - time schedule'!KP61","v":0},{"$f":"'K90 - time schedule'!KQ61","v":0},{"$f":"'K90 - time schedule'!KR61","v":0},{"$f":"'K90 - time schedule'!KS61","v":0},{"$f":"'K90 - time schedule'!KT61","v":0}]
["Boiler room K90 - final acceptance of the Work FAC","K90",{"$f":"'K90 - time schedule'!G63","v":0},{"$f":"'K90 - time schedule'!H63","v":0},{"$f":"'K90 - time schedule'!I63","v":0},{"$f":"'K90 - time schedule'!J63","v":0},{"$f":"'K90 - time schedule'!K63","v":0},{"$f":"'K90 - time schedule'!L63","v":0},{"$f":"'K90 - time schedule'!M63","v":0},{"$f":"'K90 - time schedule'!N63","v":0},{"$f":"'K90 - time schedule'!O63","v":0},{"$f":"'K90 - time schedule'!P63","v":0},{"$f":"'K90 - time schedule'!Q63","v":0},{"$f":"'K90 - time schedule'!R63","v":0},{"$f":"'K90 - time schedule'!S63","v":0},{"$f":"'K90 - time schedule'!T63","v":0},{"$f":"'K90 - time schedule'!U63","v":0},{"$f":"'K90 - time schedule'!V63","v":0},{"$f":"'K90 - time schedule'!W63","v":0},{"$f":"'K90 - time schedule'!X63","v":0},{"$f":"'K90 - time schedule'!Y63","v":0},{"$f":"'K90 - time schedule'!Z63","v":0},{"$f":"'K90 - time schedule'!AA63","v":0},{"$f":"'K90 - time schedule'!AB63","v":0},{"$f":"'K90 - time schedule'!AC63","v":0},{"$f":"'K90 - time schedule'!AD63","v":0},{"$f":"'K90 - time schedule'!AE63","v":0},{"$f":"'K90 - time schedule'!AF63","v":0},{"$f":"'K90 - time schedule'!AG63","v":0},{"$f":"'K90 - time schedule'!AH63","v":0},{"$f":"'K90 - time schedule'!AI63","v":0},{"$f":"'K90 - time schedule'!AJ63","v":0},{"$f":"'K90 - time schedule'!AK63","v":0},{"$f":"'K90 - time schedule'!AL63","v":0},{"$f":"'K90 - time schedule'!AM63","v":0},{"$f":"'K90 - time schedule'!AN63","v":0},{"$f":"'K90 - time schedule'!AO63","v":0},{"$f":"'K90 - time schedule'!AP63","v":0},{"$f":"'K90 - time schedule'!AQ63","v":0},{"$f":"'K90 - time schedule'!AR63","v":0},{"$f":"'K90 - time schedule'!AS63","v":0},{"$f":"'K90 - time schedule'!AT63","v":0},{"$f":"'K90 - time schedule'!AU63","v":0},{"$f":"'K90 - time schedule'!AV63","v":0},{"$f":"'K90 - time schedule'!AW63","v":0},{"$f":"'K90 - time schedule'!AX63","v":0},{"$f":"'K90 - time schedule'!AY63","v":0},{"$f":"'K90 - time schedule'!AZ63","v":0},{"$f":"'K90 - time schedule'!BA63","v":0},{"$f":"'K90 - time schedule'!BB63","v":0},{"$f":"'K90 - time schedule'!BC63","v":0},{"$f":"'K90 - time schedule'!BD63","v":0},{"$f":"'K90 - time schedule'!BE63","v":0},{"$f":"'K90 - time schedule'!BF63","v":0},{"$f":"'K90 - time schedule'!BG63","v":0},{"$f":"'K90 - time schedule'!BH63","v":0},{"$f":"'K90 - time schedule'!BI63","v":0},{"$f":"'K90 - time schedule'!BJ63","v":0},{"$f":"'K90 - time schedule'!BK63","v":0},{"$f":"'K90 - time schedule'!BL63","v":0},{"$f":"'K90 - time schedule'!BM63","v":0},{"$f":"'K90 - time schedule'!BN63","v":0},{"$f":"'K90 - time schedule'!BO63","v":0},{"$f":"'K90 - time schedule'!BP63","v":0},{"$f":"'K90 - time schedule'!BQ63","v":0},{"$f":"'K90 - time schedule'!BR63","v":0},{"$f":"'K90 - time schedule'!BS63","v":0},{"$f":"'K90 - time schedule'!BT63","v":0},{"$f":"'K90 - time schedule'!BU63","v":0},{"$f":"'K90 - time schedule'!BV63","v":0},{"$f":"'K90 - time schedule'!BW63","v":0},{"$f":"'K90 - time schedule'!BX63","v":0},{"$f":"'K90 - time schedule'!BY63","v":0},{"$f":"'K90 - time schedule'!BZ63","v":0},{"$f":"'K90 - time schedule'!CA63","v":0},{"$f":"'K90 - time schedule'!CB63","v":0},{"$f":"'K90 - time schedule'!CC63","v":0},{"$f":"'K90 - time schedule'!CD63","v":0},{"$f":"'K90 - time schedule'!CE63","v":0},{"$f":"'K90 - time schedule'!CF63","v":0},{"$f":"'K90 - time schedule'!CG63","v":0},{"$f":"'K90 - time schedule'!CH63","v":0},{"$f":"'K90 - time schedule'!CI63","v":0},{"$f":"'K90 - time schedule'!CJ63","v":0},{"$f":"'K90 - time schedule'!CK63","v":0},{"$f":"'K90 - time schedule'!CL63","v":0},{"$f":"'K90 - time schedule'!CM63","v":0},{"$f":"'K90 - time schedule'!CN63","v":0},{"$f":"'K90 - time schedule'!CO63","v":0},{"$f":"'K90 - time schedule'!CP63","v":0},{"$f":"'K90 - time schedule'!CQ63","v":0},{"$f":"'K90 - time schedule'!CR63","v":0},{"$f":"'K90 - time schedule'!CS63","v":0},{"$f":"'K90 - time schedule'!CT63","v":0},{"$f":"'K90 - time schedule'!CU63","v":0},{"$f":"'K90 - time schedule'!CV63","v":0},{"$f":"'K90 - time schedule'!CW63","v":0},{"$f":"'K90 - time schedule'!CX63","v":0},{"$f":"'K90 - time schedule'!CY63","v":0},{"$f":"'K90 - time schedule'!CZ63","v":0},{"$f":"'K90 - time schedule'!DA63","v":0},{"$f":"'K90 - time schedule'!DB63","v":0},{"$f":"'K90 - time schedule'!DC63","v":0},{"$f":"'K90 - time schedule'!DD63","v":0},{"$f":"'K90 - time schedule'!DE63","v":0},{"$f":"'K90 - time schedule'!DF63","v":0},{"$f":"'K90 - time schedule'!DG63","v":0},{"$f":"'K90 - time schedule'!DH63","v":0},{"$f":"'K90 - time schedule'!DI63","v":0},{"$f":"'K90 - time schedule'!DJ63","v":0},{"$f":"'K90 - time schedule'!DK63","v":0},{"$f":"'K90 - time schedule'!DL63","v":0},{"$f":"'K90 - time schedule'!DM63","v":0},{"$f":"'K90 - time schedule'!DN63","v":0},{"$f":"'K90 - time schedule'!DO63","v":0},{"$f":"'K90 - time schedule'!DP63","v":0},{"$f":"'K90 - time schedule'!DQ63","v":0},{"$f":"'K90 - time schedule'!DR63","v":0},{"$f":"'K90 - time schedule'!DS63","v":0},{"$f":"'K90 - time schedule'!DT63","v":0},{"$f":"'K90 - time schedule'!DU63","v":0},{"$f":"'K90 - time schedule'!DV63","v":0},{"$f":"'K90 - time schedule'!DW63","v":0},{"$f":"'K90 - time schedule'!DX63","v":0},{"$f":"'K90 - time schedule'!DY63","v":0},{"$f":"'K90 - time schedule'!DZ63","v":0},{"$f":"'K90 - time schedule'!EA63","v":0},{"$f":"'K90 - time schedule'!EB63","v":0},{"$f":"'K90 - time schedule'!EC63","v":0},{"$f":"'K90 - time schedule'!ED63","v":0},{"$f":"'K90 - time schedule'!EE63","v":0},{"$f":"'K90 - time schedule'!EF63","v":0},{"$f":"'K90 - time schedule'!EG63","v":0},{"$f":"'K90 - time schedule'!EH63","v":0},{"$f":"'K90 - time schedule'!EI63","v":0},{"$f":"'K90 - time schedule'!EJ63","v":0},{"$f":"'K90 - time schedule'!EK63","v":0},{"$f":"'K90 - time schedule'!EL63","v":0},{"$f":"'K90 - time schedule'!EM63","v":0},{"$f":"'K90 - time schedule'!EN63","v":0},{"$f":"'K90 - time schedule'!EO63","v":0},{"$f":"'K90 - time schedule'!EP63","v":0},{"$f":"'K90 - time schedule'!EQ63","v":0},{"$f":"'K90 - time schedule'!ER63","v":0},{"$f":"'K90 - time schedule'!ES63","v":0},{"$f":"'K90 - time schedule'!ET63","v":0},{"$f":"'K90 - time schedule'!EU63","v":0},{"$f":"'K90 - time schedule'!EV63","v":0},{"$f":"'K90 - time schedule'!EW63","v":0},{"$f":"'K90 - time schedule'!EX63","v":0},{"$f":"'K90 - time schedule'!EY63","v":0},{"$f":"'K90 - time schedule'!EZ63","v":0},{"$f":"'K90 - time schedule'!FA63","v":0},{"$f":"'K90 - time schedule'!FB63","v":0},{"$f":"'K90 - time schedule'!FC63","v":0},{"$f":"'K90 - time schedule'!FD63","v":0},{"$f":"'K90 - time schedule'!FE63","v":0},{"$f":"'K90 - time schedule'!FF63","v":0},{"$f":"'K90 - time schedule'!FG63","v":0},{"$f":"'K90 - time schedule'!FH63","v":0},{"$f":"'K90 - time schedule'!FI63","v":0},{"$f":"'K90 - time schedule'!FJ63","v":0},{"$f":"'K90 - time schedule'!FK63","v":0},{"$f":"'K90 - time schedule'!FL63","v":0},{"$f":"'K90 - time schedule'!FM63","v":0},{"$f":"'K90 - time schedule'!FN63","v":0},{"$f":"'K90 - time schedule'!FO63","v":0},{"$f":"'K90 - time schedule'!FP63","v":0},{"$f":"'K90 - time schedule'!FQ63","v":0},{"$f":"'K90 - time schedule'!FR63","v":0},{"$f":"'K90 - time schedule'!FS63","v":0},{"$f":"'K90 - time schedule'!FT63","v":0},{"$f":"'K90 - time schedule'!FU63","v":0},{"$f":"'K90 - time schedule'!FV63","v":0},{"$f":"'K90 - time schedule'!FW63","v":0},{"$f":"'K90 - time schedule'!FX63","v":0},{"$f":"'K90 - time schedule'!FY63","v":0},{"$f":"'K90 - time schedule'!FZ63","v":0},{"$f":"'K90 - time schedule'!GA63","v":0},{"$f":"'K90 - time schedule'!GB63","v":0},{"$f":"'K90 - time schedule'!GC63","v":0},{"$f":"'K90 - time schedule'!GD63","v":0},{"$f":"'K90 - time schedule'!GE63","v":0},{"$f":"'K90 - time schedule'!GF63","v":0},{"$f":"'K90 - time schedule'!GG63","v":0},{"$f":"'K90 - time schedule'!GH63","v":0},{"$f":"'K90 - time schedule'!GI63","v":0},{"$f":"'K90 - time schedule'!GJ63","v":0},{"$f":"'K90 - time schedule'!GK63","v":0},{"$f":"'K90 - time schedule'!GL63","v":0},{"$f":"'K90 - time schedule'!GM63","v":0},{"$f":"'K90 - time schedule'!GN63","v":0},{"$f":"'K90 - time schedule'!GO63","v":0},{"$f":"'K90 - time schedule'!GP63","v":0},{"$f":"'K90 - time schedule'!GQ63","v":0},{"$f":"'K90 - time schedule'!GR63","v":0},{"$f":"'K90 - time schedule'!GS63","v":0},{"$f":"'K90 - time schedule'!GT63","v":0},{"$f":"'K90 - time schedule'!GU63","v":0},{"$f":"'K90 - time schedule'!GV63","v":0},{"$f":"'K90 - time schedule'!GW63","v":0},{"$f":"'K90 - time schedule'!GX63","v":0},{"$f":"'K90 - time schedule'!GY63","v":0},{"$f":"'K90 - time schedule'!GZ63","v":0},{"$f":"'K90 - time schedule'!HA63","v":0},{"$f":"'K90 - time schedule'!HB63","v":0},{"$f":"'K90 - time schedule'!HC63","v":0},{"$f":"'K90 - time schedule'!HD63","v":0},{"$f":"'K90 - time schedule'!HE63","v":0},{"$f":"'K90 - time schedule'!HF63","v":0},{"$f":"'K90 - time schedule'!HG63","v":0},{"$f":"'K90 - time schedule'!HH63","v":0},{"$f":"'K90 - time schedule'!HI63","v":0},{"$f":"'K90 - time schedule'!HJ63","v":0},{"$f":"'K90 - time schedule'!HK63","v":0},{"$f":"'K90 - time schedule'!HL63","v":0},{"$f":"'K90 - time schedule'!HM63","v":0},{"$f":"'K90 - time schedule'!HN63","v":0},{"$f":"'K90 - time schedule'!HO63","v":0},{"$f":"'K90 - time schedule'!HP63","v":0},{"$f":"'K90 - time schedule'!HQ63","v":0},{"$f":"'K90 - time schedule'!HR63","v":0},{"$f":"'K90 - time schedule'!HS63","v":0},{"$f":"'K90 - time schedule'!HT63","v":0},{"$f":"'K90 - time schedule'!HU63","v":0},{"$f":"'K90 - time schedule'!HV63","v":0},{"$f":"'K90 - time schedule'!HW63","v":0},{"$f":"'K90 - time schedule'!HX63","v":0},{"$f":"'K90 - time schedule'!HY63","v":0},{"$f":"'K90 - time schedule'!HZ63","v":0},{"$f":"'K90 - time schedule'!IA63","v":0},{"$f":"'K90 - time schedule'!IB63","v":0},{"$f":"'K90 - time schedule'!IC63","v":0},{"$f":"'K90 - time schedule'!ID63","v":0},{"$f":"'K90 - time schedule'!IE63","v":0},{"$f":"'K90 - time schedule'!IF63","v":0},{"$f":"'K90 - time schedule'!IG63","v":0},{"$f":"'K90 - time schedule'!IH63","v":0},{"$f":"'K90 - time schedule'!II63","v":0},{"$f":"'K90 - time schedule'!IJ63","v":0},{"$f":"'K90 - time schedule'!IK63","v":0},{"$f":"'K90 - time schedule'!IL63","v":0},{"$f":"'K90 - time schedule'!IM63","v":0},{"$f":"'K90 - time schedule'!IN63","v":0},{"$f":"'K90 - time schedule'!IO63","v":0},{"$f":"'K90 - time schedule'!IP63","v":0},{"$f":"'K90 - time schedule'!IQ63","v":0},{"$f":"'K90 - time schedule'!IR63","v":0},{"$f":"'K90 - time schedule'!IS63","v":0},{"$f":"'K90 - time schedule'!IT63","v":0},{"$f":"'K90 - time schedule'!IU63","v":0},{"$f":"'K90 - time schedule'!IV63","v":0},{"$f":"'K90 - time schedule'!IW63","v":0},{"$f":"'K90 - time schedule'!IX63","v":0},{"$f":"'K90 - time schedule'!IY63","v":0},{"$f":"'K90 - time schedule'!IZ63","v":0},{"$f":"'K90 - time schedule'!JA63","v":0},{"$f":"'K90 - time schedule'!JB63","v":0},{"$f":"'K90 - time schedule'!JC63","v":0},{"$f":"'K90 - time schedule'!JD63","v":0},{"$f":"'K90 - time schedule'!JE63","v":0},{"$f":"'K90 - time schedule'!JF63","v":0},{"$f":"'K90 - time schedule'!JG63","v":0},{"$f":"'K90 - time schedule'!JH63","v":0},{"$f":"'K90 - time schedule'!JI63","v":0},{"$f":"'K90 - time schedule'!JJ63","v":0},{"$f":"'K90 - time schedule'!JK63","v":0},{"$f":"'K90 - time schedule'!JL63","v":0},{"$f":"'K90 - time schedule'!JM63","v":0},{"$f":"'K90 - time schedule'!JN63","v":0},{"$f":"'K90 - time schedule'!JO63","v":0},{"$f":"'K90 - time schedule'!JP63","v":0},{"$f":"'K90 - time schedule'!JQ63","v":0},{"$f":"'K90 - time schedule'!JR63","v":0},{"$f":"'K90 - time schedule'!JS63","v":0},{"$f":"'K90 - time schedule'!JT63","v":0},{"$f":"'K90 - time schedule'!JU63","v":0},{"$f":"'K90 - time schedule'!JV63","v":0},{"$f":"'K90 - time schedule'!JW63","v":0},{"$f":"'K90 - time schedule'!JX63","v":0},{"$f":"'K90 - time schedule'!JY63","v":0},{"$f":"'K90 - time schedule'!JZ63","v":0},{"$f":"'K90 - time schedule'!KA63","v":0},{"$f":"'K90 - time schedule'!KB63","v":0},{"$f":"'K90 - time schedule'!KC63","v":0},{"$f":"'K90 - time schedule'!KD63","v":0},{"$f":"'K90 - time schedule'!KE63","v":0},{"$f":"'K90 - time schedule'!KF63","v":0},{"$f":"'K90 - time schedule'!KG63","v":0},{"$f":"'K90 - time schedule'!KH63","v":0},{"$f":"'K90 - time schedule'!KI63","v":0},{"$f":"'K90 - time schedule'!KJ63","v":0},{"$f":"'K90 - time schedule'!KK63","v":0},{"$f":"'K90 - time schedule'!KL63","v":0},{"$f":"'K90 - time schedule'!KM63","v":0},{"$f":"'K90 - time schedule'!KN63","v":0},{"$f":"'K90 - time schedule'!KO63","v":0},{"$f":"'K90 - time schedule'!KP63","v":0},{"$f":"'K90 - time schedule'!KQ63","v":0},{"$f":"'K90 - time schedule'!KR63","v":0},{"$f":"'K90 - time schedule'!KS63","v":0},{"$f":"'K90 - time schedule'!KT63","v":0}]
["Závazné technické parametry pro OB 1 (Palivové hospodářství) "]
["Notes:"]
["The Contractor does not fill in any values on this sheet. The values are transfered from previous sheets."]
["Předání a převzetí staveniště pro K20"]
["neobsazeno"]
["Kotelna K20 - vlastní kotel včetně všech komponentů"]
["Kotelna K20 - provozní zásobníky paliva včetně dopravy štěpky do kotle"]
["Kotelna K20 - ventilátory (vzduchové, spalinové, recirkulační) včetně vnitřních spalinovodů"]
["Kotelna K20 - tkaninový filtr"]
["Kotelna K20 - technologie DSI"]
["Kotelna K20 - popelové hospodářství"]
["Kotelna K20 - elektroinstalace"]
["Kotelna K20 - ASŘ"]
["Kotelna K20 - kompresorová stanice"]
["Kotelna K20 - připojení médií"]
["Kotelna K20 - venkovní rozvody spalinovodů včetně napojení na komín"]
["Kotelna K20 - venkovní konstrukce potrubního mostu (připojení popelového hospodářství a SNCR)"]
["Kotelna K20 - opláštění a zastřešení, dokončení všech stavebních činností"]
["Kotelna K20 - další výše nevyjmenované položky"]
["Kotelna K20 - dokončení stavebních prací"]
["Kotelna K20 - ukončení montážních prací"]
["Kotelna K20 - školení zaměstnanců provozu"]
["Kotelna K20 - příprava ke kompexnímu vyzkoušení"]
["Kotelna K20 - komplexní vyzkoušení"]
["Kotelna K20 - zkušební provoz"]
["Kotelna K20 - garanční test A"]
["Kotelna K20 - předběžné převzetí díla PAC"]
["Kotelna K20 - garanční test B"]
["Kotelna K20 - finální převzetí díla FAC"]

{"sheet":"consideration - time schedule","index":25,"n_rows":120,"n_cols":303,"rows_kept":120,"cut":false,"hidden":false,"merged":[[4,283,4,286],[4,287,4,290],[4,291,4,294],[4,295,4,298],[4,299,4,302],[85,3,85,302],[84,187,84,190],[84,291,84,294],[84,295,84,298],[84,299,84,302],[4,247,4,250],[4,251,4,254],[4,255,4,258],[4,259,4,262],[4,263,4,266],[4,267,4,270],[4,271,4,274],[4,275,4,278],[4,279,4,282],[4,211,4,214],[4,215,4,218],[4,219,4,222],[4,223,4,226],[4,227,4,230],[4,231,4,234],[4,235,4,238],[4,239,4,242],[4,243,4,246],[3,0,5,0],[3,1,5,1],[3,2,5,2],[3,3,3,188],[4,3,4,6],[4,7,4,10],[4,11,4,14],[4,15,4,18],[4,43,4,46],[4,47,4,50],[4,51,4,54],[4,55,4,58],[4,59,4,62],[4,63,4,66],[4,19,4,22],[4,23,4,26],[4,27,4,30],[4,31,4,34],[4,35,4,38],[4,39,4,42],[4,91,4,94],[4,95,4,98],[4,99,4,102],[4,103,4,106],[4,107,4,110],[4,111,4,114],[4,67,4,70],[4,71,4,74],[4,75,4,78],[4,79,4,82],[4,83,4,86],[4,87,4,90],[4,139,4,142],[4,143,4,146],[4,147,4,150],[4,151,4,154],[4,155,4,158],[4,159,4,162],[4,115,4,118],[4,119,4,122],[4,123,4,126],[4,127,4,130],[4,131,4,134],[4,135,4,138],[4,191,4,194],[4,195,4,198],[4,199,4,202],[4,203,4,206],[4,207,4,210],[4,163,4,166],[4,167,4,170],[4,171,4,174],[4,175,4,178],[4,179,4,182],[4,183,4,186],[4,187,4,190],[83,0,83,2],[84,0,84,2],[84,3,84,6],[84,31,84,34],[84,35,84,38],[84,39,84,42],[84,43,84,46],[84,47,84,50],[84,51,84,54],[84,7,84,10],[84,11,84,14],[84,15,84,18],[84,19,84,22],[84,23,84,26],[84,27,84,30],[84,79,84,82],[84,83,84,86],[84,87,84,90],[84,91,84,94],[84,95,84,98],[84,99,84,102],[84,55,84,58],[84,59,84,62],[84,63,84,66],[84,67,84,70],[84,71,84,74],[84,75,84,78],[84,127,84,130],[84,131,84,134],[84,135,84,138],[84,139,84,142],[84,143,84,146],[84,147,84,150],[84,103,84,106],[84,107,84,110],[84,111,84,114],[84,115,84,118],[84,119,84,122],[84,123,84,126],[84,175,84,178],[84,179,84,182],[84,183,84,186],[84,191,84,194],[84,195,84,198],[84,151,84,154],[84,155,84,158],[84,159,84,162],[84,163,84,166],[84,167,84,170],[84,171,84,174],[84,271,84,274],[84,275,84,278],[84,279,84,282],[84,283,84,286],[84,287,84,290],[85,0,85,2],[84,247,84,250],[84,251,84,254],[84,255,84,258],[84,259,84,262],[84,263,84,266],[84,267,84,270],[84,223,84,226],[84,227,84,230],[84,231,84,234],[84,235,84,238],[84,239,84,242],[84,243,84,246],[84,199,84,202],[84,203,84,206],[84,207,84,210],[84,211,84,214],[84,215,84,218],[84,219,84,222]]}
[]
["Annex K to the Tender Documentation - price table and time schedule"]
[]
["Milestones","Stage","Price excl. VAT","Period"]
[null,null,null,"month 1",null,null,null,"month 2",null,null,null,"month 3",null,null,null,"month 4",null,null,null,"month 5",null,null,null,"month 6",null,null,null,"month 7",null,null,null,"month 8",null,null,null,"month 9",null,null,null,"month 10",null,null,null,"month 11",null,null,null,"month 12",null,null,null,"month 13",null,null,null,"month 14",null,null,null,"month 15",null,null,null,"month 16",null,null,null,"month 17",null,null,null,"month 18",null,null,null,"month 19",null,null,null,"month 20",null,null,null,"month 21",null,null,null,"month 22",null,null,null,"month 23",null,null,null,"month 24",null,null,null,"month 25",null,null,null,"month 26",null,null,null,"month 27",null,null,null,"month 28",null,null,null,"month 29",null,null,null,"month 30",null,null,null,"month 31",null,null,null,"month 32",null,null,null,"month 33",null,null,null,"month 34",null,null,null,"month 35",null,null,null,"month 36",null,null,null,"month 37",null,null,null,"month 38",null,null,null,"month 39",null,null,null,"month 40",null,null,null,"month 41",null,null,null,"month 42",null,null,null,"month 43",null,null,null,"month 44",null,null,null,"month 45",null,null,null,"month 46",null,null,null,"month 47",null,null,null,"month 48",null,null,null,"month 49",null,null,null,"month 50",null,null,null,"month 51",null,null,null,"month 52",null,null,null,"month 53",null,null,null,"month 54",null,null,null,"month 55",null,null,null,"month 56",null,null,null,"month 57",null,null,null,"month 58",null,null,null,"month 59",null,null,null,"month 60",null,null,null,"month 61",null,null,null,"month 62",null,null,null,"month 63",null,null,null,"month 64",null,null,null,"month 65",null,null,null,"month 66",null,null,null,"month 67",null,null,null,"month 68",null,null,null,"month 69",null,null,null,"month 70",null,null,null,"month 71",null,null,null,"month 72",null,null,null,"month 73",null,null,null,"month 74",null,null,null,"month 75"]
[null,null,null,"week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4","week 1","week 2","week 3","week 4"]
[1,1,null,1,2,3,4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,39,40,41,42,43,44,45,46,47,48,49,50,51,52,53,54,55,56,57,58,59,60,61,62,63,64,65,66,67,68,69,70,71,72,73,74,75,76,77,78,79,80,81,82,83,84,85,86,87,88,89,90,91,92,93,94,95,96,97,98,99,100,101,102,103,104,105,106,107,108,109,110,111,112,113,114,115,116,117,118,119,120,121,122,123,124,125,126,127,128,129,130,131,132,133,134,135,136,137,138,139,140,141,142,143,144,145,146,147,148,149,150,151,152,153,154,155,156,157,158,159,160,161,162,163,164,165,166,167,168,169,170,171,172,173,174,175,176,177,178,179,180,181,182,183,184,185,186,187,188,189,190,191,192,193,194,195,196,197,198,199,200,201,202,203,204,205,206,207,208,209,210,211,212,213,214,215,216,217,218,219,220,221,222,223,224,225,226,227,228,229,230,231,232,233,234,235,236,237,238,239,240,241,242,243,244,245,246,247,248,249,250,251,252,253,254,255,256,257,258,259,260,261,262,263,264,265,266,267,268,269,270,271,272,273,274,275,276,277,278,279,280,281,282,283,284,285,286,287,288,289,290,291,292,293,294,295,296,297,298,299,300]
["Boiler room K20 - binding technical specification for OB 6 (Construction)","K20","EUR",{"$f":"'K20 - time schedule'!G11","v":0},{"$f":"'K20 - time schedule'!H11","v":0},{"$f":"'K20 - time schedule'!I11","v":0},{"$f":"'K20 - time schedule'!J11","v":0},{"$f":"'K20 - time schedule'!K11","v":0},{"$f":"'K20 - time schedule'!L11","v":0},{"$f":"'K20 - time schedule'!M11","v":0},{"$f":"'K20 - time schedule'!N11","v":0},{"$f":"'K20 - time schedule'!O11","v":0},{"$f":"'K20 - time schedule'!P11","v":0},{"$f":"'K20 - time schedule'!Q11","v":0},{"$f":"'K20 - time schedule'!R11","v":0},{"$f":"'K20 - time schedule'!S11","v":0},{"$f":"'K20 - time schedule'!T11","v":0},{"$f":"'K20 - time schedule'!U11","v":0},{"$f":"'K20 - time schedule'!V11","v":0},{"$f":"'K20 - time schedule'!W11","v":0},{"$f":"'K20 - time schedule'!X11","v":0},{"$f":"'K20 - time schedule'!Y11","v":0},{"$f":"'K20 - time schedule'!Z11","v":0},{"$f":"'K20 - time schedule'!AA11","v":0},{"$f":"'K20 - time schedule'!AB11","v":0},{"$f":"'K20 - time schedule'!AC11","v":0},{"$f":"'K20 - time schedule'!AD11","v":0},{"$f":"'K20 - time schedule'!AE11","v":0},{"$f":"'K20 - time schedule'!AF11","v":0},{"$f":"'K20 - time schedule'!AG11","v":0},{"$f":"'K20 - time schedule'!AH11","v":0},{"$f":"'K20 - time schedule'!AI11","v":0},{"$f":"'K20 - time schedule'!AJ11","v":0},{"$f":"'K20 - time schedule'!AK11","v":0},{"$f":"'K20 - time schedule'!AL11","v":0},{"$f":"'K20 - time schedule'!AM11","v":0},{"$f":"'K20 - time schedule'!AN11","v":0},{"$f":"'K20 - time schedule'!AO11","v":0},{"$f":"'K20 - time schedule'!AP11","v":0},{"$f":"'K20 - time schedule'!AQ11","v":0},{"$f":"'K20 - time schedule'!AR11","v":0},{"$f":"'K20 - time schedule'!AS11","v":0},{"$f":"'K20 - time schedule'!AT11","v":0},{"$f":"'K20 - time schedule'!AU11","v":0},{"$f":"'K20 - time schedule'!AV11","v":0},{"$f":"'K20 - time schedule'!AW11","v":0},{"$f":"'K20 - time schedule'!AX11","v":0},{"$f":"'K20 - time schedule'!AY11","v":0},{"$f":"'K20 - time schedule'!AZ11","v":0},{"$f":"'K20 - time schedule'!BA11","v":0},{"$f":"'K20 - time schedule'!BB11","v":0},{"$f":"'K20 - time schedule'!BC11","v":0},{"$f":"'K20 - time schedule'!BD11","v":0},{"$f":"'K20 - time schedule'!BE11","v":0},{"$f":"'K20 - time schedule'!BF11","v":0},{"$f":"'K20 - time schedule'!BG11","v":0},{"$f":"'K20 - time schedule'!BH11","v":0},{"$f":"'K20 - time schedule'!BI11","v":0},{"$f":"'K20 - time schedule'!BJ11","v":0},{"$f":"'K20 - time schedule'!BK11","v":0},{"$f":"'K20 - time schedule'!BL11","v":0},{"$f":"'K20 - time schedule'!BM11","v":0},{"$f":"'K20 - time schedule'!BN11","v":0},{"$f":"'K20 - time schedule'!BO11","v":0},{"$f":"'K20 - time schedule'!BP11","v":0},{"$f":"'K20 - time schedule'!BQ11","v":0},{"$f":"'K20 - time schedule'!BR11","v":0},{"$f":"'K20 - time schedule'!BS11","v":0},{"$f":"'K20 - time schedule'!BT11","v":0},{"$f":"'K20 - time schedule'!BU11","v":0},{"$f":"'K20 - time schedule'!BV11","v":0},{"$f":"'K20 - time schedule'!BW11","v":0},{"$f":"'K20 - time schedule'!BX11","v":0},{"$f":"'K20 - time schedule'!BY11","v":0},{"$f":"'K20 - time schedule'!BZ11","v":0},{"$f":"'K20 - time schedule'!CA11","v":0},{"$f":"'K20 - time schedule'!CB11","v":0},{"$f":"'K20 - time schedule'!CC11","v":0},{"$f":"'K20 - time schedule'!CD11","v":0},{"$f":"'K20 - time schedule'!CE11","v":0},{"$f":"'K20 - time schedule'!CF11","v":0},{"$f":"'K20 - time schedule'!CG11","v":0},{"$f":"'K20 - time schedule'!CH11","v":0},{"$f":"'K20 - time schedule'!CI11","v":0},{"$f":"'K20 - time schedule'!CJ11","v":0},{"$f":"'K20 - time schedule'!CK11","v":0},{"$f":"'K20 - time schedule'!CL11","v":0},{"$f":"'K20 - time schedule'!CM11","v":0},{"$f":"'K20 - time schedule'!CN11","v":0},{"$f":"'K20 - time schedule'!CO11","v":0},{"$f":"'K20 - time schedule'!CP11","v":0},{"$f":"'K20 - time schedule'!CQ11","v":0},{"$f":"'K20 - time schedule'!CR11","v":0},{"$f":"'K20 - time schedule'!CS11","v":0},{"$f":"'K20 - time schedule'!CT11","v":0},{"$f":"'K20 - time schedule'!CU11","v":0},{"$f":"'K20 - time schedule'!CV11","v":0},{"$f":"'K20 - time schedule'!CW11","v":0},{"$f":"'K20 - time schedule'!CX11","v":0},{"$f":"'K20 - time schedule'!CY11","v":0},{"$f":"'K20 - time schedule'!CZ11","v":0},{"$f":"'K20 - time schedule'!DA11","v":0},{"$f":"'K20 - time schedule'!DB11","v":0},{"$f":"'K20 - time schedule'!DC11","v":0},{"$f":"'K20 - time schedule'!DD11","v":0},{"$f":"'K20 - time schedule'!DE11","v":0},{"$f":"'K20 - time schedule'!DF11","v":0},{"$f":"'K20 - time schedule'!DG11","v":0},{"$f":"'K20 - time schedule'!DH11","v":0},{"$f":"'K20 - time schedule'!DI11","v":0},{"$f":"'K20 - time schedule'!DJ11","v":0},{"$f":"'K20 - time schedule'!DK11","v":0},{"$f":"'K20 - time schedule'!DL11","v":0},{"$f":"'K20 - time schedule'!DM11","v":0},{"$f":"'K20 - time schedule'!DN11","v":0},{"$f":"'K20 - time schedule'!DO11","v":0},{"$f":"'K20 - time schedule'!DP11","v":0},{"$f":"'K20 - time schedule'!DQ11","v":0},{"$f":"'K20 - time schedule'!DR11","v":0},{"$f":"'K20 - time schedule'!DS11","v":0},{"$f":"'K20 - time schedule'!DT11","v":0},{"$f":"'K20 - time schedule'!DU11","v":0},{"$f":"'K20 - time schedule'!DV11","v":0},{"$f":"'K20 - time schedule'!DW11","v":0},{"$f":"'K20 - time schedule'!DX11","v":0},{"$f":"'K20 - time schedule'!DY11","v":0},{"$f":"'K20 - time schedule'!DZ11","v":0},{"$f":"'K20 - time schedule'!EA11","v":0},{"$f":"'K20 - time schedule'!EB11","v":0},{"$f":"'K20 - time schedule'!EC11","v":0},{"$f":"'K20 - time schedule'!ED11","v":0},{"$f":"'K20 - time schedule'!EE11","v":0},{"$f":"'K20 - time schedule'!EF11","v":0},{"$f":"'K20 - time schedule'!EG11","v":0},{"$f":"'K20 - time schedule'!EH11","v":0},{"$f":"'K20 - time schedule'!EI11","v":0},{"$f":"'K20 - time schedule'!EJ11","v":0},{"$f":"'K20 - time schedule'!EK11","v":0},{"$f":"'K20 - time schedule'!EL11","v":0},{"$f":"'K20 - time schedule'!EM11","v":0},{"$f":"'K20 - time schedule'!EN11","v":0},{"$f":"'K20 - time schedule'!EO11","v":0},{"$f":"'K20 - time schedule'!EP11","v":0},{"$f":"'K20 - time schedule'!EQ11","v":0},{"$f":"'K20 - time schedule'!ER11","v":0},{"$f":"'K20 - time schedule'!ES11","v":0},{"$f":"'K20 - time schedule'!ET11","v":0},{"$f":"'K20 - time schedule'!EU11","v":0},{"$f":"'K20 - time schedule'!EV11","v":0},{"$f":"'K20 - time schedule'!EW11","v":0},{"$f":"'K20 - time schedule'!EX11","v":0},{"$f":"'K20 - time schedule'!EY11","v":0},{"$f":"'K20 - time schedule'!EZ11","v":0},{"$f":"'K20 - time schedule'!FA11","v":0},{"$f":"'K20 - time schedule'!FB11","v":0},{"$f":"'K20 - time schedule'!FC11","v":0},{"$f":"'K20 - time schedule'!FD11","v":0},{"$f":"'K20 - time schedule'!FE11","v":0},{"$f":"'K20 - time schedule'!FF11","v":0},{"$f":"'K20 - time schedule'!FG11","v":0},{"$f":"'K20 - time schedule'!FH11","v":0},{"$f":"'K20 - time schedule'!FI11","v":0},{"$f":"'K20 - time schedule'!FJ11","v":0},{"$f":"'K20 - time schedule'!FK11","v":0},{"$f":"'K20 - time schedule'!FL11","v":0},{"$f":"'K20 - time schedule'!FM11","v":0},{"$f":"'K20 - time schedule'!FN11","v":0},{"$f":"'K20 - time schedule'!FO11","v":0},{"$f":"'K20 - time schedule'!FP11","v":0},{"$f":"'K20 - time schedule'!FQ11","v":0},{"$f":"'K20 - time schedule'!FR11","v":0},{"$f":"'K20 - time schedule'!FS11","v":0},{"$f":"'K20 - time schedule'!FT11","v":0},{"$f":"'K20 - time schedule'!FU11","v":0},{"$f":"'K20 - time schedule'!FV11","v":0},{"$f":"'K20 - time schedule'!FW11","v":0},{"$f":"'K20 - time schedule'!FX11","v":0},{"$f":"'K20 - time schedule'!FY11","v":0},{"$f":"'K20 - time schedule'!FZ11","v":0},{"$f":"'K20 - time schedule'!GA11","v":0},{"$f":"'K20 - time schedule'!GB11","v":0},{"$f":"'K20 - time schedule'!GC11","v":0},{"$f":"'K20 - time schedule'!GD11","v":0},{"$f":"'K20 - time schedule'!GE11","v":0},{"$f":"'K20 - time schedule'!GF11","v":0},{"$f":"'K20 - time schedule'!GG11","v":0},{"$f":"'K20 - time schedule'!GH11","v":0},{"$f":"'K20 - time schedule'!GI11","v":0},{"$f":"'K20 - time schedule'!GJ11","v":0},{"$f":"'K20 - time schedule'!GK11","v":0},{"$f":"'K20 - time schedule'!GL11","v":0},{"$f":"'K20 - time schedule'!GM11","v":0},{"$f":"'K20 - time schedule'!GN11","v":0},{"$f":"'K20 - time schedule'!GO11","v":0},{"$f":"'K20 - time schedule'!GP11","v":0},{"$f":"'K20 - time schedule'!GQ11","v":0},{"$f":"'K20 - time schedule'!GR11","v":0},{"$f":"'K20 - time schedule'!GS11","v":0},{"$f":"'K20 - time schedule'!GT11","v":0},{"$f":"'K20 - time schedule'!GU11","v":0},{"$f":"'K20 - time schedule'!GV11","v":0},{"$f":"'K20 - time schedule'!GW11","v":0},{"$f":"'K20 - time schedule'!GX11","v":0},{"$f":"'K20 - time schedule'!GY11","v":0},{"$f":"'K20 - time schedule'!GZ11","v":0},{"$f":"'K20 - time schedule'!HA11","v":0},{"$f":"'K20 - time schedule'!HB11","v":0},{"$f":"'K20 - time schedule'!HC11","v":0},{"$f":"'K20 - time schedule'!HD11","v":0},{"$f":"'K20 - time schedule'!HE11","v":0},{"$f":"'K20 - time schedule'!HF11","v":0},{"$f":"'K20 - time schedule'!HG11","v":0},{"$f":"'K20 - time schedule'!HH11","v":0},{"$f":"'K20 - time schedule'!HI11","v":0},{"$f":"'K20 - time schedule'!HJ11","v":0},{"$f":"'K20 - time schedule'!HK11","v":0},{"$f":"'K20 - time schedule'!HL11","v":0},{"$f":"'K20 - time schedule'!HM11","v":0},{"$f":"'K20 - time schedule'!HN11","v":0},{"$f":"'K20 - time schedule'!HO11","v":0},{"$f":"'K20 - time schedule'!HP11","v":0},{"$f":"'K20 - time schedule'!HQ11","v":0},{"$f":"'K20 - time schedule'!HR11","v":0},{"$f":"'K20 - time schedule'!HS11","v":0},{"$f":"'K20 - time schedule'!HT11","v":0},{"$f":"'K20 - time schedule'!HU11","v":0},{"$f":"'K20 - time schedule'!HV11","v":0},{"$f":"'K20 - time schedule'!HW11","v":0},{"$f":"'K20 - time schedule'!HX11","v":0},{"$f":"'K20 - time schedule'!HY11","v":0},{"$f":"'K20 - time schedule'!HZ11","v":0},{"$f":"'K20 - time schedule'!IA11","v":0},{"$f":"'K20 - time schedule'!IB11","v":0},{"$f":"'K20 - time schedule'!IC11","v":0},{"$f":"'K20 - time schedule'!ID11","v":0},{"$f":"'K20 - time schedule'!IE11","v":0},{"$f":"'K20 - time schedule'!IF11","v":0},{"$f":"'K20 - time schedule'!IG11","v":0},{"$f":"'K20 - time schedule'!IH11","v":0},{"$f":"'K20 - time schedule'!II11","v":0},{"$f":"'K20 - time schedule'!IJ11","v":0},{"$f":"'K20 - time schedule'!IK11","v":0},{"$f":"'K20 - time schedule'!IL11","v":0},{"$f":"'K20 - time schedule'!IM11","v":0},{"$f":"'K20 - time schedule'!IN11","v":0},{"$f":"'K20 - time schedule'!IO11","v":0},{"$f":"'K20 - time schedule'!IP11","v":0},{"$f":"'K20 - time schedule'!IQ11","v":0},{"$f":"'K20 - time schedule'!IR11","v":0},{"$f":"'K20 - time schedule'!IS11","v":0},{"$f":"'K20 - time schedule'!IT11","v":0},{"$f":"'K20 - time schedule'!IU11","v":0},{"$f":"'K20 - time schedule'!IV11","v":0},{"$f":"'K20 - time schedule'!IW11","v":0},{"$f":"'K20 - time schedule'!IX11","v":0},{"$f":"'K20 - time schedule'!IY11","v":0},{"$f":"'K20 - time schedule'!IZ11","v":0},{"$f":"'K20 - time schedule'!JA11","v":0},{"$f":"'K20 - time schedule'!JB11","v":0},{"$f":"'K20 - time schedule'!JC11","v":0},{"$f":"'K20 - time schedule'!JD11","v":0},{"$f":"'K20 - time schedule'!JE11","v":0},{"$f":"'K20 - time schedule'!JF11","v":0},{"$f":"'K20 - time schedule'!JG11","v":0},{"$f":"'K20 - time schedule'!JH11","v":0},{"$f":"'K20 - time schedule'!JI11","v":0},{"$f":"'K20 - time schedule'!JJ11","v":0},{"$f":"'K20 - time schedule'!JK11","v":0},{"$f":"'K20 - time schedule'!JL11","v":0},{"$f":"'K20 - time schedule'!JM11","v":0},{"$f":"'K20 - time schedule'!JN11","v":0},{"$f":"'K20 - time schedule'!JO11","v":0},{"$f":"'K20 - time schedule'!JP11","v":0},{"$f":"'K20 - time schedule'!JQ11","v":0},{"$f":"'K20 - time schedule'!JR11","v":0},{"$f":"'K20 - time schedule'!JS11","v":0},{"$f":"'K20 - time schedule'!JT11","v":0},{"$f":"'K20 - time schedule'!JU11","v":0},{"$f":"'K20 - time schedule'!JV11","v":0},{"$f":"'K20 - time schedule'!JW11","v":0},{"$f":"'K20 - time schedule'!JX11","v":0},{"$f":"'K20 - time schedule'!JY11","v":0},{"$f":"'K20 - time schedule'!JZ11","v":0},{"$f":"'K20 - time schedule'!KA11","v":0},{"$f":"'K20 - time schedule'!KB11","v":0},{"$f":"'K20 - time schedule'!KC11","v":0},{"$f":"'K20 - time schedule'!KD11","v":0},{"$f":"'K20 - time schedule'!KE11","v":0},{"$f":"'K20 - time schedule'!KF11","v":0},{"$f":"'K20 - time schedule'!KG11","v":0},{"$f":"'K20 - time schedule'!KH11","v":0},{"$f":"'K20 - time schedule'!KI11","v":0},{"$f":"'K20 - time schedule'!KJ11","v":0},{"$f":"'K20 - time schedule'!KK11","v":0},{"$f":"'K20 - time schedule'!KL11","v":0},{"$f":"'K20 - time schedule'!KM11","v":0},{"$f":"'K20 - time schedule'!KN11","v":0},{"$f":"'K20 - time schedule'!KO11","v":0},{"$f":"'K20 - time schedule'!KP11","v":0},{"$f":"'K20 - time schedule'!KQ11","v":0},{"$f":"'K20 - time schedule'!KR11","v":0},{"$f":"'K20 - time schedule'!KS11","v":0},{"$f":"'K20 - time schedule'!KT11","v":0}]
["Boiler room K20 - binding technical specification for OB 1 (Fuel management) ","K20","EUR",{"$f":"'K20 - time schedule'!G13","v":0},{"$f":"'K20 - time schedule'!H13","v":0},{"$f":"'K20 - time schedule'!I13","v":0},{"$f":"'K20 - time schedule'!J13","v":0},{"$f":"'K20 - time schedule'!K13","v":0},{"$f":"'K20 - time schedule'!L13","v":0},{"$f":"'K20 - time schedule'!M13","v":0},{"$f":"'K20 - time schedule'!N13","v":0},{"$f":"'K20 - time schedule'!O13","v":0},{"$f":"'K20 - time schedule'!P13","v":0},{"$f":"'K20 - time schedule'!Q13","v":0},{"$f":"'K20 - time schedule'!R13","v":0},{"$f":"'K20 - time schedule'!S13","v":0},{"$f":"'K20 - time schedule'!T13","v":0},{"$f":"'K20 - time schedule'!U13","v":0},{"$f":"'K20 - time schedule'!V13","v":0},{"$f":"'K20 - time schedule'!W13","v":0},{"$f":"'K20 - time schedule'!X13","v":0},{"$f":"'K20 - time schedule'!Y13","v":0},{"$f":"'K20 - time schedule'!Z13","v":0},{"$f":"'K20 - time schedule'!AA13","v":0},{"$f":"'K20 - time schedule'!AB13","v":0},{"$f":"'K20 - time schedule'!AC13","v":0},{"$f":"'K20 - time schedule'!AD13","v":0},{"$f":"'K20 - time schedule'!AE13","v":0},{"$f":"'K20 - time schedule'!AF13","v":0},{"$f":"'K20 - time schedule'!AG13","v":0},{"$f":"'K20 - time schedule'!AH13","v":0},{"$f":"'K20 - time schedule'!AI13","v":0},{"$f":"'K20 - time schedule'!AJ13","v":0},{"$f":"'K20 - time schedule'!AK13","v":0},{"$f":"'K20 - time schedule'!AL13","v":0},{"$f":"'K20 - time schedule'!AM13","v":0},{"$f":"'K20 - time schedule'!AN13","v":0},{"$f":"'K20 - time schedule'!AO13","v":0},{"$f":"'K20 - time schedule'!AP13","v":0},{"$f":"'K20 - time schedule'!AQ13","v":0},{"$f":"'K20 - time schedule'!AR13","v":0},{"$f":"'K20 - time schedule'!AS13","v":0},{"$f":"'K20 - time schedule'!AT13","v":0},{"$f":"'K20 - time schedule'!AU13","v":0},{"$f":"'K20 - time schedule'!AV13","v":0},{"$f":"'K20 - time schedule'!AW13","v":0},{"$f":"'K20 - time schedule'!AX13","v":0},{"$f":"'K20 - time schedule'!AY13","v":0},{"$f":"'K20 - time schedule'!AZ13","v":0},{"$f":"'K20 - time schedule'!BA13","v":0},{"$f":"'K20 - time schedule'!BB13","v":0},{"$f":"'K20 - time schedule'!BC13","v":0},{"$f":"'K20 - time schedule'!BD13","v":0},{"$f":"'K20 - time schedule'!BE13","v":0},{"$f":"'K20 - time schedule'!BF13","v":0},{"$f":"'K20 - time schedule'!BG13","v":0},{"$f":"'K20 - time schedule'!BH13","v":0},{"$f":"'K20 - time schedule'!BI13","v":0},{"$f":"'K20 - time schedule'!BJ13","v":0},{"$f":"'K20 - time schedule'!BK13","v":0},{"$f":"'K20 - time schedule'!BL13","v":0},{"$f":"'K20 - time schedule'!BM13","v":0},{"$f":"'K20 - time schedule'!BN13","v":0},{"$f":"'K20 - time schedule'!BO13","v":0},{"$f":"'K20 - time schedule'!BP13","v":0},{"$f":"'K20 - time schedule'!BQ13","v":0},{"$f":"'K20 - time schedule'!BR13","v":0},{"$f":"'K20 - time schedule'!BS13","v":0},{"$f":"'K20 - time schedule'!BT13","v":0},{"$f":"'K20 - time schedule'!BU13","v":0},{"$f":"'K20 - time schedule'!BV13","v":0},{"$f":"'K20 - time schedule'!BW13","v":0},{"$f":"'K20 - time schedule'!BX13","v":0},{"$f":"'K20 - time schedule'!BY13","v":0},{"$f":"'K20 - time schedule'!BZ13","v":0},{"$f":"'K20 - time schedule'!CA13","v":0},{"$f":"'K20 - time schedule'!CB13","v":0},{"$f":"'K20 - time schedule'!CC13","v":0},{"$f":"'K20 - time schedule'!CD13","v":0},{"$f":"'K20 - time schedule'!CE13","v":0},{"$f":"'K20 - time schedule'!CF13","v":0},{"$f":"'K20 - time schedule'!CG13","v":0},{"$f":"'K20 - time schedule'!CH13","v":0},{"$f":"'K20 - time schedule'!CI13","v":0},{"$f":"'K20 - time schedule'!CJ13","v":0},{"$f":"'K20 - time schedule'!CK13","v":0},{"$f":"'K20 - time schedule'!CL13","v":0},{"$f":"'K20 - time schedule'!CM13","v":0},{"$f":"'K20 - time schedule'!CN13","v":0},{"$f":"'K20 - time schedule'!CO13","v":0},{"$f":"'K20 - time schedule'!CP13","v":0},{"$f":"'K20 - time schedule'!CQ13","v":0},{"$f":"'K20 - time schedule'!CR13","v":0},{"$f":"'K20 - time schedule'!CS13","v":0},{"$f":"'K20 - time schedule'!CT13","v":0},{"$f":"'K20 - time schedule'!CU13","v":0},{"$f":"'K20 - time schedule'!CV13","v":0},{"$f":"'K20 - time schedule'!CW13","v":0},{"$f":"'K20 - time schedule'!CX13","v":0},{"$f":"'K20 - time schedule'!CY13","v":0},{"$f":"'K20 - time schedule'!CZ13","v":0},{"$f":"'K20 - time schedule'!DA13","v":0},{"$f":"'K20 - time schedule'!DB13","v":0},{"$f":"'K20 - time schedule'!DC13","v":0},{"$f":"'K20 - time schedule'!DD13","v":0},{"$f":"'K20 - time schedule'!DE13","v":0},{"$f":"'K20 - time schedule'!DF13","v":0},{"$f":"'K20 - time schedule'!DG13","v":0},{"$f":"'K20 - time schedule'!DH13","v":0},{"$f":"'K20 - time schedule'!DI13","v":0},{"$f":"'K20 - time schedule'!DJ13","v":0},{"$f":"'K20 - time schedule'!DK13","v":0},{"$f":"'K20 - time schedule'!DL13","v":0},{"$f":"'K20 - time schedule'!DM13","v":0},{"$f":"'K20 - time schedule'!DN13","v":0},{"$f":"'K20 - time schedule'!DO13","v":0},{"$f":"'K20 - time schedule'!DP13","v":0},{"$f":"'K20 - time schedule'!DQ13","v":0},{"$f":"'K20 - time schedule'!DR13","v":0},{"$f":"'K20 - time schedule'!DS13","v":0},{"$f":"'K20 - time schedule'!DT13","v":0},{"$f":"'K20 - time schedule'!DU13","v":0},{"$f":"'K20 - time schedule'!DV13","v":0},{"$f":"'K20 - time schedule'!DW13","v":0},{"$f":"'K20 - time schedule'!DX13","v":0},{"$f":"'K20 - time schedule'!DY13","v":0},{"$f":"'K20 - time schedule'!DZ13","v":0},{"$f":"'K20 - time schedule'!EA13","v":0},{"$f":"'K20 - time schedule'!EB13","v":0},{"$f":"'K20 - time schedule'!EC13","v":0},{"$f":"'K20 - time schedule'!ED13","v":0},{"$f":"'K20 - time schedule'!EE13","v":0},{"$f":"'K20 - time schedule'!EF13","v":0},{"$f":"'K20 - time schedule'!EG13","v":0},{"$f":"'K20 - time schedule'!EH13","v":0},{"$f":"'K20 - time schedule'!EI13","v":0},{"$f":"'K20 - time schedule'!EJ13","v":0},{"$f":"'K20 - time schedule'!EK13","v":0},{"$f":"'K20 - time schedule'!EL13","v":0},{"$f":"'K20 - time schedule'!EM13","v":0},{"$f":"'K20 - time schedule'!EN13","v":0},{"$f":"'K20 - time schedule'!EO13","v":0},{"$f":"'K20 - time schedule'!EP13","v":0},{"$f":"'K20 - time schedule'!EQ13","v":0},{"$f":"'K20 - time schedule'!ER13","v":0},{"$f":"'K20 - time schedule'!ES13","v":0},{"$f":"'K20 - time schedule'!ET13","v":0},{"$f":"'K20 - time schedule'!EU13","v":0},{"$f":"'K20 - time schedule'!EV13","v":0},{"$f":"'K20 - time schedule'!EW13","v":0},{"$f":"'K20 - time schedule'!EX13","v":0},{"$f":"'K20 - time schedule'!EY13","v":0},{"$f":"'K20 - time schedule'!EZ13","v":0},{"$f":"'K20 - time schedule'!FA13","v":0},{"$f":"'K20 - time schedule'!FB13","v":0},{"$f":"'K20 - time schedule'!FC13","v":0},{"$f":"'K20 - time schedule'!FD13","v":0},{"$f":"'K20 - time schedule'!FE13","v":0},{"$f":"'K20 - time schedule'!FF13","v":0},{"$f":"'K20 - time schedule'!FG13","v":0},{"$f":"'K20 - time schedule'!FH13","v":0},{"$f":"'K20 - time schedule'!FI13","v":0},{"$f":"'K20 - time schedule'!FJ13","v":0},{"$f":"'K20 - time schedule'!FK13","v":0},{"$f":"'K20 - time schedule'!FL13","v":0},{"$f":"'K20 - time schedule'!FM13","v":0},{"$f":"'K20 - time schedule'!FN13","v":0},{"$f":"'K20 - time schedule'!FO13","v":0},{"$f":"'K20 - time schedule'!FP13","v":0},{"$f":"'K20 - time schedule'!FQ13","v":0},{"$f":"'K20 - time schedule'!FR13","v":0},{"$f":"'K20 - time schedule'!FS13","v":0},{"$f":"'K20 - time schedule'!FT13","v":0},{"$f":"'K20 - time schedule'!FU13","v":0},{"$f":"'K20 - time schedule'!FV13","v":0},{"$f":"'K20 - time schedule'!FW13","v":0},{"$f":"'K20 - time schedule'!FX13","v":0},{"$f":"'K20 - time schedule'!FY13","v":0},{"$f":"'K20 - time schedule'!FZ13","v":0},{"$f":"'K20 - time schedule'!GA13","v":0},{"$f":"'K20 - time schedule'!GB13","v":0},{"$f":"'K20 - time schedule'!GC13","v":0},{"$f":"'K20 - time schedule'!GD13","v":0},{"$f":"'K20 - time schedule'!GE13","v":0},{"$f":"'K20 - time schedule'!GF13","v":0},{"$f":"'K20 - time schedule'!GG12","v":0},{"$f":"'K20 - time schedule'!GH12","v":0},{"$f":"'K20 - time schedule'!GI12","v":0},{"$f":"'K20 - time schedule'!GJ12","v":0},{"$f":"'K20 - time schedule'!GK12","v":0},{"$f":"'K20 - time schedule'!GL12","v":0},{"$f":"'K20 - time schedule'!GM12","v":0},{"$f":"'K20 - time schedule'!GN12","v":0},{"$f":"'K20 - time schedule'!GO12","v":0},{"$f":"'K20 - time schedule'!GP12","v":0},{"$f":"'K20 - time schedule'!GQ12","v":0},{"$f":"'K20 - time schedule'!GR12","v":0},{"$f":"'K20 - time schedule'!GS12","v":0},{"$f":"'K20 - time schedule'!GT12","v":0},{"$f":"'K20 - time schedule'!GU12","v":0},{"$f":"'K20 - time schedule'!GV12","v":0},{"$f":"'K20 - time schedule'!GW12","v":0},{"$f":"'K20 - time schedule'!GX12","v":0},{"$f":"'K20 - time schedule'!GY12","v":0},{"$f":"'K20 - time schedule'!GZ12","v":0},{"$f":"'K20 - time schedule'!HA12","v":0},{"$f":"'K20 - time schedule'!HB12","v":0},{"$f":"'K20 - time schedule'!HC12","v":0},{"$f":"'K20 - time schedule'!HD12","v":0},{"$f":"'K20 - time schedule'!HE12","v":0},{"$f":"'K20 - time schedule'!HF12","v":0},{"$f":"'K20 - time schedule'!HG12","v":0},{"$f":"'K20 - time schedule'!HH12","v":0},{"$f":"'K20 - time schedule'!HI12","v":0},{"$f":"'K20 - time schedule'!HJ12","v":0},{"$f":"'K20 - time schedule'!HK12","v":0},{"$f":"'K20 - time schedule'!HL12","v":0},{"$f":"'K20 - time schedule'!HM12","v":0},{"$f":"'K20 - time schedule'!HN12","v":0},{"$f":"'K20 - time schedule'!HO12","v":0},{"$f":"'K20 - time schedule'!HP12","v":0},{"$f":"'K20 - time schedule'!HQ12","v":0},{"$f":"'K20 - time schedule'!HR12","v":0},{"$f":"'K20 - time schedule'!HS12","v":0},{"$f":"'K20 - time schedule'!HT12","v":0},{"$f":"'K20 - time schedule'!HU12","v":0},{"$f":"'K20 - time schedule'!HV12","v":0},{"$f":"'K20 - time schedule'!HW12","v":0},{"$f":"'K20 - time schedule'!HX12","v":0},{"$f":"'K20 - time schedule'!HY12","v":0},{"$f":"'K20 - time schedule'!HZ12","v":0},{"$f":"'K20 - time schedule'!IA12","v":0},{"$f":"'K20 - time schedule'!IB12","v":0},{"$f":"'K20 - time schedule'!IC12","v":0},{"$f":"'K20 - time schedule'!ID12","v":0},{"$f":"'K20 - time schedule'!IE12","v":0},{"$f":"'K20 - time schedule'!IF12","v":0},{"$f":"'K20 - time schedule'!IG12","v":0},{"$f":"'K20 - time schedule'!IH12","v":0},{"$f":"'K20 - time schedule'!II12","v":0},{"$f":"'K20 - time schedule'!IJ12","v":0},{"$f":"'K20 - time schedule'!IK12","v":0},{"$f":"'K20 - time schedule'!IL12","v":0},{"$f":"'K20 - time schedule'!IM12","v":0},{"$f":"'K20 - time schedule'!IN12","v":0},{"$f":"'K20 - time schedule'!IO12","v":0},{"$f":"'K20 - time schedule'!IP12","v":0},{"$f":"'K20 - time schedule'!IQ12","v":0},{"$f":"'K20 - time schedule'!IR12","v":0},{"$f":"'K20 - time schedule'!IS12","v":0},{"$f":"'K20 - time schedule'!IT12","v":0},{"$f":"'K20 - time schedule'!IU12","v":0},{"$f":"'K20 - time schedule'!IV12","v":0},{"$f":"'K20 - time schedule'!IW12","v":0},{"$f":"'K20 - time schedule'!IX12","v":0},{"$f":"'K20 - time schedule'!IY12","v":0},{"$f":"'K20 - time schedule'!IZ12","v":0},{"$f":"'K20 - time schedule'!JA12","v":0},{"$f":"'K20 - time schedule'!JB12","v":0},{"$f":"'K20 - time schedule'!JC12","v":0},{"$f":"'K20 - time schedule'!JD12","v":0},{"$f":"'K20 - time schedule'!JE12","v":0},{"$f":"'K20 - time schedule'!JF12","v":0},{"$f":"'K20 - time schedule'!JG12","v":0},{"$f":"'K20 - time schedule'!JH12","v":0},{"$f":"'K20 - time schedule'!JI12","v":0},{"$f":"'K20 - time schedule'!JJ12","v":0},{"$f":"'K20 - time schedule'!JK12","v":0},{"$f":"'K20 - time schedule'!JL12","v":0},{"$f":"'K20 - time schedule'!JM12","v":0},{"$f":"'K20 - time schedule'!JN12","v":0},{"$f":"'K20 - time schedule'!JO12","v":0},{"$f":"'K20 - time schedule'!JP12","v":0},{"$f":"'K20 - time schedule'!JQ12","v":0},{"$f":"'K20 - time schedule'!JR12","v":0},{"$f":"'K20 - time schedule'!JS12","v":0},{"$f":"'K20 - time schedule'!JT12","v":0},{"$f":"'K20 - time schedule'!JU12","v":0},{"$f":"'K20 - time schedule'!JV12","v":0},{"$f":"'K20 - time schedule'!JW12","v":0},{"$f":"'K20 - time schedule'!JX12","v":0},{"$f":"'K20 - time schedule'!JY12","v":0},{"$f":"'K20 - time schedule'!JZ12","v":0},{"$f":"'K20 - time schedule'!KA12","v":0},{"$f":"'K20 - time schedule'!KB12","v":0},{"$f":"'K20 - time schedule'!KC12","v":0},{"$f":"'K20 - time schedule'!KD12","v":0},{"$f":"'K20 - time schedule'!KE12","v":0},{"$f":"'K20 - time schedule'!KF12","v":0},{"$f":"'K20 - time schedule'!KG12","v":0},{"$f":"'K20 - time schedule'!KH12","v":0},{"$f":"'K20 - time schedule'!KI12","v":0},{"$f":"'K20 - time schedule'!KJ12","v":0},{"$f":"'K20 - time schedule'!KK12","v":0},{"$f":"'K20 - time schedule'!KL12","v":0},{"$f":"'K20 - time schedule'!KM12","v":0},{"$f":"'K20 - time schedule'!KN12","v":0},{"$f":"'K20 - time schedule'!KO12","v":0},{"$f":"'K20 - time schedule'!KP12","v":0},{"$f":"'K20 - time schedule'!KQ12","v":0},{"$f":"'K20 - time schedule'!KR12","v":0},{"$f":"'K20 - time schedule'!KS12","v":0},{"$f":"'K20 - time schedule'!KT12","v":0}]
["Boiler room K20 - binding technical specification for other OBs, for other suppliers of technological units ","K20","EUR",{"$f":"'K20 - time schedule'!G15","v":0},{"$f":"'K20 - time schedule'!H15","v":0},{"$f":"'K20 - time schedule'!I15","v":0},{"$f":"'K20 - time schedule'!J15","v":0},{"$f":"'K20 - time schedule'!K15","v":0},{"$f":"'K20 - time schedule'!L15","v":0},{"$f":"'K20 - time schedule'!M15","v":0},{"$f":"'K20 - time schedule'!N15","v":0},{"$f":"'K20 - time schedule'!O15","v":0},{"$f":"'K20 - time schedule'!P15","v":0},{"$f":"'K20 - time schedule'!Q15","v":0},{"$f":"'K20 - time schedule'!R15","v":0},{"$f":"'K20 - time schedule'!S15","v":0},{"$f":"'K20 - time schedule'!T15","v":0},{"$f":"'K20 - time schedule'!U15","v":0},{"$f":"'K20 - time schedule'!V15","v":0},{"$f":"'K20 - time schedule'!W15","v":0},{"$f":"'K20 - time schedule'!X15","v":0},{"$f":"'K20 - time schedule'!Y15","v":0},{"$f":"'K20 - time schedule'!Z15","v":0},{"$f":"'K20 - time schedule'!AA15","v":0},{"$f":"'K20 - time schedule'!AB15","v":0},{"$f":"'K20 - time schedule'!AC15","v":0},{"$f":"'K20 - time schedule'!AD15","v":0},{"$f":"'K20 - time schedule'!AE15","v":0},{"$f":"'K20 - time schedule'!AF15","v":0},{"$f":"'K20 - time schedule'!AG15","v":0},{"$f":"'K20 - time schedule'!AH15","v":0},{"$f":"'K20 - time schedule'!AI15","v":0},{"$f":"'K20 - time schedule'!AJ15","v":0},{"$f":"'K20 - time schedule'!AK15","v":0},{"$f":"'K20 - time schedule'!AL15","v":0},{"$f":"'K20 - time schedule'!AM15","v":0},{"$f":"'K20 - time schedule'!AN15","v":0},{"$f":"'K20 - time schedule'!AO15","v":0},{"$f":"'K20 - time schedule'!AP15","v":0},{"$f":"'K20 - time schedule'!AQ15","v":0},{"$f":"'K20 - time schedule'!AR15","v":0},{"$f":"'K20 - time schedule'!AS15","v":0},{"$f":"'K20 - time schedule'!AT15","v":0},{"$f":"'K20 - time schedule'!AU15","v":0},{"$f":"'K20 - time schedule'!AV15","v":0},{"$f":"'K20 - time schedule'!AW15","v":0},{"$f":"'K20 - time schedule'!AX15","v":0},{"$f":"'K20 - time schedule'!AY15","v":0},{"$f":"'K20 - time schedule'!AZ15","v":0},{"$f":"'K20 - time schedule'!BA15","v":0},{"$f":"'K20 - time schedule'!BB15","v":0},{"$f":"'K20 - time schedule'!BC15","v":0},{"$f":"'K20 - time schedule'!BD15","v":0},{"$f":"'K20 - time schedule'!BE15","v":0},{"$f":"'K20 - time schedule'!BF15","v":0},{"$f":"'K20 - time schedule'!BG15","v":0},{"$f":"'K20 - time schedule'!BH15","v":0},{"$f":"'K20 - time schedule'!BI15","v":0},{"$f":"'K20 - time schedule'!BJ15","v":0},{"$f":"'K20 - time schedule'!BK15","v":0},{"$f":"'K20 - time schedule'!BL15","v":0},{"$f":"'K20 - time schedule'!BM15","v":0},{"$f":"'K20 - time schedule'!BN15","v":0},{"$f":"'K20 - time schedule'!BO15","v":0},{"$f":"'K20 - time schedule'!BP15","v":0},{"$f":"'K20 - time schedule'!BQ15","v":0},{"$f":"'K20 - time schedule'!BR15","v":0},{"$f":"'K20 - time schedule'!BS15","v":0},{"$f":"'K20 - time schedule'!BT15","v":0},{"$f":"'K20 - time schedule'!BU15","v":0},{"$f":"'K20 - time schedule'!BV15","v":0},{"$f":"'K20 - time schedule'!BW15","v":0},{"$f":"'K20 - time schedule'!BX15","v":0},{"$f":"'K20 - time schedule'!BY15","v":0},{"$f":"'K20 - time schedule'!BZ15","v":0},{"$f":"'K20 - time schedule'!CA15","v":0},{"$f":"'K20 - time schedule'!CB15","v":0},{"$f":"'K20 - time schedule'!CC15","v":0},{"$f":"'K20 - time schedule'!CD15","v":0},{"$f":"'K20 - time schedule'!CE15","v":0},{"$f":"'K20 - time schedule'!CF15","v":0},{"$f":"'K20 - time schedule'!CG15","v":0},{"$f":"'K20 - time schedule'!CH15","v":0},{"$f":"'K20 - time schedule'!CI15","v":0},{"$f":"'K20 - time schedule'!CJ15","v":0},{"$f":"'K20 - time schedule'!CK15","v":0},{"$f":"'K20 - time schedule'!CL15","v":0},{"$f":"'K20 - time schedule'!CM15","v":0},{"$f":"'K20 - time schedule'!CN15","v":0},{"$f":"'K20 - time schedule'!CO15","v":0},{"$f":"'K20 - time schedule'!CP15","v":0},{"$f":"'K20 - time schedule'!CQ15","v":0},{"$f":"'K20 - time schedule'!CR15","v":0},{"$f":"'K20 - time schedule'!CS15","v":0},{"$f":"'K20 - time schedule'!CT15","v":0},{"$f":"'K20 - time schedule'!CU15","v":0},{"$f":"'K20 - time schedule'!CV15","v":0},{"$f":"'K20 - time schedule'!CW15","v":0},{"$f":"'K20 - time schedule'!CX15","v":0},{"$f":"'K20 - time schedule'!CY15","v":0},{"$f":"'K20 - time schedule'!CZ15","v":0},{"$f":"'K20 - time schedule'!DA15","v":0},{"$f":"'K20 - time schedule'!DB15","v":0},{"$f":"'K20 - time schedule'!DC15","v":0},{"$f":"'K20 - time schedule'!DD15","v":0},{"$f":"'K20 - time schedule'!DE15","v":0},{"$f":"'K20 - time schedule'!DF15","v":0},{"$f":"'K20 - time schedule'!DG15","v":0},{"$f":"'K20 - time schedule'!DH15","v":0},{"$f":"'K20 - time schedule'!DI15","v":0},{"$f":"'K20 - time schedule'!DJ15","v":0},{"$f":"'K20 - time schedule'!DK15","v":0},{"$f":"'K20 - time schedule'!DL15","v":0},{"$f":"'K20 - time schedule'!DM15","v":0},{"$f":"'K20 - time schedule'!DN15","v":0},{"$f":"'K20 - time schedule'!DO15","v":0},{"$f":"'K20 - time schedule'!DP15","v":0},{"$f":"'K20 - time schedule'!DQ15","v":0},{"$f":"'K20 - time schedule'!DR15","v":0},{"$f":"'K20 - time schedule'!DS15","v":0},{"$f":"'K20 - time schedule'!DT15","v":0},{"$f":"'K20 - time schedule'!DU15","v":0},{"$f":"'K20 - time schedule'!DV15","v":0},{"$f":"'K20 - time schedule'!DW15","v":0},{"$f":"'K20 - time schedule'!DX15","v":0},{"$f":"'K20 - time schedule'!DY15","v":0},{"$f":"'K20 - time schedule'!DZ15","v":0},{"$f":"'K20 - time schedule'!EA15","v":0},{"$f":"'K20 - time schedule'!EB15","v":0},{"$f":"'K20 - time schedule'!EC15","v":0},{"$f":"'K20 - time schedule'!ED15","v":0},{"$f":"'K20 - time schedule'!EE15","v":0},{"$f":"'K20 - time schedule'!EF15","v":0},{"$f":"'K20 - time schedule'!EG15","v":0},{"$f":"'K20 - time schedule'!EH15","v":0},{"$f":"'K20 - time schedule'!EI15","v":0},{"$f":"'K20 - time schedule'!EJ15","v":0},{"$f":"'K20 - time schedule'!EK15","v":0},{"$f":"'K20 - time schedule'!EL15","v":0},{"$f":"'K20 - time schedule'!EM15","v":0},{"$f":"'K20 - time schedule'!EN15","v":0},{"$f":"'K20 - time schedule'!EO15","v":0},{"$f":"'K20 - time schedule'!EP15","v":0},{"$f":"'K20 - time schedule'!EQ15","v":0},{"$f":"'K20 - time schedule'!ER15","v":0},{"$f":"'K20 - time schedule'!ES15","v":0},{"$f":"'K20 - time schedule'!ET15","v":0},{"$f":"'K20 - time schedule'!EU15","v":0},{"$f":"'K20 - time schedule'!EV15","v":0},{"$f":"'K20 - time schedule'!EW15","v":0},{"$f":"'K20 - time schedule'!EX15","v":0},{"$f":"'K20 - time schedule'!EY15","v":0},{"$f":"'K20 - time schedule'!EZ15","v":0},{"$f":"'K20 - time schedule'!FA15","v":0},{"$f":"'K20 - time schedule'!FB15","v":0},{"$f":"'K20 - time schedule'!FC15","v":0},{"$f":"'K20 - time schedule'!FD15","v":0},{"$f":"'K20 - time schedule'!FE15","v":0},{"$f":"'K20 - time schedule'!FF15","v":0},{"$f":"'K20 - time schedule'!FG15","v":0},{"$f":"'K20 - time schedule'!FH15","v":0},{"$f":"'K20 - time schedule'!FI15","v":0},{"$f":"'K20 - time schedule'!FJ15","v":0},{"$f":"'K20 - time schedule'!FK15","v":0},{"$f":"'K20 - time schedule'!FL15","v":0},{"$f":"'K20 - time schedule'!FM15","v":0},{"$f":"'K20 - time schedule'!FN15","v":0},{"$f":"'K20 - time schedule'!FO15","v":0},{"$f":"'K20 - time schedule'!FP15","v":0},{"$f":"'K20 - time schedule'!FQ15","v":0},{"$f":"'K20 - time schedule'!FR15","v":0},{"$f":"'K20 - time schedule'!FS15","v":0},{"$f":"'K20 - time schedule'!FT15","v":0},{"$f":"'K20 - time schedule'!FU15","v":0},{"$f":"'K20 - time schedule'!FV15","v":0},{"$f":"'K20 - time schedule'!FW15","v":0},{"$f":"'K20 - time schedule'!FX15","v":0},{"$f":"'K20 - time schedule'!FY15","v":0},{"$f":"'K20 - time schedule'!FZ15","v":0},{"$f":"'K20 - time schedule'!GA15","v":0},{"$f":"'K20 - time schedule'!GB15","v":0},{"$f":"'K20 - time schedule'!GC15","v":0},{"$f":"'K20 - time schedule'!GD15","v":0},{"$f":"'K20 - time schedule'!GE15","v":0},{"$f":"'K20 - time schedule'!GF15","v":0},{"$f":"'K20 - time schedule'!GG13","v":0},{"$f":"'K20 - time schedule'!GH13","v":0},{"$f":"'K20 - time schedule'!GI13","v":0},{"$f":"'K20 - time schedule'!GJ13","v":0},{"$f":"'K20 - time schedule'!GK13","v":0},{"$f":"'K20 - time schedule'!GL13","v":0},{"$f":"'K20 - time schedule'!GM13","v":0},{"$f":"'K20 - time schedule'!GN13","v":0},{"$f":"'K20 - time schedule'!GO13","v":0},{"$f":"'K20 - time schedule'!GP13","v":0},{"$f":"'K20 - time schedule'!GQ13","v":0},{"$f":"'K20 - time schedule'!GR13","v":0},{"$f":"'K20 - time schedule'!GS13","v":0},{"$f":"'K20 - time schedule'!GT13","v":0},{"$f":"'K20 - time schedule'!GU13","v":0},{"$f":"'K20 - time schedule'!GV13","v":0},{"$f":"'K20 - time schedule'!GW13","v":0},{"$f":"'K20 - time schedule'!GX13","v":0},{"$f":"'K20 - time schedule'!GY13","v":0},{"$f":"'K20 - time schedule'!GZ13","v":0},{"$f":"'K20 - time schedule'!HA13","v":0},{"$f":"'K20 - time schedule'!HB13","v":0},{"$f":"'K20 - time schedule'!HC13","v":0},{"$f":"'K20 - time schedule'!HD13","v":0},{"$f":"'K20 - time schedule'!HE13","v":0},{"$f":"'K20 - time schedule'!HF13","v":0},{"$f":"'K20 - time schedule'!HG13","v":0},{"$f":"'K20 - time schedule'!HH13","v":0},{"$f":"'K20 - time schedule'!HI13","v":0},{"$f":"'K20 - time schedule'!HJ13","v":0},{"$f":"'K20 - time schedule'!HK13","v":0},{"$f":"'K20 - time schedule'!HL13","v":0},{"$f":"'K20 - time schedule'!HM13","v":0},{"$f":"'K20 - time schedule'!HN13","v":0},{"$f":"'K20 - time schedule'!HO13","v":0},{"$f":"'K20 - time schedule'!HP13","v":0},{"$f":"'K20 - time schedule'!HQ13","v":0},{"$f":"'K20 - time schedule'!HR13","v":0},{"$f":"'K20 - time schedule'!HS13","v":0},{"$f":"'K20 - time schedule'!HT13","v":0},{"$f":"'K20 - time schedule'!HU13","v":0},{"$f":"'K20 - time schedule'!HV13","v":0},{"$f":"'K20 - time schedule'!HW13","v":0},{"$f":"'K20 - time schedule'!HX13","v":0},{"$f":"'K20 - time schedule'!HY13","v":0},{"$f":"'K20 - time schedule'!HZ13","v":0},{"$f":"'K20 - time schedule'!IA13","v":0},{"$f":"'K20 - time schedule'!IB13","v":0},{"$f":"'K20 - time schedule'!IC13","v":0},{"$f":"'K20 - time schedule'!ID13","v":0},{"$f":"'K20 - time schedule'!IE13","v":0},{"$f":"'K20 - time schedule'!IF13","v":0},{"$f":"'K20 - time schedule'!IG13","v":0},{"$f":"'K20 - time schedule'!IH13","v":0},{"$f":"'K20 - time schedule'!II13","v":0},{"$f":"'K20 - time schedule'!IJ13","v":0},{"$f":"'K20 - time schedule'!IK13","v":0},{"$f":"'K20 - time schedule'!IL13","v":0},{"$f":"'K20 - time schedule'!IM13","v":0},{"$f":"'K20 - time schedule'!IN13","v":0},{"$f":"'K20 - time schedule'!IO13","v":0},{"$f":"'K20 - time schedule'!IP13","v":0},{"$f":"'K20 - time schedule'!IQ13","v":0},{"$f":"'K20 - time schedule'!IR13","v":0},{"$f":"'K20 - time schedule'!IS13","v":0},{"$f":"'K20 - time schedule'!IT13","v":0},{"$f":"'K20 - time schedule'!IU13","v":0},{"$f":"'K20 - time schedule'!IV13","v":0},{"$f":"'K20 - time schedule'!IW13","v":0},{"$f":"'K20 - time schedule'!IX13","v":0},{"$f":"'K20 - time schedule'!IY13","v":0},{"$f":"'K20 - time schedule'!IZ13","v":0},{"$f":"'K20 - time schedule'!JA13","v":0},{"$f":"'K20 - time schedule'!JB13","v":0},{"$f":"'K20 - time schedule'!JC13","v":0},{"$f":"'K20 - time schedule'!JD13","v":0},{"$f":"'K20 - time schedule'!JE13","v":0},{"$f":"'K20 - time schedule'!JF13","v":0},{"$f":"'K20 - time schedule'!JG13","v":0},{"$f":"'K20 - time schedule'!JH13","v":0},{"$f":"'K20 - time schedule'!JI13","v":0},{"$f":"'K20 - time schedule'!JJ13","v":0},{"$f":"'K20 - time schedule'!JK13","v":0},{"$f":"'K20 - time schedule'!JL13","v":0},{"$f":"'K20 - time schedule'!JM13","v":0},{"$f":"'K20 - time schedule'!JN13","v":0},{"$f":"'K20 - time schedule'!JO13","v":0},{"$f":"'K20 - time schedule'!JP13","v":0},{"$f":"'K20 - time schedule'!JQ13","v":0},{"$f":"'K20 - time schedule'!JR13","v":0},{"$f":"'K20 - time schedule'!JS13","v":0},{"$f":"'K20 - time schedule'!JT13","v":0},{"$f":"'K20 - time schedule'!JU13","v":0},{"$f":"'K20 - time schedule'!JV13","v":0},{"$f":"'K20 - time schedule'!JW13","v":0},{"$f":"'K20 - time schedule'!JX13","v":0},{"$f":"'K20 - time schedule'!JY13","v":0},{"$f":"'K20 - time schedule'!JZ13","v":0},{"$f":"'K20 - time schedule'!KA13","v":0},{"$f":"'K20 - time schedule'!KB13","v":0},{"$f":"'K20 - time schedule'!KC13","v":0},{"$f":"'K20 - time schedule'!KD13","v":0},{"$f":"'K20 - time schedule'!KE13","v":0},{"$f":"'K20 - time schedule'!KF13","v":0},{"$f":"'K20 - time schedule'!KG13","v":0},{"$f":"'K20 - time schedule'!KH13","v":0},{"$f":"'K20 - time schedule'!KI13","v":0},{"$f":"'K20 - time schedule'!KJ13","v":0},{"$f":"'K20 - time schedule'!KK13","v":0},{"$f":"'K20 - time schedule'!KL13","v":0},{"$f":"'K20 - time schedule'!KM13","v":0},{"$f":"'K20 - time schedule'!KN13","v":0},{"$f":"'K20 - time schedule'!KO13","v":0},{"$f":"'K20 - time schedule'!KP13","v":0},{"$f":"'K20 - time schedule'!KQ13","v":0},{"$f":"'K20 - time schedule'!KR13","v":0},{"$f":"'K20 - time schedule'!KS13","v":0},{"$f":"'K20 - time schedule'!KT13","v":0}]
["Boiler room K20 - approved implementation documentation","K20","EUR",{"$f":"'K20 - time schedule'!G17","v":0},{"$f":"'K20 - time schedule'!H17","v":0},{"$f":"'K20 - time schedule'!I17","v":0},{"$f":"'K20 - time schedule'!J17","v":0},{"$f":"'K20 - time schedule'!K17","v":0},{"$f":"'K20 - time schedule'!L17","v":0},{"$f":"'K20 - time schedule'!M17","v":0},{"$f":"'K20 - time schedule'!N17","v":0},{"$f":"'K20 - time schedule'!O17","v":0},{"$f":"'K20 - time schedule'!P17","v":0},{"$f":"'K20 - time schedule'!Q17","v":0},{"$f":"'K20 - time schedule'!R17","v":0},{"$f":"'K20 - time schedule'!S17","v":0},{"$f":"'K20 - time schedule'!T17","v":0},{"$f":"'K20 - time schedule'!U17","v":0},{"$f":"'K20 - time schedule'!V17","v":0},{"$f":"'K20 - time schedule'!W17","v":0},{"$f":"'K20 - time schedule'!X17","v":0},{"$f":"'K20 - time schedule'!Y17","v":0},{"$f":"'K20 - time schedule'!Z17","v":0},{"$f":"'K20 - time schedule'!AA17","v":0},{"$f":"'K20 - time schedule'!AB17","v":0},{"$f":"'K20 - time schedule'!AC17","v":0},{"$f":"'K20 - time schedule'!AD17","v":0},{"$f":"'K20 - time schedule'!AE17","v":0},{"$f":"'K20 - time schedule'!AF17","v":0},{"$f":"'K20 - time schedule'!AG17","v":0},{"$f":"'K20 - time schedule'!AH17","v":0},{"$f":"'K20 - time schedule'!AI17","v":0},{"$f":"'K20 - time schedule'!AJ17","v":0},{"$f":"'K20 - time schedule'!AK17","v":0},{"$f":"'K20 - time schedule'!AL17","v":0},{"$f":"'K20 - time schedule'!AM17","v":0},{"$f":"'K20 - time schedule'!AN17","v":0},{"$f":"'K20 - time schedule'!AO17","v":0},{"$f":"'K20 - time schedule'!AP17","v":0},{"$f":"'K20 - time schedule'!AQ17","v":0},{"$f":"'K20 - time schedule'!AR17","v":0},{"$f":"'K20 - time schedule'!AS17","v":0},{"$f":"'K20 - time schedule'!AT17","v":0},{"$f":"'K20 - time schedule'!AU17","v":0},{"$f":"'K20 - time schedule'!AV17","v":0},{"$f":"'K20 - time schedule'!AW17","v":0},{"$f":"'K20 - time schedule'!AX17","v":0},{"$f":"'K20 - time schedule'!AY17","v":0},{"$f":"'K20 - time schedule'!AZ17","v":0},{"$f":"'K20 - time schedule'!BA17","v":0},{"$f":"'K20 - time schedule'!BB17","v":0},{"$f":"'K20 - time schedule'!BC17","v":0},{"$f":"'K20 - time schedule'!BD17","v":0},{"$f":"'K20 - time schedule'!BE17","v":0},{"$f":"'K20 - time schedule'!BF17","v":0},{"$f":"'K20 - time schedule'!BG17","v":0},{"$f":"'K20 - time schedule'!BH17","v":0},{"$f":"'K20 - time schedule'!BI17","v":0},{"$f":"'K20 - time schedule'!BJ17","v":0},{"$f":"'K20 - time schedule'!BK17","v":0},{"$f":"'K20 - time schedule'!BL17","v":0},{"$f":"'K20 - time schedule'!BM17","v":0},{"$f":"'K20 - time schedule'!BN17","v":0},{"$f":"'K20 - time schedule'!BO17","v":0},{"$f":"'K20 - time schedule'!BP17","v":0},{"$f":"'K20 - time schedule'!BQ17","v":0},{"$f":"'K20 - time schedule'!BR17","v":0},{"$f":"'K20 - time schedule'!BS17","v":0},{"$f":"'K20 - time schedule'!BT17","v":0},{"$f":"'K20 - time schedule'!BU17","v":0},{"$f":"'K20 - time schedule'!BV17","v":0},{"$f":"'K20 - time schedule'!BW17","v":0},{"$f":"'K20 - time schedule'!BX17","v":0},{"$f":"'K20 - time schedule'!BY17","v":0},{"$f":"'K20 - time schedule'!BZ17","v":0},{"$f":"'K20 - time schedule'!CA17","v":0},{"$f":"'K20 - time schedule'!CB17","v":0},{"$f":"'K20 - time schedule'!CC17","v":0},{"$f":"'K20 - time schedule'!CD17","v":0},{"$f":"'K20 - time schedule'!CE17","v":0},{"$f":"'K20 - time schedule'!CF17","v":0},{"$f":"'K20 - time schedule'!CG17","v":0},{"$f":"'K20 - time schedule'!CH17","v":0},{"$f":"'K20 - time schedule'!CI17","v":0},{"$f":"'K20 - time schedule'!CJ17","v":0},{"$f":"'K20 - time schedule'!CK17","v":0},{"$f":"'K20 - time schedule'!CL17","v":0},{"$f":"'K20 - time schedule'!CM17","v":0},{"$f":"'K20 - time schedule'!CN17","v":0},{"$f":"'K20 - time schedule'!CO17","v":0},{"$f":"'K20 - time schedule'!CP17","v":0},{"$f":"'K20 - time schedule'!CQ17","v":0},{"$f":"'K20 - time schedule'!CR17","v":0},{"$f":"'K20 - time schedule'!CS17","v":0},{"$f":"'K20 - time schedule'!CT17","v":0},{"$f":"'K20 - time schedule'!CU17","v":0},{"$f":"'K20 - time schedule'!CV17","v":0},{"$f":"'K20 - time schedule'!CW17","v":0},{"$f":"'K20 - time schedule'!CX17","v":0},{"$f":"'K20 - time schedule'!CY17","v":0},{"$f":"'K20 - time schedule'!CZ17","v":0},{"$f":"'K20 - time schedule'!DA17","v":0},{"$f":"'K20 - time schedule'!DB17","v":0},{"$f":"'K20 - time schedule'!DC17","v":0},{"$f":"'K20 - time schedule'!DD17","v":0},{"$f":"'K20 - time schedule'!DE17","v":0},{"$f":"'K20 - time schedule'!DF17","v":0},{"$f":"'K20 - time schedule'!DG17","v":0},{"$f":"'K20 - time schedule'!DH17","v":0},{"$f":"'K20 - time schedule'!DI17","v":0},{"$f":"'K20 - time schedule'!DJ17","v":0},{"$f":"'K20 - time schedule'!DK17","v":0},{"$f":"'K20 - time schedule'!DL17","v":0},{"$f":"'K20 - time schedule'!DM17","v":0},{"$f":"'K20 - time schedule'!DN17","v":0},{"$f":"'K20 - time schedule'!DO17","v":0},{"$f":"'K20 - time schedule'!DP17","v":0},{"$f":"'K20 - time schedule'!DQ17","v":0},{"$f":"'K20 - time schedule'!DR17","v":0},{"$f":"'K20 - time schedule'!DS17","v":0},{"$f":"'K20 - time schedule'!DT17","v":0},{"$f":"'K20 - time schedule'!DU17","v":0},{"$f":"'K20 - time schedule'!DV17","v":0},{"$f":"'K20 - time schedule'!DW17","v":0},{"$f":"'K20 - time schedule'!DX17","v":0},{"$f":"'K20 - time schedule'!DY17","v":0},{"$f":"'K20 - time schedule'!DZ17","v":0},{"$f":"'K20 - time schedule'!EA17","v":0},{"$f":"'K20 - time schedule'!EB17","v":0},{"$f":"'K20 - time schedule'!EC17","v":0},{"$f":"'K20 - time schedule'!ED17","v":0},{"$f":"'K20 - time schedule'!EE17","v":0},{"$f":"'K20 - time schedule'!EF17","v":0},{"$f":"'K20 - time schedule'!EG17","v":0},{"$f":"'K20 - time schedule'!EH17","v":0},{"$f":"'K20 - time schedule'!EI17","v":0},{"$f":"'K20 - time schedule'!EJ17","v":0},{"$f":"'K20 - time schedule'!EK17","v":0},{"$f":"'K20 - time schedule'!EL17","v":0},{"$f":"'K20 - time schedule'!EM17","v":0},{"$f":"'K20 - time schedule'!EN17","v":0},{"$f":"'K20 - time schedule'!EO17","v":0},{"$f":"'K20 - time schedule'!EP17","v":0},{"$f":"'K20 - time schedule'!EQ17","v":0},{"$f":"'K20 - time schedule'!ER17","v":0},{"$f":"'K20 - time schedule'!ES17","v":0},{"$f":"'K20 - time schedule'!ET17","v":0},{"$f":"'K20 - time schedule'!EU17","v":0},{"$f":"'K20 - time schedule'!EV17","v":0},{"$f":"'K20 - time schedule'!EW17","v":0},{"$f":"'K20 - time schedule'!EX17","v":0},{"$f":"'K20 - time schedule'!EY17","v":0},{"$f":"'K20 - time schedule'!EZ17","v":0},{"$f":"'K20 - time schedule'!FA17","v":0},{"$f":"'K20 - time schedule'!FB17","v":0},{"$f":"'K20 - time schedule'!FC17","v":0},{"$f":"'K20 - time schedule'!FD17","v":0},{"$f":"'K20 - time schedule'!FE17","v":0},{"$f":"'K20 - time schedule'!FF17","v":0},{"$f":"'K20 - time schedule'!FG17","v":0},{"$f":"'K20 - time schedule'!FH17","v":0},{"$f":"'K20 - time schedule'!FI17","v":0},{"$f":"'K20 - time schedule'!FJ17","v":0},{"$f":"'K20 - time schedule'!FK17","v":0},{"$f":"'K20 - time schedule'!FL17","v":0},{"$f":"'K20 - time schedule'!FM17","v":0},{"$f":"'K20 - time schedule'!FN17","v":0},{"$f":"'K20 - time schedule'!FO17","v":0},{"$f":"'K20 - time schedule'!FP17","v":0},{"$f":"'K20 - time schedule'!FQ17","v":0},{"$f":"'K20 - time schedule'!FR17","v":0},{"$f":"'K20 - time schedule'!FS17","v":0},{"$f":"'K20 - time schedule'!FT17","v":0},{"$f":"'K20 - time schedule'!FU17","v":0},{"$f":"'K20 - time schedule'!FV17","v":0},{"$f":"'K20 - time schedule'!FW17","v":0},{"$f":"'K20 - time schedule'!FX17","v":0},{"$f":"'K20 - time schedule'!FY17","v":0},{"$f":"'K20 - time schedule'!FZ17","v":0},{"$f":"'K20 - time schedule'!GA17","v":0},{"$f":"'K20 - time schedule'!GB17","v":0},{"$f":"'K20 - time schedule'!GC17","v":0},{"$f":"'K20 - time schedule'!GD17","v":0},{"$f":"'K20 - time schedule'!GE17","v":0},{"$f":"'K20 - time schedule'!GF17","v":0},{"$f":"'K20 - time schedule'!GG14","v":0},{"$f":"'K20 - time schedule'!GH14","v":0},{"$f":"'K20 - time schedule'!GI14","v":0},{"$f":"'K20 - time schedule'!GJ14","v":0},{"$f":"'K20 - time schedule'!GK14","v":0},{"$f":"'K20 - time schedule'!GL14","v":0},{"$f":"'K20 - time schedule'!GM14","v":0},{"$f":"'K20 - time schedule'!GN14","v":0},{"$f":"'K20 - time schedule'!GO14","v":0},{"$f":"'K20 - time schedule'!GP14","v":0},{"$f":"'K20 - time schedule'!GQ14","v":0},{"$f":"'K20 - time schedule'!GR14","v":0},{"$f":"'K20 - time schedule'!GS14","v":0},{"$f":"'K20 - time schedule'!GT14","v":0},{"$f":"'K20 - time schedule'!GU14","v":0},{"$f":"'K20 - time schedule'!GV14","v":0},{"$f":"'K20 - time schedule'!GW14","v":0},{"$f":"'K20 - time schedule'!GX14","v":0},{"$f":"'K20 - time schedule'!GY14","v":0},{"$f":"'K20 - time schedule'!GZ14","v":0},{"$f":"'K20 - time schedule'!HA14","v":0},{"$f":"'K20 - time schedule'!HB14","v":0},{"$f":"'K20 - time schedule'!HC14","v":0},{"$f":"'K20 - time schedule'!HD14","v":0},{"$f":"'K20 - time schedule'!HE14","v":0},{"$f":"'K20 - time schedule'!HF14","v":0},{"$f":"'K20 - time schedule'!HG14","v":0},{"$f":"'K20 - time schedule'!HH14","v":0},{"$f":"'K20 - time schedule'!HI14","v":0},{"$f":"'K20 - time schedule'!HJ14","v":0},{"$f":"'K20 - time schedule'!HK14","v":0},{"$f":"'K20 - time schedule'!HL14","v":0},{"$f":"'K20 - time schedule'!HM14","v":0},{"$f":"'K20 - time schedule'!HN14","v":0},{"$f":"'K20 - time schedule'!HO14","v":0},{"$f":"'K20 - time schedule'!HP14","v":0},{"$f":"'K20 - time schedule'!HQ14","v":0},{"$f":"'K20 - time schedule'!HR14","v":0},{"$f":"'K20 - time schedule'!HS14","v":0},{"$f":"'K20 - time schedule'!HT14","v":0},{"$f":"'K20 - time schedule'!HU14","v":0},{"$f":"'K20 - time schedule'!HV14","v":0},{"$f":"'K20 - time schedule'!HW14","v":0},{"$f":"'K20 - time schedule'!HX14","v":0},{"$f":"'K20 - time schedule'!HY14","v":0},{"$f":"'K20 - time schedule'!HZ14","v":0},{"$f":"'K20 - time schedule'!IA14","v":0},{"$f":"'K20 - time schedule'!IB14","v":0},{"$f":"'K20 - time schedule'!IC14","v":0},{"$f":"'K20 - time schedule'!ID14","v":0},{"$f":"'K20 - time schedule'!IE14","v":0},{"$f":"'K20 - time schedule'!IF14","v":0},{"$f":"'K20 - time schedule'!IG14","v":0},{"$f":"'K20 - time schedule'!IH14","v":0},{"$f":"'K20 - time schedule'!II14","v":0},{"$f":"'K20 - time schedule'!IJ14","v":0},{"$f":"'K20 - time schedule'!IK14","v":0},{"$f":"'K20 - time schedule'!IL14","v":0},{"$f":"'K20 - time schedule'!IM14","v":0},{"$f":"'K20 - time schedule'!IN14","v":0},{"$f":"'K20 - time schedule'!IO14","v":0},{"$f":"'K20 - time schedule'!IP14","v":0},{"$f":"'K20 - time schedule'!IQ14","v":0},{"$f":"'K20 - time schedule'!IR14","v":0},{"$f":"'K20 - time schedule'!IS14","v":0},{"$f":"'K20 - time schedule'!IT14","v":0},{"$f":"'K20 - time schedule'!IU14","v":0},{"$f":"'K20 - time schedule'!IV14","v":0},{"$f":"'K20 - time schedule'!IW14","v":0},{"$f":"'K20 - time schedule'!IX14","v":0},{"$f":"'K20 - time schedule'!IY14","v":0},{"$f":"'K20 - time schedule'!IZ14","v":0},{"$f":"'K20 - time schedule'!JA14","v":0},{"$f":"'K20 - time schedule'!JB14","v":0},{"$f":"'K20 - time schedule'!JC14","v":0},{"$f":"'K20 - time schedule'!JD14","v":0},{"$f":"'K20 - time schedule'!JE14","v":0},{"$f":"'K20 - time schedule'!JF14","v":0},{"$f":"'K20 - time schedule'!JG14","v":0},{"$f":"'K20 - time schedule'!JH14","v":0},{"$f":"'K20 - time schedule'!JI14","v":0},{"$f":"'K20 - time schedule'!JJ14","v":0},{"$f":"'K20 - time schedule'!JK14","v":0},{"$f":"'K20 - time schedule'!JL14","v":0},{"$f":"'K20 - time schedule'!JM14","v":0},{"$f":"'K20 - time schedule'!JN14","v":0},{"$f":"'K20 - time schedule'!JO14","v":0},{"$f":"'K20 - time schedule'!JP14","v":0},{"$f":"'K20 - time schedule'!JQ14","v":0},{"$f":"'K20 - time schedule'!JR14","v":0},{"$f":"'K20 - time schedule'!JS14","v":0},{"$f":"'K20 - time schedule'!JT14","v":0},{"$f":"'K20 - time schedule'!JU14","v":0},{"$f":"'K20 - time schedule'!JV14","v":0},{"$f":"'K20 - time schedule'!JW14","v":0},{"$f":"'K20 - time schedule'!JX14","v":0},{"$f":"'K20 - time schedule'!JY14","v":0},{"$f":"'K20 - time schedule'!JZ14","v":0},{"$f":"'K20 - time schedule'!KA14","v":0},{"$f":"'K20 - time schedule'!KB14","v":0},{"$f":"'K20 - time schedule'!KC14","v":0},{"$f":"'K20 - time schedule'!KD14","v":0},{"$f":"'K20 - time schedule'!KE14","v":0},{"$f":"'K20 - time schedule'!KF14","v":0},{"$f":"'K20 - time schedule'!KG14","v":0},{"$f":"'K20 - time schedule'!KH14","v":0},{"$f":"'K20 - time schedule'!KI14","v":0},{"$f":"'K20 - time schedule'!KJ14","v":0},{"$f":"'K20 - time schedule'!KK14","v":0},{"$f":"'K20 - time schedule'!KL14","v":0},{"$f":"'K20 - time schedule'!KM14","v":0},{"$f":"'K20 - time schedule'!KN14","v":0},{"$f":"'K20 - time schedule'!KO14","v":0},{"$f":"'K20 - time schedule'!KP14","v":0},{"$f":"'K20 - time schedule'!KQ14","v":0},{"$f":"'K20 - time schedule'!KR14","v":0},{"$f":"'K20 - time schedule'!KS14","v":0},{"$f":"'K20 - time schedule'!KT14","v":0}]
["Boiler room K20 - the boiler itself including all components","K20","EUR",{"$f":"'K20 - time schedule'!G21","v":0},{"$f":"'K20 - time schedule'!H21","v":0},{"$f":"'K20 - time schedule'!I21","v":0},{"$f":"'K20 - time schedule'!J21","v":0},{"$f":"'K20 - time schedule'!K21","v":0},{"$f":"'K20 - time schedule'!L21","v":0},{"$f":"'K20 - time schedule'!M21","v":0},{"$f":"'K20 - time schedule'!N21","v":0},{"$f":"'K20 - time schedule'!O21","v":0},{"$f":"'K20 - time schedule'!P21","v":0},{"$f":"'K20 - time schedule'!Q21","v":0},{"$f":"'K20 - time schedule'!R21","v":0},{"$f":"'K20 - time schedule'!S21","v":0},{"$f":"'K20 - time schedule'!T21","v":0},{"$f":"'K20 - time schedule'!U21","v":0},{"$f":"'K20 - time schedule'!V21","v":0},{"$f":"'K20 - time schedule'!W21","v":0},{"$f":"'K20 - time schedule'!X21","v":0},{"$f":"'K20 - time schedule'!Y21","v":0},{"$f":"'K20 - time schedule'!Z21","v":0},{"$f":"'K20 - time schedule'!AA21","v":0},{"$f":"'K20 - time schedule'!AB21","v":0},{"$f":"'K20 - time schedule'!AC21","v":0},{"$f":"'K20 - time schedule'!AD21","v":0},{"$f":"'K20 - time schedule'!AE21","v":0},{"$f":"'K20 - time schedule'!AF21","v":0},{"$f":"'K20 - time schedule'!AG21","v":0},{"$f":"'K20 - time schedule'!AH21","v":0},{"$f":"'K20 - time schedule'!AI21","v":0},{"$f":"'K20 - time schedule'!AJ21","v":0},{"$f":"'K20 - time schedule'!AK21","v":0},{"$f":"'K20 - time schedule'!AL21","v":0},{"$f":"'K20 - time schedule'!AM21","v":0},{"$f":"'K20 - time schedule'!AN21","v":0},{"$f":"'K20 - time schedule'!AO21","v":0},{"$f":"'K20 - time schedule'!AP21","v":0},{"$f":"'K20 - time schedule'!AQ21","v":0},{"$f":"'K20 - time schedule'!AR21","v":0},{"$f":"'K20 - time schedule'!AS21","v":0},{"$f":"'K20 - time schedule'!AT21","v":0},{"$f":"'K20 - time schedule'!AU21","v":0},{"$f":"'K20 - time schedule'!AV21","v":0},{"$f":"'K20 - time schedule'!AW21","v":0},{"$f":"'K20 - time schedule'!AX21","v":0},{"$f":"'K20 - time schedule'!AY21","v":0},{"$f":"'K20 - time schedule'!AZ21","v":0},{"$f":"'K20 - time schedule'!BA21","v":0},{"$f":"'K20 - time schedule'!BB21","v":0},{"$f":"'K20 - time schedule'!BC21","v":0},{"$f":"'K20 - time schedule'!BD21","v":0},{"$f":"'K20 - time schedule'!BE21","v":0},{"$f":"'K20 - time schedule'!BF21","v":0},{"$f":"'K20 - time schedule'!BG21","v":0},{"$f":"'K20 - time schedule'!BH21","v":0},{"$f":"'K20 - time schedule'!BI21","v":0},{"$f":"'K20 - time schedule'!BJ21","v":0},{"$f":"'K20 - time schedule'!BK21","v":0},{"$f":"'K20 - time schedule'!BL21","v":0},{"$f":"'K20 - time schedule'!BM21","v":0},{"$f":"'K20 - time schedule'!BN21","v":0},{"$f":"'K20 - time schedule'!BO21","v":0},{"$f":"'K20 - time schedule'!BP21","v":0},{"$f":"'K20 - time schedule'!BQ21","v":0},{"$f":"'K20 - time schedule'!BR21","v":0},{"$f":"'K20 - time schedule'!BS21","v":0},{"$f":"'K20 - time schedule'!BT21","v":0},{"$f":"'K20 - time schedule'!BU21","v":0},{"$f":"'K20 - time schedule'!BV21","v":0},{"$f":"'K20 - time schedule'!BW21","v":0},{"$f":"'K20 - time schedule'!BX21","v":0},{"$f":"'K20 - time schedule'!BY21","v":0},{"$f":"'K20 - time schedule'!BZ21","v":0},{"$f":"'K20 - time schedule'!CA21","v":0},{"$f":"'K20 - time schedule'!CB21","v":0},{"$f":"'K20 - time schedule'!CC21","v":0},{"$f":"'K20 - time schedule'!CD21","v":0},{"$f":"'K20 - time schedule'!CE21","v":0},{"$f":"'K20 - time schedule'!CF21","v":0},{"$f":"'K20 - time schedule'!CG21","v":0},{"$f":"'K20 - time schedule'!CH21","v":0},{"$f":"'K20 - time schedule'!CI21","v":0},{"$f":"'K20 - time schedule'!CJ21","v":0},{"$f":"'K20 - time schedule'!CK21","v":0},{"$f":"'K20 - time schedule'!CL21","v":0},{"$f":"'K20 - time schedule'!CM21","v":0},{"$f":"'K20 - time schedule'!CN21","v":0},{"$f":"'K20 - time schedule'!CO21","v":0},{"$f":"'K20 - time schedule'!CP21","v":0},{"$f":"'K20 - time schedule'!CQ21","v":0},{"$f":"'K20 - time schedule'!CR21","v":0},{"$f":"'K20 - time schedule'!CS21","v":0},{"$f":"'K20 - time schedule'!CT21","v":0},{"$f":"'K20 - time schedule'!CU21","v":0},{"$f":"'K20 - time schedule'!CV21","v":0},{"$f":"'K20 - time schedule'!CW21","v":0},{"$f":"'K20 - time schedule'!CX21","v":0},{"$f":"'K20 - time schedule'!CY21","v":0},{"$f":"'K20 - time schedule'!CZ21","v":0},{"$f":"'K20 - time schedule'!DA21","v":0},{"$f":"'K20 - time schedule'!DB21","v":0},{"$f":"'K20 - time schedule'!DC21","v":0},{"$f":"'K20 - time schedule'!DD21","v":0},{"$f":"'K20 - time schedule'!DE21","v":0},{"$f":"'K20 - time schedule'!DF21","v":0},{"$f":"'K20 - time schedule'!DG21","v":0},{"$f":"'K20 - time schedule'!DH21","v":0},{"$f":"'K20 - time schedule'!DI21","v":0},{"$f":"'K20 - time schedule'!DJ21","v":0},{"$f":"'K20 - time schedule'!DK21","v":0},{"$f":"'K20 - time schedule'!DL21","v":0},{"$f":"'K20 - time schedule'!DM21","v":0},{"$f":"'K20 - time schedule'!DN21","v":0},{"$f":"'K20 - time schedule'!DO21","v":0},{"$f":"'K20 - time schedule'!DP21","v":0},{"$f":"'K20 - time schedule'!DQ21","v":0},{"$f":"'K20 - time schedule'!DR21","v":0},{"$f":"'K20 - time schedule'!DS21","v":0},{"$f":"'K20 - time schedule'!DT21","v":0},{"$f":"'K20 - time schedule'!DU21","v":0},{"$f":"'K20 - time schedule'!DV21","v":0},{"$f":"'K20 - time schedule'!DW21","v":0},{"$f":"'K20 - time schedule'!DX21","v":0},{"$f":"'K20 - time schedule'!DY21","v":0},{"$f":"'K20 - time schedule'!DZ21","v":0},{"$f":"'K20 - time schedule'!EA21","v":0},{"$f":"'K20 - time schedule'!EB21","v":0},{"$f":"'K20 - time schedule'!EC21","v":0},{"$f":"'K20 - time schedule'!ED21","v":0},{"$f":"'K20 - time schedule'!EE21","v":0},{"$f":"'K20 - time schedule'!EF21","v":0},{"$f":"'K20 - time schedule'!EG21","v":0},{"$f":"'K20 - time schedule'!EH21","v":0},{"$f":"'K20 - time schedule'!EI21","v":0},{"$f":"'K20 - time schedule'!EJ21","v":0},{"$f":"'K20 - time schedule'!EK21","v":0},{"$f":"'K20 - time schedule'!EL21","v":0},{"$f":"'K20 - time schedule'!EM21","v":0},{"$f":"'K20 - time schedule'!EN21","v":0},{"$f":"'K20 - time schedule'!EO21","v":0},{"$f":"'K20 - time schedule'!EP21","v":0},{"$f":"'K20 - time schedule'!EQ21","v":0},{"$f":"'K20 - time schedule'!ER21","v":0},{"$f":"'K20 - time schedule'!ES21","v":0},{"$f":"'K20 - time schedule'!ET21","v":0},{"$f":"'K20 - time schedule'!EU21","v":0},{"$f":"'K20 - time schedule'!EV21","v":0},{"$f":"'K20 - time schedule'!EW21","v":0},{"$f":"'K20 - time schedule'!EX21","v":0},{"$f":"'K20 - time schedule'!EY21","v":0},{"$f":"'K20 - time schedule'!EZ21","v":0},{"$f":"'K20 - time schedule'!FA21","v":0},{"$f":"'K20 - time schedule'!FB21","v":0},{"$f":"'K20 - time schedule'!FC21","v":0},{"$f":"'K20 - time schedule'!FD21","v":0},{"$f":"'K20 - time schedule'!FE21","v":0},{"$f":"'K20 - time schedule'!FF21","v":0},{"$f":"'K20 - time schedule'!FG21","v":0},{"$f":"'K20 - time schedule'!FH21","v":0},{"$f":"'K20 - time schedule'!FI21","v":0},{"$f":"'K20 - time schedule'!FJ21","v":0},{"$f":"'K20 - time schedule'!FK21","v":0},{"$f":"'K20 - time schedule'!FL21","v":0},{"$f":"'K20 - time schedule'!FM21","v":0},{"$f":"'K20 - time schedule'!FN21","v":0},{"$f":"'K20 - time schedule'!FO21","v":0},{"$f":"'K20 - time schedule'!FP21","v":0},{"$f":"'K20 - time schedule'!FQ21","v":0},{"$f":"'K20 - time schedule'!FR21","v":0},{"$f":"'K20 - time schedule'!FS21","v":0},{"$f":"'K20 - time schedule'!FT21","v":0},{"$f":"'K20 - time schedule'!FU21","v":0},{"$f":"'K20 - time schedule'!FV21","v":0},{"$f":"'K20 - time schedule'!FW21","v":0},{"$f":"'K20 - time schedule'!FX21","v":0},{"$f":"'K20 - time schedule'!FY21","v":0},{"$f":"'K20 - time schedule'!FZ21","v":0},{"$f":"'K20 - time schedule'!GA21","v":0},{"$f":"'K20 - time schedule'!GB21","v":0},{"$f":"'K20 - time schedule'!GC21","v":0},{"$f":"'K20 - time schedule'!GD21","v":0},{"$f":"'K20 - time schedule'!GE21","v":0},{"$f":"'K20 - time schedule'!GF21","v":0},{"$f":"'K20 - time schedule'!GG15","v":0},{"$f":"'K20 - time schedule'!GH15","v":0},{"$f":"'K20 - time schedule'!GI15","v":0},{"$f":"'K20 - time schedule'!GJ15","v":0},{"$f":"'K20 - time schedule'!GK15","v":0},{"$f":"'K20 - time schedule'!GL15","v":0},{"$f":"'K20 - time schedule'!GM15","v":0},{"$f":"'K20 - time schedule'!GN15","v":0},{"$f":"'K20 - time schedule'!GO15","v":0},{"$f":"'K20 - time schedule'!GP15","v":0},{"$f":"'K20 - time schedule'!GQ15","v":0},{"$f":"'K20 - time schedule'!GR15","v":0},{"$f":"'K20 - time schedule'!GS15","v":0},{"$f":"'K20 - time schedule'!GT15","v":0},{"$f":"'K20 - time schedule'!GU15","v":0},{"$f":"'K20 - time schedule'!GV15","v":0},{"$f":"'K20 - time schedule'!GW15","v":0},{"$f":"'K20 - time schedule'!GX15","v":0},{"$f":"'K20 - time schedule'!GY15","v":0},{"$f":"'K20 - time schedule'!GZ15","v":0},{"$f":"'K20 - time schedule'!HA15","v":0},{"$f":"'K20 - time schedule'!HB15","v":0},{"$f":"'K20 - time schedule'!HC15","v":0},{"$f":"'K20 - time schedule'!HD15","v":0},{"$f":"'K20 - time schedule'!HE15","v":0},{"$f":"'K20 - time schedule'!HF15","v":0},{"$f":"'K20 - time schedule'!HG15","v":0},{"$f":"'K20 - time schedule'!HH15","v":0},{"$f":"'K20 - time schedule'!HI15","v":0},{"$f":"'K20 - time schedule'!HJ15","v":0},{"$f":"'K20 - time schedule'!HK15","v":0},{"$f":"'K20 - time schedule'!HL15","v":0},{"$f":"'K20 - time schedule'!HM15","v":0},{"$f":"'K20 - time schedule'!HN15","v":0},{"$f":"'K20 - time schedule'!HO15","v":0},{"$f":"'K20 - time schedule'!HP15","v":0},{"$f":"'K20 - time schedule'!HQ15","v":0},{"$f":"'K20 - time schedule'!HR15","v":0},{"$f":"'K20 - time schedule'!HS15","v":0},{"$f":"'K20 - time schedule'!HT15","v":0},{"$f":"'K20 - time schedule'!HU15","v":0},{"$f":"'K20 - time schedule'!HV15","v":0},{"$f":"'K20 - time schedule'!HW15","v":0},{"$f":"'K20 - time schedule'!HX15","v":0},{"$f":"'K20 - time schedule'!HY15","v":0},{"$f":"'K20 - time schedule'!HZ15","v":0},{"$f":"'K20 - time schedule'!IA15","v":0},{"$f":"'K20 - time schedule'!IB15","v":0},{"$f":"'K20 - time schedule'!IC15","v":0},{"$f":"'K20 - time schedule'!ID15","v":0},{"$f":"'K20 - time schedule'!IE15","v":0},{"$f":"'K20 - time schedule'!IF15","v":0},{"$f":"'K20 - time schedule'!IG15","v":0},{"$f":"'K20 - time schedule'!IH15","v":0},{"$f":"'K20 - time schedule'!II15","v":0},{"$f":"'K20 - time schedule'!IJ15","v":0},{"$f":"'K20 - time schedule'!IK15","v":0},{"$f":"'K20 - time schedule'!IL15","v":0},{"$f":"'K20 - time schedule'!IM15","v":0},{"$f":"'K20 - time schedule'!IN15","v":0},{"$f":"'K20 - time schedule'!IO15","v":0},{"$f":"'K20 - time schedule'!IP15","v":0},{"$f":"'K20 - time schedule'!IQ15","v":0},{"$f":"'K20 - time schedule'!IR15","v":0},{"$f":"'K20 - time schedule'!IS15","v":0},{"$f":"'K20 - time schedule'!IT15","v":0},{"$f":"'K20 - time schedule'!IU15","v":0},{"$f":"'K20 - time schedule'!IV15","v":0},{"$f":"'K20 - time schedule'!IW15","v":0},{"$f":"'K20 - time schedule'!IX15","v":0},{"$f":"'K20 - time schedule'!IY15","v":0},{"$f":"'K20 - time schedule'!IZ15","v":0},{"$f":"'K20 - time schedule'!JA15","v":0},{"$f":"'K20 - time schedule'!JB15","v":0},{"$f":"'K20 - time schedule'!JC15","v":0},{"$f":"'K20 - time schedule'!JD15","v":0},{"$f":"'K20 - time schedule'!JE15","v":0},{"$f":"'K20 - time schedule'!JF15","v":0},{"$f":"'K20 - time schedule'!JG15","v":0},{"$f":"'K20 - time schedule'!JH15","v":0},{"$f":"'K20 - time schedule'!JI15","v":0},{"$f":"'K20 - time schedule'!JJ15","v":0},{"$f":"'K20 - time schedule'!JK15","v":0},{"$f":"'K20 - time schedule'!JL15","v":0},{"$f":"'K20 - time schedule'!JM15","v":0},{"$f":"'K20 - time schedule'!JN15","v":0},{"$f":"'K20 - time schedule'!JO15","v":0},{"$f":"'K20 - time schedule'!JP15","v":0},{"$f":"'K20 - time schedule'!JQ15","v":0},{"$f":"'K20 - time schedule'!JR15","v":0},{"$f":"'K20 - time schedule'!JS15","v":0},{"$f":"'K20 - time schedule'!JT15","v":0},{"$f":"'K20 - time schedule'!JU15","v":0},{"$f":"'K20 - time schedule'!JV15","v":0},{"$f":"'K20 - time schedule'!JW15","v":0},{"$f":"'K20 - time schedule'!JX15","v":0},{"$f":"'K20 - time schedule'!JY15","v":0},{"$f":"'K20 - time schedule'!JZ15","v":0},{"$f":"'K20 - time schedule'!KA15","v":0},{"$f":"'K20 - time schedule'!KB15","v":0},{"$f":"'K20 - time schedule'!KC15","v":0},{"$f":"'K20 - time schedule'!KD15","v":0},{"$f":"'K20 - time schedule'!KE15","v":0},{"$f":"'K20 - time schedule'!KF15","v":0},{"$f":"'K20 - time schedule'!KG15","v":0},{"$f":"'K20 - time schedule'!KH15","v":0},{"$f":"'K20 - time schedule'!KI15","v":0},{"$f":"'K20 - time schedule'!KJ15","v":0},{"$f":"'K20 - time schedule'!KK15","v":0},{"$f":"'K20 - time schedule'!KL15","v":0},{"$f":"'K20 - time schedule'!KM15","v":0},{"$f":"'K20 - time schedule'!KN15","v":0},{"$f":"'K20 - time schedule'!KO15","v":0},{"$f":"'K20 - time schedule'!KP15","v":0},{"$f":"'K20 - time schedule'!KQ15","v":0},{"$f":"'K20 - time schedule'!KR15","v":0},{"$f":"'K20 - time schedule'!KS15","v":0},{"$f":"'K20 - time schedule'!KT15","v":0}]
["Boiler room K20 - operating fuel storage tanks including transport of chips into boiler","K20","EUR",{"$f":"'K20 - time schedule'!G23","v":0},{"$f":"'K20 - time schedule'!H23","v":0},{"$f":"'K20 - time schedule'!I23","v":0},{"$f":"'K20 - time schedule'!J23","v":0},{"$f":"'K20 - time schedule'!K23","v":0},{"$f":"'K20 - time schedule'!L23","v":0},{"$f":"'K20 - time schedule'!M23","v":0},{"$f":"'K20 - time schedule'!N23","v":0},{"$f":"'K20 - time schedule'!O23","v":0},{"$f":"'K20 - time schedule'!P23","v":0},{"$f":"'K20 - time schedule'!Q23","v":0},{"$f":"'K20 - time schedule'!R23","v":0},{"$f":"'K20 - time schedule'!S23","v":0},{"$f":"'K20 - time schedule'!T23","v":0},{"$f":"'K20 - time schedule'!U23","v":0},{"$f":"'K20 - time schedule'!V23","v":0},{"$f":"'K20 - time schedule'!W23","v":0},{"$f":"'K20 - time schedule'!X23","v":0},{"$f":"'K20 - time schedule'!Y23","v":0},{"$f":"'K20 - time schedule'!Z23","v":0},{"$f":"'K20 - time schedule'!AA23","v":0},{"$f":"'K20 - time schedule'!AB23","v":0},{"$f":"'K20 - time schedule'!AC23","v":0},{"$f":"'K20 - time schedule'!AD23","v":0},{"$f":"'K20 - time schedule'!AE23","v":0},{"$f":"'K20 - time schedule'!AF23","v":0},{"$f":"'K20 - time schedule'!AG23","v":0},{"$f":"'K20 - time schedule'!AH23","v":0},{"$f":"'K20 - time schedule'!AI23","v":0},{"$f":"'K20 - time schedule'!AJ23","v":0},{"$f":"'K20 - time schedule'!AK23","v":0},{"$f":"'K20 - time schedule'!AL23","v":0},{"$f":"'K20 - time schedule'!AM23","v":0},{"$f":"'K20 - time schedule'!AN23","v":0},{"$f":"'K20 - time schedule'!AO23","v":0},{"$f":"'K20 - time schedule'!AP23","v":0},{"$f":"'K20 - time schedule'!AQ23","v":0},{"$f":"'K20 - time schedule'!AR23","v":0},{"$f":"'K20 - time schedule'!AS23","v":0},{"$f":"'K20 - time schedule'!AT23","v":0},{"$f":"'K20 - time schedule'!AU23","v":0},{"$f":"'K20 - time schedule'!AV23","v":0},{"$f":"'K20 - time schedule'!AW23","v":0},{"$f":"'K20 - time schedule'!AX23","v":0},{"$f":"'K20 - time schedule'!AY23","v":0},{"$f":"'K20 - time schedule'!AZ23","v":0},{"$f":"'K20 - time schedule'!BA23","v":0},{"$f":"'K20 - time schedule'!BB23","v":0},{"$f":"'K20 - time schedule'!BC23","v":0},{"$f":"'K20 - time schedule'!BD23","v":0},{"$f":"'K20 - time schedule'!BE23","v":0},{"$f":"'K20 - time schedule'!BF23","v":0},{"$f":"'K20 - time schedule'!BG23","v":0},{"$f":"'K20 - time schedule'!BH23","v":0},{"$f":"'K20 - time schedule'!BI23","v":0},{"$f":"'K20 - time schedule'!BJ23","v":0},{"$f":"'K20 - time schedule'!BK23","v":0},{"$f":"'K20 - time schedule'!BL23","v":0},{"$f":"'K20 - time schedule'!BM23","v":0},{"$f":"'K20 - time schedule'!BN23","v":0},{"$f":"'K20 - time schedule'!BO23","v":0},{"$f":"'K20 - time schedule'!BP23","v":0},{"$f":"'K20 - time schedule'!BQ23","v":0},{"$f":"'K20 - time schedule'!BR23","v":0},{"$f":"'K20 - time schedule'!BS23","v":0},{"$f":"'K20 - time schedule'!BT23","v":0},{"$f":"'K20 - time schedule'!BU23","v":0},{"$f":"'K20 - time schedule'!BV23","v":0},{"$f":"'K20 - time schedule'!BW23","v":0},{"$f":"'K20 - time schedule'!BX23","v":0},{"$f":"'K20 - time schedule'!BY23","v":0},{"$f":"'K20 - time schedule'!BZ23","v":0},{"$f":"'K20 - time schedule'!CA23","v":0},{"$f":"'K20 - time schedule'!CB23","v":0},{"$f":"'K20 - time schedule'!CC23","v":0},{"$f":"'K20 - time schedule'!CD23","v":0},{"$f":"'K20 - time schedule'!CE23","v":0},{"$f":"'K20 - time schedule'!CF23","v":0},{"$f":"'K20 - time schedule'!CG23","v":0},{"$f":"'K20 - time schedule'!CH23","v":0},{"$f":"'K20 - time schedule'!CI23","v":0},{"$f":"'K20 - time schedule'!CJ23","v":0},{"$f":"'K20 - time schedule'!CK23","v":0},{"$f":"'K20 - time schedule'!CL23","v":0},{"$f":"'K20 - time schedule'!CM23","v":0},{"$f":"'K20 - time schedule'!CN23","v":0},{"$f":"'K20 - time schedule'!CO23","v":0},{"$f":"'K20 - time schedule'!CP23","v":0},{"$f":"'K20 - time schedule'!CQ23","v":0},{"$f":"'K20 - time schedule'!CR23","v":0},{"$f":"'K20 - time schedule'!CS23","v":0},{"$f":"'K20 - time schedule'!CT23","v":0},{"$f":"'K20 - time schedule'!CU23","v":0},{"$f":"'K20 - time schedule'!CV23","v":0},{"$f":"'K20 - time schedule'!CW23","v":0},{"$f":"'K20 - time schedule'!CX23","v":0},{"$f":"'K20 - time schedule'!CY23","v":0},{"$f":"'K20 - time schedule'!CZ23","v":0},{"$f":"'K20 - time schedule'!DA23","v":0},{"$f":"'K20 - time schedule'!DB23","v":0},{"$f":"'K20 - time schedule'!DC23","v":0},{"$f":"'K20 - time schedule'!DD23","v":0},{"$f":"'K20 - time schedule'!DE23","v":0},{"$f":"'K20 - time schedule'!DF23","v":0},{"$f":"'K20 - time schedule'!DG23","v":0},{"$f":"'K20 - time schedule'!DH23","v":0},{"$f":"'K20 - time schedule'!DI23","v":0},{"$f":"'K20 - time schedule'!DJ23","v":0},{"$f":"'K20 - time schedule'!DK23","v":0},{"$f":"'K20 - time schedule'!DL23","v":0},{"$f":"'K20 - time schedule'!DM23","v":0},{"$f":"'K20 - time schedule'!DN23","v":0},{"$f":"'K20 - time schedule'!DO23","v":0},{"$f":"'K20 - time schedule'!DP23","v":0},{"$f":"'K20 - time schedule'!DQ23","v":0},{"$f":"'K20 - time schedule'!DR23","v":0},{"$f":"'K20 - time schedule'!DS23","v":0},{"$f":"'K20 - time schedule'!DT23","v":0},{"$f":"'K20 - time schedule'!DU23","v":0},{"$f":"'K20 - time schedule'!DV23","v":0},{"$f":"'K20 - time schedule'!DW23","v":0},{"$f":"'K20 - time schedule'!DX23","v":0},{"$f":"'K20 - time schedule'!DY23","v":0},{"$f":"'K20 - time schedule'!DZ23","v":0},{"$f":"'K20 - time schedule'!EA23","v":0},{"$f":"'K20 - time schedule'!EB23","v":0},{"$f":"'K20 - time schedule'!EC23","v":0},{"$f":"'K20 - time schedule'!ED23","v":0},{"$f":"'K20 - time schedule'!EE23","v":0},{"$f":"'K20 - time schedule'!EF23","v":0},{"$f":"'K20 - time schedule'!EG23","v":0},{"$f":"'K20 - time schedule'!EH23","v":0},{"$f":"'K20 - time schedule'!EI23","v":0},{"$f":"'K20 - time schedule'!EJ23","v":0},{"$f":"'K20 - time schedule'!EK23","v":0},{"$f":"'K20 - time schedule'!EL23","v":0},{"$f":"'K20 - time schedule'!EM23","v":0},{"$f":"'K20 - time schedule'!EN23","v":0},{"$f":"'K20 - time schedule'!EO23","v":0},{"$f":"'K20 - time schedule'!EP23","v":0},{"$f":"'K20 - time schedule'!EQ23","v":0},{"$f":"'K20 - time schedule'!ER23","v":0},{"$f":"'K20 - time schedule'!ES23","v":0},{"$f":"'K20 - time schedule'!ET23","v":0},{"$f":"'K20 - time schedule'!EU23","v":0},{"$f":"'K20 - time schedule'!EV23","v":0},{"$f":"'K20 - time schedule'!EW23","v":0},{"$f":"'K20 - time schedule'!EX23","v":0},{"$f":"'K20 - time schedule'!EY23","v":0},{"$f":"'K20 - time schedule'!EZ23","v":0},{"$f":"'K20 - time schedule'!FA23","v":0},{"$f":"'K20 - time schedule'!FB23","v":0},{"$f":"'K20 - time schedule'!FC23","v":0},{"$f":"'K20 - time schedule'!FD23","v":0},{"$f":"'K20 - time schedule'!FE23","v":0},{"$f":"'K20 - time schedule'!FF23","v":0},{"$f":"'K20 - time schedule'!FG23","v":0},{"$f":"'K20 - time schedule'!FH23","v":0},{"$f":"'K20 - time schedule'!FI23","v":0},{"$f":"'K20 - time schedule'!FJ23","v":0},{"$f":"'K20 - time schedule'!FK23","v":0},{"$f":"'K20 - time schedule'!FL23","v":0},{"$f":"'K20 - time schedule'!FM23","v":0},{"$f":"'K20 - time schedule'!FN23","v":0},{"$f":"'K20 - time schedule'!FO23","v":0},{"$f":"'K20 - time schedule'!FP23","v":0},{"$f":"'K20 - time schedule'!FQ23","v":0},{"$f":"'K20 - time schedule'!FR23","v":0},{"$f":"'K20 - time schedule'!FS23","v":0},{"$f":"'K20 - time schedule'!FT23","v":0},{"$f":"'K20 - time schedule'!FU23","v":0},{"$f":"'K20 - time schedule'!FV23","v":0},{"$f":"'K20 - time schedule'!FW23","v":0},{"$f":"'K20 - time schedule'!FX23","v":0},{"$f":"'K20 - time schedule'!FY23","v":0},{"$f":"'K20 - time schedule'!FZ23","v":0},{"$f":"'K20 - time schedule'!GA23","v":0},{"$f":"'K20 - time schedule'!GB23","v":0},{"$f":"'K20 - time schedule'!GC23","v":0},{"$f":"'K20 - time schedule'!GD23","v":0},{"$f":"'K20 - time schedule'!GE23","v":0},{"$f":"'K20 - time schedule'!GF23","v":0},{"$f":"'K20 - time schedule'!GG16","v":0},{"$f":"'K20 - time schedule'!GH16","v":0},{"$f":"'K20 - time schedule'!GI16","v":0},{"$f":"'K20 - time schedule'!GJ16","v":0},{"$f":"'K20 - time schedule'!GK16","v":0},{"$f":"'K20 - time schedule'!GL16","v":0},{"$f":"'K20 - time schedule'!GM16","v":0},{"$f":"'K20 - time schedule'!GN16","v":0},{"$f":"'K20 - time schedule'!GO16","v":0},{"$f":"'K20 - time schedule'!GP16","v":0},{"$f":"'K20 - time schedule'!GQ16","v":0},{"$f":"'K20 - time schedule'!GR16","v":0},{"$f":"'K20 - time schedule'!GS16","v":0},{"$f":"'K20 - time schedule'!GT16","v":0},{"$f":"'K20 - time schedule'!GU16","v":0},{"$f":"'K20 - time schedule'!GV16","v":0},{"$f":"'K20 - time schedule'!GW16","v":0},{"$f":"'K20 - time schedule'!GX16","v":0},{"$f":"'K20 - time schedule'!GY16","v":0},{"$f":"'K20 - time schedule'!GZ16","v":0},{"$f":"'K20 - time schedule'!HA16","v":0},{"$f":"'K20 - time schedule'!HB16","v":0},{"$f":"'K20 - time schedule'!HC16","v":0},{"$f":"'K20 - time schedule'!HD16","v":0},{"$f":"'K20 - time schedule'!HE16","v":0},{"$f":"'K20 - time schedule'!HF16","v":0},{"$f":"'K20 - time schedule'!HG16","v":0},{"$f":"'K20 - time schedule'!HH16","v":0},{"$f":"'K20 - time schedule'!HI16","v":0},{"$f":"'K20 - time schedule'!HJ16","v":0},{"$f":"'K20 - time schedule'!HK16","v":0},{"$f":"'K20 - time schedule'!HL16","v":0},{"$f":"'K20 - time schedule'!HM16","v":0},{"$f":"'K20 - time schedule'!HN16","v":0},{"$f":"'K20 - time schedule'!HO16","v":0},{"$f":"'K20 - time schedule'!HP16","v":0},{"$f":"'K20 - time schedule'!HQ16","v":0},{"$f":"'K20 - time schedule'!HR16","v":0},{"$f":"'K20 - time schedule'!HS16","v":0},{"$f":"'K20 - time schedule'!HT16","v":0},{"$f":"'K20 - time schedule'!HU16","v":0},{"$f":"'K20 - time schedule'!HV16","v":0},{"$f":"'K20 - time schedule'!HW16","v":0},{"$f":"'K20 - time schedule'!HX16","v":0},{"$f":"'K20 - time schedule'!HY16","v":0},{"$f":"'K20 - time schedule'!HZ16","v":0},{"$f":"'K20 - time schedule'!IA16","v":0},{"$f":"'K20 - time schedule'!IB16","v":0},{"$f":"'K20 - time schedule'!IC16","v":0},{"$f":"'K20 - time schedule'!ID16","v":0},{"$f":"'K20 - time schedule'!IE16","v":0},{"$f":"'K20 - time schedule'!IF16","v":0},{"$f":"'K20 - time schedule'!IG16","v":0},{"$f":"'K20 - time schedule'!IH16","v":0},{"$f":"'K20 - time schedule'!II16","v":0},{"$f":"'K20 - time schedule'!IJ16","v":0},{"$f":"'K20 - time schedule'!IK16","v":0},{"$f":"'K20 - time schedule'!IL16","v":0},{"$f":"'K20 - time schedule'!IM16","v":0},{"$f":"'K20 - time schedule'!IN16","v":0},{"$f":"'K20 - time schedule'!IO16","v":0},{"$f":"'K20 - time schedule'!IP16","v":0},{"$f":"'K20 - time schedule'!IQ16","v":0},{"$f":"'K20 - time schedule'!IR16","v":0},{"$f":"'K20 - time schedule'!IS16","v":0},{"$f":"'K20 - time schedule'!IT16","v":0},{"$f":"'K20 - time schedule'!IU16","v":0},{"$f":"'K20 - time schedule'!IV16","v":0},{"$f":"'K20 - time schedule'!IW16","v":0},{"$f":"'K20 - time schedule'!IX16","v":0},{"$f":"'K20 - time schedule'!IY16","v":0},{"$f":"'K20 - time schedule'!IZ16","v":0},{"$f":"'K20 - time schedule'!JA16","v":0},{"$f":"'K20 - time schedule'!JB16","v":0},{"$f":"'K20 - time schedule'!JC16","v":0},{"$f":"'K20 - time schedule'!JD16","v":0},{"$f":"'K20 - time schedule'!JE16","v":0},{"$f":"'K20 - time schedule'!JF16","v":0},{"$f":"'K20 - time schedule'!JG16","v":0},{"$f":"'K20 - time schedule'!JH16","v":0},{"$f":"'K20 - time schedule'!JI16","v":0},{"$f":"'K20 - time schedule'!JJ16","v":0},{"$f":"'K20 - time schedule'!JK16","v":0},{"$f":"'K20 - time schedule'!JL16","v":0},{"$f":"'K20 - time schedule'!JM16","v":0},{"$f":"'K20 - time schedule'!JN16","v":0},{"$f":"'K20 - time schedule'!JO16","v":0},{"$f":"'K20 - time schedule'!JP16","v":0},{"$f":"'K20 - time schedule'!JQ16","v":0},{"$f":"'K20 - time schedule'!JR16","v":0},{"$f":"'K20 - time schedule'!JS16","v":0},{"$f":"'K20 - time schedule'!JT16","v":0},{"$f":"'K20 - time schedule'!JU16","v":0},{"$f":"'K20 - time schedule'!JV16","v":0},{"$f":"'K20 - time schedule'!JW16","v":0},{"$f":"'K20 - time schedule'!JX16","v":0},{"$f":"'K20 - time schedule'!JY16","v":0},{"$f":"'K20 - time schedule'!JZ16","v":0},{"$f":"'K20 - time schedule'!KA16","v":0},{"$f":"'K20 - time schedule'!KB16","v":0},{"$f":"'K20 - time schedule'!KC16","v":0},{"$f":"'K20 - time schedule'!KD16","v":0},{"$f":"'K20 - time schedule'!KE16","v":0},{"$f":"'K20 - time schedule'!KF16","v":0},{"$f":"'K20 - time schedule'!KG16","v":0},{"$f":"'K20 - time schedule'!KH16","v":0},{"$f":"'K20 - time schedule'!KI16","v":0},{"$f":"'K20 - time schedule'!KJ16","v":0},{"$f":"'K20 - time schedule'!KK16","v":0},{"$f":"'K20 - time schedule'!KL16","v":0},{"$f":"'K20 - time schedule'!KM16","v":0},{"$f":"'K20 - time schedule'!KN16","v":0},{"$f":"'K20 - time schedule'!KO16","v":0},{"$f":"'K20 - time schedule'!KP16","v":0},{"$f":"'K20 - time schedule'!KQ16","v":0},{"$f":"'K20 - time schedule'!KR16","v":0},{"$f":"'K20 - time schedule'!KS16","v":0},{"$f":"'K20 - time schedule'!KT16","v":0}]
["Boiler room K20 - vents (air, flue, recirculation) including inner flue lines","K20","EUR",{"$f":"'K20 - time schedule'!G25","v":0},{"$f":"'K20 - time schedule'!H25","v":0},{"$f":"'K20 - time schedule'!I25","v":0},{"$f":"'K20 - time schedule'!J25","v":0},{"$f":"'K20 - time schedule'!K25","v":0},{"$f":"'K20 - time schedule'!L25","v":0},{"$f":"'K20 - time schedule'!M25","v":0},{"$f":"'K20 - time schedule'!N25","v":0},{"$f":"'K20 - time schedule'!O25","v":0},{"$f":"'K20 - time schedule'!P25","v":0},{"$f":"'K20 - time schedule'!Q25","v":0},{"$f":"'K20 - time schedule'!R25","v":0},{"$f":"'K20 - time schedule'!S25","v":0},{"$f":"'K20 - time schedule'!T25","v":0},{"$f":"'K20 - time schedule'!U25","v":0},{"$f":"'K20 - time schedule'!V25","v":0},{"$f":"'K20 - time schedule'!W25","v":0},{"$f":"'K20 - time schedule'!X25","v":0},{"$f":"'K20 - time schedule'!Y25","v":0},{"$f":"'K20 - time schedule'!Z25","v":0},{"$f":"'K20 - time schedule'!AA25","v":0},{"$f":"'K20 - time schedule'!AB25","v":0},{"$f":"'K20 - time schedule'!AC25","v":0},{"$f":"'K20 - time schedule'!AD25","v":0},{"$f":"'K20 - time schedule'!AE25","v":0},{"$f":"'K20 - time schedule'!AF25","v":0},{"$f":"'K20 - time schedule'!AG25","v":0},{"$f":"'K20 - time schedule'!AH25","v":0},{"$f":"'K20 - time schedule'!AI25","v":0},{"$f":"'K20 - time schedule'!AJ25","v":0},{"$f":"'K20 - time schedule'!AK25","v":0},{"$f":"'K20 - time schedule'!AL25","v":0},{"$f":"'K20 - time schedule'!AM25","v":0},{"$f":"'K20 - time schedule'!AN25","v":0},{"$f":"'K20 - time schedule'!AO25","v":0},{"$f":"'K20 - time schedule'!AP25","v":0},{"$f":"'K20 - time schedule'!AQ25","v":0},{"$f":"'K20 - time schedule'!AR25","v":0},{"$f":"'K20 - time schedule'!AS25","v":0},{"$f":"'K20 - time schedule'!AT25","v":0},{"$f":"'K20 - time schedule'!AU25","v":0},{"$f":"'K20 - time schedule'!AV25","v":0},{"$f":"'K20 - time schedule'!AW25","v":0},{"$f":"'K20 - time schedule'!AX25","v":0},{"$f":"'K20 - time schedule'!AY25","v":0},{"$f":"'K20 - time schedule'!AZ25","v":0},{"$f":"'K20 - time schedule'!BA25","v":0},{"$f":"'K20 - time schedule'!BB25","v":0},{"$f":"'K20 - time schedule'!BC25","v":0},{"$f":"'K20 - time schedule'!BD25","v":0},{"$f":"'K20 - time schedule'!BE25","v":0},{"$f":"'K20 - time schedule'!BF25","v":0},{"$f":"'K20 - time schedule'!BG25","v":0},{"$f":"'K20 - time schedule'!BH25","v":0},{"$f":"'K20 - time schedule'!BI25","v":0},{"$f":"'K20 - time schedule'!BJ25","v":0},{"$f":"'K20 - time schedule'!BK25","v":0},{"$f":"'K20 - time schedule'!BL25","v":0},{"$f":"'K20 - time schedule'!BM25","v":0},{"$f":"'K20 - time schedule'!BN25","v":0},{"$f":"'K20 - time schedule'!BO25","v":0},{"$f":"'K20 - time schedule'!BP25","v":0},{"$f":"'K20 - time schedule'!BQ25","v":0},{"$f":"'K20 - time schedule'!BR25","v":0},{"$f":"'K20 - time schedule'!BS25","v":0},{"$f":"'K20 - time schedule'!BT25","v":0},{"$f":"'K20 - time schedule'!BU25","v":0},{"$f":"'K20 - time schedule'!BV25","v":0},{"$f":"'K20 - time schedule'!BW25","v":0},{"$f":"'K20 - time schedule'!BX25","v":0},{"$f":"'K20 - time schedule'!BY25","v":0},{"$f":"'K20 - time schedule'!BZ25","v":0},{"$f":"'K20 - time schedule'!CA25","v":0},{"$f":"'K20 - time schedule'!CB25","v":0},{"$f":"'K20 - time schedule'!CC25","v":0},{"$f":"'K20 - time schedule'!CD25","v":0},{"$f":"'K20 - time schedule'!CE25","v":0},{"$f":"'K20 - time schedule'!CF25","v":0},{"$f":"'K20 - time schedule'!CG25","v":0},{"$f":"'K20 - time schedule'!CH25","v":0},{"$f":"'K20 - time schedule'!CI25","v":0},{"$f":"'K20 - time schedule'!CJ25","v":0},{"$f":"'K20 - time schedule'!CK25","v":0},{"$f":"'K20 - time schedule'!CL25","v":0},{"$f":"'K20 - time schedule'!CM25","v":0},{"$f":"'K20 - time schedule'!CN25","v":0},{"$f":"'K20 - time schedule'!CO25","v":0},{"$f":"'K20 - time schedule'!CP25","v":0},{"$f":"'K20 - time schedule'!CQ25","v":0},{"$f":"'K20 - time schedule'!CR25","v":0},{"$f":"'K20 - time schedule'!CS25","v":0},{"$f":"'K20 - time schedule'!CT25","v":0},{"$f":"'K20 - time schedule'!CU25","v":0},{"$f":"'K20 - time schedule'!CV25","v":0},{"$f":"'K20 - time schedule'!CW25","v":0},{"$f":"'K20 - time schedule'!CX25","v":0},{"$f":"'K20 - time schedule'!CY25","v":0},{"$f":"'K20 - time schedule'!CZ25","v":0},{"$f":"'K20 - time schedule'!DA25","v":0},{"$f":"'K20 - time schedule'!DB25","v":0},{"$f":"'K20 - time schedule'!DC25","v":0},{"$f":"'K20 - time schedule'!DD25","v":0},{"$f":"'K20 - time schedule'!DE25","v":0},{"$f":"'K20 - time schedule'!DF25","v":0},{"$f":"'K20 - time schedule'!DG25","v":0},{"$f":"'K20 - time schedule'!DH25","v":0},{"$f":"'K20 - time schedule'!DI25","v":0},{"$f":"'K20 - time schedule'!DJ25","v":0},{"$f":"'K20 - time schedule'!DK25","v":0},{"$f":"'K20 - time schedule'!DL25","v":0},{"$f":"'K20 - time schedule'!DM25","v":0},{"$f":"'K20 - time schedule'!DN25","v":0},{"$f":"'K20 - time schedule'!DO25","v":0},{"$f":"'K20 - time schedule'!DP25","v":0},{"$f":"'K20 - time schedule'!DQ25","v":0},{"$f":"'K20 - time schedule'!DR25","v":0},{"$f":"'K20 - time schedule'!DS25","v":0},{"$f":"'K20 - time schedule'!DT25","v":0},{"$f":"'K20 - time schedule'!DU25","v":0},{"$f":"'K20 - time schedule'!DV25","v":0},{"$f":"'K20 - time schedule'!DW25","v":0},{"$f":"'K20 - time schedule'!DX25","v":0},{"$f":"'K20 - time schedule'!DY25","v":0},{"$f":"'K20 - time schedule'!DZ25","v":0},{"$f":"'K20 - time schedule'!EA25","v":0},{"$f":"'K20 - time schedule'!EB25","v":0},{"$f":"'K20 - time schedule'!EC25","v":0},{"$f":"'K20 - time schedule'!ED25","v":0},{"$f":"'K20 - time schedule'!EE25","v":0},{"$f":"'K20 - time schedule'!EF25","v":0},{"$f":"'K20 - time schedule'!EG25","v":0},{"$f":"'K20 - time schedule'!EH25","v":0},{"$f":"'K20 - time schedule'!EI25","v":0},{"$f":"'K20 - time schedule'!EJ25","v":0},{"$f":"'K20 - time schedule'!EK25","v":0},{"$f":"'K20 - time schedule'!EL25","v":0},{"$f":"'K20 - time schedule'!EM25","v":0},{"$f":"'K20 - time schedule'!EN25","v":0},{"$f":"'K20 - time schedule'!EO25","v":0},{"$f":"'K20 - time schedule'!EP25","v":0},{"$f":"'K20 - time schedule'!EQ25","v":0},{"$f":"'K20 - time schedule'!ER25","v":0},{"$f":"'K20 - time schedule'!ES25","v":0},{"$f":"'K20 - time schedule'!ET25","v":0},{"$f":"'K20 - time schedule'!EU25","v":0},{"$f":"'K20 - time schedule'!EV25","v":0},{"$f":"'K20 - time schedule'!EW25","v":0},{"$f":"'K20 - time schedule'!EX25","v":0},{"$f":"'K20 - time schedule'!EY25","v":0},{"$f":"'K20 - time schedule'!EZ25","v":0},{"$f":"'K20 - time schedule'!FA25","v":0},{"$f":"'K20 - time schedule'!FB25","v":0},{"$f":"'K20 - time schedule'!FC25","v":0},{"$f":"'K20 - time schedule'!FD25","v":0},{"$f":"'K20 - time schedule'!FE25","v":0},{"$f":"'K20 - time schedule'!FF25","v":0},{"$f":"'K20 - time schedule'!FG25","v":0},{"$f":"'K20 - time schedule'!FH25","v":0},{"$f":"'K20 - time schedule'!FI25","v":0},{"$f":"'K20 - time schedule'!FJ25","v":0},{"$f":"'K20 - time schedule'!FK25","v":0},{"$f":"'K20 - time schedule'!FL25","v":0},{"$f":"'K20 - time schedule'!FM25","v":0},{"$f":"'K20 - time schedule'!FN25","v":0},{"$f":"'K20 - time schedule'!FO25","v":0},{"$f":"'K20 - time schedule'!FP25","v":0},{"$f":"'K20 - time schedule'!FQ25","v":0},{"$f":"'K20 - time schedule'!FR25","v":0},{"$f":"'K20 - time schedule'!FS25","v":0},{"$f":"'K20 - time schedule'!FT25","v":0},{"$f":"'K20 - time schedule'!FU25","v":0},{"$f":"'K20 - time schedule'!FV25","v":0},{"$f":"'K20 - time schedule'!FW25","v":0},{"$f":"'K20 - time schedule'!FX25","v":0},{"$f":"'K20 - time schedule'!FY25","v":0},{"$f":"'K20 - time schedule'!FZ25","v":0},{"$f":"'K20 - time schedule'!GA25","v":0},{"$f":"'K20 - time schedule'!GB25","v":0},{"$f":"'K20 - time schedule'!GC25","v":0},{"$f":"'K20 - time schedule'!GD25","v":0},{"$f":"'K20 - time schedule'!GE25","v":0},{"$f":"'K20 - time schedule'!GF25","v":0},{"$f":"'K20 - time schedule'!GG17","v":0},{"$f":"'K20 - time schedule'!GH17","v":0},{"$f":"'K20 - time schedule'!GI17","v":0},{"$f":"'K20 - time schedule'!GJ17","v":0},{"$f":"'K20 - time schedule'!GK17","v":0},{"$f":"'K20 - time schedule'!GL17","v":0},{"$f":"'K20 - time schedule'!GM17","v":0},{"$f":"'K20 - time schedule'!GN17","v":0},{"$f":"'K20 - time schedule'!GO17","v":0},{"$f":"'K20 - time schedule'!GP17","v":0},{"$f":"'K20 - time schedule'!GQ17","v":0},{"$f":"'K20 - time schedule'!GR17","v":0},{"$f":"'K20 - time schedule'!GS17","v":0},{"$f":"'K20 - time schedule'!GT17","v":0},{"$f":"'K20 - time schedule'!GU17","v":0},{"$f":"'K20 - time schedule'!GV17","v":0},{"$f":"'K20 - time schedule'!GW17","v":0},{"$f":"'K20 - time schedule'!GX17","v":0},{"$f":"'K20 - time schedule'!GY17","v":0},{"$f":"'K20 - time schedule'!GZ17","v":0},{"$f":"'K20 - time schedule'!HA17","v":0},{"$f":"'K20 - time schedule'!HB17","v":0},{"$f":"'K20 - time schedule'!HC17","v":0},{"$f":"'K20 - time schedule'!HD17","v":0},{"$f":"'K20 - time schedule'!HE17","v":0},{"$f":"'K20 - time schedule'!HF17","v":0},{"$f":"'K20 - time schedule'!HG17","v":0},{"$f":"'K20 - time schedule'!HH17","v":0},{"$f":"'K20 - time schedule'!HI17","v":0},{"$f":"'K20 - time schedule'!HJ17","v":0},{"$f":"'K20 - time schedule'!HK17","v":0},{"$f":"'K20 - time schedule'!HL17","v":0},{"$f":"'K20 - time schedule'!HM17","v":0},{"$f":"'K20 - time schedule'!HN17","v":0},{"$f":"'K20 - time schedule'!HO17","v":0},{"$f":"'K20 - time schedule'!HP17","v":0},{"$f":"'K20 - time schedule'!HQ17","v":0},{"$f":"'K20 - time schedule'!HR17","v":0},{"$f":"'K20 - time schedule'!HS17","v":0},{"$f":"'K20 - time schedule'!HT17","v":0},{"$f":"'K20 - time schedule'!HU17","v":0},{"$f":"'K20 - time schedule'!HV17","v":0},{"$f":"'K20 - time schedule'!HW17","v":0},{"$f":"'K20 - time schedule'!HX17","v":0},{"$f":"'K20 - time schedule'!HY17","v":0},{"$f":"'K20 - time schedule'!HZ17","v":0},{"$f":"'K20 - time schedule'!IA17","v":0},{"$f":"'K20 - time schedule'!IB17","v":0},{"$f":"'K20 - time schedule'!IC17","v":0},{"$f":"'K20 - time schedule'!ID17","v":0},{"$f":"'K20 - time schedule'!IE17","v":0},{"$f":"'K20 - time schedule'!IF17","v":0},{"$f":"'K20 - time schedule'!IG17","v":0},{"$f":"'K20 - time schedule'!IH17","v":0},{"$f":"'K20 - time schedule'!II17","v":0},{"$f":"'K20 - time schedule'!IJ17","v":0},{"$f":"'K20 - time schedule'!IK17","v":0},{"$f":"'K20 - time schedule'!IL17","v":0},{"$f":"'K20 - time schedule'!IM17","v":0},{"$f":"'K20 - time schedule'!IN17","v":0},{"$f":"'K20 - time schedule'!IO17","v":0},{"$f":"'K20 - time schedule'!IP17","v":0},{"$f":"'K20 - time schedule'!IQ17","v":0},{"$f":"'K20 - time schedule'!IR17","v":0},{"$f":"'K20 - time schedule'!IS17","v":0},{"$f":"'K20 - time schedule'!IT17","v":0},{"$f":"'K20 - time schedule'!IU17","v":0},{"$f":"'K20 - time schedule'!IV17","v":0},{"$f":"'K20 - time schedule'!IW17","v":0},{"$f":"'K20 - time schedule'!IX17","v":0},{"$f":"'K20 - time schedule'!IY17","v":0},{"$f":"'K20 - time schedule'!IZ17","v":0},{"$f":"'K20 - time schedule'!JA17","v":0},{"$f":"'K20 - time schedule'!JB17","v":0},{"$f":"'K20 - time schedule'!JC17","v":0},{"$f":"'K20 - time schedule'!JD17","v":0},{"$f":"'K20 - time schedule'!JE17","v":0},{"$f":"'K20 - time schedule'!JF17","v":0},{"$f":"'K20 - time schedule'!JG17","v":0},{"$f":"'K20 - time schedule'!JH17","v":0},{"$f":"'K20 - time schedule'!JI17","v":0},{"$f":"'K20 - time schedule'!JJ17","v":0},{"$f":"'K20 - time schedule'!JK17","v":0},{"$f":"'K20 - time schedule'!JL17","v":0},{"$f":"'K20 - time schedule'!JM17","v":0},{"$f":"'K20 - time schedule'!JN17","v":0},{"$f":"'K20 - time schedule'!JO17","v":0},{"$f":"'K20 - time schedule'!JP17","v":0},{"$f":"'K20 - time schedule'!JQ17","v":0},{"$f":"'K20 - time schedule'!JR17","v":0},{"$f":"'K20 - time schedule'!JS17","v":0},{"$f":"'K20 - time schedule'!JT17","v":0},{"$f":"'K20 - time schedule'!JU17","v":0},{"$f":"'K20 - time schedule'!JV17","v":0},{"$f":"'K20 - time schedule'!JW17","v":0},{"$f":"'K20 - time schedule'!JX17","v":0},{"$f":"'K20 - time schedule'!JY17","v":0},{"$f":"'K20 - time schedule'!JZ17","v":0},{"$f":"'K20 - time schedule'!KA17","v":0},{"$f":"'K20 - time schedule'!KB17","v":0},{"$f":"'K20 - time schedule'!KC17","v":0},{"$f":"'K20 - time schedule'!KD17","v":0},{"$f":"'K20 - time schedule'!KE17","v":0},{"$f":"'K20 - time schedule'!KF17","v":0},{"$f":"'K20 - time schedule'!KG17","v":0},{"$f":"'K20 - time schedule'!KH17","v":0},{"$f":"'K20 - time schedule'!KI17","v":0},{"$f":"'K20 - time schedule'!KJ17","v":0},{"$f":"'K20 - time schedule'!KK17","v":0},{"$f":"'K20 - time schedule'!KL17","v":0},{"$f":"'K20 - time schedule'!KM17","v":0},{"$f":"'K20 - time schedule'!KN17","v":0},{"$f":"'K20 - time schedule'!KO17","v":0},{"$f":"'K20 - time schedule'!KP17","v":0},{"$f":"'K20 - time schedule'!KQ17","v":0},{"$f":"'K20 - time schedule'!KR17","v":0},{"$f":"'K20 - time schedule'!KS17","v":0},{"$f":"'K20 - time schedule'!KT17","v":0}]
["Boiler room K20 - fabric filter","K20","EUR",{"$f":"'K20 - time schedule'!G27","v":0},{"$f":"'K20 - time schedule'!H27","v":0},{"$f":"'K20 - time schedule'!I27","v":0},{"$f":"'K20 - time schedule'!J27","v":0},{"$f":"'K20 - time schedule'!K27","v":0},{"$f":"'K20 - time schedule'!L27","v":0},{"$f":"'K20 - time schedule'!M27","v":0},{"$f":"'K20 - time schedule'!N27","v":0},{"$f":"'K20 - time schedule'!O27","v":0},{"$f":"'K20 - time schedule'!P27","v":0},{"$f":"'K20 - time schedule'!Q27","v":0},{"$f":"'K20 - time schedule'!R27","v":0},{"$f":"'K20 - time schedule'!S27","v":0},{"$f":"'K20 - time schedule'!T27","v":0},{"$f":"'K20 - time schedule'!U27","v":0},{"$f":"'K20 - time schedule'!V27","v":0},{"$f":"'K20 - time schedule'!W27","v":0},{"$f":"'K20 - time schedule'!X27","v":0},{"$f":"'K20 - time schedule'!Y27","v":0},{"$f":"'K20 - time schedule'!Z27","v":0},{"$f":"'K20 - time schedule'!AA27","v":0},{"$f":"'K20 - time schedule'!AB27","v":0},{"$f":"'K20 - time schedule'!AC27","v":0},{"$f":"'K20 - time schedule'!AD27","v":0},{"$f":"'K20 - time schedule'!AE27","v":0},{"$f":"'K20 - time schedule'!AF27","v":0},{"$f":"'K20 - time schedule'!AG27","v":0},{"$f":"'K20 - time schedule'!AH27","v":0},{"$f":"'K20 - time schedule'!AI27","v":0},{"$f":"'K20 - time schedule'!AJ27","v":0},{"$f":"'K20 - time schedule'!AK27","v":0},{"$f":"'K20 - time schedule'!AL27","v":0},{"$f":"'K20 - time schedule'!AM27","v":0},{"$f":"'K20 - time schedule'!AN27","v":0},{"$f":"'K20 - time schedule'!AO27","v":0},{"$f":"'K20 - time schedule'!AP27","v":0},{"$f":"'K20 - time schedule'!AQ27","v":0},{"$f":"'K20 - time schedule'!AR27","v":0},{"$f":"'K20 - time schedule'!AS27","v":0},{"$f":"'K20 - time schedule'!AT27","v":0},{"$f":"'K20 - time schedule'!AU27","v":0},{"$f":"'K20 - time schedule'!AV27","v":0},{"$f":"'K20 - time schedule'!AW27","v":0},{"$f":"'K20 - time schedule'!AX27","v":0},{"$f":"'K20 - time schedule'!AY27","v":0},{"$f":"'K20 - time schedule'!AZ27","v":0},{"$f":"'K20 - time schedule'!BA27","v":0},{"$f":"'K20 - time schedule'!BB27","v":0},{"$f":"'K20 - time schedule'!BC27","v":0},{"$f":"'K20 - time schedule'!BD27","v":0},{"$f":"'K20 - time schedule'!BE27","v":0},{"$f":"'K20 - time schedule'!BF27","v":0},{"$f":"'K20 - time schedule'!BG27","v":0},{"$f":"'K20 - time schedule'!BH27","v":0},{"$f":"'K20 - time schedule'!BI27","v":0},{"$f":"'K20 - time schedule'!BJ27","v":0},{"$f":"'K20 - time schedule'!BK27","v":0},{"$f":"'K20 - time schedule'!BL27","v":0},{"$f":"'K20 - time schedule'!BM27","v":0},{"$f":"'K20 - time schedule'!BN27","v":0},{"$f":"'K20 - time schedule'!BO27","v":0},{"$f":"'K20 - time schedule'!BP27","v":0},{"$f":"'K20 - time schedule'!BQ27","v":0},{"$f":"'K20 - time schedule'!BR27","v":0},{"$f":"'K20 - time schedule'!BS27","v":0},{"$f":"'K20 - time schedule'!BT27","v":0},{"$f":"'K20 - time schedule'!BU27","v":0},{"$f":"'K20 - time schedule'!BV27","v":0},{"$f":"'K20 - time schedule'!BW27","v":0},{"$f":"'K20 - time schedule'!BX27","v":0},{"$f":"'K20 - time schedule'!BY27","v":0},{"$f":"'K20 - time schedule'!BZ27","v":0},{"$f":"'K20 - time schedule'!CA27","v":0},{"$f":"'K20 - time schedule'!CB27","v":0},{"$f":"'K20 - time schedule'!CC27","v":0},{"$f":"'K20 - time schedule'!CD27","v":0},{"$f":"'K20 - time schedule'!CE27","v":0},{"$f":"'K20 - time schedule'!CF27","v":0},{"$f":"'K20 - time schedule'!CG27","v":0},{"$f":"'K20 - time schedule'!CH27","v":0},{"$f":"'K20 - time schedule'!CI27","v":0},{"$f":"'K20 - time schedule'!CJ27","v":0},{"$f":"'K20 - time schedule'!CK27","v":0},{"$f":"'K20 - time schedule'!CL27","v":0},{"$f":"'K20 - time schedule'!CM27","v":0},{"$f":"'K20 - time schedule'!CN27","v":0},{"$f":"'K20 - time schedule'!CO27","v":0},{"$f":"'K20 - time schedule'!CP27","v":0},{"$f":"'K20 - time schedule'!CQ27","v":0},{"$f":"'K20 - time schedule'!CR27","v":0},{"$f":"'K20 - time schedule'!CS27","v":0},{"$f":"'K20 - time schedule'!CT27","v":0},{"$f":"'K20 - time schedule'!CU27","v":0},{"$f":"'K20 - time schedule'!CV27","v":0},{"$f":"'K20 - time schedule'!CW27","v":0},{"$f":"'K20 - time schedule'!CX27","v":0},{"$f":"'K20 - time schedule'!CY27","v":0},{"$f":"'K20 - time schedule'!CZ27","v":0},{"$f":"'K20 - time schedule'!DA27","v":0},{"$f":"'K20 - time schedule'!DB27","v":0},{"$f":"'K20 - time schedule'!DC27","v":0},{"$f":"'K20 - time schedule'!DD27","v":0},{"$f":"'K20 - time schedule'!DE27","v":0},{"$f":"'K20 - time schedule'!DF27","v":0},{"$f":"'K20 - time schedule'!DG27","v":0},{"$f":"'K20 - time schedule'!DH27","v":0},{"$f":"'K20 - time schedule'!DI27","v":0},{"$f":"'K20 - time schedule'!DJ27","v":0},{"$f":"'K20 - time schedule'!DK27","v":0},{"$f":"'K20 - time schedule'!DL27","v":0},{"$f":"'K20 - time schedule'!DM27","v":0},{"$f":"'K20 - time schedule'!DN27","v":0},{"$f":"'K20 - time schedule'!DO27","v":0},{"$f":"'K20 - time schedule'!DP27","v":0},{"$f":"'K20 - time schedule'!DQ27","v":0},{"$f":"'K20 - time schedule'!DR27","v":0},{"$f":"'K20 - time schedule'!DS27","v":0},{"$f":"'K20 - time schedule'!DT27","v":0},{"$f":"'K20 - time schedule'!DU27","v":0},{"$f":"'K20 - time schedule'!DV27","v":0},{"$f":"'K20 - time schedule'!DW27","v":0},{"$f":"'K20 - time schedule'!DX27","v":0},{"$f":"'K20 - time schedule'!DY27","v":0},{"$f":"'K20 - time schedule'!DZ27","v":0},{"$f":"'K20 - time schedule'!EA27","v":0},{"$f":"'K20 - time schedule'!EB27","v":0},{"$f":"'K20 - time schedule'!EC27","v":0},{"$f":"'K20 - time schedule'!ED27","v":0},{"$f":"'K20 - time schedule'!EE27","v":0},{"$f":"'K20 - time schedule'!EF27","v":0},{"$f":"'K20 - time schedule'!EG27","v":0},{"$f":"'K20 - time schedule'!EH27","v":0},{"$f":"'K20 - time schedule'!EI27","v":0},{"$f":"'K20 - time schedule'!EJ27","v":0},{"$f":"'K20 - time schedule'!EK27","v":0},{"$f":"'K20 - time schedule'!EL27","v":0},{"$f":"'K20 - time schedule'!EM27","v":0},{"$f":"'K20 - time schedule'!EN27","v":0},{"$f":"'K20 - time schedule'!EO27","v":0},{"$f":"'K20 - time schedule'!EP27","v":0},{"$f":"'K20 - time schedule'!EQ27","v":0},{"$f":"'K20 - time schedule'!ER27","v":0},{"$f":"'K20 - time schedule'!ES27","v":0},{"$f":"'K20 - time schedule'!ET27","v":0},{"$f":"'K20 - time schedule'!EU27","v":0},{"$f":"'K20 - time schedule'!EV27","v":0},{"$f":"'K20 - time schedule'!EW27","v":0},{"$f":"'K20 - time schedule'!EX27","v":0},{"$f":"'K20 - time schedule'!EY27","v":0},{"$f":"'K20 - time schedule'!EZ27","v":0},{"$f":"'K20 - time schedule'!FA27","v":0},{"$f":"'K20 - time schedule'!FB27","v":0},{"$f":"'K20 - time schedule'!FC27","v":0},{"$f":"'K20 - time schedule'!FD27","v":0},{"$f":"'K20 - time schedule'!FE27","v":0},{"$f":"'K20 - time schedule'!FF27","v":0},{"$f":"'K20 - time schedule'!FG27","v":0},{"$f":"'K20 - time schedule'!FH27","v":0},{"$f":"'K20 - time schedule'!FI27","v":0},{"$f":"'K20 - time schedule'!FJ27","v":0},{"$f":"'K20 - time schedule'!FK27","v":0},{"$f":"'K20 - time schedule'!FL27","v":0},{"$f":"'K20 - time schedule'!FM27","v":0},{"$f":"'K20 - time schedule'!FN27","v":0},{"$f":"'K20 - time schedule'!FO27","v":0},{"$f":"'K20 - time schedule'!FP27","v":0},{"$f":"'K20 - time schedule'!FQ27","v":0},{"$f":"'K20 - time schedule'!FR27","v":0},{"$f":"'K20 - time schedule'!FS27","v":0},{"$f":"'K20 - time schedule'!FT27","v":0},{"$f":"'K20 - time schedule'!FU27","v":0},{"$f":"'K20 - time schedule'!FV27","v":0},{"$f":"'K20 - time schedule'!FW27","v":0},{"$f":"'K20 - time schedule'!FX27","v":0},{"$f":"'K20 - time schedule'!FY27","v":0},{"$f":"'K20 - time schedule'!FZ27","v":0},{"$f":"'K20 - time schedule'!GA27","v":0},{"$f":"'K20 - time schedule'!GB27","v":0},{"$f":"'K20 - time schedule'!GC27","v":0},{"$f":"'K20 - time schedule'!GD27","v":0},{"$f":"'K20 - time schedule'!GE27","v":0},{"$f":"'K20 - time schedule'!GF27","v":0},{"$f":"'K20 - time schedule'!GG18","v":0},{"$f":"'K20 - time schedule'!GH18","v":0},{"$f":"'K20 - time schedule'!GI18","v":0},{"$f":"'K20 - time schedule'!GJ18","v":0},{"$f":"'K20 - time schedule'!GK18","v":0},{"$f":"'K20 - time schedule'!GL18","v":0},{"$f":"'K20 - time schedule'!GM18","v":0},{"$f":"'K20 - time schedule'!GN18","v":0},{"$f":"'K20 - time schedule'!GO18","v":0},{"$f":"'K20 - time schedule'!GP18","v":0},{"$f":"'K20 - time schedule'!GQ18","v":0},{"$f":"'K20 - time schedule'!GR18","v":0},{"$f":"'K20 - time schedule'!GS18","v":0},{"$f":"'K20 - time schedule'!GT18","v":0},{"$f":"'K20 - time schedule'!GU18","v":0},{"$f":"'K20 - time schedule'!GV18","v":0},{"$f":"'K20 - time schedule'!GW18","v":0},{"$f":"'K20 - time schedule'!GX18","v":0},{"$f":"'K20 - time schedule'!GY18","v":0},{"$f":"'K20 - time schedule'!GZ18","v":0},{"$f":"'K20 - time schedule'!HA18","v":0},{"$f":"'K20 - time schedule'!HB18","v":0},{"$f":"'K20 - time schedule'!HC18","v":0},{"$f":"'K20 - time schedule'!HD18","v":0},{"$f":"'K20 - time schedule'!HE18","v":0},{"$f":"'K20 - time schedule'!HF18","v":0},{"$f":"'K20 - time schedule'!HG18","v":0},{"$f":"'K20 - time schedule'!HH18","v":0},{"$f":"'K20 - time schedule'!HI18","v":0},{"$f":"'K20 - time schedule'!HJ18","v":0},{"$f":"'K20 - time schedule'!HK18","v":0},{"$f":"'K20 - time schedule'!HL18","v":0},{"$f":"'K20 - time schedule'!HM18","v":0},{"$f":"'K20 - time schedule'!HN18","v":0},{"$f":"'K20 - time schedule'!HO18","v":0},{"$f":"'K20 - time schedule'!HP18","v":0},{"$f":"'K20 - time schedule'!HQ18","v":0},{"$f":"'K20 - time schedule'!HR18","v":0},{"$f":"'K20 - time schedule'!HS18","v":0},{"$f":"'K20 - time schedule'!HT18","v":0},{"$f":"'K20 - time schedule'!HU18","v":0},{"$f":"'K20 - time schedule'!HV18","v":0},{"$f":"'K20 - time schedule'!HW18","v":0},{"$f":"'K20 - time schedule'!HX18","v":0},{"$f":"'K20 - time schedule'!HY18","v":0},{"$f":"'K20 - time schedule'!HZ18","v":0},{"$f":"'K20 - time schedule'!IA18","v":0},{"$f":"'K20 - time schedule'!IB18","v":0},{"$f":"'K20 - time schedule'!IC18","v":0},{"$f":"'K20 - time schedule'!ID18","v":0},{"$f":"'K20 - time schedule'!IE18","v":0},{"$f":"'K20 - time schedule'!IF18","v":0},{"$f":"'K20 - time schedule'!IG18","v":0},{"$f":"'K20 - time schedule'!IH18","v":0},{"$f":"'K20 - time schedule'!II18","v":0},{"$f":"'K20 - time schedule'!IJ18","v":0},{"$f":"'K20 - time schedule'!IK18","v":0},{"$f":"'K20 - time schedule'!IL18","v":0},{"$f":"'K20 - time schedule'!IM18","v":0},{"$f":"'K20 - time schedule'!IN18","v":0},{"$f":"'K20 - time schedule'!IO18","v":0},{"$f":"'K20 - time schedule'!IP18","v":0},{"$f":"'K20 - time schedule'!IQ18","v":0},{"$f":"'K20 - time schedule'!IR18","v":0},{"$f":"'K20 - time schedule'!IS18","v":0},{"$f":"'K20 - time schedule'!IT18","v":0},{"$f":"'K20 - time schedule'!IU18","v":0},{"$f":"'K20 - time schedule'!IV18","v":0},{"$f":"'K20 - time schedule'!IW18","v":0},{"$f":"'K20 - time schedule'!IX18","v":0},{"$f":"'K20 - time schedule'!IY18","v":0},{"$f":"'K20 - time schedule'!IZ18","v":0},{"$f":"'K20 - time schedule'!JA18","v":0},{"$f":"'K20 - time schedule'!JB18","v":0},{"$f":"'K20 - time schedule'!JC18","v":0},{"$f":"'K20 - time schedule'!JD18","v":0},{"$f":"'K20 - time schedule'!JE18","v":0},{"$f":"'K20 - time schedule'!JF18","v":0},{"$f":"'K20 - time schedule'!JG18","v":0},{"$f":"'K20 - time schedule'!JH18","v":0},{"$f":"'K20 - time schedule'!JI18","v":0},{"$f":"'K20 - time schedule'!JJ18","v":0},{"$f":"'K20 - time schedule'!JK18","v":0},{"$f":"'K20 - time schedule'!JL18","v":0},{"$f":"'K20 - time schedule'!JM18","v":0},{"$f":"'K20 - time schedule'!JN18","v":0},{"$f":"'K20 - time schedule'!JO18","v":0},{"$f":"'K20 - time schedule'!JP18","v":0},{"$f":"'K20 - time schedule'!JQ18","v":0},{"$f":"'K20 - time schedule'!JR18","v":0},{"$f":"'K20 - time schedule'!JS18","v":0},{"$f":"'K20 - time schedule'!JT18","v":0},{"$f":"'K20 - time schedule'!JU18","v":0},{"$f":"'K20 - time schedule'!JV18","v":0},{"$f":"'K20 - time schedule'!JW18","v":0},{"$f":"'K20 - time schedule'!JX18","v":0},{"$f":"'K20 - time schedule'!JY18","v":0},{"$f":"'K20 - time schedule'!JZ18","v":0},{"$f":"'K20 - time schedule'!KA18","v":0},{"$f":"'K20 - time schedule'!KB18","v":0},{"$f":"'K20 - time schedule'!KC18","v":0},{"$f":"'K20 - time schedule'!KD18","v":0},{"$f":"'K20 - time schedule'!KE18","v":0},{"$f":"'K20 - time schedule'!KF18","v":0},{"$f":"'K20 - time schedule'!KG18","v":0},{"$f":"'K20 - time schedule'!KH18","v":0},{"$f":"'K20 - time schedule'!KI18","v":0},{"$f":"'K20 - time schedule'!KJ18","v":0},{"$f":"'K20 - time schedule'!KK18","v":0},{"$f":"'K20 - time schedule'!KL18","v":0},{"$f":"'K20 - time schedule'!KM18","v":0},{"$f":"'K20 - time schedule'!KN18","v":0},{"$f":"'K20 - time schedule'!KO18","v":0},{"$f":"'K20 - time schedule'!KP18","v":0},{"$f":"'K20 - time schedule'!KQ18","v":0},{"$f":"'K20 - time schedule'!KR18","v":0},{"$f":"'K20 - time schedule'!KS18","v":0},{"$f":"'K20 - time schedule'!KT18","v":0}]
["Boiler room K20 - DSI technology","K20","EUR",{"$f":"'K20 - time schedule'!G29","v":0},{"$f":"'K20 - time schedule'!H29","v":0},{"$f":"'K20 - time schedule'!I29","v":0},{"$f":"'K20 - time schedule'!J29","v":0},{"$f":"'K20 - time schedule'!K29","v":0},{"$f":"'K20 - time schedule'!L29","v":0},{"$f":"'K20 - time schedule'!M29","v":0},{"$f":"'K20 - time schedule'!N29","v":0},{"$f":"'K20 - time schedule'!O29","v":0},{"$f":"'K20 - time schedule'!P29","v":0},{"$f":"'K20 - time schedule'!Q29","v":0},{"$f":"'K20 - time schedule'!R29","v":0},{"$f":"'K20 - time schedule'!S29","v":0},{"$f":"'K20 - time schedule'!T29","v":0},{"$f":"'K20 - time schedule'!U29","v":0},{"$f":"'K20 - time schedule'!V29","v":0},{"$f":"'K20 - time schedule'!W29","v":0},{"$f":"'K20 - time schedule'!X29","v":0},{"$f":"'K20 - time schedule'!Y29","v":0},{"$f":"'K20 - time schedule'!Z29","v":0},{"$f":"'K20 - time schedule'!AA29","v":0},{"$f":"'K20 - time schedule'!AB29","v":0},{"$f":"'K20 - time schedule'!AC29","v":0},{"$f":"'K20 - time schedule'!AD29","v":0},{"$f":"'K20 - time schedule'!AE29","v":0},{"$f":"'K20 - time schedule'!AF29","v":0},{"$f":"'K20 - time schedule'!AG29","v":0},{"$f":"'K20 - time schedule'!AH29","v":0},{"$f":"'K20 - time schedule'!AI29","v":0},{"$f":"'K20 - time schedule'!AJ29","v":0},{"$f":"'K20 - time schedule'!AK29","v":0},{"$f":"'K20 - time schedule'!AL29","v":0},{"$f":"'K20 - time schedule'!AM29","v":0},{"$f":"'K20 - time schedule'!AN29","v":0},{"$f":"'K20 - time schedule'!AO29","v":0},{"$f":"'K20 - time schedule'!AP29","v":0},{"$f":"'K20 - time schedule'!AQ29","v":0},{"$f":"'K20 - time schedule'!AR29","v":0},{"$f":"'K20 - time schedule'!AS29","v":0},{"$f":"'K20 - time schedule'!AT29","v":0},{"$f":"'K20 - time schedule'!AU29","v":0},{"$f":"'K20 - time schedule'!AV29","v":0},{"$f":"'K20 - time schedule'!AW29","v":0},{"$f":"'K20 - time schedule'!AX29","v":0},{"$f":"'K20 - time schedule'!AY29","v":0},{"$f":"'K20 - time schedule'!AZ29","v":0},{"$f":"'K20 - time schedule'!BA29","v":0},{"$f":"'K20 - time schedule'!BB29","v":0},{"$f":"'K20 - time schedule'!BC29","v":0},{"$f":"'K20 - time schedule'!BD29","v":0},{"$f":"'K20 - time schedule'!BE29","v":0},{"$f":"'K20 - time schedule'!BF29","v":0},{"$f":"'K20 - time schedule'!BG29","v":0},{"$f":"'K20 - time schedule'!BH29","v":0},{"$f":"'K20 - time schedule'!BI29","v":0},{"$f":"'K20 - time schedule'!BJ29","v":0},{"$f":"'K20 - time schedule'!BK29","v":0},{"$f":"'K20 - time schedule'!BL29","v":0},{"$f":"'K20 - time schedule'!BM29","v":0},{"$f":"'K20 - time schedule'!BN29","v":0},{"$f":"'K20 - time schedule'!BO29","v":0},{"$f":"'K20 - time schedule'!BP29","v":0},{"$f":"'K20 - time schedule'!BQ29","v":0},{"$f":"'K20 - time schedule'!BR29","v":0},{"$f":"'K20 - time schedule'!BS29","v":0},{"$f":"'K20 - time schedule'!BT29","v":0},{"$f":"'K20 - time schedule'!BU29","v":0},{"$f":"'K20 - time schedule'!BV29","v":0},{"$f":"'K20 - time schedule'!BW29","v":0},{"$f":"'K20 - time schedule'!BX29","v":0},{"$f":"'K20 - time schedule'!BY29","v":0},{"$f":"'K20 - time schedule'!BZ29","v":0},{"$f":"'K20 - time schedule'!CA29","v":0},{"$f":"'K20 - time schedule'!CB29","v":0},{"$f":"'K20 - time schedule'!CC29","v":0},{"$f":"'K20 - time schedule'!CD29","v":0},{"$f":"'K20 - time schedule'!CE29","v":0},{"$f":"'K20 - time schedule'!CF29","v":0},{"$f":"'K20 - time schedule'!CG29","v":0},{"$f":"'K20 - time schedule'!CH29","v":0},{"$f":"'K20 - time schedule'!CI29","v":0},{"$f":"'K20 - time schedule'!CJ29","v":0},{"$f":"'K20 - time schedule'!CK29","v":0},{"$f":"'K20 - time schedule'!CL29","v":0},{"$f":"'K20 - time schedule'!CM29","v":0},{"$f":"'K20 - time schedule'!CN29","v":0},{"$f":"'K20 - time schedule'!CO29","v":0},{"$f":"'K20 - time schedule'!CP29","v":0},{"$f":"'K20 - time schedule'!CQ29","v":0},{"$f":"'K20 - time schedule'!CR29","v":0},{"$f":"'K20 - time schedule'!CS29","v":0},{"$f":"'K20 - time schedule'!CT29","v":0},{"$f":"'K20 - time schedule'!CU29","v":0},{"$f":"'K20 - time schedule'!CV29","v":0},{"$f":"'K20 - time schedule'!CW29","v":0},{"$f":"'K20 - time schedule'!CX29","v":0},{"$f":"'K20 - time schedule'!CY29","v":0},{"$f":"'K20 - time schedule'!CZ29","v":0},{"$f":"'K20 - time schedule'!DA29","v":0},{"$f":"'K20 - time schedule'!DB29","v":0},{"$f":"'K20 - time schedule'!DC29","v":0},{"$f":"'K20 - time schedule'!DD29","v":0},{"$f":"'K20 - time schedule'!DE29","v":0},{"$f":"'K20 - time schedule'!DF29","v":0},{"$f":"'K20 - time schedule'!DG29","v":0},{"$f":"'K20 - time schedule'!DH29","v":0},{"$f":"'K20 - time schedule'!DI29","v":0},{"$f":"'K20 - time schedule'!DJ29","v":0},{"$f":"'K20 - time schedule'!DK29","v":0},{"$f":"'K20 - time schedule'!DL29","v":0},{"$f":"'K20 - time schedule'!DM29","v":0},{"$f":"'K20 - time schedule'!DN29","v":0},{"$f":"'K20 - time schedule'!DO29","v":0},{"$f":"'K20 - time schedule'!DP29","v":0},{"$f":"'K20 - time schedule'!DQ29","v":0},{"$f":"'K20 - time schedule'!DR29","v":0},{"$f":"'K20 - time schedule'!DS29","v":0},{"$f":"'K20 - time schedule'!DT29","v":0},{"$f":"'K20 - time schedule'!DU29","v":0},{"$f":"'K20 - time schedule'!DV29","v":0},{"$f":"'K20 - time schedule'!DW29","v":0},{"$f":"'K20 - time schedule'!DX29","v":0},{"$f":"'K20 - time schedule'!DY29","v":0},{"$f":"'K20 - time schedule'!DZ29","v":0},{"$f":"'K20 - time schedule'!EA29","v":0},{"$f":"'K20 - time schedule'!EB29","v":0},{"$f":"'K20 - time schedule'!EC29","v":0},{"$f":"'K20 - time schedule'!ED29","v":0},{"$f":"'K20 - time schedule'!EE29","v":0},{"$f":"'K20 - time schedule'!EF29","v":0},{"$f":"'K20 - time schedule'!EG29","v":0},{"$f":"'K20 - time schedule'!EH29","v":0},{"$f":"'K20 - time schedule'!EI29","v":0},{"$f":"'K20 - time schedule'!EJ29","v":0},{"$f":"'K20 - time schedule'!EK29","v":0},{"$f":"'K20 - time schedule'!EL29","v":0},{"$f":"'K20 - time schedule'!EM29","v":0},{"$f":"'K20 - time schedule'!EN29","v":0},{"$f":"'K20 - time schedule'!EO29","v":0},{"$f":"'K20 - time schedule'!EP29","v":0},{"$f":"'K20 - time schedule'!EQ29","v":0},{"$f":"'K20 - time schedule'!ER29","v":0},{"$f":"'K20 - time schedule'!ES29","v":0},{"$f":"'K20 - time schedule'!ET29","v":0},{"$f":"'K20 - time schedule'!EU29","v":0},{"$f":"'K20 - time schedule'!EV29","v":0},{"$f":"'K20 - time schedule'!EW29","v":0},{"$f":"'K20 - time schedule'!EX29","v":0},{"$f":"'K20 - time schedule'!EY29","v":0},{"$f":"'K20 - time schedule'!EZ29","v":0},{"$f":"'K20 - time schedule'!FA29","v":0},{"$f":"'K20 - time schedule'!FB29","v":0},{"$f":"'K20 - time schedule'!FC29","v":0},{"$f":"'K20 - time schedule'!FD29","v":0},{"$f":"'K20 - time schedule'!FE29","v":0},{"$f":"'K20 - time schedule'!FF29","v":0},{"$f":"'K20 - time schedule'!FG29","v":0},{"$f":"'K20 - time schedule'!FH29","v":0},{"$f":"'K20 - time schedule'!FI29","v":0},{"$f":"'K20 - time schedule'!FJ29","v":0},{"$f":"'K20 - time schedule'!FK29","v":0},{"$f":"'K20 - time schedule'!FL29","v":0},{"$f":"'K20 - time schedule'!FM29","v":0},{"$f":"'K20 - time schedule'!FN29","v":0},{"$f":"'K20 - time schedule'!FO29","v":0},{"$f":"'K20 - time schedule'!FP29","v":0},{"$f":"'K20 - time schedule'!FQ29","v":0},{"$f":"'K20 - time schedule'!FR29","v":0},{"$f":"'K20 - time schedule'!FS29","v":0},{"$f":"'K20 - time schedule'!FT29","v":0},{"$f":"'K20 - time schedule'!FU29","v":0},{"$f":"'K20 - time schedule'!FV29","v":0},{"$f":"'K20 - time schedule'!FW29","v":0},{"$f":"'K20 - time schedule'!FX29","v":0},{"$f":"'K20 - time schedule'!FY29","v":0},{"$f":"'K20 - time schedule'!FZ29","v":0},{"$f":"'K20 - time schedule'!GA29","v":0},{"$f":"'K20 - time schedule'!GB29","v":0},{"$f":"'K20 - time schedule'!GC29","v":0},{"$f":"'K20 - time schedule'!GD29","v":0},{"$f":"'K20 - time schedule'!GE29","v":0},{"$f":"'K20 - time schedule'!GF29","v":0},{"$f":"'K20 - time schedule'!GG19","v":0},{"$f":"'K20 - time schedule'!GH19","v":0},{"$f":"'K20 - time schedule'!GI19","v":0},{"$f":"'K20 - time schedule'!GJ19","v":"Kotelna K20 - tkaninový filtr"},{"$f":"'K20 - time schedule'!GK19","v":0},{"$f":"'K20 - time schedule'!GL19","v":0},{"$f":"'K20 - time schedule'!GM19","v":0},{"$f":"'K20 - time schedule'!GN19","v":0},{"$f":"'K20 - time schedule'!GO19","v":0},{"$f":"'K20 - time schedule'!GP19","v":0},{"$f":"'K20 - time schedule'!GQ19","v":0},{"$f":"'K20 - time schedule'!GR19","v":0},{"$f":"'K20 - time schedule'!GS19","v":0},{"$f":"'K20 - time schedule'!GT19","v":0},{"$f":"'K20 - time schedule'!GU19","v":0},{"$f":"'K20 - time schedule'!GV19","v":0},{"$f":"'K20 - time schedule'!GW19","v":0},{"$f":"'K20 - time schedule'!GX19","v":0},{"$f":"'K20 - time schedule'!GY19","v":0},{"$f":"'K20 - time schedule'!GZ19","v":0},{"$f":"'K20 - time schedule'!HA19","v":0},{"$f":"'K20 - time schedule'!HB19","v":0},{"$f":"'K20 - time schedule'!HC19","v":0},{"$f":"'K20 - time schedule'!HD19","v":0},{"$f":"'K20 - time schedule'!HE19","v":0},{"$f":"'K20 - time schedule'!HF19","v":0},{"$f":"'K20 - time schedule'!HG19","v":0},{"$f":"'K20 - time schedule'!HH19","v":0},{"$f":"'K20 - time schedule'!HI19","v":0},{"$f":"'K20 - time schedule'!HJ19","v":0},{"$f":"'K20 - time schedule'!HK19","v":0},{"$f":"'K20 - time schedule'!HL19","v":0},{"$f":"'K20 - time schedule'!HM19","v":0},{"$f":"'K20 - time schedule'!HN19","v":0},{"$f":"'K20 - time schedule'!HO19","v":0},{"$f":"'K20 - time schedule'!HP19","v":0},{"$f":"'K20 - time schedule'!HQ19","v":0},{"$f":"'K20 - time schedule'!HR19","v":0},{"$f":"'K20 - time schedule'!HS19","v":0},{"$f":"'K20 - time schedule'!HT19","v":0},{"$f":"'K20 - time schedule'!HU19","v":0},{"$f":"'K20 - time schedule'!HV19","v":0},{"$f":"'K20 - time schedule'!HW19","v":0},{"$f":"'K20 - time schedule'!HX19","v":0},{"$f":"'K20 - time schedule'!HY19","v":0},{"$f":"'K20 - time schedule'!HZ19","v":0},{"$f":"'K20 - time schedule'!IA19","v":0},{"$f":"'K20 - time schedule'!IB19","v":0},{"$f":"'K20 - time schedule'!IC19","v":0},{"$f":"'K20 - time schedule'!ID19","v":0},{"$f":"'K20 - time schedule'!IE19","v":0},{"$f":"'K20 - time schedule'!IF19","v":0},{"$f":"'K20 - time schedule'!IG19","v":0},{"$f":"'K20 - time schedule'!IH19","v":0},{"$f":"'K20 - time schedule'!II19","v":0},{"$f":"'K20 - time schedule'!IJ19","v":0},{"$f":"'K20 - time schedule'!IK19","v":0},{"$f":"'K20 - time schedule'!IL19","v":0},{"$f":"'K20 - time schedule'!IM19","v":0},{"$f":"'K20 - time schedule'!IN19","v":0},{"$f":"'K20 - time schedule'!IO19","v":0},{"$f":"'K20 - time schedule'!IP19","v":0},{"$f":"'K20 - time schedule'!IQ19","v":0},{"$f":"'K20 - time schedule'!IR19","v":0},{"$f":"'K20 - time schedule'!IS19","v":0},{"$f":"'K20 - time schedule'!IT19","v":0},{"$f":"'K20 - time schedule'!IU19","v":0},{"$f":"'K20 - time schedule'!IV19","v":0},{"$f":"'K20 - time schedule'!IW19","v":0},{"$f":"'K20 - time schedule'!IX19","v":0},{"$f":"'K20 - time schedule'!IY19","v":0},{"$f":"'K20 - time schedule'!IZ19","v":0},{"$f":"'K20 - time schedule'!JA19","v":0},{"$f":"'K20 - time schedule'!JB19","v":0},{"$f":"'K20 - time schedule'!JC19","v":0},{"$f":"'K20 - time schedule'!JD19","v":0},{"$f":"'K20 - time schedule'!JE19","v":0},{"$f":"'K20 - time schedule'!JF19","v":0},{"$f":"'K20 - time schedule'!JG19","v":0},{"$f":"'K20 - time schedule'!JH19","v":0},{"$f":"'K20 - time schedule'!JI19","v":0},{"$f":"'K20 - time schedule'!JJ19","v":0},{"$f":"'K20 - time schedule'!JK19","v":0},{"$f":"'K20 - time schedule'!JL19","v":0},{"$f":"'K20 - time schedule'!JM19","v":0},{"$f":"'K20 - time schedule'!JN19","v":0},{"$f":"'K20 - time schedule'!JO19","v":0},{"$f":"'K20 - time schedule'!JP19","v":0},{"$f":"'K20 - time schedule'!JQ19","v":0},{"$f":"'K20 - time schedule'!JR19","v":0},{"$f":"'K20 - time schedule'!JS19","v":0},{"$f":"'K20 - time schedule'!JT19","v":0},{"$f":"'K20 - time schedule'!JU19","v":0},{"$f":"'K20 - time schedule'!JV19","v":0},{"$f":"'K20 - time schedule'!JW19","v":0},{"$f":"'K20 - time schedule'!JX19","v":0},{"$f":"'K20 - time schedule'!JY19","v":0},{"$f":"'K20 - time schedule'!JZ19","v":0},{"$f":"'K20 - time schedule'!KA19","v":0},{"$f":"'K20 - time schedule'!KB19","v":0},{"$f":"'K20 - time schedule'!KC19","v":0},{"$f":"'K20 - time schedule'!KD19","v":0},{"$f":"'K20 - time schedule'!KE19","v":0},{"$f":"'K20 - time schedule'!KF19","v":0},{"$f":"'K20 - time schedule'!KG19","v":0},{"$f":"'K20 - time schedule'!KH19","v":0},{"$f":"'K20 - time schedule'!KI19","v":0},{"$f":"'K20 - time schedule'!KJ19","v":0},{"$f":"'K20 - time schedule'!KK19","v":0},{"$f":"'K20 - time schedule'!KL19","v":0},{"$f":"'K20 - time schedule'!KM19","v":0},{"$f":"'K20 - time schedule'!KN19","v":0},{"$f":"'K20 - time schedule'!KO19","v":0},{"$f":"'K20 - time schedule'!KP19","v":0},{"$f":"'K20 - time schedule'!KQ19","v":0},{"$f":"'K20 - time schedule'!KR19","v":0},{"$f":"'K20 - time schedule'!KS19","v":0},{"$f":"'K20 - time schedule'!KT19","v":0}]
["Boiler room K20 - cooler and sorter of ash","K20","EUR",{"$f":"'K20 - time schedule'!G31","v":0},{"$f":"'K20 - time schedule'!H31","v":0},{"$f":"'K20 - time schedule'!I31","v":0},{"$f":"'K20 - time schedule'!J31","v":0},{"$f":"'K20 - time schedule'!K31","v":0},{"$f":"'K20 - time schedule'!L31","v":0},{"$f":"'K20 - time schedule'!M31","v":0},{"$f":"'K20 - time schedule'!N31","v":0},{"$f":"'K20 - time schedule'!O31","v":0},{"$f":"'K20 - time schedule'!P31","v":0},{"$f":"'K20 - time schedule'!Q31","v":0},{"$f":"'K20 - time schedule'!R31","v":0},{"$f":"'K20 - time schedule'!S31","v":0},{"$f":"'K20 - time schedule'!T31","v":0},{"$f":"'K20 - time schedule'!U31","v":0},{"$f":"'K20 - time schedule'!V31","v":0},{"$f":"'K20 - time schedule'!W31","v":0},{"$f":"'K20 - time schedule'!X31","v":0},{"$f":"'K20 - time schedule'!Y31","v":0},{"$f":"'K20 - time schedule'!Z31","v":0},{"$f":"'K20 - time schedule'!AA31","v":0},{"$f":"'K20 - time schedule'!AB31","v":0},{"$f":"'K20 - time schedule'!AC31","v":0},{"$f":"'K20 - time schedule'!AD31","v":0},{"$f":"'K20 - time schedule'!AE31","v":0},{"$f":"'K20 - time schedule'!AF31","v":0},{"$f":"'K20 - time schedule'!AG31","v":0},{"$f":"'K20 - time schedule'!AH31","v":0},{"$f":"'K20 - time schedule'!AI31","v":0},{"$f":"'K20 - time schedule'!AJ31","v":0},{"$f":"'K20 - time schedule'!AK31","v":0},{"$f":"'K20 - time schedule'!AL31","v":0},{"$f":"'K20 - time schedule'!AM31","v":0},{"$f":"'K20 - time schedule'!AN31","v":0},{"$f":"'K20 - time schedule'!AO31","v":0},{"$f":"'K20 - time schedule'!AP31","v":0},{"$f":"'K20 - time schedule'!AQ31","v":0},{"$f":"'K20 - time schedule'!AR31","v":0},{"$f":"'K20 - time schedule'!AS31","v":0},{"$f":"'K20 - time schedule'!AT31","v":0},{"$f":"'K20 - time schedule'!AU31","v":0},{"$f":"'K20 - time schedule'!AV31","v":0},{"$f":"'K20 - time schedule'!AW31","v":0},{"$f":"'K20 - time schedule'!AX31","v":0},{"$f":"'K20 - time schedule'!AY31","v":0},{"$f":"'K20 - time schedule'!AZ31","v":0},{"$f":"'K20 - time schedule'!BA31","v":0},{"$f":"'K20 - time schedule'!BB31","v":0},{"$f":"'K20 - time schedule'!BC31","v":0},{"$f":"'K20 - time schedule'!BD31","v":0},{"$f":"'K20 - time schedule'!BE31","v":0},{"$f":"'K20 - time schedule'!BF31","v":0},{"$f":"'K20 - time schedule'!BG31","v":0},{"$f":"'K20 - time schedule'!BH31","v":0},{"$f":"'K20 - time schedule'!BI31","v":0},{"$f":"'K20 - time schedule'!BJ31","v":0},{"$f":"'K20 - time schedule'!BK31","v":0},{"$f":"'K20 - time schedule'!BL31","v":0},{"$f":"'K20 - time schedule'!BM31","v":0},{"$f":"'K20 - time schedule'!BN31","v":0},{"$f":"'K20 - time schedule'!BO31","v":0},{"$f":"'K20 - time schedule'!BP31","v":0},{"$f":"'K20 - time schedule'!BQ31","v":0},{"$f":"'K20 - time schedule'!BR31","v":0},{"$f":"'K20 - time schedule'!BS31","v":0},{"$f":"'K20 - time schedule'!BT31","v":0},{"$f":"'K20 - time schedule'!BU31","v":0},{"$f":"'K20 - time schedule'!BV31","v":0},{"$f":"'K20 - time schedule'!BW31","v":0},{"$f":"'K20 - time schedule'!BX31","v":0},{"$f":"'K20 - time schedule'!BY31","v":0},{"$f":"'K20 - time schedule'!BZ31","v":0},{"$f":"'K20 - time schedule'!CA31","v":0},{"$f":"'K20 - time schedule'!CB31","v":0},{"$f":"'K20 - time schedule'!CC31","v":0},{"$f":"'K20 - time schedule'!CD31","v":0},{"$f":"'K20 - time schedule'!CE31","v":0},{"$f":"'K20 - time schedule'!CF31","v":0},{"$f":"'K20 - time schedule'!CG31","v":0},{"$f":"'K20 - time schedule'!CH31","v":0},{"$f":"'K20 - time schedule'!CI31","v":0},{"$f":"'K20 - time schedule'!CJ31","v":0},{"$f":"'K20 - time schedule'!CK31","v":0},{"$f":"'K20 - time schedule'!CL31","v":0},{"$f":"'K20 - time schedule'!CM31","v":0},{"$f":"'K20 - time schedule'!CN31","v":0},{"$f":"'K20 - time schedule'!CO31","v":0},{"$f":"'K20 - time schedule'!CP31","v":0},{"$f":"'K20 - time schedule'!CQ31","v":0},{"$f":"'K20 - time schedule'!CR31","v":0},{"$f":"'K20 - time schedule'!CS31","v":0},{"$f":"'K20 - time schedule'!CT31","v":0},{"$f":"'K20 - time schedule'!CU31","v":0},{"$f":"'K20 - time schedule'!CV31","v":0},{"$f":"'K20 - time schedule'!CW31","v":0},{"$f":"'K20 - time schedule'!CX31","v":0},{"$f":"'K20 - time schedule'!CY31","v":0},{"$f":"'K20 - time schedule'!CZ31","v":0},{"$f":"'K20 - time schedule'!DA31","v":0},{"$f":"'K20 - time schedule'!DB31","v":0},{"$f":"'K20 - time schedule'!DC31","v":0},{"$f":"'K20 - time schedule'!DD31","v":0},{"$f":"'K20 - time schedule'!DE31","v":0},{"$f":"'K20 - time schedule'!DF31","v":0},{"$f":"'K20 - time schedule'!DG31","v":0},{"$f":"'K20 - time schedule'!DH31","v":0},{"$f":"'K20 - time schedule'!DI31","v":0},{"$f":"'K20 - time schedule'!DJ31","v":0},{"$f":"'K20 - time schedule'!DK31","v":0},{"$f":"'K20 - time schedule'!DL31","v":0},{"$f":"'K20 - time schedule'!DM31","v":0},{"$f":"'K20 - time schedule'!DN31","v":0},{"$f":"'K20 - time schedule'!DO31","v":0},{"$f":"'K20 - time schedule'!DP31","v":0},{"$f":"'K20 - time schedule'!DQ31","v":0},{"$f":"'K20 - time schedule'!DR31","v":0},{"$f":"'K20 - time schedule'!DS31","v":0},{"$f":"'K20 - time schedule'!DT31","v":0},{"$f":"'K20 - time schedule'!DU31","v":0},{"$f":"'K20 - time schedule'!DV31","v":0},{"$f":"'K20 - time schedule'!DW31","v":0},{"$f":"'K20 - time schedule'!DX31","v":0},{"$f":"'K20 - time schedule'!DY31","v":0},{"$f":"'K20 - time schedule'!DZ31","v":0},{"$f":"'K20 - time schedule'!EA31","v":0},{"$f":"'K20 - time schedule'!EB31","v":0},{"$f":"'K20 - time schedule'!EC31","v":0},{"$f":"'K20 - time schedule'!ED31","v":0},{"$f":"'K20 - time schedule'!EE31","v":0},{"$f":"'K20 - time schedule'!EF31","v":0},{"$f":"'K20 - time schedule'!EG31","v":0},{"$f":"'K20 - time schedule'!EH31","v":0},{"$f":"'K20 - time schedule'!EI31","v":0},{"$f":"'K20 - time schedule'!EJ31","v":0},{"$f":"'K20 - time schedule'!EK31","v":0},{"$f":"'K20 - time schedule'!EL31","v":0},{"$f":"'K20 - time schedule'!EM31","v":0},{"$f":"'K20 - time schedule'!EN31","v":0},{"$f":"'K20 - time schedule'!EO31","v":0},{"$f":"'K20 - time schedule'!EP31","v":0},{"$f":"'K20 - time schedule'!EQ31","v":0},{"$f":"'K20 - time schedule'!ER31","v":0},{"$f":"'K20 - time schedule'!ES31","v":0},{"$f":"'K20 - time schedule'!ET31","v":0},{"$f":"'K20 - time schedule'!EU31","v":0},{"$f":"'K20 - time schedule'!EV31","v":0},{"$f":"'K20 - time schedule'!EW31","v":0},{"$f":"'K20 - time schedule'!EX31","v":0},{"$f":"'K20 - time schedule'!EY31","v":0},{"$f":"'K20 - time schedule'!EZ31","v":0},{"$f":"'K20 - time schedule'!FA31","v":0},{"$f":"'K20 - time schedule'!FB31","v":0},{"$f":"'K20 - time schedule'!FC31","v":0},{"$f":"'K20 - time schedule'!FD31","v":0},{"$f":"'K20 - time schedule'!FE31","v":0},{"$f":"'K20 - time schedule'!FF31","v":0},{"$f":"'K20 - time schedule'!FG31","v":0},{"$f":"'K20 - time schedule'!FH31","v":0},{"$f":"'K20 - time schedule'!FI31","v":0},{"$f":"'K20 - time schedule'!FJ31","v":0},{"$f":"'K20 - time schedule'!FK31","v":0},{"$f":"'K20 - time schedule'!FL31","v":0},{"$f":"'K20 - time schedule'!FM31","v":0},{"$f":"'K20 - time schedule'!FN31","v":0},{"$f":"'K20 - time schedule'!FO31","v":0},{"$f":"'K20 - time schedule'!FP31","v":0},{"$f":"'K20 - time schedule'!FQ31","v":0},{"$f":"'K20 - time schedule'!FR31","v":0},{"$f":"'K20 - time schedule'!FS31","v":0},{"$f":"'K20 - time schedule'!FT31","v":0},{"$f":"'K20 - time schedule'!FU31","v":0},{"$f":"'K20 - time schedule'!FV31","v":0},{"$f":"'K20 - time schedule'!FW31","v":0},{"$f":"'K20 - time schedule'!FX31","v":0},{"$f":"'K20 - time schedule'!FY31","v":0},{"$f":"'K20 - time schedule'!FZ31","v":0},{"$f":"'K20 - time schedule'!GA31","v":0},{"$f":"'K20 - time schedule'!GB31","v":0},{"$f":"'K20 - time schedule'!GC31","v":0},{"$f":"'K20 - time schedule'!GD31","v":0},{"$f":"'K20 - time schedule'!GE31","v":0},{"$f":"'K20 - time schedule'!GF31","v":0},{"$f":"'K20 - time schedule'!GG20","v":0},{"$f":"'K20 - time schedule'!GH20","v":0},{"$f":"'K20 - time schedule'!GI20","v":0},{"$f":"'K20 - time schedule'!GJ20","v":0},{"$f":"'K20 - time schedule'!GK20","v":0},{"$f":"'K20 - time schedule'!GL20","v":0},{"$f":"'K20 - time schedule'!GM20","v":0},{"$f":"'K20 - time schedule'!GN20","v":0},{"$f":"'K20 - time schedule'!GO20","v":0},{"$f":"'K20 - time schedule'!GP20","v":0},{"$f":"'K20 - time schedule'!GQ20","v":0},{"$f":"'K20 - time schedule'!GR20","v":0},{"$f":"'K20 - time schedule'!GS20","v":0},{"$f":"'K20 - time schedule'!GT20","v":0},{"$f":"'K20 - time schedule'!GU20","v":0},{"$f":"'K20 - time schedule'!GV20","v":0},{"$f":"'K20 - time schedule'!GW20","v":0},{"$f":"'K20 - time schedule'!GX20","v":0},{"$f":"'K20 - time schedule'!GY20","v":0},{"$f":"'K20 - time schedule'!GZ20","v":0},{"$f":"'K20 - time schedule'!HA20","v":0},{"$f":"'K20 - time schedule'!HB20","v":0},{"$f":"'K20 - time schedule'!HC20","v":0},{"$f":"'K20 - time schedule'!HD20","v":0},{"$f":"'K20 - time schedule'!HE20","v":0},{"$f":"'K20 - time schedule'!HF20","v":0},{"$f":"'K20 - time schedule'!HG20","v":0},{"$f":"'K20 - time schedule'!HH20","v":0},{"$f":"'K20 - time schedule'!HI20","v":0},{"$f":"'K20 - time schedule'!HJ20","v":0},{"$f":"'K20 - time schedule'!HK20","v":0},{"$f":"'K20 - time schedule'!HL20","v":0},{"$f":"'K20 - time schedule'!HM20","v":0},{"$f":"'K20 - time schedule'!HN20","v":0},{"$f":"'K20 - time schedule'!HO20","v":0},{"$f":"'K20 - time schedule'!HP20","v":0},{"$f":"'K20 - time schedule'!HQ20","v":0},{"$f":"'K20 - time schedule'!HR20","v":0},{"$f":"'K20 - time schedule'!HS20","v":0},{"$f":"'K20 - time schedule'!HT20","v":0},{"$f":"'K20 - time schedule'!HU20","v":0},{"$f":"'K20 - time schedule'!HV20","v":0},{"$f":"'K20 - time schedule'!HW20","v":0},{"$f":"'K20 - time schedule'!HX20","v":0},{"$f":"'K20 - time schedule'!HY20","v":0},{"$f":"'K20 - time schedule'!HZ20","v":0},{"$f":"'K20 - time schedule'!IA20","v":0},{"$f":"'K20 - time schedule'!IB20","v":0},{"$f":"'K20 - time schedule'!IC20","v":0},{"$f":"'K20 - time schedule'!ID20","v":0},{"$f":"'K20 - time schedule'!IE20","v":0},{"$f":"'K20 - time schedule'!IF20","v":0},{"$f":"'K20 - time schedule'!IG20","v":0},{"$f":"'K20 - time schedule'!IH20","v":0},{"$f":"'K20 - time schedule'!II20","v":0},{"$f":"'K20 - time schedule'!IJ20","v":0},{"$f":"'K20 - time schedule'!IK20","v":0},{"$f":"'K20 - time schedule'!IL20","v":0},{"$f":"'K20 - time schedule'!IM20","v":0},{"$f":"'K20 - time schedule'!IN20","v":0},{"$f":"'K20 - time schedule'!IO20","v":0},{"$f":"'K20 - time schedule'!IP20","v":0},{"$f":"'K20 - time schedule'!IQ20","v":0},{"$f":"'K20 - time schedule'!IR20","v":0},{"$f":"'K20 - time schedule'!IS20","v":0},{"$f":"'K20 - time schedule'!IT20","v":0},{"$f":"'K20 - time schedule'!IU20","v":0},{"$f":"'K20 - time schedule'!IV20","v":0},{"$f":"'K20 - time schedule'!IW20","v":0},{"$f":"'K20 - time schedule'!IX20","v":0},{"$f":"'K20 - time schedule'!IY20","v":0},{"$f":"'K20 - time schedule'!IZ20","v":0},{"$f":"'K20 - time schedule'!JA20","v":0},{"$f":"'K20 - time schedule'!JB20","v":0},{"$f":"'K20 - time schedule'!JC20","v":0},{"$f":"'K20 - time schedule'!JD20","v":0},{"$f":"'K20 - time schedule'!JE20","v":0},{"$f":"'K20 - time schedule'!JF20","v":0},{"$f":"'K20 - time schedule'!JG20","v":0},{"$f":"'K20 - time schedule'!JH20","v":0},{"$f":"'K20 - time schedule'!JI20","v":0},{"$f":"'K20 - time schedule'!JJ20","v":0},{"$f":"'K20 - time schedule'!JK20","v":0},{"$f":"'K20 - time schedule'!JL20","v":0},{"$f":"'K20 - time schedule'!JM20","v":0},{"$f":"'K20 - time schedule'!JN20","v":0},{"$f":"'K20 - time schedule'!JO20","v":0},{"$f":"'K20 - time schedule'!JP20","v":0},{"$f":"'K20 - time schedule'!JQ20","v":0},{"$f":"'K20 - time schedule'!JR20","v":0},{"$f":"'K20 - time schedule'!JS20","v":0},{"$f":"'K20 - time schedule'!JT20","v":0},{"$f":"'K20 - time schedule'!JU20","v":0},{"$f":"'K20 - time schedule'!JV20","v":0},{"$f":"'K20 - time schedule'!JW20","v":0},{"$f":"'K20 - time schedule'!JX20","v":0},{"$f":"'K20 - time schedule'!JY20","v":0},{"$f":"'K20 - time schedule'!JZ20","v":0},{"$f":"'K20 - time schedule'!KA20","v":0},{"$f":"'K20 - time schedule'!KB20","v":0},{"$f":"'K20 - time schedule'!KC20","v":0},{"$f":"'K20 - time schedule'!KD20","v":0},{"$f":"'K20 - time schedule'!KE20","v":0},{"$f":"'K20 - time schedule'!KF20","v":0},{"$f":"'K20 - time schedule'!KG20","v":0},{"$f":"'K20 - time schedule'!KH20","v":0},{"$f":"'K20 - time schedule'!KI20","v":0},{"$f":"'K20 - time schedule'!KJ20","v":0},{"$f":"'K20 - time schedule'!KK20","v":0},{"$f":"'K20 - time schedule'!KL20","v":0},{"$f":"'K20 - time schedule'!KM20","v":0},{"$f":"'K20 - time schedule'!KN20","v":0},{"$f":"'K20 - time schedule'!KO20","v":0},{"$f":"'K20 - time schedule'!KP20","v":0},{"$f":"'K20 - time schedule'!KQ20","v":0},{"$f":"'K20 - time schedule'!KR20","v":0},{"$f":"'K20 - time schedule'!KS20","v":0},{"$f":"'K20 - time schedule'!KT20","v":0}]
["Boiler room K20 - electrical installation","K20","EUR",{"$f":"'K20 - time schedule'!G33","v":0},{"$f":"'K20 - time schedule'!H33","v":0},{"$f":"'K20 - time schedule'!I33","v":0},{"$f":"'K20 - time schedule'!J33","v":0},{"$f":"'K20 - time schedule'!K33","v":0},{"$f":"'K20 - time schedule'!L33","v":0},{"$f":"'K20 - time schedule'!M33","v":0},{"$f":"'K20 - time schedule'!N33","v":0},{"$f":"'K20 - time schedule'!O33","v":0},{"$f":"'K20 - time schedule'!P33","v":0},{"$f":"'K20 - time schedule'!Q33","v":0},{"$f":"'K20 - time schedule'!R33","v":0},{"$f":"'K20 - time schedule'!S33","v":0},{"$f":"'K20 - time schedule'!T33","v":0},{"$f":"'K20 - time schedule'!U33","v":0},{"$f":"'K20 - time schedule'!V33","v":0},{"$f":"'K20 - time schedule'!W33","v":0},{"$f":"'K20 - time schedule'!X33","v":0},{"$f":"'K20 - time schedule'!Y33","v":0},{"$f":"'K20 - time schedule'!Z33","v":0},{"$f":"'K20 - time schedule'!AA33","v":0},{"$f":"'K20 - time schedule'!AB33","v":0},{"$f":"'K20 - time schedule'!AC33","v":0},{"$f":"'K20 - time schedule'!AD33","v":0},{"$f":"'K20 - time schedule'!AE33","v":0},{"$f":"'K20 - time schedule'!AF33","v":0},{"$f":"'K20 - time schedule'!AG33","v":0},{"$f":"'K20 - time schedule'!AH33","v":0},{"$f":"'K20 - time schedule'!AI33","v":0},{"$f":"'K20 - time schedule'!AJ33","v":0},{"$f":"'K20 - time schedule'!AK33","v":0},{"$f":"'K20 - time schedule'!AL33","v":0},{"$f":"'K20 - time schedule'!AM33","v":0},{"$f":"'K20 - time schedule'!AN33","v":0},{"$f":"'K20 - time schedule'!AO33","v":0},{"$f":"'K20 - time schedule'!AP33","v":0},{"$f":"'K20 - time schedule'!AQ33","v":0},{"$f":"'K20 - time schedule'!AR33","v":0},{"$f":"'K20 - time schedule'!AS33","v":0},{"$f":"'K20 - time schedule'!AT33","v":0},{"$f":"'K20 - time schedule'!AU33","v":0},{"$f":"'K20 - time schedule'!AV33","v":0},{"$f":"'K20 - time schedule'!AW33","v":0},{"$f":"'K20 - time schedule'!AX33","v":0},{"$f":"'K20 - time schedule'!AY33","v":0},{"$f":"'K20 - time schedule'!AZ33","v":0},{"$f":"'K20 - time schedule'!BA33","v":0},{"$f":"'K20 - time schedule'!BB33","v":0},{"$f":"'K20 - time schedule'!BC33","v":0},{"$f":"'K20 - time schedule'!BD33","v":0},{"$f":"'K20 - time schedule'!BE33","v":0},{"$f":"'K20 - time schedule'!BF33","v":0},{"$f":"'K20 - time schedule'!BG33","v":0},{"$f":"'K20 - time schedule'!BH33","v":0},{"$f":"'K20 - time schedule'!BI33","v":0},{"$f":"'K20 - time schedule'!BJ33","v":0},{"$f":"'K20 - time schedule'!BK33","v":0},{"$f":"'K20 - time schedule'!BL33","v":0},{"$f":"'K20 - time schedule'!BM33","v":0},{"$f":"'K20 - time schedule'!BN33","v":0},{"$f":"'K20 - time schedule'!BO33","v":0},{"$f":"'K20 - time schedule'!BP33","v":0},{"$f":"'K20 - time schedule'!BQ33","v":0},{"$f":"'K20 - time schedule'!BR33","v":0},{"$f":"'K20 - time schedule'!BS33","v":0},{"$f":"'K20 - time schedule'!BT33","v":0},{"$f":"'K20 - time schedule'!BU33","v":0},{"$f":"'K20 - time schedule'!BV33","v":0},{"$f":"'K20 - time schedule'!BW33","v":0},{"$f":"'K20 - time schedule'!BX33","v":0},{"$f":"'K20 - time schedule'!BY33","v":0},{"$f":"'K20 - time schedule'!BZ33","v":0},{"$f":"'K20 - time schedule'!CA33","v":0},{"$f":"'K20 - time schedule'!CB33","v":0},{"$f":"'K20 - time schedule'!CC33","v":0},{"$f":"'K20 - time schedule'!CD33","v":0},{"$f":"'K20 - time schedule'!CE33","v":0},{"$f":"'K20 - time schedule'!CF33","v":0},{"$f":"'K20 - time schedule'!CG33","v":0},{"$f":"'K20 - time schedule'!CH33","v":0},{"$f":"'K20 - time schedule'!CI33","v":0},{"$f":"'K20 - time schedule'!CJ33","v":0},{"$f":"'K20 - time schedule'!CK33","v":0},{"$f":"'K20 - time schedule'!CL33","v":0},{"$f":"'K20 - time schedule'!CM33","v":0},{"$f":"'K20 - time schedule'!CN33","v":0},{"$f":"'K20 - time schedule'!CO33","v":0},{"$f":"'K20 - time schedule'!CP33","v":0},{"$f":"'K20 - time schedule'!CQ33","v":0},{"$f":"'K20 - time schedule'!CR33","v":0},{"$f":"'K20 - time schedule'!CS33","v":0},{"$f":"'K20 - time schedule'!CT33","v":0},{"$f":"'K20 - time schedule'!CU33","v":0},{"$f":"'K20 - time schedule'!CV33","v":0},{"$f":"'K20 - time schedule'!CW33","v":0},{"$f":"'K20 - time schedule'!CX33","v":0},{"$f":"'K20 - time schedule'!CY33","v":0},{"$f":"'K20 - time schedule'!CZ33","v":0},{"$f":"'K20 - time schedule'!DA33","v":0},{"$f":"'K20 - time schedule'!DB33","v":0},{"$f":"'K20 - time schedule'!DC33","v":0},{"$f":"'K20 - time schedule'!DD33","v":0},{"$f":"'K20 - time schedule'!DE33","v":0},{"$f":"'K20 - time schedule'!DF33","v":0},{"$f":"'K20 - time schedule'!DG33","v":0},{"$f":"'K20 - time schedule'!DH33","v":0},{"$f":"'K20 - time schedule'!DI33","v":0},{"$f":"'K20 - time schedule'!DJ33","v":0},{"$f":"'K20 - time schedule'!DK33","v":0},{"$f":"'K20 - time schedule'!DL33","v":0},{"$f":"'K20 - time schedule'!DM33","v":0},{"$f":"'K20 - time schedule'!DN33","v":0},{"$f":"'K20 - time schedule'!DO33","v":0},{"$f":"'K20 - time schedule'!DP33","v":0},{"$f":"'K20 - time schedule'!DQ33","v":0},{"$f":"'K20 - time schedule'!DR33","v":0},{"$f":"'K20 - time schedule'!DS33","v":0},{"$f":"'K20 - time schedule'!DT33","v":0},{"$f":"'K20 - time schedule'!DU33","v":0},{"$f":"'K20 - time schedule'!DV33","v":0},{"$f":"'K20 - time schedule'!DW33","v":0},{"$f":"'K20 - time schedule'!DX33","v":0},{"$f":"'K20 - time schedule'!DY33","v":0},{"$f":"'K20 - time schedule'!DZ33","v":0},{"$f":"'K20 - time schedule'!EA33","v":0},{"$f":"'K20 - time schedule'!EB33","v":0},{"$f":"'K20 - time schedule'!EC33","v":0},{"$f":"'K20 - time schedule'!ED33","v":0},{"$f":"'K20 - time schedule'!EE33","v":0},{"$f":"'K20 - time schedule'!EF33","v":0},{"$f":"'K20 - time schedule'!EG33","v":0},{"$f":"'K20 - time schedule'!EH33","v":0},{"$f":"'K20 - time schedule'!EI33","v":0},{"$f":"'K20 - time schedule'!EJ33","v":0},{"$f":"'K20 - time schedule'!EK33","v":0},{"$f":"'K20 - time schedule'!EL33","v":0},{"$f":"'K20 - time schedule'!EM33","v":0},{"$f":"'K20 - time schedule'!EN33","v":0},{"$f":"'K20 - time schedule'!EO33","v":0},{"$f":"'K20 - time schedule'!EP33","v":0},{"$f":"'K20 - time schedule'!EQ33","v":0},{"$f":"'K20 - time schedule'!ER33","v":0},{"$f":"'K20 - time schedule'!ES33","v":0},{"$f":"'K20 - time schedule'!ET33","v":0},{"$f":"'K20 - time schedule'!EU33","v":0},{"$f":"'K20 - time schedule'!EV33","v":0},{"$f":"'K20 - time schedule'!EW33","v":0},{"$f":"'K20 - time schedule'!EX33","v":0},{"$f":"'K20 - time schedule'!EY33","v":0},{"$f":"'K20 - time schedule'!EZ33","v":0},{"$f":"'K20 - time schedule'!FA33","v":0},{"$f":"'K20 - time schedule'!FB33","v":0},{"$f":"'K20 - time schedule'!FC33","v":0},{"$f":"'K20 - time schedule'!FD33","v":0},{"$f":"'K20 - time schedule'!FE33","v":0},{"$f":"'K20 - time schedule'!FF33","v":0},{"$f":"'K20 - time schedule'!FG33","v":0},{"$f":"'K20 - time schedule'!FH33","v":0},{"$f":"'K20 - time schedule'!FI33","v":0},{"$f":"'K20 - time schedule'!FJ33","v":0},{"$f":"'K20 - time schedule'!FK33","v":0},{"$f":"'K20 - time schedule'!FL33","v":0},{"$f":"'K20 - time schedule'!FM33","v":0},{"$f":"'K20 - time schedule'!FN33","v":0},{"$f":"'K20 - time schedule'!FO33","v":0},{"$f":"'K20 - time schedule'!FP33","v":0},{"$f":"'K20 - time schedule'!FQ33","v":0},{"$f":"'K20 - time schedule'!FR33","v":0},{"$f":"'K20 - time schedule'!FS33","v":0},{"$f":"'K20 - time schedule'!FT33","v":0},{"$f":"'K20 - time schedule'!FU33","v":0},{"$f":"'K20 - time schedule'!FV33","v":0},{"$f":"'K20 - time schedule'!FW33","v":0},{"$f":"'K20 - time schedule'!FX33","v":0},{"$f":"'K20 - time schedule'!FY33","v":0},{"$f":"'K20 - time schedule'!FZ33","v":0},{"$f":"'K20 - time schedule'!GA33","v":0},{"$f":"'K20 - time schedule'!GB33","v":0},{"$f":"'K20 - time schedule'!GC33","v":0},{"$f":"'K20 - time schedule'!GD33","v":0},{"$f":"'K20 - time schedule'!GE33","v":0},{"$f":"'K20 - time schedule'!GF33","v":0},{"$f":"'K20 - time schedule'!GG21","v":0},{"$f":"'K20 - time schedule'!GH21","v":0},{"$f":"'K20 - time schedule'!GI21","v":0},{"$f":"'K20 - time schedule'!GJ21","v":0},{"$f":"'K20 - time schedule'!GK21","v":0},{"$f":"'K20 - time schedule'!GL21","v":0},{"$f":"'K20 - time schedule'!GM21","v":0},{"$f":"'K20 - time schedule'!GN21","v":0},{"$f":"'K20 - time schedule'!GO21","v":0},{"$f":"'K20 - time schedule'!GP21","v":0},{"$f":"'K20 - time schedule'!GQ21","v":0},{"$f":"'K20 - time schedule'!GR21","v":0},{"$f":"'K20 - time schedule'!GS21","v":0},{"$f":"'K20 - time schedule'!GT21","v":0},{"$f":"'K20 - time schedule'!GU21","v":0},{"$f":"'K20 - time schedule'!GV21","v":0},{"$f":"'K20 - time schedule'!GW21","v":0},{"$f":"'K20 - time schedule'!GX21","v":0},{"$f":"'K20 - time schedule'!GY21","v":0},{"$f":"'K20 - time schedule'!GZ21","v":0},{"$f":"'K20 - time schedule'!HA21","v":0},{"$f":"'K20 - time schedule'!HB21","v":0},{"$f":"'K20 - time schedule'!HC21","v":0},{"$f":"'K20 - time schedule'!HD21","v":0},{"$f":"'K20 - time schedule'!HE21","v":0},{"$f":"'K20 - time schedule'!HF21","v":0},{"$f":"'K20 - time schedule'!HG21","v":0},{"$f":"'K20 - time schedule'!HH21","v":0},{"$f":"'K20 - time schedule'!HI21","v":0},{"$f":"'K20 - time schedule'!HJ21","v":0},{"$f":"'K20 - time schedule'!HK21","v":0},{"$f":"'K20 - time schedule'!HL21","v":0},{"$f":"'K20 - time schedule'!HM21","v":0},{"$f":"'K20 - time schedule'!HN21","v":0},{"$f":"'K20 - time schedule'!HO21","v":0},{"$f":"'K20 - time schedule'!HP21","v":0},{"$f":"'K20 - time schedule'!HQ21","v":0},{"$f":"'K20 - time schedule'!HR21","v":0},{"$f":"'K20 - time schedule'!HS21","v":0},{"$f":"'K20 - time schedule'!HT21","v":0},{"$f":"'K20 - time schedule'!HU21","v":0},{"$f":"'K20 - time schedule'!HV21","v":0},{"$f":"'K20 - time schedule'!HW21","v":0},{"$f":"'K20 - time schedule'!HX21","v":0},{"$f":"'K20 - time schedule'!HY21","v":0},{"$f":"'K20 - time schedule'!HZ21","v":0},{"$f":"'K20 - time schedule'!IA21","v":0},{"$f":"'K20 - time schedule'!IB21","v":0},{"$f":"'K20 - time schedule'!IC21","v":0},{"$f":"'K20 - time schedule'!ID21","v":0},{"$f":"'K20 - time schedule'!IE21","v":0},{"$f":"'K20 - time schedule'!IF21","v":0},{"$f":"'K20 - time schedule'!IG21","v":0},{"$f":"'K20 - time schedule'!IH21","v":0},{"$f":"'K20 - time schedule'!II21","v":0},{"$f":"'K20 - time schedule'!IJ21","v":0},{"$f":"'K20 - time schedule'!IK21","v":0},{"$f":"'K20 - time schedule'!IL21","v":0},{"$f":"'K20 - time schedule'!IM21","v":0},{"$f":"'K20 - time schedule'!IN21","v":0},{"$f":"'K20 - time schedule'!IO21","v":0},{"$f":"'K20 - time schedule'!IP21","v":0},{"$f":"'K20 - time schedule'!IQ21","v":0},{"$f":"'K20 - time schedule'!IR21","v":0},{"$f":"'K20 - time schedule'!IS21","v":0},{"$f":"'K20 - time schedule'!IT21","v":0},{"$f":"'K20 - time schedule'!IU21","v":0},{"$f":"'K20 - time schedule'!IV21","v":0},{"$f":"'K20 - time schedule'!IW21","v":0},{"$f":"'K20 - time schedule'!IX21","v":0},{"$f":"'K20 - time schedule'!IY21","v":0},{"$f":"'K20 - time schedule'!IZ21","v":0},{"$f":"'K20 - time schedule'!JA21","v":0},{"$f":"'K20 - time schedule'!JB21","v":0},{"$f":"'K20 - time schedule'!JC21","v":0},{"$f":"'K20 - time schedule'!JD21","v":0},{"$f":"'K20 - time schedule'!JE21","v":0},{"$f":"'K20 - time schedule'!JF21","v":0},{"$f":"'K20 - time schedule'!JG21","v":0},{"$f":"'K20 - time schedule'!JH21","v":0},{"$f":"'K20 - time schedule'!JI21","v":0},{"$f":"'K20 - time schedule'!JJ21","v":0},{"$f":"'K20 - time schedule'!JK21","v":0},{"$f":"'K20 - time schedule'!JL21","v":0},{"$f":"'K20 - time schedule'!JM21","v":0},{"$f":"'K20 - time schedule'!JN21","v":0},{"$f":"'K20 - time schedule'!JO21","v":0},{"$f":"'K20 - time schedule'!JP21","v":0},{"$f":"'K20 - time schedule'!JQ21","v":0},{"$f":"'K20 - time schedule'!JR21","v":0},{"$f":"'K20 - time schedule'!JS21","v":0},{"$f":"'K20 - time schedule'!JT21","v":0},{"$f":"'K20 - time schedule'!JU21","v":0},{"$f":"'K20 - time schedule'!JV21","v":0},{"$f":"'K20 - time schedule'!JW21","v":0},{"$f":"'K20 - time schedule'!JX21","v":0},{"$f":"'K20 - time schedule'!JY21","v":0},{"$f":"'K20 - time schedule'!JZ21","v":0},{"$f":"'K20 - time schedule'!KA21","v":0},{"$f":"'K20 - time schedule'!KB21","v":0},{"$f":"'K20 - time schedule'!KC21","v":0},{"$f":"'K20 - time schedule'!KD21","v":0},{"$f":"'K20 - time schedule'!KE21","v":0},{"$f":"'K20 - time schedule'!KF21","v":0},{"$f":"'K20 - time schedule'!KG21","v":0},{"$f":"'K20 - time schedule'!KH21","v":0},{"$f":"'K20 - time schedule'!KI21","v":0},{"$f":"'K20 - time schedule'!KJ21","v":0},{"$f":"'K20 - time schedule'!KK21","v":0},{"$f":"'K20 - time schedule'!KL21","v":0},{"$f":"'K20 - time schedule'!KM21","v":0},{"$f":"'K20 - time schedule'!KN21","v":0},{"$f":"'K20 - time schedule'!KO21","v":0},{"$f":"'K20 - time schedule'!KP21","v":0},{"$f":"'K20 - time schedule'!KQ21","v":0},{"$f":"'K20 - time schedule'!KR21","v":0},{"$f":"'K20 - time schedule'!KS21","v":0},{"$f":"'K20 - time schedule'!KT21","v":0}]
["Boiler room K20 - automatic control system","K20","EUR",{"$f":"'K20 - time schedule'!G35","v":0},{"$f":"'K20 - time schedule'!H35","v":0},{"$f":"'K20 - time schedule'!I35","v":0},{"$f":"'K20 - time schedule'!J35","v":0},{"$f":"'K20 - time schedule'!K35","v":0},{"$f":"'K20 - time schedule'!L35","v":0},{"$f":"'K20 - time schedule'!M35","v":0},{"$f":"'K20 - time schedule'!N35","v":0},{"$f":"'K20 - time schedule'!O35","v":0},{"$f":"'K20 - time schedule'!P35","v":0},{"$f":"'K20 - time schedule'!Q35","v":0},{"$f":"'K20 - time schedule'!R35","v":0},{"$f":"'K20 - time schedule'!S35","v":0},{"$f":"'K20 - time schedule'!T35","v":0},{"$f":"'K20 - time schedule'!U35","v":0},{"$f":"'K20 - time schedule'!V35","v":0},{"$f":"'K20 - time schedule'!W35","v":0},{"$f":"'K20 - time schedule'!X35","v":0},{"$f":"'K20 - time schedule'!Y35","v":0},{"$f":"'K20 - time schedule'!Z35","v":0},{"$f":"'K20 - time schedule'!AA35","v":0},{"$f":"'K20 - time schedule'!AB35","v":0},{"$f":"'K20 - time schedule'!AC35","v":0},{"$f":"'K20 - time schedule'!AD35","v":0},{"$f":"'K20 - time schedule'!AE35","v":0},{"$f":"'K20 - time schedule'!AF35","v":0},{"$f":"'K20 - time schedule'!AG35","v":0},{"$f":"'K20 - time schedule'!AH35","v":0},{"$f":"'K20 - time schedule'!AI35","v":0},{"$f":"'K20 - time schedule'!AJ35","v":0},{"$f":"'K20 - time schedule'!AK35","v":0},{"$f":"'K20 - time schedule'!AL35","v":0},{"$f":"'K20 - time schedule'!AM35","v":0},{"$f":"'K20 - time schedule'!AN35","v":0},{"$f":"'K20 - time schedule'!AO35","v":0},{"$f":"'K20 - time schedule'!AP35","v":0},{"$f":"'K20 - time schedule'!AQ35","v":0},{"$f":"'K20 - time schedule'!AR35","v":0},{"$f":"'K20 - time schedule'!AS35","v":0},{"$f":"'K20 - time schedule'!AT35","v":0},{"$f":"'K20 - time schedule'!AU35","v":0},{"$f":"'K20 - time schedule'!AV35","v":0},{"$f":"'K20 - time schedule'!AW35","v":0},{"$f":"'K20 - time schedule'!AX35","v":0},{"$f":"'K20 - time schedule'!AY35","v":0},{"$f":"'K20 - time schedule'!AZ35","v":0},{"$f":"'K20 - time schedule'!BA35","v":0},{"$f":"'K20 - time schedule'!BB35","v":0},{"$f":"'K20 - time schedule'!BC35","v":0},{"$f":"'K20 - time schedule'!BD35","v":0},{"$f":"'K20 - time schedule'!BE35","v":0},{"$f":"'K20 - time schedule'!BF35","v":0},{"$f":"'K20 - time schedule'!BG35","v":0},{"$f":"'K20 - time schedule'!BH35","v":0},{"$f":"'K20 - time schedule'!BI35","v":0},{"$f":"'K20 - time schedule'!BJ35","v":0},{"$f":"'K20 - time schedule'!BK35","v":0},{"$f":"'K20 - time schedule'!BL35","v":0},{"$f":"'K20 - time schedule'!BM35","v":0},{"$f":"'K20 - time schedule'!BN35","v":0},{"$f":"'K20 - time schedule'!BO35","v":0},{"$f":"'K20 - time schedule'!BP35","v":0},{"$f":"'K20 - time schedule'!BQ35","v":0},{"$f":"'K20 - time schedule'!BR35","v":0},{"$f":"'K20 - time schedule'!BS35","v":0},{"$f":"'K20 - time schedule'!BT35","v":0},{"$f":"'K20 - time schedule'!BU35","v":0},{"$f":"'K20 - time schedule'!BV35","v":0},{"$f":"'K20 - time schedule'!BW35","v":0},{"$f":"'K20 - time schedule'!BX35","v":0},{"$f":"'K20 - time schedule'!BY35","v":0},{"$f":"'K20 - time schedule'!BZ35","v":0},{"$f":"'K20 - time schedule'!CA35","v":0},{"$f":"'K20 - time schedule'!CB35","v":0},{"$f":"'K20 - time schedule'!CC35","v":0},{"$f":"'K20 - time schedule'!CD35","v":0},{"$f":"'K20 - time schedule'!CE35","v":0},{"$f":"'K20 - time schedule'!CF35","v":0},{"$f":"'K20 - time schedule'!CG35","v":0},{"$f":"'K20 - time schedule'!CH35","v":0},{"$f":"'K20 - time schedule'!CI35","v":0},{"$f":"'K20 - time schedule'!CJ35","v":0},{"$f":"'K20 - time schedule'!CK35","v":0},{"$f":"'K20 - time schedule'!CL35","v":0},{"$f":"'K20 - time schedule'!CM35","v":0},{"$f":"'K20 - time schedule'!CN35","v":0},{"$f":"'K20 - time schedule'!CO35","v":0},{"$f":"'K20 - time schedule'!CP35","v":0},{"$f":"'K20 - time schedule'!CQ35","v":0},{"$f":"'K20 - time schedule'!CR35","v":0},{"$f":"'K20 - time schedule'!CS35","v":0},{"$f":"'K20 - time schedule'!CT35","v":0},{"$f":"'K20 - time schedule'!CU35","v":0},{"$f":"'K20 - time schedule'!CV35","v":0},{"$f":"'K20 - time schedule'!CW35","v":0},{"$f":"'K20 - time schedule'!CX35","v":0},{"$f":"'K20 - time schedule'!CY35","v":0},{"$f":"'K20 - time schedule'!CZ35","v":0},{"$f":"'K20 - time schedule'!DA35","v":0},{"$f":"'K20 - time schedule'!DB35","v":0},{"$f":"'K20 - time schedule'!DC35","v":0},{"$f":"'K20 - time schedule'!DD35","v":0},{"$f":"'K20 - time schedule'!DE35","v":0},{"$f":"'K20 - time schedule'!DF35","v":0},{"$f":"'K20 - time schedule'!DG35","v":0},{"$f":"'K20 - time schedule'!DH35","v":0},{"$f":"'K20 - time schedule'!DI35","v":0},{"$f":"'K20 - time schedule'!DJ35","v":0},{"$f":"'K20 - time schedule'!DK35","v":0},{"$f":"'K20 - time schedule'!DL35","v":0},{"$f":"'K20 - time schedule'!DM35","v":0},{"$f":"'K20 - time schedule'!DN35","v":0},{"$f":"'K20 - time schedule'!DO35","v":0},{"$f":"'K20 - time schedule'!DP35","v":0},{"$f":"'K20 - time schedule'!DQ35","v":0},{"$f":"'K20 - time schedule'!DR35","v":0},{"$f":"'K20 - time schedule'!DS35","v":0},{"$f":"'K20 - time schedule'!DT35","v":0},{"$f":"'K20 - time schedule'!DU35","v":0},{"$f":"'K20 - time schedule'!DV35","v":0},{"$f":"'K20 - time schedule'!DW35","v":0},{"$f":"'K20 - time schedule'!DX35","v":0},{"$f":"'K20 - time schedule'!DY35","v":0},{"$f":"'K20 - time schedule'!DZ35","v":0},{"$f":"'K20 - time schedule'!EA35","v":0},{"$f":"'K20 - time schedule'!EB35","v":0},{"$f":"'K20 - time schedule'!EC35","v":0},{"$f":"'K20 - time schedule'!ED35","v":0},{"$f":"'K20 - time schedule'!EE35","v":0},{"$f":"'K20 - time schedule'!EF35","v":0},{"$f":"'K20 - time schedule'!EG35","v":0},{"$f":"'K20 - time schedule'!EH35","v":0},{"$f":"'K20 - time schedule'!EI35","v":0},{"$f":"'K20 - time schedule'!EJ35","v":0},{"$f":"'K20 - time schedule'!EK35","v":0},{"$f":"'K20 - time schedule'!EL35","v":0},{"$f":"'K20 - time schedule'!EM35","v":0},{"$f":"'K20 - time schedule'!EN35","v":0},{"$f":"'K20 - time schedule'!EO35","v":0},{"$f":"'K20 - time schedule'!EP35","v":0},{"$f":"'K20 - time schedule'!EQ35","v":0},{"$f":"'K20 - time schedule'!ER35","v":0},{"$f":"'K20 - time schedule'!ES35","v":0},{"$f":"'K20 - time schedule'!ET35","v":0},{"$f":"'K20 - time schedule'!EU35","v":0},{"$f":"'K20 - time schedule'!EV35","v":0},{"$f":"'K20 - time schedule'!EW35","v":0},{"$f":"'K20 - time schedule'!EX35","v":0},{"$f":"'K20 - time schedule'!EY35","v":0},{"$f":"'K20 - time schedule'!EZ35","v":0},{"$f":"'K20 - time schedule'!FA35","v":0},{"$f":"'K20 - time schedule'!FB35","v":0},{"$f":"'K20 - time schedule'!FC35","v":0},{"$f":"'K20 - time schedule'!FD35","v":0},{"$f":"'K20 - time schedule'!FE35","v":0},{"$f":"'K20 - time schedule'!FF35","v":0},{"$f":"'K20 - time schedule'!FG35","v":0},{"$f":"'K20 - time schedule'!FH35","v":0},{"$f":"'K20 - time schedule'!FI35","v":0},{"$f":"'K20 - time schedule'!FJ35","v":0},{"$f":"'K20 - time schedule'!FK35","v":0},{"$f":"'K20 - time schedule'!FL35","v":0},{"$f":"'K20 - time schedule'!FM35","v":0},{"$f":"'K20 - time schedule'!FN35","v":0},{"$f":"'K20 - time schedule'!FO35","v":0},{"$f":"'K20 - time schedule'!FP35","v":0},{"$f":"'K20 - time schedule'!FQ35","v":0},{"$f":"'K20 - time schedule'!FR35","v":0},{"$f":"'K20 - time schedule'!FS35","v":0},{"$f":"'K20 - time schedule'!FT35","v":0},{"$f":"'K20 - time schedule'!FU35","v":0},{"$f":"'K20 - time schedule'!FV35","v":0},{"$f":"'K20 - time schedule'!FW35","v":0},{"$f":"'K20 - time schedule'!FX35","v":0},{"$f":"'K20 - time schedule'!FY35","v":0},{"$f":"'K20 - time schedule'!FZ35","v":0},{"$f":"'K20 - time schedule'!GA35","v":0},{"$f":"'K20 - time schedule'!GB35","v":0},{"$f":"'K20 - time schedule'!GC35","v":0},{"$f":"'K20 - time schedule'!GD35","v":0},{"$f":"'K20 - time schedule'!GE35","v":0},{"$f":"'K20 - time schedule'!GF35","v":0},{"$f":"'K20 - time schedule'!GG22","v":0},{"$f":"'K20 - time schedule'!GH22","v":0},{"$f":"'K20 - time schedule'!GI22","v":0},{"$f":"'K20 - time schedule'!GJ22","v":0},{"$f":"'K20 - time schedule'!GK22","v":0},{"$f":"'K20 - time schedule'!GL22","v":0},{"$f":"'K20 - time schedule'!GM22","v":0},{"$f":"'K20 - time schedule'!GN22","v":0},{"$f":"'K20 - time schedule'!GO22","v":0},{"$f":"'K20 - time schedule'!GP22","v":0},{"$f":"'K20 - time schedule'!GQ22","v":0},{"$f":"'K20 - time schedule'!GR22","v":0},{"$f":"'K20 - time schedule'!GS22","v":0},{"$f":"'K20 - time schedule'!GT22","v":0},{"$f":"'K20 - time schedule'!GU22","v":0},{"$f":"'K20 - time schedule'!GV22","v":0},{"$f":"'K20 - time schedule'!GW22","v":0},{"$f":"'K20 - time schedule'!GX22","v":0},{"$f":"'K20 - time schedule'!GY22","v":0},{"$f":"'K20 - time schedule'!GZ22","v":0},{"$f":"'K20 - time schedule'!HA22","v":0},{"$f":"'K20 - time schedule'!HB22","v":0},{"$f":"'K20 - time schedule'!HC22","v":0},{"$f":"'K20 - time schedule'!HD22","v":0},{"$f":"'K20 - time schedule'!HE22","v":0},{"$f":"'K20 - time schedule'!HF22","v":0},{"$f":"'K20 - time schedule'!HG22","v":0},{"$f":"'K20 - time schedule'!HH22","v":0},{"$f":"'K20 - time schedule'!HI22","v":0},{"$f":"'K20 - time schedule'!HJ22","v":0},{"$f":"'K20 - time schedule'!HK22","v":0},{"$f":"'K20 - time schedule'!HL22","v":0},{"$f":"'K20 - time schedule'!HM22","v":0},{"$f":"'K20 - time schedule'!HN22","v":0},{"$f":"'K20 - time schedule'!HO22","v":0},{"$f":"'K20 - time schedule'!HP22","v":0},{"$f":"'K20 - time schedule'!HQ22","v":0},{"$f":"'K20 - time schedule'!HR22","v":0},{"$f":"'K20 - time schedule'!HS22","v":0},{"$f":"'K20 - time schedule'!HT22","v":0},{"$f":"'K20 - time schedule'!HU22","v":0},{"$f":"'K20 - time schedule'!HV22","v":0},{"$f":"'K20 - time schedule'!HW22","v":0},{"$f":"'K20 - time schedule'!HX22","v":0},{"$f":"'K20 - time schedule'!HY22","v":0},{"$f":"'K20 - time schedule'!HZ22","v":0},{"$f":"'K20 - time schedule'!IA22","v":0},{"$f":"'K20 - time schedule'!IB22","v":0},{"$f":"'K20 - time schedule'!IC22","v":0},{"$f":"'K20 - time schedule'!ID22","v":0},{"$f":"'K20 - time schedule'!IE22","v":0},{"$f":"'K20 - time schedule'!IF22","v":0},{"$f":"'K20 - time schedule'!IG22","v":0},{"$f":"'K20 - time schedule'!IH22","v":0},{"$f":"'K20 - time schedule'!II22","v":0},{"$f":"'K20 - time schedule'!IJ22","v":0},{"$f":"'K20 - time schedule'!IK22","v":0},{"$f":"'K20 - time schedule'!IL22","v":0},{"$f":"'K20 - time schedule'!IM22","v":0},{"$f":"'K20 - time schedule'!IN22","v":0},{"$f":"'K20 - time schedule'!IO22","v":0},{"$f":"'K20 - time schedule'!IP22","v":0},{"$f":"'K20 - time schedule'!IQ22","v":0},{"$f":"'K20 - time schedule'!IR22","v":0},{"$f":"'K20 - time schedule'!IS22","v":0},{"$f":"'K20 - time schedule'!IT22","v":0},{"$f":"'K20 - time schedule'!IU22","v":0},{"$f":"'K20 - time schedule'!IV22","v":0},{"$f":"'K20 - time schedule'!IW22","v":0},{"$f":"'K20 - time schedule'!IX22","v":0},{"$f":"'K20 - time schedule'!IY22","v":0},{"$f":"'K20 - time schedule'!IZ22","v":0},{"$f":"'K20 - time schedule'!JA22","v":0},{"$f":"'K20 - time schedule'!JB22","v":0},{"$f":"'K20 - time schedule'!JC22","v":0},{"$f":"'K20 - time schedule'!JD22","v":0},{"$f":"'K20 - time schedule'!JE22","v":0},{"$f":"'K20 - time schedule'!JF22","v":0},{"$f":"'K20 - time schedule'!JG22","v":0},{"$f":"'K20 - time schedule'!JH22","v":0},{"$f":"'K20 - time schedule'!JI22","v":0},{"$f":"'K20 - time schedule'!JJ22","v":0},{"$f":"'K20 - time schedule'!JK22","v":0},{"$f":"'K20 - time schedule'!JL22","v":0},{"$f":"'K20 - time schedule'!JM22","v":0},{"$f":"'K20 - time schedule'!JN22","v":0},{"$f":"'K20 - time schedule'!JO22","v":0},{"$f":"'K20 - time schedule'!JP22","v":0},{"$f":"'K20 - time schedule'!JQ22","v":0},{"$f":"'K20 - time schedule'!JR22","v":0},{"$f":"'K20 - time schedule'!JS22","v":0},{"$f":"'K20 - time schedule'!JT22","v":0},{"$f":"'K20 - time schedule'!JU22","v":0},{"$f":"'K20 - time schedule'!JV22","v":0},{"$f":"'K20 - time schedule'!JW22","v":0},{"$f":"'K20 - time schedule'!JX22","v":0},{"$f":"'K20 - time schedule'!JY22","v":0},{"$f":"'K20 - time schedule'!JZ22","v":0},{"$f":"'K20 - time schedule'!KA22","v":0},{"$f":"'K20 - time schedule'!KB22","v":0},{"$f":"'K20 - time schedule'!KC22","v":0},{"$f":"'K20 - time schedule'!KD22","v":0},{"$f":"'K20 - time schedule'!KE22","v":0},{"$f":"'K20 - time schedule'!KF22","v":0},{"$f":"'K20 - time schedule'!KG22","v":0},{"$f":"'K20 - time schedule'!KH22","v":0},{"$f":"'K20 - time schedule'!KI22","v":0},{"$f":"'K20 - time schedule'!KJ22","v":0},{"$f":"'K20 - time schedule'!KK22","v":0},{"$f":"'K20 - time schedule'!KL22","v":0},{"$f":"'K20 - time schedule'!KM22","v":0},{"$f":"'K20 - time schedule'!KN22","v":0},{"$f":"'K20 - time schedule'!KO22","v":0},{"$f":"'K20 - time schedule'!KP22","v":0},{"$f":"'K20 - time schedule'!KQ22","v":0},{"$f":"'K20 - time schedule'!KR22","v":0},{"$f":"'K20 - time schedule'!KS22","v":0},{"$f":"'K20 - time schedule'!KT22","v":0}]
["Boiler room K20 - compressor station","K20","EUR",{"$f":"'K20 - time schedule'!G37","v":0},{"$f":"'K20 - time schedule'!H37","v":0},{"$f":"'K20 - time schedule'!I37","v":0},{"$f":"'K20 - time schedule'!J37","v":0},{"$f":"'K20 - time schedule'!K37","v":0},{"$f":"'K20 - time schedule'!L37","v":0},{"$f":"'K20 - time schedule'!M37","v":0},{"$f":"'K20 - time schedule'!N37","v":0},{"$f":"'K20 - time schedule'!O37","v":0},{"$f":"'K20 - time schedule'!P37","v":0},{"$f":"'K20 - time schedule'!Q37","v":0},{"$f":"'K20 - time schedule'!R37","v":0},{"$f":"'K20 - time schedule'!S37","v":0},{"$f":"'K20 - time schedule'!T37","v":0},{"$f":"'K20 - time schedule'!U37","v":0},{"$f":"'K20 - time schedule'!V37","v":0},{"$f":"'K20 - time schedule'!W37","v":0},{"$f":"'K20 - time schedule'!X37","v":0},{"$f":"'K20 - time schedule'!Y37","v":0},{"$f":"'K20 - time schedule'!Z37","v":0},{"$f":"'K20 - time schedule'!AA37","v":0},{"$f":"'K20 - time schedule'!AB37","v":0},{"$f":"'K20 - time schedule'!AC37","v":0},{"$f":"'K20 - time schedule'!AD37","v":0},{"$f":"'K20 - time schedule'!AE37","v":0},{"$f":"'K20 - time schedule'!AF37","v":0},{"$f":"'K20 - time schedule'!AG37","v":0},{"$f":"'K20 - time schedule'!AH37","v":0},{"$f":"'K20 - time schedule'!AI37","v":0},{"$f":"'K20 - time schedule'!AJ37","v":0},{"$f":"'K20 - time schedule'!AK37","v":0},{"$f":"'K20 - time schedule'!AL37","v":0},{"$f":"'K20 - time schedule'!AM37","v":0},{"$f":"'K20 - time schedule'!AN37","v":0},{"$f":"'K20 - time schedule'!AO37","v":0},{"$f":"'K20 - time schedule'!AP37","v":0},{"$f":"'K20 - time schedule'!AQ37","v":0},{"$f":"'K20 - time schedule'!AR37","v":0},{"$f":"'K20 - time schedule'!AS37","v":0},{"$f":"'K20 - time schedule'!AT37","v":0},{"$f":"'K20 - time schedule'!AU37","v":0},{"$f":"'K20 - time schedule'!AV37","v":0},{"$f":"'K20 - time schedule'!AW37","v":0},{"$f":"'K20 - time schedule'!AX37","v":0},{"$f":"'K20 - time schedule'!AY37","v":0},{"$f":"'K20 - time schedule'!AZ37","v":0},{"$f":"'K20 - time schedule'!BA37","v":0},{"$f":"'K20 - time schedule'!BB37","v":0},{"$f":"'K20 - time schedule'!BC37","v":0},{"$f":"'K20 - time schedule'!BD37","v":0},{"$f":"'K20 - time schedule'!BE37","v":0},{"$f":"'K20 - time schedule'!BF37","v":0},{"$f":"'K20 - time schedule'!BG37","v":0},{"$f":"'K20 - time schedule'!BH37","v":0},{"$f":"'K20 - time schedule'!BI37","v":0},{"$f":"'K20 - time schedule'!BJ37","v":0},{"$f":"'K20 - time schedule'!BK37","v":0},{"$f":"'K20 - time schedule'!BL37","v":0},{"$f":"'K20 - time schedule'!BM37","v":0},{"$f":"'K20 - time schedule'!BN37","v":0},{"$f":"'K20 - time schedule'!BO37","v":0},{"$f":"'K20 - time schedule'!BP37","v":0},{"$f":"'K20 - time schedule'!BQ37","v":0},{"$f":"'K20 - time schedule'!BR37","v":0},{"$f":"'K20 - time schedule'!BS37","v":0},{"$f":"'K20 - time schedule'!BT37","v":0},{"$f":"'K20 - time schedule'!BU37","v":0},{"$f":"'K20 - time schedule'!BV37","v":0},{"$f":"'K20 - time schedule'!BW37","v":0},{"$f":"'K20 - time schedule'!BX37","v":0},{"$f":"'K20 - time schedule'!BY37","v":0},{"$f":"'K20 - time schedule'!BZ37","v":0},{"$f":"'K20 - time schedule'!CA37","v":0},{"$f":"'K20 - time schedule'!CB37","v":0},{"$f":"'K20 - time schedule'!CC37","v":0},{"$f":"'K20 - time schedule'!CD37","v":0},{"$f":"'K20 - time schedule'!CE37","v":0},{"$f":"'K20 - time schedule'!CF37","v":0},{"$f":"'K20 - time schedule'!CG37","v":0},{"$f":"'K20 - time schedule'!CH37","v":0},{"$f":"'K20 - time schedule'!CI37","v":0},{"$f":"'K20 - time schedule'!CJ37","v":0},{"$f":"'K20 - time schedule'!CK37","v":0},{"$f":"'K20 - time schedule'!CL37","v":0},{"$f":"'K20 - time schedule'!CM37","v":0},{"$f":"'K20 - time schedule'!CN37","v":0},{"$f":"'K20 - time schedule'!CO37","v":0},{"$f":"'K20 - time schedule'!CP37","v":0},{"$f":"'K20 - time schedule'!CQ37","v":0},{"$f":"'K20 - time schedule'!CR37","v":0},{"$f":"'K20 - time schedule'!CS37","v":0},{"$f":"'K20 - time schedule'!CT37","v":0},{"$f":"'K20 - time schedule'!CU37","v":0},{"$f":"'K20 - time schedule'!CV37","v":0},{"$f":"'K20 - time schedule'!CW37","v":0},{"$f":"'K20 - time schedule'!CX37","v":0},{"$f":"'K20 - time schedule'!CY37","v":0},{"$f":"'K20 - time schedule'!CZ37","v":0},{"$f":"'K20 - time schedule'!DA37","v":0},{"$f":"'K20 - time schedule'!DB37","v":0},{"$f":"'K20 - time schedule'!DC37","v":0},{"$f":"'K20 - time schedule'!DD37","v":0},{"$f":"'K20 - time schedule'!DE37","v":0},{"$f":"'K20 - time schedule'!DF37","v":0},{"$f":"'K20 - time schedule'!DG37","v":0},{"$f":"'K20 - time schedule'!DH37","v":0},{"$f":"'K20 - time schedule'!DI37","v":0},{"$f":"'K20 - time schedule'!DJ37","v":0},{"$f":"'K20 - time schedule'!DK37","v":0},{"$f":"'K20 - time schedule'!DL37","v":0},{"$f":"'K20 - time schedule'!DM37","v":0},{"$f":"'K20 - time schedule'!DN37","v":0},{"$f":"'K20 - time schedule'!DO37","v":0},{"$f":"'K20 - time schedule'!DP37","v":0},{"$f":"'K20 - time schedule'!DQ37","v":0},{"$f":"'K20 - time schedule'!DR37","v":0},{"$f":"'K20 - time schedule'!DS37","v":0},{"$f":"'K20 - time schedule'!DT37","v":0},{"$f":"'K20 - time schedule'!DU37","v":0},{"$f":"'K20 - time schedule'!DV37","v":0},{"$f":"'K20 - time schedule'!DW37","v":0},{"$f":"'K20 - time schedule'!DX37","v":0},{"$f":"'K20 - time schedule'!DY37","v":0},{"$f":"'K20 - time schedule'!DZ37","v":0},{"$f":"'K20 - time schedule'!EA37","v":0},{"$f":"'K20 - time schedule'!EB37","v":0},{"$f":"'K20 - time schedule'!EC37","v":0},{"$f":"'K20 - time schedule'!ED37","v":0},{"$f":"'K20 - time schedule'!EE37","v":0},{"$f":"'K20 - time schedule'!EF37","v":0},{"$f":"'K20 - time schedule'!EG37","v":0},{"$f":"'K20 - time schedule'!EH37","v":0},{"$f":"'K20 - time schedule'!EI37","v":0},{"$f":"'K20 - time schedule'!EJ37","v":0},{"$f":"'K20 - time schedule'!EK37","v":0},{"$f":"'K20 - time schedule'!EL37","v":0},{"$f":"'K20 - time schedule'!EM37","v":0},{"$f":"'K20 - time schedule'!EN37","v":0},{"$f":"'K20 - time schedule'!EO37","v":0},{"$f":"'K20 - time schedule'!EP37","v":0},{"$f":"'K20 - time schedule'!EQ37","v":0},{"$f":"'K20 - time schedule'!ER37","v":0},{"$f":"'K20 - time schedule'!ES37","v":0},{"$f":"'K20 - time schedule'!ET37","v":0},{"$f":"'K20 - time schedule'!EU37","v":0},{"$f":"'K20 - time schedule'!EV37","v":0},{"$f":"'K20 - time schedule'!EW37","v":0},{"$f":"'K20 - time schedule'!EX37","v":0},{"$f":"'K20 - time schedule'!EY37","v":0},{"$f":"'K20 - time schedule'!EZ37","v":0},{"$f":"'K20 - time schedule'!FA37","v":0},{"$f":"'K20 - time schedule'!FB37","v":0},{"$f":"'K20 - time schedule'!FC37","v":0},{"$f":"'K20 - time schedule'!FD37","v":0},{"$f":"'K20 - time schedule'!FE37","v":0},{"$f":"'K20 - time schedule'!FF37","v":0},{"$f":"'K20 - time schedule'!FG37","v":0},{"$f":"'K20 - time schedule'!FH37","v":0},{"$f":"'K20 - time schedule'!FI37","v":0},{"$f":"'K20 - time schedule'!FJ37","v":0},{"$f":"'K20 - time schedule'!FK37","v":0},{"$f":"'K20 - time schedule'!FL37","v":0},{"$f":"'K20 - time schedule'!FM37","v":0},{"$f":"'K20 - time schedule'!FN37","v":0},{"$f":"'K20 - time schedule'!FO37","v":0},{"$f":"'K20 - time schedule'!FP37","v":0},{"$f":"'K20 - time schedule'!FQ37","v":0},{"$f":"'K20 - time schedule'!FR37","v":0},{"$f":"'K20 - time schedule'!FS37","v":0},{"$f":"'K20 - time schedule'!FT37","v":0},{"$f":"'K20 - time schedule'!FU37","v":0},{"$f":"'K20 - time schedule'!FV37","v":0},{"$f":"'K20 - time schedule'!FW37","v":0},{"$f":"'K20 - time schedule'!FX37","v":0},{"$f":"'K20 - time schedule'!FY37","v":0},{"$f":"'K20 - time schedule'!FZ37","v":0},{"$f":"'K20 - time schedule'!GA37","v":0},{"$f":"'K20 - time schedule'!GB37","v":0},{"$f":"'K20 - time schedule'!GC37","v":0},{"$f":"'K20 - time schedule'!GD37","v":0},{"$f":"'K20 - time schedule'!GE37","v":0},{"$f":"'K20 - time schedule'!GF37","v":0},{"$f":"'K20 - time schedule'!GG23","v":0},{"$f":"'K20 - time schedule'!GH23","v":0},{"$f":"'K20 - time schedule'!GI23","v":0},{"$f":"'K20 - time schedule'!GJ23","v":0},{"$f":"'K20 - time schedule'!GK23","v":0},{"$f":"'K20 - time schedule'!GL23","v":0},{"$f":"'K20 - time schedule'!GM23","v":0},{"$f":"'K20 - time schedule'!GN23","v":0},{"$f":"'K20 - time schedule'!GO23","v":0},{"$f":"'K20 - time schedule'!GP23","v":0},{"$f":"'K20 - time schedule'!GQ23","v":0},{"$f":"'K20 - time schedule'!GR23","v":0},{"$f":"'K20 - time schedule'!GS23","v":0},{"$f":"'K20 - time schedule'!GT23","v":0},{"$f":"'K20 - time schedule'!GU23","v":0},{"$f":"'K20 - time schedule'!GV23","v":0},{"$f":"'K20 - time schedule'!GW23","v":0},{"$f":"'K20 - time schedule'!GX23","v":0},{"$f":"'K20 - time schedule'!GY23","v":0},{"$f":"'K20 - time schedule'!GZ23","v":0},{"$f":"'K20 - time schedule'!HA23","v":0},{"$f":"'K20 - time schedule'!HB23","v":0},{"$f":"'K20 - time schedule'!HC23","v":0},{"$f":"'K20 - time schedule'!HD23","v":0},{"$f":"'K20 - time schedule'!HE23","v":0},{"$f":"'K20 - time schedule'!HF23","v":0},{"$f":"'K20 - time schedule'!HG23","v":0},{"$f":"'K20 - time schedule'!HH23","v":0},{"$f":"'K20 - time schedule'!HI23","v":0},{"$f":"'K20 - time schedule'!HJ23","v":0},{"$f":"'K20 - time schedule'!HK23","v":0},{"$f":"'K20 - time schedule'!HL23","v":0},{"$f":"'K20 - time schedule'!HM23","v":0},{"$f":"'K20 - time schedule'!HN23","v":0},{"$f":"'K20 - time schedule'!HO23","v":0},{"$f":"'K20 - time schedule'!HP23","v":0},{"$f":"'K20 - time schedule'!HQ23","v":0},{"$f":"'K20 - time schedule'!HR23","v":0},{"$f":"'K20 - time schedule'!HS23","v":0},{"$f":"'K20 - time schedule'!HT23","v":0},{"$f":"'K20 - time schedule'!HU23","v":0},{"$f":"'K20 - time schedule'!HV23","v":0},{"$f":"'K20 - time schedule'!HW23","v":0},{"$f":"'K20 - time schedule'!HX23","v":0},{"$f":"'K20 - time schedule'!HY23","v":0},{"$f":"'K20 - time schedule'!HZ23","v":0},{"$f":"'K20 - time schedule'!IA23","v":0},{"$f":"'K20 - time schedule'!IB23","v":0},{"$f":"'K20 - time schedule'!IC23","v":0},{"$f":"'K20 - time schedule'!ID23","v":0},{"$f":"'K20 - time schedule'!IE23","v":0},{"$f":"'K20 - time schedule'!IF23","v":0},{"$f":"'K20 - time schedule'!IG23","v":0},{"$f":"'K20 - time schedule'!IH23","v":0},{"$f":"'K20 - time schedule'!II23","v":0},{"$f":"'K20 - time schedule'!IJ23","v":0},{"$f":"'K20 - time schedule'!IK23","v":0},{"$f":"'K20 - time schedule'!IL23","v":0},{"$f":"'K20 - time schedule'!IM23","v":0},{"$f":"'K20 - time schedule'!IN23","v":0},{"$f":"'K20 - time schedule'!IO23","v":0},{"$f":"'K20 - time schedule'!IP23","v":0},{"$f":"'K20 - time schedule'!IQ23","v":0},{"$f":"'K20 - time schedule'!IR23","v":0},{"$f":"'K20 - time schedule'!IS23","v":0},{"$f":"'K20 - time schedule'!IT23","v":0},{"$f":"'K20 - time schedule'!IU23","v":0},{"$f":"'K20 - time schedule'!IV23","v":0},{"$f":"'K20 - time schedule'!IW23","v":0},{"$f":"'K20 - time schedule'!IX23","v":0},{"$f":"'K20 - time schedule'!IY23","v":0},{"$f":"'K20 - time schedule'!IZ23","v":0},{"$f":"'K20 - time schedule'!JA23","v":0},{"$f":"'K20 - time schedule'!JB23","v":0},{"$f":"'K20 - time schedule'!JC23","v":0},{"$f":"'K20 - time schedule'!JD23","v":0},{"$f":"'K20 - time schedule'!JE23","v":0},{"$f":"'K20 - time schedule'!JF23","v":0},{"$f":"'K20 - time schedule'!JG23","v":0},{"$f":"'K20 - time schedule'!JH23","v":0},{"$f":"'K20 - time schedule'!JI23","v":0},{"$f":"'K20 - time schedule'!JJ23","v":0},{"$f":"'K20 - time schedule'!JK23","v":0},{"$f":"'K20 - time schedule'!JL23","v":0},{"$f":"'K20 - time schedule'!JM23","v":0},{"$f":"'K20 - time schedule'!JN23","v":0},{"$f":"'K20 - time schedule'!JO23","v":0},{"$f":"'K20 - time schedule'!JP23","v":0},{"$f":"'K20 - time schedule'!JQ23","v":0},{"$f":"'K20 - time schedule'!JR23","v":0},{"$f":"'K20 - time schedule'!JS23","v":0},{"$f":"'K20 - time schedule'!JT23","v":0},{"$f":"'K20 - time schedule'!JU23","v":0},{"$f":"'K20 - time schedule'!JV23","v":0},{"$f":"'K20 - time schedule'!JW23","v":0},{"$f":"'K20 - time schedule'!JX23","v":0},{"$f":"'K20 - time schedule'!JY23","v":0},{"$f":"'K20 - time schedule'!JZ23","v":0},{"$f":"'K20 - time schedule'!KA23","v":0},{"$f":"'K20 - time schedule'!KB23","v":0},{"$f":"'K20 - time schedule'!KC23","v":0},{"$f":"'K20 - time schedule'!KD23","v":0},{"$f":"'K20 - time schedule'!KE23","v":0},{"$f":"'K20 - time schedule'!KF23","v":0},{"$f":"'K20 - time schedule'!KG23","v":0},{"$f":"'K20 - time schedule'!KH23","v":0},{"$f":"'K20 - time schedule'!KI23","v":0},{"$f":"'K20 - time schedule'!KJ23","v":0},{"$f":"'K20 - time schedule'!KK23","v":0},{"$f":"'K20 - time schedule'!KL23","v":0},{"$f":"'K20 - time schedule'!KM23","v":0},{"$f":"'K20 - time schedule'!KN23","v":0},{"$f":"'K20 - time schedule'!KO23","v":0},{"$f":"'K20 - time schedule'!KP23","v":0},{"$f":"'K20 - time schedule'!KQ23","v":0},{"$f":"'K20 - time schedule'!KR23","v":0},{"$f":"'K20 - time schedule'!KS23","v":0},{"$f":"'K20 - time schedule'!KT23","v":0}]
["Boiler room K20 - media connection","K20","EUR",{"$f":"'K20 - time schedule'!G39","v":0},{"$f":"'K20 - time schedule'!H39","v":0},{"$f":"'K20 - time schedule'!I39","v":0},{"$f":"'K20 - time schedule'!J39","v":0},{"$f":"'K20 - time schedule'!K39","v":0},{"$f":"'K20 - time schedule'!L39","v":0},{"$f":"'K20 - time schedule'!M39","v":0},{"$f":"'K20 - time schedule'!N39","v":0},{"$f":"'K20 - time schedule'!O39","v":0},{"$f":"'K20 - time schedule'!P39","v":0},{"$f":"'K20 - time schedule'!Q39","v":0},{"$f":"'K20 - time schedule'!R39","v":0},{"$f":"'K20 - time schedule'!S39","v":0},{"$f":"'K20 - time schedule'!T39","v":0},{"$f":"'K20 - time schedule'!U39","v":0},{"$f":"'K20 - time schedule'!V39","v":0},{"$f":"'K20 - time schedule'!W39","v":0},{"$f":"'K20 - time schedule'!X39","v":0},{"$f":"'K20 - time schedule'!Y39","v":0},{"$f":"'K20 - time schedule'!Z39","v":0},{"$f":"'K20 - time schedule'!AA39","v":0},{"$f":"'K20 - time schedule'!AB39","v":0},{"$f":"'K20 - time schedule'!AC39","v":0},{"$f":"'K20 - time schedule'!AD39","v":0},{"$f":"'K20 - time schedule'!AE39","v":0},{"$f":"'K20 - time schedule'!AF39","v":0},{"$f":"'K20 - time schedule'!AG39","v":0},{"$f":"'K20 - time schedule'!AH39","v":0},{"$f":"'K20 - time schedule'!AI39","v":0},{"$f":"'K20 - time schedule'!AJ39","v":0},{"$f":"'K20 - time schedule'!AK39","v":0},{"$f":"'K20 - time schedule'!AL39","v":0},{"$f":"'K20 - time schedule'!AM39","v":0},{"$f":"'K20 - time schedule'!AN39","v":0},{"$f":"'K20 - time schedule'!AO39","v":0},{"$f":"'K20 - time schedule'!AP39","v":0},{"$f":"'K20 - time schedule'!AQ39","v":0},{"$f":"'K20 - time schedule'!AR39","v":0},{"$f":"'K20 - time schedule'!AS39","v":0},{"$f":"'K20 - time schedule'!AT39","v":0},{"$f":"'K20 - time schedule'!AU39","v":0},{"$f":"'K20 - time schedule'!AV39","v":0},{"$f":"'K20 - time schedule'!AW39","v":0},{"$f":"'K20 - time schedule'!AX39","v":0},{"$f":"'K20 - time schedule'!AY39","v":0},{"$f":"'K20 - time schedule'!AZ39","v":0},{"$f":"'K20 - time schedule'!BA39","v":0},{"$f":"'K20 - time schedule'!BB39","v":0},{"$f":"'K20 - time schedule'!BC39","v":0},{"$f":"'K20 - time schedule'!BD39","v":0},{"$f":"'K20 - time schedule'!BE39","v":0},{"$f":"'K20 - time schedule'!BF39","v":0},{"$f":"'K20 - time schedule'!BG39","v":0},{"$f":"'K20 - time schedule'!BH39","v":0},{"$f":"'K20 - time schedule'!BI39","v":0},{"$f":"'K20 - time schedule'!BJ39","v":0},{"$f":"'K20 - time schedule'!BK39","v":0},{"$f":"'K20 - time schedule'!BL39","v":0},{"$f":"'K20 - time schedule'!BM39","v":0},{"$f":"'K20 - time schedule'!BN39","v":0},{"$f":"'K20 - time schedule'!BO39","v":0},{"$f":"'K20 - time schedule'!BP39","v":0},{"$f":"'K20 - time schedule'!BQ39","v":0},{"$f":"'K20 - time schedule'!BR39","v":0},{"$f":"'K20 - time schedule'!BS39","v":0},{"$f":"'K20 - time schedule'!BT39","v":0},{"$f":"'K20 - time schedule'!BU39","v":0},{"$f":"'K20 - time schedule'!BV39","v":0},{"$f":"'K20 - time schedule'!BW39","v":0},{"$f":"'K20 - time schedule'!BX39","v":0},{"$f":"'K20 - time schedule'!BY39","v":0},{"$f":"'K20 - time schedule'!BZ39","v":0},{"$f":"'K20 - time schedule'!CA39","v":0},{"$f":"'K20 - time schedule'!CB39","v":0},{"$f":"'K20 - time schedule'!CC39","v":0},{"$f":"'K20 - time schedule'!CD39","v":0},{"$f":"'K20 - time schedule'!CE39","v":0},{"$f":"'K20 - time schedule'!CF39","v":0},{"$f":"'K20 - time schedule'!CG39","v":0},{"$f":"'K20 - time schedule'!CH39","v":0},{"$f":"'K20 - time schedule'!CI39","v":0},{"$f":"'K20 - time schedule'!CJ39","v":0},{"$f":"'K20 - time schedule'!CK39","v":0},{"$f":"'K20 - time schedule'!CL39","v":0},{"$f":"'K20 - time schedule'!CM39","v":0},{"$f":"'K20 - time schedule'!CN39","v":0},{"$f":"'K20 - time schedule'!CO39","v":0},{"$f":"'K20 - time schedule'!CP39","v":0},{"$f":"'K20 - time schedule'!CQ39","v":0},{"$f":"'K20 - time schedule'!CR39","v":0},{"$f":"'K20 - time schedule'!CS39","v":0},{"$f":"'K20 - time schedule'!CT39","v":0},{"$f":"'K20 - time schedule'!CU39","v":0},{"$f":"'K20 - time schedule'!CV39","v":0},{"$f":"'K20 - time schedule'!CW39","v":0},{"$f":"'K20 - time schedule'!CX39","v":0},{"$f":"'K20 - time schedule'!CY39","v":0},{"$f":"'K20 - time schedule'!CZ39","v":0},{"$f":"'K20 - time schedule'!DA39","v":0},{"$f":"'K20 - time schedule'!DB39","v":0},{"$f":"'K20 - time schedule'!DC39","v":0},{"$f":"'K20 - time schedule'!DD39","v":0},{"$f":"'K20 - time schedule'!DE39","v":0},{"$f":"'K20 - time schedule'!DF39","v":0},{"$f":"'K20 - time schedule'!DG39","v":0},{"$f":"'K20 - time schedule'!DH39","v":0},{"$f":"'K20 - time schedule'!DI39","v":0},{"$f":"'K20 - time schedule'!DJ39","v":0},{"$f":"'K20 - time schedule'!DK39","v":0},{"$f":"'K20 - time schedule'!DL39","v":0},{"$f":"'K20 - time schedule'!DM39","v":0},{"$f":"'K20 - time schedule'!DN39","v":0},{"$f":"'K20 - time schedule'!DO39","v":0},{"$f":"'K20 - time schedule'!DP39","v":0},{"$f":"'K20 - time schedule'!DQ39","v":0},{"$f":"'K20 - time schedule'!DR39","v":0},{"$f":"'K20 - time schedule'!DS39","v":0},{"$f":"'K20 - time schedule'!DT39","v":0},{"$f":"'K20 - time schedule'!DU39","v":0},{"$f":"'K20 - time schedule'!DV39","v":0},{"$f":"'K20 - time schedule'!DW39","v":0},{"$f":"'K20 - time schedule'!DX39","v":0},{"$f":"'K20 - time schedule'!DY39","v":0},{"$f":"'K20 - time schedule'!DZ39","v":0},{"$f":"'K20 - time schedule'!EA39","v":0},{"$f":"'K20 - time schedule'!EB39","v":0},{"$f":"'K20 - time schedule'!EC39","v":0},{"$f":"'K20 - time schedule'!ED39","v":0},{"$f":"'K20 - time schedule'!EE39","v":0},{"$f":"'K20 - time schedule'!EF39","v":0},{"$f":"'K20 - time schedule'!EG39","v":0},{"$f":"'K20 - time schedule'!EH39","v":0},{"$f":"'K20 - time schedule'!EI39","v":0},{"$f":"'K20 - time schedule'!EJ39","v":0},{"$f":"'K20 - time schedule'!EK39","v":0},{"$f":"'K20 - time schedule'!EL39","v":0},{"$f":"'K20 - time schedule'!EM39","v":0},{"$f":"'K20 - time schedule'!EN39","v":0},{"$f":"'K20 - time schedule'!EO39","v":0},{"$f":"'K20 - time schedule'!EP39","v":0},{"$f":"'K20 - time schedule'!EQ39","v":0},{"$f":"'K20 - time schedule'!ER39","v":0},{"$f":"'K20 - time schedule'!ES39","v":0},{"$f":"'K20 - time schedule'!ET39","v":0},{"$f":"'K20 - time schedule'!EU39","v":0},{"$f":"'K20 - time schedule'!EV39","v":0},{"$f":"'K20 - time schedule'!EW39","v":0},{"$f":"'K20 - time schedule'!EX39","v":0},{"$f":"'K20 - time schedule'!EY39","v":0},{"$f":"'K20 - time schedule'!EZ39","v":0},{"$f":"'K20 - time schedule'!FA39","v":0},{"$f":"'K20 - time schedule'!FB39","v":0},{"$f":"'K20 - time schedule'!FC39","v":0},{"$f":"'K20 - time schedule'!FD39","v":0},{"$f":"'K20 - time schedule'!FE39","v":0},{"$f":"'K20 - time schedule'!FF39","v":0},{"$f":"'K20 - time schedule'!FG39","v":0},{"$f":"'K20 - time schedule'!FH39","v":0},{"$f":"'K20 - time schedule'!FI39","v":0},{"$f":"'K20 - time schedule'!FJ39","v":0},{"$f":"'K20 - time schedule'!FK39","v":0},{"$f":"'K20 - time schedule'!FL39","v":0},{"$f":"'K20 - time schedule'!FM39","v":0},{"$f":"'K20 - time schedule'!FN39","v":0},{"$f":"'K20 - time schedule'!FO39","v":0},{"$f":"'K20 - time schedule'!FP39","v":0},{"$f":"'K20 - time schedule'!FQ39","v":0},{"$f":"'K20 - time schedule'!FR39","v":0},{"$f":"'K20 - time schedule'!FS39","v":0},{"$f":"'K20 - time schedule'!FT39","v":0},{"$f":"'K20 - time schedule'!FU39","v":0},{"$f":"'K20 - time schedule'!FV39","v":0},{"$f":"'K20 - time schedule'!FW39","v":0},{"$f":"'K20 - time schedule'!FX39","v":0},{"$f":"'K20 - time schedule'!FY39","v":0},{"$f":"'K20 - time schedule'!FZ39","v":0},{"$f":"'K20 - time schedule'!GA39","v":0},{"$f":"'K20 - time schedule'!GB39","v":0},{"$f":"'K20 - time schedule'!GC39","v":0},{"$f":"'K20 - time schedule'!GD39","v":0},{"$f":"'K20 - time schedule'!GE39","v":0},{"$f":"'K20 - time schedule'!GF39","v":0},{"$f":"'K20 - time schedule'!GG24","v":0},{"$f":"'K20 - time schedule'!GH24","v":0},{"$f":"'K20 - time schedule'!GI24","v":0},{"$f":"'K20 - time schedule'!GJ24","v":0},{"$f":"'K20 - time schedule'!GK24","v":0},{"$f":"'K20 - time schedule'!GL24","v":0},{"$f":"'K20 - time schedule'!GM24","v":0},{"$f":"'K20 - time schedule'!GN24","v":0},{"$f":"'K20 - time schedule'!GO24","v":0},{"$f":"'K20 - time schedule'!GP24","v":0},{"$f":"'K20 - time schedule'!GQ24","v":0},{"$f":"'K20 - time schedule'!GR24","v":0},{"$f":"'K20 - time schedule'!GS24","v":0},{"$f":"'K20 - time schedule'!GT24","v":0},{"$f":"'K20 - time schedule'!GU24","v":0},{"$f":"'K20 - time schedule'!GV24","v":0},{"$f":"'K20 - time schedule'!GW24","v":0},{"$f":"'K20 - time schedule'!GX24","v":0},{"$f":"'K20 - time schedule'!GY24","v":0},{"$f":"'K20 - time schedule'!GZ24","v":0},{"$f":"'K20 - time schedule'!HA24","v":0},{"$f":"'K20 - time schedule'!HB24","v":0},{"$f":"'K20 - time schedule'!HC24","v":0},{"$f":"'K20 - time schedule'!HD24","v":0},{"$f":"'K20 - time schedule'!HE24","v":0},{"$f":"'K20 - time schedule'!HF24","v":0},{"$f":"'K20 - time schedule'!HG24","v":0},{"$f":"'K20 - time schedule'!HH24","v":0},{"$f":"'K20 - time schedule'!HI24","v":0},{"$f":"'K20 - time schedule'!HJ24","v":0},{"$f":"'K20 - time schedule'!HK24","v":0},{"$f":"'K20 - time schedule'!HL24","v":0},{"$f":"'K20 - time schedule'!HM24","v":0},{"$f":"'K20 - time schedule'!HN24","v":0},{"$f":"'K20 - time schedule'!HO24","v":0},{"$f":"'K20 - time schedule'!HP24","v":0},{"$f":"'K20 - time schedule'!HQ24","v":0},{"$f":"'K20 - time schedule'!HR24","v":0},{"$f":"'K20 - time schedule'!HS24","v":0},{"$f":"'K20 - time schedule'!HT24","v":0},{"$f":"'K20 - time schedule'!HU24","v":0},{"$f":"'K20 - time schedule'!HV24","v":0},{"$f":"'K20 - time schedule'!HW24","v":0},{"$f":"'K20 - time schedule'!HX24","v":0},{"$f":"'K20 - time schedule'!HY24","v":0},{"$f":"'K20 - time schedule'!HZ24","v":0},{"$f":"'K20 - time schedule'!IA24","v":0},{"$f":"'K20 - time schedule'!IB24","v":0},{"$f":"'K20 - time schedule'!IC24","v":0},{"$f":"'K20 - time schedule'!ID24","v":0},{"$f":"'K20 - time schedule'!IE24","v":0},{"$f":"'K20 - time schedule'!IF24","v":0},{"$f":"'K20 - time schedule'!IG24","v":0},{"$f":"'K20 - time schedule'!IH24","v":0},{"$f":"'K20 - time schedule'!II24","v":0},{"$f":"'K20 - time schedule'!IJ24","v":0},{"$f":"'K20 - time schedule'!IK24","v":0},{"$f":"'K20 - time schedule'!IL24","v":0},{"$f":"'K20 - time schedule'!IM24","v":0},{"$f":"'K20 - time schedule'!IN24","v":0},{"$f":"'K20 - time schedule'!IO24","v":0},{"$f":"'K20 - time schedule'!IP24","v":0},{"$f":"'K20 - time schedule'!IQ24","v":0},{"$f":"'K20 - time schedule'!IR24","v":0},{"$f":"'K20 - time schedule'!IS24","v":0},{"$f":"'K20 - time schedule'!IT24","v":0},{"$f":"'K20 - time schedule'!IU24","v":0},{"$f":"'K20 - time schedule'!IV24","v":0},{"$f":"'K20 - time schedule'!IW24","v":0},{"$f":"'K20 - time schedule'!IX24","v":0},{"$f":"'K20 - time schedule'!IY24","v":0},{"$f":"'K20 - time schedule'!IZ24","v":0},{"$f":"'K20 - time schedule'!JA24","v":0},{"$f":"'K20 - time schedule'!JB24","v":0},{"$f":"'K20 - time schedule'!JC24","v":0},{"$f":"'K20 - time schedule'!JD24","v":0},{"$f":"'K20 - time schedule'!JE24","v":0},{"$f":"'K20 - time schedule'!JF24","v":0},{"$f":"'K20 - time schedule'!JG24","v":0},{"$f":"'K20 - time schedule'!JH24","v":0},{"$f":"'K20 - time schedule'!JI24","v":0},{"$f":"'K20 - time schedule'!JJ24","v":0},{"$f":"'K20 - time schedule'!JK24","v":0},{"$f":"'K20 - time schedule'!JL24","v":0},{"$f":"'K20 - time schedule'!JM24","v":0},{"$f":"'K20 - time schedule'!JN24","v":0},{"$f":"'K20 - time schedule'!JO24","v":0},{"$f":"'K20 - time schedule'!JP24","v":0},{"$f":"'K20 - time schedule'!JQ24","v":0},{"$f":"'K20 - time schedule'!JR24","v":0},{"$f":"'K20 - time schedule'!JS24","v":0},{"$f":"'K20 - time schedule'!JT24","v":0},{"$f":"'K20 - time schedule'!JU24","v":0},{"$f":"'K20 - time schedule'!JV24","v":0},{"$f":"'K20 - time schedule'!JW24","v":0},{"$f":"'K20 - time schedule'!JX24","v":0},{"$f":"'K20 - time schedule'!JY24","v":0},{"$f":"'K20 - time schedule'!JZ24","v":0},{"$f":"'K20 - time schedule'!KA24","v":0},{"$f":"'K20 - time schedule'!KB24","v":0},{"$f":"'K20 - time schedule'!KC24","v":0},{"$f":"'K20 - time schedule'!KD24","v":0},{"$f":"'K20 - time schedule'!KE24","v":0},{"$f":"'K20 - time schedule'!KF24","v":0},{"$f":"'K20 - time schedule'!KG24","v":0},{"$f":"'K20 - time schedule'!KH24","v":0},{"$f":"'K20 - time schedule'!KI24","v":0},{"$f":"'K20 - time schedule'!KJ24","v":0},{"$f":"'K20 - time schedule'!KK24","v":0},{"$f":"'K20 - time schedule'!KL24","v":0},{"$f":"'K20 - time schedule'!KM24","v":0},{"$f":"'K20 - time schedule'!KN24","v":0},{"$f":"'K20 - time schedule'!KO24","v":0},{"$f":"'K20 - time schedule'!KP24","v":0},{"$f":"'K20 - time schedule'!KQ24","v":0},{"$f":"'K20 - time schedule'!KR24","v":0},{"$f":"'K20 - time schedule'!KS24","v":0},{"$f":"'K20 - time schedule'!KT24","v":0}]
["Boiler room K20 - outdoor flue lines including chimney connection","K20","EUR",{"$f":"'K20 - time schedule'!G41","v":0},{"$f":"'K20 - time schedule'!H41","v":0},{"$f":"'K20 - time schedule'!I41","v":0},{"$f":"'K20 - time schedule'!J41","v":0},{"$f":"'K20 - time schedule'!K41","v":0},{"$f":"'K20 - time schedule'!L41","v":0},{"$f":"'K20 - time schedule'!M41","v":0},{"$f":"'K20 - time schedule'!N41","v":0},{"$f":"'K20 - time schedule'!O41","v":0},{"$f":"'K20 - time schedule'!P41","v":0},{"$f":"'K20 - time schedule'!Q41","v":0},{"$f":"'K20 - time schedule'!R41","v":0},{"$f":"'K20 - time schedule'!S41","v":0},{"$f":"'K20 - time schedule'!T41","v":0},{"$f":"'K20 - time schedule'!U41","v":0},{"$f":"'K20 - time schedule'!V41","v":0},{"$f":"'K20 - time schedule'!W41","v":0},{"$f":"'K20 - time schedule'!X41","v":0},{"$f":"'K20 - time schedule'!Y41","v":0},{"$f":"'K20 - time schedule'!Z41","v":0},{"$f":"'K20 - time schedule'!AA41","v":0},{"$f":"'K20 - time schedule'!AB41","v":0},{"$f":"'K20 - time schedule'!AC41","v":0},{"$f":"'K20 - time schedule'!AD41","v":0},{"$f":"'K20 - time schedule'!AE41","v":0},{"$f":"'K20 - time schedule'!AF41","v":0},{"$f":"'K20 - time schedule'!AG41","v":0},{"$f":"'K20 - time schedule'!AH41","v":0},{"$f":"'K20 - time schedule'!AI41","v":0},{"$f":"'K20 - time schedule'!AJ41","v":0},{"$f":"'K20 - time schedule'!AK41","v":0},{"$f":"'K20 - time schedule'!AL41","v":0},{"$f":"'K20 - time schedule'!AM41","v":0},{"$f":"'K20 - time schedule'!AN41","v":0},{"$f":"'K20 - time schedule'!AO41","v":0},{"$f":"'K20 - time schedule'!AP41","v":0},{"$f":"'K20 - time schedule'!AQ41","v":0},{"$f":"'K20 - time schedule'!AR41","v":0},{"$f":"'K20 - time schedule'!AS41","v":0},{"$f":"'K20 - time schedule'!AT41","v":0},{"$f":"'K20 - time schedule'!AU41","v":0},{"$f":"'K20 - time schedule'!AV41","v":0},{"$f":"'K20 - time schedule'!AW41","v":0},{"$f":"'K20 - time schedule'!AX41","v":0},{"$f":"'K20 - time schedule'!AY41","v":0},{"$f":"'K20 - time schedule'!AZ41","v":0},{"$f":"'K20 - time schedule'!BA41","v":0},{"$f":"'K20 - time schedule'!BB41","v":0},{"$f":"'K20 - time schedule'!BC41","v":0},{"$f":"'K20 - time schedule'!BD41","v":0},{"$f":"'K20 - time schedule'!BE41","v":0},{"$f":"'K20 - time schedule'!BF41","v":0},{"$f":"'K20 - time schedule'!BG41","v":0},{"$f":"'K20 - time schedule'!BH41","v":0},{"$f":"'K20 - time schedule'!BI41","v":0},{"$f":"'K20 - time schedule'!BJ41","v":0},{"$f":"'K20 - time schedule'!BK41","v":0},{"$f":"'K20 - time schedule'!BL41","v":0},{"$f":"'K20 - time schedule'!BM41","v":0},{"$f":"'K20 - time schedule'!BN41","v":0},{"$f":"'K20 - time schedule'!BO41","v":0},{"$f":"'K20 - time schedule'!BP41","v":0},{"$f":"'K20 - time schedule'!BQ41","v":0},{"$f":"'K20 - time schedule'!BR41","v":0},{"$f":"'K20 - time schedule'!BS41","v":0},{"$f":"'K20 - time schedule'!BT41","v":0},{"$f":"'K20 - time schedule'!BU41","v":0},{"$f":"'K20 - time schedule'!BV41","v":0},{"$f":"'K20 - time schedule'!BW41","v":0},{"$f":"'K20 - time schedule'!BX41","v":0},{"$f":"'K20 - time schedule'!BY41","v":0},{"$f":"'K20 - time schedule'!BZ41","v":0},{"$f":"'K20 - time schedule'!CA41","v":0},{"$f":"'K20 - time schedule'!CB41","v":0},{"$f":"'K20 - time schedule'!CC41","v":0},{"$f":"'K20 - time schedule'!CD41","v":0},{"$f":"'K20 - time schedule'!CE41","v":0},{"$f":"'K20 - time schedule'!CF41","v":0},{"$f":"'K20 - time schedule'!CG41","v":0},{"$f":"'K20 - time schedule'!CH41","v":0},{"$f":"'K20 - time schedule'!CI41","v":0},{"$f":"'K20 - time schedule'!CJ41","v":0},{"$f":"'K20 - time schedule'!CK41","v":0},{"$f":"'K20 - time schedule'!CL41","v":0},{"$f":"'K20 - time schedule'!CM41","v":0},{"$f":"'K20 - time schedule'!CN41","v":0},{"$f":"'K20 - time schedule'!CO41","v":0},{"$f":"'K20 - time schedule'!CP41","v":0},{"$f":"'K20 - time schedule'!CQ41","v":0},{"$f":"'K20 - time schedule'!CR41","v":0},{"$f":"'K20 - time schedule'!CS41","v":0},{"$f":"'K20 - time schedule'!CT41","v":0},{"$f":"'K20 - time schedule'!CU41","v":0},{"$f":"'K20 - time schedule'!CV41","v":0},{"$f":"'K20 - time schedule'!CW41","v":0},{"$f":"'K20 - time schedule'!CX41","v":0},{"$f":"'K20 - time schedule'!CY41","v":0},{"$f":"'K20 - time schedule'!CZ41","v":0},{"$f":"'K20 - time schedule'!DA41","v":0},{"$f":"'K20 - time schedule'!DB41","v":0},{"$f":"'K20 - time schedule'!DC41","v":0},{"$f":"'K20 - time schedule'!DD41","v":0},{"$f":"'K20 - time schedule'!DE41","v":0},{"$f":"'K20 - time schedule'!DF41","v":0},{"$f":"'K20 - time schedule'!DG41","v":0},{"$f":"'K20 - time schedule'!DH41","v":0},{"$f":"'K20 - time schedule'!DI41","v":0},{"$f":"'K20 - time schedule'!DJ41","v":0},{"$f":"'K20 - time schedule'!DK41","v":0},{"$f":"'K20 - time schedule'!DL41","v":0},{"$f":"'K20 - time schedule'!DM41","v":0},{"$f":"'K20 - time schedule'!DN41","v":0},{"$f":"'K20 - time schedule'!DO41","v":0},{"$f":"'K20 - time schedule'!DP41","v":0},{"$f":"'K20 - time schedule'!DQ41","v":0},{"$f":"'K20 - time schedule'!DR41","v":0},{"$f":"'K20 - time schedule'!DS41","v":0},{"$f":"'K20 - time schedule'!DT41","v":0},{"$f":"'K20 - time schedule'!DU41","v":0},{"$f":"'K20 - time schedule'!DV41","v":0},{"$f":"'K20 - time schedule'!DW41","v":0},{"$f":"'K20 - time schedule'!DX41","v":0},{"$f":"'K20 - time schedule'!DY41","v":0},{"$f":"'K20 - time schedule'!DZ41","v":0},{"$f":"'K20 - time schedule'!EA41","v":0},{"$f":"'K20 - time schedule'!EB41","v":0},{"$f":"'K20 - time schedule'!EC41","v":0},{"$f":"'K20 - time schedule'!ED41","v":0},{"$f":"'K20 - time schedule'!EE41","v":0},{"$f":"'K20 - time schedule'!EF41","v":0},{"$f":"'K20 - time schedule'!EG41","v":0},{"$f":"'K20 - time schedule'!EH41","v":0},{"$f":"'K20 - time schedule'!EI41","v":0},{"$f":"'K20 - time schedule'!EJ41","v":0},{"$f":"'K20 - time schedule'!EK41","v":0},{"$f":"'K20 - time schedule'!EL41","v":0},{"$f":"'K20 - time schedule'!EM41","v":0},{"$f":"'K20 - time schedule'!EN41","v":0},{"$f":"'K20 - time schedule'!EO41","v":0},{"$f":"'K20 - time schedule'!EP41","v":0},{"$f":"'K20 - time schedule'!EQ41","v":0},{"$f":"'K20 - time schedule'!ER41","v":0},{"$f":"'K20 - time schedule'!ES41","v":0},{"$f":"'K20 - time schedule'!ET41","v":0},{"$f":"'K20 - time schedule'!EU41","v":0},{"$f":"'K20 - time schedule'!EV41","v":0},{"$f":"'K20 - time schedule'!EW41","v":0},{"$f":"'K20 - time schedule'!EX41","v":0},{"$f":"'K20 - time schedule'!EY41","v":0},{"$f":"'K20 - time schedule'!EZ41","v":0},{"$f":"'K20 - time schedule'!FA41","v":0},{"$f":"'K20 - time schedule'!FB41","v":0},{"$f":"'K20 - time schedule'!FC41","v":0},{"$f":"'K20 - time schedule'!FD41","v":0},{"$f":"'K20 - time schedule'!FE41","v":0},{"$f":"'K20 - time schedule'!FF41","v":0},{"$f":"'K20 - time schedule'!FG41","v":0},{"$f":"'K20 - time schedule'!FH41","v":0},{"$f":"'K20 - time schedule'!FI41","v":0},{"$f":"'K20 - time schedule'!FJ41","v":0},{"$f":"'K20 - time schedule'!FK41","v":0},{"$f":"'K20 - time schedule'!FL41","v":0},{"$f":"'K20 - time schedule'!FM41","v":0},{"$f":"'K20 - time schedule'!FN41","v":0},{"$f":"'K20 - time schedule'!FO41","v":0},{"$f":"'K20 - time schedule'!FP41","v":0},{"$f":"'K20 - time schedule'!FQ41","v":0},{"$f":"'K20 - time schedule'!FR41","v":0},{"$f":"'K20 - time schedule'!FS41","v":0},{"$f":"'K20 - time schedule'!FT41","v":0},{"$f":"'K20 - time schedule'!FU41","v":0},{"$f":"'K20 - time schedule'!FV41","v":0},{"$f":"'K20 - time schedule'!FW41","v":0},{"$f":"'K20 - time schedule'!FX41","v":0},{"$f":"'K20 - time schedule'!FY41","v":0},{"$f":"'K20 - time schedule'!FZ41","v":0},{"$f":"'K20 - time schedule'!GA41","v":0},{"$f":"'K20 - time schedule'!GB41","v":0},{"$f":"'K20 - time schedule'!GC41","v":0},{"$f":"'K20 - time schedule'!GD41","v":0},{"$f":"'K20 - time schedule'!GE41","v":0},{"$f":"'K20 - time schedule'!GF41","v":0},{"$f":"'K20 - time schedule'!GG25","v":0},{"$f":"'K20 - time schedule'!GH25","v":0},{"$f":"'K20 - time schedule'!GI25","v":0},{"$f":"'K20 - time schedule'!GJ25","v":0},{"$f":"'K20 - time schedule'!GK25","v":0},{"$f":"'K20 - time schedule'!GL25","v":0},{"$f":"'K20 - time schedule'!GM25","v":0},{"$f":"'K20 - time schedule'!GN25","v":0},{"$f":"'K20 - time schedule'!GO25","v":0},{"$f":"'K20 - time schedule'!GP25","v":0},{"$f":"'K20 - time schedule'!GQ25","v":0},{"$f":"'K20 - time schedule'!GR25","v":0},{"$f":"'K20 - time schedule'!GS25","v":0},{"$f":"'K20 - time schedule'!GT25","v":0},{"$f":"'K20 - time schedule'!GU25","v":0},{"$f":"'K20 - time schedule'!GV25","v":0},{"$f":"'K20 - time schedule'!GW25","v":0},{"$f":"'K20 - time schedule'!GX25","v":0},{"$f":"'K20 - time schedule'!GY25","v":0},{"$f":"'K20 - time schedule'!GZ25","v":0},{"$f":"'K20 - time schedule'!HA25","v":0},{"$f":"'K20 - time schedule'!HB25","v":0},{"$f":"'K20 - time schedule'!HC25","v":0},{"$f":"'K20 - time schedule'!HD25","v":0},{"$f":"'K20 - time schedule'!HE25","v":0},{"$f":"'K20 - time schedule'!HF25","v":0},{"$f":"'K20 - time schedule'!HG25","v":0},{"$f":"'K20 - time schedule'!HH25","v":0},{"$f":"'K20 - time schedule'!HI25","v":0},{"$f":"'K20 - time schedule'!HJ25","v":0},{"$f":"'K20 - time schedule'!HK25","v":0},{"$f":"'K20 - time schedule'!HL25","v":0},{"$f":"'K20 - time schedule'!HM25","v":0},{"$f":"'K20 - time schedule'!HN25","v":0},{"$f":"'K20 - time schedule'!HO25","v":0},{"$f":"'K20 - time schedule'!HP25","v":0},{"$f":"'K20 - time schedule'!HQ25","v":0},{"$f":"'K20 - time schedule'!HR25","v":0},{"$f":"'K20 - time schedule'!HS25","v":0},{"$f":"'K20 - time schedule'!HT25","v":0},{"$f":"'K20 - time schedule'!HU25","v":0},{"$f":"'K20 - time schedule'!HV25","v":0},{"$f":"'K20 - time schedule'!HW25","v":0},{"$f":"'K20 - time schedule'!HX25","v":0},{"$f":"'K20 - time schedule'!HY25","v":0},{"$f":"'K20 - time schedule'!HZ25","v":0},{"$f":"'K20 - time schedule'!IA25","v":0},{"$f":"'K20 - time schedule'!IB25","v":0},{"$f":"'K20 - time schedule'!IC25","v":0},{"$f":"'K20 - time schedule'!ID25","v":0},{"$f":"'K20 - time schedule'!IE25","v":0},{"$f":"'K20 - time schedule'!IF25","v":0},{"$f":"'K20 - time schedule'!IG25","v":0},{"$f":"'K20 - time schedule'!IH25","v":0},{"$f":"'K20 - time schedule'!II25","v":0},{"$f":"'K20 - time schedule'!IJ25","v":0},{"$f":"'K20 - time schedule'!IK25","v":0},{"$f":"'K20 - time schedule'!IL25","v":0},{"$f":"'K20 - time schedule'!IM25","v":0},{"$f":"'K20 - time schedule'!IN25","v":0},{"$f":"'K20 - time schedule'!IO25","v":0},{"$f":"'K20 - time schedule'!IP25","v":0},{"$f":"'K20 - time schedule'!IQ25","v":0},{"$f":"'K20 - time schedule'!IR25","v":0},{"$f":"'K20 - time schedule'!IS25","v":0},{"$f":"'K20 - time schedule'!IT25","v":0},{"$f":"'K20 - time schedule'!IU25","v":0},{"$f":"'K20 - time schedule'!IV25","v":0},{"$f":"'K20 - time schedule'!IW25","v":0},{"$f":"'K20 - time schedule'!IX25","v":0},{"$f":"'K20 - time schedule'!IY25","v":0},{"$f":"'K20 - time schedule'!IZ25","v":0},{"$f":"'K20 - time schedule'!JA25","v":0},{"$f":"'K20 - time schedule'!JB25","v":0},{"$f":"'K20 - time schedule'!JC25","v":0},{"$f":"'K20 - time schedule'!JD25","v":0},{"$f":"'K20 - time schedule'!JE25","v":0},{"$f":"'K20 - time schedule'!JF25","v":0},{"$f":"'K20 - time schedule'!JG25","v":0},{"$f":"'K20 - time schedule'!JH25","v":0},{"$f":"'K20 - time schedule'!JI25","v":0},{"$f":"'K20 - time schedule'!JJ25","v":0},{"$f":"'K20 - time schedule'!JK25","v":0},{"$f":"'K20 - time schedule'!JL25","v":0},{"$f":"'K20 - time schedule'!JM25","v":0},{"$f":"'K20 - time schedule'!JN25","v":0},{"$f":"'K20 - time schedule'!JO25","v":0},{"$f":"'K20 - time schedule'!JP25","v":0},{"$f":"'K20 - time schedule'!JQ25","v":0},{"$f":"'K20 - time schedule'!JR25","v":0},{"$f":"'K20 - time schedule'!JS25","v":0},{"$f":"'K20 - time schedule'!JT25","v":0},{"$f":"'K20 - time schedule'!JU25","v":0},{"$f":"'K20 - time schedule'!JV25","v":0},{"$f":"'K20 - time schedule'!JW25","v":0},{"$f":"'K20 - time schedule'!JX25","v":0},{"$f":"'K20 - time schedule'!JY25","v":0},{"$f":"'K20 - time schedule'!JZ25","v":0},{"$f":"'K20 - time schedule'!KA25","v":0},{"$f":"'K20 - time schedule'!KB25","v":0},{"$f":"'K20 - time schedule'!KC25","v":0},{"$f":"'K20 - time schedule'!KD25","v":0},{"$f":"'K20 - time schedule'!KE25","v":0},{"$f":"'K20 - time schedule'!KF25","v":0},{"$f":"'K20 - time schedule'!KG25","v":0},{"$f":"'K20 - time schedule'!KH25","v":0},{"$f":"'K20 - time schedule'!KI25","v":0},{"$f":"'K20 - time schedule'!KJ25","v":0},{"$f":"'K20 - time schedule'!KK25","v":0},{"$f":"'K20 - time schedule'!KL25","v":0},{"$f":"'K20 - time schedule'!KM25","v":0},{"$f":"'K20 - time schedule'!KN25","v":0},{"$f":"'K20 - time schedule'!KO25","v":0},{"$f":"'K20 - time schedule'!KP25","v":0},{"$f":"'K20 - time schedule'!KQ25","v":0},{"$f":"'K20 - time schedule'!KR25","v":0},{"$f":"'K20 - time schedule'!KS25","v":0},{"$f":"'K20 - time schedule'!KT25","v":0}]
["Boiler room K20 - outdoor pipeline bridge construction (connection of ash management and SNCR)","K20","EUR",{"$f":"'K20 - time schedule'!G43","v":0},{"$f":"'K20 - time schedule'!H43","v":0},{"$f":"'K20 - time schedule'!I43","v":0},{"$f":"'K20 - time schedule'!J43","v":0},{"$f":"'K20 - time schedule'!K43","v":0},{"$f":"'K20 - time schedule'!L43","v":0},{"$f":"'K20 - time schedule'!M43","v":0},{"$f":"'K20 - time schedule'!N43","v":0},{"$f":"'K20 - time schedule'!O43","v":0},{"$f":"'K20 - time schedule'!P43","v":0},{"$f":"'K20 - time schedule'!Q43","v":0},{"$f":"'K20 - time schedule'!R43","v":0},{"$f":"'K20 - time schedule'!S43","v":0},{"$f":"'K20 - time schedule'!T43","v":0},{"$f":"'K20 - time schedule'!U43","v":0},{"$f":"'K20 - time schedule'!V43","v":0},{"$f":"'K20 - time schedule'!W43","v":0},{"$f":"'K20 - time schedule'!X43","v":0},{"$f":"'K20 - time schedule'!Y43","v":0},{"$f":"'K20 - time schedule'!Z43","v":0},{"$f":"'K20 - time schedule'!AA43","v":0},{"$f":"'K20 - time schedule'!AB43","v":0},{"$f":"'K20 - time schedule'!AC43","v":0},{"$f":"'K20 - time schedule'!AD43","v":0},{"$f":"'K20 - time schedule'!AE43","v":0},{"$f":"'K20 - time schedule'!AF43","v":0},{"$f":"'K20 - time schedule'!AG43","v":0},{"$f":"'K20 - time schedule'!AH43","v":0},{"$f":"'K20 - time schedule'!AI43","v":0},{"$f":"'K20 - time schedule'!AJ43","v":0},{"$f":"'K20 - time schedule'!AK43","v":0},{"$f":"'K20 - time schedule'!AL43","v":0},{"$f":"'K20 - time schedule'!AM43","v":0},{"$f":"'K20 - time schedule'!AN43","v":0},{"$f":"'K20 - time schedule'!AO43","v":0},{"$f":"'K20 - time schedule'!AP43","v":0},{"$f":"'K20 - time schedule'!AQ43","v":0},{"$f":"'K20 - time schedule'!AR43","v":0},{"$f":"'K20 - time schedule'!AS43","v":0},{"$f":"'K20 - time schedule'!AT43","v":0},{"$f":"'K20 - time schedule'!AU43","v":0},{"$f":"'K20 - time schedule'!AV43","v":0},{"$f":"'K20 - time schedule'!AW43","v":0},{"$f":"'K20 - time schedule'!AX43","v":0},{"$f":"'K20 - time schedule'!AY43","v":0},{"$f":"'K20 - time schedule'!AZ43","v":0},{"$f":"'K20 - time schedule'!BA43","v":0},{"$f":"'K20 - time schedule'!BB43","v":0},{"$f":"'K20 - time schedule'!BC43","v":0},{"$f":"'K20 - time schedule'!BD43","v":0},{"$f":"'K20 - time schedule'!BE43","v":0},{"$f":"'K20 - time schedule'!BF43","v":0},{"$f":"'K20 - time schedule'!BG43","v":0},{"$f":"'K20 - time schedule'!BH43","v":0},{"$f":"'K20 - time schedule'!BI43","v":0},{"$f":"'K20 - time schedule'!BJ43","v":0},{"$f":"'K20 - time schedule'!BK43","v":0},{"$f":"'K20 - time schedule'!BL43","v":0},{"$f":"'K20 - time schedule'!BM43","v":0},{"$f":"'K20 - time schedule'!BN43","v":0},{"$f":"'K20 - time schedule'!BO43","v":0},{"$f":"'K20 - time schedule'!BP43","v":0},{"$f":"'K20 - time schedule'!BQ43","v":0},{"$f":"'K20 - time schedule'!BR43","v":0},{"$f":"'K20 - time schedule'!BS43","v":0},{"$f":"'K20 - time schedule'!BT43","v":0},{"$f":"'K20 - time schedule'!BU43","v":0},{"$f":"'K20 - time schedule'!BV43","v":0},{"$f":"'K20 - time schedule'!BW43","v":0},{"$f":"'K20 - time schedule'!BX43","v":0},{"$f":"'K20 - time schedule'!BY43","v":0},{"$f":"'K20 - time schedule'!BZ43","v":0},{"$f":"'K20 - time schedule'!CA43","v":0},{"$f":"'K20 - time schedule'!CB43","v":0},{"$f":"'K20 - time schedule'!CC43","v":0},{"$f":"'K20 - time schedule'!CD43","v":0},{"$f":"'K20 - time schedule'!CE43","v":0},{"$f":"'K20 - time schedule'!CF43","v":0},{"$f":"'K20 - time schedule'!CG43","v":0},{"$f":"'K20 - time schedule'!CH43","v":0},{"$f":"'K20 - time schedule'!CI43","v":0},{"$f":"'K20 - time schedule'!CJ43","v":0},{"$f":"'K20 - time schedule'!CK43","v":0},{"$f":"'K20 - time schedule'!CL43","v":0},{"$f":"'K20 - time schedule'!CM43","v":0},{"$f":"'K20 - time schedule'!CN43","v":0},{"$f":"'K20 - time schedule'!CO43","v":0},{"$f":"'K20 - time schedule'!CP43","v":0},{"$f":"'K20 - time schedule'!CQ43","v":0},{"$f":"'K20 - time schedule'!CR43","v":0},{"$f":"'K20 - time schedule'!CS43","v":0},{"$f":"'K20 - time schedule'!CT43","v":0},{"$f":"'K20 - time schedule'!CU43","v":0},{"$f":"'K20 - time schedule'!CV43","v":0},{"$f":"'K20 - time schedule'!CW43","v":0},{"$f":"'K20 - time schedule'!CX43","v":0},{"$f":"'K20 - time schedule'!CY43","v":0},{"$f":"'K20 - time schedule'!CZ43","v":0},{"$f":"'K20 - time schedule'!DA43","v":0},{"$f":"'K20 - time schedule'!DB43","v":0},{"$f":"'K20 - time schedule'!DC43","v":0},{"$f":"'K20 - time schedule'!DD43","v":0},{"$f":"'K20 - time schedule'!DE43","v":0},{"$f":"'K20 - time schedule'!DF43","v":0},{"$f":"'K20 - time schedule'!DG43","v":0},{"$f":"'K20 - time schedule'!DH43","v":0},{"$f":"'K20 - time schedule'!DI43","v":0},{"$f":"'K20 - time schedule'!DJ43","v":0},{"$f":"'K20 - time schedule'!DK43","v":0},{"$f":"'K20 - time schedule'!DL43","v":0},{"$f":"'K20 - time schedule'!DM43","v":0},{"$f":"'K20 - time schedule'!DN43","v":0},{"$f":"'K20 - time schedule'!DO43","v":0},{"$f":"'K20 - time schedule'!DP43","v":0},{"$f":"'K20 - time schedule'!DQ43","v":0},{"$f":"'K20 - time schedule'!DR43","v":0},{"$f":"'K20 - time schedule'!DS43","v":0},{"$f":"'K20 - time schedule'!DT43","v":0},{"$f":"'K20 - time schedule'!DU43","v":0},{"$f":"'K20 - time schedule'!DV43","v":0},{"$f":"'K20 - time schedule'!DW43","v":0},{"$f":"'K20 - time schedule'!DX43","v":0},{"$f":"'K20 - time schedule'!DY43","v":0},{"$f":"'K20 - time schedule'!DZ43","v":0},{"$f":"'K20 - time schedule'!EA43","v":0},{"$f":"'K20 - time schedule'!EB43","v":0},{"$f":"'K20 - time schedule'!EC43","v":0},{"$f":"'K20 - time schedule'!ED43","v":0},{"$f":"'K20 - time schedule'!EE43","v":0},{"$f":"'K20 - time schedule'!EF43","v":0},{"$f":"'K20 - time schedule'!EG43","v":0},{"$f":"'K20 - time schedule'!EH43","v":0},{"$f":"'K20 - time schedule'!EI43","v":0},{"$f":"'K20 - time schedule'!EJ43","v":0},{"$f":"'K20 - time schedule'!EK43","v":0},{"$f":"'K20 - time schedule'!EL43","v":0},{"$f":"'K20 - time schedule'!EM43","v":0},{"$f":"'K20 - time schedule'!EN43","v":0},{"$f":"'K20 - time schedule'!EO43","v":0},{"$f":"'K20 - time schedule'!EP43","v":0},{"$f":"'K20 - time schedule'!EQ43","v":0},{"$f":"'K20 - time schedule'!ER43","v":0},{"$f":"'K20 - time schedule'!ES43","v":0},{"$f":"'K20 - time schedule'!ET43","v":0},{"$f":"'K20 - time schedule'!EU43","v":0},{"$f":"'K20 - time schedule'!EV43","v":0},{"$f":"'K20 - time schedule'!EW43","v":0},{"$f":"'K20 - time schedule'!EX43","v":0},{"$f":"'K20 - time schedule'!EY43","v":0},{"$f":"'K20 - time schedule'!EZ43","v":0},{"$f":"'K20 - time schedule'!FA43","v":0},{"$f":"'K20 - time schedule'!FB43","v":0},{"$f":"'K20 - time schedule'!FC43","v":0},{"$f":"'K20 - time schedule'!FD43","v":0},{"$f":"'K20 - time schedule'!FE43","v":0},{"$f":"'K20 - time schedule'!FF43","v":0},{"$f":"'K20 - time schedule'!FG43","v":0},{"$f":"'K20 - time schedule'!FH43","v":0},{"$f":"'K20 - time schedule'!FI43","v":0},{"$f":"'K20 - time schedule'!FJ43","v":0},{"$f":"'K20 - time schedule'!FK43","v":0},{"$f":"'K20 - time schedule'!FL43","v":0},{"$f":"'K20 - time schedule'!FM43","v":0},{"$f":"'K20 - time schedule'!FN43","v":0},{"$f":"'K20 - time schedule'!FO43","v":0},{"$f":"'K20 - time schedule'!FP43","v":0},{"$f":"'K20 - time schedule'!FQ43","v":0},{"$f":"'K20 - time schedule'!FR43","v":0},{"$f":"'K20 - time schedule'!FS43","v":0},{"$f":"'K20 - time schedule'!FT43","v":0},{"$f":"'K20 - time schedule'!FU43","v":0},{"$f":"'K20 - time schedule'!FV43","v":0},{"$f":"'K20 - time schedule'!FW43","v":0},{"$f":"'K20 - time schedule'!FX43","v":0},{"$f":"'K20 - time schedule'!FY43","v":0},{"$f":"'K20 - time schedule'!FZ43","v":0},{"$f":"'K20 - time schedule'!GA43","v":0},{"$f":"'K20 - time schedule'!GB43","v":0},{"$f":"'K20 - time schedule'!GC43","v":0},{"$f":"'K20 - time schedule'!GD43","v":0},{"$f":"'K20 - time schedule'!GE43","v":0},{"$f":"'K20 - time schedule'!GF43","v":0},{"$f":"'K20 - time schedule'!GG26","v":0},{"$f":"'K20 - time schedule'!GH26","v":0},{"$f":"'K20 - time schedule'!GI26","v":0},{"$f":"'K20 - time schedule'!GJ26","v":0},{"$f":"'K20 - time schedule'!GK26","v":0},{"$f":"'K20 - time schedule'!GL26","v":0},{"$f":"'K20 - time schedule'!GM26","v":0},{"$f":"'K20 - time schedule'!GN26","v":0},{"$f":"'K20 - time schedule'!GO26","v":0},{"$f":"'K20 - time schedule'!GP26","v":0},{"$f":"'K20 - time schedule'!GQ26","v":0},{"$f":"'K20 - time schedule'!GR26","v":0},{"$f":"'K20 - time schedule'!GS26","v":0},{"$f":"'K20 - time schedule'!GT26","v":0},{"$f":"'K20 - time schedule'!GU26","v":0},{"$f":"'K20 - time schedule'!GV26","v":0},{"$f":"'K20 - time schedule'!GW26","v":0},{"$f":"'K20 - time schedule'!GX26","v":0},{"$f":"'K20 - time schedule'!GY26","v":0},{"$f":"'K20 - time schedule'!GZ26","v":0},{"$f":"'K20 - time schedule'!HA26","v":0},{"$f":"'K20 - time schedule'!HB26","v":0},{"$f":"'K20 - time schedule'!HC26","v":0},{"$f":"'K20 - time schedule'!HD26","v":0},{"$f":"'K20 - time schedule'!HE26","v":0},{"$f":"'K20 - time schedule'!HF26","v":0},{"$f":"'K20 - time schedule'!HG26","v":0},{"$f":"'K20 - time schedule'!HH26","v":0},{"$f":"'K20 - time schedule'!HI26","v":0},{"$f":"'K20 - time schedule'!HJ26","v":0},{"$f":"'K20 - time schedule'!HK26","v":0},{"$f":"'K20 - time schedule'!HL26","v":0},{"$f":"'K20 - time schedule'!HM26","v":0},{"$f":"'K20 - time schedule'!HN26","v":0},{"$f":"'K20 - time schedule'!HO26","v":0},{"$f":"'K20 - time schedule'!HP26","v":0},{"$f":"'K20 - time schedule'!HQ26","v":0},{"$f":"'K20 - time schedule'!HR26","v":0},{"$f":"'K20 - time schedule'!HS26","v":0},{"$f":"'K20 - time schedule'!HT26","v":0},{"$f":"'K20 - time schedule'!HU26","v":0},{"$f":"'K20 - time schedule'!HV26","v":0},{"$f":"'K20 - time schedule'!HW26","v":0},{"$f":"'K20 - time schedule'!HX26","v":0},{"$f":"'K20 - time schedule'!HY26","v":0},{"$f":"'K20 - time schedule'!HZ26","v":0},{"$f":"'K20 - time schedule'!IA26","v":0},{"$f":"'K20 - time schedule'!IB26","v":0},{"$f":"'K20 - time schedule'!IC26","v":0},{"$f":"'K20 - time schedule'!ID26","v":0},{"$f":"'K20 - time schedule'!IE26","v":0},{"$f":"'K20 - time schedule'!IF26","v":0},{"$f":"'K20 - time schedule'!IG26","v":0},{"$f":"'K20 - time schedule'!IH26","v":0},{"$f":"'K20 - time schedule'!II26","v":0},{"$f":"'K20 - time schedule'!IJ26","v":0},{"$f":"'K20 - time schedule'!IK26","v":0},{"$f":"'K20 - time schedule'!IL26","v":0},{"$f":"'K20 - time schedule'!IM26","v":0},{"$f":"'K20 - time schedule'!IN26","v":0},{"$f":"'K20 - time schedule'!IO26","v":0},{"$f":"'K20 - time schedule'!IP26","v":0},{"$f":"'K20 - time schedule'!IQ26","v":0},{"$f":"'K20 - time schedule'!IR26","v":0},{"$f":"'K20 - time schedule'!IS26","v":0},{"$f":"'K20 - time schedule'!IT26","v":0},{"$f":"'K20 - time schedule'!IU26","v":0},{"$f":"'K20 - time schedule'!IV26","v":0},{"$f":"'K20 - time schedule'!IW26","v":0},{"$f":"'K20 - time schedule'!IX26","v":0},{"$f":"'K20 - time schedule'!IY26","v":0},{"$f":"'K20 - time schedule'!IZ26","v":0},{"$f":"'K20 - time schedule'!JA26","v":0},{"$f":"'K20 - time schedule'!JB26","v":0},{"$f":"'K20 - time schedule'!JC26","v":0},{"$f":"'K20 - time schedule'!JD26","v":0},{"$f":"'K20 - time schedule'!JE26","v":0},{"$f":"'K20 - time schedule'!JF26","v":0},{"$f":"'K20 - time schedule'!JG26","v":0},{"$f":"'K20 - time schedule'!JH26","v":0},{"$f":"'K20 - time schedule'!JI26","v":0},{"$f":"'K20 - time schedule'!JJ26","v":0},{"$f":"'K20 - time schedule'!JK26","v":0},{"$f":"'K20 - time schedule'!JL26","v":0},{"$f":"'K20 - time schedule'!JM26","v":0},{"$f":"'K20 - time schedule'!JN26","v":0},{"$f":"'K20 - time schedule'!JO26","v":0},{"$f":"'K20 - time schedule'!JP26","v":0},{"$f":"'K20 - time schedule'!JQ26","v":0},{"$f":"'K20 - time schedule'!JR26","v":0},{"$f":"'K20 - time schedule'!JS26","v":0},{"$f":"'K20 - time schedule'!JT26","v":0},{"$f":"'K20 - time schedule'!JU26","v":0},{"$f":"'K20 - time schedule'!JV26","v":0},{"$f":"'K20 - time schedule'!JW26","v":0},{"$f":"'K20 - time schedule'!JX26","v":0},{"$f":"'K20 - time schedule'!JY26","v":0},{"$f":"'K20 - time schedule'!JZ26","v":0},{"$f":"'K20 - time schedule'!KA26","v":0},{"$f":"'K20 - time schedule'!KB26","v":0},{"$f":"'K20 - time schedule'!KC26","v":0},{"$f":"'K20 - time schedule'!KD26","v":0},{"$f":"'K20 - time schedule'!KE26","v":0},{"$f":"'K20 - time schedule'!KF26","v":0},{"$f":"'K20 - time schedule'!KG26","v":0},{"$f":"'K20 - time schedule'!KH26","v":0},{"$f":"'K20 - time schedule'!KI26","v":0},{"$f":"'K20 - time schedule'!KJ26","v":0},{"$f":"'K20 - time schedule'!KK26","v":0},{"$f":"'K20 - time schedule'!KL26","v":0},{"$f":"'K20 - time schedule'!KM26","v":0},{"$f":"'K20 - time schedule'!KN26","v":0},{"$f":"'K20 - time schedule'!KO26","v":0},{"$f":"'K20 - time schedule'!KP26","v":0},{"$f":"'K20 - time schedule'!KQ26","v":0},{"$f":"'K20 - time schedule'!KR26","v":0},{"$f":"'K20 - time schedule'!KS26","v":0},{"$f":"'K20 - time schedule'!KT26","v":0}]
["Boiler room K20 - cladding and roofing, completion of all construction activities","K20","EUR",{"$f":"'K20 - time schedule'!G45","v":0},{"$f":"'K20 - time schedule'!H45","v":0},{"$f":"'K20 - time schedule'!I45","v":0},{"$f":"'K20 - time schedule'!J45","v":0},{"$f":"'K20 - time schedule'!K45","v":0},{"$f":"'K20 - time schedule'!L45","v":0},{"$f":"'K20 - time schedule'!M45","v":0},{"$f":"'K20 - time schedule'!N45","v":0},{"$f":"'K20 - time schedule'!O45","v":0},{"$f":"'K20 - time schedule'!P45","v":0},{"$f":"'K20 - time schedule'!Q45","v":0},{"$f":"'K20 - time schedule'!R45","v":0},{"$f":"'K20 - time schedule'!S45","v":0},{"$f":"'K20 - time schedule'!T45","v":0},{"$f":"'K20 - time schedule'!U45","v":0},{"$f":"'K20 - time schedule'!V45","v":0},{"$f":"'K20 - time schedule'!W45","v":0},{"$f":"'K20 - time schedule'!X45","v":0},{"$f":"'K20 - time schedule'!Y45","v":0},{"$f":"'K20 - time schedule'!Z45","v":0},{"$f":"'K20 - time schedule'!AA45","v":0},{"$f":"'K20 - time schedule'!AB45","v":0},{"$f":"'K20 - time schedule'!AC45","v":0},{"$f":"'K20 - time schedule'!AD45","v":0},{"$f":"'K20 - time schedule'!AE45","v":0},{"$f":"'K20 - time schedule'!AF45","v":0},{"$f":"'K20 - time schedule'!AG45","v":0},{"$f":"'K20 - time schedule'!AH45","v":0},{"$f":"'K20 - time schedule'!AI45","v":0},{"$f":"'K20 - time schedule'!AJ45","v":0},{"$f":"'K20 - time schedule'!AK45","v":0},{"$f":"'K20 - time schedule'!AL45","v":0},{"$f":"'K20 - time schedule'!AM45","v":0},{"$f":"'K20 - time schedule'!AN45","v":0},{"$f":"'K20 - time schedule'!AO45","v":0},{"$f":"'K20 - time schedule'!AP45","v":0},{"$f":"'K20 - time schedule'!AQ45","v":0},{"$f":"'K20 - time schedule'!AR45","v":0},{"$f":"'K20 - time schedule'!AS45","v":0},{"$f":"'K20 - time schedule'!AT45","v":0},{"$f":"'K20 - time schedule'!AU45","v":0},{"$f":"'K20 - time schedule'!AV45","v":0},{"$f":"'K20 - time schedule'!AW45","v":0},{"$f":"'K20 - time schedule'!AX45","v":0},{"$f":"'K20 - time schedule'!AY45","v":0},{"$f":"'K20 - time schedule'!AZ45","v":0},{"$f":"'K20 - time schedule'!BA45","v":0},{"$f":"'K20 - time schedule'!BB45","v":0},{"$f":"'K20 - time schedule'!BC45","v":0},{"$f":"'K20 - time schedule'!BD45","v":0},{"$f":"'K20 - time schedule'!BE45","v":0},{"$f":"'K20 - time schedule'!BF45","v":0},{"$f":"'K20 - time schedule'!BG45","v":0},{"$f":"'K20 - time schedule'!BH45","v":0},{"$f":"'K20 - time schedule'!BI45","v":0},{"$f":"'K20 - time schedule'!BJ45","v":0},{"$f":"'K20 - time schedule'!BK45","v":0},{"$f":"'K20 - time schedule'!BL45","v":0},{"$f":"'K20 - time schedule'!BM45","v":0},{"$f":"'K20 - time schedule'!BN45","v":0},{"$f":"'K20 - time schedule'!BO45","v":0},{"$f":"'K20 - time schedule'!BP45","v":0},{"$f":"'K20 - time schedule'!BQ45","v":0},{"$f":"'K20 - time schedule'!BR45","v":0},{"$f":"'K20 - time schedule'!BS45","v":0},{"$f":"'K20 - time schedule'!BT45","v":0},{"$f":"'K20 - time schedule'!BU45","v":0},{"$f":"'K20 - time schedule'!BV45","v":0},{"$f":"'K20 - time schedule'!BW45","v":0},{"$f":"'K20 - time schedule'!BX45","v":0},{"$f":"'K20 - time schedule'!BY45","v":0},{"$f":"'K20 - time schedule'!BZ45","v":0},{"$f":"'K20 - time schedule'!CA45","v":0},{"$f":"'K20 - time schedule'!CB45","v":0},{"$f":"'K20 - time schedule'!CC45","v":0},{"$f":"'K20 - time schedule'!CD45","v":0},{"$f":"'K20 - time schedule'!CE45","v":0},{"$f":"'K20 - time schedule'!CF45","v":0},{"$f":"'K20 - time schedule'!CG45","v":0},{"$f":"'K20 - time schedule'!CH45","v":0},{"$f":"'K20 - time schedule'!CI45","v":0},{"$f":"'K20 - time schedule'!CJ45","v":0},{"$f":"'K20 - time schedule'!CK45","v":0},{"$f":"'K20 - time schedule'!CL45","v":0},{"$f":"'K20 - time schedule'!CM45","v":0},{"$f":"'K20 - time schedule'!CN45","v":0},{"$f":"'K20 - time schedule'!CO45","v":0},{"$f":"'K20 - time schedule'!CP45","v":0},{"$f":"'K20 - time schedule'!CQ45","v":0},{"$f":"'K20 - time schedule'!CR45","v":0},{"$f":"'K20 - time schedule'!CS45","v":0},{"$f":"'K20 - time schedule'!CT45","v":0},{"$f":"'K20 - time schedule'!CU45","v":0},{"$f":"'K20 - time schedule'!CV45","v":0},{"$f":"'K20 - time schedule'!CW45","v":0},{"$f":"'K20 - time schedule'!CX45","v":0},{"$f":"'K20 - time schedule'!CY45","v":0},{"$f":"'K20 - time schedule'!CZ45","v":0},{"$f":"'K20 - time schedule'!DA45","v":0},{"$f":"'K20 - time schedule'!DB45","v":0},{"$f":"'K20 - time schedule'!DC45","v":0},{"$f":"'K20 - time schedule'!DD45","v":0},{"$f":"'K20 - time schedule'!DE45","v":0},{"$f":"'K20 - time schedule'!DF45","v":0},{"$f":"'K20 - time schedule'!DG45","v":0},{"$f":"'K20 - time schedule'!DH45","v":0},{"$f":"'K20 - time schedule'!DI45","v":0},{"$f":"'K20 - time schedule'!DJ45","v":0},{"$f":"'K20 - time schedule'!DK45","v":0},{"$f":"'K20 - time schedule'!DL45","v":0},{"$f":"'K20 - time schedule'!DM45","v":0},{"$f":"'K20 - time schedule'!DN45","v":0},{"$f":"'K20 - time schedule'!DO45","v":0},{"$f":"'K20 - time schedule'!DP45","v":0},{"$f":"'K20 - time schedule'!DQ45","v":0},{"$f":"'K20 - time schedule'!DR45","v":0},{"$f":"'K20 - time schedule'!DS45","v":0},{"$f":"'K20 - time schedule'!DT45","v":0},{"$f":"'K20 - time schedule'!DU45","v":0},{"$f":"'K20 - time schedule'!DV45","v":0},{"$f":"'K20 - time schedule'!DW45","v":0},{"$f":"'K20 - time schedule'!DX45","v":0},{"$f":"'K20 - time schedule'!DY45","v":0},{"$f":"'K20 - time schedule'!DZ45","v":0},{"$f":"'K20 - time schedule'!EA45","v":0},{"$f":"'K20 - time schedule'!EB45","v":0},{"$f":"'K20 - time schedule'!EC45","v":0},{"$f":"'K20 - time schedule'!ED45","v":0},{"$f":"'K20 - time schedule'!EE45","v":0},{"$f":"'K20 - time schedule'!EF45","v":0},{"$f":"'K20 - time schedule'!EG45","v":0},{"$f":"'K20 - time schedule'!EH45","v":0},{"$f":"'K20 - time schedule'!EI45","v":0},{"$f":"'K20 - time schedule'!EJ45","v":0},{"$f":"'K20 - time schedule'!EK45","v":0},{"$f":"'K20 - time schedule'!EL45","v":0},{"$f":"'K20 - time schedule'!EM45","v":0},{"$f":"'K20 - time schedule'!EN45","v":0},{"$f":"'K20 - time schedule'!EO45","v":0},{"$f":"'K20 - time schedule'!EP45","v":0},{"$f":"'K20 - time schedule'!EQ45","v":0},{"$f":"'K20 - time schedule'!ER45","v":0},{"$f":"'K20 - time schedule'!ES45","v":0},{"$f":"'K20 - time schedule'!ET45","v":0},{"$f":"'K20 - time schedule'!EU45","v":0},{"$f":"'K20 - time schedule'!EV45","v":0},{"$f":"'K20 - time schedule'!EW45","v":0},{"$f":"'K20 - time schedule'!EX45","v":0},{"$f":"'K20 - time schedule'!EY45","v":0},{"$f":"'K20 - time schedule'!EZ45","v":0},{"$f":"'K20 - time schedule'!FA45","v":0},{"$f":"'K20 - time schedule'!FB45","v":0},{"$f":"'K20 - time schedule'!FC45","v":0},{"$f":"'K20 - time schedule'!FD45","v":0},{"$f":"'K20 - time schedule'!FE45","v":0},{"$f":"'K20 - time schedule'!FF45","v":0},{"$f":"'K20 - time schedule'!FG45","v":0},{"$f":"'K20 - time schedule'!FH45","v":0},{"$f":"'K20 - time schedule'!FI45","v":0},{"$f":"'K20 - time schedule'!FJ45","v":0},{"$f":"'K20 - time schedule'!FK45","v":0},{"$f":"'K20 - time schedule'!FL45","v":0},{"$f":"'K20 - time schedule'!FM45","v":0},{"$f":"'K20 - time schedule'!FN45","v":0},{"$f":"'K20 - time schedule'!FO45","v":0},{"$f":"'K20 - time schedule'!FP45","v":0},{"$f":"'K20 - time schedule'!FQ45","v":0},{"$f":"'K20 - time schedule'!FR45","v":0},{"$f":"'K20 - time schedule'!FS45","v":0},{"$f":"'K20 - time schedule'!FT45","v":0},{"$f":"'K20 - time schedule'!FU45","v":0},{"$f":"'K20 - time schedule'!FV45","v":0},{"$f":"'K20 - time schedule'!FW45","v":0},{"$f":"'K20 - time schedule'!FX45","v":0},{"$f":"'K20 - time schedule'!FY45","v":0},{"$f":"'K20 - time schedule'!FZ45","v":0},{"$f":"'K20 - time schedule'!GA45","v":0},{"$f":"'K20 - time schedule'!GB45","v":0},{"$f":"'K20 - time schedule'!GC45","v":0},{"$f":"'K20 - time schedule'!GD45","v":0},{"$f":"'K20 - time schedule'!GE45","v":0},{"$f":"'K20 - time schedule'!GF45","v":0},{"$f":"'K20 - time schedule'!GG27","v":0},{"$f":"'K20 - time schedule'!GH27","v":0},{"$f":"'K20 - time schedule'!GI27","v":0},{"$f":"'K20 - time schedule'!GJ27","v":0},{"$f":"'K20 - time schedule'!GK27","v":0},{"$f":"'K20 - time schedule'!GL27","v":0},{"$f":"'K20 - time schedule'!GM27","v":0},{"$f":"'K20 - time schedule'!GN27","v":0},{"$f":"'K20 - time schedule'!GO27","v":0},{"$f":"'K20 - time schedule'!GP27","v":0},{"$f":"'K20 - time schedule'!GQ27","v":0},{"$f":"'K20 - time schedule'!GR27","v":0},{"$f":"'K20 - time schedule'!GS27","v":0},{"$f":"'K20 - time schedule'!GT27","v":0},{"$f":"'K20 - time schedule'!GU27","v":0},{"$f":"'K20 - time schedule'!GV27","v":0},{"$f":"'K20 - time schedule'!GW27","v":0},{"$f":"'K20 - time schedule'!GX27","v":0},{"$f":"'K20 - time schedule'!GY27","v":0},{"$f":"'K20 - time schedule'!GZ27","v":0},{"$f":"'K20 - time schedule'!HA27","v":0},{"$f":"'K20 - time schedule'!HB27","v":0},{"$f":"'K20 - time schedule'!HC27","v":0},{"$f":"'K20 - time schedule'!HD27","v":0},{"$f":"'K20 - time schedule'!HE27","v":0},{"$f":"'K20 - time schedule'!HF27","v":0},{"$f":"'K20 - time schedule'!HG27","v":0},{"$f":"'K20 - time schedule'!HH27","v":0},{"$f":"'K20 - time schedule'!HI27","v":0},{"$f":"'K20 - time schedule'!HJ27","v":0},{"$f":"'K20 - time schedule'!HK27","v":0},{"$f":"'K20 - time schedule'!HL27","v":0},{"$f":"'K20 - time schedule'!HM27","v":0},{"$f":"'K20 - time schedule'!HN27","v":0},{"$f":"'K20 - time schedule'!HO27","v":0},{"$f":"'K20 - time schedule'!HP27","v":0},{"$f":"'K20 - time schedule'!HQ27","v":0},{"$f":"'K20 - time schedule'!HR27","v":0},{"$f":"'K20 - time schedule'!HS27","v":0},{"$f":"'K20 - time schedule'!HT27","v":0},{"$f":"'K20 - time schedule'!HU27","v":0},{"$f":"'K20 - time schedule'!HV27","v":0},{"$f":"'K20 - time schedule'!HW27","v":0},{"$f":"'K20 - time schedule'!HX27","v":0},{"$f":"'K20 - time schedule'!HY27","v":0},{"$f":"'K20 - time schedule'!HZ27","v":0},{"$f":"'K20 - time schedule'!IA27","v":0},{"$f":"'K20 - time schedule'!IB27","v":0},{"$f":"'K20 - time schedule'!IC27","v":0},{"$f":"'K20 - time schedule'!ID27","v":0},{"$f":"'K20 - time schedule'!IE27","v":0},{"$f":"'K20 - time schedule'!IF27","v":0},{"$f":"'K20 - time schedule'!IG27","v":0},{"$f":"'K20 - time schedule'!IH27","v":0},{"$f":"'K20 - time schedule'!II27","v":0},{"$f":"'K20 - time schedule'!IJ27","v":0},{"$f":"'K20 - time schedule'!IK27","v":0},{"$f":"'K20 - time schedule'!IL27","v":0},{"$f":"'K20 - time schedule'!IM27","v":0},{"$f":"'K20 - time schedule'!IN27","v":0},{"$f":"'K20 - time schedule'!IO27","v":0},{"$f":"'K20 - time schedule'!IP27","v":0},{"$f":"'K20 - time schedule'!IQ27","v":0},{"$f":"'K20 - time schedule'!IR27","v":0},{"$f":"'K20 - time schedule'!IS27","v":0},{"$f":"'K20 - time schedule'!IT27","v":0},{"$f":"'K20 - time schedule'!IU27","v":0},{"$f":"'K20 - time schedule'!IV27","v":0},{"$f":"'K20 - time schedule'!IW27","v":0},{"$f":"'K20 - time schedule'!IX27","v":0},{"$f":"'K20 - time schedule'!IY27","v":0},{"$f":"'K20 - time schedule'!IZ27","v":0},{"$f":"'K20 - time schedule'!JA27","v":0},{"$f":"'K20 - time schedule'!JB27","v":0},{"$f":"'K20 - time schedule'!JC27","v":0},{"$f":"'K20 - time schedule'!JD27","v":0},{"$f":"'K20 - time schedule'!JE27","v":0},{"$f":"'K20 - time schedule'!JF27","v":0},{"$f":"'K20 - time schedule'!JG27","v":0},{"$f":"'K20 - time schedule'!JH27","v":0},{"$f":"'K20 - time schedule'!JI27","v":0},{"$f":"'K20 - time schedule'!JJ27","v":0},{"$f":"'K20 - time schedule'!JK27","v":0},{"$f":"'K20 - time schedule'!JL27","v":0},{"$f":"'K20 - time schedule'!JM27","v":0},{"$f":"'K20 - time schedule'!JN27","v":0},{"$f":"'K20 - time schedule'!JO27","v":0},{"$f":"'K20 - time schedule'!JP27","v":0},{"$f":"'K20 - time schedule'!JQ27","v":0},{"$f":"'K20 - time schedule'!JR27","v":0},{"$f":"'K20 - time schedule'!JS27","v":0},{"$f":"'K20 - time schedule'!JT27","v":0},{"$f":"'K20 - time schedule'!JU27","v":0},{"$f":"'K20 - time schedule'!JV27","v":0},{"$f":"'K20 - time schedule'!JW27","v":0},{"$f":"'K20 - time schedule'!JX27","v":0},{"$f":"'K20 - time schedule'!JY27","v":0},{"$f":"'K20 - time schedule'!JZ27","v":0},{"$f":"'K20 - time schedule'!KA27","v":0},{"$f":"'K20 - time schedule'!KB27","v":0},{"$f":"'K20 - time schedule'!KC27","v":0},{"$f":"'K20 - time schedule'!KD27","v":0},{"$f":"'K20 - time schedule'!KE27","v":0},{"$f":"'K20 - time schedule'!KF27","v":0},{"$f":"'K20 - time schedule'!KG27","v":0},{"$f":"'K20 - time schedule'!KH27","v":0},{"$f":"'K20 - time schedule'!KI27","v":0},{"$f":"'K20 - time schedule'!KJ27","v":0},{"$f":"'K20 - time schedule'!KK27","v":0},{"$f":"'K20 - time schedule'!KL27","v":0},{"$f":"'K20 - time schedule'!KM27","v":0},{"$f":"'K20 - time schedule'!KN27","v":0},{"$f":"'K20 - time schedule'!KO27","v":0},{"$f":"'K20 - time schedule'!KP27","v":0},{"$f":"'K20 - time schedule'!KQ27","v":0},{"$f":"'K20 - time schedule'!KR27","v":0},{"$f":"'K20 - time schedule'!KS27","v":0},{"$f":"'K20 - time schedule'!KT27","v":0}]
["Boiler room K20 - other above not specified items","K20","EUR",{"$f":"'K20 - time schedule'!G47","v":0},{"$f":"'K20 - time schedule'!H47","v":0},{"$f":"'K20 - time schedule'!I47","v":0},{"$f":"'K20 - time schedule'!J47","v":0},{"$f":"'K20 - time schedule'!K47","v":0},{"$f":"'K20 - time schedule'!L47","v":0},{"$f":"'K20 - time schedule'!M47","v":0},{"$f":"'K20 - time schedule'!N47","v":0},{"$f":"'K20 - time schedule'!O47","v":0},{"$f":"'K20 - time schedule'!P47","v":0},{"$f":"'K20 - time schedule'!Q47","v":0},{"$f":"'K20 - time schedule'!R47","v":0},{"$f":"'K20 - time schedule'!S47","v":0},{"$f":"'K20 - time schedule'!T47","v":0},{"$f":"'K20 - time schedule'!U47","v":0},{"$f":"'K20 - time schedule'!V47","v":0},{"$f":"'K20 - time schedule'!W47","v":0},{"$f":"'K20 - time schedule'!X47","v":0},{"$f":"'K20 - time schedule'!Y47","v":0},{"$f":"'K20 - time schedule'!Z47","v":0},{"$f":"'K20 - time schedule'!AA47","v":0},{"$f":"'K20 - time schedule'!AB47","v":0},{"$f":"'K20 - time schedule'!AC47","v":0},{"$f":"'K20 - time schedule'!AD47","v":0},{"$f":"'K20 - time schedule'!AE47","v":0},{"$f":"'K20 - time schedule'!AF47","v":0},{"$f":"'K20 - time schedule'!AG47","v":0},{"$f":"'K20 - time schedule'!AH47","v":0},{"$f":"'K20 - time schedule'!AI47","v":0},{"$f":"'K20 - time schedule'!AJ47","v":0},{"$f":"'K20 - time schedule'!AK47","v":0},{"$f":"'K20 - time schedule'!AL47","v":0},{"$f":"'K20 - time schedule'!AM47","v":0},{"$f":"'K20 - time schedule'!AN47","v":0},{"$f":"'K20 - time schedule'!AO47","v":0},{"$f":"'K20 - time schedule'!AP47","v":0},{"$f":"'K20 - time schedule'!AQ47","v":0},{"$f":"'K20 - time schedule'!AR47","v":0},{"$f":"'K20 - time schedule'!AS47","v":0},{"$f":"'K20 - time schedule'!AT47","v":0},{"$f":"'K20 - time schedule'!AU47","v":0},{"$f":"'K20 - time schedule'!AV47","v":0},{"$f":"'K20 - time schedule'!AW47","v":0},{"$f":"'K20 - time schedule'!AX47","v":0},{"$f":"'K20 - time schedule'!AY47","v":0},{"$f":"'K20 - time schedule'!AZ47","v":0},{"$f":"'K20 - time schedule'!BA47","v":0},{"$f":"'K20 - time schedule'!BB47","v":0},{"$f":"'K20 - time schedule'!BC47","v":0},{"$f":"'K20 - time schedule'!BD47","v":0},{"$f":"'K20 - time schedule'!BE47","v":0},{"$f":"'K20 - time schedule'!BF47","v":0},{"$f":"'K20 - time schedule'!BG47","v":0},{"$f":"'K20 - time schedule'!BH47","v":0},{"$f":"'K20 - time schedule'!BI47","v":0},{"$f":"'K20 - time schedule'!BJ47","v":0},{"$f":"'K20 - time schedule'!BK47","v":0},{"$f":"'K20 - time schedule'!BL47","v":0},{"$f":"'K20 - time schedule'!BM47","v":0},{"$f":"'K20 - time schedule'!BN47","v":0},{"$f":"'K20 - time schedule'!BO47","v":0},{"$f":"'K20 - time schedule'!BP47","v":0},{"$f":"'K20 - time schedule'!BQ47","v":0},{"$f":"'K20 - time schedule'!BR47","v":0},{"$f":"'K20 - time schedule'!BS47","v":0},{"$f":"'K20 - time schedule'!BT47","v":0},{"$f":"'K20 - time schedule'!BU47","v":0},{"$f":"'K20 - time schedule'!BV47","v":0},{"$f":"'K20 - time schedule'!BW47","v":0},{"$f":"'K20 - time schedule'!BX47","v":0},{"$f":"'K20 - time schedule'!BY47","v":0},{"$f":"'K20 - time schedule'!BZ47","v":0},{"$f":"'K20 - time schedule'!CA47","v":0},{"$f":"'K20 - time schedule'!CB47","v":0},{"$f":"'K20 - time schedule'!CC47","v":0},{"$f":"'K20 - time schedule'!CD47","v":0},{"$f":"'K20 - time schedule'!CE47","v":0},{"$f":"'K20 - time schedule'!CF47","v":0},{"$f":"'K20 - time schedule'!CG47","v":0},{"$f":"'K20 - time schedule'!CH47","v":0},{"$f":"'K20 - time schedule'!CI47","v":0},{"$f":"'K20 - time schedule'!CJ47","v":0},{"$f":"'K20 - time schedule'!CK47","v":0},{"$f":"'K20 - time schedule'!CL47","v":0},{"$f":"'K20 - time schedule'!CM47","v":0},{"$f":"'K20 - time schedule'!CN47","v":0},{"$f":"'K20 - time schedule'!CO47","v":0},{"$f":"'K20 - time schedule'!CP47","v":0},{"$f":"'K20 - time schedule'!CQ47","v":0},{"$f":"'K20 - time schedule'!CR47","v":0},{"$f":"'K20 - time schedule'!CS47","v":0},{"$f":"'K20 - time schedule'!CT47","v":0},{"$f":"'K20 - time schedule'!CU47","v":0},{"$f":"'K20 - time schedule'!CV47","v":0},{"$f":"'K20 - time schedule'!CW47","v":0},{"$f":"'K20 - time schedule'!CX47","v":0},{"$f":"'K20 - time schedule'!CY47","v":0},{"$f":"'K20 - time schedule'!CZ47","v":0},{"$f":"'K20 - time schedule'!DA47","v":0},{"$f":"'K20 - time schedule'!DB47","v":0},{"$f":"'K20 - time schedule'!DC47","v":0},{"$f":"'K20 - time schedule'!DD47","v":0},{"$f":"'K20 - time schedule'!DE47","v":0},{"$f":"'K20 - time schedule'!DF47","v":0},{"$f":"'K20 - time schedule'!DG47","v":0},{"$f":"'K20 - time schedule'!DH47","v":0},{"$f":"'K20 - time schedule'!DI47","v":0},{"$f":"'K20 - time schedule'!DJ47","v":0},{"$f":"'K20 - time schedule'!DK47","v":0},{"$f":"'K20 - time schedule'!DL47","v":0},{"$f":"'K20 - time schedule'!DM47","v":0},{"$f":"'K20 - time schedule'!DN47","v":0},{"$f":"'K20 - time schedule'!DO47","v":0},{"$f":"'K20 - time schedule'!DP47","v":0},{"$f":"'K20 - time schedule'!DQ47","v":0},{"$f":"'K20 - time schedule'!DR47","v":0},{"$f":"'K20 - time schedule'!DS47","v":0},{"$f":"'K20 - time schedule'!DT47","v":0},{"$f":"'K20 - time schedule'!DU47","v":0},{"$f":"'K20 - time schedule'!DV47","v":0},{"$f":"'K20 - time schedule'!DW47","v":0},{"$f":"'K20 - time schedule'!DX47","v":0},{"$f":"'K20 - time schedule'!DY47","v":0},{"$f":"'K20 - time schedule'!DZ47","v":0},{"$f":"'K20 - time schedule'!EA47","v":0},{"$f":"'K20 - time schedule'!EB47","v":0},{"$f":"'K20 - time schedule'!EC47","v":0},{"$f":"'K20 - time schedule'!ED47","v":0},{"$f":"'K20 - time schedule'!EE47","v":0},{"$f":"'K20 - time schedule'!EF47","v":0},{"$f":"'K20 - time schedule'!EG47","v":0},{"$f":"'K20 - time schedule'!EH47","v":0},{"$f":"'K20 - time schedule'!EI47","v":0},{"$f":"'K20 - time schedule'!EJ47","v":0},{"$f":"'K20 - time schedule'!EK47","v":0},{"$f":"'K20 - time schedule'!EL47","v":0},{"$f":"'K20 - time schedule'!EM47","v":0},{"$f":"'K20 - time schedule'!EN47","v":0},{"$f":"'K20 - time schedule'!EO47","v":0},{"$f":"'K20 - time schedule'!EP47","v":0},{"$f":"'K20 - time schedule'!EQ47","v":0},{"$f":"'K20 - time schedule'!ER47","v":0},{"$f":"'K20 - time schedule'!ES47","v":0},{"$f":"'K20 - time schedule'!ET47","v":0},{"$f":"'K20 - time schedule'!EU47","v":0},{"$f":"'K20 - time schedule'!EV47","v":0},{"$f":"'K20 - time schedule'!EW47","v":0},{"$f":"'K20 - time schedule'!EX47","v":0},{"$f":"'K20 - time schedule'!EY47","v":0},{"$f":"'K20 - time schedule'!EZ47","v":0},{"$f":"'K20 - time schedule'!FA47","v":0},{"$f":"'K20 - time schedule'!FB47","v":0},{"$f":"'K20 - time schedule'!FC47","v":0},{"$f":"'K20 - time schedule'!FD47","v":0},{"$f":"'K20 - time schedule'!FE47","v":0},{"$f":"'K20 - time schedule'!FF47","v":0},{"$f":"'K20 - time schedule'!FG47","v":0},{"$f":"'K20 - time schedule'!FH47","v":0},{"$f":"'K20 - time schedule'!FI47","v":0},{"$f":"'K20 - time schedule'!FJ47","v":0},{"$f":"'K20 - time schedule'!FK47","v":0},{"$f":"'K20 - time schedule'!FL47","v":0},{"$f":"'K20 - time schedule'!FM47","v":0},{"$f":"'K20 - time schedule'!FN47","v":0},{"$f":"'K20 - time schedule'!FO47","v":0},{"$f":"'K20 - time schedule'!FP47","v":0},{"$f":"'K20 - time schedule'!FQ47","v":0},{"$f":"'K20 - time schedule'!FR47","v":0},{"$f":"'K20 - time schedule'!FS47","v":0},{"$f":"'K20 - time schedule'!FT47","v":0},{"$f":"'K20 - time schedule'!FU47","v":0},{"$f":"'K20 - time schedule'!FV47","v":0},{"$f":"'K20 - time schedule'!FW47","v":0},{"$f":"'K20 - time schedule'!FX47","v":0},{"$f":"'K20 - time schedule'!FY47","v":0},{"$f":"'K20 - time schedule'!FZ47","v":0},{"$f":"'K20 - time schedule'!GA47","v":0},{"$f":"'K20 - time schedule'!GB47","v":0},{"$f":"'K20 - time schedule'!GC47","v":0},{"$f":"'K20 - time schedule'!GD47","v":0},{"$f":"'K20 - time schedule'!GE47","v":0},{"$f":"'K20 - time schedule'!GF47","v":0},{"$f":"'K20 - time schedule'!GG28","v":0},{"$f":"'K20 - time schedule'!GH28","v":0},{"$f":"'K20 - time schedule'!GI28","v":0},{"$f":"'K20 - time schedule'!GJ28","v":0},{"$f":"'K20 - time schedule'!GK28","v":0},{"$f":"'K20 - time schedule'!GL28","v":0},{"$f":"'K20 - time schedule'!GM28","v":0},{"$f":"'K20 - time schedule'!GN28","v":0},{"$f":"'K20 - time schedule'!GO28","v":0},{"$f":"'K20 - time schedule'!GP28","v":0},{"$f":"'K20 - time schedule'!GQ28","v":0},{"$f":"'K20 - time schedule'!GR28","v":0},{"$f":"'K20 - time schedule'!GS28","v":0},{"$f":"'K20 - time schedule'!GT28","v":0},{"$f":"'K20 - time schedule'!GU28","v":0},{"$f":"'K20 - time schedule'!GV28","v":0},{"$f":"'K20 - time schedule'!GW28","v":0},{"$f":"'K20 - time schedule'!GX28","v":0},{"$f":"'K20 - time schedule'!GY28","v":0},{"$f":"'K20 - time schedule'!GZ28","v":0},{"$f":"'K20 - time schedule'!HA28","v":0},{"$f":"'K20 - time schedule'!HB28","v":0},{"$f":"'K20 - time schedule'!HC28","v":0},{"$f":"'K20 - time schedule'!HD28","v":0},{"$f":"'K20 - time schedule'!HE28","v":0},{"$f":"'K20 - time schedule'!HF28","v":0},{"$f":"'K20 - time schedule'!HG28","v":0},{"$f":"'K20 - time schedule'!HH28","v":0},{"$f":"'K20 - time schedule'!HI28","v":0},{"$f":"'K20 - time schedule'!HJ28","v":0},{"$f":"'K20 - time schedule'!HK28","v":0},{"$f":"'K20 - time schedule'!HL28","v":0},{"$f":"'K20 - time schedule'!HM28","v":0},{"$f":"'K20 - time schedule'!HN28","v":0},{"$f":"'K20 - time schedule'!HO28","v":0},{"$f":"'K20 - time schedule'!HP28","v":0},{"$f":"'K20 - time schedule'!HQ28","v":0},{"$f":"'K20 - time schedule'!HR28","v":0},{"$f":"'K20 - time schedule'!HS28","v":0},{"$f":"'K20 - time schedule'!HT28","v":0},{"$f":"'K20 - time schedule'!HU28","v":0},{"$f":"'K20 - time schedule'!HV28","v":0},{"$f":"'K20 - time schedule'!HW28","v":0},{"$f":"'K20 - time schedule'!HX28","v":0},{"$f":"'K20 - time schedule'!HY28","v":0},{"$f":"'K20 - time schedule'!HZ28","v":0},{"$f":"'K20 - time schedule'!IA28","v":0},{"$f":"'K20 - time schedule'!IB28","v":0},{"$f":"'K20 - time schedule'!IC28","v":0},{"$f":"'K20 - time schedule'!ID28","v":0},{"$f":"'K20 - time schedule'!IE28","v":0},{"$f":"'K20 - time schedule'!IF28","v":0},{"$f":"'K20 - time schedule'!IG28","v":0},{"$f":"'K20 - time schedule'!IH28","v":0},{"$f":"'K20 - time schedule'!II28","v":0},{"$f":"'K20 - time schedule'!IJ28","v":0},{"$f":"'K20 - time schedule'!IK28","v":0},{"$f":"'K20 - time schedule'!IL28","v":0},{"$f":"'K20 - time schedule'!IM28","v":0},{"$f":"'K20 - time schedule'!IN28","v":0},{"$f":"'K20 - time schedule'!IO28","v":0},{"$f":"'K20 - time schedule'!IP28","v":0},{"$f":"'K20 - time schedule'!IQ28","v":0},{"$f":"'K20 - time schedule'!IR28","v":0},{"$f":"'K20 - time schedule'!IS28","v":0},{"$f":"'K20 - time schedule'!IT28","v":0},{"$f":"'K20 - time schedule'!IU28","v":0},{"$f":"'K20 - time schedule'!IV28","v":0},{"$f":"'K20 - time schedule'!IW28","v":0},{"$f":"'K20 - time schedule'!IX28","v":0},{"$f":"'K20 - time schedule'!IY28","v":0},{"$f":"'K20 - time schedule'!IZ28","v":0},{"$f":"'K20 - time schedule'!JA28","v":0},{"$f":"'K20 - time schedule'!JB28","v":0},{"$f":"'K20 - time schedule'!JC28","v":0},{"$f":"'K20 - time schedule'!JD28","v":0},{"$f":"'K20 - time schedule'!JE28","v":0},{"$f":"'K20 - time schedule'!JF28","v":0},{"$f":"'K20 - time schedule'!JG28","v":0},{"$f":"'K20 - time schedule'!JH28","v":0},{"$f":"'K20 - time schedule'!JI28","v":0},{"$f":"'K20 - time schedule'!JJ28","v":0},{"$f":"'K20 - time schedule'!JK28","v":0},{"$f":"'K20 - time schedule'!JL28","v":0},{"$f":"'K20 - time schedule'!JM28","v":0},{"$f":"'K20 - time schedule'!JN28","v":0},{"$f":"'K20 - time schedule'!JO28","v":0},{"$f":"'K20 - time schedule'!JP28","v":0},{"$f":"'K20 - time schedule'!JQ28","v":0},{"$f":"'K20 - time schedule'!JR28","v":0},{"$f":"'K20 - time schedule'!JS28","v":0},{"$f":"'K20 - time schedule'!JT28","v":0},{"$f":"'K20 - time schedule'!JU28","v":0},{"$f":"'K20 - time schedule'!JV28","v":0},{"$f":"'K20 - time schedule'!JW28","v":0},{"$f":"'K20 - time schedule'!JX28","v":0},{"$f":"'K20 - time schedule'!JY28","v":0},{"$f":"'K20 - time schedule'!JZ28","v":0},{"$f":"'K20 - time schedule'!KA28","v":0},{"$f":"'K20 - time schedule'!KB28","v":0},{"$f":"'K20 - time schedule'!KC28","v":0},{"$f":"'K20 - time schedule'!KD28","v":0},{"$f":"'K20 - time schedule'!KE28","v":0},{"$f":"'K20 - time schedule'!KF28","v":0},{"$f":"'K20 - time schedule'!KG28","v":0},{"$f":"'K20 - time schedule'!KH28","v":0},{"$f":"'K20 - time schedule'!KI28","v":0},{"$f":"'K20 - time schedule'!KJ28","v":0},{"$f":"'K20 - time schedule'!KK28","v":0},{"$f":"'K20 - time schedule'!KL28","v":0},{"$f":"'K20 - time schedule'!KM28","v":0},{"$f":"'K20 - time schedule'!KN28","v":0},{"$f":"'K20 - time schedule'!KO28","v":0},{"$f":"'K20 - time schedule'!KP28","v":0},{"$f":"'K20 - time schedule'!KQ28","v":0},{"$f":"'K20 - time schedule'!KR28","v":0},{"$f":"'K20 - time schedule'!KS28","v":0},{"$f":"'K20 - time schedule'!KT28","v":0}]
["Boiler room K20 - operating staff training","K20","EUR",{"$f":"'K20 - time schedule'!G51","v":0},{"$f":"'K20 - time schedule'!H51","v":0},{"$f":"'K20 - time schedule'!I51","v":0},{"$f":"'K20 - time schedule'!J51","v":0},{"$f":"'K20 - time schedule'!K51","v":0},{"$f":"'K20 - time schedule'!L51","v":0},{"$f":"'K20 - time schedule'!M51","v":0},{"$f":"'K20 - time schedule'!N51","v":0},{"$f":"'K20 - time schedule'!O51","v":0},{"$f":"'K20 - time schedule'!P51","v":0},{"$f":"'K20 - time schedule'!Q51","v":0},{"$f":"'K20 - time schedule'!R51","v":0},{"$f":"'K20 - time schedule'!S51","v":0},{"$f":"'K20 - time schedule'!T51","v":0},{"$f":"'K20 - time schedule'!U51","v":0},{"$f":"'K20 - time schedule'!V51","v":0},{"$f":"'K20 - time schedule'!W51","v":0},{"$f":"'K20 - time schedule'!X51","v":0},{"$f":"'K20 - time schedule'!Y51","v":0},{"$f":"'K20 - time schedule'!Z51","v":0},{"$f":"'K20 - time schedule'!AA51","v":0},{"$f":"'K20 - time schedule'!AB51","v":0},{"$f":"'K20 - time schedule'!AC51","v":0},{"$f":"'K20 - time schedule'!AD51","v":0},{"$f":"'K20 - time schedule'!AE51","v":0},{"$f":"'K20 - time schedule'!AF51","v":0},{"$f":"'K20 - time schedule'!AG51","v":0},{"$f":"'K20 - time schedule'!AH51","v":0},{"$f":"'K20 - time schedule'!AI51","v":0},{"$f":"'K20 - time schedule'!AJ51","v":0},{"$f":"'K20 - time schedule'!AK51","v":0},{"$f":"'K20 - time schedule'!AL51","v":0},{"$f":"'K20 - time schedule'!AM51","v":0},{"$f":"'K20 - time schedule'!AN51","v":0},{"$f":"'K20 - time schedule'!AO51","v":0},{"$f":"'K20 - time schedule'!AP51","v":0},{"$f":"'K20 - time schedule'!AQ51","v":0},{"$f":"'K20 - time schedule'!AR51","v":0},{"$f":"'K20 - time schedule'!AS51","v":0},{"$f":"'K20 - time schedule'!AT51","v":0},{"$f":"'K20 - time schedule'!AU51","v":0},{"$f":"'K20 - time schedule'!AV51","v":0},{"$f":"'K20 - time schedule'!AW51","v":0},{"$f":"'K20 - time schedule'!AX51","v":0},{"$f":"'K20 - time schedule'!AY51","v":0},{"$f":"'K20 - time schedule'!AZ51","v":0},{"$f":"'K20 - time schedule'!BA51","v":0},{"$f":"'K20 - time schedule'!BB51","v":0},{"$f":"'K20 - time schedule'!BC51","v":0},{"$f":"'K20 - time schedule'!BD51","v":0},{"$f":"'K20 - time schedule'!BE51","v":0},{"$f":"'K20 - time schedule'!BF51","v":0},{"$f":"'K20 - time schedule'!BG51","v":0},{"$f":"'K20 - time schedule'!BH51","v":0},{"$f":"'K20 - time schedule'!BI51","v":0},{"$f":"'K20 - time schedule'!BJ51","v":0},{"$f":"'K20 - time schedule'!BK51","v":0},{"$f":"'K20 - time schedule'!BL51","v":0},{"$f":"'K20 - time schedule'!BM51","v":0},{"$f":"'K20 - time schedule'!BN51","v":0},{"$f":"'K20 - time schedule'!BO51","v":0},{"$f":"'K20 - time schedule'!BP51","v":0},{"$f":"'K20 - time schedule'!BQ51","v":0},{"$f":"'K20 - time schedule'!BR51","v":0},{"$f":"'K20 - time schedule'!BS51","v":0},{"$f":"'K20 - time schedule'!BT51","v":0},{"$f":"'K20 - time schedule'!BU51","v":0},{"$f":"'K20 - time schedule'!BV51","v":0},{"$f":"'K20 - time schedule'!BW51","v":0},{"$f":"'K20 - time schedule'!BX51","v":0},{"$f":"'K20 - time schedule'!BY51","v":0},{"$f":"'K20 - time schedule'!BZ51","v":0},{"$f":"'K20 - time schedule'!CA51","v":0},{"$f":"'K20 - time schedule'!CB51","v":0},{"$f":"'K20 - time schedule'!CC51","v":0},{"$f":"'K20 - time schedule'!CD51","v":0},{"$f":"'K20 - time schedule'!CE51","v":0},{"$f":"'K20 - time schedule'!CF51","v":0},{"$f":"'K20 - time schedule'!CG51","v":0},{"$f":"'K20 - time schedule'!CH51","v":0},{"$f":"'K20 - time schedule'!CI51","v":0},{"$f":"'K20 - time schedule'!CJ51","v":0},{"$f":"'K20 - time schedule'!CK51","v":0},{"$f":"'K20 - time schedule'!CL51","v":0},{"$f":"'K20 - time schedule'!CM51","v":0},{"$f":"'K20 - time schedule'!CN51","v":0},{"$f":"'K20 - time schedule'!CO51","v":0},{"$f":"'K20 - time schedule'!CP51","v":0},{"$f":"'K20 - time schedule'!CQ51","v":0},{"$f":"'K20 - time schedule'!CR51","v":0},{"$f":"'K20 - time schedule'!CS51","v":0},{"$f":"'K20 - time schedule'!CT51","v":0},{"$f":"'K20 - time schedule'!CU51","v":0},{"$f":"'K20 - time schedule'!CV51","v":0},{"$f":"'K20 - time schedule'!CW51","v":0},{"$f":"'K20 - time schedule'!CX51","v":0},{"$f":"'K20 - time schedule'!CY51","v":0},{"$f":"'K20 - time schedule'!CZ51","v":0},{"$f":"'K20 - time schedule'!DA51","v":0},{"$f":"'K20 - time schedule'!DB51","v":0},{"$f":"'K20 - time schedule'!DC51","v":0},{"$f":"'K20 - time schedule'!DD51","v":0},{"$f":"'K20 - time schedule'!DE51","v":0},{"$f":"'K20 - time schedule'!DF51","v":0},{"$f":"'K20 - time schedule'!DG51","v":0},{"$f":"'K20 - time schedule'!DH51","v":0},{"$f":"'K20 - time schedule'!DI51","v":0},{"$f":"'K20 - time schedule'!DJ51","v":0},{"$f":"'K20 - time schedule'!DK51","v":0},{"$f":"'K20 - time schedule'!DL51","v":0},{"$f":"'K20 - time schedule'!DM51","v":0},{"$f":"'K20 - time schedule'!DN51","v":0},{"$f":"'K20 - time schedule'!DO51","v":0},{"$f":"'K20 - time schedule'!DP51","v":0},{"$f":"'K20 - time schedule'!DQ51","v":0},{"$f":"'K20 - time schedule'!DR51","v":0},{"$f":"'K20 - time schedule'!DS51","v":0},{"$f":"'K20 - time schedule'!DT51","v":0},{"$f":"'K20 - time schedule'!DU51","v":0},{"$f":"'K20 - time schedule'!DV51","v":0},{"$f":"'K20 - time schedule'!DW51","v":0},{"$f":"'K20 - time schedule'!DX51","v":0},{"$f":"'K20 - time schedule'!DY51","v":0},{"$f":"'K20 - time schedule'!DZ51","v":0},{"$f":"'K20 - time schedule'!EA51","v":0},{"$f":"'K20 - time schedule'!EB51","v":0},{"$f":"'K20 - time schedule'!EC51","v":0},{"$f":"'K20 - time schedule'!ED51","v":0},{"$f":"'K20 - time schedule'!EE51","v":0},{"$f":"'K20 - time schedule'!EF51","v":0},{"$f":"'K20 - time schedule'!EG51","v":0},{"$f":"'K20 - time schedule'!EH51","v":0},{"$f":"'K20 - time schedule'!EI51","v":0},{"$f":"'K20 - time schedule'!EJ51","v":0},{"$f":"'K20 - time schedule'!EK51","v":0},{"$f":"'K20 - time schedule'!EL51","v":0},{"$f":"'K20 - time schedule'!EM51","v":0},{"$f":"'K20 - time schedule'!EN51","v":0},{"$f":"'K20 - time schedule'!EO51","v":0},{"$f":"'K20 - time schedule'!EP51","v":0},{"$f":"'K20 - time schedule'!EQ51","v":0},{"$f":"'K20 - time schedule'!ER51","v":0},{"$f":"'K20 - time schedule'!ES51","v":0},{"$f":"'K20 - time schedule'!ET51","v":0},{"$f":"'K20 - time schedule'!EU51","v":0},{"$f":"'K20 - time schedule'!EV51","v":0},{"$f":"'K20 - time schedule'!EW51","v":0},{"$f":"'K20 - time schedule'!EX51","v":0},{"$f":"'K20 - time schedule'!EY51","v":0},{"$f":"'K20 - time schedule'!EZ51","v":0},{"$f":"'K20 - time schedule'!FA51","v":0},{"$f":"'K20 - time schedule'!FB51","v":0},{"$f":"'K20 - time schedule'!FC51","v":0},{"$f":"'K20 - time schedule'!FD51","v":0},{"$f":"'K20 - time schedule'!FE51","v":0},{"$f":"'K20 - time schedule'!FF51","v":0},{"$f":"'K20 - time schedule'!FG51","v":0},{"$f":"'K20 - time schedule'!FH51","v":0},{"$f":"'K20 - time schedule'!FI51","v":0},{"$f":"'K20 - time schedule'!FJ51","v":0},{"$f":"'K20 - time schedule'!FK51","v":0},{"$f":"'K20 - time schedule'!FL51","v":0},{"$f":"'K20 - time schedule'!FM51","v":0},{"$f":"'K20 - time schedule'!FN51","v":0},{"$f":"'K20 - time schedule'!FO51","v":0},{"$f":"'K20 - time schedule'!FP51","v":0},{"$f":"'K20 - time schedule'!FQ51","v":0},{"$f":"'K20 - time schedule'!FR51","v":0},{"$f":"'K20 - time schedule'!FS51","v":0},{"$f":"'K20 - time schedule'!FT51","v":0},{"$f":"'K20 - time schedule'!FU51","v":0},{"$f":"'K20 - time schedule'!FV51","v":0},{"$f":"'K20 - time schedule'!FW51","v":0},{"$f":"'K20 - time schedule'!FX51","v":0},{"$f":"'K20 - time schedule'!FY51","v":0},{"$f":"'K20 - time schedule'!FZ51","v":0},{"$f":"'K20 - time schedule'!GA51","v":0},{"$f":"'K20 - time schedule'!GB51","v":0},{"$f":"'K20 - time schedule'!GC51","v":0},{"$f":"'K20 - time schedule'!GD51","v":0},{"$f":"'K20 - time schedule'!GE51","v":0},{"$f":"'K20 - time schedule'!GF51","v":0},{"$f":"'K20 - time schedule'!GG29","v":0},{"$f":"'K20 - time schedule'!GH29","v":0},{"$f":"'K20 - time schedule'!GI29","v":0},{"$f":"'K20 - time schedule'!GJ29","v":0},{"$f":"'K20 - time schedule'!GK29","v":0},{"$f":"'K20 - time schedule'!GL29","v":0},{"$f":"'K20 - time schedule'!GM29","v":0},{"$f":"'K20 - time schedule'!GN29","v":0},{"$f":"'K20 - time schedule'!GO29","v":0},{"$f":"'K20 - time schedule'!GP29","v":0},{"$f":"'K20 - time schedule'!GQ29","v":0},{"$f":"'K20 - time schedule'!GR29","v":0},{"$f":"'K20 - time schedule'!GS29","v":0},{"$f":"'K20 - time schedule'!GT29","v":0},{"$f":"'K20 - time schedule'!GU29","v":0},{"$f":"'K20 - time schedule'!GV29","v":0},{"$f":"'K20 - time schedule'!GW29","v":0},{"$f":"'K20 - time schedule'!GX29","v":0},{"$f":"'K20 - time schedule'!GY29","v":0},{"$f":"'K20 - time schedule'!GZ29","v":0},{"$f":"'K20 - time schedule'!HA29","v":0},{"$f":"'K20 - time schedule'!HB29","v":0},{"$f":"'K20 - time schedule'!HC29","v":0},{"$f":"'K20 - time schedule'!HD29","v":0},{"$f":"'K20 - time schedule'!HE29","v":0},{"$f":"'K20 - time schedule'!HF29","v":0},{"$f":"'K20 - time schedule'!HG29","v":0},{"$f":"'K20 - time schedule'!HH29","v":0},{"$f":"'K20 - time schedule'!HI29","v":0},{"$f":"'K20 - time schedule'!HJ29","v":0},{"$f":"'K20 - time schedule'!HK29","v":0},{"$f":"'K20 - time schedule'!HL29","v":0},{"$f":"'K20 - time schedule'!HM29","v":0},{"$f":"'K20 - time schedule'!HN29","v":0},{"$f":"'K20 - time schedule'!HO29","v":0},{"$f":"'K20 - time schedule'!HP29","v":0},{"$f":"'K20 - time schedule'!HQ29","v":0},{"$f":"'K20 - time schedule'!HR29","v":0},{"$f":"'K20 - time schedule'!HS29","v":0},{"$f":"'K20 - time schedule'!HT29","v":0},{"$f":"'K20 - time schedule'!HU29","v":0},{"$f":"'K20 - time schedule'!HV29","v":0},{"$f":"'K20 - time schedule'!HW29","v":0},{"$f":"'K20 - time schedule'!HX29","v":0},{"$f":"'K20 - time schedule'!HY29","v":0},{"$f":"'K20 - time schedule'!HZ29","v":0},{"$f":"'K20 - time schedule'!IA29","v":0},{"$f":"'K20 - time schedule'!IB29","v":0},{"$f":"'K20 - time schedule'!IC29","v":0},{"$f":"'K20 - time schedule'!ID29","v":0},{"$f":"'K20 - time schedule'!IE29","v":0},{"$f":"'K20 - time schedule'!IF29","v":0},{"$f":"'K20 - time schedule'!IG29","v":0},{"$f":"'K20 - time schedule'!IH29","v":0},{"$f":"'K20 - time schedule'!II29","v":0},{"$f":"'K20 - time schedule'!IJ29","v":0},{"$f":"'K20 - time schedule'!IK29","v":0},{"$f":"'K20 - time schedule'!IL29","v":0},{"$f":"'K20 - time schedule'!IM29","v":0},{"$f":"'K20 - time schedule'!IN29","v":0},{"$f":"'K20 - time schedule'!IO29","v":0},{"$f":"'K20 - time schedule'!IP29","v":0},{"$f":"'K20 - time schedule'!IQ29","v":0},{"$f":"'K20 - time schedule'!IR29","v":0},{"$f":"'K20 - time schedule'!IS29","v":0},{"$f":"'K20 - time schedule'!IT29","v":0},{"$f":"'K20 - time schedule'!IU29","v":0},{"$f":"'K20 - time schedule'!IV29","v":0},{"$f":"'K20 - time schedule'!IW29","v":0},{"$f":"'K20 - time schedule'!IX29","v":0},{"$f":"'K20 - time schedule'!IY29","v":0},{"$f":"'K20 - time schedule'!IZ29","v":0},{"$f":"'K20 - time schedule'!JA29","v":0},{"$f":"'K20 - time schedule'!JB29","v":0},{"$f":"'K20 - time schedule'!JC29","v":0},{"$f":"'K20 - time schedule'!JD29","v":0},{"$f":"'K20 - time schedule'!JE29","v":0},{"$f":"'K20 - time schedule'!JF29","v":0},{"$f":"'K20 - time schedule'!JG29","v":0},{"$f":"'K20 - time schedule'!JH29","v":0},{"$f":"'K20 - time schedule'!JI29","v":0},{"$f":"'K20 - time schedule'!JJ29","v":0},{"$f":"'K20 - time schedule'!JK29","v":0},{"$f":"'K20 - time schedule'!JL29","v":0},{"$f":"'K20 - time schedule'!JM29","v":0},{"$f":"'K20 - time schedule'!JN29","v":0},{"$f":"'K20 - time schedule'!JO29","v":0},{"$f":"'K20 - time schedule'!JP29","v":0},{"$f":"'K20 - time schedule'!JQ29","v":0},{"$f":"'K20 - time schedule'!JR29","v":0},{"$f":"'K20 - time schedule'!JS29","v":0},{"$f":"'K20 - time schedule'!JT29","v":0},{"$f":"'K20 - time schedule'!JU29","v":0},{"$f":"'K20 - time schedule'!JV29","v":0},{"$f":"'K20 - time schedule'!JW29","v":0},{"$f":"'K20 - time schedule'!JX29","v":0},{"$f":"'K20 - time schedule'!JY29","v":0},{"$f":"'K20 - time schedule'!JZ29","v":0},{"$f":"'K20 - time schedule'!KA29","v":0},{"$f":"'K20 - time schedule'!KB29","v":0},{"$f":"'K20 - time schedule'!KC29","v":0},{"$f":"'K20 - time schedule'!KD29","v":0},{"$f":"'K20 - time schedule'!KE29","v":0},{"$f":"'K20 - time schedule'!KF29","v":0},{"$f":"'K20 - time schedule'!KG29","v":0},{"$f":"'K20 - time schedule'!KH29","v":0},{"$f":"'K20 - time schedule'!KI29","v":0},{"$f":"'K20 - time schedule'!KJ29","v":0},{"$f":"'K20 - time schedule'!KK29","v":0},{"$f":"'K20 - time schedule'!KL29","v":0},{"$f":"'K20 - time schedule'!KM29","v":0},{"$f":"'K20 - time schedule'!KN29","v":0},{"$f":"'K20 - time schedule'!KO29","v":0},{"$f":"'K20 - time schedule'!KP29","v":0},{"$f":"'K20 - time schedule'!KQ29","v":0},{"$f":"'K20 - time schedule'!KR29","v":0},{"$f":"'K20 - time schedule'!KS29","v":0},{"$f":"'K20 - time schedule'!KT29","v":0}]
["Boiler room K20 - comprehensive testing","K20","EUR",{"$f":"'K20 - time schedule'!G54","v":0},{"$f":"'K20 - time schedule'!H54","v":0},{"$f":"'K20 - time schedule'!I54","v":0},{"$f":"'K20 - time schedule'!J54","v":0},{"$f":"'K20 - time schedule'!K54","v":0},{"$f":"'K20 - time schedule'!L54","v":0},{"$f":"'K20 - time schedule'!M54","v":0},{"$f":"'K20 - time schedule'!N54","v":0},{"$f":"'K20 - time schedule'!O54","v":0},{"$f":"'K20 - time schedule'!P54","v":0},{"$f":"'K20 - time schedule'!Q54","v":0},{"$f":"'K20 - time schedule'!R54","v":0},{"$f":"'K20 - time schedule'!S54","v":0},{"$f":"'K20 - time schedule'!T54","v":0},{"$f":"'K20 - time schedule'!U54","v":0},{"$f":"'K20 - time schedule'!V54","v":0},{"$f":"'K20 - time schedule'!W54","v":0},{"$f":"'K20 - time schedule'!X54","v":0},{"$f":"'K20 - time schedule'!Y54","v":0},{"$f":"'K20 - time schedule'!Z54","v":0},{"$f":"'K20 - time schedule'!AA54","v":0},{"$f":"'K20 - time schedule'!AB54","v":0},{"$f":"'K20 - time schedule'!AC54","v":0},{"$f":"'K20 - time schedule'!AD54","v":0},{"$f":"'K20 - time schedule'!AE54","v":0},{"$f":"'K20 - time schedule'!AF54","v":0},{"$f":"'K20 - time schedule'!AG54","v":0},{"$f":"'K20 - time schedule'!AH54","v":0},{"$f":"'K20 - time schedule'!AI54","v":0},{"$f":"'K20 - time schedule'!AJ54","v":0},{"$f":"'K20 - time schedule'!AK54","v":0},{"$f":"'K20 - time schedule'!AL54","v":0},{"$f":"'K20 - time schedule'!AM54","v":0},{"$f":"'K20 - time schedule'!AN54","v":0},{"$f":"'K20 - time schedule'!AO54","v":0},{"$f":"'K20 - time schedule'!AP54","v":0},{"$f":"'K20 - time schedule'!AQ54","v":0},{"$f":"'K20 - time schedule'!AR54","v":0},{"$f":"'K20 - time schedule'!AS54","v":0},{"$f":"'K20 - time schedule'!AT54","v":0},{"$f":"'K20 - time schedule'!AU54","v":0},{"$f":"'K20 - time schedule'!AV54","v":0},{"$f":"'K20 - time schedule'!AW54","v":0},{"$f":"'K20 - time schedule'!AX54","v":0},{"$f":"'K20 - time schedule'!AY54","v":0},{"$f":"'K20 - time schedule'!AZ54","v":0},{"$f":"'K20 - time schedule'!BA54","v":0},{"$f":"'K20 - time schedule'!BB54","v":0},{"$f":"'K20 - time schedule'!BC54","v":0},{"$f":"'K20 - time schedule'!BD54","v":0},{"$f":"'K20 - time schedule'!BE54","v":0},{"$f":"'K20 - time schedule'!BF54","v":0},{"$f":"'K20 - time schedule'!BG54","v":0},{"$f":"'K20 - time schedule'!BH54","v":0},{"$f":"'K20 - time schedule'!BI54","v":0},{"$f":"'K20 - time schedule'!BJ54","v":0},{"$f":"'K20 - time schedule'!BK54","v":0},{"$f":"'K20 - time schedule'!BL54","v":0},{"$f":"'K20 - time schedule'!BM54","v":0},{"$f":"'K20 - time schedule'!BN54","v":0},{"$f":"'K20 - time schedule'!BO54","v":0},{"$f":"'K20 - time schedule'!BP54","v":0},{"$f":"'K20 - time schedule'!BQ54","v":0},{"$f":"'K20 - time schedule'!BR54","v":0},{"$f":"'K20 - time schedule'!BS54","v":0},{"$f":"'K20 - time schedule'!BT54","v":0},{"$f":"'K20 - time schedule'!BU54","v":0},{"$f":"'K20 - time schedule'!BV54","v":0},{"$f":"'K20 - time schedule'!BW54","v":0},{"$f":"'K20 - time schedule'!BX54","v":0},{"$f":"'K20 - time schedule'!BY54","v":0},{"$f":"'K20 - time schedule'!BZ54","v":0},{"$f":"'K20 - time schedule'!CA54","v":0},{"$f":"'K20 - time schedule'!CB54","v":0},{"$f":"'K20 - time schedule'!CC54","v":0},{"$f":"'K20 - time schedule'!CD54","v":0},{"$f":"'K20 - time schedule'!CE54","v":0},{"$f":"'K20 - time schedule'!CF54","v":0},{"$f":"'K20 - time schedule'!CG54","v":0},{"$f":"'K20 - time schedule'!CH54","v":0},{"$f":"'K20 - time schedule'!CI54","v":0},{"$f":"'K20 - time schedule'!CJ54","v":0},{"$f":"'K20 - time schedule'!CK54","v":0},{"$f":"'K20 - time schedule'!CL54","v":0},{"$f":"'K20 - time schedule'!CM54","v":0},{"$f":"'K20 - time schedule'!CN54","v":0},{"$f":"'K20 - time schedule'!CO54","v":0},{"$f":"'K20 - time schedule'!CP54","v":0},{"$f":"'K20 - time schedule'!CQ54","v":0},{"$f":"'K20 - time schedule'!CR54","v":0},{"$f":"'K20 - time schedule'!CS54","v":0},{"$f":"'K20 - time schedule'!CT54","v":0},{"$f":"'K20 - time schedule'!CU54","v":0},{"$f":"'K20 - time schedule'!CV54","v":0},{"$f":"'K20 - time schedule'!CW54","v":0},{"$f":"'K20 - time schedule'!CX54","v":0},{"$f":"'K20 - time schedule'!CY54","v":0},{"$f":"'K20 - time schedule'!CZ54","v":0},{"$f":"'K20 - time schedule'!DA54","v":0},{"$f":"'K20 - time schedule'!DB54","v":0},{"$f":"'K20 - time schedule'!DC54","v":0},{"$f":"'K20 - time schedule'!DD54","v":0},{"$f":"'K20 - time schedule'!DE54","v":0},{"$f":"'K20 - time schedule'!DF54","v":0},{"$f":"'K20 - time schedule'!DG54","v":0},{"$f":"'K20 - time schedule'!DH54","v":0},{"$f":"'K20 - time schedule'!DI54","v":0},{"$f":"'K20 - time schedule'!DJ54","v":0},{"$f":"'K20 - time schedule'!DK54","v":0},{"$f":"'K20 - time schedule'!DL54","v":0},{"$f":"'K20 - time schedule'!DM54","v":0},{"$f":"'K20 - time schedule'!DN54","v":0},{"$f":"'K20 - time schedule'!DO54","v":0},{"$f":"'K20 - time schedule'!DP54","v":0},{"$f":"'K20 - time schedule'!DQ54","v":0},{"$f":"'K20 - time schedule'!DR54","v":0},{"$f":"'K20 - time schedule'!DS54","v":0},{"$f":"'K20 - time schedule'!DT54","v":0},{"$f":"'K20 - time schedule'!DU54","v":0},{"$f":"'K20 - time schedule'!DV54","v":0},{"$f":"'K20 - time schedule'!DW54","v":0},{"$f":"'K20 - time schedule'!DX54","v":0},{"$f":"'K20 - time schedule'!DY54","v":0},{"$f":"'K20 - time schedule'!DZ54","v":0},{"$f":"'K20 - time schedule'!EA54","v":0},{"$f":"'K20 - time schedule'!EB54","v":0},{"$f":"'K20 - time schedule'!EC54","v":0},{"$f":"'K20 - time schedule'!ED54","v":0},{"$f":"'K20 - time schedule'!EE54","v":0},{"$f":"'K20 - time schedule'!EF54","v":0},{"$f":"'K20 - time schedule'!EG54","v":0},{"$f":"'K20 - time schedule'!EH54","v":0},{"$f":"'K20 - time schedule'!EI54","v":0},{"$f":"'K20 - time schedule'!EJ54","v":0},{"$f":"'K20 - time schedule'!EK54","v":0},{"$f":"'K20 - time schedule'!EL54","v":0},{"$f":"'K20 - time schedule'!EM54","v":0},{"$f":"'K20 - time schedule'!EN54","v":0},{"$f":"'K20 - time schedule'!EO54","v":0},{"$f":"'K20 - time schedule'!EP54","v":0},{"$f":"'K20 - time schedule'!EQ54","v":0},{"$f":"'K20 - time schedule'!ER54","v":0},{"$f":"'K20 - time schedule'!ES54","v":0},{"$f":"'K20 - time schedule'!ET54","v":0},{"$f":"'K20 - time schedule'!EU54","v":0},{"$f":"'K20 - time schedule'!EV54","v":0},{"$f":"'K20 - time schedule'!EW54","v":0},{"$f":"'K20 - time schedule'!EX54","v":0},{"$f":"'K20 - time schedule'!EY54","v":0},{"$f":"'K20 - time schedule'!EZ54","v":0},{"$f":"'K20 - time schedule'!FA54","v":0},{"$f":"'K20 - time schedule'!FB54","v":0},{"$f":"'K20 - time schedule'!FC54","v":0},{"$f":"'K20 - time schedule'!FD54","v":0},{"$f":"'K20 - time schedule'!FE54","v":0},{"$f":"'K20 - time schedule'!FF54","v":0},{"$f":"'K20 - time schedule'!FG54","v":0},{"$f":"'K20 - time schedule'!FH54","v":0},{"$f":"'K20 - time schedule'!FI54","v":0},{"$f":"'K20 - time schedule'!FJ54","v":0},{"$f":"'K20 - time schedule'!FK54","v":0},{"$f":"'K20 - time schedule'!FL54","v":0},{"$f":"'K20 - time schedule'!FM54","v":0},{"$f":"'K20 - time schedule'!FN54","v":0},{"$f":"'K20 - time schedule'!FO54","v":0},{"$f":"'K20 - time schedule'!FP54","v":0},{"$f":"'K20 - time schedule'!FQ54","v":0},{"$f":"'K20 - time schedule'!FR54","v":0},{"$f":"'K20 - time schedule'!FS54","v":0},{"$f":"'K20 - time schedule'!FT54","v":0},{"$f":"'K20 - time schedule'!FU54","v":0},{"$f":"'K20 - time schedule'!FV54","v":0},{"$f":"'K20 - time schedule'!FW54","v":0},{"$f":"'K20 - time schedule'!FX54","v":0},{"$f":"'K20 - time schedule'!FY54","v":0},{"$f":"'K20 - time schedule'!FZ54","v":0},{"$f":"'K20 - time schedule'!GA54","v":0},{"$f":"'K20 - time schedule'!GB54","v":0},{"$f":"'K20 - time schedule'!GC54","v":0},{"$f":"'K20 - time schedule'!GD54","v":0},{"$f":"'K20 - time schedule'!GE54","v":0},{"$f":"'K20 - time schedule'!GF54","v":0},{"$f":"'K20 - time schedule'!GG30","v":0},{"$f":"'K20 - time schedule'!GH30","v":0},{"$f":"'K20 - time schedule'!GI30","v":0},{"$f":"'K20 - time schedule'!GJ30","v":0},{"$f":"'K20 - time schedule'!GK30","v":0},{"$f":"'K20 - time schedule'!GL30","v":0},{"$f":"'K20 - time schedule'!GM30","v":0},{"$f":"'K20 - time schedule'!GN30","v":0},{"$f":"'K20 - time schedule'!GO30","v":0},{"$f":"'K20 - time schedule'!GP30","v":0},{"$f":"'K20 - time schedule'!GQ30","v":0},{"$f":"'K20 - time schedule'!GR30","v":0},{"$f":"'K20 - time schedule'!GS30","v":0},{"$f":"'K20 - time schedule'!GT30","v":0},{"$f":"'K20 - time schedule'!GU30","v":0},{"$f":"'K20 - time schedule'!GV30","v":0},{"$f":"'K20 - time schedule'!GW30","v":0},{"$f":"'K20 - time schedule'!GX30","v":0},{"$f":"'K20 - time schedule'!GY30","v":0},{"$f":"'K20 - time schedule'!GZ30","v":0},{"$f":"'K20 - time schedule'!HA30","v":0},{"$f":"'K20 - time schedule'!HB30","v":0},{"$f":"'K20 - time schedule'!HC30","v":0},{"$f":"'K20 - time schedule'!HD30","v":0},{"$f":"'K20 - time schedule'!HE30","v":0},{"$f":"'K20 - time schedule'!HF30","v":0},{"$f":"'K20 - time schedule'!HG30","v":0},{"$f":"'K20 - time schedule'!HH30","v":0},{"$f":"'K20 - time schedule'!HI30","v":0},{"$f":"'K20 - time schedule'!HJ30","v":0},{"$f":"'K20 - time schedule'!HK30","v":0},{"$f":"'K20 - time schedule'!HL30","v":0},{"$f":"'K20 - time schedule'!HM30","v":0},{"$f":"'K20 - time schedule'!HN30","v":0},{"$f":"'K20 - time schedule'!HO30","v":0},{"$f":"'K20 - time schedule'!HP30","v":0},{"$f":"'K20 - time schedule'!HQ30","v":0},{"$f":"'K20 - time schedule'!HR30","v":0},{"$f":"'K20 - time schedule'!HS30","v":0},{"$f":"'K20 - time schedule'!HT30","v":0},{"$f":"'K20 - time schedule'!HU30","v":0},{"$f":"'K20 - time schedule'!HV30","v":0},{"$f":"'K20 - time schedule'!HW30","v":0},{"$f":"'K20 - time schedule'!HX30","v":0},{"$f":"'K20 - time schedule'!HY30","v":0},{"$f":"'K20 - time schedule'!HZ30","v":0},{"$f":"'K20 - time schedule'!IA30","v":0},{"$f":"'K20 - time schedule'!IB30","v":0},{"$f":"'K20 - time schedule'!IC30","v":0},{"$f":"'K20 - time schedule'!ID30","v":0},{"$f":"'K20 - time schedule'!IE30","v":0},{"$f":"'K20 - time schedule'!IF30","v":0},{"$f":"'K20 - time schedule'!IG30","v":0},{"$f":"'K20 - time schedule'!IH30","v":0},{"$f":"'K20 - time schedule'!II30","v":0},{"$f":"'K20 - time schedule'!IJ30","v":0},{"$f":"'K20 - time schedule'!IK30","v":0},{"$f":"'K20 - time schedule'!IL30","v":0},{"$f":"'K20 - time schedule'!IM30","v":0},{"$f":"'K20 - time schedule'!IN30","v":0},{"$f":"'K20 - time schedule'!IO30","v":0},{"$f":"'K20 - time schedule'!IP30","v":0},{"$f":"'K20 - time schedule'!IQ30","v":0},{"$f":"'K20 - time schedule'!IR30","v":0},{"$f":"'K20 - time schedule'!IS30","v":0},{"$f":"'K20 - time schedule'!IT30","v":0},{"$f":"'K20 - time schedule'!IU30","v":0},{"$f":"'K20 - time schedule'!IV30","v":0},{"$f":"'K20 - time schedule'!IW30","v":0},{"$f":"'K20 - time schedule'!IX30","v":0},{"$f":"'K20 - time schedule'!IY30","v":0},{"$f":"'K20 - time schedule'!IZ30","v":0},{"$f":"'K20 - time schedule'!JA30","v":0},{"$f":"'K20 - time schedule'!JB30","v":0},{"$f":"'K20 - time schedule'!JC30","v":0},{"$f":"'K20 - time schedule'!JD30","v":0},{"$f":"'K20 - time schedule'!JE30","v":0},{"$f":"'K20 - time schedule'!JF30","v":0},{"$f":"'K20 - time schedule'!JG30","v":0},{"$f":"'K20 - time schedule'!JH30","v":0},{"$f":"'K20 - time schedule'!JI30","v":0},{"$f":"'K20 - time schedule'!JJ30","v":0},{"$f":"'K20 - time schedule'!JK30","v":0},{"$f":"'K20 - time schedule'!JL30","v":0},{"$f":"'K20 - time schedule'!JM30","v":0},{"$f":"'K20 - time schedule'!JN30","v":0},{"$f":"'K20 - time schedule'!JO30","v":0},{"$f":"'K20 - time schedule'!JP30","v":0},{"$f":"'K20 - time schedule'!JQ30","v":0},{"$f":"'K20 - time schedule'!JR30","v":0},{"$f":"'K20 - time schedule'!JS30","v":0},{"$f":"'K20 - time schedule'!JT30","v":0},{"$f":"'K20 - time schedule'!JU30","v":0},{"$f":"'K20 - time schedule'!JV30","v":0},{"$f":"'K20 - time schedule'!JW30","v":0},{"$f":"'K20 - time schedule'!JX30","v":0},{"$f":"'K20 - time schedule'!JY30","v":0},{"$f":"'K20 - time schedule'!JZ30","v":0},{"$f":"'K20 - time schedule'!KA30","v":0},{"$f":"'K20 - time schedule'!KB30","v":0},{"$f":"'K20 - time schedule'!KC30","v":0},{"$f":"'K20 - time schedule'!KD30","v":0},{"$f":"'K20 - time schedule'!KE30","v":0},{"$f":"'K20 - time schedule'!KF30","v":0},{"$f":"'K20 - time schedule'!KG30","v":0},{"$f":"'K20 - time schedule'!KH30","v":0},{"$f":"'K20 - time schedule'!KI30","v":0},{"$f":"'K20 - time schedule'!KJ30","v":0},{"$f":"'K20 - time schedule'!KK30","v":0},{"$f":"'K20 - time schedule'!KL30","v":0},{"$f":"'K20 - time schedule'!KM30","v":0},{"$f":"'K20 - time schedule'!KN30","v":0},{"$f":"'K20 - time schedule'!KO30","v":0},{"$f":"'K20 - time schedule'!KP30","v":0},{"$f":"'K20 - time schedule'!KQ30","v":0},{"$f":"'K20 - time schedule'!KR30","v":0},{"$f":"'K20 - time schedule'!KS30","v":0},{"$f":"'K20 - time schedule'!KT30","v":0}]
["Boiler room K20 - trial operation","K20","EUR",{"$f":"'K20 - time schedule'!G56","v":0},{"$f":"'K20 - time schedule'!H56","v":0},{"$f":"'K20 - time schedule'!I56","v":0},{"$f":"'K20 - time schedule'!J56","v":0},{"$f":"'K20 - time schedule'!K56","v":0},{"$f":"'K20 - time schedule'!L56","v":0},{"$f":"'K20 - time schedule'!M56","v":0},{"$f":"'K20 - time schedule'!N56","v":0},{"$f":"'K20 - time schedule'!O56","v":0},{"$f":"'K20 - time schedule'!P56","v":0},{"$f":"'K20 - time schedule'!Q56","v":0},{"$f":"'K20 - time schedule'!R56","v":0},{"$f":"'K20 - time schedule'!S56","v":0},{"$f":"'K20 - time schedule'!T56","v":0},{"$f":"'K20 - time schedule'!U56","v":0},{"$f":"'K20 - time schedule'!V56","v":0},{"$f":"'K20 - time schedule'!W56","v":0},{"$f":"'K20 - time schedule'!X56","v":0},{"$f":"'K20 - time schedule'!Y56","v":0},{"$f":"'K20 - time schedule'!Z56","v":0},{"$f":"'K20 - time schedule'!AA56","v":0},{"$f":"'K20 - time schedule'!AB56","v":0},{"$f":"'K20 - time schedule'!AC56","v":0},{"$f":"'K20 - time schedule'!AD56","v":0},{"$f":"'K20 - time schedule'!AE56","v":0},{"$f":"'K20 - time schedule'!AF56","v":0},{"$f":"'K20 - time schedule'!AG56","v":0},{"$f":"'K20 - time schedule'!AH56","v":0},{"$f":"'K20 - time schedule'!AI56","v":0},{"$f":"'K20 - time schedule'!AJ56","v":0},{"$f":"'K20 - time schedule'!AK56","v":0},{"$f":"'K20 - time schedule'!AL56","v":0},{"$f":"'K20 - time schedule'!AM56","v":0},{"$f":"'K20 - time schedule'!AN56","v":0},{"$f":"'K20 - time schedule'!AO56","v":0},{"$f":"'K20 - time schedule'!AP56","v":0},{"$f":"'K20 - time schedule'!AQ56","v":0},{"$f":"'K20 - time schedule'!AR56","v":0},{"$f":"'K20 - time schedule'!AS56","v":0},{"$f":"'K20 - time schedule'!AT56","v":0},{"$f":"'K20 - time schedule'!AU56","v":0},{"$f":"'K20 - time schedule'!AV56","v":0},{"$f":"'K20 - time schedule'!AW56","v":0},{"$f":"'K20 - time schedule'!AX56","v":0},{"$f":"'K20 - time schedule'!AY56","v":0},{"$f":"'K20 - time schedule'!AZ56","v":0},{"$f":"'K20 - time schedule'!BA56","v":0},{"$f":"'K20 - time schedule'!BB56","v":0},{"$f":"'K20 - time schedule'!BC56","v":0},{"$f":"'K20 - time schedule'!BD56","v":0},{"$f":"'K20 - time schedule'!BE56","v":0},{"$f":"'K20 - time schedule'!BF56","v":0},{"$f":"'K20 - time schedule'!BG56","v":0},{"$f":"'K20 - time schedule'!BH56","v":0},{"$f":"'K20 - time schedule'!BI56","v":0},{"$f":"'K20 - time schedule'!BJ56","v":0},{"$f":"'K20 - time schedule'!BK56","v":0},{"$f":"'K20 - time schedule'!BL56","v":0},{"$f":"'K20 - time schedule'!BM56","v":0},{"$f":"'K20 - time schedule'!BN56","v":0},{"$f":"'K20 - time schedule'!BO56","v":0},{"$f":"'K20 - time schedule'!BP56","v":0},{"$f":"'K20 - time schedule'!BQ56","v":0},{"$f":"'K20 - time schedule'!BR56","v":0},{"$f":"'K20 - time schedule'!BS56","v":0},{"$f":"'K20 - time schedule'!BT56","v":0},{"$f":"'K20 - time schedule'!BU56","v":0},{"$f":"'K20 - time schedule'!BV56","v":0},{"$f":"'K20 - time schedule'!BW56","v":0},{"$f":"'K20 - time schedule'!BX56","v":0},{"$f":"'K20 - time schedule'!BY56","v":0},{"$f":"'K20 - time schedule'!BZ56","v":0},{"$f":"'K20 - time schedule'!CA56","v":0},{"$f":"'K20 - time schedule'!CB56","v":0},{"$f":"'K20 - time schedule'!CC56","v":0},{"$f":"'K20 - time schedule'!CD56","v":0},{"$f":"'K20 - time schedule'!CE56","v":0},{"$f":"'K20 - time schedule'!CF56","v":0},{"$f":"'K20 - time schedule'!CG56","v":0},{"$f":"'K20 - time schedule'!CH56","v":0},{"$f":"'K20 - time schedule'!CI56","v":0},{"$f":"'K20 - time schedule'!CJ56","v":0},{"$f":"'K20 - time schedule'!CK56","v":0},{"$f":"'K20 - time schedule'!CL56","v":0},{"$f":"'K20 - time schedule'!CM56","v":0},{"$f":"'K20 - time schedule'!CN56","v":0},{"$f":"'K20 - time schedule'!CO56","v":0},{"$f":"'K20 - time schedule'!CP56","v":0},{"$f":"'K20 - time schedule'!CQ56","v":0},{"$f":"'K20 - time schedule'!CR56","v":0},{"$f":"'K20 - time schedule'!CS56","v":0},{"$f":"'K20 - time schedule'!CT56","v":0},{"$f":"'K20 - time schedule'!CU56","v":0},{"$f":"'K20 - time schedule'!CV56","v":0},{"$f":"'K20 - time schedule'!CW56","v":0},{"$f":"'K20 - time schedule'!CX56","v":0},{"$f":"'K20 - time schedule'!CY56","v":0},{"$f":"'K20 - time schedule'!CZ56","v":0},{"$f":"'K20 - time schedule'!DA56","v":0},{"$f":"'K20 - time schedule'!DB56","v":0},{"$f":"'K20 - time schedule'!DC56","v":0},{"$f":"'K20 - time schedule'!DD56","v":0},{"$f":"'K20 - time schedule'!DE56","v":0},{"$f":"'K20 - time schedule'!DF56","v":0},{"$f":"'K20 - time schedule'!DG56","v":0},{"$f":"'K20 - time schedule'!DH56","v":0},{"$f":"'K20 - time schedule'!DI56","v":0},{"$f":"'K20 - time schedule'!DJ56","v":0},{"$f":"'K20 - time schedule'!DK56","v":0},{"$f":"'K20 - time schedule'!DL56","v":0},{"$f":"'K20 - time schedule'!DM56","v":0},{"$f":"'K20 - time schedule'!DN56","v":0},{"$f":"'K20 - time schedule'!DO56","v":0},{"$f":"'K20 - time schedule'!DP56","v":0},{"$f":"'K20 - time schedule'!DQ56","v":0},{"$f":"'K20 - time schedule'!DR56","v":0},{"$f":"'K20 - time schedule'!DS56","v":0},{"$f":"'K20 - time schedule'!DT56","v":0},{"$f":"'K20 - time schedule'!DU56","v":0},{"$f":"'K20 - time schedule'!DV56","v":0},{"$f":"'K20 - time schedule'!DW56","v":0},{"$f":"'K20 - time schedule'!DX56","v":0},{"$f":"'K20 - time schedule'!DY56","v":0},{"$f":"'K20 - time schedule'!DZ56","v":0},{"$f":"'K20 - time schedule'!EA56","v":0},{"$f":"'K20 - time schedule'!EB56","v":0},{"$f":"'K20 - time schedule'!EC56","v":0},{"$f":"'K20 - time schedule'!ED56","v":0},{"$f":"'K20 - time schedule'!EE56","v":0},{"$f":"'K20 - time schedule'!EF56","v":0},{"$f":"'K20 - time schedule'!EG56","v":0},{"$f":"'K20 - time schedule'!EH56","v":0},{"$f":"'K20 - time schedule'!EI56","v":0},{"$f":"'K20 - time schedule'!EJ56","v":0},{"$f":"'K20 - time schedule'!EK56","v":0},{"$f":"'K20 - time schedule'!EL56","v":0},{"$f":"'K20 - time schedule'!EM56","v":0},{"$f":"'K20 - time schedule'!EN56","v":0},{"$f":"'K20 - time schedule'!EO56","v":0},{"$f":"'K20 - time schedule'!EP56","v":0},{"$f":"'K20 - time schedule'!EQ56","v":0},{"$f":"'K20 - time schedule'!ER56","v":0},{"$f":"'K20 - time schedule'!ES56","v":0},{"$f":"'K20 - time schedule'!ET56","v":0},{"$f":"'K20 - time schedule'!EU56","v":0},{"$f":"'K20 - time schedule'!EV56","v":0},{"$f":"'K20 - time schedule'!EW56","v":0},{"$f":"'K20 - time schedule'!EX56","v":0},{"$f":"'K20 - time schedule'!EY56","v":0},{"$f":"'K20 - time schedule'!EZ56","v":0},{"$f":"'K20 - time schedule'!FA56","v":0},{"$f":"'K20 - time schedule'!FB56","v":0},{"$f":"'K20 - time schedule'!FC56","v":0},{"$f":"'K20 - time schedule'!FD56","v":0},{"$f":"'K20 - time schedule'!FE56","v":0},{"$f":"'K20 - time schedule'!FF56","v":0},{"$f":"'K20 - time schedule'!FG56","v":0},{"$f":"'K20 - time schedule'!FH56","v":0},{"$f":"'K20 - time schedule'!FI56","v":0},{"$f":"'K20 - time schedule'!FJ56","v":0},{"$f":"'K20 - time schedule'!FK56","v":0},{"$f":"'K20 - time schedule'!FL56","v":0},{"$f":"'K20 - time schedule'!FM56","v":0},{"$f":"'K20 - time schedule'!FN56","v":0},{"$f":"'K20 - time schedule'!FO56","v":0},{"$f":"'K20 - time schedule'!FP56","v":0},{"$f":"'K20 - time schedule'!FQ56","v":0},{"$f":"'K20 - time schedule'!FR56","v":0},{"$f":"'K20 - time schedule'!FS56","v":0},{"$f":"'K20 - time schedule'!FT56","v":0},{"$f":"'K20 - time schedule'!FU56","v":0},{"$f":"'K20 - time schedule'!FV56","v":0},{"$f":"'K20 - time schedule'!FW56","v":0},{"$f":"'K20 - time schedule'!FX56","v":0},{"$f":"'K20 - time schedule'!FY56","v":0},{"$f":"'K20 - time schedule'!FZ56","v":0},{"$f":"'K20 - time schedule'!GA56","v":0},{"$f":"'K20 - time schedule'!GB56","v":0},{"$f":"'K20 - time schedule'!GC56","v":0},{"$f":"'K20 - time schedule'!GD56","v":0},{"$f":"'K20 - time schedule'!GE56","v":0},{"$f":"'K20 - time schedule'!GF56","v":0},{"$f":"'K20 - time schedule'!GG31","v":0},{"$f":"'K20 - time schedule'!GH31","v":0},{"$f":"'K20 - time schedule'!GI31","v":0},{"$f":"'K20 - time schedule'!GJ31","v":0},{"$f":"'K20 - time schedule'!GK31","v":0},{"$f":"'K20 - time schedule'!GL31","v":0},{"$f":"'K20 - time schedule'!GM31","v":0},{"$f":"'K20 - time schedule'!GN31","v":0},{"$f":"'K20 - time schedule'!GO31","v":0},{"$f":"'K20 - time schedule'!GP31","v":0},{"$f":"'K20 - time schedule'!GQ31","v":0},{"$f":"'K20 - time schedule'!GR31","v":0},{"$f":"'K20 - time schedule'!GS31","v":0},{"$f":"'K20 - time schedule'!GT31","v":0},{"$f":"'K20 - time schedule'!GU31","v":0},{"$f":"'K20 - time schedule'!GV31","v":0},{"$f":"'K20 - time schedule'!GW31","v":0},{"$f":"'K20 - time schedule'!GX31","v":0},{"$f":"'K20 - time schedule'!GY31","v":0},{"$f":"'K20 - time schedule'!GZ31","v":0},{"$f":"'K20 - time schedule'!HA31","v":0},{"$f":"'K20 - time schedule'!HB31","v":0},{"$f":"'K20 - time schedule'!HC31","v":0},{"$f":"'K20 - time schedule'!HD31","v":0},{"$f":"'K20 - time schedule'!HE31","v":0},{"$f":"'K20 - time schedule'!HF31","v":0},{"$f":"'K20 - time schedule'!HG31","v":0},{"$f":"'K20 - time schedule'!HH31","v":0},{"$f":"'K20 - time schedule'!HI31","v":0},{"$f":"'K20 - time schedule'!HJ31","v":0},{"$f":"'K20 - time schedule'!HK31","v":0},{"$f":"'K20 - time schedule'!HL31","v":0},{"$f":"'K20 - time schedule'!HM31","v":0},{"$f":"'K20 - time schedule'!HN31","v":0},{"$f":"'K20 - time schedule'!HO31","v":0},{"$f":"'K20 - time schedule'!HP31","v":0},{"$f":"'K20 - time schedule'!HQ31","v":0},{"$f":"'K20 - time schedule'!HR31","v":0},{"$f":"'K20 - time schedule'!HS31","v":0},{"$f":"'K20 - time schedule'!HT31","v":0},{"$f":"'K20 - time schedule'!HU31","v":0},{"$f":"'K20 - time schedule'!HV31","v":0},{"$f":"'K20 - time schedule'!HW31","v":0},{"$f":"'K20 - time schedule'!HX31","v":0},{"$f":"'K20 - time schedule'!HY31","v":0},{"$f":"'K20 - time schedule'!HZ31","v":0},{"$f":"'K20 - time schedule'!IA31","v":0},{"$f":"'K20 - time schedule'!IB31","v":0},{"$f":"'K20 - time schedule'!IC31","v":0},{"$f":"'K20 - time schedule'!ID31","v":0},{"$f":"'K20 - time schedule'!IE31","v":0},{"$f":"'K20 - time schedule'!IF31","v":0},{"$f":"'K20 - time schedule'!IG31","v":0},{"$f":"'K20 - time schedule'!IH31","v":0},{"$f":"'K20 - time schedule'!II31","v":0},{"$f":"'K20 - time schedule'!IJ31","v":0},{"$f":"'K20 - time schedule'!IK31","v":0},{"$f":"'K20 - time schedule'!IL31","v":0},{"$f":"'K20 - time schedule'!IM31","v":0},{"$f":"'K20 - time schedule'!IN31","v":0},{"$f":"'K20 - time schedule'!IO31","v":0},{"$f":"'K20 - time schedule'!IP31","v":0},{"$f":"'K20 - time schedule'!IQ31","v":0},{"$f":"'K20 - time schedule'!IR31","v":0},{"$f":"'K20 - time schedule'!IS31","v":0},{"$f":"'K20 - time schedule'!IT31","v":0},{"$f":"'K20 - time schedule'!IU31","v":0},{"$f":"'K20 - time schedule'!IV31","v":0},{"$f":"'K20 - time schedule'!IW31","v":0},{"$f":"'K20 - time schedule'!IX31","v":0},{"$f":"'K20 - time schedule'!IY31","v":0},{"$f":"'K20 - time schedule'!IZ31","v":0},{"$f":"'K20 - time schedule'!JA31","v":0},{"$f":"'K20 - time schedule'!JB31","v":0},{"$f":"'K20 - time schedule'!JC31","v":0},{"$f":"'K20 - time schedule'!JD31","v":0},{"$f":"'K20 - time schedule'!JE31","v":0},{"$f":"'K20 - time schedule'!JF31","v":0},{"$f":"'K20 - time schedule'!JG31","v":0},{"$f":"'K20 - time schedule'!JH31","v":0},{"$f":"'K20 - time schedule'!JI31","v":0},{"$f":"'K20 - time schedule'!JJ31","v":0},{"$f":"'K20 - time schedule'!JK31","v":0},{"$f":"'K20 - time schedule'!JL31","v":0},{"$f":"'K20 - time schedule'!JM31","v":0},{"$f":"'K20 - time schedule'!JN31","v":0},{"$f":"'K20 - time schedule'!JO31","v":0},{"$f":"'K20 - time schedule'!JP31","v":0},{"$f":"'K20 - time schedule'!JQ31","v":0},{"$f":"'K20 - time schedule'!JR31","v":0},{"$f":"'K20 - time schedule'!JS31","v":0},{"$f":"'K20 - time schedule'!JT31","v":0},{"$f":"'K20 - time schedule'!JU31","v":0},{"$f":"'K20 - time schedule'!JV31","v":0},{"$f":"'K20 - time schedule'!JW31","v":0},{"$f":"'K20 - time schedule'!JX31","v":0},{"$f":"'K20 - time schedule'!JY31","v":0},{"$f":"'K20 - time schedule'!JZ31","v":0},{"$f":"'K20 - time schedule'!KA31","v":0},{"$f":"'K20 - time schedule'!KB31","v":0},{"$f":"'K20 - time schedule'!KC31","v":0},{"$f":"'K20 - time schedule'!KD31","v":0},{"$f":"'K20 - time schedule'!KE31","v":0},{"$f":"'K20 - time schedule'!KF31","v":0},{"$f":"'K20 - time schedule'!KG31","v":0},{"$f":"'K20 - time schedule'!KH31","v":0},{"$f":"'K20 - time schedule'!KI31","v":0},{"$f":"'K20 - time schedule'!KJ31","v":0},{"$f":"'K20 - time schedule'!KK31","v":0},{"$f":"'K20 - time schedule'!KL31","v":0},{"$f":"'K20 - time schedule'!KM31","v":0},{"$f":"'K20 - time schedule'!KN31","v":0},{"$f":"'K20 - time schedule'!KO31","v":0},{"$f":"'K20 - time schedule'!KP31","v":0},{"$f":"'K20 - time schedule'!KQ31","v":0},{"$f":"'K20 - time schedule'!KR31","v":0},{"$f":"'K20 - time schedule'!KS31","v":0},{"$f":"'K20 - time schedule'!KT31","v":0}]
["Boiler room K20 - guarantee test A","K20","EUR",{"$f":"'K20 - time schedule'!G58","v":0},{"$f":"'K20 - time schedule'!H58","v":0},{"$f":"'K20 - time schedule'!I58","v":0},{"$f":"'K20 - time schedule'!J58","v":0},{"$f":"'K20 - time schedule'!K58","v":0},{"$f":"'K20 - time schedule'!L58","v":0},{"$f":"'K20 - time schedule'!M58","v":0},{"$f":"'K20 - time schedule'!N58","v":0},{"$f":"'K20 - time schedule'!O58","v":0},{"$f":"'K20 - time schedule'!P58","v":0},{"$f":"'K20 - time schedule'!Q58","v":0},{"$f":"'K20 - time schedule'!R58","v":0},{"$f":"'K20 - time schedule'!S58","v":0},{"$f":"'K20 - time schedule'!T58","v":0},{"$f":"'K20 - time schedule'!U58","v":0},{"$f":"'K20 - time schedule'!V58","v":0},{"$f":"'K20 - time schedule'!W58","v":0},{"$f":"'K20 - time schedule'!X58","v":0},{"$f":"'K20 - time schedule'!Y58","v":0},{"$f":"'K20 - time schedule'!Z58","v":0},{"$f":"'K20 - time schedule'!AA58","v":0},{"$f":"'K20 - time schedule'!AB58","v":0},{"$f":"'K20 - time schedule'!AC58","v":0},{"$f":"'K20 - time schedule'!AD58","v":0},{"$f":"'K20 - time schedule'!AE58","v":0},{"$f":"'K20 - time schedule'!AF58","v":0},{"$f":"'K20 - time schedule'!AG58","v":0},{"$f":"'K20 - time schedule'!AH58","v":0},{"$f":"'K20 - time schedule'!AI58","v":0},{"$f":"'K20 - time schedule'!AJ58","v":0},{"$f":"'K20 - time schedule'!AK58","v":0},{"$f":"'K20 - time schedule'!AL58","v":0},{"$f":"'K20 - time schedule'!AM58","v":0},{"$f":"'K20 - time schedule'!AN58","v":0},{"$f":"'K20 - time schedule'!AO58","v":0},{"$f":"'K20 - time schedule'!AP58","v":0},{"$f":"'K20 - time schedule'!AQ58","v":0},{"$f":"'K20 - time schedule'!AR58","v":0},{"$f":"'K20 - time schedule'!AS58","v":0},{"$f":"'K20 - time schedule'!AT58","v":0},{"$f":"'K20 - time schedule'!AU58","v":0},{"$f":"'K20 - time schedule'!AV58","v":0},{"$f":"'K20 - time schedule'!AW58","v":0},{"$f":"'K20 - time schedule'!AX58","v":0},{"$f":"'K20 - time schedule'!AY58","v":0},{"$f":"'K20 - time schedule'!AZ58","v":0},{"$f":"'K20 - time schedule'!BA58","v":0},{"$f":"'K20 - time schedule'!BB58","v":0},{"$f":"'K20 - time schedule'!BC58","v":0},{"$f":"'K20 - time schedule'!BD58","v":0},{"$f":"'K20 - time schedule'!BE58","v":0},{"$f":"'K20 - time schedule'!BF58","v":0},{"$f":"'K20 - time schedule'!BG58","v":0},{"$f":"'K20 - time schedule'!BH58","v":0},{"$f":"'K20 - time schedule'!BI58","v":0},{"$f":"'K20 - time schedule'!BJ58","v":0},{"$f":"'K20 - time schedule'!BK58","v":0},{"$f":"'K20 - time schedule'!BL58","v":0},{"$f":"'K20 - time schedule'!BM58","v":0},{"$f":"'K20 - time schedule'!BN58","v":0},{"$f":"'K20 - time schedule'!BO58","v":0},{"$f":"'K20 - time schedule'!BP58","v":0},{"$f":"'K20 - time schedule'!BQ58","v":0},{"$f":"'K20 - time schedule'!BR58","v":0},{"$f":"'K20 - time schedule'!BS58","v":0},{"$f":"'K20 - time schedule'!BT58","v":0},{"$f":"'K20 - time schedule'!BU58","v":0},{"$f":"'K20 - time schedule'!BV58","v":0},{"$f":"'K20 - time schedule'!BW58","v":0},{"$f":"'K20 - time schedule'!BX58","v":0},{"$f":"'K20 - time schedule'!BY58","v":0},{"$f":"'K20 - time schedule'!BZ58","v":0},{"$f":"'K20 - time schedule'!CA58","v":0},{"$f":"'K20 - time schedule'!CB58","v":0},{"$f":"'K20 - time schedule'!CC58","v":0},{"$f":"'K20 - time schedule'!CD58","v":0},{"$f":"'K20 - time schedule'!CE58","v":0},{"$f":"'K20 - time schedule'!CF58","v":0},{"$f":"'K20 - time schedule'!CG58","v":0},{"$f":"'K20 - time schedule'!CH58","v":0},{"$f":"'K20 - time schedule'!CI58","v":0},{"$f":"'K20 - time schedule'!CJ58","v":0},{"$f":"'K20 - time schedule'!CK58","v":0},{"$f":"'K20 - time schedule'!CL58","v":0},{"$f":"'K20 - time schedule'!CM58","v":0},{"$f":"'K20 - time schedule'!CN58","v":0},{"$f":"'K20 - time schedule'!CO58","v":0},{"$f":"'K20 - time schedule'!CP58","v":0},{"$f":"'K20 - time schedule'!CQ58","v":0},{"$f":"'K20 - time schedule'!CR58","v":0},{"$f":"'K20 - time schedule'!CS58","v":0},{"$f":"'K20 - time schedule'!CT58","v":0},{"$f":"'K20 - time schedule'!CU58","v":0},{"$f":"'K20 - time schedule'!CV58","v":0},{"$f":"'K20 - time schedule'!CW58","v":0},{"$f":"'K20 - time schedule'!CX58","v":0},{"$f":"'K20 - time schedule'!CY58","v":0},{"$f":"'K20 - time schedule'!CZ58","v":0},{"$f":"'K20 - time schedule'!DA58","v":0},{"$f":"'K20 - time schedule'!DB58","v":0},{"$f":"'K20 - time schedule'!DC58","v":0},{"$f":"'K20 - time schedule'!DD58","v":0},{"$f":"'K20 - time schedule'!DE58","v":0},{"$f":"'K20 - time schedule'!DF58","v":0},{"$f":"'K20 - time schedule'!DG58","v":0},{"$f":"'K20 - time schedule'!DH58","v":0},{"$f":"'K20 - time schedule'!DI58","v":0},{"$f":"'K20 - time schedule'!DJ58","v":0},{"$f":"'K20 - time schedule'!DK58","v":0},{"$f":"'K20 - time schedule'!DL58","v":0},{"$f":"'K20 - time schedule'!DM58","v":0},{"$f":"'K20 - time schedule'!DN58","v":0},{"$f":"'K20 - time schedule'!DO58","v":0},{"$f":"'K20 - time schedule'!DP58","v":0},{"$f":"'K20 - time schedule'!DQ58","v":0},{"$f":"'K20 - time schedule'!DR58","v":0},{"$f":"'K20 - time schedule'!DS58","v":0},{"$f":"'K20 - time schedule'!DT58","v":0},{"$f":"'K20 - time schedule'!DU58","v":0},{"$f":"'K20 - time schedule'!DV58","v":0},{"$f":"'K20 - time schedule'!DW58","v":0},{"$f":"'K20 - time schedule'!DX58","v":0},{"$f":"'K20 - time schedule'!DY58","v":0},{"$f":"'K20 - time schedule'!DZ58","v":0},{"$f":"'K20 - time schedule'!EA58","v":0},{"$f":"'K20 - time schedule'!EB58","v":0},{"$f":"'K20 - time schedule'!EC58","v":0},{"$f":"'K20 - time schedule'!ED58","v":0},{"$f":"'K20 - time schedule'!EE58","v":0},{"$f":"'K20 - time schedule'!EF58","v":0},{"$f":"'K20 - time schedule'!EG58","v":0},{"$f":"'K20 - time schedule'!EH58","v":0},{"$f":"'K20 - time schedule'!EI58","v":0},{"$f":"'K20 - time schedule'!EJ58","v":0},{"$f":"'K20 - time schedule'!EK58","v":0},{"$f":"'K20 - time schedule'!EL58","v":0},{"$f":"'K20 - time schedule'!EM58","v":0},{"$f":"'K20 - time schedule'!EN58","v":0},{"$f":"'K20 - time schedule'!EO58","v":0},{"$f":"'K20 - time schedule'!EP58","v":0},{"$f":"'K20 - time schedule'!EQ58","v":0},{"$f":"'K20 - time schedule'!ER58","v":0},{"$f":"'K20 - time schedule'!ES58","v":0},{"$f":"'K20 - time schedule'!ET58","v":0},{"$f":"'K20 - time schedule'!EU58","v":0},{"$f":"'K20 - time schedule'!EV58","v":0},{"$f":"'K20 - time schedule'!EW58","v":0},{"$f":"'K20 - time schedule'!EX58","v":0},{"$f":"'K20 - time schedule'!EY58","v":0},{"$f":"'K20 - time schedule'!EZ58","v":0},{"$f":"'K20 - time schedule'!FA58","v":0},{"$f":"'K20 - time schedule'!FB58","v":0},{"$f":"'K20 - time schedule'!FC58","v":0},{"$f":"'K20 - time schedule'!FD58","v":0},{"$f":"'K20 - time schedule'!FE58","v":0},{"$f":"'K20 - time schedule'!FF58","v":0},{"$f":"'K20 - time schedule'!FG58","v":0},{"$f":"'K20 - time schedule'!FH58","v":0},{"$f":"'K20 - time schedule'!FI58","v":0},{"$f":"'K20 - time schedule'!FJ58","v":0},{"$f":"'K20 - time schedule'!FK58","v":0},{"$f":"'K20 - time schedule'!FL58","v":0},{"$f":"'K20 - time schedule'!FM58","v":0},{"$f":"'K20 - time schedule'!FN58","v":0},{"$f":"'K20 - time schedule'!FO58","v":0},{"$f":"'K20 - time schedule'!FP58","v":0},{"$f":"'K20 - time schedule'!FQ58","v":0},{"$f":"'K20 - time schedule'!FR58","v":0},{"$f":"'K20 - time schedule'!FS58","v":0},{"$f":"'K20 - time schedule'!FT58","v":0},{"$f":"'K20 - time schedule'!FU58","v":0},{"$f":"'K20 - time schedule'!FV58","v":0},{"$f":"'K20 - time schedule'!FW58","v":0},{"$f":"'K20 - time schedule'!FX58","v":0},{"$f":"'K20 - time schedule'!FY58","v":0},{"$f":"'K20 - time schedule'!FZ58","v":0},{"$f":"'K20 - time schedule'!GA58","v":0},{"$f":"'K20 - time schedule'!GB58","v":0},{"$f":"'K20 - time schedule'!GC58","v":0},{"$f":"'K20 - time schedule'!GD58","v":0},{"$f":"'K20 - time schedule'!GE58","v":0},{"$f":"'K20 - time schedule'!GF58","v":0},{"$f":"'K20 - time schedule'!GG32","v":0},{"$f":"'K20 - time schedule'!GH32","v":0},{"$f":"'K20 - time schedule'!GI32","v":0},{"$f":"'K20 - time schedule'!GJ32","v":0},{"$f":"'K20 - time schedule'!GK32","v":0},{"$f":"'K20 - time schedule'!GL32","v":0},{"$f":"'K20 - time schedule'!GM32","v":0},{"$f":"'K20 - time schedule'!GN32","v":0},{"$f":"'K20 - time schedule'!GO32","v":0},{"$f":"'K20 - time schedule'!GP32","v":0},{"$f":"'K20 - time schedule'!GQ32","v":0},{"$f":"'K20 - time schedule'!GR32","v":0},{"$f":"'K20 - time schedule'!GS32","v":0},{"$f":"'K20 - time schedule'!GT32","v":0},{"$f":"'K20 - time schedule'!GU32","v":0},{"$f":"'K20 - time schedule'!GV32","v":0},{"$f":"'K20 - time schedule'!GW32","v":0},{"$f":"'K20 - time schedule'!GX32","v":0},{"$f":"'K20 - time schedule'!GY32","v":0},{"$f":"'K20 - time schedule'!GZ32","v":0},{"$f":"'K20 - time schedule'!HA32","v":0},{"$f":"'K20 - time schedule'!HB32","v":0},{"$f":"'K20 - time schedule'!HC32","v":0},{"$f":"'K20 - time schedule'!HD32","v":0},{"$f":"'K20 - time schedule'!HE32","v":0},{"$f":"'K20 - time schedule'!HF32","v":0},{"$f":"'K20 - time schedule'!HG32","v":0},{"$f":"'K20 - time schedule'!HH32","v":0},{"$f":"'K20 - time schedule'!HI32","v":0},{"$f":"'K20 - time schedule'!HJ32","v":0},{"$f":"'K20 - time schedule'!HK32","v":0},{"$f":"'K20 - time schedule'!HL32","v":0},{"$f":"'K20 - time schedule'!HM32","v":0},{"$f":"'K20 - time schedule'!HN32","v":0},{"$f":"'K20 - time schedule'!HO32","v":0},{"$f":"'K20 - time schedule'!HP32","v":0},{"$f":"'K20 - time schedule'!HQ32","v":0},{"$f":"'K20 - time schedule'!HR32","v":0},{"$f":"'K20 - time schedule'!HS32","v":0},{"$f":"'K20 - time schedule'!HT32","v":0},{"$f":"'K20 - time schedule'!HU32","v":0},{"$f":"'K20 - time schedule'!HV32","v":0},{"$f":"'K20 - time schedule'!HW32","v":0},{"$f":"'K20 - time schedule'!HX32","v":0},{"$f":"'K20 - time schedule'!HY32","v":0},{"$f":"'K20 - time schedule'!HZ32","v":0},{"$f":"'K20 - time schedule'!IA32","v":0},{"$f":"'K20 - time schedule'!IB32","v":0},{"$f":"'K20 - time schedule'!IC32","v":0},{"$f":"'K20 - time schedule'!ID32","v":0},{"$f":"'K20 - time schedule'!IE32","v":0},{"$f":"'K20 - time schedule'!IF32","v":0},{"$f":"'K20 - time schedule'!IG32","v":0},{"$f":"'K20 - time schedule'!IH32","v":0},{"$f":"'K20 - time schedule'!II32","v":0},{"$f":"'K20 - time schedule'!IJ32","v":0},{"$f":"'K20 - time schedule'!IK32","v":0},{"$f":"'K20 - time schedule'!IL32","v":0},{"$f":"'K20 - time schedule'!IM32","v":0},{"$f":"'K20 - time schedule'!IN32","v":0},{"$f":"'K20 - time schedule'!IO32","v":0},{"$f":"'K20 - time schedule'!IP32","v":0},{"$f":"'K20 - time schedule'!IQ32","v":0},{"$f":"'K20 - time schedule'!IR32","v":0},{"$f":"'K20 - time schedule'!IS32","v":0},{"$f":"'K20 - time schedule'!IT32","v":0},{"$f":"'K20 - time schedule'!IU32","v":0},{"$f":"'K20 - time schedule'!IV32","v":0},{"$f":"'K20 - time schedule'!IW32","v":0},{"$f":"'K20 - time schedule'!IX32","v":0},{"$f":"'K20 - time schedule'!IY32","v":0},{"$f":"'K20 - time schedule'!IZ32","v":0},{"$f":"'K20 - time schedule'!JA32","v":0},{"$f":"'K20 - time schedule'!JB32","v":0},{"$f":"'K20 - time schedule'!JC32","v":0},{"$f":"'K20 - time schedule'!JD32","v":0},{"$f":"'K20 - time schedule'!JE32","v":0},{"$f":"'K20 - time schedule'!JF32","v":0},{"$f":"'K20 - time schedule'!JG32","v":0},{"$f":"'K20 - time schedule'!JH32","v":0},{"$f":"'K20 - time schedule'!JI32","v":0},{"$f":"'K20 - time schedule'!JJ32","v":0},{"$f":"'K20 - time schedule'!JK32","v":0},{"$f":"'K20 - time schedule'!JL32","v":0},{"$f":"'K20 - time schedule'!JM32","v":0},{"$f":"'K20 - time schedule'!JN32","v":0},{"$f":"'K20 - time schedule'!JO32","v":0},{"$f":"'K20 - time schedule'!JP32","v":0},{"$f":"'K20 - time schedule'!JQ32","v":0},{"$f":"'K20 - time schedule'!JR32","v":0},{"$f":"'K20 - time schedule'!JS32","v":0},{"$f":"'K20 - time schedule'!JT32","v":0},{"$f":"'K20 - time schedule'!JU32","v":0},{"$f":"'K20 - time schedule'!JV32","v":0},{"$f":"'K20 - time schedule'!JW32","v":0},{"$f":"'K20 - time schedule'!JX32","v":0},{"$f":"'K20 - time schedule'!JY32","v":0},{"$f":"'K20 - time schedule'!JZ32","v":0},{"$f":"'K20 - time schedule'!KA32","v":0},{"$f":"'K20 - time schedule'!KB32","v":0},{"$f":"'K20 - time schedule'!KC32","v":0},{"$f":"'K20 - time schedule'!KD32","v":0},{"$f":"'K20 - time schedule'!KE32","v":0},{"$f":"'K20 - time schedule'!KF32","v":0},{"$f":"'K20 - time schedule'!KG32","v":0},{"$f":"'K20 - time schedule'!KH32","v":0},{"$f":"'K20 - time schedule'!KI32","v":0},{"$f":"'K20 - time schedule'!KJ32","v":0},{"$f":"'K20 - time schedule'!KK32","v":0},{"$f":"'K20 - time schedule'!KL32","v":0},{"$f":"'K20 - time schedule'!KM32","v":0},{"$f":"'K20 - time schedule'!KN32","v":0},{"$f":"'K20 - time schedule'!KO32","v":0},{"$f":"'K20 - time schedule'!KP32","v":0},{"$f":"'K20 - time schedule'!KQ32","v":0},{"$f":"'K20 - time schedule'!KR32","v":0},{"$f":"'K20 - time schedule'!KS32","v":0},{"$f":"'K20 - time schedule'!KT32","v":0}]
["Boiler room K20 - preliminary acceptance of the Work PAC","K20","EUR",{"$f":"'K20 - time schedule'!G60","v":0},{"$f":"'K20 - time schedule'!H60","v":0},{"$f":"'K20 - time schedule'!I60","v":0},{"$f":"'K20 - time schedule'!J60","v":0},{"$f":"'K20 - time schedule'!K60","v":0},{"$f":"'K20 - time schedule'!L60","v":0},{"$f":"'K20 - time schedule'!M60","v":0},{"$f":"'K20 - time schedule'!N60","v":0},{"$f":"'K20 - time schedule'!O60","v":0},{"$f":"'K20 - time schedule'!P60","v":0},{"$f":"'K20 - time schedule'!Q60","v":0},{"$f":"'K20 - time schedule'!R60","v":0},{"$f":"'K20 - time schedule'!S60","v":0},{"$f":"'K20 - time schedule'!T60","v":0},{"$f":"'K20 - time schedule'!U60","v":0},{"$f":"'K20 - time schedule'!V60","v":0},{"$f":"'K20 - time schedule'!W60","v":0},{"$f":"'K20 - time schedule'!X60","v":0},{"$f":"'K20 - time schedule'!Y60","v":0},{"$f":"'K20 - time schedule'!Z60","v":0},{"$f":"'K20 - time schedule'!AA60","v":0},{"$f":"'K20 - time schedule'!AB60","v":0},{"$f":"'K20 - time schedule'!AC60","v":0},{"$f":"'K20 - time schedule'!AD60","v":0},{"$f":"'K20 - time schedule'!AE60","v":0},{"$f":"'K20 - time schedule'!AF60","v":0},{"$f":"'K20 - time schedule'!AG60","v":0},{"$f":"'K20 - time schedule'!AH60","v":0},{"$f":"'K20 - time schedule'!AI60","v":0},{"$f":"'K20 - time schedule'!AJ60","v":0},{"$f":"'K20 - time schedule'!AK60","v":0},{"$f":"'K20 - time schedule'!AL60","v":0},{"$f":"'K20 - time schedule'!AM60","v":0},{"$f":"'K20 - time schedule'!AN60","v":0},{"$f":"'K20 - time schedule'!AO60","v":0},{"$f":"'K20 - time schedule'!AP60","v":0},{"$f":"'K20 - time schedule'!AQ60","v":0},{"$f":"'K20 - time schedule'!AR60","v":0},{"$f":"'K20 - time schedule'!AS60","v":0},{"$f":"'K20 - time schedule'!AT60","v":0},{"$f":"'K20 - time schedule'!AU60","v":0},{"$f":"'K20 - time schedule'!AV60","v":0},{"$f":"'K20 - time schedule'!AW60","v":0},{"$f":"'K20 - time schedule'!AX60","v":0},{"$f":"'K20 - time schedule'!AY60","v":0},{"$f":"'K20 - time schedule'!AZ60","v":0},{"$f":"'K20 - time schedule'!BA60","v":0},{"$f":"'K20 - time schedule'!BB60","v":0},{"$f":"'K20 - time schedule'!BC60","v":0},{"$f":"'K20 - time schedule'!BD60","v":0},{"$f":"'K20 - time schedule'!BE60","v":0},{"$f":"'K20 - time schedule'!BF60","v":0},{"$f":"'K20 - time schedule'!BG60","v":0},{"$f":"'K20 - time schedule'!BH60","v":0},{"$f":"'K20 - time schedule'!BI60","v":0},{"$f":"'K20 - time schedule'!BJ60","v":0},{"$f":"'K20 - time schedule'!BK60","v":0},{"$f":"'K20 - time schedule'!BL60","v":0},{"$f":"'K20 - time schedule'!BM60","v":0},{"$f":"'K20 - time schedule'!BN60","v":0},{"$f":"'K20 - time schedule'!BO60","v":0},{"$f":"'K20 - time schedule'!BP60","v":0},{"$f":"'K20 - time schedule'!BQ60","v":0},{"$f":"'K20 - time schedule'!BR60","v":0},{"$f":"'K20 - time schedule'!BS60","v":0},{"$f":"'K20 - time schedule'!BT60","v":0},{"$f":"'K20 - time schedule'!BU60","v":0},{"$f":"'K20 - time schedule'!BV60","v":0},{"$f":"'K20 - time schedule'!BW60","v":0},{"$f":"'K20 - time schedule'!BX60","v":0},{"$f":"'K20 - time schedule'!BY60","v":0},{"$f":"'K20 - time schedule'!BZ60","v":0},{"$f":"'K20 - time schedule'!CA60","v":0},{"$f":"'K20 - time schedule'!CB60","v":0},{"$f":"'K20 - time schedule'!CC60","v":0},{"$f":"'K20 - time schedule'!CD60","v":0},{"$f":"'K20 - time schedule'!CE60","v":0},{"$f":"'K20 - time schedule'!CF60","v":0},{"$f":"'K20 - time schedule'!CG60","v":0},{"$f":"'K20 - time schedule'!CH60","v":0},{"$f":"'K20 - time schedule'!CI60","v":0},{"$f":"'K20 - time schedule'!CJ60","v":0},{"$f":"'K20 - time schedule'!CK60","v":0},{"$f":"'K20 - time schedule'!CL60","v":0},{"$f":"'K20 - time schedule'!CM60","v":0},{"$f":"'K20 - time schedule'!CN60","v":0},{"$f":"'K20 - time schedule'!CO60","v":0},{"$f":"'K20 - time schedule'!CP60","v":0},{"$f":"'K20 - time schedule'!CQ60","v":0},{"$f":"'K20 - time schedule'!CR60","v":0},{"$f":"'K20 - time schedule'!CS60","v":0},{"$f":"'K20 - time schedule'!CT60","v":0},{"$f":"'K20 - time schedule'!CU60","v":0},{"$f":"'K20 - time schedule'!CV60","v":0},{"$f":"'K20 - time schedule'!CW60","v":0},{"$f":"'K20 - time schedule'!CX60","v":0},{"$f":"'K20 - time schedule'!CY60","v":0},{"$f":"'K20 - time schedule'!CZ60","v":0},{"$f":"'K20 - time schedule'!DA60","v":0},{"$f":"'K20 - time schedule'!DB60","v":0},{"$f":"'K20 - time schedule'!DC60","v":0},{"$f":"'K20 - time schedule'!DD60","v":0},{"$f":"'K20 - time schedule'!DE60","v":0},{"$f":"'K20 - time schedule'!DF60","v":0},{"$f":"'K20 - time schedule'!DG60","v":0},{"$f":"'K20 - time schedule'!DH60","v":0},{"$f":"'K20 - time schedule'!DI60","v":0},{"$f":"'K20 - time schedule'!DJ60","v":0},{"$f":"'K20 - time schedule'!DK60","v":0},{"$f":"'K20 - time schedule'!DL60","v":0},{"$f":"'K20 - time schedule'!DM60","v":0},{"$f":"'K20 - time schedule'!DN60","v":0},{"$f":"'K20 - time schedule'!DO60","v":0},{"$f":"'K20 - time schedule'!DP60","v":0},{"$f":"'K20 - time schedule'!DQ60","v":0},{"$f":"'K20 - time schedule'!DR60","v":0},{"$f":"'K20 - time schedule'!DS60","v":0},{"$f":"'K20 - time schedule'!DT60","v":0},{"$f":"'K20 - time schedule'!DU60","v":0},{"$f":"'K20 - time schedule'!DV60","v":0},{"$f":"'K20 - time schedule'!DW60","v":0},{"$f":"'K20 - time schedule'!DX60","v":0},{"$f":"'K20 - time schedule'!DY60","v":0},{"$f":"'K20 - time schedule'!DZ60","v":0},{"$f":"'K20 - time schedule'!EA60","v":0},{"$f":"'K20 - time schedule'!EB60","v":0},{"$f":"'K20 - time schedule'!EC60","v":0},{"$f":"'K20 - time schedule'!ED60","v":0},{"$f":"'K20 - time schedule'!EE60","v":0},{"$f":"'K20 - time schedule'!EF60","v":0},{"$f":"'K20 - time schedule'!EG60","v":0},{"$f":"'K20 - time schedule'!EH60","v":0},{"$f":"'K20 - time schedule'!EI60","v":0},{"$f":"'K20 - time schedule'!EJ60","v":0},{"$f":"'K20 - time schedule'!EK60","v":0},{"$f":"'K20 - time schedule'!EL60","v":0},{"$f":"'K20 - time schedule'!EM60","v":0},{"$f":"'K20 - time schedule'!EN60","v":0},{"$f":"'K20 - time schedule'!EO60","v":0},{"$f":"'K20 - time schedule'!EP60","v":0},{"$f":"'K20 - time schedule'!EQ60","v":0},{"$f":"'K20 - time schedule'!ER60","v":0},{"$f":"'K20 - time schedule'!ES60","v":0},{"$f":"'K20 - time schedule'!ET60","v":0},{"$f":"'K20 - time schedule'!EU60","v":0},{"$f":"'K20 - time schedule'!EV60","v":0},{"$f":"'K20 - time schedule'!EW60","v":0},{"$f":"'K20 - time schedule'!EX60","v":0},{"$f":"'K20 - time schedule'!EY60","v":0},{"$f":"'K20 - time schedule'!EZ60","v":0},{"$f":"'K20 - time schedule'!FA60","v":0},{"$f":"'K20 - time schedule'!FB60","v":0},{"$f":"'K20 - time schedule'!FC60","v":0},{"$f":"'K20 - time schedule'!FD60","v":0},{"$f":"'K20 - time schedule'!FE60","v":0},{"$f":"'K20 - time schedule'!FF60","v":0},{"$f":"'K20 - time schedule'!FG60","v":0},{"$f":"'K20 - time schedule'!FH60","v":0},{"$f":"'K20 - time schedule'!FI60","v":0},{"$f":"'K20 - time schedule'!FJ60","v":0},{"$f":"'K20 - time schedule'!FK60","v":0},{"$f":"'K20 - time schedule'!FL60","v":0},{"$f":"'K20 - time schedule'!FM60","v":0},{"$f":"'K20 - time schedule'!FN60","v":0},{"$f":"'K20 - time schedule'!FO60","v":0},{"$f":"'K20 - time schedule'!FP60","v":0},{"$f":"'K20 - time schedule'!FQ60","v":0},{"$f":"'K20 - time schedule'!FR60","v":0},{"$f":"'K20 - time schedule'!FS60","v":0},{"$f":"'K20 - time schedule'!FT60","v":0},{"$f":"'K20 - time schedule'!FU60","v":0},{"$f":"'K20 - time schedule'!FV60","v":0},{"$f":"'K20 - time schedule'!FW60","v":0},{"$f":"'K20 - time schedule'!FX60","v":0},{"$f":"'K20 - time schedule'!FY60","v":0},{"$f":"'K20 - time schedule'!FZ60","v":0},{"$f":"'K20 - time schedule'!GA60","v":0},{"$f":"'K20 - time schedule'!GB60","v":0},{"$f":"'K20 - time schedule'!GC60","v":0},{"$f":"'K20 - time schedule'!GD60","v":0},{"$f":"'K20 - time schedule'!GE60","v":0},{"$f":"'K20 - time schedule'!GF60","v":0},{"$f":"'K20 - time schedule'!GG33","v":0},{"$f":"'K20 - time schedule'!GH33","v":0},{"$f":"'K20 - time schedule'!GI33","v":0},{"$f":"'K20 - time schedule'!GJ33","v":0},{"$f":"'K20 - time schedule'!GK33","v":0},{"$f":"'K20 - time schedule'!GL33","v":0},{"$f":"'K20 - time schedule'!GM33","v":0},{"$f":"'K20 - time schedule'!GN33","v":0},{"$f":"'K20 - time schedule'!GO33","v":0},{"$f":"'K20 - time schedule'!GP33","v":0},{"$f":"'K20 - time schedule'!GQ33","v":0},{"$f":"'K20 - time schedule'!GR33","v":0},{"$f":"'K20 - time schedule'!GS33","v":0},{"$f":"'K20 - time schedule'!GT33","v":0},{"$f":"'K20 - time schedule'!GU33","v":0},{"$f":"'K20 - time schedule'!GV33","v":0},{"$f":"'K20 - time schedule'!GW33","v":0},{"$f":"'K20 - time schedule'!GX33","v":0},{"$f":"'K20 - time schedule'!GY33","v":0},{"$f":"'K20 - time schedule'!GZ33","v":0},{"$f":"'K20 - time schedule'!HA33","v":0},{"$f":"'K20 - time schedule'!HB33","v":0},{"$f":"'K20 - time schedule'!HC33","v":0},{"$f":"'K20 - time schedule'!HD33","v":0},{"$f":"'K20 - time schedule'!HE33","v":0},{"$f":"'K20 - time schedule'!HF33","v":0},{"$f":"'K20 - time schedule'!HG33","v":0},{"$f":"'K20 - time schedule'!HH33","v":0},{"$f":"'K20 - time schedule'!HI33","v":0},{"$f":"'K20 - time schedule'!HJ33","v":0},{"$f":"'K20 - time schedule'!HK33","v":0},{"$f":"'K20 - time schedule'!HL33","v":0},{"$f":"'K20 - time schedule'!HM33","v":0},{"$f":"'K20 - time schedule'!HN33","v":0},{"$f":"'K20 - time schedule'!HO33","v":0},{"$f":"'K20 - time schedule'!HP33","v":0},{"$f":"'K20 - time schedule'!HQ33","v":0},{"$f":"'K20 - time schedule'!HR33","v":0},{"$f":"'K20 - time schedule'!HS33","v":0},{"$f":"'K20 - time schedule'!HT33","v":0},{"$f":"'K20 - time schedule'!HU33","v":0},{"$f":"'K20 - time schedule'!HV33","v":0},{"$f":"'K20 - time schedule'!HW33","v":0},{"$f":"'K20 - time schedule'!HX33","v":0},{"$f":"'K20 - time schedule'!HY33","v":0},{"$f":"'K20 - time schedule'!HZ33","v":0},{"$f":"'K20 - time schedule'!IA33","v":0},{"$f":"'K20 - time schedule'!IB33","v":0},{"$f":"'K20 - time schedule'!IC33","v":0},{"$f":"'K20 - time schedule'!ID33","v":0},{"$f":"'K20 - time schedule'!IE33","v":0},{"$f":"'K20 - time schedule'!IF33","v":0},{"$f":"'K20 - time schedule'!IG33","v":0},{"$f":"'K20 - time schedule'!IH33","v":0},{"$f":"'K20 - time schedule'!II33","v":0},{"$f":"'K20 - time schedule'!IJ33","v":0},{"$f":"'K20 - time schedule'!IK33","v":0},{"$f":"'K20 - time schedule'!IL33","v":0},{"$f":"'K20 - time schedule'!IM33","v":0},{"$f":"'K20 - time schedule'!IN33","v":0},{"$f":"'K20 - time schedule'!IO33","v":0},{"$f":"'K20 - time schedule'!IP33","v":0},{"$f":"'K20 - time schedule'!IQ33","v":0},{"$f":"'K20 - time schedule'!IR33","v":0},{"$f":"'K20 - time schedule'!IS33","v":0},{"$f":"'K20 - time schedule'!IT33","v":0},{"$f":"'K20 - time schedule'!IU33","v":0},{"$f":"'K20 - time schedule'!IV33","v":0},{"$f":"'K20 - time schedule'!IW33","v":0},{"$f":"'K20 - time schedule'!IX33","v":0},{"$f":"'K20 - time schedule'!IY33","v":0},{"$f":"'K20 - time schedule'!IZ33","v":0},{"$f":"'K20 - time schedule'!JA33","v":0},{"$f":"'K20 - time schedule'!JB33","v":0},{"$f":"'K20 - time schedule'!JC33","v":0},{"$f":"'K20 - time schedule'!JD33","v":0},{"$f":"'K20 - time schedule'!JE33","v":0},{"$f":"'K20 - time schedule'!JF33","v":0},{"$f":"'K20 - time schedule'!JG33","v":0},{"$f":"'K20 - time schedule'!JH33","v":0},{"$f":"'K20 - time schedule'!JI33","v":0},{"$f":"'K20 - time schedule'!JJ33","v":0},{"$f":"'K20 - time schedule'!JK33","v":0},{"$f":"'K20 - time schedule'!JL33","v":0},{"$f":"'K20 - time schedule'!JM33","v":0},{"$f":"'K20 - time schedule'!JN33","v":0},{"$f":"'K20 - time schedule'!JO33","v":0},{"$f":"'K20 - time schedule'!JP33","v":0},{"$f":"'K20 - time schedule'!JQ33","v":0},{"$f":"'K20 - time schedule'!JR33","v":0},{"$f":"'K20 - time schedule'!JS33","v":0},{"$f":"'K20 - time schedule'!JT33","v":0},{"$f":"'K20 - time schedule'!JU33","v":0},{"$f":"'K20 - time schedule'!JV33","v":0},{"$f":"'K20 - time schedule'!JW33","v":0},{"$f":"'K20 - time schedule'!JX33","v":0},{"$f":"'K20 - time schedule'!JY33","v":0},{"$f":"'K20 - time schedule'!JZ33","v":0},{"$f":"'K20 - time schedule'!KA33","v":0},{"$f":"'K20 - time schedule'!KB33","v":0},{"$f":"'K20 - time schedule'!KC33","v":0},{"$f":"'K20 - time schedule'!KD33","v":0},{"$f":"'K20 - time schedule'!KE33","v":0},{"$f":"'K20 - time schedule'!KF33","v":0},{"$f":"'K20 - time schedule'!KG33","v":0},{"$f":"'K20 - time schedule'!KH33","v":0},{"$f":"'K20 - time schedule'!KI33","v":0},{"$f":"'K20 - time schedule'!KJ33","v":0},{"$f":"'K20 - time schedule'!KK33","v":0},{"$f":"'K20 - time schedule'!KL33","v":0},{"$f":"'K20 - time schedule'!KM33","v":0},{"$f":"'K20 - time schedule'!KN33","v":0},{"$f":"'K20 - time schedule'!KO33","v":0},{"$f":"'K20 - time schedule'!KP33","v":0},{"$f":"'K20 - time schedule'!KQ33","v":0},{"$f":"'K20 - time schedule'!KR33","v":0},{"$f":"'K20 - time schedule'!KS33","v":0},{"$f":"'K20 - time schedule'!KT33","v":0}]
["Boiler room K20 - guarantee test B","K20","EUR",{"$f":"'K20 - time schedule'!G62","v":0},{"$f":"'K20 - time schedule'!H62","v":0},{"$f":"'K20 - time schedule'!I62","v":0},{"$f":"'K20 - time schedule'!J62","v":0},{"$f":"'K20 - time schedule'!K62","v":0},{"$f":"'K20 - time schedule'!L62","v":0},{"$f":"'K20 - time schedule'!M62","v":0},{"$f":"'K20 - time schedule'!N62","v":0},{"$f":"'K20 - time schedule'!O62","v":0},{"$f":"'K20 - time schedule'!P62","v":0},{"$f":"'K20 - time schedule'!Q62","v":0},{"$f":"'K20 - time schedule'!R62","v":0},{"$f":"'K20 - time schedule'!S62","v":0},{"$f":"'K20 - time schedule'!T62","v":0},{"$f":"'K20 - time schedule'!U62","v":0},{"$f":"'K20 - time schedule'!V62","v":0},{"$f":"'K20 - time schedule'!W62","v":0},{"$f":"'K20 - time schedule'!X62","v":0},{"$f":"'K20 - time schedule'!Y62","v":0},{"$f":"'K20 - time schedule'!Z62","v":0},{"$f":"'K20 - time schedule'!AA62","v":0},{"$f":"'K20 - time schedule'!AB62","v":0},{"$f":"'K20 - time schedule'!AC62","v":0},{"$f":"'K20 - time schedule'!AD62","v":0},{"$f":"'K20 - time schedule'!AE62","v":0},{"$f":"'K20 - time schedule'!AF62","v":0},{"$f":"'K20 - time schedule'!AG62","v":0},{"$f":"'K20 - time schedule'!AH62","v":0},{"$f":"'K20 - time schedule'!AI62","v":0},{"$f":"'K20 - time schedule'!AJ62","v":0},{"$f":"'K20 - time schedule'!AK62","v":0},{"$f":"'K20 - time schedule'!AL62","v":0},{"$f":"'K20 - time schedule'!AM62","v":0},{"$f":"'K20 - time schedule'!AN62","v":0},{"$f":"'K20 - time schedule'!AO62","v":0},{"$f":"'K20 - time schedule'!AP62","v":0},{"$f":"'K20 - time schedule'!AQ62","v":0},{"$f":"'K20 - time schedule'!AR62","v":0},{"$f":"'K20 - time schedule'!AS62","v":0},{"$f":"'K20 - time schedule'!AT62","v":0},{"$f":"'K20 - time schedule'!AU62","v":0},{"$f":"'K20 - time schedule'!AV62","v":0},{"$f":"'K20 - time schedule'!AW62","v":0},{"$f":"'K20 - time schedule'!AX62","v":0},{"$f":"'K20 - time schedule'!AY62","v":0},{"$f":"'K20 - time schedule'!AZ62","v":0},{"$f":"'K20 - time schedule'!BA62","v":0},{"$f":"'K20 - time schedule'!BB62","v":0},{"$f":"'K20 - time schedule'!BC62","v":0},{"$f":"'K20 - time schedule'!BD62","v":0},{"$f":"'K20 - time schedule'!BE62","v":0},{"$f":"'K20 - time schedule'!BF62","v":0},{"$f":"'K20 - time schedule'!BG62","v":0},{"$f":"'K20 - time schedule'!BH62","v":0},{"$f":"'K20 - time schedule'!BI62","v":0},{"$f":"'K20 - time schedule'!BJ62","v":0},{"$f":"'K20 - time schedule'!BK62","v":0},{"$f":"'K20 - time schedule'!BL62","v":0},{"$f":"'K20 - time schedule'!BM62","v":0},{"$f":"'K20 - time schedule'!BN62","v":0},{"$f":"'K20 - time schedule'!BO62","v":0},{"$f":"'K20 - time schedule'!BP62","v":0},{"$f":"'K20 - time schedule'!BQ62","v":0},{"$f":"'K20 - time schedule'!BR62","v":0},{"$f":"'K20 - time schedule'!BS62","v":0},{"$f":"'K20 - time schedule'!BT62","v":0},{"$f":"'K20 - time schedule'!BU62","v":0},{"$f":"'K20 - time schedule'!BV62","v":0},{"$f":"'K20 - time schedule'!BW62","v":0},{"$f":"'K20 - time schedule'!BX62","v":0},{"$f":"'K20 - time schedule'!BY62","v":0},{"$f":"'K20 - time schedule'!BZ62","v":0},{"$f":"'K20 - time schedule'!CA62","v":0},{"$f":"'K20 - time schedule'!CB62","v":0},{"$f":"'K20 - time schedule'!CC62","v":0},{"$f":"'K20 - time schedule'!CD62","v":0},{"$f":"'K20 - time schedule'!CE62","v":0},{"$f":"'K20 - time schedule'!CF62","v":0},{"$f":"'K20 - time schedule'!CG62","v":0},{"$f":"'K20 - time schedule'!CH62","v":0},{"$f":"'K20 - time schedule'!CI62","v":0},{"$f":"'K20 - time schedule'!CJ62","v":0},{"$f":"'K20 - time schedule'!CK62","v":0},{"$f":"'K20 - time schedule'!CL62","v":0},{"$f":"'K20 - time schedule'!CM62","v":0},{"$f":"'K20 - time schedule'!CN62","v":0},{"$f":"'K20 - time schedule'!CO62","v":0},{"$f":"'K20 - time schedule'!CP62","v":0},{"$f":"'K20 - time schedule'!CQ62","v":0},{"$f":"'K20 - time schedule'!CR62","v":0},{"$f":"'K20 - time schedule'!CS62","v":0},{"$f":"'K20 - time schedule'!CT62","v":0},{"$f":"'K20 - time schedule'!CU62","v":0},{"$f":"'K20 - time schedule'!CV62","v":0},{"$f":"'K20 - time schedule'!CW62","v":0},{"$f":"'K20 - time schedule'!CX62","v":0},{"$f":"'K20 - time schedule'!CY62","v":0},{"$f":"'K20 - time schedule'!CZ62","v":0},{"$f":"'K20 - time schedule'!DA62","v":0},{"$f":"'K20 - time schedule'!DB62","v":0},{"$f":"'K20 - time schedule'!DC62","v":0},{"$f":"'K20 - time schedule'!DD62","v":0},{"$f":"'K20 - time schedule'!DE62","v":0},{"$f":"'K20 - time schedule'!DF62","v":0},{"$f":"'K20 - time schedule'!DG62","v":0},{"$f":"'K20 - time schedule'!DH62","v":0},{"$f":"'K20 - time schedule'!DI62","v":0},{"$f":"'K20 - time schedule'!DJ62","v":0},{"$f":"'K20 - time schedule'!DK62","v":0},{"$f":"'K20 - time schedule'!DL62","v":0},{"$f":"'K20 - time schedule'!DM62","v":0},{"$f":"'K20 - time schedule'!DN62","v":0},{"$f":"'K20 - time schedule'!DO62","v":0},{"$f":"'K20 - time schedule'!DP62","v":0},{"$f":"'K20 - time schedule'!DQ62","v":0},{"$f":"'K20 - time schedule'!DR62","v":0},{"$f":"'K20 - time schedule'!DS62","v":0},{"$f":"'K20 - time schedule'!DT62","v":0},{"$f":"'K20 - time schedule'!DU62","v":0},{"$f":"'K20 - time schedule'!DV62","v":0},{"$f":"'K20 - time schedule'!DW62","v":0},{"$f":"'K20 - time schedule'!DX62","v":0},{"$f":"'K20 - time schedule'!DY62","v":0},{"$f":"'K20 - time schedule'!DZ62","v":0},{"$f":"'K20 - time schedule'!EA62","v":0},{"$f":"'K20 - time schedule'!EB62","v":0},{"$f":"'K20 - time schedule'!EC62","v":0},{"$f":"'K20 - time schedule'!ED62","v":0},{"$f":"'K20 - time schedule'!EE62","v":0},{"$f":"'K20 - time schedule'!EF62","v":0},{"$f":"'K20 - time schedule'!EG62","v":0},{"$f":"'K20 - time schedule'!EH62","v":0},{"$f":"'K20 - time schedule'!EI62","v":0},{"$f":"'K20 - time schedule'!EJ62","v":0},{"$f":"'K20 - time schedule'!EK62","v":0},{"$f":"'K20 - time schedule'!EL62","v":0},{"$f":"'K20 - time schedule'!EM62","v":0},{"$f":"'K20 - time schedule'!EN62","v":0},{"$f":"'K20 - time schedule'!EO62","v":0},{"$f":"'K20 - time schedule'!EP62","v":0},{"$f":"'K20 - time schedule'!EQ62","v":0},{"$f":"'K20 - time schedule'!ER62","v":0},{"$f":"'K20 - time schedule'!ES62","v":0},{"$f":"'K20 - time schedule'!ET62","v":0},{"$f":"'K20 - time schedule'!EU62","v":0},{"$f":"'K20 - time schedule'!EV62","v":0},{"$f":"'K20 - time schedule'!EW62","v":0},{"$f":"'K20 - time schedule'!EX62","v":0},{"$f":"'K20 - time schedule'!EY62","v":0},{"$f":"'K20 - time schedule'!EZ62","v":0},{"$f":"'K20 - time schedule'!FA62","v":0},{"$f":"'K20 - time schedule'!FB62","v":0},{"$f":"'K20 - time schedule'!FC62","v":0},{"$f":"'K20 - time schedule'!FD62","v":0},{"$f":"'K20 - time schedule'!FE62","v":0},{"$f":"'K20 - time schedule'!FF62","v":0},{"$f":"'K20 - time schedule'!FG62","v":0},{"$f":"'K20 - time schedule'!FH62","v":0},{"$f":"'K20 - time schedule'!FI62","v":0},{"$f":"'K20 - time schedule'!FJ62","v":0},{"$f":"'K20 - time schedule'!FK62","v":0},{"$f":"'K20 - time schedule'!FL62","v":0},{"$f":"'K20 - time schedule'!FM62","v":0},{"$f":"'K20 - time schedule'!FN62","v":0},{"$f":"'K20 - time schedule'!FO62","v":0},{"$f":"'K20 - time schedule'!FP62","v":0},{"$f":"'K20 - time schedule'!FQ62","v":0},{"$f":"'K20 - time schedule'!FR62","v":0},{"$f":"'K20 - time schedule'!FS62","v":0},{"$f":"'K20 - time schedule'!FT62","v":0},{"$f":"'K20 - time schedule'!FU62","v":0},{"$f":"'K20 - time schedule'!FV62","v":0},{"$f":"'K20 - time schedule'!FW62","v":0},{"$f":"'K20 - time schedule'!FX62","v":0},{"$f":"'K20 - time schedule'!FY62","v":0},{"$f":"'K20 - time schedule'!FZ62","v":0},{"$f":"'K20 - time schedule'!GA62","v":0},{"$f":"'K20 - time schedule'!GB62","v":0},{"$f":"'K20 - time schedule'!GC62","v":0},{"$f":"'K20 - time schedule'!GD62","v":0},{"$f":"'K20 - time schedule'!GE62","v":0},{"$f":"'K20 - time schedule'!GF62","v":0},{"$f":"'K20 - time schedule'!GG34","v":0},{"$f":"'K20 - time schedule'!GH34","v":0},{"$f":"'K20 - time schedule'!GI34","v":0},{"$f":"'K20 - time schedule'!GJ34","v":0},{"$f":"'K20 - time schedule'!GK34","v":0},{"$f":"'K20 - time schedule'!GL34","v":0},{"$f":"'K20 - time schedule'!GM34","v":0},{"$f":"'K20 - time schedule'!GN34","v":0},{"$f":"'K20 - time schedule'!GO34","v":0},{"$f":"'K20 - time schedule'!GP34","v":0},{"$f":"'K20 - time schedule'!GQ34","v":0},{"$f":"'K20 - time schedule'!GR34","v":0},{"$f":"'K20 - time schedule'!GS34","v":0},{"$f":"'K20 - time schedule'!GT34","v":0},{"$f":"'K20 - time schedule'!GU34","v":0},{"$f":"'K20 - time schedule'!GV34","v":0},{"$f":"'K20 - time schedule'!GW34","v":0},{"$f":"'K20 - time schedule'!GX34","v":0},{"$f":"'K20 - time schedule'!GY34","v":0},{"$f":"'K20 - time schedule'!GZ34","v":0},{"$f":"'K20 - time schedule'!HA34","v":0},{"$f":"'K20 - time schedule'!HB34","v":0},{"$f":"'K20 - time schedule'!HC34","v":0},{"$f":"'K20 - time schedule'!HD34","v":0},{"$f":"'K20 - time schedule'!HE34","v":0},{"$f":"'K20 - time schedule'!HF34","v":0},{"$f":"'K20 - time schedule'!HG34","v":0},{"$f":"'K20 - time schedule'!HH34","v":0},{"$f":"'K20 - time schedule'!HI34","v":0},{"$f":"'K20 - time schedule'!HJ34","v":0},{"$f":"'K20 - time schedule'!HK34","v":0},{"$f":"'K20 - time schedule'!HL34","v":0},{"$f":"'K20 - time schedule'!HM34","v":0},{"$f":"'K20 - time schedule'!HN34","v":0},{"$f":"'K20 - time schedule'!HO34","v":0},{"$f":"'K20 - time schedule'!HP34","v":0},{"$f":"'K20 - time schedule'!HQ34","v":0},{"$f":"'K20 - time schedule'!HR34","v":0},{"$f":"'K20 - time schedule'!HS34","v":0},{"$f":"'K20 - time schedule'!HT34","v":0},{"$f":"'K20 - time schedule'!HU34","v":0},{"$f":"'K20 - time schedule'!HV34","v":0},{"$f":"'K20 - time schedule'!HW34","v":0},{"$f":"'K20 - time schedule'!HX34","v":0},{"$f":"'K20 - time schedule'!HY34","v":0},{"$f":"'K20 - time schedule'!HZ34","v":0},{"$f":"'K20 - time schedule'!IA34","v":0},{"$f":"'K20 - time schedule'!IB34","v":0},{"$f":"'K20 - time schedule'!IC34","v":0},{"$f":"'K20 - time schedule'!ID34","v":0},{"$f":"'K20 - time schedule'!IE34","v":0},{"$f":"'K20 - time schedule'!IF34","v":0},{"$f":"'K20 - time schedule'!IG34","v":0},{"$f":"'K20 - time schedule'!IH34","v":0},{"$f":"'K20 - time schedule'!II34","v":0},{"$f":"'K20 - time schedule'!IJ34","v":0},{"$f":"'K20 - time schedule'!IK34","v":0},{"$f":"'K20 - time schedule'!IL34","v":0},{"$f":"'K20 - time schedule'!IM34","v":0},{"$f":"'K20 - time schedule'!IN34","v":0},{"$f":"'K20 - time schedule'!IO34","v":0},{"$f":"'K20 - time schedule'!IP34","v":0},{"$f":"'K20 - time schedule'!IQ34","v":0},{"$f":"'K20 - time schedule'!IR34","v":0},{"$f":"'K20 - time schedule'!IS34","v":0},{"$f":"'K20 - time schedule'!IT34","v":0},{"$f":"'K20 - time schedule'!IU34","v":0},{"$f":"'K20 - time schedule'!IV34","v":0},{"$f":"'K20 - time schedule'!IW34","v":0},{"$f":"'K20 - time schedule'!IX34","v":0},{"$f":"'K20 - time schedule'!IY34","v":0},{"$f":"'K20 - time schedule'!IZ34","v":0},{"$f":"'K20 - time schedule'!JA34","v":0},{"$f":"'K20 - time schedule'!JB34","v":0},{"$f":"'K20 - time schedule'!JC34","v":0},{"$f":"'K20 - time schedule'!JD34","v":0},{"$f":"'K20 - time schedule'!JE34","v":0},{"$f":"'K20 - time schedule'!JF34","v":0},{"$f":"'K20 - time schedule'!JG34","v":0},{"$f":"'K20 - time schedule'!JH34","v":0},{"$f":"'K20 - time schedule'!JI34","v":0},{"$f":"'K20 - time schedule'!JJ34","v":0},{"$f":"'K20 - time schedule'!JK34","v":0},{"$f":"'K20 - time schedule'!JL34","v":0},{"$f":"'K20 - time schedule'!JM34","v":0},{"$f":"'K20 - time schedule'!JN34","v":0},{"$f":"'K20 - time schedule'!JO34","v":0},{"$f":"'K20 - time schedule'!JP34","v":0},{"$f":"'K20 - time schedule'!JQ34","v":0},{"$f":"'K20 - time schedule'!JR34","v":0},{"$f":"'K20 - time schedule'!JS34","v":0},{"$f":"'K20 - time schedule'!JT34","v":0},{"$f":"'K20 - time schedule'!JU34","v":0},{"$f":"'K20 - time schedule'!JV34","v":0},{"$f":"'K20 - time schedule'!JW34","v":0},{"$f":"'K20 - time schedule'!JX34","v":0},{"$f":"'K20 - time schedule'!JY34","v":0},{"$f":"'K20 - time schedule'!JZ34","v":0},{"$f":"'K20 - time schedule'!KA34","v":0},{"$f":"'K20 - time schedule'!KB34","v":0},{"$f":"'K20 - time schedule'!KC34","v":0},{"$f":"'K20 - time schedule'!KD34","v":0},{"$f":"'K20 - time schedule'!KE34","v":0},{"$f":"'K20 - time schedule'!KF34","v":0},{"$f":"'K20 - time schedule'!KG34","v":0},{"$f":"'K20 - time schedule'!KH34","v":0},{"$f":"'K20 - time schedule'!KI34","v":0},{"$f":"'K20 - time schedule'!KJ34","v":0},{"$f":"'K20 - time schedule'!KK34","v":0},{"$f":"'K20 - time schedule'!KL34","v":0},{"$f":"'K20 - time schedule'!KM34","v":0},{"$f":"'K20 - time schedule'!KN34","v":0},{"$f":"'K20 - time schedule'!KO34","v":0},{"$f":"'K20 - time schedule'!KP34","v":0},{"$f":"'K20 - time schedule'!KQ34","v":0},{"$f":"'K20 - time schedule'!KR34","v":0},{"$f":"'K20 - time schedule'!KS34","v":0},{"$f":"'K20 - time schedule'!KT34","v":0}]
["Boiler room K20 - final acceptance of the Work FAC","K20","EUR",{"$f":"'K20 - time schedule'!G64","v":0},{"$f":"'K20 - time schedule'!H64","v":0},{"$f":"'K20 - time schedule'!I64","v":0},{"$f":"'K20 - time schedule'!J64","v":0},{"$f":"'K20 - time schedule'!K64","v":0},{"$f":"'K20 - time schedule'!L64","v":0},{"$f":"'K20 - time schedule'!M64","v":0},{"$f":"'K20 - time schedule'!N64","v":0},{"$f":"'K20 - time schedule'!O64","v":0},{"$f":"'K20 - time schedule'!P64","v":0},{"$f":"'K20 - time schedule'!Q64","v":0},{"$f":"'K20 - time schedule'!R64","v":0},{"$f":"'K20 - time schedule'!S64","v":0},{"$f":"'K20 - time schedule'!T64","v":0},{"$f":"'K20 - time schedule'!U64","v":0},{"$f":"'K20 - time schedule'!V64","v":0},{"$f":"'K20 - time schedule'!W64","v":0},{"$f":"'K20 - time schedule'!X64","v":0},{"$f":"'K20 - time schedule'!Y64","v":0},{"$f":"'K20 - time schedule'!Z64","v":0},{"$f":"'K20 - time schedule'!AA64","v":0},{"$f":"'K20 - time schedule'!AB64","v":0},{"$f":"'K20 - time schedule'!AC64","v":0},{"$f":"'K20 - time schedule'!AD64","v":0},{"$f":"'K20 - time schedule'!AE64","v":0},{"$f":"'K20 - time schedule'!AF64","v":0},{"$f":"'K20 - time schedule'!AG64","v":0},{"$f":"'K20 - time schedule'!AH64","v":0},{"$f":"'K20 - time schedule'!AI64","v":0},{"$f":"'K20 - time schedule'!AJ64","v":0},{"$f":"'K20 - time schedule'!AK64","v":0},{"$f":"'K20 - time schedule'!AL64","v":0},{"$f":"'K20 - time schedule'!AM64","v":0},{"$f":"'K20 - time schedule'!AN64","v":0},{"$f":"'K20 - time schedule'!AO64","v":0},{"$f":"'K20 - time schedule'!AP64","v":0},{"$f":"'K20 - time schedule'!AQ64","v":0},{"$f":"'K20 - time schedule'!AR64","v":0},{"$f":"'K20 - time schedule'!AS64","v":0},{"$f":"'K20 - time schedule'!AT64","v":0},{"$f":"'K20 - time schedule'!AU64","v":0},{"$f":"'K20 - time schedule'!AV64","v":0},{"$f":"'K20 - time schedule'!AW64","v":0},{"$f":"'K20 - time schedule'!AX64","v":0},{"$f":"'K20 - time schedule'!AY64","v":0},{"$f":"'K20 - time schedule'!AZ64","v":0},{"$f":"'K20 - time schedule'!BA64","v":0},{"$f":"'K20 - time schedule'!BB64","v":0},{"$f":"'K20 - time schedule'!BC64","v":0},{"$f":"'K20 - time schedule'!BD64","v":0},{"$f":"'K20 - time schedule'!BE64","v":0},{"$f":"'K20 - time schedule'!BF64","v":0},{"$f":"'K20 - time schedule'!BG64","v":0},{"$f":"'K20 - time schedule'!BH64","v":0},{"$f":"'K20 - time schedule'!BI64","v":0},{"$f":"'K20 - time schedule'!BJ64","v":0},{"$f":"'K20 - time schedule'!BK64","v":0},{"$f":"'K20 - time schedule'!BL64","v":0},{"$f":"'K20 - time schedule'!BM64","v":0},{"$f":"'K20 - time schedule'!BN64","v":0},{"$f":"'K20 - time schedule'!BO64","v":0},{"$f":"'K20 - time schedule'!BP64","v":0},{"$f":"'K20 - time schedule'!BQ64","v":0},{"$f":"'K20 - time schedule'!BR64","v":0},{"$f":"'K20 - time schedule'!BS64","v":0},{"$f":"'K20 - time schedule'!BT64","v":0},{"$f":"'K20 - time schedule'!BU64","v":0},{"$f":"'K20 - time schedule'!BV64","v":0},{"$f":"'K20 - time schedule'!BW64","v":0},{"$f":"'K20 - time schedule'!BX64","v":0},{"$f":"'K20 - time schedule'!BY64","v":0},{"$f":"'K20 - time schedule'!BZ64","v":0},{"$f":"'K20 - time schedule'!CA64","v":0},{"$f":"'K20 - time schedule'!CB64","v":0},{"$f":"'K20 - time schedule'!CC64","v":0},{"$f":"'K20 - time schedule'!CD64","v":0},{"$f":"'K20 - time schedule'!CE64","v":0},{"$f":"'K20 - time schedule'!CF64","v":0},{"$f":"'K20 - time schedule'!CG64","v":0},{"$f":"'K20 - time schedule'!CH64","v":0},{"$f":"'K20 - time schedule'!CI64","v":0},{"$f":"'K20 - time schedule'!CJ64","v":0},{"$f":"'K20 - time schedule'!CK64","v":0},{"$f":"'K20 - time schedule'!CL64","v":0},{"$f":"'K20 - time schedule'!CM64","v":0},{"$f":"'K20 - time schedule'!CN64","v":0},{"$f":"'K20 - time schedule'!CO64","v":0},{"$f":"'K20 - time schedule'!CP64","v":0},{"$f":"'K20 - time schedule'!CQ64","v":0},{"$f":"'K20 - time schedule'!CR64","v":0},{"$f":"'K20 - time schedule'!CS64","v":0},{"$f":"'K20 - time schedule'!CT64","v":0},{"$f":"'K20 - time schedule'!CU64","v":0},{"$f":"'K20 - time schedule'!CV64","v":0},{"$f":"'K20 - time schedule'!CW64","v":0},{"$f":"'K20 - time schedule'!CX64","v":0},{"$f":"'K20 - time schedule'!CY64","v":0},{"$f":"'K20 - time schedule'!CZ64","v":0},{"$f":"'K20 - time schedule'!DA64","v":0},{"$f":"'K20 - time schedule'!DB64","v":0},{"$f":"'K20 - time schedule'!DC64","v":0},{"$f":"'K20 - time schedule'!DD64","v":0},{"$f":"'K20 - time schedule'!DE64","v":0},{"$f":"'K20 - time schedule'!DF64","v":0},{"$f":"'K20 - time schedule'!DG64","v":0},{"$f":"'K20 - time schedule'!DH64","v":0},{"$f":"'K20 - time schedule'!DI64","v":0},{"$f":"'K20 - time schedule'!DJ64","v":0},{"$f":"'K20 - time schedule'!DK64","v":0},{"$f":"'K20 - time schedule'!DL64","v":0},{"$f":"'K20 - time schedule'!DM64","v":0},{"$f":"'K20 - time schedule'!DN64","v":0},{"$f":"'K20 - time schedule'!DO64","v":0},{"$f":"'K20 - time schedule'!DP64","v":0},{"$f":"'K20 - time schedule'!DQ64","v":0},{"$f":"'K20 - time schedule'!DR64","v":0},{"$f":"'K20 - time schedule'!DS64","v":0},{"$f":"'K20 - time schedule'!DT64","v":0},{"$f":"'K20 - time schedule'!DU64","v":0},{"$f":"'K20 - time schedule'!DV64","v":0},{"$f":"'K20 - time schedule'!DW64","v":0},{"$f":"'K20 - time schedule'!DX64","v":0},{"$f":"'K20 - time schedule'!DY64","v":0},{"$f":"'K20 - time schedule'!DZ64","v":0},{"$f":"'K20 - time schedule'!EA64","v":0},{"$f":"'K20 - time schedule'!EB64","v":0},{"$f":"'K20 - time schedule'!EC64","v":0},{"$f":"'K20 - time schedule'!ED64","v":0},{"$f":"'K20 - time schedule'!EE64","v":0},{"$f":"'K20 - time schedule'!EF64","v":0},{"$f":"'K20 - time schedule'!EG64","v":0},{"$f":"'K20 - time schedule'!EH64","v":0},{"$f":"'K20 - time schedule'!EI64","v":0},{"$f":"'K20 - time schedule'!EJ64","v":0},{"$f":"'K20 - time schedule'!EK64","v":0},{"$f":"'K20 - time schedule'!EL64","v":0},{"$f":"'K20 - time schedule'!EM64","v":0},{"$f":"'K20 - time schedule'!EN64","v":0},{"$f":"'K20 - time schedule'!EO64","v":0},{"$f":"'K20 - time schedule'!EP64","v":0},{"$f":"'K20 - time schedule'!EQ64","v":0},{"$f":"'K20 - time schedule'!ER64","v":0},{"$f":"'K20 - time schedule'!ES64","v":0},{"$f":"'K20 - time schedule'!ET64","v":0},{"$f":"'K20 - time schedule'!EU64","v":0},{"$f":"'K20 - time schedule'!EV64","v":0},{"$f":"'K20 - time schedule'!EW64","v":0},{"$f":"'K20 - time schedule'!EX64","v":0},{"$f":"'K20 - time schedule'!EY64","v":0},{"$f":"'K20 - time schedule'!EZ64","v":0},{"$f":"'K20 - time schedule'!FA64","v":0},{"$f":"'K20 - time schedule'!FB64","v":0},{"$f":"'K20 - time schedule'!FC64","v":0},{"$f":"'K20 - time schedule'!FD64","v":0},{"$f":"'K20 - time schedule'!FE64","v":0},{"$f":"'K20 - time schedule'!FF64","v":0},{"$f":"'K20 - time schedule'!FG64","v":0},{"$f":"'K20 - time schedule'!FH64","v":0},{"$f":"'K20 - time schedule'!FI64","v":0},{"$f":"'K20 - time schedule'!FJ64","v":0},{"$f":"'K20 - time schedule'!FK64","v":0},{"$f":"'K20 - time schedule'!FL64","v":0},{"$f":"'K20 - time schedule'!FM64","v":0},{"$f":"'K20 - time schedule'!FN64","v":0},{"$f":"'K20 - time schedule'!FO64","v":0},{"$f":"'K20 - time schedule'!FP64","v":0},{"$f":"'K20 - time schedule'!FQ64","v":0},{"$f":"'K20 - time schedule'!FR64","v":0},{"$f":"'K20 - time schedule'!FS64","v":0},{"$f":"'K20 - time schedule'!FT64","v":0},{"$f":"'K20 - time schedule'!FU64","v":0},{"$f":"'K20 - time schedule'!FV64","v":0},{"$f":"'K20 - time schedule'!FW64","v":0},{"$f":"'K20 - time schedule'!FX64","v":0},{"$f":"'K20 - time schedule'!FY64","v":0},{"$f":"'K20 - time schedule'!FZ64","v":0},{"$f":"'K20 - time schedule'!GA64","v":0},{"$f":"'K20 - time schedule'!GB64","v":0},{"$f":"'K20 - time schedule'!GC64","v":0},{"$f":"'K20 - time schedule'!GD64","v":0},{"$f":"'K20 - time schedule'!GE64","v":0},{"$f":"'K20 - time schedule'!GF64","v":0},{"$f":"'K20 - time schedule'!GG35","v":0},{"$f":"'K20 - time schedule'!GH35","v":0},{"$f":"'K20 - time schedule'!GI35","v":0},{"$f":"'K20 - time schedule'!GJ35","v":0},{"$f":"'K20 - time schedule'!GK35","v":0},{"$f":"'K20 - time schedule'!GL35","v":0},{"$f":"'K20 - time schedule'!GM35","v":0},{"$f":"'K20 - time schedule'!GN35","v":0},{"$f":"'K20 - time schedule'!GO35","v":0},{"$f":"'K20 - time schedule'!GP35","v":0},{"$f":"'K20 - time schedule'!GQ35","v":0},{"$f":"'K20 - time schedule'!GR35","v":0},{"$f":"'K20 - time schedule'!GS35","v":0},{"$f":"'K20 - time schedule'!GT35","v":0},{"$f":"'K20 - time schedule'!GU35","v":0},{"$f":"'K20 - time schedule'!GV35","v":0},{"$f":"'K20 - time schedule'!GW35","v":0},{"$f":"'K20 - time schedule'!GX35","v":0},{"$f":"'K20 - time schedule'!GY35","v":0},{"$f":"'K20 - time schedule'!GZ35","v":0},{"$f":"'K20 - time schedule'!HA35","v":0},{"$f":"'K20 - time schedule'!HB35","v":0},{"$f":"'K20 - time schedule'!HC35","v":0},{"$f":"'K20 - time schedule'!HD35","v":0},{"$f":"'K20 - time schedule'!HE35","v":0},{"$f":"'K20 - time schedule'!HF35","v":0},{"$f":"'K20 - time schedule'!HG35","v":0},{"$f":"'K20 - time schedule'!HH35","v":0},{"$f":"'K20 - time schedule'!HI35","v":0},{"$f":"'K20 - time schedule'!HJ35","v":0},{"$f":"'K20 - time schedule'!HK35","v":0},{"$f":"'K20 - time schedule'!HL35","v":0},{"$f":"'K20 - time schedule'!HM35","v":0},{"$f":"'K20 - time schedule'!HN35","v":0},{"$f":"'K20 - time schedule'!HO35","v":0},{"$f":"'K20 - time schedule'!HP35","v":0},{"$f":"'K20 - time schedule'!HQ35","v":0},{"$f":"'K20 - time schedule'!HR35","v":0},{"$f":"'K20 - time schedule'!HS35","v":0},{"$f":"'K20 - time schedule'!HT35","v":0},{"$f":"'K20 - time schedule'!HU35","v":0},{"$f":"'K20 - time schedule'!HV35","v":0},{"$f":"'K20 - time schedule'!HW35","v":0},{"$f":"'K20 - time schedule'!HX35","v":0},{"$f":"'K20 - time schedule'!HY35","v":0},{"$f":"'K20 - time schedule'!HZ35","v":0},{"$f":"'K20 - time schedule'!IA35","v":0},{"$f":"'K20 - time schedule'!IB35","v":0},{"$f":"'K20 - time schedule'!IC35","v":0},{"$f":"'K20 - time schedule'!ID35","v":0},{"$f":"'K20 - time schedule'!IE35","v":0},{"$f":"'K20 - time schedule'!IF35","v":0},{"$f":"'K20 - time schedule'!IG35","v":0},{"$f":"'K20 - time schedule'!IH35","v":0},{"$f":"'K20 - time schedule'!II35","v":0},{"$f":"'K20 - time schedule'!IJ35","v":0},{"$f":"'K20 - time schedule'!IK35","v":0},{"$f":"'K20 - time schedule'!IL35","v":0},{"$f":"'K20 - time schedule'!IM35","v":0},{"$f":"'K20 - time schedule'!IN35","v":0},{"$f":"'K20 - time schedule'!IO35","v":0},{"$f":"'K20 - time schedule'!IP35","v":0},{"$f":"'K20 - time schedule'!IQ35","v":0},{"$f":"'K20 - time schedule'!IR35","v":0},{"$f":"'K20 - time schedule'!IS35","v":0},{"$f":"'K20 - time schedule'!IT35","v":0},{"$f":"'K20 - time schedule'!IU35","v":0},{"$f":"'K20 - time schedule'!IV35","v":0},{"$f":"'K20 - time schedule'!IW35","v":0},{"$f":"'K20 - time schedule'!IX35","v":0},{"$f":"'K20 - time schedule'!IY35","v":0},{"$f":"'K20 - time schedule'!IZ35","v":0},{"$f":"'K20 - time schedule'!JA35","v":0},{"$f":"'K20 - time schedule'!JB35","v":0},{"$f":"'K20 - time schedule'!JC35","v":0},{"$f":"'K20 - time schedule'!JD35","v":0},{"$f":"'K20 - time schedule'!JE35","v":0},{"$f":"'K20 - time schedule'!JF35","v":0},{"$f":"'K20 - time schedule'!JG35","v":0},{"$f":"'K20 - time schedule'!JH35","v":0},{"$f":"'K20 - time schedule'!JI35","v":0},{"$f":"'K20 - time schedule'!JJ35","v":0},{"$f":"'K20 - time schedule'!JK35","v":0},{"$f":"'K20 - time schedule'!JL35","v":0},{"$f":"'K20 - time schedule'!JM35","v":0},{"$f":"'K20 - time schedule'!JN35","v":0},{"$f":"'K20 - time schedule'!JO35","v":0},{"$f":"'K20 - time schedule'!JP35","v":0},{"$f":"'K20 - time schedule'!JQ35","v":0},{"$f":"'K20 - time schedule'!JR35","v":0},{"$f":"'K20 - time schedule'!JS35","v":0},{"$f":"'K20 - time schedule'!JT35","v":0},{"$f":"'K20 - time schedule'!JU35","v":0},{"$f":"'K20 - time schedule'!JV35","v":0},{"$f":"'K20 - time schedule'!JW35","v":0},{"$f":"'K20 - time schedule'!JX35","v":0},{"$f":"'K20 - time schedule'!JY35","v":0},{"$f":"'K20 - time schedule'!JZ35","v":0},{"$f":"'K20 - time schedule'!KA35","v":0},{"$f":"'K20 - time schedule'!KB35","v":0},{"$f":"'K20 - time schedule'!KC35","v":0},{"$f":"'K20 - time schedule'!KD35","v":0},{"$f":"'K20 - time schedule'!KE35","v":0},{"$f":"'K20 - time schedule'!KF35","v":0},{"$f":"'K20 - time schedule'!KG35","v":0},{"$f":"'K20 - time schedule'!KH35","v":0},{"$f":"'K20 - time schedule'!KI35","v":0},{"$f":"'K20 - time schedule'!KJ35","v":0},{"$f":"'K20 - time schedule'!KK35","v":0},{"$f":"'K20 - time schedule'!KL35","v":0},{"$f":"'K20 - time schedule'!KM35","v":0},{"$f":"'K20 - time schedule'!KN35","v":0},{"$f":"'K20 - time schedule'!KO35","v":0},{"$f":"'K20 - time schedule'!KP35","v":0},{"$f":"'K20 - time schedule'!KQ35","v":0},{"$f":"'K20 - time schedule'!KR35","v":0},{"$f":"'K20 - time schedule'!KS35","v":0},{"$f":"'K20 - time schedule'!KT35","v":0}]
["Boiler room K80 - binding technical specification for OB 6 (Construction)","K80","EUR",{"$f":"'K80 - time schedule'!G11","v":0},{"$f":"'K80 - time schedule'!H11","v":0},{"$f":"'K80 - time schedule'!I11","v":0},{"$f":"'K80 - time schedule'!J11","v":0},{"$f":"'K80 - time schedule'!K11","v":0},{"$f":"'K80 - time schedule'!L11","v":0},{"$f":"'K80 - time schedule'!M11","v":0},{"$f":"'K80 - time schedule'!N11","v":0},{"$f":"'K80 - time schedule'!O11","v":0},{"$f":"'K80 - time schedule'!P11","v":0},{"$f":"'K80 - time schedule'!Q11","v":0},{"$f":"'K80 - time schedule'!R11","v":0},{"$f":"'K80 - time schedule'!S11","v":0},{"$f":"'K80 - time schedule'!T11","v":0},{"$f":"'K80 - time schedule'!U11","v":0},{"$f":"'K80 - time schedule'!V11","v":0},{"$f":"'K80 - time schedule'!W11","v":0},{"$f":"'K80 - time schedule'!X11","v":0},{"$f":"'K80 - time schedule'!Y11","v":0},{"$f":"'K80 - time schedule'!Z11","v":0},{"$f":"'K80 - time schedule'!AA11","v":0},{"$f":"'K80 - time schedule'!AB11","v":0},{"$f":"'K80 - time schedule'!AC11","v":0},{"$f":"'K80 - time schedule'!AD11","v":0},{"$f":"'K80 - time schedule'!AE11","v":0},{"$f":"'K80 - time schedule'!AF11","v":0},{"$f":"'K80 - time schedule'!AG11","v":0},{"$f":"'K80 - time schedule'!AH11","v":0},{"$f":"'K80 - time schedule'!AI11","v":0},{"$f":"'K80 - time schedule'!AJ11","v":0},{"$f":"'K80 - time schedule'!AK11","v":0},{"$f":"'K80 - time schedule'!AL11","v":0},{"$f":"'K80 - time schedule'!AM11","v":0},{"$f":"'K80 - time schedule'!AN11","v":0},{"$f":"'K80 - time schedule'!AO11","v":0},{"$f":"'K80 - time schedule'!AP11","v":0},{"$f":"'K80 - time schedule'!AQ11","v":0},{"$f":"'K80 - time schedule'!AR11","v":0},{"$f":"'K80 - time schedule'!AS11","v":0},{"$f":"'K80 - time schedule'!AT11","v":0},{"$f":"'K80 - time schedule'!AU11","v":0},{"$f":"'K80 - time schedule'!AV11","v":0},{"$f":"'K80 - time schedule'!AW11","v":0},{"$f":"'K80 - time schedule'!AX11","v":0},{"$f":"'K80 - time schedule'!AY11","v":0},{"$f":"'K80 - time schedule'!AZ11","v":0},{"$f":"'K80 - time schedule'!BA11","v":0},{"$f":"'K80 - time schedule'!BB11","v":0},{"$f":"'K80 - time schedule'!BC11","v":0},{"$f":"'K80 - time schedule'!BD11","v":0},{"$f":"'K80 - time schedule'!BE11","v":0},{"$f":"'K80 - time schedule'!BF11","v":0},{"$f":"'K80 - time schedule'!BG11","v":0},{"$f":"'K80 - time schedule'!BH11","v":0},{"$f":"'K80 - time schedule'!BI11","v":0},{"$f":"'K80 - time schedule'!BJ11","v":0},{"$f":"'K80 - time schedule'!BK11","v":0},{"$f":"'K80 - time schedule'!BL11","v":0},{"$f":"'K80 - time schedule'!BM11","v":0},{"$f":"'K80 - time schedule'!BN11","v":0},{"$f":"'K80 - time schedule'!BO11","v":0},{"$f":"'K80 - time schedule'!BP11","v":0},{"$f":"'K80 - time schedule'!BQ11","v":0},{"$f":"'K80 - time schedule'!BR11","v":0},{"$f":"'K80 - time schedule'!BS11","v":0},{"$f":"'K80 - time schedule'!BT11","v":0},{"$f":"'K80 - time schedule'!BU11","v":0},{"$f":"'K80 - time schedule'!BV11","v":0},{"$f":"'K80 - time schedule'!BW11","v":0},{"$f":"'K80 - time schedule'!BX11","v":0},{"$f":"'K80 - time schedule'!BY11","v":0},{"$f":"'K80 - time schedule'!BZ11","v":0},{"$f":"'K80 - time schedule'!CA11","v":0},{"$f":"'K80 - time schedule'!CB11","v":0},{"$f":"'K80 - time schedule'!CC11","v":0},{"$f":"'K80 - time schedule'!CD11","v":0},{"$f":"'K80 - time schedule'!CE11","v":0},{"$f":"'K80 - time schedule'!CF11","v":0},{"$f":"'K80 - time schedule'!CG11","v":0},{"$f":"'K80 - time schedule'!CH11","v":0},{"$f":"'K80 - time schedule'!CI11","v":0},{"$f":"'K80 - time schedule'!CJ11","v":0},{"$f":"'K80 - time schedule'!CK11","v":0},{"$f":"'K80 - time schedule'!CL11","v":0},{"$f":"'K80 - time schedule'!CM11","v":0},{"$f":"'K80 - time schedule'!CN11","v":0},{"$f":"'K80 - time schedule'!CO11","v":0},{"$f":"'K80 - time schedule'!CP11","v":0},{"$f":"'K80 - time schedule'!CQ11","v":0},{"$f":"'K80 - time schedule'!CR11","v":0},{"$f":"'K80 - time schedule'!CS11","v":0},{"$f":"'K80 - time schedule'!CT11","v":0},{"$f":"'K80 - time schedule'!CU11","v":0},{"$f":"'K80 - time schedule'!CV11","v":0},{"$f":"'K80 - time schedule'!CW11","v":0},{"$f":"'K80 - time schedule'!CX11","v":0},{"$f":"'K80 - time schedule'!CY11","v":0},{"$f":"'K80 - time schedule'!CZ11","v":0},{"$f":"'K80 - time schedule'!DA11","v":0},{"$f":"'K80 - time schedule'!DB11","v":0},{"$f":"'K80 - time schedule'!DC11","v":0},{"$f":"'K80 - time schedule'!DD11","v":0},{"$f":"'K80 - time schedule'!DE11","v":0},{"$f":"'K80 - time schedule'!DF11","v":0},{"$f":"'K80 - time schedule'!DG11","v":0},{"$f":"'K80 - time schedule'!DH11","v":0},{"$f":"'K80 - time schedule'!DI11","v":0},{"$f":"'K80 - time schedule'!DJ11","v":0},{"$f":"'K80 - time schedule'!DK11","v":0},{"$f":"'K80 - time schedule'!DL11","v":0},{"$f":"'K80 - time schedule'!DM11","v":0},{"$f":"'K80 - time schedule'!DN11","v":0},{"$f":"'K80 - time schedule'!DO11","v":0},{"$f":"'K80 - time schedule'!DP11","v":0},{"$f":"'K80 - time schedule'!DQ11","v":0},{"$f":"'K80 - time schedule'!DR11","v":0},{"$f":"'K80 - time schedule'!DS11","v":0},{"$f":"'K80 - time schedule'!DT11","v":0},{"$f":"'K80 - time schedule'!DU11","v":0},{"$f":"'K80 - time schedule'!DV11","v":0},{"$f":"'K80 - time schedule'!DW11","v":0},{"$f":"'K80 - time schedule'!DX11","v":0},{"$f":"'K80 - time schedule'!DY11","v":0},{"$f":"'K80 - time schedule'!DZ11","v":0},{"$f":"'K80 - time schedule'!EA11","v":0},{"$f":"'K80 - time schedule'!EB11","v":0},{"$f":"'K80 - time schedule'!EC11","v":0},{"$f":"'K80 - time schedule'!ED11","v":0},{"$f":"'K80 - time schedule'!EE11","v":0},{"$f":"'K80 - time schedule'!EF11","v":0},{"$f":"'K80 - time schedule'!EG11","v":0},{"$f":"'K80 - time schedule'!EH11","v":0},{"$f":"'K80 - time schedule'!EI11","v":0},{"$f":"'K80 - time schedule'!EJ11","v":0},{"$f":"'K80 - time schedule'!EK11","v":0},{"$f":"'K80 - time schedule'!EL11","v":0},{"$f":"'K80 - time schedule'!EM11","v":0},{"$f":"'K80 - time schedule'!EN11","v":0},{"$f":"'K80 - time schedule'!EO11","v":0},{"$f":"'K80 - time schedule'!EP11","v":0},{"$f":"'K80 - time schedule'!EQ11","v":0},{"$f":"'K80 - time schedule'!ER11","v":0},{"$f":"'K80 - time schedule'!ES11","v":0},{"$f":"'K80 - time schedule'!ET11","v":0},{"$f":"'K80 - time schedule'!EU11","v":0},{"$f":"'K80 - time schedule'!EV11","v":0},{"$f":"'K80 - time schedule'!EW11","v":0},{"$f":"'K80 - time schedule'!EX11","v":0},{"$f":"'K80 - time schedule'!EY11","v":0},{"$f":"'K80 - time schedule'!EZ11","v":0},{"$f":"'K80 - time schedule'!FA11","v":0},{"$f":"'K80 - time schedule'!FB11","v":0},{"$f":"'K80 - time schedule'!FC11","v":0},{"$f":"'K80 - time schedule'!FD11","v":0},{"$f":"'K80 - time schedule'!FE11","v":0},{"$f":"'K80 - time schedule'!FF11","v":0},{"$f":"'K80 - time schedule'!FG11","v":0},{"$f":"'K80 - time schedule'!FH11","v":0},{"$f":"'K80 - time schedule'!FI11","v":0},{"$f":"'K80 - time schedule'!FJ11","v":0},{"$f":"'K80 - time schedule'!FK11","v":0},{"$f":"'K80 - time schedule'!FL11","v":0},{"$f":"'K80 - time schedule'!FM11","v":0},{"$f":"'K80 - time schedule'!FN11","v":0},{"$f":"'K80 - time schedule'!FO11","v":0},{"$f":"'K80 - time schedule'!FP11","v":0},{"$f":"'K80 - time schedule'!FQ11","v":0},{"$f":"'K80 - time schedule'!FR11","v":0},{"$f":"'K80 - time schedule'!FS11","v":0},{"$f":"'K80 - time schedule'!FT11","v":0},{"$f":"'K80 - time schedule'!FU11","v":0},{"$f":"'K80 - time schedule'!FV11","v":0},{"$f":"'K80 - time schedule'!FW11","v":0},{"$f":"'K80 - time schedule'!FX11","v":0},{"$f":"'K80 - time schedule'!FY11","v":0},{"$f":"'K80 - time schedule'!FZ11","v":0},{"$f":"'K80 - time schedule'!GA11","v":0},{"$f":"'K80 - time schedule'!GB11","v":0},{"$f":"'K80 - time schedule'!GC11","v":0},{"$f":"'K80 - time schedule'!GD11","v":0},{"$f":"'K80 - time schedule'!GE11","v":0},{"$f":"'K80 - time schedule'!GF11","v":0},{"$f":"'K20 - time schedule'!GG36","v":0},{"$f":"'K20 - time schedule'!GH36","v":0},{"$f":"'K20 - time schedule'!GI36","v":0},{"$f":"'K20 - time schedule'!GJ36","v":0},{"$f":"'K20 - time schedule'!GK36","v":0},{"$f":"'K20 - time schedule'!GL36","v":0},{"$f":"'K20 - time schedule'!GM36","v":0},{"$f":"'K20 - time schedule'!GN36","v":0},{"$f":"'K20 - time schedule'!GO36","v":0},{"$f":"'K20 - time schedule'!GP36","v":0},{"$f":"'K20 - time schedule'!GQ36","v":0},{"$f":"'K20 - time schedule'!GR36","v":0},{"$f":"'K20 - time schedule'!GS36","v":0},{"$f":"'K20 - time schedule'!GT36","v":0},{"$f":"'K20 - time schedule'!GU36","v":0},{"$f":"'K20 - time schedule'!GV36","v":0},{"$f":"'K20 - time schedule'!GW36","v":0},{"$f":"'K20 - time schedule'!GX36","v":0},{"$f":"'K20 - time schedule'!GY36","v":0},{"$f":"'K20 - time schedule'!GZ36","v":0},{"$f":"'K20 - time schedule'!HA36","v":0},{"$f":"'K20 - time schedule'!HB36","v":0},{"$f":"'K20 - time schedule'!HC36","v":0},{"$f":"'K20 - time schedule'!HD36","v":0},{"$f":"'K20 - time schedule'!HE36","v":0},{"$f":"'K20 - time schedule'!HF36","v":0},{"$f":"'K20 - time schedule'!HG36","v":0},{"$f":"'K20 - time schedule'!HH36","v":0},{"$f":"'K20 - time schedule'!HI36","v":0},{"$f":"'K20 - time schedule'!HJ36","v":0},{"$f":"'K20 - time schedule'!HK36","v":0},{"$f":"'K20 - time schedule'!HL36","v":0},{"$f":"'K20 - time schedule'!HM36","v":0},{"$f":"'K20 - time schedule'!HN36","v":0},{"$f":"'K20 - time schedule'!HO36","v":0},{"$f":"'K20 - time schedule'!HP36","v":0},{"$f":"'K20 - time schedule'!HQ36","v":0},{"$f":"'K20 - time schedule'!HR36","v":0},{"$f":"'K20 - time schedule'!HS36","v":0},{"$f":"'K20 - time schedule'!HT36","v":0},{"$f":"'K20 - time schedule'!HU36","v":0},{"$f":"'K20 - time schedule'!HV36","v":0},{"$f":"'K20 - time schedule'!HW36","v":0},{"$f":"'K20 - time schedule'!HX36","v":0},{"$f":"'K20 - time schedule'!HY36","v":0},{"$f":"'K20 - time schedule'!HZ36","v":0},{"$f":"'K20 - time schedule'!IA36","v":0},{"$f":"'K20 - time schedule'!IB36","v":0},{"$f":"'K20 - time schedule'!IC36","v":0},{"$f":"'K20 - time schedule'!ID36","v":0},{"$f":"'K20 - time schedule'!IE36","v":0},{"$f":"'K20 - time schedule'!IF36","v":0},{"$f":"'K20 - time schedule'!IG36","v":0},{"$f":"'K20 - time schedule'!IH36","v":0},{"$f":"'K20 - time schedule'!II36","v":0},{"$f":"'K20 - time schedule'!IJ36","v":0},{"$f":"'K20 - time schedule'!IK36","v":0},{"$f":"'K20 - time schedule'!IL36","v":0},{"$f":"'K20 - time schedule'!IM36","v":0},{"$f":"'K20 - time schedule'!IN36","v":0},{"$f":"'K20 - time schedule'!IO36","v":0},{"$f":"'K20 - time schedule'!IP36","v":0},{"$f":"'K20 - time schedule'!IQ36","v":0},{"$f":"'K20 - time schedule'!IR36","v":0},{"$f":"'K20 - time schedule'!IS36","v":0},{"$f":"'K20 - time schedule'!IT36","v":0},{"$f":"'K20 - time schedule'!IU36","v":0},{"$f":"'K20 - time schedule'!IV36","v":0},{"$f":"'K20 - time schedule'!IW36","v":0},{"$f":"'K20 - time schedule'!IX36","v":0},{"$f":"'K20 - time schedule'!IY36","v":0},{"$f":"'K20 - time schedule'!IZ36","v":0},{"$f":"'K20 - time schedule'!JA36","v":0},{"$f":"'K20 - time schedule'!JB36","v":0},{"$f":"'K20 - time schedule'!JC36","v":0},{"$f":"'K20 - time schedule'!JD36","v":0},{"$f":"'K20 - time schedule'!JE36","v":0},{"$f":"'K20 - time schedule'!JF36","v":0},{"$f":"'K20 - time schedule'!JG36","v":0},{"$f":"'K20 - time schedule'!JH36","v":0},{"$f":"'K20 - time schedule'!JI36","v":0},{"$f":"'K20 - time schedule'!JJ36","v":0},{"$f":"'K20 - time schedule'!JK36","v":0},{"$f":"'K20 - time schedule'!JL36","v":0},{"$f":"'K20 - time schedule'!JM36","v":0},{"$f":"'K20 - time schedule'!JN36","v":0},{"$f":"'K20 - time schedule'!JO36","v":0},{"$f":"'K20 - time schedule'!JP36","v":0},{"$f":"'K20 - time schedule'!JQ36","v":0},{"$f":"'K20 - time schedule'!JR36","v":0},{"$f":"'K20 - time schedule'!JS36","v":0},{"$f":"'K20 - time schedule'!JT36","v":0},{"$f":"'K20 - time schedule'!JU36","v":0},{"$f":"'K20 - time schedule'!JV36","v":0},{"$f":"'K20 - time schedule'!JW36","v":0},{"$f":"'K20 - time schedule'!JX36","v":0},{"$f":"'K20 - time schedule'!JY36","v":0},{"$f":"'K20 - time schedule'!JZ36","v":0},{"$f":"'K20 - time schedule'!KA36","v":0},{"$f":"'K20 - time schedule'!KB36","v":0},{"$f":"'K20 - time schedule'!KC36","v":0},{"$f":"'K20 - time schedule'!KD36","v":0},{"$f":"'K20 - time schedule'!KE36","v":0},{"$f":"'K20 - time schedule'!KF36","v":0},{"$f":"'K20 - time schedule'!KG36","v":0},{"$f":"'K20 - time schedule'!KH36","v":0},{"$f":"'K20 - time schedule'!KI36","v":0},{"$f":"'K20 - time schedule'!KJ36","v":0},{"$f":"'K20 - time schedule'!KK36","v":0},{"$f":"'K20 - time schedule'!KL36","v":0},{"$f":"'K20 - time schedule'!KM36","v":0},{"$f":"'K20 - time schedule'!KN36","v":0},{"$f":"'K20 - time schedule'!KO36","v":0},{"$f":"'K20 - time schedule'!KP36","v":0},{"$f":"'K20 - time schedule'!KQ36","v":0},{"$f":"'K20 - time schedule'!KR36","v":0},{"$f":"'K20 - time schedule'!KS36","v":0},{"$f":"'K20 - time schedule'!KT36","v":0}]
["Boiler room K80 - binding technical specification for OB 1 (Fuel management) ","K80","EUR",{"$f":"'K80 - time schedule'!G13","v":0},{"$f":"'K80 - time schedule'!H13","v":0},{"$f":"'K80 - time schedule'!I13","v":0},{"$f":"'K80 - time schedule'!J13","v":0},{"$f":"'K80 - time schedule'!K13","v":0},{"$f":"'K80 - time schedule'!L13","v":0},{"$f":"'K80 - time schedule'!M13","v":0},{"$f":"'K80 - time schedule'!N13","v":0},{"$f":"'K80 - time schedule'!O13","v":0},{"$f":"'K80 - time schedule'!P13","v":0},{"$f":"'K80 - time schedule'!Q13","v":0},{"$f":"'K80 - time schedule'!R13","v":0},{"$f":"'K80 - time schedule'!S13","v":0},{"$f":"'K80 - time schedule'!T13","v":0},{"$f":"'K80 - time schedule'!U13","v":0},{"$f":"'K80 - time schedule'!V13","v":0},{"$f":"'K80 - time schedule'!W13","v":0},{"$f":"'K80 - time schedule'!X13","v":0},{"$f":"'K80 - time schedule'!Y13","v":0},{"$f":"'K80 - time schedule'!Z13","v":0},{"$f":"'K80 - time schedule'!AA13","v":0},{"$f":"'K80 - time schedule'!AB13","v":0},{"$f":"'K80 - time schedule'!AC13","v":0},{"$f":"'K80 - time schedule'!AD13","v":0},{"$f":"'K80 - time schedule'!AE13","v":0},{"$f":"'K80 - time schedule'!AF13","v":0},{"$f":"'K80 - time schedule'!AG13","v":0},{"$f":"'K80 - time schedule'!AH13","v":0},{"$f":"'K80 - time schedule'!AI13","v":0},{"$f":"'K80 - time schedule'!AJ13","v":0},{"$f":"'K80 - time schedule'!AK13","v":0},{"$f":"'K80 - time schedule'!AL13","v":0},{"$f":"'K80 - time schedule'!AM13","v":0},{"$f":"'K80 - time schedule'!AN13","v":0},{"$f":"'K80 - time schedule'!AO13","v":0},{"$f":"'K80 - time schedule'!AP13","v":0},{"$f":"'K80 - time schedule'!AQ13","v":0},{"$f":"'K80 - time schedule'!AR13","v":0},{"$f":"'K80 - time schedule'!AS13","v":0},{"$f":"'K80 - time schedule'!AT13","v":0},{"$f":"'K80 - time schedule'!AU13","v":0},{"$f":"'K80 - time schedule'!AV13","v":0},{"$f":"'K80 - time schedule'!AW13","v":0},{"$f":"'K80 - time schedule'!AX13","v":0},{"$f":"'K80 - time schedule'!AY13","v":0},{"$f":"'K80 - time schedule'!AZ13","v":0},{"$f":"'K80 - time schedule'!BA13","v":0},{"$f":"'K80 - time schedule'!BB13","v":0},{"$f":"'K80 - time schedule'!BC13","v":0},{"$f":"'K80 - time schedule'!BD13","v":0},{"$f":"'K80 - time schedule'!BE13","v":0},{"$f":"'K80 - time schedule'!BF13","v":0},{"$f":"'K80 - time schedule'!BG13","v":0},{"$f":"'K80 - time schedule'!BH13","v":0},{"$f":"'K80 - time schedule'!BI13","v":0},{"$f":"'K80 - time schedule'!BJ13","v":0},{"$f":"'K80 - time schedule'!BK13","v":0},{"$f":"'K80 - time schedule'!BL13","v":0},{"$f":"'K80 - time schedule'!BM13","v":0},{"$f":"'K80 - time schedule'!BN13","v":0},{"$f":"'K80 - time schedule'!BO13","v":0},{"$f":"'K80 - time schedule'!BP13","v":0},{"$f":"'K80 - time schedule'!BQ13","v":0},{"$f":"'K80 - time schedule'!BR13","v":0},{"$f":"'K80 - time schedule'!BS13","v":0},{"$f":"'K80 - time schedule'!BT13","v":0},{"$f":"'K80 - time schedule'!BU13","v":0},{"$f":"'K80 - time schedule'!BV13","v":0},{"$f":"'K80 - time schedule'!BW13","v":0},{"$f":"'K80 - time schedule'!BX13","v":0},{"$f":"'K80 - time schedule'!BY13","v":0},{"$f":"'K80 - time schedule'!BZ13","v":0},{"$f":"'K80 - time schedule'!CA13","v":0},{"$f":"'K80 - time schedule'!CB13","v":0},{"$f":"'K80 - time schedule'!CC13","v":0},{"$f":"'K80 - time schedule'!CD13","v":0},{"$f":"'K80 - time schedule'!CE13","v":0},{"$f":"'K80 - time schedule'!CF13","v":0},{"$f":"'K80 - time schedule'!CG13","v":0},{"$f":"'K80 - time schedule'!CH13","v":0},{"$f":"'K80 - time schedule'!CI13","v":0},{"$f":"'K80 - time schedule'!CJ13","v":0},{"$f":"'K80 - time schedule'!CK13","v":0},{"$f":"'K80 - time schedule'!CL13","v":0},{"$f":"'K80 - time schedule'!CM13","v":0},{"$f":"'K80 - time schedule'!CN13","v":0},{"$f":"'K80 - time schedule'!CO13","v":0},{"$f":"'K80 - time schedule'!CP13","v":0},{"$f":"'K80 - time schedule'!CQ13","v":0},{"$f":"'K80 - time schedule'!CR13","v":0},{"$f":"'K80 - time schedule'!CS13","v":0},{"$f":"'K80 - time schedule'!CT13","v":0},{"$f":"'K80 - time schedule'!CU13","v":0},{"$f":"'K80 - time schedule'!CV13","v":0},{"$f":"'K80 - time schedule'!CW13","v":0},{"$f":"'K80 - time schedule'!CX13","v":0},{"$f":"'K80 - time schedule'!CY13","v":0},{"$f":"'K80 - time schedule'!CZ13","v":0},{"$f":"'K80 - time schedule'!DA13","v":0},{"$f":"'K80 - time schedule'!DB13","v":0},{"$f":"'K80 - time schedule'!DC13","v":0},{"$f":"'K80 - time schedule'!DD13","v":0},{"$f":"'K80 - time schedule'!DE13","v":0},{"$f":"'K80 - time schedule'!DF13","v":0},{"$f":"'K80 - time schedule'!DG13","v":0},{"$f":"'K80 - time schedule'!DH13","v":0},{"$f":"'K80 - time schedule'!DI13","v":0},{"$f":"'K80 - time schedule'!DJ13","v":0},{"$f":"'K80 - time schedule'!DK13","v":0},{"$f":"'K80 - time schedule'!DL13","v":0},{"$f":"'K80 - time schedule'!DM13","v":0},{"$f":"'K80 - time schedule'!DN13","v":0},{"$f":"'K80 - time schedule'!DO13","v":0},{"$f":"'K80 - time schedule'!DP13","v":0},{"$f":"'K80 - time schedule'!DQ13","v":0},{"$f":"'K80 - time schedule'!DR13","v":0},{"$f":"'K80 - time schedule'!DS13","v":0},{"$f":"'K80 - time schedule'!DT13","v":0},{"$f":"'K80 - time schedule'!DU13","v":0},{"$f":"'K80 - time schedule'!DV13","v":0},{"$f":"'K80 - time schedule'!DW13","v":0},{"$f":"'K80 - time schedule'!DX13","v":0},{"$f":"'K80 - time schedule'!DY13","v":0},{"$f":"'K80 - time schedule'!DZ13","v":0},{"$f":"'K80 - time schedule'!EA13","v":0},{"$f":"'K80 - time schedule'!EB13","v":0},{"$f":"'K80 - time schedule'!EC13","v":0},{"$f":"'K80 - time schedule'!ED13","v":0},{"$f":"'K80 - time schedule'!EE13","v":0},{"$f":"'K80 - time schedule'!EF13","v":0},{"$f":"'K80 - time schedule'!EG13","v":0},{"$f":"'K80 - time schedule'!EH13","v":0},{"$f":"'K80 - time schedule'!EI13","v":0},{"$f":"'K80 - time schedule'!EJ13","v":0},{"$f":"'K80 - time schedule'!EK13","v":0},{"$f":"'K80 - time schedule'!EL13","v":0},{"$f":"'K80 - time schedule'!EM13","v":0},{"$f":"'K80 - time schedule'!EN13","v":0},{"$f":"'K80 - time schedule'!EO13","v":0},{"$f":"'K80 - time schedule'!EP13","v":0},{"$f":"'K80 - time schedule'!EQ13","v":0},{"$f":"'K80 - time schedule'!ER13","v":0},{"$f":"'K80 - time schedule'!ES13","v":0},{"$f":"'K80 - time schedule'!ET13","v":0},{"$f":"'K80 - time schedule'!EU13","v":0},{"$f":"'K80 - time schedule'!EV13","v":0},{"$f":"'K80 - time schedule'!EW13","v":0},{"$f":"'K80 - time schedule'!EX13","v":0},{"$f":"'K80 - time schedule'!EY13","v":0},{"$f":"'K80 - time schedule'!EZ13","v":0},{"$f":"'K80 - time schedule'!FA13","v":0},{"$f":"'K80 - time schedule'!FB13","v":0},{"$f":"'K80 - time schedule'!FC13","v":0},{"$f":"'K80 - time schedule'!FD13","v":0},{"$f":"'K80 - time schedule'!FE13","v":0},{"$f":"'K80 - time schedule'!FF13","v":0},{"$f":"'K80 - time schedule'!FG13","v":0},{"$f":"'K80 - time schedule'!FH13","v":0},{"$f":"'K80 - time schedule'!FI13","v":0},{"$f":"'K80 - time schedule'!FJ13","v":0},{"$f":"'K80 - time schedule'!FK13","v":0},{"$f":"'K80 - time schedule'!FL13","v":0},{"$f":"'K80 - time schedule'!FM13","v":0},{"$f":"'K80 - time schedule'!FN13","v":0},{"$f":"'K80 - time schedule'!FO13","v":0},{"$f":"'K80 - time schedule'!FP13","v":0},{"$f":"'K80 - time schedule'!FQ13","v":0},{"$f":"'K80 - time schedule'!FR13","v":0},{"$f":"'K80 - time schedule'!FS13","v":0},{"$f":"'K80 - time schedule'!FT13","v":0},{"$f":"'K80 - time schedule'!FU13","v":0},{"$f":"'K80 - time schedule'!FV13","v":0},{"$f":"'K80 - time schedule'!FW13","v":0},{"$f":"'K80 - time schedule'!FX13","v":0},{"$f":"'K80 - time schedule'!FY13","v":0},{"$f":"'K80 - time schedule'!FZ13","v":0},{"$f":"'K80 - time schedule'!GA13","v":0},{"$f":"'K80 - time schedule'!GB13","v":0},{"$f":"'K80 - time schedule'!GC13","v":0},{"$f":"'K80 - time schedule'!GD13","v":0},{"$f":"'K80 - time schedule'!GE13","v":0},{"$f":"'K80 - time schedule'!GF13","v":0},{"$f":"'K20 - time schedule'!GG37","v":0},{"$f":"'K20 - time schedule'!GH37","v":0},{"$f":"'K20 - time schedule'!GI37","v":0},{"$f":"'K20 - time schedule'!GJ37","v":0},{"$f":"'K20 - time schedule'!GK37","v":0},{"$f":"'K20 - time schedule'!GL37","v":0},{"$f":"'K20 - time schedule'!GM37","v":0},{"$f":"'K20 - time schedule'!GN37","v":0},{"$f":"'K20 - time schedule'!GO37","v":0},{"$f":"'K20 - time schedule'!GP37","v":0},{"$f":"'K20 - time schedule'!GQ37","v":0},{"$f":"'K20 - time schedule'!GR37","v":0},{"$f":"'K20 - time schedule'!GS37","v":0},{"$f":"'K20 - time schedule'!GT37","v":0},{"$f":"'K20 - time schedule'!GU37","v":0},{"$f":"'K20 - time schedule'!GV37","v":0},{"$f":"'K20 - time schedule'!GW37","v":0},{"$f":"'K20 - time schedule'!GX37","v":0},{"$f":"'K20 - time schedule'!GY37","v":0},{"$f":"'K20 - time schedule'!GZ37","v":0},{"$f":"'K20 - time schedule'!HA37","v":0},{"$f":"'K20 - time schedule'!HB37","v":0},{"$f":"'K20 - time schedule'!HC37","v":0},{"$f":"'K20 - time schedule'!HD37","v":0},{"$f":"'K20 - time schedule'!HE37","v":0},{"$f":"'K20 - time schedule'!HF37","v":0},{"$f":"'K20 - time schedule'!HG37","v":0},{"$f":"'K20 - time schedule'!HH37","v":0},{"$f":"'K20 - time schedule'!HI37","v":0},{"$f":"'K20 - time schedule'!HJ37","v":0},{"$f":"'K20 - time schedule'!HK37","v":0},{"$f":"'K20 - time schedule'!HL37","v":0},{"$f":"'K20 - time schedule'!HM37","v":0},{"$f":"'K20 - time schedule'!HN37","v":0},{"$f":"'K20 - time schedule'!HO37","v":0},{"$f":"'K20 - time schedule'!HP37","v":0},{"$f":"'K20 - time schedule'!HQ37","v":0},{"$f":"'K20 - time schedule'!HR37","v":0},{"$f":"'K20 - time schedule'!HS37","v":0},{"$f":"'K20 - time schedule'!HT37","v":0},{"$f":"'K20 - time schedule'!HU37","v":0},{"$f":"'K20 - time schedule'!HV37","v":0},{"$f":"'K20 - time schedule'!HW37","v":0},{"$f":"'K20 - time schedule'!HX37","v":0},{"$f":"'K20 - time schedule'!HY37","v":0},{"$f":"'K20 - time schedule'!HZ37","v":0},{"$f":"'K20 - time schedule'!IA37","v":0},{"$f":"'K20 - time schedule'!IB37","v":0},{"$f":"'K20 - time schedule'!IC37","v":0},{"$f":"'K20 - time schedule'!ID37","v":0},{"$f":"'K20 - time schedule'!IE37","v":0},{"$f":"'K20 - time schedule'!IF37","v":0},{"$f":"'K20 - time schedule'!IG37","v":0},{"$f":"'K20 - time schedule'!IH37","v":0},{"$f":"'K20 - time schedule'!II37","v":0},{"$f":"'K20 - time schedule'!IJ37","v":0},{"$f":"'K20 - time schedule'!IK37","v":0},{"$f":"'K20 - time schedule'!IL37","v":0},{"$f":"'K20 - time schedule'!IM37","v":0},{"$f":"'K20 - time schedule'!IN37","v":0},{"$f":"'K20 - time schedule'!IO37","v":0},{"$f":"'K20 - time schedule'!IP37","v":0},{"$f":"'K20 - time schedule'!IQ37","v":0},{"$f":"'K20 - time schedule'!IR37","v":0},{"$f":"'K20 - time schedule'!IS37","v":0},{"$f":"'K20 - time schedule'!IT37","v":0},{"$f":"'K20 - time schedule'!IU37","v":0},{"$f":"'K20 - time schedule'!IV37","v":0},{"$f":"'K20 - time schedule'!IW37","v":0},{"$f":"'K20 - time schedule'!IX37","v":0},{"$f":"'K20 - time schedule'!IY37","v":0},{"$f":"'K20 - time schedule'!IZ37","v":0},{"$f":"'K20 - time schedule'!JA37","v":0},{"$f":"'K20 - time schedule'!JB37","v":0},{"$f":"'K20 - time schedule'!JC37","v":0},{"$f":"'K20 - time schedule'!JD37","v":0},{"$f":"'K20 - time schedule'!JE37","v":0},{"$f":"'K20 - time schedule'!JF37","v":0},{"$f":"'K20 - time schedule'!JG37","v":0},{"$f":"'K20 - time schedule'!JH37","v":0},{"$f":"'K20 - time schedule'!JI37","v":0},{"$f":"'K20 - time schedule'!JJ37","v":0},{"$f":"'K20 - time schedule'!JK37","v":0},{"$f":"'K20 - time schedule'!JL37","v":0},{"$f":"'K20 - time schedule'!JM37","v":0},{"$f":"'K20 - time schedule'!JN37","v":0},{"$f":"'K20 - time schedule'!JO37","v":0},{"$f":"'K20 - time schedule'!JP37","v":0},{"$f":"'K20 - time schedule'!JQ37","v":0},{"$f":"'K20 - time schedule'!JR37","v":0},{"$f":"'K20 - time schedule'!JS37","v":0},{"$f":"'K20 - time schedule'!JT37","v":0},{"$f":"'K20 - time schedule'!JU37","v":0},{"$f":"'K20 - time schedule'!JV37","v":0},{"$f":"'K20 - time schedule'!JW37","v":0},{"$f":"'K20 - time schedule'!JX37","v":0},{"$f":"'K20 - time schedule'!JY37","v":0},{"$f":"'K20 - time schedule'!JZ37","v":0},{"$f":"'K20 - time schedule'!KA37","v":0},{"$f":"'K20 - time schedule'!KB37","v":0},{"$f":"'K20 - time schedule'!KC37","v":0},{"$f":"'K20 - time schedule'!KD37","v":0},{"$f":"'K20 - time schedule'!KE37","v":0},{"$f":"'K20 - time schedule'!KF37","v":0},{"$f":"'K20 - time schedule'!KG37","v":0},{"$f":"'K20 - time schedule'!KH37","v":0},{"$f":"'K20 - time schedule'!KI37","v":0},{"$f":"'K20 - time schedule'!KJ37","v":0},{"$f":"'K20 - time schedule'!KK37","v":0},{"$f":"'K20 - time schedule'!KL37","v":0},{"$f":"'K20 - time schedule'!KM37","v":0},{"$f":"'K20 - time schedule'!KN37","v":0},{"$f":"'K20 - time schedule'!KO37","v":0},{"$f":"'K20 - time schedule'!KP37","v":0},{"$f":"'K20 - time schedule'!KQ37","v":0},{"$f":"'K20 - time schedule'!KR37","v":0},{"$f":"'K20 - time schedule'!KS37","v":0},{"$f":"'K20 - time schedule'!KT37","v":0}]
["Boiler room K80 - binding technical specification for other OBs, for other suppliers of technological units ","K80","EUR",{"$f":"'K80 - time schedule'!G15","v":0},{"$f":"'K80 - time schedule'!H15","v":0},{"$f":"'K80 - time schedule'!I15","v":0},{"$f":"'K80 - time schedule'!J15","v":0},{"$f":"'K80 - time schedule'!K15","v":0},{"$f":"'K80 - time schedule'!L15","v":0},{"$f":"'K80 - time schedule'!M15","v":0},{"$f":"'K80 - time schedule'!N15","v":0},{"$f":"'K80 - time schedule'!O15","v":0},{"$f":"'K80 - time schedule'!P15","v":0},{"$f":"'K80 - time schedule'!Q15","v":0},{"$f":"'K80 - time schedule'!R15","v":0},{"$f":"'K80 - time schedule'!S15","v":0},{"$f":"'K80 - time schedule'!T15","v":0},{"$f":"'K80 - time schedule'!U15","v":0},{"$f":"'K80 - time schedule'!V15","v":0},{"$f":"'K80 - time schedule'!W15","v":0},{"$f":"'K80 - time schedule'!X15","v":0},{"$f":"'K80 - time schedule'!Y15","v":0},{"$f":"'K80 - time schedule'!Z15","v":0},{"$f":"'K80 - time schedule'!AA15","v":0},{"$f":"'K80 - time schedule'!AB15","v":0},{"$f":"'K80 - time schedule'!AC15","v":0},{"$f":"'K80 - time schedule'!AD15","v":0},{"$f":"'K80 - time schedule'!AE15","v":0},{"$f":"'K80 - time schedule'!AF15","v":0},{"$f":"'K80 - time schedule'!AG15","v":0},{"$f":"'K80 - time schedule'!AH15","v":0},{"$f":"'K80 - time schedule'!AI15","v":0},{"$f":"'K80 - time schedule'!AJ15","v":0},{"$f":"'K80 - time schedule'!AK15","v":0},{"$f":"'K80 - time schedule'!AL15","v":0},{"$f":"'K80 - time schedule'!AM15","v":0},{"$f":"'K80 - time schedule'!AN15","v":0},{"$f":"'K80 - time schedule'!AO15","v":0},{"$f":"'K80 - time schedule'!AP15","v":0},{"$f":"'K80 - time schedule'!AQ15","v":0},{"$f":"'K80 - time schedule'!AR15","v":0},{"$f":"'K80 - time schedule'!AS15","v":0},{"$f":"'K80 - time schedule'!AT15","v":0},{"$f":"'K80 - time schedule'!AU15","v":0},{"$f":"'K80 - time schedule'!AV15","v":0},{"$f":"'K80 - time schedule'!AW15","v":0},{"$f":"'K80 - time schedule'!AX15","v":0},{"$f":"'K80 - time schedule'!AY15","v":0},{"$f":"'K80 - time schedule'!AZ15","v":0},{"$f":"'K80 - time schedule'!BA15","v":0},{"$f":"'K80 - time schedule'!BB15","v":0},{"$f":"'K80 - time schedule'!BC15","v":0},{"$f":"'K80 - time schedule'!BD15","v":0},{"$f":"'K80 - time schedule'!BE15","v":0},{"$f":"'K80 - time schedule'!BF15","v":0},{"$f":"'K80 - time schedule'!BG15","v":0},{"$f":"'K80 - time schedule'!BH15","v":0},{"$f":"'K80 - time schedule'!BI15","v":0},{"$f":"'K80 - time schedule'!BJ15","v":0},{"$f":"'K80 - time schedule'!BK15","v":0},{"$f":"'K80 - time schedule'!BL15","v":0},{"$f":"'K80 - time schedule'!BM15","v":0},{"$f":"'K80 - time schedule'!BN15","v":0},{"$f":"'K80 - time schedule'!BO15","v":0},{"$f":"'K80 - time schedule'!BP15","v":0},{"$f":"'K80 - time schedule'!BQ15","v":0},{"$f":"'K80 - time schedule'!BR15","v":0},{"$f":"'K80 - time schedule'!BS15","v":0},{"$f":"'K80 - time schedule'!BT15","v":0},{"$f":"'K80 - time schedule'!BU15","v":0},{"$f":"'K80 - time schedule'!BV15","v":0},{"$f":"'K80 - time schedule'!BW15","v":0},{"$f":"'K80 - time schedule'!BX15","v":0},{"$f":"'K80 - time schedule'!BY15","v":0},{"$f":"'K80 - time schedule'!BZ15","v":0},{"$f":"'K80 - time schedule'!CA15","v":0},{"$f":"'K80 - time schedule'!CB15","v":0},{"$f":"'K80 - time schedule'!CC15","v":0},{"$f":"'K80 - time schedule'!CD15","v":0},{"$f":"'K80 - time schedule'!CE15","v":0},{"$f":"'K80 - time schedule'!CF15","v":0},{"$f":"'K80 - time schedule'!CG15","v":0},{"$f":"'K80 - time schedule'!CH15","v":0},{"$f":"'K80 - time schedule'!CI15","v":0},{"$f":"'K80 - time schedule'!CJ15","v":0},{"$f":"'K80 - time schedule'!CK15","v":0},{"$f":"'K80 - time schedule'!CL15","v":0},{"$f":"'K80 - time schedule'!CM15","v":0},{"$f":"'K80 - time schedule'!CN15","v":0},{"$f":"'K80 - time schedule'!CO15","v":0},{"$f":"'K80 - time schedule'!CP15","v":0},{"$f":"'K80 - time schedule'!CQ15","v":0},{"$f":"'K80 - time schedule'!CR15","v":0},{"$f":"'K80 - time schedule'!CS15","v":0},{"$f":"'K80 - time schedule'!CT15","v":0},{"$f":"'K80 - time schedule'!CU15","v":0},{"$f":"'K80 - time schedule'!CV15","v":0},{"$f":"'K80 - time schedule'!CW15","v":0},{"$f":"'K80 - time schedule'!CX15","v":0},{"$f":"'K80 - time schedule'!CY15","v":0},{"$f":"'K80 - time schedule'!CZ15","v":0},{"$f":"'K80 - time schedule'!DA15","v":0},{"$f":"'K80 - time schedule'!DB15","v":0},{"$f":"'K80 - time schedule'!DC15","v":0},{"$f":"'K80 - time schedule'!DD15","v":0},{"$f":"'K80 - time schedule'!DE15","v":0},{"$f":"'K80 - time schedule'!DF15","v":0},{"$f":"'K80 - time schedule'!DG15","v":0},{"$f":"'K80 - time schedule'!DH15","v":0},{"$f":"'K80 - time schedule'!DI15","v":0},{"$f":"'K80 - time schedule'!DJ15","v":0},{"$f":"'K80 - time schedule'!DK15","v":0},{"$f":"'K80 - time schedule'!DL15","v":0},{"$f":"'K80 - time schedule'!DM15","v":0},{"$f":"'K80 - time schedule'!DN15","v":0},{"$f":"'K80 - time schedule'!DO15","v":0},{"$f":"'K80 - time schedule'!DP15","v":0},{"$f":"'K80 - time schedule'!DQ15","v":0},{"$f":"'K80 - time schedule'!DR15","v":0},{"$f":"'K80 - time schedule'!DS15","v":0},{"$f":"'K80 - time schedule'!DT15","v":0},{"$f":"'K80 - time schedule'!DU15","v":0},{"$f":"'K80 - time schedule'!DV15","v":0},{"$f":"'K80 - time schedule'!DW15","v":0},{"$f":"'K80 - time schedule'!DX15","v":0},{"$f":"'K80 - time schedule'!DY15","v":0},{"$f":"'K80 - time schedule'!DZ15","v":0},{"$f":"'K80 - time schedule'!EA15","v":0},{"$f":"'K80 - time schedule'!EB15","v":0},{"$f":"'K80 - time schedule'!EC15","v":0},{"$f":"'K80 - time schedule'!ED15","v":0},{"$f":"'K80 - time schedule'!EE15","v":0},{"$f":"'K80 - time schedule'!EF15","v":0},{"$f":"'K80 - time schedule'!EG15","v":0},{"$f":"'K80 - time schedule'!EH15","v":0},{"$f":"'K80 - time schedule'!EI15","v":0},{"$f":"'K80 - time schedule'!EJ15","v":0},{"$f":"'K80 - time schedule'!EK15","v":0},{"$f":"'K80 - time schedule'!EL15","v":0},{"$f":"'K80 - time schedule'!EM15","v":0},{"$f":"'K80 - time schedule'!EN15","v":0},{"$f":"'K80 - time schedule'!EO15","v":0},{"$f":"'K80 - time schedule'!EP15","v":0},{"$f":"'K80 - time schedule'!EQ15","v":0},{"$f":"'K80 - time schedule'!ER15","v":0},{"$f":"'K80 - time schedule'!ES15","v":0},{"$f":"'K80 - time schedule'!ET15","v":0},{"$f":"'K80 - time schedule'!EU15","v":0},{"$f":"'K80 - time schedule'!EV15","v":0},{"$f":"'K80 - time schedule'!EW15","v":0},{"$f":"'K80 - time schedule'!EX15","v":0},{"$f":"'K80 - time schedule'!EY15","v":0},{"$f":"'K80 - time schedule'!EZ15","v":0},{"$f":"'K80 - time schedule'!FA15","v":0},{"$f":"'K80 - time schedule'!FB15","v":0},{"$f":"'K80 - time schedule'!FC15","v":0},{"$f":"'K80 - time schedule'!FD15","v":0},{"$f":"'K80 - time schedule'!FE15","v":0},{"$f":"'K80 - time schedule'!FF15","v":0},{"$f":"'K80 - time schedule'!FG15","v":0},{"$f":"'K80 - time schedule'!FH15","v":0},{"$f":"'K80 - time schedule'!FI15","v":0},{"$f":"'K80 - time schedule'!FJ15","v":0},{"$f":"'K80 - time schedule'!FK15","v":0},{"$f":"'K80 - time schedule'!FL15","v":0},{"$f":"'K80 - time schedule'!FM15","v":0},{"$f":"'K80 - time schedule'!FN15","v":0},{"$f":"'K80 - time schedule'!FO15","v":0},{"$f":"'K80 - time schedule'!FP15","v":0},{"$f":"'K80 - time schedule'!FQ15","v":0},{"$f":"'K80 - time schedule'!FR15","v":0},{"$f":"'K80 - time schedule'!FS15","v":0},{"$f":"'K80 - time schedule'!FT15","v":0},{"$f":"'K80 - time schedule'!FU15","v":0},{"$f":"'K80 - time schedule'!FV15","v":0},{"$f":"'K80 - time schedule'!FW15","v":0},{"$f":"'K80 - time schedule'!FX15","v":0},{"$f":"'K80 - time schedule'!FY15","v":0},{"$f":"'K80 - time schedule'!FZ15","v":0},{"$f":"'K80 - time schedule'!GA15","v":0},{"$f":"'K80 - time schedule'!GB15","v":0},{"$f":"'K80 - time schedule'!GC15","v":0},{"$f":"'K80 - time schedule'!GD15","v":0},{"$f":"'K80 - time schedule'!GE15","v":0},{"$f":"'K80 - time schedule'!GF15","v":0},{"$f":"'K20 - time schedule'!GG38","v":0},{"$f":"'K20 - time schedule'!GH38","v":0},{"$f":"'K20 - time schedule'!GI38","v":0},{"$f":"'K20 - time schedule'!GJ38","v":0},{"$f":"'K20 - time schedule'!GK38","v":0},{"$f":"'K20 - time schedule'!GL38","v":0},{"$f":"'K20 - time schedule'!GM38","v":0},{"$f":"'K20 - time schedule'!GN38","v":0},{"$f":"'K20 - time schedule'!GO38","v":0},{"$f":"'K20 - time schedule'!GP38","v":0},{"$f":"'K20 - time schedule'!GQ38","v":0},{"$f":"'K20 - time schedule'!GR38","v":0},{"$f":"'K20 - time schedule'!GS38","v":0},{"$f":"'K20 - time schedule'!GT38","v":0},{"$f":"'K20 - time schedule'!GU38","v":0},{"$f":"'K20 - time schedule'!GV38","v":0},{"$f":"'K20 - time schedule'!GW38","v":0},{"$f":"'K20 - time schedule'!GX38","v":0},{"$f":"'K20 - time schedule'!GY38","v":0},{"$f":"'K20 - time schedule'!GZ38","v":0},{"$f":"'K20 - time schedule'!HA38","v":0},{"$f":"'K20 - time schedule'!HB38","v":0},{"$f":"'K20 - time schedule'!HC38","v":0},{"$f":"'K20 - time schedule'!HD38","v":0},{"$f":"'K20 - time schedule'!HE38","v":0},{"$f":"'K20 - time schedule'!HF38","v":0},{"$f":"'K20 - time schedule'!HG38","v":0},{"$f":"'K20 - time schedule'!HH38","v":0},{"$f":"'K20 - time schedule'!HI38","v":0},{"$f":"'K20 - time schedule'!HJ38","v":0},{"$f":"'K20 - time schedule'!HK38","v":0},{"$f":"'K20 - time schedule'!HL38","v":0},{"$f":"'K20 - time schedule'!HM38","v":0},{"$f":"'K20 - time schedule'!HN38","v":0},{"$f":"'K20 - time schedule'!HO38","v":0},{"$f":"'K20 - time schedule'!HP38","v":0},{"$f":"'K20 - time schedule'!HQ38","v":0},{"$f":"'K20 - time schedule'!HR38","v":0},{"$f":"'K20 - time schedule'!HS38","v":0},{"$f":"'K20 - time schedule'!HT38","v":0},{"$f":"'K20 - time schedule'!HU38","v":0},{"$f":"'K20 - time schedule'!HV38","v":0},{"$f":"'K20 - time schedule'!HW38","v":0},{"$f":"'K20 - time schedule'!HX38","v":0},{"$f":"'K20 - time schedule'!HY38","v":0},{"$f":"'K20 - time schedule'!HZ38","v":0},{"$f":"'K20 - time schedule'!IA38","v":0},{"$f":"'K20 - time schedule'!IB38","v":0},{"$f":"'K20 - time schedule'!IC38","v":0},{"$f":"'K20 - time schedule'!ID38","v":0},{"$f":"'K20 - time schedule'!IE38","v":0},{"$f":"'K20 - time schedule'!IF38","v":0},{"$f":"'K20 - time schedule'!IG38","v":0},{"$f":"'K20 - time schedule'!IH38","v":0},{"$f":"'K20 - time schedule'!II38","v":0},{"$f":"'K20 - time schedule'!IJ38","v":0},{"$f":"'K20 - time schedule'!IK38","v":0},{"$f":"'K20 - time schedule'!IL38","v":0},{"$f":"'K20 - time schedule'!IM38","v":0},{"$f":"'K20 - time schedule'!IN38","v":0},{"$f":"'K20 - time schedule'!IO38","v":0},{"$f":"'K20 - time schedule'!IP38","v":0},{"$f":"'K20 - time schedule'!IQ38","v":0},{"$f":"'K20 - time schedule'!IR38","v":0},{"$f":"'K20 - time schedule'!IS38","v":0},{"$f":"'K20 - time schedule'!IT38","v":0},{"$f":"'K20 - time schedule'!IU38","v":0},{"$f":"'K20 - time schedule'!IV38","v":0},{"$f":"'K20 - time schedule'!IW38","v":0},{"$f":"'K20 - time schedule'!IX38","v":0},{"$f":"'K20 - time schedule'!IY38","v":0},{"$f":"'K20 - time schedule'!IZ38","v":0},{"$f":"'K20 - time schedule'!JA38","v":0},{"$f":"'K20 - time schedule'!JB38","v":0},{"$f":"'K20 - time schedule'!JC38","v":0},{"$f":"'K20 - time schedule'!JD38","v":0},{"$f":"'K20 - time schedule'!JE38","v":0},{"$f":"'K20 - time schedule'!JF38","v":0},{"$f":"'K20 - time schedule'!JG38","v":0},{"$f":"'K20 - time schedule'!JH38","v":0},{"$f":"'K20 - time schedule'!JI38","v":0},{"$f":"'K20 - time schedule'!JJ38","v":0},{"$f":"'K20 - time schedule'!JK38","v":0},{"$f":"'K20 - time schedule'!JL38","v":0},{"$f":"'K20 - time schedule'!JM38","v":0},{"$f":"'K20 - time schedule'!JN38","v":0},{"$f":"'K20 - time schedule'!JO38","v":0},{"$f":"'K20 - time schedule'!JP38","v":0},{"$f":"'K20 - time schedule'!JQ38","v":0},{"$f":"'K20 - time schedule'!JR38","v":0},{"$f":"'K20 - time schedule'!JS38","v":0},{"$f":"'K20 - time schedule'!JT38","v":0},{"$f":"'K20 - time schedule'!JU38","v":0},{"$f":"'K20 - time schedule'!JV38","v":0},{"$f":"'K20 - time schedule'!JW38","v":0},{"$f":"'K20 - time schedule'!JX38","v":0},{"$f":"'K20 - time schedule'!JY38","v":0},{"$f":"'K20 - time schedule'!JZ38","v":0},{"$f":"'K20 - time schedule'!KA38","v":0},{"$f":"'K20 - time schedule'!KB38","v":0},{"$f":"'K20 - time schedule'!KC38","v":0},{"$f":"'K20 - time schedule'!KD38","v":0},{"$f":"'K20 - time schedule'!KE38","v":0},{"$f":"'K20 - time schedule'!KF38","v":0},{"$f":"'K20 - time schedule'!KG38","v":0},{"$f":"'K20 - time schedule'!KH38","v":0},{"$f":"'K20 - time schedule'!KI38","v":0},{"$f":"'K20 - time schedule'!KJ38","v":0},{"$f":"'K20 - time schedule'!KK38","v":0},{"$f":"'K20 - time schedule'!KL38","v":0},{"$f":"'K20 - time schedule'!KM38","v":0},{"$f":"'K20 - time schedule'!KN38","v":0},{"$f":"'K20 - time schedule'!KO38","v":0},{"$f":"'K20 - time schedule'!KP38","v":0},{"$f":"'K20 - time schedule'!KQ38","v":0},{"$f":"'K20 - time schedule'!KR38","v":0},{"$f":"'K20 - time schedule'!KS38","v":0},{"$f":"'K20 - time schedule'!KT38","v":0}]
["Boiler room K80 - approved implementation documentation","K80","EUR",{"$f":"'K80 - time schedule'!G17","v":0},{"$f":"'K80 - time schedule'!H17","v":0},{"$f":"'K80 - time schedule'!I17","v":0},{"$f":"'K80 - time schedule'!J17","v":0},{"$f":"'K80 - time schedule'!K17","v":0},{"$f":"'K80 - time schedule'!L17","v":0},{"$f":"'K80 - time schedule'!M17","v":0},{"$f":"'K80 - time schedule'!N17","v":0},{"$f":"'K80 - time schedule'!O17","v":0},{"$f":"'K80 - time schedule'!P17","v":0},{"$f":"'K80 - time schedule'!Q17","v":0},{"$f":"'K80 - time schedule'!R17","v":0},{"$f":"'K80 - time schedule'!S17","v":0},{"$f":"'K80 - time schedule'!T17","v":0},{"$f":"'K80 - time schedule'!U17","v":0},{"$f":"'K80 - time schedule'!V17","v":0},{"$f":"'K80 - time schedule'!W17","v":0},{"$f":"'K80 - time schedule'!X17","v":0},{"$f":"'K80 - time schedule'!Y17","v":0},{"$f":"'K80 - time schedule'!Z17","v":0},{"$f":"'K80 - time schedule'!AA17","v":0},{"$f":"'K80 - time schedule'!AB17","v":0},{"$f":"'K80 - time schedule'!AC17","v":0},{"$f":"'K80 - time schedule'!AD17","v":0},{"$f":"'K80 - time schedule'!AE17","v":0},{"$f":"'K80 - time schedule'!AF17","v":0},{"$f":"'K80 - time schedule'!AG17","v":0},{"$f":"'K80 - time schedule'!AH17","v":0},{"$f":"'K80 - time schedule'!AI17","v":0},{"$f":"'K80 - time schedule'!AJ17","v":0},{"$f":"'K80 - time schedule'!AK17","v":0},{"$f":"'K80 - time schedule'!AL17","v":0},{"$f":"'K80 - time schedule'!AM17","v":0},{"$f":"'K80 - time schedule'!AN17","v":0},{"$f":"'K80 - time schedule'!AO17","v":0},{"$f":"'K80 - time schedule'!AP17","v":0},{"$f":"'K80 - time schedule'!AQ17","v":0},{"$f":"'K80 - time schedule'!AR17","v":0},{"$f":"'K80 - time schedule'!AS17","v":0},{"$f":"'K80 - time schedule'!AT17","v":0},{"$f":"'K80 - time schedule'!AU17","v":0},{"$f":"'K80 - time schedule'!AV17","v":0},{"$f":"'K80 - time schedule'!AW17","v":0},{"$f":"'K80 - time schedule'!AX17","v":0},{"$f":"'K80 - time schedule'!AY17","v":0},{"$f":"'K80 - time schedule'!AZ17","v":0},{"$f":"'K80 - time schedule'!BA17","v":0},{"$f":"'K80 - time schedule'!BB17","v":0},{"$f":"'K80 - time schedule'!BC17","v":0},{"$f":"'K80 - time schedule'!BD17","v":0},{"$f":"'K80 - time schedule'!BE17","v":0},{"$f":"'K80 - time schedule'!BF17","v":0},{"$f":"'K80 - time schedule'!BG17","v":0},{"$f":"'K80 - time schedule'!BH17","v":0},{"$f":"'K80 - time schedule'!BI17","v":0},{"$f":"'K80 - time schedule'!BJ17","v":0},{"$f":"'K80 - time schedule'!BK17","v":0},{"$f":"'K80 - time schedule'!BL17","v":0},{"$f":"'K80 - time schedule'!BM17","v":0},{"$f":"'K80 - time schedule'!BN17","v":0},{"$f":"'K80 - time schedule'!BO17","v":0},{"$f":"'K80 - time schedule'!BP17","v":0},{"$f":"'K80 - time schedule'!BQ17","v":0},{"$f":"'K80 - time schedule'!BR17","v":0},{"$f":"'K80 - time schedule'!BS17","v":0},{"$f":"'K80 - time schedule'!BT17","v":0},{"$f":"'K80 - time schedule'!BU17","v":0},{"$f":"'K80 - time schedule'!BV17","v":0},{"$f":"'K80 - time schedule'!BW17","v":0},{"$f":"'K80 - time schedule'!BX17","v":0},{"$f":"'K80 - time schedule'!BY17","v":0},{"$f":"'K80 - time schedule'!BZ17","v":0},{"$f":"'K80 - time schedule'!CA17","v":0},{"$f":"'K80 - time schedule'!CB17","v":0},{"$f":"'K80 - time schedule'!CC17","v":0},{"$f":"'K80 - time schedule'!CD17","v":0},{"$f":"'K80 - time schedule'!CE17","v":0},{"$f":"'K80 - time schedule'!CF17","v":0},{"$f":"'K80 - time schedule'!CG17","v":0},{"$f":"'K80 - time schedule'!CH17","v":0},{"$f":"'K80 - time schedule'!CI17","v":0},{"$f":"'K80 - time schedule'!CJ17","v":0},{"$f":"'K80 - time schedule'!CK17","v":0},{"$f":"'K80 - time schedule'!CL17","v":0},{"$f":"'K80 - time schedule'!CM17","v":0},{"$f":"'K80 - time schedule'!CN17","v":0},{"$f":"'K80 - time schedule'!CO17","v":0},{"$f":"'K80 - time schedule'!CP17","v":0},{"$f":"'K80 - time schedule'!CQ17","v":0},{"$f":"'K80 - time schedule'!CR17","v":0},{"$f":"'K80 - time schedule'!CS17","v":0},{"$f":"'K80 - time schedule'!CT17","v":0},{"$f":"'K80 - time schedule'!CU17","v":0},{"$f":"'K80 - time schedule'!CV17","v":0},{"$f":"'K80 - time schedule'!CW17","v":0},{"$f":"'K80 - time schedule'!CX17","v":0},{"$f":"'K80 - time schedule'!CY17","v":0},{"$f":"'K80 - time schedule'!CZ17","v":0},{"$f":"'K80 - time schedule'!DA17","v":0},{"$f":"'K80 - time schedule'!DB17","v":0},{"$f":"'K80 - time schedule'!DC17","v":0},{"$f":"'K80 - time schedule'!DD17","v":0},{"$f":"'K80 - time schedule'!DE17","v":0},{"$f":"'K80 - time schedule'!DF17","v":0},{"$f":"'K80 - time schedule'!DG17","v":0},{"$f":"'K80 - time schedule'!DH17","v":0},{"$f":"'K80 - time schedule'!DI17","v":0},{"$f":"'K80 - time schedule'!DJ17","v":0},{"$f":"'K80 - time schedule'!DK17","v":0},{"$f":"'K80 - time schedule'!DL17","v":0},{"$f":"'K80 - time schedule'!DM17","v":0},{"$f":"'K80 - time schedule'!DN17","v":0},{"$f":"'K80 - time schedule'!DO17","v":0},{"$f":"'K80 - time schedule'!DP17","v":0},{"$f":"'K80 - time schedule'!DQ17","v":0},{"$f":"'K80 - time schedule'!DR17","v":0},{"$f":"'K80 - time schedule'!DS17","v":0},{"$f":"'K80 - time schedule'!DT17","v":0},{"$f":"'K80 - time schedule'!DU17","v":0},{"$f":"'K80 - time schedule'!DV17","v":0},{"$f":"'K80 - time schedule'!DW17","v":0},{"$f":"'K80 - time schedule'!DX17","v":0},{"$f":"'K80 - time schedule'!DY17","v":0},{"$f":"'K80 - time schedule'!DZ17","v":0},{"$f":"'K80 - time schedule'!EA17","v":0},{"$f":"'K80 - time schedule'!EB17","v":0},{"$f":"'K80 - time schedule'!EC17","v":0},{"$f":"'K80 - time schedule'!ED17","v":0},{"$f":"'K80 - time schedule'!EE17","v":0},{"$f":"'K80 - time schedule'!EF17","v":0},{"$f":"'K80 - time schedule'!EG17","v":0},{"$f":"'K80 - time schedule'!EH17","v":0},{"$f":"'K80 - time schedule'!EI17","v":0},{"$f":"'K80 - time schedule'!EJ17","v":0},{"$f":"'K80 - time schedule'!EK17","v":0},{"$f":"'K80 - time schedule'!EL17","v":0},{"$f":"'K80 - time schedule'!EM17","v":0},{"$f":"'K80 - time schedule'!EN17","v":0},{"$f":"'K80 - time schedule'!EO17","v":0},{"$f":"'K80 - time schedule'!EP17","v":0},{"$f":"'K80 - time schedule'!EQ17","v":0},{"$f":"'K80 - time schedule'!ER17","v":0},{"$f":"'K80 - time schedule'!ES17","v":0},{"$f":"'K80 - time schedule'!ET17","v":0},{"$f":"'K80 - time schedule'!EU17","v":0},{"$f":"'K80 - time schedule'!EV17","v":0},{"$f":"'K80 - time schedule'!EW17","v":0},{"$f":"'K80 - time schedule'!EX17","v":0},{"$f":"'K80 - time schedule'!EY17","v":0},{"$f":"'K80 - time schedule'!EZ17","v":0},{"$f":"'K80 - time schedule'!FA17","v":0},{"$f":"'K80 - time schedule'!FB17","v":0},{"$f":"'K80 - time schedule'!FC17","v":0},{"$f":"'K80 - time schedule'!FD17","v":0},{"$f":"'K80 - time schedule'!FE17","v":0},{"$f":"'K80 - time schedule'!FF17","v":0},{"$f":"'K80 - time schedule'!FG17","v":0},{"$f":"'K80 - time schedule'!FH17","v":0},{"$f":"'K80 - time schedule'!FI17","v":0},{"$f":"'K80 - time schedule'!FJ17","v":0},{"$f":"'K80 - time schedule'!FK17","v":0},{"$f":"'K80 - time schedule'!FL17","v":0},{"$f":"'K80 - time schedule'!FM17","v":0},{"$f":"'K80 - time schedule'!FN17","v":0},{"$f":"'K80 - time schedule'!FO17","v":0},{"$f":"'K80 - time schedule'!FP17","v":0},{"$f":"'K80 - time schedule'!FQ17","v":0},{"$f":"'K80 - time schedule'!FR17","v":0},{"$f":"'K80 - time schedule'!FS17","v":0},{"$f":"'K80 - time schedule'!FT17","v":0},{"$f":"'K80 - time schedule'!FU17","v":0},{"$f":"'K80 - time schedule'!FV17","v":0},{"$f":"'K80 - time schedule'!FW17","v":0},{"$f":"'K80 - time schedule'!FX17","v":0},{"$f":"'K80 - time schedule'!FY17","v":0},{"$f":"'K80 - time schedule'!FZ17","v":0},{"$f":"'K80 - time schedule'!GA17","v":0},{"$f":"'K80 - time schedule'!GB17","v":0},{"$f":"'K80 - time schedule'!GC17","v":0},{"$f":"'K80 - time schedule'!GD17","v":0},{"$f":"'K80 - time schedule'!GE17","v":0},{"$f":"'K80 - time schedule'!GF17","v":0},{"$f":"'K20 - time schedule'!GG39","v":0},{"$f":"'K20 - time schedule'!GH39","v":0},{"$f":"'K20 - time schedule'!GI39","v":0},{"$f":"'K20 - time schedule'!GJ39","v":0},{"$f":"'K20 - time schedule'!GK39","v":0},{"$f":"'K20 - time schedule'!GL39","v":0},{"$f":"'K20 - time schedule'!GM39","v":0},{"$f":"'K20 - time schedule'!GN39","v":0},{"$f":"'K20 - time schedule'!GO39","v":0},{"$f":"'K20 - time schedule'!GP39","v":0},{"$f":"'K20 - time schedule'!GQ39","v":0},{"$f":"'K20 - time schedule'!GR39","v":0},{"$f":"'K20 - time schedule'!GS39","v":0},{"$f":"'K20 - time schedule'!GT39","v":0},{"$f":"'K20 - time schedule'!GU39","v":0},{"$f":"'K20 - time schedule'!GV39","v":0},{"$f":"'K20 - time schedule'!GW39","v":0},{"$f":"'K20 - time schedule'!GX39","v":0},{"$f":"'K20 - time schedule'!GY39","v":0},{"$f":"'K20 - time schedule'!GZ39","v":0},{"$f":"'K20 - time schedule'!HA39","v":0},{"$f":"'K20 - time schedule'!HB39","v":0},{"$f":"'K20 - time schedule'!HC39","v":0},{"$f":"'K20 - time schedule'!HD39","v":0},{"$f":"'K20 - time schedule'!HE39","v":0},{"$f":"'K20 - time schedule'!HF39","v":0},{"$f":"'K20 - time schedule'!HG39","v":0},{"$f":"'K20 - time schedule'!HH39","v":0},{"$f":"'K20 - time schedule'!HI39","v":0},{"$f":"'K20 - time schedule'!HJ39","v":0},{"$f":"'K20 - time schedule'!HK39","v":0},{"$f":"'K20 - time schedule'!HL39","v":0},{"$f":"'K20 - time schedule'!HM39","v":0},{"$f":"'K20 - time schedule'!HN39","v":0},{"$f":"'K20 - time schedule'!HO39","v":0},{"$f":"'K20 - time schedule'!HP39","v":0},{"$f":"'K20 - time schedule'!HQ39","v":0},{"$f":"'K20 - time schedule'!HR39","v":0},{"$f":"'K20 - time schedule'!HS39","v":0},{"$f":"'K20 - time schedule'!HT39","v":0},{"$f":"'K20 - time schedule'!HU39","v":0},{"$f":"'K20 - time schedule'!HV39","v":0},{"$f":"'K20 - time schedule'!HW39","v":0},{"$f":"'K20 - time schedule'!HX39","v":0},{"$f":"'K20 - time schedule'!HY39","v":0},{"$f":"'K20 - time schedule'!HZ39","v":0},{"$f":"'K20 - time schedule'!IA39","v":0},{"$f":"'K20 - time schedule'!IB39","v":0},{"$f":"'K20 - time schedule'!IC39","v":0},{"$f":"'K20 - time schedule'!ID39","v":0},{"$f":"'K20 - time schedule'!IE39","v":0},{"$f":"'K20 - time schedule'!IF39","v":0},{"$f":"'K20 - time schedule'!IG39","v":0},{"$f":"'K20 - time schedule'!IH39","v":0},{"$f":"'K20 - time schedule'!II39","v":0},{"$f":"'K20 - time schedule'!IJ39","v":0},{"$f":"'K20 - time schedule'!IK39","v":0},{"$f":"'K20 - time schedule'!IL39","v":0},{"$f":"'K20 - time schedule'!IM39","v":0},{"$f":"'K20 - time schedule'!IN39","v":0},{"$f":"'K20 - time schedule'!IO39","v":0},{"$f":"'K20 - time schedule'!IP39","v":0},{"$f":"'K20 - time schedule'!IQ39","v":0},{"$f":"'K20 - time schedule'!IR39","v":0},{"$f":"'K20 - time schedule'!IS39","v":0},{"$f":"'K20 - time schedule'!IT39","v":0},{"$f":"'K20 - time schedule'!IU39","v":0},{"$f":"'K20 - time schedule'!IV39","v":0},{"$f":"'K20 - time schedule'!IW39","v":0},{"$f":"'K20 - time schedule'!IX39","v":0},{"$f":"'K20 - time schedule'!IY39","v":0},{"$f":"'K20 - time schedule'!IZ39","v":0},{"$f":"'K20 - time schedule'!JA39","v":0},{"$f":"'K20 - time schedule'!JB39","v":0},{"$f":"'K20 - time schedule'!JC39","v":0},{"$f":"'K20 - time schedule'!JD39","v":0},{"$f":"'K20 - time schedule'!JE39","v":0},{"$f":"'K20 - time schedule'!JF39","v":0},{"$f":"'K20 - time schedule'!JG39","v":0},{"$f":"'K20 - time schedule'!JH39","v":0},{"$f":"'K20 - time schedule'!JI39","v":0},{"$f":"'K20 - time schedule'!JJ39","v":0},{"$f":"'K20 - time schedule'!JK39","v":0},{"$f":"'K20 - time schedule'!JL39","v":0},{"$f":"'K20 - time schedule'!JM39","v":0},{"$f":"'K20 - time schedule'!JN39","v":0},{"$f":"'K20 - time schedule'!JO39","v":0},{"$f":"'K20 - time schedule'!JP39","v":0},{"$f":"'K20 - time schedule'!JQ39","v":0},{"$f":"'K20 - time schedule'!JR39","v":0},{"$f":"'K20 - time schedule'!JS39","v":0},{"$f":"'K20 - time schedule'!JT39","v":0},{"$f":"'K20 - time schedule'!JU39","v":0},{"$f":"'K20 - time schedule'!JV39","v":0},{"$f":"'K20 - time schedule'!JW39","v":0},{"$f":"'K20 - time schedule'!JX39","v":0},{"$f":"'K20 - time schedule'!JY39","v":0},{"$f":"'K20 - time schedule'!JZ39","v":0},{"$f":"'K20 - time schedule'!KA39","v":0},{"$f":"'K20 - time schedule'!KB39","v":0},{"$f":"'K20 - time schedule'!KC39","v":0},{"$f":"'K20 - time schedule'!KD39","v":0},{"$f":"'K20 - time schedule'!KE39","v":0},{"$f":"'K20 - time schedule'!KF39","v":0},{"$f":"'K20 - time schedule'!KG39","v":0},{"$f":"'K20 - time schedule'!KH39","v":0},{"$f":"'K20 - time schedule'!KI39","v":0},{"$f":"'K20 - time schedule'!KJ39","v":0},{"$f":"'K20 - time schedule'!KK39","v":0},{"$f":"'K20 - time schedule'!KL39","v":0},{"$f":"'K20 - time schedule'!KM39","v":0},{"$f":"'K20 - time schedule'!KN39","v":0},{"$f":"'K20 - time schedule'!KO39","v":0},{"$f":"'K20 - time schedule'!KP39","v":0},{"$f":"'K20 - time schedule'!KQ39","v":0},{"$f":"'K20 - time schedule'!KR39","v":0},{"$f":"'K20 - time schedule'!KS39","v":0},{"$f":"'K20 - time schedule'!KT39","v":0}]
["Boiler room K80 - dismantling","K80","EUR",{"$f":"'K80 - time schedule'!G21","v":0},{"$f":"'K80 - time schedule'!H21","v":0},{"$f":"'K80 - time schedule'!I21","v":0},{"$f":"'K80 - time schedule'!J21","v":0},{"$f":"'K80 - time schedule'!K21","v":0},{"$f":"'K80 - time schedule'!L21","v":0},{"$f":"'K80 - time schedule'!M21","v":0},{"$f":"'K80 - time schedule'!N21","v":0},{"$f":"'K80 - time schedule'!O21","v":0},{"$f":"'K80 - time schedule'!P21","v":0},{"$f":"'K80 - time schedule'!Q21","v":0},{"$f":"'K80 - time schedule'!R21","v":0},{"$f":"'K80 - time schedule'!S21","v":0},{"$f":"'K80 - time schedule'!T21","v":0},{"$f":"'K80 - time schedule'!U21","v":0},{"$f":"'K80 - time schedule'!V21","v":0},{"$f":"'K80 - time schedule'!W21","v":0},{"$f":"'K80 - time schedule'!X21","v":0},{"$f":"'K80 - time schedule'!Y21","v":0},{"$f":"'K80 - time schedule'!Z21","v":0},{"$f":"'K80 - time schedule'!AA21","v":0},{"$f":"'K80 - time schedule'!AB21","v":0},{"$f":"'K80 - time schedule'!AC21","v":0},{"$f":"'K80 - time schedule'!AD21","v":0},{"$f":"'K80 - time schedule'!AE21","v":0},{"$f":"'K80 - time schedule'!AF21","v":0},{"$f":"'K80 - time schedule'!AG21","v":0},{"$f":"'K80 - time schedule'!AH21","v":0},{"$f":"'K80 - time schedule'!AI21","v":0},{"$f":"'K80 - time schedule'!AJ21","v":0},{"$f":"'K80 - time schedule'!AK21","v":0},{"$f":"'K80 - time schedule'!AL21","v":0},{"$f":"'K80 - time schedule'!AM21","v":0},{"$f":"'K80 - time schedule'!AN21","v":0},{"$f":"'K80 - time schedule'!AO21","v":0},{"$f":"'K80 - time schedule'!AP21","v":0},{"$f":"'K80 - time schedule'!AQ21","v":0},{"$f":"'K80 - time schedule'!AR21","v":0},{"$f":"'K80 - time schedule'!AS21","v":0},{"$f":"'K80 - time schedule'!AT21","v":0},{"$f":"'K80 - time schedule'!AU21","v":0},{"$f":"'K80 - time schedule'!AV21","v":0},{"$f":"'K80 - time schedule'!AW21","v":0},{"$f":"'K80 - time schedule'!AX21","v":0},{"$f":"'K80 - time schedule'!AY21","v":0},{"$f":"'K80 - time schedule'!AZ21","v":0},{"$f":"'K80 - time schedule'!BA21","v":0},{"$f":"'K80 - time schedule'!BB21","v":0},{"$f":"'K80 - time schedule'!BC21","v":0},{"$f":"'K80 - time schedule'!BD21","v":0},{"$f":"'K80 - time schedule'!BE21","v":0},{"$f":"'K80 - time schedule'!BF21","v":0},{"$f":"'K80 - time schedule'!BG21","v":0},{"$f":"'K80 - time schedule'!BH21","v":0},{"$f":"'K80 - time schedule'!BI21","v":0},{"$f":"'K80 - time schedule'!BJ21","v":0},{"$f":"'K80 - time schedule'!BK21","v":0},{"$f":"'K80 - time schedule'!BL21","v":0},{"$f":"'K80 - time schedule'!BM21","v":0},{"$f":"'K80 - time schedule'!BN21","v":0},{"$f":"'K80 - time schedule'!BO21","v":0},{"$f":"'K80 - time schedule'!BP21","v":0},{"$f":"'K80 - time schedule'!BQ21","v":0},{"$f":"'K80 - time schedule'!BR21","v":0},{"$f":"'K80 - time schedule'!BS21","v":0},{"$f":"'K80 - time schedule'!BT21","v":0},{"$f":"'K80 - time schedule'!BU21","v":0},{"$f":"'K80 - time schedule'!BV21","v":0},{"$f":"'K80 - time schedule'!BW21","v":0},{"$f":"'K80 - time schedule'!BX21","v":0},{"$f":"'K80 - time schedule'!BY21","v":0},{"$f":"'K80 - time schedule'!BZ21","v":0},{"$f":"'K80 - time schedule'!CA21","v":0},{"$f":"'K80 - time schedule'!CB21","v":0},{"$f":"'K80 - time schedule'!CC21","v":0},{"$f":"'K80 - time schedule'!CD21","v":0},{"$f":"'K80 - time schedule'!CE21","v":0},{"$f":"'K80 - time schedule'!CF21","v":0},{"$f":"'K80 - time schedule'!CG21","v":0},{"$f":"'K80 - time schedule'!CH21","v":0},{"$f":"'K80 - time schedule'!CI21","v":0},{"$f":"'K80 - time schedule'!CJ21","v":0},{"$f":"'K80 - time schedule'!CK21","v":0},{"$f":"'K80 - time schedule'!CL21","v":0},{"$f":"'K80 - time schedule'!CM21","v":0},{"$f":"'K80 - time schedule'!CN21","v":0},{"$f":"'K80 - time schedule'!CO21","v":0},{"$f":"'K80 - time schedule'!CP21","v":0},{"$f":"'K80 - time schedule'!CQ21","v":0},{"$f":"'K80 - time schedule'!CR21","v":0},{"$f":"'K80 - time schedule'!CS21","v":0},{"$f":"'K80 - time schedule'!CT21","v":0},{"$f":"'K80 - time schedule'!CU21","v":0},{"$f":"'K80 - time schedule'!CV21","v":0},{"$f":"'K80 - time schedule'!CW21","v":0},{"$f":"'K80 - time schedule'!CX21","v":0},{"$f":"'K80 - time schedule'!CY21","v":0},{"$f":"'K80 - time schedule'!CZ21","v":0},{"$f":"'K80 - time schedule'!DA21","v":0},{"$f":"'K80 - time schedule'!DB21","v":0},{"$f":"'K80 - time schedule'!DC21","v":0},{"$f":"'K80 - time schedule'!DD21","v":0},{"$f":"'K80 - time schedule'!DE21","v":0},{"$f":"'K80 - time schedule'!DF21","v":0},{"$f":"'K80 - time schedule'!DG21","v":0},{"$f":"'K80 - time schedule'!DH21","v":0},{"$f":"'K80 - time schedule'!DI21","v":0},{"$f":"'K80 - time schedule'!DJ21","v":0},{"$f":"'K80 - time schedule'!DK21","v":0},{"$f":"'K80 - time schedule'!DL21","v":0},{"$f":"'K80 - time schedule'!DM21","v":0},{"$f":"'K80 - time schedule'!DN21","v":0},{"$f":"'K80 - time schedule'!DO21","v":0},{"$f":"'K80 - time schedule'!DP21","v":0},{"$f":"'K80 - time schedule'!DQ21","v":0},{"$f":"'K80 - time schedule'!DR21","v":0},{"$f":"'K80 - time schedule'!DS21","v":0},{"$f":"'K80 - time schedule'!DT21","v":0},{"$f":"'K80 - time schedule'!DU21","v":0},{"$f":"'K80 - time schedule'!DV21","v":0},{"$f":"'K80 - time schedule'!DW21","v":0},{"$f":"'K80 - time schedule'!DX21","v":0},{"$f":"'K80 - time schedule'!DY21","v":0},{"$f":"'K80 - time schedule'!DZ21","v":0},{"$f":"'K80 - time schedule'!EA21","v":0},{"$f":"'K80 - time schedule'!EB21","v":0},{"$f":"'K80 - time schedule'!EC21","v":0},{"$f":"'K80 - time schedule'!ED21","v":0},{"$f":"'K80 - time schedule'!EE21","v":0},{"$f":"'K80 - time schedule'!EF21","v":0},{"$f":"'K80 - time schedule'!EG21","v":0},{"$f":"'K80 - time schedule'!EH21","v":0},{"$f":"'K80 - time schedule'!EI21","v":0},{"$f":"'K80 - time schedule'!EJ21","v":0},{"$f":"'K80 - time schedule'!EK21","v":0},{"$f":"'K80 - time schedule'!EL21","v":0},{"$f":"'K80 - time schedule'!EM21","v":0},{"$f":"'K80 - time schedule'!EN21","v":0},{"$f":"'K80 - time schedule'!EO21","v":0},{"$f":"'K80 - time schedule'!EP21","v":0},{"$f":"'K80 - time schedule'!EQ21","v":0},{"$f":"'K80 - time schedule'!ER21","v":0},{"$f":"'K80 - time schedule'!ES21","v":0},{"$f":"'K80 - time schedule'!ET21","v":0},{"$f":"'K80 - time schedule'!EU21","v":0},{"$f":"'K80 - time schedule'!EV21","v":0},{"$f":"'K80 - time schedule'!EW21","v":0},{"$f":"'K80 - time schedule'!EX21","v":0},{"$f":"'K80 - time schedule'!EY21","v":0},{"$f":"'K80 - time schedule'!EZ21","v":0},{"$f":"'K80 - time schedule'!FA21","v":0},{"$f":"'K80 - time schedule'!FB21","v":0},{"$f":"'K80 - time schedule'!FC21","v":0},{"$f":"'K80 - time schedule'!FD21","v":0},{"$f":"'K80 - time schedule'!FE21","v":0},{"$f":"'K80 - time schedule'!FF21","v":0},{"$f":"'K80 - time schedule'!FG21","v":0},{"$f":"'K80 - time schedule'!FH21","v":0},{"$f":"'K80 - time schedule'!FI21","v":0},{"$f":"'K80 - time schedule'!FJ21","v":0},{"$f":"'K80 - time schedule'!FK21","v":0},{"$f":"'K80 - time schedule'!FL21","v":0},{"$f":"'K80 - time schedule'!FM21","v":0},{"$f":"'K80 - time schedule'!FN21","v":0},{"$f":"'K80 - time schedule'!FO21","v":0},{"$f":"'K80 - time schedule'!FP21","v":0},{"$f":"'K80 - time schedule'!FQ21","v":0},{"$f":"'K80 - time schedule'!FR21","v":0},{"$f":"'K80 - time schedule'!FS21","v":0},{"$f":"'K80 - time schedule'!FT21","v":0},{"$f":"'K80 - time schedule'!FU21","v":0},{"$f":"'K80 - time schedule'!FV21","v":0},{"$f":"'K80 - time schedule'!FW21","v":0},{"$f":"'K80 - time schedule'!FX21","v":0},{"$f":"'K80 - time schedule'!FY21","v":0},{"$f":"'K80 - time schedule'!FZ21","v":0},{"$f":"'K80 - time schedule'!GA21","v":0},{"$f":"'K80 - time schedule'!GB21","v":0},{"$f":"'K80 - time schedule'!GC21","v":0},{"$f":"'K80 - time schedule'!GD21","v":0},{"$f":"'K80 - time schedule'!GE21","v":0},{"$f":"'K80 - time schedule'!GF21","v":0},{"$f":"'K20 - time schedule'!GG40","v":0},{"$f":"'K20 - time schedule'!GH40","v":0},{"$f":"'K20 - time schedule'!GI40","v":0},{"$f":"'K20 - time schedule'!GJ40","v":0},{"$f":"'K20 - time schedule'!GK40","v":0},{"$f":"'K20 - time schedule'!GL40","v":0},{"$f":"'K20 - time schedule'!GM40","v":0},{"$f":"'K20 - time schedule'!GN40","v":0},{"$f":"'K20 - time schedule'!GO40","v":0},{"$f":"'K20 - time schedule'!GP40","v":0},{"$f":"'K20 - time schedule'!GQ40","v":0},{"$f":"'K20 - time schedule'!GR40","v":0},{"$f":"'K20 - time schedule'!GS40","v":0},{"$f":"'K20 - time schedule'!GT40","v":0},{"$f":"'K20 - time schedule'!GU40","v":0},{"$f":"'K20 - time schedule'!GV40","v":0},{"$f":"'K20 - time schedule'!GW40","v":0},{"$f":"'K20 - time schedule'!GX40","v":0},{"$f":"'K20 - time schedule'!GY40","v":0},{"$f":"'K20 - time schedule'!GZ40","v":0},{"$f":"'K20 - time schedule'!HA40","v":0},{"$f":"'K20 - time schedule'!HB40","v":0},{"$f":"'K20 - time schedule'!HC40","v":0},{"$f":"'K20 - time schedule'!HD40","v":0},{"$f":"'K20 - time schedule'!HE40","v":0},{"$f":"'K20 - time schedule'!HF40","v":0},{"$f":"'K20 - time schedule'!HG40","v":0},{"$f":"'K20 - time schedule'!HH40","v":0},{"$f":"'K20 - time schedule'!HI40","v":0},{"$f":"'K20 - time schedule'!HJ40","v":0},{"$f":"'K20 - time schedule'!HK40","v":0},{"$f":"'K20 - time schedule'!HL40","v":0},{"$f":"'K20 - time schedule'!HM40","v":0},{"$f":"'K20 - time schedule'!HN40","v":0},{"$f":"'K20 - time schedule'!HO40","v":0},{"$f":"'K20 - time schedule'!HP40","v":0},{"$f":"'K20 - time schedule'!HQ40","v":0},{"$f":"'K20 - time schedule'!HR40","v":0},{"$f":"'K20 - time schedule'!HS40","v":0},{"$f":"'K20 - time schedule'!HT40","v":0},{"$f":"'K20 - time schedule'!HU40","v":0},{"$f":"'K20 - time schedule'!HV40","v":0},{"$f":"'K20 - time schedule'!HW40","v":0},{"$f":"'K20 - time schedule'!HX40","v":0},{"$f":"'K20 - time schedule'!HY40","v":0},{"$f":"'K20 - time schedule'!HZ40","v":0},{"$f":"'K20 - time schedule'!IA40","v":0},{"$f":"'K20 - time schedule'!IB40","v":0},{"$f":"'K20 - time schedule'!IC40","v":0},{"$f":"'K20 - time schedule'!ID40","v":0},{"$f":"'K20 - time schedule'!IE40","v":0},{"$f":"'K20 - time schedule'!IF40","v":0},{"$f":"'K20 - time schedule'!IG40","v":0},{"$f":"'K20 - time schedule'!IH40","v":0},{"$f":"'K20 - time schedule'!II40","v":0},{"$f":"'K20 - time schedule'!IJ40","v":0},{"$f":"'K20 - time schedule'!IK40","v":0},{"$f":"'K20 - time schedule'!IL40","v":0},{"$f":"'K20 - time schedule'!IM40","v":0},{"$f":"'K20 - time schedule'!IN40","v":0},{"$f":"'K20 - time schedule'!IO40","v":0},{"$f":"'K20 - time schedule'!IP40","v":0},{"$f":"'K20 - time schedule'!IQ40","v":0},{"$f":"'K20 - time schedule'!IR40","v":0},{"$f":"'K20 - time schedule'!IS40","v":0},{"$f":"'K20 - time schedule'!IT40","v":0},{"$f":"'K20 - time schedule'!IU40","v":0},{"$f":"'K20 - time schedule'!IV40","v":0},{"$f":"'K20 - time schedule'!IW40","v":0},{"$f":"'K20 - time schedule'!IX40","v":0},{"$f":"'K20 - time schedule'!IY40","v":0},{"$f":"'K20 - time schedule'!IZ40","v":0},{"$f":"'K20 - time schedule'!JA40","v":0},{"$f":"'K20 - time schedule'!JB40","v":0},{"$f":"'K20 - time schedule'!JC40","v":0},{"$f":"'K20 - time schedule'!JD40","v":0},{"$f":"'K20 - time schedule'!JE40","v":0},{"$f":"'K20 - time schedule'!JF40","v":0},{"$f":"'K20 - time schedule'!JG40","v":0},{"$f":"'K20 - time schedule'!JH40","v":0},{"$f":"'K20 - time schedule'!JI40","v":0},{"$f":"'K20 - time schedule'!JJ40","v":0},{"$f":"'K20 - time schedule'!JK40","v":0},{"$f":"'K20 - time schedule'!JL40","v":0},{"$f":"'K20 - time schedule'!JM40","v":0},{"$f":"'K20 - time schedule'!JN40","v":0},{"$f":"'K20 - time schedule'!JO40","v":0},{"$f":"'K20 - time schedule'!JP40","v":0},{"$f":"'K20 - time schedule'!JQ40","v":0},{"$f":"'K20 - time schedule'!JR40","v":0},{"$f":"'K20 - time schedule'!JS40","v":0},{"$f":"'K20 - time schedule'!JT40","v":0},{"$f":"'K20 - time schedule'!JU40","v":0},{"$f":"'K20 - time schedule'!JV40","v":0},{"$f":"'K20 - time schedule'!JW40","v":0},{"$f":"'K20 - time schedule'!JX40","v":0},{"$f":"'K20 - time schedule'!JY40","v":0},{"$f":"'K20 - time schedule'!JZ40","v":0},{"$f":"'K20 - time schedule'!KA40","v":0},{"$f":"'K20 - time schedule'!KB40","v":0},{"$f":"'K20 - time schedule'!KC40","v":0},{"$f":"'K20 - time schedule'!KD40","v":0},{"$f":"'K20 - time schedule'!KE40","v":0},{"$f":"'K20 - time schedule'!KF40","v":0},{"$f":"'K20 - time schedule'!KG40","v":0},{"$f":"'K20 - time schedule'!KH40","v":0},{"$f":"'K20 - time schedule'!KI40","v":0},{"$f":"'K20 - time schedule'!KJ40","v":0},{"$f":"'K20 - time schedule'!KK40","v":0},{"$f":"'K20 - time schedule'!KL40","v":0},{"$f":"'K20 - time schedule'!KM40","v":0},{"$f":"'K20 - time schedule'!KN40","v":0},{"$f":"'K20 - time schedule'!KO40","v":0},{"$f":"'K20 - time schedule'!KP40","v":0},{"$f":"'K20 - time schedule'!KQ40","v":0},{"$f":"'K20 - time schedule'!KR40","v":0},{"$f":"'K20 - time schedule'!KS40","v":0},{"$f":"'K20 - time schedule'!KT40","v":0}]
["Boiler room K80 - supply of combustion air","K80","EUR",{"$f":"'K80 - time schedule'!G23","v":0},{"$f":"'K80 - time schedule'!H23","v":0},{"$f":"'K80 - time schedule'!I23","v":0},{"$f":"'K80 - time schedule'!J23","v":0},{"$f":"'K80 - time schedule'!K23","v":0},{"$f":"'K80 - time schedule'!L23","v":0},{"$f":"'K80 - time schedule'!M23","v":0},{"$f":"'K80 - time schedule'!N23","v":0},{"$f":"'K80 - time schedule'!O23","v":0},{"$f":"'K80 - time schedule'!P23","v":0},{"$f":"'K80 - time schedule'!Q23","v":0},{"$f":"'K80 - time schedule'!R23","v":0},{"$f":"'K80 - time schedule'!S23","v":0},{"$f":"'K80 - time schedule'!T23","v":0},{"$f":"'K80 - time schedule'!U23","v":0},{"$f":"'K80 - time schedule'!V23","v":0},{"$f":"'K80 - time schedule'!W23","v":0},{"$f":"'K80 - time schedule'!X23","v":0},{"$f":"'K80 - time schedule'!Y23","v":0},{"$f":"'K80 - time schedule'!Z23","v":0},{"$f":"'K80 - time schedule'!AA23","v":0},{"$f":"'K80 - time schedule'!AB23","v":0},{"$f":"'K80 - time schedule'!AC23","v":0},{"$f":"'K80 - time schedule'!AD23","v":0},{"$f":"'K80 - time schedule'!AE23","v":0},{"$f":"'K80 - time schedule'!AF23","v":0},{"$f":"'K80 - time schedule'!AG23","v":0},{"$f":"'K80 - time schedule'!AH23","v":0},{"$f":"'K80 - time schedule'!AI23","v":0},{"$f":"'K80 - time schedule'!AJ23","v":0},{"$f":"'K80 - time schedule'!AK23","v":0},{"$f":"'K80 - time schedule'!AL23","v":0},{"$f":"'K80 - time schedule'!AM23","v":0},{"$f":"'K80 - time schedule'!AN23","v":0},{"$f":"'K80 - time schedule'!AO23","v":0},{"$f":"'K80 - time schedule'!AP23","v":0},{"$f":"'K80 - time schedule'!AQ23","v":0},{"$f":"'K80 - time schedule'!AR23","v":0},{"$f":"'K80 - time schedule'!AS23","v":0},{"$f":"'K80 - time schedule'!AT23","v":0},{"$f":"'K80 - time schedule'!AU23","v":0},{"$f":"'K80 - time schedule'!AV23","v":0},{"$f":"'K80 - time schedule'!AW23","v":0},{"$f":"'K80 - time schedule'!AX23","v":0},{"$f":"'K80 - time schedule'!AY23","v":0},{"$f":"'K80 - time schedule'!AZ23","v":0},{"$f":"'K80 - time schedule'!BA23","v":0},{"$f":"'K80 - time schedule'!BB23","v":0},{"$f":"'K80 - time schedule'!BC23","v":0},{"$f":"'K80 - time schedule'!BD23","v":0},{"$f":"'K80 - time schedule'!BE23","v":0},{"$f":"'K80 - time schedule'!BF23","v":0},{"$f":"'K80 - time schedule'!BG23","v":0},{"$f":"'K80 - time schedule'!BH23","v":0},{"$f":"'K80 - time schedule'!BI23","v":0},{"$f":"'K80 - time schedule'!BJ23","v":0},{"$f":"'K80 - time schedule'!BK23","v":0},{"$f":"'K80 - time schedule'!BL23","v":0},{"$f":"'K80 - time schedule'!BM23","v":0},{"$f":"'K80 - time schedule'!BN23","v":0},{"$f":"'K80 - time schedule'!BO23","v":0},{"$f":"'K80 - time schedule'!BP23","v":0},{"$f":"'K80 - time schedule'!BQ23","v":0},{"$f":"'K80 - time schedule'!BR23","v":0},{"$f":"'K80 - time schedule'!BS23","v":0},{"$f":"'K80 - time schedule'!BT23","v":0},{"$f":"'K80 - time schedule'!BU23","v":0},{"$f":"'K80 - time schedule'!BV23","v":0},{"$f":"'K80 - time schedule'!BW23","v":0},{"$f":"'K80 - time schedule'!BX23","v":0},{"$f":"'K80 - time schedule'!BY23","v":0},{"$f":"'K80 - time schedule'!BZ23","v":0},{"$f":"'K80 - time schedule'!CA23","v":0},{"$f":"'K80 - time schedule'!CB23","v":0},{"$f":"'K80 - time schedule'!CC23","v":0},{"$f":"'K80 - time schedule'!CD23","v":0},{"$f":"'K80 - time schedule'!CE23","v":0},{"$f":"'K80 - time schedule'!CF23","v":0},{"$f":"'K80 - time schedule'!CG23","v":0},{"$f":"'K80 - time schedule'!CH23","v":0},{"$f":"'K80 - time schedule'!CI23","v":0},{"$f":"'K80 - time schedule'!CJ23","v":0},{"$f":"'K80 - time schedule'!CK23","v":0},{"$f":"'K80 - time schedule'!CL23","v":0},{"$f":"'K80 - time schedule'!CM23","v":0},{"$f":"'K80 - time schedule'!CN23","v":0},{"$f":"'K80 - time schedule'!CO23","v":0},{"$f":"'K80 - time schedule'!CP23","v":0},{"$f":"'K80 - time schedule'!CQ23","v":0},{"$f":"'K80 - time schedule'!CR23","v":0},{"$f":"'K80 - time schedule'!CS23","v":0},{"$f":"'K80 - time schedule'!CT23","v":0},{"$f":"'K80 - time schedule'!CU23","v":0},{"$f":"'K80 - time schedule'!CV23","v":0},{"$f":"'K80 - time schedule'!CW23","v":0},{"$f":"'K80 - time schedule'!CX23","v":0},{"$f":"'K80 - time schedule'!CY23","v":0},{"$f":"'K80 - time schedule'!CZ23","v":0},{"$f":"'K80 - time schedule'!DA23","v":0},{"$f":"'K80 - time schedule'!DB23","v":0},{"$f":"'K80 - time schedule'!DC23","v":0},{"$f":"'K80 - time schedule'!DD23","v":0},{"$f":"'K80 - time schedule'!DE23","v":0},{"$f":"'K80 - time schedule'!DF23","v":0},{"$f":"'K80 - time schedule'!DG23","v":0},{"$f":"'K80 - time schedule'!DH23","v":0},{"$f":"'K80 - time schedule'!DI23","v":0},{"$f":"'K80 - time schedule'!DJ23","v":0},{"$f":"'K80 - time schedule'!DK23","v":0},{"$f":"'K80 - time schedule'!DL23","v":0},{"$f":"'K80 - time schedule'!DM23","v":0},{"$f":"'K80 - time schedule'!DN23","v":0},{"$f":"'K80 - time schedule'!DO23","v":0},{"$f":"'K80 - time schedule'!DP23","v":0},{"$f":"'K80 - time schedule'!DQ23","v":0},{"$f":"'K80 - time schedule'!DR23","v":0},{"$f":"'K80 - time schedule'!DS23","v":0},{"$f":"'K80 - time schedule'!DT23","v":0},{"$f":"'K80 - time schedule'!DU23","v":0},{"$f":"'K80 - time schedule'!DV23","v":0},{"$f":"'K80 - time schedule'!DW23","v":0},{"$f":"'K80 - time schedule'!DX23","v":0},{"$f":"'K80 - time schedule'!DY23","v":0},{"$f":"'K80 - time schedule'!DZ23","v":0},{"$f":"'K80 - time schedule'!EA23","v":0},{"$f":"'K80 - time schedule'!EB23","v":0},{"$f":"'K80 - time schedule'!EC23","v":0},{"$f":"'K80 - time schedule'!ED23","v":0},{"$f":"'K80 - time schedule'!EE23","v":0},{"$f":"'K80 - time schedule'!EF23","v":0},{"$f":"'K80 - time schedule'!EG23","v":0},{"$f":"'K80 - time schedule'!EH23","v":0},{"$f":"'K80 - time schedule'!EI23","v":0},{"$f":"'K80 - time schedule'!EJ23","v":0},{"$f":"'K80 - time schedule'!EK23","v":0},{"$f":"'K80 - time schedule'!EL23","v":0},{"$f":"'K80 - time schedule'!EM23","v":0},{"$f":"'K80 - time schedule'!EN23","v":0},{"$f":"'K80 - time schedule'!EO23","v":0},{"$f":"'K80 - time schedule'!EP23","v":0},{"$f":"'K80 - time schedule'!EQ23","v":0},{"$f":"'K80 - time schedule'!ER23","v":0},{"$f":"'K80 - time schedule'!ES23","v":0},{"$f":"'K80 - time schedule'!ET23","v":0},{"$f":"'K80 - time schedule'!EU23","v":0},{"$f":"'K80 - time schedule'!EV23","v":0},{"$f":"'K80 - time schedule'!EW23","v":0},{"$f":"'K80 - time schedule'!EX23","v":0},{"$f":"'K80 - time schedule'!EY23","v":0},{"$f":"'K80 - time schedule'!EZ23","v":0},{"$f":"'K80 - time schedule'!FA23","v":0},{"$f":"'K80 - time schedule'!FB23","v":0},{"$f":"'K80 - time schedule'!FC23","v":0},{"$f":"'K80 - time schedule'!FD23","v":0},{"$f":"'K80 - time schedule'!FE23","v":0},{"$f":"'K80 - time schedule'!FF23","v":0},{"$f":"'K80 - time schedule'!FG23","v":0},{"$f":"'K80 - time schedule'!FH23","v":0},{"$f":"'K80 - time schedule'!FI23","v":0},{"$f":"'K80 - time schedule'!FJ23","v":0},{"$f":"'K80 - time schedule'!FK23","v":0},{"$f":"'K80 - time schedule'!FL23","v":0},{"$f":"'K80 - time schedule'!FM23","v":0},{"$f":"'K80 - time schedule'!FN23","v":0},{"$f":"'K80 - time schedule'!FO23","v":0},{"$f":"'K80 - time schedule'!FP23","v":0},{"$f":"'K80 - time schedule'!FQ23","v":0},{"$f":"'K80 - time schedule'!FR23","v":0},{"$f":"'K80 - time schedule'!FS23","v":0},{"$f":"'K80 - time schedule'!FT23","v":0},{"$f":"'K80 - time schedule'!FU23","v":0},{"$f":"'K80 - time schedule'!FV23","v":0},{"$f":"'K80 - time schedule'!FW23","v":0},{"$f":"'K80 - time schedule'!FX23","v":0},{"$f":"'K80 - time schedule'!FY23","v":0},{"$f":"'K80 - time schedule'!FZ23","v":0},{"$f":"'K80 - time schedule'!GA23","v":0},{"$f":"'K80 - time schedule'!GB23","v":0},{"$f":"'K80 - time schedule'!GC23","v":0},{"$f":"'K80 - time schedule'!GD23","v":0},{"$f":"'K80 - time schedule'!GE23","v":0},{"$f":"'K80 - time schedule'!GF23","v":0},{"$f":"'K20 - time schedule'!GG41","v":0},{"$f":"'K20 - time schedule'!GH41","v":0},{"$f":"'K20 - time schedule'!GI41","v":0},{"$f":"'K20 - time schedule'!GJ41","v":0},{"$f":"'K20 - time schedule'!GK41","v":0},{"$f":"'K20 - time schedule'!GL41","v":0},{"$f":"'K20 - time schedule'!GM41","v":0},{"$f":"'K20 - time schedule'!GN41","v":0},{"$f":"'K20 - time schedule'!GO41","v":0},{"$f":"'K20 - time schedule'!GP41","v":0},{"$f":"'K20 - time schedule'!GQ41","v":0},{"$f":"'K20 - time schedule'!GR41","v":0},{"$f":"'K20 - time schedule'!GS41","v":0},{"$f":"'K20 - time schedule'!GT41","v":0},{"$f":"'K20 - time schedule'!GU41","v":0},{"$f":"'K20 - time schedule'!GV41","v":0},{"$f":"'K20 - time schedule'!GW41","v":0},{"$f":"'K20 - time schedule'!GX41","v":0},{"$f":"'K20 - time schedule'!GY41","v":0},{"$f":"'K20 - time schedule'!GZ41","v":0},{"$f":"'K20 - time schedule'!HA41","v":0},{"$f":"'K20 - time schedule'!HB41","v":0},{"$f":"'K20 - time schedule'!HC41","v":0},{"$f":"'K20 - time schedule'!HD41","v":0},{"$f":"'K20 - time schedule'!HE41","v":0},{"$f":"'K20 - time schedule'!HF41","v":0},{"$f":"'K20 - time schedule'!HG41","v":0},{"$f":"'K20 - time schedule'!HH41","v":0},{"$f":"'K20 - time schedule'!HI41","v":0},{"$f":"'K20 - time schedule'!HJ41","v":0},{"$f":"'K20 - time schedule'!HK41","v":0},{"$f":"'K20 - time schedule'!HL41","v":0},{"$f":"'K20 - time schedule'!HM41","v":0},{"$f":"'K20 - time schedule'!HN41","v":0},{"$f":"'K20 - time schedule'!HO41","v":0},{"$f":"'K20 - time schedule'!HP41","v":0},{"$f":"'K20 - time schedule'!HQ41","v":0},{"$f":"'K20 - time schedule'!HR41","v":0},{"$f":"'K20 - time schedule'!HS41","v":0},{"$f":"'K20 - time schedule'!HT41","v":0},{"$f":"'K20 - time schedule'!HU41","v":0},{"$f":"'K20 - time schedule'!HV41","v":0},{"$f":"'K20 - time schedule'!HW41","v":0},{"$f":"'K20 - time schedule'!HX41","v":0},{"$f":"'K20 - time schedule'!HY41","v":0},{"$f":"'K20 - time schedule'!HZ41","v":0},{"$f":"'K20 - time schedule'!IA41","v":0},{"$f":"'K20 - time schedule'!IB41","v":0},{"$f":"'K20 - time schedule'!IC41","v":0},{"$f":"'K20 - time schedule'!ID41","v":0},{"$f":"'K20 - time schedule'!IE41","v":0},{"$f":"'K20 - time schedule'!IF41","v":0},{"$f":"'K20 - time schedule'!IG41","v":0},{"$f":"'K20 - time schedule'!IH41","v":0},{"$f":"'K20 - time schedule'!II41","v":0},{"$f":"'K20 - time schedule'!IJ41","v":0},{"$f":"'K20 - time schedule'!IK41","v":0},{"$f":"'K20 - time schedule'!IL41","v":0},{"$f":"'K20 - time schedule'!IM41","v":0},{"$f":"'K20 - time schedule'!IN41","v":0},{"$f":"'K20 - time schedule'!IO41","v":0},{"$f":"'K20 - time schedule'!IP41","v":0},{"$f":"'K20 - time schedule'!IQ41","v":0},{"$f":"'K20 - time schedule'!IR41","v":0},{"$f":"'K20 - time schedule'!IS41","v":0},{"$f":"'K20 - time schedule'!IT41","v":0},{"$f":"'K20 - time schedule'!IU41","v":0},{"$f":"'K20 - time schedule'!IV41","v":0},{"$f":"'K20 - time schedule'!IW41","v":0},{"$f":"'K20 - time schedule'!IX41","v":0},{"$f":"'K20 - time schedule'!IY41","v":0},{"$f":"'K20 - time schedule'!IZ41","v":0},{"$f":"'K20 - time schedule'!JA41","v":0},{"$f":"'K20 - time schedule'!JB41","v":0},{"$f":"'K20 - time schedule'!JC41","v":0},{"$f":"'K20 - time schedule'!JD41","v":0},{"$f":"'K20 - time schedule'!JE41","v":0},{"$f":"'K20 - time schedule'!JF41","v":0},{"$f":"'K20 - time schedule'!JG41","v":0},{"$f":"'K20 - time schedule'!JH41","v":0},{"$f":"'K20 - time schedule'!JI41","v":0},{"$f":"'K20 - time schedule'!JJ41","v":0},{"$f":"'K20 - time schedule'!JK41","v":0},{"$f":"'K20 - time schedule'!JL41","v":0},{"$f":"'K20 - time schedule'!JM41","v":0},{"$f":"'K20 - time schedule'!JN41","v":0},{"$f":"'K20 - time schedule'!JO41","v":0},{"$f":"'K20 - time schedule'!JP41","v":0},{"$f":"'K20 - time schedule'!JQ41","v":0},{"$f":"'K20 - time schedule'!JR41","v":0},{"$f":"'K20 - time schedule'!JS41","v":0},{"$f":"'K20 - time schedule'!JT41","v":0},{"$f":"'K20 - time schedule'!JU41","v":0},{"$f":"'K20 - time schedule'!JV41","v":0},{"$f":"'K20 - time schedule'!JW41","v":0},{"$f":"'K20 - time schedule'!JX41","v":0},{"$f":"'K20 - time schedule'!JY41","v":0},{"$f":"'K20 - time schedule'!JZ41","v":0},{"$f":"'K20 - time schedule'!KA41","v":0},{"$f":"'K20 - time schedule'!KB41","v":0},{"$f":"'K20 - time schedule'!KC41","v":0},{"$f":"'K20 - time schedule'!KD41","v":0},{"$f":"'K20 - time schedule'!KE41","v":0},{"$f":"'K20 - time schedule'!KF41","v":0},{"$f":"'K20 - time schedule'!KG41","v":0},{"$f":"'K20 - time schedule'!KH41","v":0},{"$f":"'K20 - time schedule'!KI41","v":0},{"$f":"'K20 - time schedule'!KJ41","v":0},{"$f":"'K20 - time schedule'!KK41","v":0},{"$f":"'K20 - time schedule'!KL41","v":0},{"$f":"'K20 - time schedule'!KM41","v":0},{"$f":"'K20 - time schedule'!KN41","v":0},{"$f":"'K20 - time schedule'!KO41","v":0},{"$f":"'K20 - time schedule'!KP41","v":0},{"$f":"'K20 - time schedule'!KQ41","v":0},{"$f":"'K20 - time schedule'!KR41","v":0},{"$f":"'K20 - time schedule'!KS41","v":0},{"$f":"'K20 - time schedule'!KT41","v":0}]
["Boiler room K80 - fuel silos, including transport of fuel to the boiler","K80","EUR",{"$f":"'K80 - time schedule'!G25","v":0},{"$f":"'K80 - time schedule'!H25","v":0},{"$f":"'K80 - time schedule'!I25","v":0},{"$f":"'K80 - time schedule'!J25","v":0},{"$f":"'K80 - time schedule'!K25","v":0},{"$f":"'K80 - time schedule'!L25","v":0},{"$f":"'K80 - time schedule'!M25","v":0},{"$f":"'K80 - time schedule'!N25","v":0},{"$f":"'K80 - time schedule'!O25","v":0},{"$f":"'K80 - time schedule'!P25","v":0},{"$f":"'K80 - time schedule'!Q25","v":0},{"$f":"'K80 - time schedule'!R25","v":0},{"$f":"'K80 - time schedule'!S25","v":0},{"$f":"'K80 - time schedule'!T25","v":0},{"$f":"'K80 - time schedule'!U25","v":0},{"$f":"'K80 - time schedule'!V25","v":0},{"$f":"'K80 - time schedule'!W25","v":0},{"$f":"'K80 - time schedule'!X25","v":0},{"$f":"'K80 - time schedule'!Y25","v":0},{"$f":"'K80 - time schedule'!Z25","v":0},{"$f":"'K80 - time schedule'!AA25","v":0},{"$f":"'K80 - time schedule'!AB25","v":0},{"$f":"'K80 - time schedule'!AC25","v":0},{"$f":"'K80 - time schedule'!AD25","v":0},{"$f":"'K80 - time schedule'!AE25","v":0},{"$f":"'K80 - time schedule'!AF25","v":0},{"$f":"'K80 - time schedule'!AG25","v":0},{"$f":"'K80 - time schedule'!AH25","v":0},{"$f":"'K80 - time schedule'!AI25","v":0},{"$f":"'K80 - time schedule'!AJ25","v":0},{"$f":"'K80 - time schedule'!AK25","v":0},{"$f":"'K80 - time schedule'!AL25","v":0},{"$f":"'K80 - time schedule'!AM25","v":0},{"$f":"'K80 - time schedule'!AN25","v":0},{"$f":"'K80 - time schedule'!AO25","v":0},{"$f":"'K80 - time schedule'!AP25","v":0},{"$f":"'K80 - time schedule'!AQ25","v":0},{"$f":"'K80 - time schedule'!AR25","v":0},{"$f":"'K80 - time schedule'!AS25","v":0},{"$f":"'K80 - time schedule'!AT25","v":0},{"$f":"'K80 - time schedule'!AU25","v":0},{"$f":"'K80 - time schedule'!AV25","v":0},{"$f":"'K80 - time schedule'!AW25","v":0},{"$f":"'K80 - time schedule'!AX25","v":0},{"$f":"'K80 - time schedule'!AY25","v":0},{"$f":"'K80 - time schedule'!AZ25","v":0},{"$f":"'K80 - time schedule'!BA25","v":0},{"$f":"'K80 - time schedule'!BB25","v":0},{"$f":"'K80 - time schedule'!BC25","v":0},{"$f":"'K80 - time schedule'!BD25","v":0},{"$f":"'K80 - time schedule'!BE25","v":0},{"$f":"'K80 - time schedule'!BF25","v":0},{"$f":"'K80 - time schedule'!BG25","v":0},{"$f":"'K80 - time schedule'!BH25","v":0},{"$f":"'K80 - time schedule'!BI25","v":0},{"$f":"'K80 - time schedule'!BJ25","v":0},{"$f":"'K80 - time schedule'!BK25","v":0},{"$f":"'K80 - time schedule'!BL25","v":0},{"$f":"'K80 - time schedule'!BM25","v":0},{"$f":"'K80 - time schedule'!BN25","v":0},{"$f":"'K80 - time schedule'!BO25","v":0},{"$f":"'K80 - time schedule'!BP25","v":0},{"$f":"'K80 - time schedule'!BQ25","v":0},{"$f":"'K80 - time schedule'!BR25","v":0},{"$f":"'K80 - time schedule'!BS25","v":0},{"$f":"'K80 - time schedule'!BT25","v":0},{"$f":"'K80 - time schedule'!BU25","v":0},{"$f":"'K80 - time schedule'!BV25","v":0},{"$f":"'K80 - time schedule'!BW25","v":0},{"$f":"'K80 - time schedule'!BX25","v":0},{"$f":"'K80 - time schedule'!BY25","v":0},{"$f":"'K80 - time schedule'!BZ25","v":0},{"$f":"'K80 - time schedule'!CA25","v":0},{"$f":"'K80 - time schedule'!CB25","v":0},{"$f":"'K80 - time schedule'!CC25","v":0},{"$f":"'K80 - time schedule'!CD25","v":0},{"$f":"'K80 - time schedule'!CE25","v":0},{"$f":"'K80 - time schedule'!CF25","v":0},{"$f":"'K80 - time schedule'!CG25","v":0},{"$f":"'K80 - time schedule'!CH25","v":0},{"$f":"'K80 - time schedule'!CI25","v":0},{"$f":"'K80 - time schedule'!CJ25","v":0},{"$f":"'K80 - time schedule'!CK25","v":0},{"$f":"'K80 - time schedule'!CL25","v":0},{"$f":"'K80 - time schedule'!CM25","v":0},{"$f":"'K80 - time schedule'!CN25","v":0},{"$f":"'K80 - time schedule'!CO25","v":0},{"$f":"'K80 - time schedule'!CP25","v":0},{"$f":"'K80 - time schedule'!CQ25","v":0},{"$f":"'K80 - time schedule'!CR25","v":0},{"$f":"'K80 - time schedule'!CS25","v":0},{"$f":"'K80 - time schedule'!CT25","v":0},{"$f":"'K80 - time schedule'!CU25","v":0},{"$f":"'K80 - time schedule'!CV25","v":0},{"$f":"'K80 - time schedule'!CW25","v":0},{"$f":"'K80 - time schedule'!CX25","v":0},{"$f":"'K80 - time schedule'!CY25","v":0},{"$f":"'K80 - time schedule'!CZ25","v":0},{"$f":"'K80 - time schedule'!DA25","v":0},{"$f":"'K80 - time schedule'!DB25","v":0},{"$f":"'K80 - time schedule'!DC25","v":0},{"$f":"'K80 - time schedule'!DD25","v":0},{"$f":"'K80 - time schedule'!DE25","v":0},{"$f":"'K80 - time schedule'!DF25","v":0},{"$f":"'K80 - time schedule'!DG25","v":0},{"$f":"'K80 - time schedule'!DH25","v":0},{"$f":"'K80 - time schedule'!DI25","v":0},{"$f":"'K80 - time schedule'!DJ25","v":0},{"$f":"'K80 - time schedule'!DK25","v":0},{"$f":"'K80 - time schedule'!DL25","v":0},{"$f":"'K80 - time schedule'!DM25","v":0},{"$f":"'K80 - time schedule'!DN25","v":0},{"$f":"'K80 - time schedule'!DO25","v":0},{"$f":"'K80 - time schedule'!DP25","v":0},{"$f":"'K80 - time schedule'!DQ25","v":0},{"$f":"'K80 - time schedule'!DR25","v":0},{"$f":"'K80 - time schedule'!DS25","v":0},{"$f":"'K80 - time schedule'!DT25","v":0},{"$f":"'K80 - time schedule'!DU25","v":0},{"$f":"'K80 - time schedule'!DV25","v":0},{"$f":"'K80 - time schedule'!DW25","v":0},{"$f":"'K80 - time schedule'!DX25","v":0},{"$f":"'K80 - time schedule'!DY25","v":0},{"$f":"'K80 - time schedule'!DZ25","v":0},{"$f":"'K80 - time schedule'!EA25","v":0},{"$f":"'K80 - time schedule'!EB25","v":0},{"$f":"'K80 - time schedule'!EC25","v":0},{"$f":"'K80 - time schedule'!ED25","v":0},{"$f":"'K80 - time schedule'!EE25","v":0},{"$f":"'K80 - time schedule'!EF25","v":0},{"$f":"'K80 - time schedule'!EG25","v":0},{"$f":"'K80 - time schedule'!EH25","v":0},{"$f":"'K80 - time schedule'!EI25","v":0},{"$f":"'K80 - time schedule'!EJ25","v":0},{"$f":"'K80 - time schedule'!EK25","v":0},{"$f":"'K80 - time schedule'!EL25","v":0},{"$f":"'K80 - time schedule'!EM25","v":0},{"$f":"'K80 - time schedule'!EN25","v":0},{"$f":"'K80 - time schedule'!EO25","v":0},{"$f":"'K80 - time schedule'!EP25","v":0},{"$f":"'K80 - time schedule'!EQ25","v":0},{"$f":"'K80 - time schedule'!ER25","v":0},{"$f":"'K80 - time schedule'!ES25","v":0},{"$f":"'K80 - time schedule'!ET25","v":0},{"$f":"'K80 - time schedule'!EU25","v":0},{"$f":"'K80 - time schedule'!EV25","v":0},{"$f":"'K80 - time schedule'!EW25","v":0},{"$f":"'K80 - time schedule'!EX25","v":0},{"$f":"'K80 - time schedule'!EY25","v":0},{"$f":"'K80 - time schedule'!EZ25","v":0},{"$f":"'K80 - time schedule'!FA25","v":0},{"$f":"'K80 - time schedule'!FB25","v":0},{"$f":"'K80 - time schedule'!FC25","v":0},{"$f":"'K80 - time schedule'!FD25","v":0},{"$f":"'K80 - time schedule'!FE25","v":0},{"$f":"'K80 - time schedule'!FF25","v":0},{"$f":"'K80 - time schedule'!FG25","v":0},{"$f":"'K80 - time schedule'!FH25","v":0},{"$f":"'K80 - time schedule'!FI25","v":0},{"$f":"'K80 - time schedule'!FJ25","v":0},{"$f":"'K80 - time schedule'!FK25","v":0},{"$f":"'K80 - time schedule'!FL25","v":0},{"$f":"'K80 - time schedule'!FM25","v":0},{"$f":"'K80 - time schedule'!FN25","v":0},{"$f":"'K80 - time schedule'!FO25","v":0},{"$f":"'K80 - time schedule'!FP25","v":0},{"$f":"'K80 - time schedule'!FQ25","v":0},{"$f":"'K80 - time schedule'!FR25","v":0},{"$f":"'K80 - time schedule'!FS25","v":0},{"$f":"'K80 - time schedule'!FT25","v":0},{"$f":"'K80 - time schedule'!FU25","v":0},{"$f":"'K80 - time schedule'!FV25","v":0},{"$f":"'K80 - time schedule'!FW25","v":0},{"$f":"'K80 - time schedule'!FX25","v":0},{"$f":"'K80 - time schedule'!FY25","v":0},{"$f":"'K80 - time schedule'!FZ25","v":0},{"$f":"'K80 - time schedule'!GA25","v":0},{"$f":"'K80 - time schedule'!GB25","v":0},{"$f":"'K80 - time schedule'!GC25","v":0},{"$f":"'K80 - time schedule'!GD25","v":0},{"$f":"'K80 - time schedule'!GE25","v":0},{"$f":"'K80 - time schedule'!GF25","v":0},{"$f":"'K20 - time schedule'!GG42","v":0},{"$f":"'K20 - time schedule'!GH42","v":0},{"$f":"'K20 - time schedule'!GI42","v":0},{"$f":"'K20 - time schedule'!GJ42","v":0},{"$f":"'K20 - time schedule'!GK42","v":0},{"$f":"'K20 - time schedule'!GL42","v":0},{"$f":"'K20 - time schedule'!GM42","v":0},{"$f":"'K20 - time schedule'!GN42","v":0},{"$f":"'K20 - time schedule'!GO42","v":0},{"$f":"'K20 - time schedule'!GP42","v":0},{"$f":"'K20 - time schedule'!GQ42","v":0},{"$f":"'K20 - time schedule'!GR42","v":0},{"$f":"'K20 - time schedule'!GS42","v":0},{"$f":"'K20 - time schedule'!GT42","v":0},{"$f":"'K20 - time schedule'!GU42","v":0},{"$f":"'K20 - time schedule'!GV42","v":0},{"$f":"'K20 - time schedule'!GW42","v":0},{"$f":"'K20 - time schedule'!GX42","v":0},{"$f":"'K20 - time schedule'!GY42","v":0},{"$f":"'K20 - time schedule'!GZ42","v":0},{"$f":"'K20 - time schedule'!HA42","v":0},{"$f":"'K20 - time schedule'!HB42","v":0},{"$f":"'K20 - time schedule'!HC42","v":0},{"$f":"'K20 - time schedule'!HD42","v":0},{"$f":"'K20 - time schedule'!HE42","v":0},{"$f":"'K20 - time schedule'!HF42","v":0},{"$f":"'K20 - time schedule'!HG42","v":0},{"$f":"'K20 - time schedule'!HH42","v":0},{"$f":"'K20 - time schedule'!HI42","v":0},{"$f":"'K20 - time schedule'!HJ42","v":0},{"$f":"'K20 - time schedule'!HK42","v":0},{"$f":"'K20 - time schedule'!HL42","v":0},{"$f":"'K20 - time schedule'!HM42","v":0},{"$f":"'K20 - time schedule'!HN42","v":0},{"$f":"'K20 - time schedule'!HO42","v":0},{"$f":"'K20 - time schedule'!HP42","v":0},{"$f":"'K20 - time schedule'!HQ42","v":0},{"$f":"'K20 - time schedule'!HR42","v":0},{"$f":"'K20 - time schedule'!HS42","v":0},{"$f":"'K20 - time schedule'!HT42","v":0},{"$f":"'K20 - time schedule'!HU42","v":0},{"$f":"'K20 - time schedule'!HV42","v":0},{"$f":"'K20 - time schedule'!HW42","v":0},{"$f":"'K20 - time schedule'!HX42","v":0},{"$f":"'K20 - time schedule'!HY42","v":0},{"$f":"'K20 - time schedule'!HZ42","v":0},{"$f":"'K20 - time schedule'!IA42","v":0},{"$f":"'K20 - time schedule'!IB42","v":0},{"$f":"'K20 - time schedule'!IC42","v":0},{"$f":"'K20 - time schedule'!ID42","v":0},{"$f":"'K20 - time schedule'!IE42","v":0},{"$f":"'K20 - time schedule'!IF42","v":0},{"$f":"'K20 - time schedule'!IG42","v":0},{"$f":"'K20 - time schedule'!IH42","v":0},{"$f":"'K20 - time schedule'!II42","v":0},{"$f":"'K20 - time schedule'!IJ42","v":0},{"$f":"'K20 - time schedule'!IK42","v":0},{"$f":"'K20 - time schedule'!IL42","v":0},{"$f":"'K20 - time schedule'!IM42","v":0},{"$f":"'K20 - time schedule'!IN42","v":0},{"$f":"'K20 - time schedule'!IO42","v":0},{"$f":"'K20 - time schedule'!IP42","v":0},{"$f":"'K20 - time schedule'!IQ42","v":0},{"$f":"'K20 - time schedule'!IR42","v":0},{"$f":"'K20 - time schedule'!IS42","v":0},{"$f":"'K20 - time schedule'!IT42","v":0},{"$f":"'K20 - time schedule'!IU42","v":0},{"$f":"'K20 - time schedule'!IV42","v":0},{"$f":"'K20 - time schedule'!IW42","v":0},{"$f":"'K20 - time schedule'!IX42","v":0},{"$f":"'K20 - time schedule'!IY42","v":0},{"$f":"'K20 - time schedule'!IZ42","v":0},{"$f":"'K20 - time schedule'!JA42","v":0},{"$f":"'K20 - time schedule'!JB42","v":0},{"$f":"'K20 - time schedule'!JC42","v":0},{"$f":"'K20 - time schedule'!JD42","v":0},{"$f":"'K20 - time schedule'!JE42","v":0},{"$f":"'K20 - time schedule'!JF42","v":0},{"$f":"'K20 - time schedule'!JG42","v":0},{"$f":"'K20 - time schedule'!JH42","v":0},{"$f":"'K20 - time schedule'!JI42","v":0},{"$f":"'K20 - time schedule'!JJ42","v":0},{"$f":"'K20 - time schedule'!JK42","v":0},{"$f":"'K20 - time schedule'!JL42","v":0},{"$f":"'K20 - time schedule'!JM42","v":0},{"$f":"'K20 - time schedule'!JN42","v":0},{"$f":"'K20 - time schedule'!JO42","v":0},{"$f":"'K20 - time schedule'!JP42","v":0},{"$f":"'K20 - time schedule'!JQ42","v":0},{"$f":"'K20 - time schedule'!JR42","v":0},{"$f":"'K20 - time schedule'!JS42","v":0},{"$f":"'K20 - time schedule'!JT42","v":0},{"$f":"'K20 - time schedule'!JU42","v":0},{"$f":"'K20 - time schedule'!JV42","v":0},{"$f":"'K20 - time schedule'!JW42","v":0},{"$f":"'K20 - time schedule'!JX42","v":0},{"$f":"'K20 - time schedule'!JY42","v":0},{"$f":"'K20 - time schedule'!JZ42","v":0},{"$f":"'K20 - time schedule'!KA42","v":0},{"$f":"'K20 - time schedule'!KB42","v":0},{"$f":"'K20 - time schedule'!KC42","v":0},{"$f":"'K20 - time schedule'!KD42","v":0},{"$f":"'K20 - time schedule'!KE42","v":0},{"$f":"'K20 - time schedule'!KF42","v":0},{"$f":"'K20 - time schedule'!KG42","v":0},{"$f":"'K20 - time schedule'!KH42","v":0},{"$f":"'K20 - time schedule'!KI42","v":0},{"$f":"'K20 - time schedule'!KJ42","v":0},{"$f":"'K20 - time schedule'!KK42","v":0},{"$f":"'K20 - time schedule'!KL42","v":0},{"$f":"'K20 - time schedule'!KM42","v":0},{"$f":"'K20 - time schedule'!KN42","v":0},{"$f":"'K20 - time schedule'!KO42","v":0},{"$f":"'K20 - time schedule'!KP42","v":0},{"$f":"'K20 - time schedule'!KQ42","v":0},{"$f":"'K20 - time schedule'!KR42","v":0},{"$f":"'K20 - time schedule'!KS42","v":0},{"$f":"'K20 - time schedule'!KT42","v":0}]
["Boiler room K80 - air heating","K80","EUR",{"$f":"'K80 - time schedule'!G27","v":0},{"$f":"'K80 - time schedule'!H27","v":0},{"$f":"'K80 - time schedule'!I27","v":0},{"$f":"'K80 - time schedule'!J27","v":0},{"$f":"'K80 - time schedule'!K27","v":0},{"$f":"'K80 - time schedule'!L27","v":0},{"$f":"'K80 - time schedule'!M27","v":0},{"$f":"'K80 - time schedule'!N27","v":0},{"$f":"'K80 - time schedule'!O27","v":0},{"$f":"'K80 - time schedule'!P27","v":0},{"$f":"'K80 - time schedule'!Q27","v":0},{"$f":"'K80 - time schedule'!R27","v":0},{"$f":"'K80 - time schedule'!S27","v":0},{"$f":"'K80 - time schedule'!T27","v":0},{"$f":"'K80 - time schedule'!U27","v":0},{"$f":"'K80 - time schedule'!V27","v":0},{"$f":"'K80 - time schedule'!W27","v":0},{"$f":"'K80 - time schedule'!X27","v":0},{"$f":"'K80 - time schedule'!Y27","v":0},{"$f":"'K80 - time schedule'!Z27","v":0},{"$f":"'K80 - time schedule'!AA27","v":0},{"$f":"'K80 - time schedule'!AB27","v":0},{"$f":"'K80 - time schedule'!AC27","v":0},{"$f":"'K80 - time schedule'!AD27","v":0},{"$f":"'K80 - time schedule'!AE27","v":0},{"$f":"'K80 - time schedule'!AF27","v":0},{"$f":"'K80 - time schedule'!AG27","v":0},{"$f":"'K80 - time schedule'!AH27","v":0},{"$f":"'K80 - time schedule'!AI27","v":0},{"$f":"'K80 - time schedule'!AJ27","v":0},{"$f":"'K80 - time schedule'!AK27","v":0},{"$f":"'K80 - time schedule'!AL27","v":0},{"$f":"'K80 - time schedule'!AM27","v":0},{"$f":"'K80 - time schedule'!AN27","v":0},{"$f":"'K80 - time schedule'!AO27","v":0},{"$f":"'K80 - time schedule'!AP27","v":0},{"$f":"'K80 - time schedule'!AQ27","v":0},{"$f":"'K80 - time schedule'!AR27","v":0},{"$f":"'K80 - time schedule'!AS27","v":0},{"$f":"'K80 - time schedule'!AT27","v":0},{"$f":"'K80 - time schedule'!AU27","v":0},{"$f":"'K80 - time schedule'!AV27","v":0},{"$f":"'K80 - time schedule'!AW27","v":0},{"$f":"'K80 - time schedule'!AX27","v":0},{"$f":"'K80 - time schedule'!AY27","v":0},{"$f":"'K80 - time schedule'!AZ27","v":0},{"$f":"'K80 - time schedule'!BA27","v":0},{"$f":"'K80 - time schedule'!BB27","v":0},{"$f":"'K80 - time schedule'!BC27","v":0},{"$f":"'K80 - time schedule'!BD27","v":0},{"$f":"'K80 - time schedule'!BE27","v":0},{"$f":"'K80 - time schedule'!BF27","v":0},{"$f":"'K80 - time schedule'!BG27","v":0},{"$f":"'K80 - time schedule'!BH27","v":0},{"$f":"'K80 - time schedule'!BI27","v":0},{"$f":"'K80 - time schedule'!BJ27","v":0},{"$f":"'K80 - time schedule'!BK27","v":0},{"$f":"'K80 - time schedule'!BL27","v":0},{"$f":"'K80 - time schedule'!BM27","v":0},{"$f":"'K80 - time schedule'!BN27","v":0},{"$f":"'K80 - time schedule'!BO27","v":0},{"$f":"'K80 - time schedule'!BP27","v":0},{"$f":"'K80 - time schedule'!BQ27","v":0},{"$f":"'K80 - time schedule'!BR27","v":0},{"$f":"'K80 - time schedule'!BS27","v":0},{"$f":"'K80 - time schedule'!BT27","v":0},{"$f":"'K80 - time schedule'!BU27","v":0},{"$f":"'K80 - time schedule'!BV27","v":0},{"$f":"'K80 - time schedule'!BW27","v":0},{"$f":"'K80 - time schedule'!BX27","v":0},{"$f":"'K80 - time schedule'!BY27","v":0},{"$f":"'K80 - time schedule'!BZ27","v":0},{"$f":"'K80 - time schedule'!CA27","v":0},{"$f":"'K80 - time schedule'!CB27","v":0},{"$f":"'K80 - time schedule'!CC27","v":0},{"$f":"'K80 - time schedule'!CD27","v":0},{"$f":"'K80 - time schedule'!CE27","v":0},{"$f":"'K80 - time schedule'!CF27","v":0},{"$f":"'K80 - time schedule'!CG27","v":0},{"$f":"'K80 - time schedule'!CH27","v":0},{"$f":"'K80 - time schedule'!CI27","v":0},{"$f":"'K80 - time schedule'!CJ27","v":0},{"$f":"'K80 - time schedule'!CK27","v":0},{"$f":"'K80 - time schedule'!CL27","v":0},{"$f":"'K80 - time schedule'!CM27","v":0},{"$f":"'K80 - time schedule'!CN27","v":0},{"$f":"'K80 - time schedule'!CO27","v":0},{"$f":"'K80 - time schedule'!CP27","v":0},{"$f":"'K80 - time schedule'!CQ27","v":0},{"$f":"'K80 - time schedule'!CR27","v":0},{"$f":"'K80 - time schedule'!CS27","v":0},{"$f":"'K80 - time schedule'!CT27","v":0},{"$f":"'K80 - time schedule'!CU27","v":0},{"$f":"'K80 - time schedule'!CV27","v":0},{"$f":"'K80 - time schedule'!CW27","v":0},{"$f":"'K80 - time schedule'!CX27","v":0},{"$f":"'K80 - time schedule'!CY27","v":0},{"$f":"'K80 - time schedule'!CZ27","v":0},{"$f":"'K80 - time schedule'!DA27","v":0},{"$f":"'K80 - time schedule'!DB27","v":0},{"$f":"'K80 - time schedule'!DC27","v":0},{"$f":"'K80 - time schedule'!DD27","v":0},{"$f":"'K80 - time schedule'!DE27","v":0},{"$f":"'K80 - time schedule'!DF27","v":0},{"$f":"'K80 - time schedule'!DG27","v":0},{"$f":"'K80 - time schedule'!DH27","v":0},{"$f":"'K80 - time schedule'!DI27","v":0},{"$f":"'K80 - time schedule'!DJ27","v":0},{"$f":"'K80 - time schedule'!DK27","v":0},{"$f":"'K80 - time schedule'!DL27","v":0},{"$f":"'K80 - time schedule'!DM27","v":0},{"$f":"'K80 - time schedule'!DN27","v":0},{"$f":"'K80 - time schedule'!DO27","v":0},{"$f":"'K80 - time schedule'!DP27","v":0},{"$f":"'K80 - time schedule'!DQ27","v":0},{"$f":"'K80 - time schedule'!DR27","v":0},{"$f":"'K80 - time schedule'!DS27","v":0},{"$f":"'K80 - time schedule'!DT27","v":0},{"$f":"'K80 - time schedule'!DU27","v":0},{"$f":"'K80 - time schedule'!DV27","v":0},{"$f":"'K80 - time schedule'!DW27","v":0},{"$f":"'K80 - time schedule'!DX27","v":0},{"$f":"'K80 - time schedule'!DY27","v":0},{"$f":"'K80 - time schedule'!DZ27","v":0},{"$f":"'K80 - time schedule'!EA27","v":0},{"$f":"'K80 - time schedule'!EB27","v":0},{"$f":"'K80 - time schedule'!EC27","v":0},{"$f":"'K80 - time schedule'!ED27","v":0},{"$f":"'K80 - time schedule'!EE27","v":0},{"$f":"'K80 - time schedule'!EF27","v":0},{"$f":"'K80 - time schedule'!EG27","v":0},{"$f":"'K80 - time schedule'!EH27","v":0},{"$f":"'K80 - time schedule'!EI27","v":0},{"$f":"'K80 - time schedule'!EJ27","v":0},{"$f":"'K80 - time schedule'!EK27","v":0},{"$f":"'K80 - time schedule'!EL27","v":0},{"$f":"'K80 - time schedule'!EM27","v":0},{"$f":"'K80 - time schedule'!EN27","v":0},{"$f":"'K80 - time schedule'!EO27","v":0},{"$f":"'K80 - time schedule'!EP27","v":0},{"$f":"'K80 - time schedule'!EQ27","v":0},{"$f":"'K80 - time schedule'!ER27","v":0},{"$f":"'K80 - time schedule'!ES27","v":0},{"$f":"'K80 - time schedule'!ET27","v":0},{"$f":"'K80 - time schedule'!EU27","v":0},{"$f":"'K80 - time schedule'!EV27","v":0},{"$f":"'K80 - time schedule'!EW27","v":0},{"$f":"'K80 - time schedule'!EX27","v":0},{"$f":"'K80 - time schedule'!EY27","v":0},{"$f":"'K80 - time schedule'!EZ27","v":0},{"$f":"'K80 - time schedule'!FA27","v":0},{"$f":"'K80 - time schedule'!FB27","v":0},{"$f":"'K80 - time schedule'!FC27","v":0},{"$f":"'K80 - time schedule'!FD27","v":0},{"$f":"'K80 - time schedule'!FE27","v":0},{"$f":"'K80 - time schedule'!FF27","v":0},{"$f":"'K80 - time schedule'!FG27","v":0},{"$f":"'K80 - time schedule'!FH27","v":0},{"$f":"'K80 - time schedule'!FI27","v":0},{"$f":"'K80 - time schedule'!FJ27","v":0},{"$f":"'K80 - time schedule'!FK27","v":0},{"$f":"'K80 - time schedule'!FL27","v":0},{"$f":"'K80 - time schedule'!FM27","v":0},{"$f":"'K80 - time schedule'!FN27","v":0},{"$f":"'K80 - time schedule'!FO27","v":0},{"$f":"'K80 - time schedule'!FP27","v":0},{"$f":"'K80 - time schedule'!FQ27","v":0},{"$f":"'K80 - time schedule'!FR27","v":0},{"$f":"'K80 - time schedule'!FS27","v":0},{"$f":"'K80 - time schedule'!FT27","v":0},{"$f":"'K80 - time schedule'!FU27","v":0},{"$f":"'K80 - time schedule'!FV27","v":0},{"$f":"'K80 - time schedule'!FW27","v":0},{"$f":"'K80 - time schedule'!FX27","v":0},{"$f":"'K80 - time schedule'!FY27","v":0},{"$f":"'K80 - time schedule'!FZ27","v":0},{"$f":"'K80 - time schedule'!GA27","v":0},{"$f":"'K80 - time schedule'!GB27","v":0},{"$f":"'K80 - time schedule'!GC27","v":0},{"$f":"'K80 - time schedule'!GD27","v":0},{"$f":"'K80 - time schedule'!GE27","v":0},{"$f":"'K80 - time schedule'!GF27","v":0},{"$f":"'K20 - time schedule'!GG43","v":0},{"$f":"'K20 - time schedule'!GH43","v":0},{"$f":"'K20 - time schedule'!GI43","v":0},{"$f":"'K20 - time schedule'!GJ43","v":0},{"$f":"'K20 - time schedule'!GK43","v":0},{"$f":"'K20 - time schedule'!GL43","v":0},{"$f":"'K20 - time schedule'!GM43","v":0},{"$f":"'K20 - time schedule'!GN43","v":0},{"$f":"'K20 - time schedule'!GO43","v":0},{"$f":"'K20 - time schedule'!GP43","v":0},{"$f":"'K20 - time schedule'!GQ43","v":0},{"$f":"'K20 - time schedule'!GR43","v":0},{"$f":"'K20 - time schedule'!GS43","v":0},{"$f":"'K20 - time schedule'!GT43","v":0},{"$f":"'K20 - time schedule'!GU43","v":0},{"$f":"'K20 - time schedule'!GV43","v":0},{"$f":"'K20 - time schedule'!GW43","v":0},{"$f":"'K20 - time schedule'!GX43","v":0},{"$f":"'K20 - time schedule'!GY43","v":0},{"$f":"'K20 - time schedule'!GZ43","v":0},{"$f":"'K20 - time schedule'!HA43","v":0},{"$f":"'K20 - time schedule'!HB43","v":0},{"$f":"'K20 - time schedule'!HC43","v":0},{"$f":"'K20 - time schedule'!HD43","v":0},{"$f":"'K20 - time schedule'!HE43","v":0},{"$f":"'K20 - time schedule'!HF43","v":0},{"$f":"'K20 - time schedule'!HG43","v":0},{"$f":"'K20 - time schedule'!HH43","v":0},{"$f":"'K20 - time schedule'!HI43","v":0},{"$f":"'K20 - time schedule'!HJ43","v":0},{"$f":"'K20 - time schedule'!HK43","v":0},{"$f":"'K20 - time schedule'!HL43","v":0},{"$f":"'K20 - time schedule'!HM43","v":0},{"$f":"'K20 - time schedule'!HN43","v":0},{"$f":"'K20 - time schedule'!HO43","v":0},{"$f":"'K20 - time schedule'!HP43","v":0},{"$f":"'K20 - time schedule'!HQ43","v":0},{"$f":"'K20 - time schedule'!HR43","v":0},{"$f":"'K20 - time schedule'!HS43","v":0},{"$f":"'K20 - time schedule'!HT43","v":0},{"$f":"'K20 - time schedule'!HU43","v":0},{"$f":"'K20 - time schedule'!HV43","v":0},{"$f":"'K20 - time schedule'!HW43","v":0},{"$f":"'K20 - time schedule'!HX43","v":0},{"$f":"'K20 - time schedule'!HY43","v":0},{"$f":"'K20 - time schedule'!HZ43","v":0},{"$f":"'K20 - time schedule'!IA43","v":0},{"$f":"'K20 - time schedule'!IB43","v":0},{"$f":"'K20 - time schedule'!IC43","v":0},{"$f":"'K20 - time schedule'!ID43","v":0},{"$f":"'K20 - time schedule'!IE43","v":0},{"$f":"'K20 - time schedule'!IF43","v":0},{"$f":"'K20 - time schedule'!IG43","v":0},{"$f":"'K20 - time schedule'!IH43","v":0},{"$f":"'K20 - time schedule'!II43","v":0},{"$f":"'K20 - time schedule'!IJ43","v":0},{"$f":"'K20 - time schedule'!IK43","v":0},{"$f":"'K20 - time schedule'!IL43","v":0},{"$f":"'K20 - time schedule'!IM43","v":0},{"$f":"'K20 - time schedule'!IN43","v":0},{"$f":"'K20 - time schedule'!IO43","v":0},{"$f":"'K20 - time schedule'!IP43","v":0},{"$f":"'K20 - time schedule'!IQ43","v":0},{"$f":"'K20 - time schedule'!IR43","v":0},{"$f":"'K20 - time schedule'!IS43","v":0},{"$f":"'K20 - time schedule'!IT43","v":0},{"$f":"'K20 - time schedule'!IU43","v":0},{"$f":"'K20 - time schedule'!IV43","v":0},{"$f":"'K20 - time schedule'!IW43","v":0},{"$f":"'K20 - time schedule'!IX43","v":0},{"$f":"'K20 - time schedule'!IY43","v":0},{"$f":"'K20 - time schedule'!IZ43","v":0},{"$f":"'K20 - time schedule'!JA43","v":0},{"$f":"'K20 - time schedule'!JB43","v":0},{"$f":"'K20 - time schedule'!JC43","v":0},{"$f":"'K20 - time schedule'!JD43","v":0},{"$f":"'K20 - time schedule'!JE43","v":0},{"$f":"'K20 - time schedule'!JF43","v":0},{"$f":"'K20 - time schedule'!JG43","v":0},{"$f":"'K20 - time schedule'!JH43","v":0},{"$f":"'K20 - time schedule'!JI43","v":0},{"$f":"'K20 - time schedule'!JJ43","v":0},{"$f":"'K20 - time schedule'!JK43","v":0},{"$f":"'K20 - time schedule'!JL43","v":0},{"$f":"'K20 - time schedule'!JM43","v":0},{"$f":"'K20 - time schedule'!JN43","v":0},{"$f":"'K20 - time schedule'!JO43","v":0},{"$f":"'K20 - time schedule'!JP43","v":0},{"$f":"'K20 - time schedule'!JQ43","v":0},{"$f":"'K20 - time schedule'!JR43","v":0},{"$f":"'K20 - time schedule'!JS43","v":0},{"$f":"'K20 - time schedule'!JT43","v":0},{"$f":"'K20 - time schedule'!JU43","v":0},{"$f":"'K20 - time schedule'!JV43","v":0},{"$f":"'K20 - time schedule'!JW43","v":0},{"$f":"'K20 - time schedule'!JX43","v":0},{"$f":"'K20 - time schedule'!JY43","v":0},{"$f":"'K20 - time schedule'!JZ43","v":0},{"$f":"'K20 - time schedule'!KA43","v":0},{"$f":"'K20 - time schedule'!KB43","v":0},{"$f":"'K20 - time schedule'!KC43","v":0},{"$f":"'K20 - time schedule'!KD43","v":0},{"$f":"'K20 - time schedule'!KE43","v":0},{"$f":"'K20 - time schedule'!KF43","v":0},{"$f":"'K20 - time schedule'!KG43","v":0},{"$f":"'K20 - time schedule'!KH43","v":0},{"$f":"'K20 - time schedule'!KI43","v":0},{"$f":"'K20 - time schedule'!KJ43","v":0},{"$f":"'K20 - time schedule'!KK43","v":0},{"$f":"'K20 - time schedule'!KL43","v":0},{"$f":"'K20 - time schedule'!KM43","v":0},{"$f":"'K20 - time schedule'!KN43","v":0},{"$f":"'K20 - time schedule'!KO43","v":0},{"$f":"'K20 - time schedule'!KP43","v":0},{"$f":"'K20 - time schedule'!KQ43","v":0},{"$f":"'K20 - time schedule'!KR43","v":0},{"$f":"'K20 - time schedule'!KS43","v":0},{"$f":"'K20 - time schedule'!KT43","v":0}]
["Boiler room K80 - overheating","K80","EUR",{"$f":"'K80 - time schedule'!G29","v":0},{"$f":"'K80 - time schedule'!H29","v":0},{"$f":"'K80 - time schedule'!I29","v":0},{"$f":"'K80 - time schedule'!J29","v":0},{"$f":"'K80 - time schedule'!K29","v":0},{"$f":"'K80 - time schedule'!L29","v":0},{"$f":"'K80 - time schedule'!M29","v":0},{"$f":"'K80 - time schedule'!N29","v":0},{"$f":"'K80 - time schedule'!O29","v":0},{"$f":"'K80 - time schedule'!P29","v":0},{"$f":"'K80 - time schedule'!Q29","v":0},{"$f":"'K80 - time schedule'!R29","v":0},{"$f":"'K80 - time schedule'!S29","v":0},{"$f":"'K80 - time schedule'!T29","v":0},{"$f":"'K80 - time schedule'!U29","v":0},{"$f":"'K80 - time schedule'!V29","v":0},{"$f":"'K80 - time schedule'!W29","v":0},{"$f":"'K80 - time schedule'!X29","v":0},{"$f":"'K80 - time schedule'!Y29","v":0},{"$f":"'K80 - time schedule'!Z29","v":0},{"$f":"'K80 - time schedule'!AA29","v":0},{"$f":"'K80 - time schedule'!AB29","v":0},{"$f":"'K80 - time schedule'!AC29","v":0},{"$f":"'K80 - time schedule'!AD29","v":0},{"$f":"'K80 - time schedule'!AE29","v":0},{"$f":"'K80 - time schedule'!AF29","v":0},{"$f":"'K80 - time schedule'!AG29","v":0},{"$f":"'K80 - time schedule'!AH29","v":0},{"$f":"'K80 - time schedule'!AI29","v":0},{"$f":"'K80 - time schedule'!AJ29","v":0},{"$f":"'K80 - time schedule'!AK29","v":0},{"$f":"'K80 - time schedule'!AL29","v":0},{"$f":"'K80 - time schedule'!AM29","v":0},{"$f":"'K80 - time schedule'!AN29","v":0},{"$f":"'K80 - time schedule'!AO29","v":0},{"$f":"'K80 - time schedule'!AP29","v":0},{"$f":"'K80 - time schedule'!AQ29","v":0},{"$f":"'K80 - time schedule'!AR29","v":0},{"$f":"'K80 - time schedule'!AS29","v":0},{"$f":"'K80 - time schedule'!AT29","v":0},{"$f":"'K80 - time schedule'!AU29","v":0},{"$f":"'K80 - time schedule'!AV29","v":0},{"$f":"'K80 - time schedule'!AW29","v":0},{"$f":"'K80 - time schedule'!AX29","v":0},{"$f":"'K80 - time schedule'!AY29","v":0},{"$f":"'K80 - time schedule'!AZ29","v":0},{"$f":"'K80 - time schedule'!BA29","v":0},{"$f":"'K80 - time schedule'!BB29","v":0},{"$f":"'K80 - time schedule'!BC29","v":0},{"$f":"'K80 - time schedule'!BD29","v":0},{"$f":"'K80 - time schedule'!BE29","v":0},{"$f":"'K80 - time schedule'!BF29","v":0},{"$f":"'K80 - time schedule'!BG29","v":0},{"$f":"'K80 - time schedule'!BH29","v":0},{"$f":"'K80 - time schedule'!BI29","v":0},{"$f":"'K80 - time schedule'!BJ29","v":0},{"$f":"'K80 - time schedule'!BK29","v":0},{"$f":"'K80 - time schedule'!BL29","v":0},{"$f":"'K80 - time schedule'!BM29","v":0},{"$f":"'K80 - time schedule'!BN29","v":0},{"$f":"'K80 - time schedule'!BO29","v":0},{"$f":"'K80 - time schedule'!BP29","v":0},{"$f":"'K80 - time schedule'!BQ29","v":0},{"$f":"'K80 - time schedule'!BR29","v":0},{"$f":"'K80 - time schedule'!BS29","v":0},{"$f":"'K80 - time schedule'!BT29","v":0},{"$f":"'K80 - time schedule'!BU29","v":0},{"$f":"'K80 - time schedule'!BV29","v":0},{"$f":"'K80 - time schedule'!BW29","v":0},{"$f":"'K80 - time schedule'!BX29","v":0},{"$f":"'K80 - time schedule'!BY29","v":0},{"$f":"'K80 - time schedule'!BZ29","v":0},{"$f":"'K80 - time schedule'!CA29","v":0},{"$f":"'K80 - time schedule'!CB29","v":0},{"$f":"'K80 - time schedule'!CC29","v":0},{"$f":"'K80 - time schedule'!CD29","v":0},{"$f":"'K80 - time schedule'!CE29","v":0},{"$f":"'K80 - time schedule'!CF29","v":0},{"$f":"'K80 - time schedule'!CG29","v":0},{"$f":"'K80 - time schedule'!CH29","v":0},{"$f":"'K80 - time schedule'!CI29","v":0},{"$f":"'K80 - time schedule'!CJ29","v":0},{"$f":"'K80 - time schedule'!CK29","v":0},{"$f":"'K80 - time schedule'!CL29","v":0},{"$f":"'K80 - time schedule'!CM29","v":0},{"$f":"'K80 - time schedule'!CN29","v":0},{"$f":"'K80 - time schedule'!CO29","v":0},{"$f":"'K80 - time schedule'!CP29","v":0},{"$f":"'K80 - time schedule'!CQ29","v":0},{"$f":"'K80 - time schedule'!CR29","v":0},{"$f":"'K80 - time schedule'!CS29","v":0},{"$f":"'K80 - time schedule'!CT29","v":0},{"$f":"'K80 - time schedule'!CU29","v":0},{"$f":"'K80 - time schedule'!CV29","v":0},{"$f":"'K80 - time schedule'!CW29","v":0},{"$f":"'K80 - time schedule'!CX29","v":0},{"$f":"'K80 - time schedule'!CY29","v":0},{"$f":"'K80 - time schedule'!CZ29","v":0},{"$f":"'K80 - time schedule'!DA29","v":0},{"$f":"'K80 - time schedule'!DB29","v":0},{"$f":"'K80 - time schedule'!DC29","v":0},{"$f":"'K80 - time schedule'!DD29","v":0},{"$f":"'K80 - time schedule'!DE29","v":0},{"$f":"'K80 - time schedule'!DF29","v":0},{"$f":"'K80 - time schedule'!DG29","v":0},{"$f":"'K80 - time schedule'!DH29","v":0},{"$f":"'K80 - time schedule'!DI29","v":0},{"$f":"'K80 - time schedule'!DJ29","v":0},{"$f":"'K80 - time schedule'!DK29","v":0},{"$f":"'K80 - time schedule'!DL29","v":0},{"$f":"'K80 - time schedule'!DM29","v":0},{"$f":"'K80 - time schedule'!DN29","v":0},{"$f":"'K80 - time schedule'!DO29","v":0},{"$f":"'K80 - time schedule'!DP29","v":0},{"$f":"'K80 - time schedule'!DQ29","v":0},{"$f":"'K80 - time schedule'!DR29","v":0},{"$f":"'K80 - time schedule'!DS29","v":0},{"$f":"'K80 - time schedule'!DT29","v":0},{"$f":"'K80 - time schedule'!DU29","v":0},{"$f":"'K80 - time schedule'!DV29","v":0},{"$f":"'K80 - time schedule'!DW29","v":0},{"$f":"'K80 - time schedule'!DX29","v":0},{"$f":"'K80 - time schedule'!DY29","v":0},{"$f":"'K80 - time schedule'!DZ29","v":0},{"$f":"'K80 - time schedule'!EA29","v":0},{"$f":"'K80 - time schedule'!EB29","v":0},{"$f":"'K80 - time schedule'!EC29","v":0},{"$f":"'K80 - time schedule'!ED29","v":0},{"$f":"'K80 - time schedule'!EE29","v":0},{"$f":"'K80 - time schedule'!EF29","v":0},{"$f":"'K80 - time schedule'!EG29","v":0},{"$f":"'K80 - time schedule'!EH29","v":0},{"$f":"'K80 - time schedule'!EI29","v":0},{"$f":"'K80 - time schedule'!EJ29","v":0},{"$f":"'K80 - time schedule'!EK29","v":0},{"$f":"'K80 - time schedule'!EL29","v":0},{"$f":"'K80 - time schedule'!EM29","v":0},{"$f":"'K80 - time schedule'!EN29","v":0},{"$f":"'K80 - time schedule'!EO29","v":0},{"$f":"'K80 - time schedule'!EP29","v":0},{"$f":"'K80 - time schedule'!EQ29","v":0},{"$f":"'K80 - time schedule'!ER29","v":0},{"$f":"'K80 - time schedule'!ES29","v":0},{"$f":"'K80 - time schedule'!ET29","v":0},{"$f":"'K80 - time schedule'!EU29","v":0},{"$f":"'K80 - time schedule'!EV29","v":0},{"$f":"'K80 - time schedule'!EW29","v":0},{"$f":"'K80 - time schedule'!EX29","v":0},{"$f":"'K80 - time schedule'!EY29","v":0},{"$f":"'K80 - time schedule'!EZ29","v":0},{"$f":"'K80 - time schedule'!FA29","v":0},{"$f":"'K80 - time schedule'!FB29","v":0},{"$f":"'K80 - time schedule'!FC29","v":0},{"$f":"'K80 - time schedule'!FD29","v":0},{"$f":"'K80 - time schedule'!FE29","v":0},{"$f":"'K80 - time schedule'!FF29","v":0},{"$f":"'K80 - time schedule'!FG29","v":0},{"$f":"'K80 - time schedule'!FH29","v":0},{"$f":"'K80 - time schedule'!FI29","v":0},{"$f":"'K80 - time schedule'!FJ29","v":0},{"$f":"'K80 - time schedule'!FK29","v":0},{"$f":"'K80 - time schedule'!FL29","v":0},{"$f":"'K80 - time schedule'!FM29","v":0},{"$f":"'K80 - time schedule'!FN29","v":0},{"$f":"'K80 - time schedule'!FO29","v":0},{"$f":"'K80 - time schedule'!FP29","v":0},{"$f":"'K80 - time schedule'!FQ29","v":0},{"$f":"'K80 - time schedule'!FR29","v":0},{"$f":"'K80 - time schedule'!FS29","v":0},{"$f":"'K80 - time schedule'!FT29","v":0},{"$f":"'K80 - time schedule'!FU29","v":0},{"$f":"'K80 - time schedule'!FV29","v":0},{"$f":"'K80 - time schedule'!FW29","v":0},{"$f":"'K80 - time schedule'!FX29","v":0},{"$f":"'K80 - time schedule'!FY29","v":0},{"$f":"'K80 - time schedule'!FZ29","v":0},{"$f":"'K80 - time schedule'!GA29","v":0},{"$f":"'K80 - time schedule'!GB29","v":0},{"$f":"'K80 - time schedule'!GC29","v":0},{"$f":"'K80 - time schedule'!GD29","v":0},{"$f":"'K80 - time schedule'!GE29","v":0},{"$f":"'K80 - time schedule'!GF29","v":0},{"$f":"'K20 - time schedule'!GG44","v":0},{"$f":"'K20 - time schedule'!GH44","v":0},{"$f":"'K20 - time schedule'!GI44","v":0},{"$f":"'K20 - time schedule'!GJ44","v":0},{"$f":"'K20 - time schedule'!GK44","v":0},{"$f":"'K20 - time schedule'!GL44","v":0},{"$f":"'K20 - time schedule'!GM44","v":0},{"$f":"'K20 - time schedule'!GN44","v":0},{"$f":"'K20 - time schedule'!GO44","v":0},{"$f":"'K20 - time schedule'!GP44","v":0},{"$f":"'K20 - time schedule'!GQ44","v":0},{"$f":"'K20 - time schedule'!GR44","v":0},{"$f":"'K20 - time schedule'!GS44","v":0},{"$f":"'K20 - time schedule'!GT44","v":0},{"$f":"'K20 - time schedule'!GU44","v":0},{"$f":"'K20 - time schedule'!GV44","v":0},{"$f":"'K20 - time schedule'!GW44","v":0},{"$f":"'K20 - time schedule'!GX44","v":0},{"$f":"'K20 - time schedule'!GY44","v":0},{"$f":"'K20 - time schedule'!GZ44","v":0},{"$f":"'K20 - time schedule'!HA44","v":0},{"$f":"'K20 - time schedule'!HB44","v":0},{"$f":"'K20 - time schedule'!HC44","v":0},{"$f":"'K20 - time schedule'!HD44","v":0},{"$f":"'K20 - time schedule'!HE44","v":0},{"$f":"'K20 - time schedule'!HF44","v":0},{"$f":"'K20 - time schedule'!HG44","v":0},{"$f":"'K20 - time schedule'!HH44","v":0},{"$f":"'K20 - time schedule'!HI44","v":0},{"$f":"'K20 - time schedule'!HJ44","v":0},{"$f":"'K20 - time schedule'!HK44","v":0},{"$f":"'K20 - time schedule'!HL44","v":0},{"$f":"'K20 - time schedule'!HM44","v":0},{"$f":"'K20 - time schedule'!HN44","v":0},{"$f":"'K20 - time schedule'!HO44","v":0},{"$f":"'K20 - time schedule'!HP44","v":0},{"$f":"'K20 - time schedule'!HQ44","v":0},{"$f":"'K20 - time schedule'!HR44","v":0},{"$f":"'K20 - time schedule'!HS44","v":0},{"$f":"'K20 - time schedule'!HT44","v":0},{"$f":"'K20 - time schedule'!HU44","v":0},{"$f":"'K20 - time schedule'!HV44","v":0},{"$f":"'K20 - time schedule'!HW44","v":0},{"$f":"'K20 - time schedule'!HX44","v":0},{"$f":"'K20 - time schedule'!HY44","v":0},{"$f":"'K20 - time schedule'!HZ44","v":0},{"$f":"'K20 - time schedule'!IA44","v":0},{"$f":"'K20 - time schedule'!IB44","v":0},{"$f":"'K20 - time schedule'!IC44","v":0},{"$f":"'K20 - time schedule'!ID44","v":0},{"$f":"'K20 - time schedule'!IE44","v":0},{"$f":"'K20 - time schedule'!IF44","v":0},{"$f":"'K20 - time schedule'!IG44","v":0},{"$f":"'K20 - time schedule'!IH44","v":0},{"$f":"'K20 - time schedule'!II44","v":0},{"$f":"'K20 - time schedule'!IJ44","v":0},{"$f":"'K20 - time schedule'!IK44","v":0},{"$f":"'K20 - time schedule'!IL44","v":0},{"$f":"'K20 - time schedule'!IM44","v":0},{"$f":"'K20 - time schedule'!IN44","v":0},{"$f":"'K20 - time schedule'!IO44","v":0},{"$f":"'K20 - time schedule'!IP44","v":0},{"$f":"'K20 - time schedule'!IQ44","v":0},{"$f":"'K20 - time schedule'!IR44","v":0},{"$f":"'K20 - time schedule'!IS44","v":0},{"$f":"'K20 - time schedule'!IT44","v":0},{"$f":"'K20 - time schedule'!IU44","v":0},{"$f":"'K20 - time schedule'!IV44","v":0},{"$f":"'K20 - time schedule'!IW44","v":0},{"$f":"'K20 - time schedule'!IX44","v":0},{"$f":"'K20 - time schedule'!IY44","v":0},{"$f":"'K20 - time schedule'!IZ44","v":0},{"$f":"'K20 - time schedule'!JA44","v":0},{"$f":"'K20 - time schedule'!JB44","v":0},{"$f":"'K20 - time schedule'!JC44","v":0},{"$f":"'K20 - time schedule'!JD44","v":0},{"$f":"'K20 - time schedule'!JE44","v":0},{"$f":"'K20 - time schedule'!JF44","v":0},{"$f":"'K20 - time schedule'!JG44","v":0},{"$f":"'K20 - time schedule'!JH44","v":0},{"$f":"'K20 - time schedule'!JI44","v":0},{"$f":"'K20 - time schedule'!JJ44","v":0},{"$f":"'K20 - time schedule'!JK44","v":0},{"$f":"'K20 - time schedule'!JL44","v":0},{"$f":"'K20 - time schedule'!JM44","v":0},{"$f":"'K20 - time schedule'!JN44","v":0},{"$f":"'K20 - time schedule'!JO44","v":0},{"$f":"'K20 - time schedule'!JP44","v":0},{"$f":"'K20 - time schedule'!JQ44","v":0},{"$f":"'K20 - time schedule'!JR44","v":0},{"$f":"'K20 - time schedule'!JS44","v":0},{"$f":"'K20 - time schedule'!JT44","v":0},{"$f":"'K20 - time schedule'!JU44","v":0},{"$f":"'K20 - time schedule'!JV44","v":0},{"$f":"'K20 - time schedule'!JW44","v":0},{"$f":"'K20 - time schedule'!JX44","v":0},{"$f":"'K20 - time schedule'!JY44","v":0},{"$f":"'K20 - time schedule'!JZ44","v":0},{"$f":"'K20 - time schedule'!KA44","v":0},{"$f":"'K20 - time schedule'!KB44","v":0},{"$f":"'K20 - time schedule'!KC44","v":0},{"$f":"'K20 - time schedule'!KD44","v":0},{"$f":"'K20 - time schedule'!KE44","v":0},{"$f":"'K20 - time schedule'!KF44","v":0},{"$f":"'K20 - time schedule'!KG44","v":0},{"$f":"'K20 - time schedule'!KH44","v":0},{"$f":"'K20 - time schedule'!KI44","v":0},{"$f":"'K20 - time schedule'!KJ44","v":0},{"$f":"'K20 - time schedule'!KK44","v":0},{"$f":"'K20 - time schedule'!KL44","v":0},{"$f":"'K20 - time schedule'!KM44","v":0},{"$f":"'K20 - time schedule'!KN44","v":0},{"$f":"'K20 - time schedule'!KO44","v":0},{"$f":"'K20 - time schedule'!KP44","v":0},{"$f":"'K20 - time schedule'!KQ44","v":0},{"$f":"'K20 - time schedule'!KR44","v":0},{"$f":"'K20 - time schedule'!KS44","v":0},{"$f":"'K20 - time schedule'!KT44","v":0}]
["Boiler room K80 - economizer","K80","EUR",{"$f":"'K80 - time schedule'!G31","v":0},{"$f":"'K80 - time schedule'!H31","v":0},{"$f":"'K80 - time schedule'!I31","v":0},{"$f":"'K80 - time schedule'!J31","v":0},{"$f":"'K80 - time schedule'!K31","v":0},{"$f":"'K80 - time schedule'!L31","v":0},{"$f":"'K80 - time schedule'!M31","v":0},{"$f":"'K80 - time schedule'!N31","v":0},{"$f":"'K80 - time schedule'!O31","v":0},{"$f":"'K80 - time schedule'!P31","v":0},{"$f":"'K80 - time schedule'!Q31","v":0},{"$f":"'K80 - time schedule'!R31","v":0},{"$f":"'K80 - time schedule'!S31","v":0},{"$f":"'K80 - time schedule'!T31","v":0},{"$f":"'K80 - time schedule'!U31","v":0},{"$f":"'K80 - time schedule'!V31","v":0},{"$f":"'K80 - time schedule'!W31","v":0},{"$f":"'K80 - time schedule'!X31","v":0},{"$f":"'K80 - time schedule'!Y31","v":0},{"$f":"'K80 - time schedule'!Z31","v":0},{"$f":"'K80 - time schedule'!AA31","v":0},{"$f":"'K80 - time schedule'!AB31","v":0},{"$f":"'K80 - time schedule'!AC31","v":0},{"$f":"'K80 - time schedule'!AD31","v":0},{"$f":"'K80 - time schedule'!AE31","v":0},{"$f":"'K80 - time schedule'!AF31","v":0},{"$f":"'K80 - time schedule'!AG31","v":0},{"$f":"'K80 - time schedule'!AH31","v":0},{"$f":"'K80 - time schedule'!AI31","v":0},{"$f":"'K80 - time schedule'!AJ31","v":0},{"$f":"'K80 - time schedule'!AK31","v":0},{"$f":"'K80 - time schedule'!AL31","v":0},{"$f":"'K80 - time schedule'!AM31","v":0},{"$f":"'K80 - time schedule'!AN31","v":0},{"$f":"'K80 - time schedule'!AO31","v":0},{"$f":"'K80 - time schedule'!AP31","v":0},{"$f":"'K80 - time schedule'!AQ31","v":0},{"$f":"'K80 - time schedule'!AR31","v":0},{"$f":"'K80 - time schedule'!AS31","v":0},{"$f":"'K80 - time schedule'!AT31","v":0},{"$f":"'K80 - time schedule'!AU31","v":0},{"$f":"'K80 - time schedule'!AV31","v":0},{"$f":"'K80 - time schedule'!AW31","v":0},{"$f":"'K80 - time schedule'!AX31","v":0},{"$f":"'K80 - time schedule'!AY31","v":0},{"$f":"'K80 - time schedule'!AZ31","v":0},{"$f":"'K80 - time schedule'!BA31","v":0},{"$f":"'K80 - time schedule'!BB31","v":0},{"$f":"'K80 - time schedule'!BC31","v":0},{"$f":"'K80 - time schedule'!BD31","v":0},{"$f":"'K80 - time schedule'!BE31","v":0},{"$f":"'K80 - time schedule'!BF31","v":0},{"$f":"'K80 - time schedule'!BG31","v":0},{"$f":"'K80 - time schedule'!BH31","v":0},{"$f":"'K80 - time schedule'!BI31","v":0},{"$f":"'K80 - time schedule'!BJ31","v":0},{"$f":"'K80 - time schedule'!BK31","v":0},{"$f":"'K80 - time schedule'!BL31","v":0},{"$f":"'K80 - time schedule'!BM31","v":0},{"$f":"'K80 - time schedule'!BN31","v":0},{"$f":"'K80 - time schedule'!BO31","v":0},{"$f":"'K80 - time schedule'!BP31","v":0},{"$f":"'K80 - time schedule'!BQ31","v":0},{"$f":"'K80 - time schedule'!BR31","v":0},{"$f":"'K80 - time schedule'!BS31","v":0},{"$f":"'K80 - time schedule'!BT31","v":0},{"$f":"'K80 - time schedule'!BU31","v":0},{"$f":"'K80 - time schedule'!BV31","v":0},{"$f":"'K80 - time schedule'!BW31","v":0},{"$f":"'K80 - time schedule'!BX31","v":0},{"$f":"'K80 - time schedule'!BY31","v":0},{"$f":"'K80 - time schedule'!BZ31","v":0},{"$f":"'K80 - time schedule'!CA31","v":0},{"$f":"'K80 - time schedule'!CB31","v":0},{"$f":"'K80 - time schedule'!CC31","v":0},{"$f":"'K80 - time schedule'!CD31","v":0},{"$f":"'K80 - time schedule'!CE31","v":0},{"$f":"'K80 - time schedule'!CF31","v":0},{"$f":"'K80 - time schedule'!CG31","v":0},{"$f":"'K80 - time schedule'!CH31","v":0},{"$f":"'K80 - time schedule'!CI31","v":0},{"$f":"'K80 - time schedule'!CJ31","v":0},{"$f":"'K80 - time schedule'!CK31","v":0},{"$f":"'K80 - time schedule'!CL31","v":0},{"$f":"'K80 - time schedule'!CM31","v":0},{"$f":"'K80 - time schedule'!CN31","v":0},{"$f":"'K80 - time schedule'!CO31","v":0},{"$f":"'K80 - time schedule'!CP31","v":0},{"$f":"'K80 - time schedule'!CQ31","v":0},{"$f":"'K80 - time schedule'!CR31","v":0},{"$f":"'K80 - time schedule'!CS31","v":0},{"$f":"'K80 - time schedule'!CT31","v":0},{"$f":"'K80 - time schedule'!CU31","v":0},{"$f":"'K80 - time schedule'!CV31","v":0},{"$f":"'K80 - time schedule'!CW31","v":0},{"$f":"'K80 - time schedule'!CX31","v":0},{"$f":"'K80 - time schedule'!CY31","v":0},{"$f":"'K80 - time schedule'!CZ31","v":0},{"$f":"'K80 - time schedule'!DA31","v":0},{"$f":"'K80 - time schedule'!DB31","v":0},{"$f":"'K80 - time schedule'!DC31","v":0},{"$f":"'K80 - time schedule'!DD31","v":0},{"$f":"'K80 - time schedule'!DE31","v":0},{"$f":"'K80 - time schedule'!DF31","v":0},{"$f":"'K80 - time schedule'!DG31","v":0},{"$f":"'K80 - time schedule'!DH31","v":0},{"$f":"'K80 - time schedule'!DI31","v":0},{"$f":"'K80 - time schedule'!DJ31","v":0},{"$f":"'K80 - time schedule'!DK31","v":0},{"$f":"'K80 - time schedule'!DL31","v":0},{"$f":"'K80 - time schedule'!DM31","v":0},{"$f":"'K80 - time schedule'!DN31","v":0},{"$f":"'K80 - time schedule'!DO31","v":0},{"$f":"'K80 - time schedule'!DP31","v":0},{"$f":"'K80 - time schedule'!DQ31","v":0},{"$f":"'K80 - time schedule'!DR31","v":0},{"$f":"'K80 - time schedule'!DS31","v":0},{"$f":"'K80 - time schedule'!DT31","v":0},{"$f":"'K80 - time schedule'!DU31","v":0},{"$f":"'K80 - time schedule'!DV31","v":0},{"$f":"'K80 - time schedule'!DW31","v":0},{"$f":"'K80 - time schedule'!DX31","v":0},{"$f":"'K80 - time schedule'!DY31","v":0},{"$f":"'K80 - time schedule'!DZ31","v":0},{"$f":"'K80 - time schedule'!EA31","v":0},{"$f":"'K80 - time schedule'!EB31","v":0},{"$f":"'K80 - time schedule'!EC31","v":0},{"$f":"'K80 - time schedule'!ED31","v":0},{"$f":"'K80 - time schedule'!EE31","v":0},{"$f":"'K80 - time schedule'!EF31","v":0},{"$f":"'K80 - time schedule'!EG31","v":0},{"$f":"'K80 - time schedule'!EH31","v":0},{"$f":"'K80 - time schedule'!EI31","v":0},{"$f":"'K80 - time schedule'!EJ31","v":0},{"$f":"'K80 - time schedule'!EK31","v":0},{"$f":"'K80 - time schedule'!EL31","v":0},{"$f":"'K80 - time schedule'!EM31","v":0},{"$f":"'K80 - time schedule'!EN31","v":0},{"$f":"'K80 - time schedule'!EO31","v":0},{"$f":"'K80 - time schedule'!EP31","v":0},{"$f":"'K80 - time schedule'!EQ31","v":0},{"$f":"'K80 - time schedule'!ER31","v":0},{"$f":"'K80 - time schedule'!ES31","v":0},{"$f":"'K80 - time schedule'!ET31","v":0},{"$f":"'K80 - time schedule'!EU31","v":0},{"$f":"'K80 - time schedule'!EV31","v":0},{"$f":"'K80 - time schedule'!EW31","v":0},{"$f":"'K80 - time schedule'!EX31","v":0},{"$f":"'K80 - time schedule'!EY31","v":0},{"$f":"'K80 - time schedule'!EZ31","v":0},{"$f":"'K80 - time schedule'!FA31","v":0},{"$f":"'K80 - time schedule'!FB31","v":0},{"$f":"'K80 - time schedule'!FC31","v":0},{"$f":"'K80 - time schedule'!FD31","v":0},{"$f":"'K80 - time schedule'!FE31","v":0},{"$f":"'K80 - time schedule'!FF31","v":0},{"$f":"'K80 - time schedule'!FG31","v":0},{"$f":"'K80 - time schedule'!FH31","v":0},{"$f":"'K80 - time schedule'!FI31","v":0},{"$f":"'K80 - time schedule'!FJ31","v":0},{"$f":"'K80 - time schedule'!FK31","v":0},{"$f":"'K80 - time schedule'!FL31","v":0},{"$f":"'K80 - time schedule'!FM31","v":0},{"$f":"'K80 - time schedule'!FN31","v":0},{"$f":"'K80 - time schedule'!FO31","v":0},{"$f":"'K80 - time schedule'!FP31","v":0},{"$f":"'K80 - time schedule'!FQ31","v":0},{"$f":"'K80 - time schedule'!FR31","v":0},{"$f":"'K80 - time schedule'!FS31","v":0},{"$f":"'K80 - time schedule'!FT31","v":0},{"$f":"'K80 - time schedule'!FU31","v":0},{"$f":"'K80 - time schedule'!FV31","v":0},{"$f":"'K80 - time schedule'!FW31","v":0},{"$f":"'K80 - time schedule'!FX31","v":0},{"$f":"'K80 - time schedule'!FY31","v":0},{"$f":"'K80 - time schedule'!FZ31","v":0},{"$f":"'K80 - time schedule'!GA31","v":0},{"$f":"'K80 - time schedule'!GB31","v":0},{"$f":"'K80 - time schedule'!GC31","v":0},{"$f":"'K80 - time schedule'!GD31","v":0},{"$f":"'K80 - time schedule'!GE31","v":0},{"$f":"'K80 - time schedule'!GF31","v":0},{"$f":"'K20 - time schedule'!GG45","v":0},{"$f":"'K20 - time schedule'!GH45","v":0},{"$f":"'K20 - time schedule'!GI45","v":0},{"$f":"'K20 - time schedule'!GJ45","v":0},{"$f":"'K20 - time schedule'!GK45","v":0},{"$f":"'K20 - time schedule'!GL45","v":0},{"$f":"'K20 - time schedule'!GM45","v":0},{"$f":"'K20 - time schedule'!GN45","v":0},{"$f":"'K20 - time schedule'!GO45","v":0},{"$f":"'K20 - time schedule'!GP45","v":0},{"$f":"'K20 - time schedule'!GQ45","v":0},{"$f":"'K20 - time schedule'!GR45","v":0},{"$f":"'K20 - time schedule'!GS45","v":0},{"$f":"'K20 - time schedule'!GT45","v":0},{"$f":"'K20 - time schedule'!GU45","v":0},{"$f":"'K20 - time schedule'!GV45","v":0},{"$f":"'K20 - time schedule'!GW45","v":0},{"$f":"'K20 - time schedule'!GX45","v":0},{"$f":"'K20 - time schedule'!GY45","v":0},{"$f":"'K20 - time schedule'!GZ45","v":0},{"$f":"'K20 - time schedule'!HA45","v":0},{"$f":"'K20 - time schedule'!HB45","v":0},{"$f":"'K20 - time schedule'!HC45","v":0},{"$f":"'K20 - time schedule'!HD45","v":0},{"$f":"'K20 - time schedule'!HE45","v":0},{"$f":"'K20 - time schedule'!HF45","v":0},{"$f":"'K20 - time schedule'!HG45","v":0},{"$f":"'K20 - time schedule'!HH45","v":0},{"$f":"'K20 - time schedule'!HI45","v":0},{"$f":"'K20 - time schedule'!HJ45","v":0},{"$f":"'K20 - time schedule'!HK45","v":0},{"$f":"'K20 - time schedule'!HL45","v":0},{"$f":"'K20 - time schedule'!HM45","v":0},{"$f":"'K20 - time schedule'!HN45","v":0},{"$f":"'K20 - time schedule'!HO45","v":0},{"$f":"'K20 - time schedule'!HP45","v":0},{"$f":"'K20 - time schedule'!HQ45","v":0},{"$f":"'K20 - time schedule'!HR45","v":0},{"$f":"'K20 - time schedule'!HS45","v":0},{"$f":"'K20 - time schedule'!HT45","v":0},{"$f":"'K20 - time schedule'!HU45","v":0},{"$f":"'K20 - time schedule'!HV45","v":0},{"$f":"'K20 - time schedule'!HW45","v":0},{"$f":"'K20 - time schedule'!HX45","v":0},{"$f":"'K20 - time schedule'!HY45","v":0},{"$f":"'K20 - time schedule'!HZ45","v":0},{"$f":"'K20 - time schedule'!IA45","v":0},{"$f":"'K20 - time schedule'!IB45","v":0},{"$f":"'K20 - time schedule'!IC45","v":0},{"$f":"'K20 - time schedule'!ID45","v":0},{"$f":"'K20 - time schedule'!IE45","v":0},{"$f":"'K20 - time schedule'!IF45","v":0},{"$f":"'K20 - time schedule'!IG45","v":0},{"$f":"'K20 - time schedule'!IH45","v":0},{"$f":"'K20 - time schedule'!II45","v":0},{"$f":"'K20 - time schedule'!IJ45","v":0},{"$f":"'K20 - time schedule'!IK45","v":0},{"$f":"'K20 - time schedule'!IL45","v":0},{"$f":"'K20 - time schedule'!IM45","v":0},{"$f":"'K20 - time schedule'!IN45","v":0},{"$f":"'K20 - time schedule'!IO45","v":0},{"$f":"'K20 - time schedule'!IP45","v":0},{"$f":"'K20 - time schedule'!IQ45","v":0},{"$f":"'K20 - time schedule'!IR45","v":0},{"$f":"'K20 - time schedule'!IS45","v":0},{"$f":"'K20 - time schedule'!IT45","v":0},{"$f":"'K20 - time schedule'!IU45","v":0},{"$f":"'K20 - time schedule'!IV45","v":0},{"$f":"'K20 - time schedule'!IW45","v":0},{"$f":"'K20 - time schedule'!IX45","v":0},{"$f":"'K20 - time schedule'!IY45","v":0},{"$f":"'K20 - time schedule'!IZ45","v":0},{"$f":"'K20 - time schedule'!JA45","v":0},{"$f":"'K20 - time schedule'!JB45","v":0},{"$f":"'K20 - time schedule'!JC45","v":0},{"$f":"'K20 - time schedule'!JD45","v":0},{"$f":"'K20 - time schedule'!JE45","v":0},{"$f":"'K20 - time schedule'!JF45","v":0},{"$f":"'K20 - time schedule'!JG45","v":0},{"$f":"'K20 - time schedule'!JH45","v":0},{"$f":"'K20 - time schedule'!JI45","v":0},{"$f":"'K20 - time schedule'!JJ45","v":0},{"$f":"'K20 - time schedule'!JK45","v":0},{"$f":"'K20 - time schedule'!JL45","v":0},{"$f":"'K20 - time schedule'!JM45","v":0},{"$f":"'K20 - time schedule'!JN45","v":0},{"$f":"'K20 - time schedule'!JO45","v":0},{"$f":"'K20 - time schedule'!JP45","v":0},{"$f":"'K20 - time schedule'!JQ45","v":0},{"$f":"'K20 - time schedule'!JR45","v":0},{"$f":"'K20 - time schedule'!JS45","v":0},{"$f":"'K20 - time schedule'!JT45","v":0},{"$f":"'K20 - time schedule'!JU45","v":0},{"$f":"'K20 - time schedule'!JV45","v":0},{"$f":"'K20 - time schedule'!JW45","v":0},{"$f":"'K20 - time schedule'!JX45","v":0},{"$f":"'K20 - time schedule'!JY45","v":0},{"$f":"'K20 - time schedule'!JZ45","v":0},{"$f":"'K20 - time schedule'!KA45","v":0},{"$f":"'K20 - time schedule'!KB45","v":0},{"$f":"'K20 - time schedule'!KC45","v":0},{"$f":"'K20 - time schedule'!KD45","v":0},{"$f":"'K20 - time schedule'!KE45","v":0},{"$f":"'K20 - time schedule'!KF45","v":0},{"$f":"'K20 - time schedule'!KG45","v":0},{"$f":"'K20 - time schedule'!KH45","v":0},{"$f":"'K20 - time schedule'!KI45","v":0},{"$f":"'K20 - time schedule'!KJ45","v":0},{"$f":"'K20 - time schedule'!KK45","v":0},{"$f":"'K20 - time schedule'!KL45","v":0},{"$f":"'K20 - time schedule'!KM45","v":0},{"$f":"'K20 - time schedule'!KN45","v":0},{"$f":"'K20 - time schedule'!KO45","v":0},{"$f":"'K20 - time schedule'!KP45","v":0},{"$f":"'K20 - time schedule'!KQ45","v":0},{"$f":"'K20 - time schedule'!KR45","v":0},{"$f":"'K20 - time schedule'!KS45","v":0},{"$f":"'K20 - time schedule'!KT45","v":0}]
["Boiler room K80 - lining","K80","EUR",{"$f":"'K80 - time schedule'!G33","v":0},{"$f":"'K80 - time schedule'!H33","v":0},{"$f":"'K80 - time schedule'!I33","v":0},{"$f":"'K80 - time schedule'!J33","v":0},{"$f":"'K80 - time schedule'!K33","v":0},{"$f":"'K80 - time schedule'!L33","v":0},{"$f":"'K80 - time schedule'!M33","v":0},{"$f":"'K80 - time schedule'!N33","v":0},{"$f":"'K80 - time schedule'!O33","v":0},{"$f":"'K80 - time schedule'!P33","v":0},{"$f":"'K80 - time schedule'!Q33","v":0},{"$f":"'K80 - time schedule'!R33","v":0},{"$f":"'K80 - time schedule'!S33","v":0},{"$f":"'K80 - time schedule'!T33","v":0},{"$f":"'K80 - time schedule'!U33","v":0},{"$f":"'K80 - time schedule'!V33","v":0},{"$f":"'K80 - time schedule'!W33","v":0},{"$f":"'K80 - time schedule'!X33","v":0},{"$f":"'K80 - time schedule'!Y33","v":0},{"$f":"'K80 - time schedule'!Z33","v":0},{"$f":"'K80 - time schedule'!AA33","v":0},{"$f":"'K80 - time schedule'!AB33","v":0},{"$f":"'K80 - time schedule'!AC33","v":0},{"$f":"'K80 - time schedule'!AD33","v":0},{"$f":"'K80 - time schedule'!AE33","v":0},{"$f":"'K80 - time schedule'!AF33","v":0},{"$f":"'K80 - time schedule'!AG33","v":0},{"$f":"'K80 - time schedule'!AH33","v":0},{"$f":"'K80 - time schedule'!AI33","v":0},{"$f":"'K80 - time schedule'!AJ33","v":0},{"$f":"'K80 - time schedule'!AK33","v":0},{"$f":"'K80 - time schedule'!AL33","v":0},{"$f":"'K80 - time schedule'!AM33","v":0},{"$f":"'K80 - time schedule'!AN33","v":0},{"$f":"'K80 - time schedule'!AO33","v":0},{"$f":"'K80 - time schedule'!AP33","v":0},{"$f":"'K80 - time schedule'!AQ33","v":0},{"$f":"'K80 - time schedule'!AR33","v":0},{"$f":"'K80 - time schedule'!AS33","v":0},{"$f":"'K80 - time schedule'!AT33","v":0},{"$f":"'K80 - time schedule'!AU33","v":0},{"$f":"'K80 - time schedule'!AV33","v":0},{"$f":"'K80 - time schedule'!AW33","v":0},{"$f":"'K80 - time schedule'!AX33","v":0},{"$f":"'K80 - time schedule'!AY33","v":0},{"$f":"'K80 - time schedule'!AZ33","v":0},{"$f":"'K80 - time schedule'!BA33","v":0},{"$f":"'K80 - time schedule'!BB33","v":0},{"$f":"'K80 - time schedule'!BC33","v":0},{"$f":"'K80 - time schedule'!BD33","v":0},{"$f":"'K80 - time schedule'!BE33","v":0},{"$f":"'K80 - time schedule'!BF33","v":0},{"$f":"'K80 - time schedule'!BG33","v":0},{"$f":"'K80 - time schedule'!BH33","v":0},{"$f":"'K80 - time schedule'!BI33","v":0},{"$f":"'K80 - time schedule'!BJ33","v":0},{"$f":"'K80 - time schedule'!BK33","v":0},{"$f":"'K80 - time schedule'!BL33","v":0},{"$f":"'K80 - time schedule'!BM33","v":0},{"$f":"'K80 - time schedule'!BN33","v":0},{"$f":"'K80 - time schedule'!BO33","v":0},{"$f":"'K80 - time schedule'!BP33","v":0},{"$f":"'K80 - time schedule'!BQ33","v":0},{"$f":"'K80 - time schedule'!BR33","v":0},{"$f":"'K80 - time schedule'!BS33","v":0},{"$f":"'K80 - time schedule'!BT33","v":0},{"$f":"'K80 - time schedule'!BU33","v":0},{"$f":"'K80 - time schedule'!BV33","v":0},{"$f":"'K80 - time schedule'!BW33","v":0},{"$f":"'K80 - time schedule'!BX33","v":0},{"$f":"'K80 - time schedule'!BY33","v":0},{"$f":"'K80 - time schedule'!BZ33","v":0},{"$f":"'K80 - time schedule'!CA33","v":0},{"$f":"'K80 - time schedule'!CB33","v":0},{"$f":"'K80 - time schedule'!CC33","v":0},{"$f":"'K80 - time schedule'!CD33","v":0},{"$f":"'K80 - time schedule'!CE33","v":0},{"$f":"'K80 - time schedule'!CF33","v":0},{"$f":"'K80 - time schedule'!CG33","v":0},{"$f":"'K80 - time schedule'!CH33","v":0},{"$f":"'K80 - time schedule'!CI33","v":0},{"$f":"'K80 - time schedule'!CJ33","v":0},{"$f":"'K80 - time schedule'!CK33","v":0},{"$f":"'K80 - time schedule'!CL33","v":0},{"$f":"'K80 - time schedule'!CM33","v":0},{"$f":"'K80 - time schedule'!CN33","v":0},{"$f":"'K80 - time schedule'!CO33","v":0},{"$f":"'K80 - time schedule'!CP33","v":0},{"$f":"'K80 - time schedule'!CQ33","v":0},{"$f":"'K80 - time schedule'!CR33","v":0},{"$f":"'K80 - time schedule'!CS33","v":0},{"$f":"'K80 - time schedule'!CT33","v":0},{"$f":"'K80 - time schedule'!CU33","v":0},{"$f":"'K80 - time schedule'!CV33","v":0},{"$f":"'K80 - time schedule'!CW33","v":0},{"$f":"'K80 - time schedule'!CX33","v":0},{"$f":"'K80 - time schedule'!CY33","v":0},{"$f":"'K80 - time schedule'!CZ33","v":0},{"$f":"'K80 - time schedule'!DA33","v":0},{"$f":"'K80 - time schedule'!DB33","v":0},{"$f":"'K80 - time schedule'!DC33","v":0},{"$f":"'K80 - time schedule'!DD33","v":0},{"$f":"'K80 - time schedule'!DE33","v":0},{"$f":"'K80 - time schedule'!DF33","v":0},{"$f":"'K80 - time schedule'!DG33","v":0},{"$f":"'K80 - time schedule'!DH33","v":0},{"$f":"'K80 - time schedule'!DI33","v":0},{"$f":"'K80 - time schedule'!DJ33","v":0},{"$f":"'K80 - time schedule'!DK33","v":0},{"$f":"'K80 - time schedule'!DL33","v":0},{"$f":"'K80 - time schedule'!DM33","v":0},{"$f":"'K80 - time schedule'!DN33","v":0},{"$f":"'K80 - time schedule'!DO33","v":0},{"$f":"'K80 - time schedule'!DP33","v":0},{"$f":"'K80 - time schedule'!DQ33","v":0},{"$f":"'K80 - time schedule'!DR33","v":0},{"$f":"'K80 - time schedule'!DS33","v":0},{"$f":"'K80 - time schedule'!DT33","v":0},{"$f":"'K80 - time schedule'!DU33","v":0},{"$f":"'K80 - time schedule'!DV33","v":0},{"$f":"'K80 - time schedule'!DW33","v":0},{"$f":"'K80 - time schedule'!DX33","v":0},{"$f":"'K80 - time schedule'!DY33","v":0},{"$f":"'K80 - time schedule'!DZ33","v":0},{"$f":"'K80 - time schedule'!EA33","v":0},{"$f":"'K80 - time schedule'!EB33","v":0},{"$f":"'K80 - time schedule'!EC33","v":0},{"$f":"'K80 - time schedule'!ED33","v":0},{"$f":"'K80 - time schedule'!EE33","v":0},{"$f":"'K80 - time schedule'!EF33","v":0},{"$f":"'K80 - time schedule'!EG33","v":0},{"$f":"'K80 - time schedule'!EH33","v":0},{"$f":"'K80 - time schedule'!EI33","v":0},{"$f":"'K80 - time schedule'!EJ33","v":0},{"$f":"'K80 - time schedule'!EK33","v":0},{"$f":"'K80 - time schedule'!EL33","v":0},{"$f":"'K80 - time schedule'!EM33","v":0},{"$f":"'K80 - time schedule'!EN33","v":0},{"$f":"'K80 - time schedule'!EO33","v":0},{"$f":"'K80 - time schedule'!EP33","v":0},{"$f":"'K80 - time schedule'!EQ33","v":0},{"$f":"'K80 - time schedule'!ER33","v":0},{"$f":"'K80 - time schedule'!ES33","v":0},{"$f":"'K80 - time schedule'!ET33","v":0},{"$f":"'K80 - time schedule'!EU33","v":0},{"$f":"'K80 - time schedule'!EV33","v":0},{"$f":"'K80 - time schedule'!EW33","v":0},{"$f":"'K80 - time schedule'!EX33","v":0},{"$f":"'K80 - time schedule'!EY33","v":0},{"$f":"'K80 - time schedule'!EZ33","v":0},{"$f":"'K80 - time schedule'!FA33","v":0},{"$f":"'K80 - time schedule'!FB33","v":0},{"$f":"'K80 - time schedule'!FC33","v":0},{"$f":"'K80 - time schedule'!FD33","v":0},{"$f":"'K80 - time schedule'!FE33","v":0},{"$f":"'K80 - time schedule'!FF33","v":0},{"$f":"'K80 - time schedule'!FG33","v":0},{"$f":"'K80 - time schedule'!FH33","v":0},{"$f":"'K80 - time schedule'!FI33","v":0},{"$f":"'K80 - time schedule'!FJ33","v":0},{"$f":"'K80 - time schedule'!FK33","v":0},{"$f":"'K80 - time schedule'!FL33","v":0},{"$f":"'K80 - time schedule'!FM33","v":0},{"$f":"'K80 - time schedule'!FN33","v":0},{"$f":"'K80 - time schedule'!FO33","v":0},{"$f":"'K80 - time schedule'!FP33","v":0},{"$f":"'K80 - time schedule'!FQ33","v":0},{"$f":"'K80 - time schedule'!FR33","v":0},{"$f":"'K80 - time schedule'!FS33","v":0},{"$f":"'K80 - time schedule'!FT33","v":0},{"$f":"'K80 - time schedule'!FU33","v":0},{"$f":"'K80 - time schedule'!FV33","v":0},{"$f":"'K80 - time schedule'!FW33","v":0},{"$f":"'K80 - time schedule'!FX33","v":0},{"$f":"'K80 - time schedule'!FY33","v":0},{"$f":"'K80 - time schedule'!FZ33","v":0},{"$f":"'K80 - time schedule'!GA33","v":0},{"$f":"'K80 - time schedule'!GB33","v":0},{"$f":"'K80 - time schedule'!GC33","v":0},{"$f":"'K80 - time schedule'!GD33","v":0},{"$f":"'K80 - time schedule'!GE33","v":0},{"$f":"'K80 - time schedule'!GF33","v":0},{"$f":"'K20 - time schedule'!GG46","v":0},{"$f":"'K20 - time schedule'!GH46","v":0},{"$f":"'K20 - time schedule'!GI46","v":0},{"$f":"'K20 - time schedule'!GJ46","v":0},{"$f":"'K20 - time schedule'!GK46","v":0},{"$f":"'K20 - time schedule'!GL46","v":0},{"$f":"'K20 - time schedule'!GM46","v":0},{"$f":"'K20 - time schedule'!GN46","v":0},{"$f":"'K20 - time schedule'!GO46","v":0},{"$f":"'K20 - time schedule'!GP46","v":0},{"$f":"'K20 - time schedule'!GQ46","v":0},{"$f":"'K20 - time schedule'!GR46","v":0},{"$f":"'K20 - time schedule'!GS46","v":0},{"$f":"'K20 - time schedule'!GT46","v":0},{"$f":"'K20 - time schedule'!GU46","v":0},{"$f":"'K20 - time schedule'!GV46","v":0},{"$f":"'K20 - time schedule'!GW46","v":0},{"$f":"'K20 - time schedule'!GX46","v":0},{"$f":"'K20 - time schedule'!GY46","v":0},{"$f":"'K20 - time schedule'!GZ46","v":0},{"$f":"'K20 - time schedule'!HA46","v":0},{"$f":"'K20 - time schedule'!HB46","v":0},{"$f":"'K20 - time schedule'!HC46","v":0},{"$f":"'K20 - time schedule'!HD46","v":0},{"$f":"'K20 - time schedule'!HE46","v":0},{"$f":"'K20 - time schedule'!HF46","v":0},{"$f":"'K20 - time schedule'!HG46","v":0},{"$f":"'K20 - time schedule'!HH46","v":0},{"$f":"'K20 - time schedule'!HI46","v":0},{"$f":"'K20 - time schedule'!HJ46","v":0},{"$f":"'K20 - time schedule'!HK46","v":0},{"$f":"'K20 - time schedule'!HL46","v":0},{"$f":"'K20 - time schedule'!HM46","v":0},{"$f":"'K20 - time schedule'!HN46","v":0},{"$f":"'K20 - time schedule'!HO46","v":0},{"$f":"'K20 - time schedule'!HP46","v":0},{"$f":"'K20 - time schedule'!HQ46","v":0},{"$f":"'K20 - time schedule'!HR46","v":0},{"$f":"'K20 - time schedule'!HS46","v":0},{"$f":"'K20 - time schedule'!HT46","v":0},{"$f":"'K20 - time schedule'!HU46","v":0},{"$f":"'K20 - time schedule'!HV46","v":0},{"$f":"'K20 - time schedule'!HW46","v":0},{"$f":"'K20 - time schedule'!HX46","v":0},{"$f":"'K20 - time schedule'!HY46","v":0},{"$f":"'K20 - time schedule'!HZ46","v":0},{"$f":"'K20 - time schedule'!IA46","v":0},{"$f":"'K20 - time schedule'!IB46","v":0},{"$f":"'K20 - time schedule'!IC46","v":0},{"$f":"'K20 - time schedule'!ID46","v":0},{"$f":"'K20 - time schedule'!IE46","v":0},{"$f":"'K20 - time schedule'!IF46","v":0},{"$f":"'K20 - time schedule'!IG46","v":0},{"$f":"'K20 - time schedule'!IH46","v":0},{"$f":"'K20 - time schedule'!II46","v":0},{"$f":"'K20 - time schedule'!IJ46","v":0},{"$f":"'K20 - time schedule'!IK46","v":0},{"$f":"'K20 - time schedule'!IL46","v":0},{"$f":"'K20 - time schedule'!IM46","v":0},{"$f":"'K20 - time schedule'!IN46","v":0},{"$f":"'K20 - time schedule'!IO46","v":0},{"$f":"'K20 - time schedule'!IP46","v":0},{"$f":"'K20 - time schedule'!IQ46","v":0},{"$f":"'K20 - time schedule'!IR46","v":0},{"$f":"'K20 - time schedule'!IS46","v":0},{"$f":"'K20 - time schedule'!IT46","v":0},{"$f":"'K20 - time schedule'!IU46","v":0},{"$f":"'K20 - time schedule'!IV46","v":0},{"$f":"'K20 - time schedule'!IW46","v":0},{"$f":"'K20 - time schedule'!IX46","v":0},{"$f":"'K20 - time schedule'!IY46","v":0},{"$f":"'K20 - time schedule'!IZ46","v":0},{"$f":"'K20 - time schedule'!JA46","v":0},{"$f":"'K20 - time schedule'!JB46","v":0},{"$f":"'K20 - time schedule'!JC46","v":0},{"$f":"'K20 - time schedule'!JD46","v":0},{"$f":"'K20 - time schedule'!JE46","v":0},{"$f":"'K20 - time schedule'!JF46","v":0},{"$f":"'K20 - time schedule'!JG46","v":0},{"$f":"'K20 - time schedule'!JH46","v":0},{"$f":"'K20 - time schedule'!JI46","v":0},{"$f":"'K20 - time schedule'!JJ46","v":0},{"$f":"'K20 - time schedule'!JK46","v":0},{"$f":"'K20 - time schedule'!JL46","v":0},{"$f":"'K20 - time schedule'!JM46","v":0},{"$f":"'K20 - time schedule'!JN46","v":0},{"$f":"'K20 - time schedule'!JO46","v":0},{"$f":"'K20 - time schedule'!JP46","v":0},{"$f":"'K20 - time schedule'!JQ46","v":0},{"$f":"'K20 - time schedule'!JR46","v":0},{"$f":"'K20 - time schedule'!JS46","v":0},{"$f":"'K20 - time schedule'!JT46","v":0},{"$f":"'K20 - time schedule'!JU46","v":0},{"$f":"'K20 - time schedule'!JV46","v":0},{"$f":"'K20 - time schedule'!JW46","v":0},{"$f":"'K20 - time schedule'!JX46","v":0},{"$f":"'K20 - time schedule'!JY46","v":0},{"$f":"'K20 - time schedule'!JZ46","v":0},{"$f":"'K20 - time schedule'!KA46","v":0},{"$f":"'K20 - time schedule'!KB46","v":0},{"$f":"'K20 - time schedule'!KC46","v":0},{"$f":"'K20 - time schedule'!KD46","v":0},{"$f":"'K20 - time schedule'!KE46","v":0},{"$f":"'K20 - time schedule'!KF46","v":0},{"$f":"'K20 - time schedule'!KG46","v":0},{"$f":"'K20 - time schedule'!KH46","v":0},{"$f":"'K20 - time schedule'!KI46","v":0},{"$f":"'K20 - time schedule'!KJ46","v":0},{"$f":"'K20 - time schedule'!KK46","v":0},{"$f":"'K20 - time schedule'!KL46","v":0},{"$f":"'K20 - time schedule'!KM46","v":0},{"$f":"'K20 - time schedule'!KN46","v":0},{"$f":"'K20 - time schedule'!KO46","v":0},{"$f":"'K20 - time schedule'!KP46","v":0},{"$f":"'K20 - time schedule'!KQ46","v":0},{"$f":"'K20 - time schedule'!KR46","v":0},{"$f":"'K20 - time schedule'!KS46","v":0},{"$f":"'K20 - time schedule'!KT46","v":0}]
["Boiler room K80 - bottom of combustion chamber","K80","EUR",{"$f":"'K80 - time schedule'!G35","v":0},{"$f":"'K80 - time schedule'!H35","v":0},{"$f":"'K80 - time schedule'!I35","v":0},{"$f":"'K80 - time schedule'!J35","v":0},{"$f":"'K80 - time schedule'!K35","v":0},{"$f":"'K80 - time schedule'!L35","v":0},{"$f":"'K80 - time schedule'!M35","v":0},{"$f":"'K80 - time schedule'!N35","v":0},{"$f":"'K80 - time schedule'!O35","v":0},{"$f":"'K80 - time schedule'!P35","v":0},{"$f":"'K80 - time schedule'!Q35","v":0},{"$f":"'K80 - time schedule'!R35","v":0},{"$f":"'K80 - time schedule'!S35","v":0},{"$f":"'K80 - time schedule'!T35","v":0},{"$f":"'K80 - time schedule'!U35","v":0},{"$f":"'K80 - time schedule'!V35","v":0},{"$f":"'K80 - time schedule'!W35","v":0},{"$f":"'K80 - time schedule'!X35","v":0},{"$f":"'K80 - time schedule'!Y35","v":0},{"$f":"'K80 - time schedule'!Z35","v":0},{"$f":"'K80 - time schedule'!AA35","v":0},{"$f":"'K80 - time schedule'!AB35","v":0},{"$f":"'K80 - time schedule'!AC35","v":0},{"$f":"'K80 - time schedule'!AD35","v":0},{"$f":"'K80 - time schedule'!AE35","v":0},{"$f":"'K80 - time schedule'!AF35","v":0},{"$f":"'K80 - time schedule'!AG35","v":0},{"$f":"'K80 - time schedule'!AH35","v":0},{"$f":"'K80 - time schedule'!AI35","v":0},{"$f":"'K80 - time schedule'!AJ35","v":0},{"$f":"'K80 - time schedule'!AK35","v":0},{"$f":"'K80 - time schedule'!AL35","v":0},{"$f":"'K80 - time schedule'!AM35","v":0},{"$f":"'K80 - time schedule'!AN35","v":0},{"$f":"'K80 - time schedule'!AO35","v":0},{"$f":"'K80 - time schedule'!AP35","v":0},{"$f":"'K80 - time schedule'!AQ35","v":0},{"$f":"'K80 - time schedule'!AR35","v":0},{"$f":"'K80 - time schedule'!AS35","v":0},{"$f":"'K80 - time schedule'!AT35","v":0},{"$f":"'K80 - time schedule'!AU35","v":0},{"$f":"'K80 - time schedule'!AV35","v":0},{"$f":"'K80 - time schedule'!AW35","v":0},{"$f":"'K80 - time schedule'!AX35","v":0},{"$f":"'K80 - time schedule'!AY35","v":0},{"$f":"'K80 - time schedule'!AZ35","v":0},{"$f":"'K80 - time schedule'!BA35","v":0},{"$f":"'K80 - time schedule'!BB35","v":0},{"$f":"'K80 - time schedule'!BC35","v":0},{"$f":"'K80 - time schedule'!BD35","v":0},{"$f":"'K80 - time schedule'!BE35","v":0},{"$f":"'K80 - time schedule'!BF35","v":0},{"$f":"'K80 - time schedule'!BG35","v":0},{"$f":"'K80 - time schedule'!BH35","v":0},{"$f":"'K80 - time schedule'!BI35","v":0},{"$f":"'K80 - time schedule'!BJ35","v":0},{"$f":"'K80 - time schedule'!BK35","v":0},{"$f":"'K80 - time schedule'!BL35","v":0},{"$f":"'K80 - time schedule'!BM35","v":0},{"$f":"'K80 - time schedule'!BN35","v":0},{"$f":"'K80 - time schedule'!BO35","v":0},{"$f":"'K80 - time schedule'!BP35","v":0},{"$f":"'K80 - time schedule'!BQ35","v":0},{"$f":"'K80 - time schedule'!BR35","v":0},{"$f":"'K80 - time schedule'!BS35","v":0},{"$f":"'K80 - time schedule'!BT35","v":0},{"$f":"'K80 - time schedule'!BU35","v":0},{"$f":"'K80 - time schedule'!BV35","v":0},{"$f":"'K80 - time schedule'!BW35","v":0},{"$f":"'K80 - time schedule'!BX35","v":0},{"$f":"'K80 - time schedule'!BY35","v":0},{"$f":"'K80 - time schedule'!BZ35","v":0},{"$f":"'K80 - time schedule'!CA35","v":0},{"$f":"'K80 - time schedule'!CB35","v":0},{"$f":"'K80 - time schedule'!CC35","v":0},{"$f":"'K80 - time schedule'!CD35","v":0},{"$f":"'K80 - time schedule'!CE35","v":0},{"$f":"'K80 - time schedule'!CF35","v":0},{"$f":"'K80 - time schedule'!CG35","v":0},{"$f":"'K80 - time schedule'!CH35","v":0},{"$f":"'K80 - time schedule'!CI35","v":0},{"$f":"'K80 - time schedule'!CJ35","v":0},{"$f":"'K80 - time schedule'!CK35","v":0},{"$f":"'K80 - time schedule'!CL35","v":0},{"$f":"'K80 - time schedule'!CM35","v":0},{"$f":"'K80 - time schedule'!CN35","v":0},{"$f":"'K80 - time schedule'!CO35","v":0},{"$f":"'K80 - time schedule'!CP35","v":0},{"$f":"'K80 - time schedule'!CQ35","v":0},{"$f":"'K80 - time schedule'!CR35","v":0},{"$f":"'K80 - time schedule'!CS35","v":0},{"$f":"'K80 - time schedule'!CT35","v":0},{"$f":"'K80 - time schedule'!CU35","v":0},{"$f":"'K80 - time schedule'!CV35","v":0},{"$f":"'K80 - time schedule'!CW35","v":0},{"$f":"'K80 - time schedule'!CX35","v":0},{"$f":"'K80 - time schedule'!CY35","v":0},{"$f":"'K80 - time schedule'!CZ35","v":0},{"$f":"'K80 - time schedule'!DA35","v":0},{"$f":"'K80 - time schedule'!DB35","v":0},{"$f":"'K80 - time schedule'!DC35","v":0},{"$f":"'K80 - time schedule'!DD35","v":0},{"$f":"'K80 - time schedule'!DE35","v":0},{"$f":"'K80 - time schedule'!DF35","v":0},{"$f":"'K80 - time schedule'!DG35","v":0},{"$f":"'K80 - time schedule'!DH35","v":0},{"$f":"'K80 - time schedule'!DI35","v":0},{"$f":"'K80 - time schedule'!DJ35","v":0},{"$f":"'K80 - time schedule'!DK35","v":0},{"$f":"'K80 - time schedule'!DL35","v":0},{"$f":"'K80 - time schedule'!DM35","v":0},{"$f":"'K80 - time schedule'!DN35","v":0},{"$f":"'K80 - time schedule'!DO35","v":0},{"$f":"'K80 - time schedule'!DP35","v":0},{"$f":"'K80 - time schedule'!DQ35","v":0},{"$f":"'K80 - time schedule'!DR35","v":0},{"$f":"'K80 - time schedule'!DS35","v":0},{"$f":"'K80 - time schedule'!DT35","v":0},{"$f":"'K80 - time schedule'!DU35","v":0},{"$f":"'K80 - time schedule'!DV35","v":0},{"$f":"'K80 - time schedule'!DW35","v":0},{"$f":"'K80 - time schedule'!DX35","v":0},{"$f":"'K80 - time schedule'!DY35","v":0},{"$f":"'K80 - time schedule'!DZ35","v":0},{"$f":"'K80 - time schedule'!EA35","v":0},{"$f":"'K80 - time schedule'!EB35","v":0},{"$f":"'K80 - time schedule'!EC35","v":0},{"$f":"'K80 - time schedule'!ED35","v":0},{"$f":"'K80 - time schedule'!EE35","v":0},{"$f":"'K80 - time schedule'!EF35","v":0},{"$f":"'K80 - time schedule'!EG35","v":0},{"$f":"'K80 - time schedule'!EH35","v":0},{"$f":"'K80 - time schedule'!EI35","v":0},{"$f":"'K80 - time schedule'!EJ35","v":0},{"$f":"'K80 - time schedule'!EK35","v":0},{"$f":"'K80 - time schedule'!EL35","v":0},{"$f":"'K80 - time schedule'!EM35","v":0},{"$f":"'K80 - time schedule'!EN35","v":0},{"$f":"'K80 - time schedule'!EO35","v":0},{"$f":"'K80 - time schedule'!EP35","v":0},{"$f":"'K80 - time schedule'!EQ35","v":0},{"$f":"'K80 - time schedule'!ER35","v":0},{"$f":"'K80 - time schedule'!ES35","v":0},{"$f":"'K80 - time schedule'!ET35","v":0},{"$f":"'K80 - time schedule'!EU35","v":0},{"$f":"'K80 - time schedule'!EV35","v":0},{"$f":"'K80 - time schedule'!EW35","v":0},{"$f":"'K80 - time schedule'!EX35","v":0},{"$f":"'K80 - time schedule'!EY35","v":0},{"$f":"'K80 - time schedule'!EZ35","v":0},{"$f":"'K80 - time schedule'!FA35","v":0},{"$f":"'K80 - time schedule'!FB35","v":0},{"$f":"'K80 - time schedule'!FC35","v":0},{"$f":"'K80 - time schedule'!FD35","v":0},{"$f":"'K80 - time schedule'!FE35","v":0},{"$f":"'K80 - time schedule'!FF35","v":0},{"$f":"'K80 - time schedule'!FG35","v":0},{"$f":"'K80 - time schedule'!FH35","v":0},{"$f":"'K80 - time schedule'!FI35","v":0},{"$f":"'K80 - time schedule'!FJ35","v":0},{"$f":"'K80 - time schedule'!FK35","v":0},{"$f":"'K80 - time schedule'!FL35","v":0},{"$f":"'K80 - time schedule'!FM35","v":0},{"$f":"'K80 - time schedule'!FN35","v":0},{"$f":"'K80 - time schedule'!FO35","v":0},{"$f":"'K80 - time schedule'!FP35","v":0},{"$f":"'K80 - time schedule'!FQ35","v":0},{"$f":"'K80 - time schedule'!FR35","v":0},{"$f":"'K80 - time schedule'!FS35","v":0},{"$f":"'K80 - time schedule'!FT35","v":0},{"$f":"'K80 - time schedule'!FU35","v":0},{"$f":"'K80 - time schedule'!FV35","v":0},{"$f":"'K80 - time schedule'!FW35","v":0},{"$f":"'K80 - time schedule'!FX35","v":0},{"$f":"'K80 - time schedule'!FY35","v":0},{"$f":"'K80 - time schedule'!FZ35","v":0},{"$f":"'K80 - time schedule'!GA35","v":0},{"$f":"'K80 - time schedule'!GB35","v":0},{"$f":"'K80 - time schedule'!GC35","v":0},{"$f":"'K80 - time schedule'!GD35","v":0},{"$f":"'K80 - time schedule'!GE35","v":0},{"$f":"'K80 - time schedule'!GF35","v":0},{"$f":"'K20 - time schedule'!GG47","v":0},{"$f":"'K20 - time schedule'!GH47","v":0},{"$f":"'K20 - time schedule'!GI47","v":0},{"$f":"'K20 - time schedule'!GJ47","v":0},{"$f":"'K20 - time schedule'!GK47","v":0},{"$f":"'K20 - time schedule'!GL47","v":0},{"$f":"'K20 - time schedule'!GM47","v":0},{"$f":"'K20 - time schedule'!GN47","v":0},{"$f":"'K20 - time schedule'!GO47","v":0},{"$f":"'K20 - time schedule'!GP47","v":0},{"$f":"'K20 - time schedule'!GQ47","v":0},{"$f":"'K20 - time schedule'!GR47","v":0},{"$f":"'K20 - time schedule'!GS47","v":0},{"$f":"'K20 - time schedule'!GT47","v":0},{"$f":"'K20 - time schedule'!GU47","v":0},{"$f":"'K20 - time schedule'!GV47","v":0},{"$f":"'K20 - time schedule'!GW47","v":0},{"$f":"'K20 - time schedule'!GX47","v":0},{"$f":"'K20 - time schedule'!GY47","v":0},{"$f":"'K20 - time schedule'!GZ47","v":0},{"$f":"'K20 - time schedule'!HA47","v":0},{"$f":"'K20 - time schedule'!HB47","v":0},{"$f":"'K20 - time schedule'!HC47","v":0},{"$f":"'K20 - time schedule'!HD47","v":0},{"$f":"'K20 - time schedule'!HE47","v":0},{"$f":"'K20 - time schedule'!HF47","v":0},{"$f":"'K20 - time schedule'!HG47","v":0},{"$f":"'K20 - time schedule'!HH47","v":0},{"$f":"'K20 - time schedule'!HI47","v":0},{"$f":"'K20 - time schedule'!HJ47","v":0},{"$f":"'K20 - time schedule'!HK47","v":0},{"$f":"'K20 - time schedule'!HL47","v":0},{"$f":"'K20 - time schedule'!HM47","v":0},{"$f":"'K20 - time schedule'!HN47","v":0},{"$f":"'K20 - time schedule'!HO47","v":0},{"$f":"'K20 - time schedule'!HP47","v":0},{"$f":"'K20 - time schedule'!HQ47","v":0},{"$f":"'K20 - time schedule'!HR47","v":0},{"$f":"'K20 - time schedule'!HS47","v":0},{"$f":"'K20 - time schedule'!HT47","v":0},{"$f":"'K20 - time schedule'!HU47","v":0},{"$f":"'K20 - time schedule'!HV47","v":0},{"$f":"'K20 - time schedule'!HW47","v":0},{"$f":"'K20 - time schedule'!HX47","v":0},{"$f":"'K20 - time schedule'!HY47","v":0},{"$f":"'K20 - time schedule'!HZ47","v":0},{"$f":"'K20 - time schedule'!IA47","v":0},{"$f":"'K20 - time schedule'!IB47","v":0},{"$f":"'K20 - time schedule'!IC47","v":0},{"$f":"'K20 - time schedule'!ID47","v":0},{"$f":"'K20 - time schedule'!IE47","v":0},{"$f":"'K20 - time schedule'!IF47","v":0},{"$f":"'K20 - time schedule'!IG47","v":0},{"$f":"'K20 - time schedule'!IH47","v":0},{"$f":"'K20 - time schedule'!II47","v":0},{"$f":"'K20 - time schedule'!IJ47","v":0},{"$f":"'K20 - time schedule'!IK47","v":0},{"$f":"'K20 - time schedule'!IL47","v":0},{"$f":"'K20 - time schedule'!IM47","v":0},{"$f":"'K20 - time schedule'!IN47","v":0},{"$f":"'K20 - time schedule'!IO47","v":0},{"$f":"'K20 - time schedule'!IP47","v":0},{"$f":"'K20 - time schedule'!IQ47","v":0},{"$f":"'K20 - time schedule'!IR47","v":0},{"$f":"'K20 - time schedule'!IS47","v":0},{"$f":"'K20 - time schedule'!IT47","v":0},{"$f":"'K20 - time schedule'!IU47","v":0},{"$f":"'K20 - time schedule'!IV47","v":0},{"$f":"'K20 - time schedule'!IW47","v":0},{"$f":"'K20 - time schedule'!IX47","v":0},{"$f":"'K20 - time schedule'!IY47","v":0},{"$f":"'K20 - time schedule'!IZ47","v":0},{"$f":"'K20 - time schedule'!JA47","v":0},{"$f":"'K20 - time schedule'!JB47","v":0},{"$f":"'K20 - time schedule'!JC47","v":0},{"$f":"'K20 - time schedule'!JD47","v":0},{"$f":"'K20 - time schedule'!JE47","v":0},{"$f":"'K20 - time schedule'!JF47","v":0},{"$f":"'K20 - time schedule'!JG47","v":0},{"$f":"'K20 - time schedule'!JH47","v":0},{"$f":"'K20 - time schedule'!JI47","v":0},{"$f":"'K20 - time schedule'!JJ47","v":0},{"$f":"'K20 - time schedule'!JK47","v":0},{"$f":"'K20 - time schedule'!JL47","v":0},{"$f":"'K20 - time schedule'!JM47","v":0},{"$f":"'K20 - time schedule'!JN47","v":0},{"$f":"'K20 - time schedule'!JO47","v":0},{"$f":"'K20 - time schedule'!JP47","v":0},{"$f":"'K20 - time schedule'!JQ47","v":0},{"$f":"'K20 - time schedule'!JR47","v":0},{"$f":"'K20 - time schedule'!JS47","v":0},{"$f":"'K20 - time schedule'!JT47","v":0},{"$f":"'K20 - time schedule'!JU47","v":0},{"$f":"'K20 - time schedule'!JV47","v":0},{"$f":"'K20 - time schedule'!JW47","v":0},{"$f":"'K20 - time schedule'!JX47","v":0},{"$f":"'K20 - time schedule'!JY47","v":0},{"$f":"'K20 - time schedule'!JZ47","v":0},{"$f":"'K20 - time schedule'!KA47","v":0},{"$f":"'K20 - time schedule'!KB47","v":0},{"$f":"'K20 - time schedule'!KC47","v":0},{"$f":"'K20 - time schedule'!KD47","v":0},{"$f":"'K20 - time schedule'!KE47","v":0},{"$f":"'K20 - time schedule'!KF47","v":0},{"$f":"'K20 - time schedule'!KG47","v":0},{"$f":"'K20 - time schedule'!KH47","v":0},{"$f":"'K20 - time schedule'!KI47","v":0},{"$f":"'K20 - time schedule'!KJ47","v":0},{"$f":"'K20 - time schedule'!KK47","v":0},{"$f":"'K20 - time schedule'!KL47","v":0},{"$f":"'K20 - time schedule'!KM47","v":0},{"$f":"'K20 - time schedule'!KN47","v":0},{"$f":"'K20 - time schedule'!KO47","v":0},{"$f":"'K20 - time schedule'!KP47","v":0},{"$f":"'K20 - time schedule'!KQ47","v":0},{"$f":"'K20 - time schedule'!KR47","v":0},{"$f":"'K20 - time schedule'!KS47","v":0},{"$f":"'K20 - time schedule'!KT47","v":0}]
["Boiler room K80 - flue lines, including fabric filter","K80","EUR",{"$f":"'K80 - time schedule'!G37","v":0},{"$f":"'K80 - time schedule'!H37","v":0},{"$f":"'K80 - time schedule'!I37","v":0},{"$f":"'K80 - time schedule'!J37","v":0},{"$f":"'K80 - time schedule'!K37","v":0},{"$f":"'K80 - time schedule'!L37","v":0},{"$f":"'K80 - time schedule'!M37","v":0},{"$f":"'K80 - time schedule'!N37","v":0},{"$f":"'K80 - time schedule'!O37","v":0},{"$f":"'K80 - time schedule'!P37","v":0},{"$f":"'K80 - time schedule'!Q37","v":0},{"$f":"'K80 - time schedule'!R37","v":0},{"$f":"'K80 - time schedule'!S37","v":0},{"$f":"'K80 - time schedule'!T37","v":0},{"$f":"'K80 - time schedule'!U37","v":0},{"$f":"'K80 - time schedule'!V37","v":0},{"$f":"'K80 - time schedule'!W37","v":0},{"$f":"'K80 - time schedule'!X37","v":0},{"$f":"'K80 - time schedule'!Y37","v":0},{"$f":"'K80 - time schedule'!Z37","v":0},{"$f":"'K80 - time schedule'!AA37","v":0},{"$f":"'K80 - time schedule'!AB37","v":0},{"$f":"'K80 - time schedule'!AC37","v":0},{"$f":"'K80 - time schedule'!AD37","v":0},{"$f":"'K80 - time schedule'!AE37","v":0},{"$f":"'K80 - time schedule'!AF37","v":0},{"$f":"'K80 - time schedule'!AG37","v":0},{"$f":"'K80 - time schedule'!AH37","v":0},{"$f":"'K80 - time schedule'!AI37","v":0},{"$f":"'K80 - time schedule'!AJ37","v":0},{"$f":"'K80 - time schedule'!AK37","v":0},{"$f":"'K80 - time schedule'!AL37","v":0},{"$f":"'K80 - time schedule'!AM37","v":0},{"$f":"'K80 - time schedule'!AN37","v":0},{"$f":"'K80 - time schedule'!AO37","v":0},{"$f":"'K80 - time schedule'!AP37","v":0},{"$f":"'K80 - time schedule'!AQ37","v":0},{"$f":"'K80 - time schedule'!AR37","v":0},{"$f":"'K80 - time schedule'!AS37","v":0},{"$f":"'K80 - time schedule'!AT37","v":0},{"$f":"'K80 - time schedule'!AU37","v":0},{"$f":"'K80 - time schedule'!AV37","v":0},{"$f":"'K80 - time schedule'!AW37","v":0},{"$f":"'K80 - time schedule'!AX37","v":0},{"$f":"'K80 - time schedule'!AY37","v":0},{"$f":"'K80 - time schedule'!AZ37","v":0},{"$f":"'K80 - time schedule'!BA37","v":0},{"$f":"'K80 - time schedule'!BB37","v":0},{"$f":"'K80 - time schedule'!BC37","v":0},{"$f":"'K80 - time schedule'!BD37","v":0},{"$f":"'K80 - time schedule'!BE37","v":0},{"$f":"'K80 - time schedule'!BF37","v":0},{"$f":"'K80 - time schedule'!BG37","v":0},{"$f":"'K80 - time schedule'!BH37","v":0},{"$f":"'K80 - time schedule'!BI37","v":0},{"$f":"'K80 - time schedule'!BJ37","v":0},{"$f":"'K80 - time schedule'!BK37","v":0},{"$f":"'K80 - time schedule'!BL37","v":0},{"$f":"'K80 - time schedule'!BM37","v":0},{"$f":"'K80 - time schedule'!BN37","v":0},{"$f":"'K80 - time schedule'!BO37","v":0},{"$f":"'K80 - time schedule'!BP37","v":0},{"$f":"'K80 - time schedule'!BQ37","v":0},{"$f":"'K80 - time schedule'!BR37","v":0},{"$f":"'K80 - time schedule'!BS37","v":0},{"$f":"'K80 - time schedule'!BT37","v":0},{"$f":"'K80 - time schedule'!BU37","v":0},{"$f":"'K80 - time schedule'!BV37","v":0},{"$f":"'K80 - time schedule'!BW37","v":0},{"$f":"'K80 - time schedule'!BX37","v":0},{"$f":"'K80 - time schedule'!BY37","v":0},{"$f":"'K80 - time schedule'!BZ37","v":0},{"$f":"'K80 - time schedule'!CA37","v":0},{"$f":"'K80 - time schedule'!CB37","v":0},{"$f":"'K80 - time schedule'!CC37","v":0},{"$f":"'K80 - time schedule'!CD37","v":0},{"$f":"'K80 - time schedule'!CE37","v":0},{"$f":"'K80 - time schedule'!CF37","v":0},{"$f":"'K80 - time schedule'!CG37","v":0},{"$f":"'K80 - time schedule'!CH37","v":0},{"$f":"'K80 - time schedule'!CI37","v":0},{"$f":"'K80 - time schedule'!CJ37","v":0},{"$f":"'K80 - time schedule'!CK37","v":0},{"$f":"'K80 - time schedule'!CL37","v":0},{"$f":"'K80 - time schedule'!CM37","v":0},{"$f":"'K80 - time schedule'!CN37","v":0},{"$f":"'K80 - time schedule'!CO37","v":0},{"$f":"'K80 - time schedule'!CP37","v":0},{"$f":"'K80 - time schedule'!CQ37","v":0},{"$f":"'K80 - time schedule'!CR37","v":0},{"$f":"'K80 - time schedule'!CS37","v":0},{"$f":"'K80 - time schedule'!CT37","v":0},{"$f":"'K80 - time schedule'!CU37","v":0},{"$f":"'K80 - time schedule'!CV37","v":0},{"$f":"'K80 - time schedule'!CW37","v":0},{"$f":"'K80 - time schedule'!CX37","v":0},{"$f":"'K80 - time schedule'!CY37","v":0},{"$f":"'K80 - time schedule'!CZ37","v":0},{"$f":"'K80 - time schedule'!DA37","v":0},{"$f":"'K80 - time schedule'!DB37","v":0},{"$f":"'K80 - time schedule'!DC37","v":0},{"$f":"'K80 - time schedule'!DD37","v":0},{"$f":"'K80 - time schedule'!DE37","v":0},{"$f":"'K80 - time schedule'!DF37","v":0},{"$f":"'K80 - time schedule'!DG37","v":0},{"$f":"'K80 - time schedule'!DH37","v":0},{"$f":"'K80 - time schedule'!DI37","v":0},{"$f":"'K80 - time schedule'!DJ37","v":0},{"$f":"'K80 - time schedule'!DK37","v":0},{"$f":"'K80 - time schedule'!DL37","v":0},{"$f":"'K80 - time schedule'!DM37","v":0},{"$f":"'K80 - time schedule'!DN37","v":0},{"$f":"'K80 - time schedule'!DO37","v":0},{"$f":"'K80 - time schedule'!DP37","v":0},{"$f":"'K80 - time schedule'!DQ37","v":0},{"$f":"'K80 - time schedule'!DR37","v":0},{"$f":"'K80 - time schedule'!DS37","v":0},{"$f":"'K80 - time schedule'!DT37","v":0},{"$f":"'K80 - time schedule'!DU37","v":0},{"$f":"'K80 - time schedule'!DV37","v":0},{"$f":"'K80 - time schedule'!DW37","v":0},{"$f":"'K80 - time schedule'!DX37","v":0},{"$f":"'K80 - time schedule'!DY37","v":0},{"$f":"'K80 - time schedule'!DZ37","v":0},{"$f":"'K80 - time schedule'!EA37","v":0},{"$f":"'K80 - time schedule'!EB37","v":0},{"$f":"'K80 - time schedule'!EC37","v":0},{"$f":"'K80 - time schedule'!ED37","v":0},{"$f":"'K80 - time schedule'!EE37","v":0},{"$f":"'K80 - time schedule'!EF37","v":0},{"$f":"'K80 - time schedule'!EG37","v":0},{"$f":"'K80 - time schedule'!EH37","v":0},{"$f":"'K80 - time schedule'!EI37","v":0},{"$f":"'K80 - time schedule'!EJ37","v":0},{"$f":"'K80 - time schedule'!EK37","v":0},{"$f":"'K80 - time schedule'!EL37","v":0},{"$f":"'K80 - time schedule'!EM37","v":0},{"$f":"'K80 - time schedule'!EN37","v":0},{"$f":"'K80 - time schedule'!EO37","v":0},{"$f":"'K80 - time schedule'!EP37","v":0},{"$f":"'K80 - time schedule'!EQ37","v":0},{"$f":"'K80 - time schedule'!ER37","v":0},{"$f":"'K80 - time schedule'!ES37","v":0},{"$f":"'K80 - time schedule'!ET37","v":0},{"$f":"'K80 - time schedule'!EU37","v":0},{"$f":"'K80 - time schedule'!EV37","v":0},{"$f":"'K80 - time schedule'!EW37","v":0},{"$f":"'K80 - time schedule'!EX37","v":0},{"$f":"'K80 - time schedule'!EY37","v":0},{"$f":"'K80 - time schedule'!EZ37","v":0},{"$f":"'K80 - time schedule'!FA37","v":0},{"$f":"'K80 - time schedule'!FB37","v":0},{"$f":"'K80 - time schedule'!FC37","v":0},{"$f":"'K80 - time schedule'!FD37","v":0},{"$f":"'K80 - time schedule'!FE37","v":0},{"$f":"'K80 - time schedule'!FF37","v":0},{"$f":"'K80 - time schedule'!FG37","v":0},{"$f":"'K80 - time schedule'!FH37","v":0},{"$f":"'K80 - time schedule'!FI37","v":0},{"$f":"'K80 - time schedule'!FJ37","v":0},{"$f":"'K80 - time schedule'!FK37","v":0},{"$f":"'K80 - time schedule'!FL37","v":0},{"$f":"'K80 - time schedule'!FM37","v":0},{"$f":"'K80 - time schedule'!FN37","v":0},{"$f":"'K80 - time schedule'!FO37","v":0},{"$f":"'K80 - time schedule'!FP37","v":0},{"$f":"'K80 - time schedule'!FQ37","v":0},{"$f":"'K80 - time schedule'!FR37","v":0},{"$f":"'K80 - time schedule'!FS37","v":0},{"$f":"'K80 - time schedule'!FT37","v":0},{"$f":"'K80 - time schedule'!FU37","v":0},{"$f":"'K80 - time schedule'!FV37","v":0},{"$f":"'K80 - time schedule'!FW37","v":0},{"$f":"'K80 - time schedule'!FX37","v":0},{"$f":"'K80 - time schedule'!FY37","v":0},{"$f":"'K80 - time schedule'!FZ37","v":0},{"$f":"'K80 - time schedule'!GA37","v":0},{"$f":"'K80 - time schedule'!GB37","v":0},{"$f":"'K80 - time schedule'!GC37","v":0},{"$f":"'K80 - time schedule'!GD37","v":0},{"$f":"'K80 - time schedule'!GE37","v":0},{"$f":"'K80 - time schedule'!GF37","v":0},{"$f":"'K20 - time schedule'!GG48","v":0},{"$f":"'K20 - time schedule'!GH48","v":0},{"$f":"'K20 - time schedule'!GI48","v":0},{"$f":"'K20 - time schedule'!GJ48","v":0},{"$f":"'K20 - time schedule'!GK48","v":0},{"$f":"'K20 - time schedule'!GL48","v":0},{"$f":"'K20 - time schedule'!GM48","v":0},{"$f":"'K20 - time schedule'!GN48","v":0},{"$f":"'K20 - time schedule'!GO48","v":0},{"$f":"'K20 - time schedule'!GP48","v":0},{"$f":"'K20 - time schedule'!GQ48","v":0},{"$f":"'K20 - time schedule'!GR48","v":0},{"$f":"'K20 - time schedule'!GS48","v":0},{"$f":"'K20 - time schedule'!GT48","v":0},{"$f":"'K20 - time schedule'!GU48","v":0},{"$f":"'K20 - time schedule'!GV48","v":0},{"$f":"'K20 - time schedule'!GW48","v":0},{"$f":"'K20 - time schedule'!GX48","v":0},{"$f":"'K20 - time schedule'!GY48","v":0},{"$f":"'K20 - time schedule'!GZ48","v":0},{"$f":"'K20 - time schedule'!HA48","v":0},{"$f":"'K20 - time schedule'!HB48","v":0},{"$f":"'K20 - time schedule'!HC48","v":0},{"$f":"'K20 - time schedule'!HD48","v":0},{"$f":"'K20 - time schedule'!HE48","v":0},{"$f":"'K20 - time schedule'!HF48","v":0},{"$f":"'K20 - time schedule'!HG48","v":0},{"$f":"'K20 - time schedule'!HH48","v":0},{"$f":"'K20 - time schedule'!HI48","v":0},{"$f":"'K20 - time schedule'!HJ48","v":0},{"$f":"'K20 - time schedule'!HK48","v":0},{"$f":"'K20 - time schedule'!HL48","v":0},{"$f":"'K20 - time schedule'!HM48","v":0},{"$f":"'K20 - time schedule'!HN48","v":0},{"$f":"'K20 - time schedule'!HO48","v":0},{"$f":"'K20 - time schedule'!HP48","v":0},{"$f":"'K20 - time schedule'!HQ48","v":0},{"$f":"'K20 - time schedule'!HR48","v":0},{"$f":"'K20 - time schedule'!HS48","v":0},{"$f":"'K20 - time schedule'!HT48","v":0},{"$f":"'K20 - time schedule'!HU48","v":0},{"$f":"'K20 - time schedule'!HV48","v":0},{"$f":"'K20 - time schedule'!HW48","v":0},{"$f":"'K20 - time schedule'!HX48","v":0},{"$f":"'K20 - time schedule'!HY48","v":0},{"$f":"'K20 - time schedule'!HZ48","v":0},{"$f":"'K20 - time schedule'!IA48","v":0},{"$f":"'K20 - time schedule'!IB48","v":0},{"$f":"'K20 - time schedule'!IC48","v":0},{"$f":"'K20 - time schedule'!ID48","v":0},{"$f":"'K20 - time schedule'!IE48","v":0},{"$f":"'K20 - time schedule'!IF48","v":0},{"$f":"'K20 - time schedule'!IG48","v":0},{"$f":"'K20 - time schedule'!IH48","v":0},{"$f":"'K20 - time schedule'!II48","v":0},{"$f":"'K20 - time schedule'!IJ48","v":0},{"$f":"'K20 - time schedule'!IK48","v":0},{"$f":"'K20 - time schedule'!IL48","v":0},{"$f":"'K20 - time schedule'!IM48","v":0},{"$f":"'K20 - time schedule'!IN48","v":0},{"$f":"'K20 - time schedule'!IO48","v":0},{"$f":"'K20 - time schedule'!IP48","v":0},{"$f":"'K20 - time schedule'!IQ48","v":0},{"$f":"'K20 - time schedule'!IR48","v":0},{"$f":"'K20 - time schedule'!IS48","v":0},{"$f":"'K20 - time schedule'!IT48","v":0},{"$f":"'K20 - time schedule'!IU48","v":0},{"$f":"'K20 - time schedule'!IV48","v":0},{"$f":"'K20 - time schedule'!IW48","v":0},{"$f":"'K20 - time schedule'!IX48","v":0},{"$f":"'K20 - time schedule'!IY48","v":0},{"$f":"'K20 - time schedule'!IZ48","v":0},{"$f":"'K20 - time schedule'!JA48","v":0},{"$f":"'K20 - time schedule'!JB48","v":0},{"$f":"'K20 - time schedule'!JC48","v":0},{"$f":"'K20 - time schedule'!JD48","v":0},{"$f":"'K20 - time schedule'!JE48","v":0},{"$f":"'K20 - time schedule'!JF48","v":0},{"$f":"'K20 - time schedule'!JG48","v":0},{"$f":"'K20 - time schedule'!JH48","v":0},{"$f":"'K20 - time schedule'!JI48","v":0},{"$f":"'K20 - time schedule'!JJ48","v":0},{"$f":"'K20 - time schedule'!JK48","v":0},{"$f":"'K20 - time schedule'!JL48","v":0},{"$f":"'K20 - time schedule'!JM48","v":0},{"$f":"'K20 - time schedule'!JN48","v":0},{"$f":"'K20 - time schedule'!JO48","v":0},{"$f":"'K20 - time schedule'!JP48","v":0},{"$f":"'K20 - time schedule'!JQ48","v":0},{"$f":"'K20 - time schedule'!JR48","v":0},{"$f":"'K20 - time schedule'!JS48","v":0},{"$f":"'K20 - time schedule'!JT48","v":0},{"$f":"'K20 - time schedule'!JU48","v":0},{"$f":"'K20 - time schedule'!JV48","v":0},{"$f":"'K20 - time schedule'!JW48","v":0},{"$f":"'K20 - time schedule'!JX48","v":0},{"$f":"'K20 - time schedule'!JY48","v":0},{"$f":"'K20 - time schedule'!JZ48","v":0},{"$f":"'K20 - time schedule'!KA48","v":0},{"$f":"'K20 - time schedule'!KB48","v":0},{"$f":"'K20 - time schedule'!KC48","v":0},{"$f":"'K20 - time schedule'!KD48","v":0},{"$f":"'K20 - time schedule'!KE48","v":0},{"$f":"'K20 - time schedule'!KF48","v":0},{"$f":"'K20 - time schedule'!KG48","v":0},{"$f":"'K20 - time schedule'!KH48","v":0},{"$f":"'K20 - time schedule'!KI48","v":0},{"$f":"'K20 - time schedule'!KJ48","v":0},{"$f":"'K20 - time schedule'!KK48","v":0},{"$f":"'K20 - time schedule'!KL48","v":0},{"$f":"'K20 - time schedule'!KM48","v":0},{"$f":"'K20 - time schedule'!KN48","v":0},{"$f":"'K20 - time schedule'!KO48","v":0},{"$f":"'K20 - time schedule'!KP48","v":0},{"$f":"'K20 - time schedule'!KQ48","v":0},{"$f":"'K20 - time schedule'!KR48","v":0},{"$f":"'K20 - time schedule'!KS48","v":0},{"$f":"'K20 - time schedule'!KT48","v":0}]
["Boiler room K80 - electrical installation","K80","EUR",{"$f":"'K80 - time schedule'!G39","v":0},{"$f":"'K80 - time schedule'!H39","v":0},{"$f":"'K80 - time schedule'!I39","v":0},{"$f":"'K80 - time schedule'!J39","v":0},{"$f":"'K80 - time schedule'!K39","v":0},{"$f":"'K80 - time schedule'!L39","v":0},{"$f":"'K80 - time schedule'!M39","v":0},{"$f":"'K80 - time schedule'!N39","v":0},{"$f":"'K80 - time schedule'!O39","v":0},{"$f":"'K80 - time schedule'!P39","v":0},{"$f":"'K80 - time schedule'!Q39","v":0},{"$f":"'K80 - time schedule'!R39","v":0},{"$f":"'K80 - time schedule'!S39","v":0},{"$f":"'K80 - time schedule'!T39","v":0},{"$f":"'K80 - time schedule'!U39","v":0},{"$f":"'K80 - time schedule'!V39","v":0},{"$f":"'K80 - time schedule'!W39","v":0},{"$f":"'K80 - time schedule'!X39","v":0},{"$f":"'K80 - time schedule'!Y39","v":0},{"$f":"'K80 - time schedule'!Z39","v":0},{"$f":"'K80 - time schedule'!AA39","v":0},{"$f":"'K80 - time schedule'!AB39","v":0},{"$f":"'K80 - time schedule'!AC39","v":0},{"$f":"'K80 - time schedule'!AD39","v":0},{"$f":"'K80 - time schedule'!AE39","v":0},{"$f":"'K80 - time schedule'!AF39","v":0},{"$f":"'K80 - time schedule'!AG39","v":0},{"$f":"'K80 - time schedule'!AH39","v":0},{"$f":"'K80 - time schedule'!AI39","v":0},{"$f":"'K80 - time schedule'!AJ39","v":0},{"$f":"'K80 - time schedule'!AK39","v":0},{"$f":"'K80 - time schedule'!AL39","v":0},{"$f":"'K80 - time schedule'!AM39","v":0},{"$f":"'K80 - time schedule'!AN39","v":0},{"$f":"'K80 - time schedule'!AO39","v":0},{"$f":"'K80 - time schedule'!AP39","v":0},{"$f":"'K80 - time schedule'!AQ39","v":0},{"$f":"'K80 - time schedule'!AR39","v":0},{"$f":"'K80 - time schedule'!AS39","v":0},{"$f":"'K80 - time schedule'!AT39","v":0},{"$f":"'K80 - time schedule'!AU39","v":0},{"$f":"'K80 - time schedule'!AV39","v":0},{"$f":"'K80 - time schedule'!AW39","v":0},{"$f":"'K80 - time schedule'!AX39","v":0},{"$f":"'K80 - time schedule'!AY39","v":0},{"$f":"'K80 - time schedule'!AZ39","v":0},{"$f":"'K80 - time schedule'!BA39","v":0},{"$f":"'K80 - time schedule'!BB39","v":0},{"$f":"'K80 - time schedule'!BC39","v":0},{"$f":"'K80 - time schedule'!BD39","v":0},{"$f":"'K80 - time schedule'!BE39","v":0},{"$f":"'K80 - time schedule'!BF39","v":0},{"$f":"'K80 - time schedule'!BG39","v":0},{"$f":"'K80 - time schedule'!BH39","v":0},{"$f":"'K80 - time schedule'!BI39","v":0},{"$f":"'K80 - time schedule'!BJ39","v":0},{"$f":"'K80 - time schedule'!BK39","v":0},{"$f":"'K80 - time schedule'!BL39","v":0},{"$f":"'K80 - time schedule'!BM39","v":0},{"$f":"'K80 - time schedule'!BN39","v":0},{"$f":"'K80 - time schedule'!BO39","v":0},{"$f":"'K80 - time schedule'!BP39","v":0},{"$f":"'K80 - time schedule'!BQ39","v":0},{"$f":"'K80 - time schedule'!BR39","v":0},{"$f":"'K80 - time schedule'!BS39","v":0},{"$f":"'K80 - time schedule'!BT39","v":0},{"$f":"'K80 - time schedule'!BU39","v":0},{"$f":"'K80 - time schedule'!BV39","v":0},{"$f":"'K80 - time schedule'!BW39","v":0},{"$f":"'K80 - time schedule'!BX39","v":0},{"$f":"'K80 - time schedule'!BY39","v":0},{"$f":"'K80 - time schedule'!BZ39","v":0},{"$f":"'K80 - time schedule'!CA39","v":0},{"$f":"'K80 - time schedule'!CB39","v":0},{"$f":"'K80 - time schedule'!CC39","v":0},{"$f":"'K80 - time schedule'!CD39","v":0},{"$f":"'K80 - time schedule'!CE39","v":0},{"$f":"'K80 - time schedule'!CF39","v":0},{"$f":"'K80 - time schedule'!CG39","v":0},{"$f":"'K80 - time schedule'!CH39","v":0},{"$f":"'K80 - time schedule'!CI39","v":0},{"$f":"'K80 - time schedule'!CJ39","v":0},{"$f":"'K80 - time schedule'!CK39","v":0},{"$f":"'K80 - time schedule'!CL39","v":0},{"$f":"'K80 - time schedule'!CM39","v":0},{"$f":"'K80 - time schedule'!CN39","v":0},{"$f":"'K80 - time schedule'!CO39","v":0},{"$f":"'K80 - time schedule'!CP39","v":0},{"$f":"'K80 - time schedule'!CQ39","v":0},{"$f":"'K80 - time schedule'!CR39","v":0},{"$f":"'K80 - time schedule'!CS39","v":0},{"$f":"'K80 - time schedule'!CT39","v":0},{"$f":"'K80 - time schedule'!CU39","v":0},{"$f":"'K80 - time schedule'!CV39","v":0},{"$f":"'K80 - time schedule'!CW39","v":0},{"$f":"'K80 - time schedule'!CX39","v":0},{"$f":"'K80 - time schedule'!CY39","v":0},{"$f":"'K80 - time schedule'!CZ39","v":0},{"$f":"'K80 - time schedule'!DA39","v":0},{"$f":"'K80 - time schedule'!DB39","v":0},{"$f":"'K80 - time schedule'!DC39","v":0},{"$f":"'K80 - time schedule'!DD39","v":0},{"$f":"'K80 - time schedule'!DE39","v":0},{"$f":"'K80 - time schedule'!DF39","v":0},{"$f":"'K80 - time schedule'!DG39","v":0},{"$f":"'K80 - time schedule'!DH39","v":0},{"$f":"'K80 - time schedule'!DI39","v":0},{"$f":"'K80 - time schedule'!DJ39","v":0},{"$f":"'K80 - time schedule'!DK39","v":0},{"$f":"'K80 - time schedule'!DL39","v":0},{"$f":"'K80 - time schedule'!DM39","v":0},{"$f":"'K80 - time schedule'!DN39","v":0},{"$f":"'K80 - time schedule'!DO39","v":0},{"$f":"'K80 - time schedule'!DP39","v":0},{"$f":"'K80 - time schedule'!DQ39","v":0},{"$f":"'K80 - time schedule'!DR39","v":0},{"$f":"'K80 - time schedule'!DS39","v":0},{"$f":"'K80 - time schedule'!DT39","v":0},{"$f":"'K80 - time schedule'!DU39","v":0},{"$f":"'K80 - time schedule'!DV39","v":0},{"$f":"'K80 - time schedule'!DW39","v":0},{"$f":"'K80 - time schedule'!DX39","v":0},{"$f":"'K80 - time schedule'!DY39","v":0},{"$f":"'K80 - time schedule'!DZ39","v":0},{"$f":"'K80 - time schedule'!EA39","v":0},{"$f":"'K80 - time schedule'!EB39","v":0},{"$f":"'K80 - time schedule'!EC39","v":0},{"$f":"'K80 - time schedule'!ED39","v":0},{"$f":"'K80 - time schedule'!EE39","v":0},{"$f":"'K80 - time schedule'!EF39","v":0},{"$f":"'K80 - time schedule'!EG39","v":0},{"$f":"'K80 - time schedule'!EH39","v":0},{"$f":"'K80 - time schedule'!EI39","v":0},{"$f":"'K80 - time schedule'!EJ39","v":0},{"$f":"'K80 - time schedule'!EK39","v":0},{"$f":"'K80 - time schedule'!EL39","v":0},{"$f":"'K80 - time schedule'!EM39","v":0},{"$f":"'K80 - time schedule'!EN39","v":0},{"$f":"'K80 - time schedule'!EO39","v":0},{"$f":"'K80 - time schedule'!EP39","v":0},{"$f":"'K80 - time schedule'!EQ39","v":0},{"$f":"'K80 - time schedule'!ER39","v":0},{"$f":"'K80 - time schedule'!ES39","v":0},{"$f":"'K80 - time schedule'!ET39","v":0},{"$f":"'K80 - time schedule'!EU39","v":0},{"$f":"'K80 - time schedule'!EV39","v":0},{"$f":"'K80 - time schedule'!EW39","v":0},{"$f":"'K80 - time schedule'!EX39","v":0},{"$f":"'K80 - time schedule'!EY39","v":0},{"$f":"'K80 - time schedule'!EZ39","v":0},{"$f":"'K80 - time schedule'!FA39","v":0},{"$f":"'K80 - time schedule'!FB39","v":0},{"$f":"'K80 - time schedule'!FC39","v":0},{"$f":"'K80 - time schedule'!FD39","v":0},{"$f":"'K80 - time schedule'!FE39","v":0},{"$f":"'K80 - time schedule'!FF39","v":0},{"$f":"'K80 - time schedule'!FG39","v":0},{"$f":"'K80 - time schedule'!FH39","v":0},{"$f":"'K80 - time schedule'!FI39","v":0},{"$f":"'K80 - time schedule'!FJ39","v":0},{"$f":"'K80 - time schedule'!FK39","v":0},{"$f":"'K80 - time schedule'!FL39","v":0},{"$f":"'K80 - time schedule'!FM39","v":0},{"$f":"'K80 - time schedule'!FN39","v":0},{"$f":"'K80 - time schedule'!FO39","v":0},{"$f":"'K80 - time schedule'!FP39","v":0},{"$f":"'K80 - time schedule'!FQ39","v":0},{"$f":"'K80 - time schedule'!FR39","v":0},{"$f":"'K80 - time schedule'!FS39","v":0},{"$f":"'K80 - time schedule'!FT39","v":0},{"$f":"'K80 - time schedule'!FU39","v":0},{"$f":"'K80 - time schedule'!FV39","v":0},{"$f":"'K80 - time schedule'!FW39","v":0},{"$f":"'K80 - time schedule'!FX39","v":0},{"$f":"'K80 - time schedule'!FY39","v":0},{"$f":"'K80 - time schedule'!FZ39","v":0},{"$f":"'K80 - time schedule'!GA39","v":0},{"$f":"'K80 - time schedule'!GB39","v":0},{"$f":"'K80 - time schedule'!GC39","v":0},{"$f":"'K80 - time schedule'!GD39","v":0},{"$f":"'K80 - time schedule'!GE39","v":0},{"$f":"'K80 - time schedule'!GF39","v":0},{"$f":"'K20 - time schedule'!GG49","v":0},{"$f":"'K20 - time schedule'!GH49","v":0},{"$f":"'K20 - time schedule'!GI49","v":0},{"$f":"'K20 - time schedule'!GJ49","v":0},{"$f":"'K20 - time schedule'!GK49","v":0},{"$f":"'K20 - time schedule'!GL49","v":0},{"$f":"'K20 - time schedule'!GM49","v":0},{"$f":"'K20 - time schedule'!GN49","v":0},{"$f":"'K20 - time schedule'!GO49","v":0},{"$f":"'K20 - time schedule'!GP49","v":0},{"$f":"'K20 - time schedule'!GQ49","v":0},{"$f":"'K20 - time schedule'!GR49","v":0},{"$f":"'K20 - time schedule'!GS49","v":0},{"$f":"'K20 - time schedule'!GT49","v":0},{"$f":"'K20 - time schedule'!GU49","v":0},{"$f":"'K20 - time schedule'!GV49","v":0},{"$f":"'K20 - time schedule'!GW49","v":0},{"$f":"'K20 - time schedule'!GX49","v":0},{"$f":"'K20 - time schedule'!GY49","v":0},{"$f":"'K20 - time schedule'!GZ49","v":0},{"$f":"'K20 - time schedule'!HA49","v":0},{"$f":"'K20 - time schedule'!HB49","v":0},{"$f":"'K20 - time schedule'!HC49","v":0},{"$f":"'K20 - time schedule'!HD49","v":0},{"$f":"'K20 - time schedule'!HE49","v":0},{"$f":"'K20 - time schedule'!HF49","v":0},{"$f":"'K20 - time schedule'!HG49","v":0},{"$f":"'K20 - time schedule'!HH49","v":0},{"$f":"'K20 - time schedule'!HI49","v":0},{"$f":"'K20 - time schedule'!HJ49","v":0},{"$f":"'K20 - time schedule'!HK49","v":0},{"$f":"'K20 - time schedule'!HL49","v":0},{"$f":"'K20 - time schedule'!HM49","v":0},{"$f":"'K20 - time schedule'!HN49","v":0},{"$f":"'K20 - time schedule'!HO49","v":0},{"$f":"'K20 - time schedule'!HP49","v":0},{"$f":"'K20 - time schedule'!HQ49","v":0},{"$f":"'K20 - time schedule'!HR49","v":0},{"$f":"'K20 - time schedule'!HS49","v":0},{"$f":"'K20 - time schedule'!HT49","v":0},{"$f":"'K20 - time schedule'!HU49","v":0},{"$f":"'K20 - time schedule'!HV49","v":0},{"$f":"'K20 - time schedule'!HW49","v":0},{"$f":"'K20 - time schedule'!HX49","v":0},{"$f":"'K20 - time schedule'!HY49","v":0},{"$f":"'K20 - time schedule'!HZ49","v":0},{"$f":"'K20 - time schedule'!IA49","v":0},{"$f":"'K20 - time schedule'!IB49","v":0},{"$f":"'K20 - time schedule'!IC49","v":0},{"$f":"'K20 - time schedule'!ID49","v":0},{"$f":"'K20 - time schedule'!IE49","v":0},{"$f":"'K20 - time schedule'!IF49","v":0},{"$f":"'K20 - time schedule'!IG49","v":0},{"$f":"'K20 - time schedule'!IH49","v":0},{"$f":"'K20 - time schedule'!II49","v":0},{"$f":"'K20 - time schedule'!IJ49","v":0},{"$f":"'K20 - time schedule'!IK49","v":0},{"$f":"'K20 - time schedule'!IL49","v":0},{"$f":"'K20 - time schedule'!IM49","v":0},{"$f":"'K20 - time schedule'!IN49","v":0},{"$f":"'K20 - time schedule'!IO49","v":0},{"$f":"'K20 - time schedule'!IP49","v":0},{"$f":"'K20 - time schedule'!IQ49","v":0},{"$f":"'K20 - time schedule'!IR49","v":0},{"$f":"'K20 - time schedule'!IS49","v":0},{"$f":"'K20 - time schedule'!IT49","v":0},{"$f":"'K20 - time schedule'!IU49","v":0},{"$f":"'K20 - time schedule'!IV49","v":0},{"$f":"'K20 - time schedule'!IW49","v":0},{"$f":"'K20 - time schedule'!IX49","v":0},{"$f":"'K20 - time schedule'!IY49","v":0},{"$f":"'K20 - time schedule'!IZ49","v":0},{"$f":"'K20 - time schedule'!JA49","v":0},{"$f":"'K20 - time schedule'!JB49","v":0},{"$f":"'K20 - time schedule'!JC49","v":0},{"$f":"'K20 - time schedule'!JD49","v":0},{"$f":"'K20 - time schedule'!JE49","v":0},{"$f":"'K20 - time schedule'!JF49","v":0},{"$f":"'K20 - time schedule'!JG49","v":0},{"$f":"'K20 - time schedule'!JH49","v":0},{"$f":"'K20 - time schedule'!JI49","v":0},{"$f":"'K20 - time schedule'!JJ49","v":0},{"$f":"'K20 - time schedule'!JK49","v":0},{"$f":"'K20 - time schedule'!JL49","v":0},{"$f":"'K20 - time schedule'!JM49","v":0},{"$f":"'K20 - time schedule'!JN49","v":0},{"$f":"'K20 - time schedule'!JO49","v":0},{"$f":"'K20 - time schedule'!JP49","v":0},{"$f":"'K20 - time schedule'!JQ49","v":0},{"$f":"'K20 - time schedule'!JR49","v":0},{"$f":"'K20 - time schedule'!JS49","v":0},{"$f":"'K20 - time schedule'!JT49","v":0},{"$f":"'K20 - time schedule'!JU49","v":0},{"$f":"'K20 - time schedule'!JV49","v":0},{"$f":"'K20 - time schedule'!JW49","v":0},{"$f":"'K20 - time schedule'!JX49","v":0},{"$f":"'K20 - time schedule'!JY49","v":0},{"$f":"'K20 - time schedule'!JZ49","v":0},{"$f":"'K20 - time schedule'!KA49","v":0},{"$f":"'K20 - time schedule'!KB49","v":0},{"$f":"'K20 - time schedule'!KC49","v":0},{"$f":"'K20 - time schedule'!KD49","v":0},{"$f":"'K20 - time schedule'!KE49","v":0},{"$f":"'K20 - time schedule'!KF49","v":0},{"$f":"'K20 - time schedule'!KG49","v":0},{"$f":"'K20 - time schedule'!KH49","v":0},{"$f":"'K20 - time schedule'!KI49","v":0},{"$f":"'K20 - time schedule'!KJ49","v":0},{"$f":"'K20 - time schedule'!KK49","v":0},{"$f":"'K20 - time schedule'!KL49","v":0},{"$f":"'K20 - time schedule'!KM49","v":0},{"$f":"'K20 - time schedule'!KN49","v":0},{"$f":"'K20 - time schedule'!KO49","v":0},{"$f":"'K20 - time schedule'!KP49","v":0},{"$f":"'K20 - time schedule'!KQ49","v":0},{"$f":"'K20 - time schedule'!KR49","v":0},{"$f":"'K20 - time schedule'!KS49","v":0},{"$f":"'K20 - time schedule'!KT49","v":0}]
["Boiler room K80 - management of automatic control system","K80","EUR",{"$f":"'K80 - time schedule'!G41","v":0},{"$f":"'K80 - time schedule'!H41","v":0},{"$f":"'K80 - time schedule'!I41","v":0},{"$f":"'K80 - time schedule'!J41","v":0},{"$f":"'K80 - time schedule'!K41","v":0},{"$f":"'K80 - time schedule'!L41","v":0},{"$f":"'K80 - time schedule'!M41","v":0},{"$f":"'K80 - time schedule'!N41","v":0},{"$f":"'K80 - time schedule'!O41","v":0},{"$f":"'K80 - time schedule'!P41","v":0},{"$f":"'K80 - time schedule'!Q41","v":0},{"$f":"'K80 - time schedule'!R41","v":0},{"$f":"'K80 - time schedule'!S41","v":0},{"$f":"'K80 - time schedule'!T41","v":0},{"$f":"'K80 - time schedule'!U41","v":0},{"$f":"'K80 - time schedule'!V41","v":0},{"$f":"'K80 - time schedule'!W41","v":0},{"$f":"'K80 - time schedule'!X41","v":0},{"$f":"'K80 - time schedule'!Y41","v":0},{"$f":"'K80 - time schedule'!Z41","v":0},{"$f":"'K80 - time schedule'!AA41","v":0},{"$f":"'K80 - time schedule'!AB41","v":0},{"$f":"'K80 - time schedule'!AC41","v":0},{"$f":"'K80 - time schedule'!AD41","v":0},{"$f":"'K80 - time schedule'!AE41","v":0},{"$f":"'K80 - time schedule'!AF41","v":0},{"$f":"'K80 - time schedule'!AG41","v":0},{"$f":"'K80 - time schedule'!AH41","v":0},{"$f":"'K80 - time schedule'!AI41","v":0},{"$f":"'K80 - time schedule'!AJ41","v":0},{"$f":"'K80 - time schedule'!AK41","v":0},{"$f":"'K80 - time schedule'!AL41","v":0},{"$f":"'K80 - time schedule'!AM41","v":0},{"$f":"'K80 - time schedule'!AN41","v":0},{"$f":"'K80 - time schedule'!AO41","v":0},{"$f":"'K80 - time schedule'!AP41","v":0},{"$f":"'K80 - time schedule'!AQ41","v":0},{"$f":"'K80 - time schedule'!AR41","v":0},{"$f":"'K80 - time schedule'!AS41","v":0},{"$f":"'K80 - time schedule'!AT41","v":0},{"$f":"'K80 - time schedule'!AU41","v":0},{"$f":"'K80 - time schedule'!AV41","v":0},{"$f":"'K80 - time schedule'!AW41","v":0},{"$f":"'K80 - time schedule'!AX41","v":0},{"$f":"'K80 - time schedule'!AY41","v":0},{"$f":"'K80 - time schedule'!AZ41","v":0},{"$f":"'K80 - time schedule'!BA41","v":0},{"$f":"'K80 - time schedule'!BB41","v":0},{"$f":"'K80 - time schedule'!BC41","v":0},{"$f":"'K80 - time schedule'!BD41","v":0},{"$f":"'K80 - time schedule'!BE41","v":0},{"$f":"'K80 - time schedule'!BF41","v":0},{"$f":"'K80 - time schedule'!BG41","v":0},{"$f":"'K80 - time schedule'!BH41","v":0},{"$f":"'K80 - time schedule'!BI41","v":0},{"$f":"'K80 - time schedule'!BJ41","v":0},{"$f":"'K80 - time schedule'!BK41","v":0},{"$f":"'K80 - time schedule'!BL41","v":0},{"$f":"'K80 - time schedule'!BM41","v":0},{"$f":"'K80 - time schedule'!BN41","v":0},{"$f":"'K80 - time schedule'!BO41","v":0},{"$f":"'K80 - time schedule'!BP41","v":0},{"$f":"'K80 - time schedule'!BQ41","v":0},{"$f":"'K80 - time schedule'!BR41","v":0},{"$f":"'K80 - time schedule'!BS41","v":0},{"$f":"'K80 - time schedule'!BT41","v":0},{"$f":"'K80 - time schedule'!BU41","v":0},{"$f":"'K80 - time schedule'!BV41","v":0},{"$f":"'K80 - time schedule'!BW41","v":0},{"$f":"'K80 - time schedule'!BX41","v":0},{"$f":"'K80 - time schedule'!BY41","v":0},{"$f":"'K80 - time schedule'!BZ41","v":0},{"$f":"'K80 - time schedule'!CA41","v":0},{"$f":"'K80 - time schedule'!CB41","v":0},{"$f":"'K80 - time schedule'!CC41","v":0},{"$f":"'K80 - time schedule'!CD41","v":0},{"$f":"'K80 - time schedule'!CE41","v":0},{"$f":"'K80 - time schedule'!CF41","v":0},{"$f":"'K80 - time schedule'!CG41","v":0},{"$f":"'K80 - time schedule'!CH41","v":0},{"$f":"'K80 - time schedule'!CI41","v":0},{"$f":"'K80 - time schedule'!CJ41","v":0},{"$f":"'K80 - time schedule'!CK41","v":0},{"$f":"'K80 - time schedule'!CL41","v":0},{"$f":"'K80 - time schedule'!CM41","v":0},{"$f":"'K80 - time schedule'!CN41","v":0},{"$f":"'K80 - time schedule'!CO41","v":0},{"$f":"'K80 - time schedule'!CP41","v":0},{"$f":"'K80 - time schedule'!CQ41","v":0},{"$f":"'K80 - time schedule'!CR41","v":0},{"$f":"'K80 - time schedule'!CS41","v":0},{"$f":"'K80 - time schedule'!CT41","v":0},{"$f":"'K80 - time schedule'!CU41","v":0},{"$f":"'K80 - time schedule'!CV41","v":0},{"$f":"'K80 - time schedule'!CW41","v":0},{"$f":"'K80 - time schedule'!CX41","v":0},{"$f":"'K80 - time schedule'!CY41","v":0},{"$f":"'K80 - time schedule'!CZ41","v":0},{"$f":"'K80 - time schedule'!DA41","v":0},{"$f":"'K80 - time schedule'!DB41","v":0},{"$f":"'K80 - time schedule'!DC41","v":0},{"$f":"'K80 - time schedule'!DD41","v":0},{"$f":"'K80 - time schedule'!DE41","v":0},{"$f":"'K80 - time schedule'!DF41","v":0},{"$f":"'K80 - time schedule'!DG41","v":0},{"$f":"'K80 - time schedule'!DH41","v":0},{"$f":"'K80 - time schedule'!DI41","v":0},{"$f":"'K80 - time schedule'!DJ41","v":0},{"$f":"'K80 - time schedule'!DK41","v":0},{"$f":"'K80 - time schedule'!DL41","v":0},{"$f":"'K80 - time schedule'!DM41","v":0},{"$f":"'K80 - time schedule'!DN41","v":0},{"$f":"'K80 - time schedule'!DO41","v":0},{"$f":"'K80 - time schedule'!DP41","v":0},{"$f":"'K80 - time schedule'!DQ41","v":0},{"$f":"'K80 - time schedule'!DR41","v":0},{"$f":"'K80 - time schedule'!DS41","v":0},{"$f":"'K80 - time schedule'!DT41","v":0},{"$f":"'K80 - time schedule'!DU41","v":0},{"$f":"'K80 - time schedule'!DV41","v":0},{"$f":"'K80 - time schedule'!DW41","v":0},{"$f":"'K80 - time schedule'!DX41","v":0},{"$f":"'K80 - time schedule'!DY41","v":0},{"$f":"'K80 - time schedule'!DZ41","v":0},{"$f":"'K80 - time schedule'!EA41","v":0},{"$f":"'K80 - time schedule'!EB41","v":0},{"$f":"'K80 - time schedule'!EC41","v":0},{"$f":"'K80 - time schedule'!ED41","v":0},{"$f":"'K80 - time schedule'!EE41","v":0},{"$f":"'K80 - time schedule'!EF41","v":0},{"$f":"'K80 - time schedule'!EG41","v":0},{"$f":"'K80 - time schedule'!EH41","v":0},{"$f":"'K80 - time schedule'!EI41","v":0},{"$f":"'K80 - time schedule'!EJ41","v":0},{"$f":"'K80 - time schedule'!EK41","v":0},{"$f":"'K80 - time schedule'!EL41","v":0},{"$f":"'K80 - time schedule'!EM41","v":0},{"$f":"'K80 - time schedule'!EN41","v":0},{"$f":"'K80 - time schedule'!EO41","v":0},{"$f":"'K80 - time schedule'!EP41","v":0},{"$f":"'K80 - time schedule'!EQ41","v":0},{"$f":"'K80 - time schedule'!ER41","v":0},{"$f":"'K80 - time schedule'!ES41","v":0},{"$f":"'K80 - time schedule'!ET41","v":0},{"$f":"'K80 - time schedule'!EU41","v":0},{"$f":"'K80 - time schedule'!EV41","v":0},{"$f":"'K80 - time schedule'!EW41","v":0},{"$f":"'K80 - time schedule'!EX41","v":0},{"$f":"'K80 - time schedule'!EY41","v":0},{"$f":"'K80 - time schedule'!EZ41","v":0},{"$f":"'K80 - time schedule'!FA41","v":0},{"$f":"'K80 - time schedule'!FB41","v":0},{"$f":"'K80 - time schedule'!FC41","v":0},{"$f":"'K80 - time schedule'!FD41","v":0},{"$f":"'K80 - time schedule'!FE41","v":0},{"$f":"'K80 - time schedule'!FF41","v":0},{"$f":"'K80 - time schedule'!FG41","v":0},{"$f":"'K80 - time schedule'!FH41","v":0},{"$f":"'K80 - time schedule'!FI41","v":0},{"$f":"'K80 - time schedule'!FJ41","v":0},{"$f":"'K80 - time schedule'!FK41","v":0},{"$f":"'K80 - time schedule'!FL41","v":0},{"$f":"'K80 - time schedule'!FM41","v":0},{"$f":"'K80 - time schedule'!FN41","v":0},{"$f":"'K80 - time schedule'!FO41","v":0},{"$f":"'K80 - time schedule'!FP41","v":0},{"$f":"'K80 - time schedule'!FQ41","v":0},{"$f":"'K80 - time schedule'!FR41","v":0},{"$f":"'K80 - time schedule'!FS41","v":0},{"$f":"'K80 - time schedule'!FT41","v":0},{"$f":"'K80 - time schedule'!FU41","v":0},{"$f":"'K80 - time schedule'!FV41","v":0},{"$f":"'K80 - time schedule'!FW41","v":0},{"$f":"'K80 - time schedule'!FX41","v":0},{"$f":"'K80 - time schedule'!FY41","v":0},{"$f":"'K80 - time schedule'!FZ41","v":0},{"$f":"'K80 - time schedule'!GA41","v":0},{"$f":"'K80 - time schedule'!GB41","v":0},{"$f":"'K80 - time schedule'!GC41","v":0},{"$f":"'K80 - time schedule'!GD41","v":0},{"$f":"'K80 - time schedule'!GE41","v":0},{"$f":"'K80 - time schedule'!GF41","v":0},{"$f":"'K20 - time schedule'!GG50","v":0},{"$f":"'K20 - time schedule'!GH50","v":0},{"$f":"'K20 - time schedule'!GI50","v":0},{"$f":"'K20 - time schedule'!GJ50","v":0},{"$f":"'K20 - time schedule'!GK50","v":0},{"$f":"'K20 - time schedule'!GL50","v":0},{"$f":"'K20 - time schedule'!GM50","v":0},{"$f":"'K20 - time schedule'!GN50","v":0},{"$f":"'K20 - time schedule'!GO50","v":0},{"$f":"'K20 - time schedule'!GP50","v":0},{"$f":"'K20 - time schedule'!GQ50","v":0},{"$f":"'K20 - time schedule'!GR50","v":0},{"$f":"'K20 - time schedule'!GS50","v":0},{"$f":"'K20 - time schedule'!GT50","v":0},{"$f":"'K20 - time schedule'!GU50","v":0},{"$f":"'K20 - time schedule'!GV50","v":0},{"$f":"'K20 - time schedule'!GW50","v":0},{"$f":"'K20 - time schedule'!GX50","v":0},{"$f":"'K20 - time schedule'!GY50","v":0},{"$f":"'K20 - time schedule'!GZ50","v":0},{"$f":"'K20 - time schedule'!HA50","v":0},{"$f":"'K20 - time schedule'!HB50","v":0},{"$f":"'K20 - time schedule'!HC50","v":0},{"$f":"'K20 - time schedule'!HD50","v":0},{"$f":"'K20 - time schedule'!HE50","v":0},{"$f":"'K20 - time schedule'!HF50","v":0},{"$f":"'K20 - time schedule'!HG50","v":0},{"$f":"'K20 - time schedule'!HH50","v":0},{"$f":"'K20 - time schedule'!HI50","v":0},{"$f":"'K20 - time schedule'!HJ50","v":0},{"$f":"'K20 - time schedule'!HK50","v":0},{"$f":"'K20 - time schedule'!HL50","v":0},{"$f":"'K20 - time schedule'!HM50","v":0},{"$f":"'K20 - time schedule'!HN50","v":0},{"$f":"'K20 - time schedule'!HO50","v":0},{"$f":"'K20 - time schedule'!HP50","v":0},{"$f":"'K20 - time schedule'!HQ50","v":0},{"$f":"'K20 - time schedule'!HR50","v":0},{"$f":"'K20 - time schedule'!HS50","v":0},{"$f":"'K20 - time schedule'!HT50","v":0},{"$f":"'K20 - time schedule'!HU50","v":0},{"$f":"'K20 - time schedule'!HV50","v":0},{"$f":"'K20 - time schedule'!HW50","v":0},{"$f":"'K20 - time schedule'!HX50","v":0},{"$f":"'K20 - time schedule'!HY50","v":0},{"$f":"'K20 - time schedule'!HZ50","v":0},{"$f":"'K20 - time schedule'!IA50","v":0},{"$f":"'K20 - time schedule'!IB50","v":0},{"$f":"'K20 - time schedule'!IC50","v":0},{"$f":"'K20 - time schedule'!ID50","v":0},{"$f":"'K20 - time schedule'!IE50","v":0},{"$f":"'K20 - time schedule'!IF50","v":0},{"$f":"'K20 - time schedule'!IG50","v":0},{"$f":"'K20 - time schedule'!IH50","v":0},{"$f":"'K20 - time schedule'!II50","v":0},{"$f":"'K20 - time schedule'!IJ50","v":0},{"$f":"'K20 - time schedule'!IK50","v":0},{"$f":"'K20 - time schedule'!IL50","v":0},{"$f":"'K20 - time schedule'!IM50","v":0},{"$f":"'K20 - time schedule'!IN50","v":0},{"$f":"'K20 - time schedule'!IO50","v":0},{"$f":"'K20 - time schedule'!IP50","v":0},{"$f":"'K20 - time schedule'!IQ50","v":0},{"$f":"'K20 - time schedule'!IR50","v":0},{"$f":"'K20 - time schedule'!IS50","v":0},{"$f":"'K20 - time schedule'!IT50","v":0},{"$f":"'K20 - time schedule'!IU50","v":0},{"$f":"'K20 - time schedule'!IV50","v":0},{"$f":"'K20 - time schedule'!IW50","v":0},{"$f":"'K20 - time schedule'!IX50","v":0},{"$f":"'K20 - time schedule'!IY50","v":0},{"$f":"'K20 - time schedule'!IZ50","v":0},{"$f":"'K20 - time schedule'!JA50","v":0},{"$f":"'K20 - time schedule'!JB50","v":0},{"$f":"'K20 - time schedule'!JC50","v":0},{"$f":"'K20 - time schedule'!JD50","v":0},{"$f":"'K20 - time schedule'!JE50","v":0},{"$f":"'K20 - time schedule'!JF50","v":0},{"$f":"'K20 - time schedule'!JG50","v":0},{"$f":"'K20 - time schedule'!JH50","v":0},{"$f":"'K20 - time schedule'!JI50","v":0},{"$f":"'K20 - time schedule'!JJ50","v":0},{"$f":"'K20 - time schedule'!JK50","v":0},{"$f":"'K20 - time schedule'!JL50","v":0},{"$f":"'K20 - time schedule'!JM50","v":0},{"$f":"'K20 - time schedule'!JN50","v":0},{"$f":"'K20 - time schedule'!JO50","v":0},{"$f":"'K20 - time schedule'!JP50","v":0},{"$f":"'K20 - time schedule'!JQ50","v":0},{"$f":"'K20 - time schedule'!JR50","v":0},{"$f":"'K20 - time schedule'!JS50","v":0},{"$f":"'K20 - time schedule'!JT50","v":0},{"$f":"'K20 - time schedule'!JU50","v":0},{"$f":"'K20 - time schedule'!JV50","v":0},{"$f":"'K20 - time schedule'!JW50","v":0},{"$f":"'K20 - time schedule'!JX50","v":0},{"$f":"'K20 - time schedule'!JY50","v":0},{"$f":"'K20 - time schedule'!JZ50","v":0},{"$f":"'K20 - time schedule'!KA50","v":0},{"$f":"'K20 - time schedule'!KB50","v":0},{"$f":"'K20 - time schedule'!KC50","v":0},{"$f":"'K20 - time schedule'!KD50","v":0},{"$f":"'K20 - time schedule'!KE50","v":0},{"$f":"'K20 - time schedule'!KF50","v":0},{"$f":"'K20 - time schedule'!KG50","v":0},{"$f":"'K20 - time schedule'!KH50","v":0},{"$f":"'K20 - time schedule'!KI50","v":0},{"$f":"'K20 - time schedule'!KJ50","v":0},{"$f":"'K20 - time schedule'!KK50","v":0},{"$f":"'K20 - time schedule'!KL50","v":0},{"$f":"'K20 - time schedule'!KM50","v":0},{"$f":"'K20 - time schedule'!KN50","v":0},{"$f":"'K20 - time schedule'!KO50","v":0},{"$f":"'K20 - time schedule'!KP50","v":0},{"$f":"'K20 - time schedule'!KQ50","v":0},{"$f":"'K20 - time schedule'!KR50","v":0},{"$f":"'K20 - time schedule'!KS50","v":0},{"$f":"'K20 - time schedule'!KT50","v":0}]
["Boiler room K80 - construction structures","K80","EUR",{"$f":"'K80 - time schedule'!G43","v":0},{"$f":"'K80 - time schedule'!H43","v":0},{"$f":"'K80 - time schedule'!I43","v":0},{"$f":"'K80 - time schedule'!J43","v":0},{"$f":"'K80 - time schedule'!K43","v":0},{"$f":"'K80 - time schedule'!L43","v":0},{"$f":"'K80 - time schedule'!M43","v":0},{"$f":"'K80 - time schedule'!N43","v":0},{"$f":"'K80 - time schedule'!O43","v":0},{"$f":"'K80 - time schedule'!P43","v":0},{"$f":"'K80 - time schedule'!Q43","v":0},{"$f":"'K80 - time schedule'!R43","v":0},{"$f":"'K80 - time schedule'!S43","v":0},{"$f":"'K80 - time schedule'!T43","v":0},{"$f":"'K80 - time schedule'!U43","v":0},{"$f":"'K80 - time schedule'!V43","v":0},{"$f":"'K80 - time schedule'!W43","v":0},{"$f":"'K80 - time schedule'!X43","v":0},{"$f":"'K80 - time schedule'!Y43","v":0},{"$f":"'K80 - time schedule'!Z43","v":0},{"$f":"'K80 - time schedule'!AA43","v":0},{"$f":"'K80 - time schedule'!AB43","v":0},{"$f":"'K80 - time schedule'!AC43","v":0},{"$f":"'K80 - time schedule'!AD43","v":0},{"$f":"'K80 - time schedule'!AE43","v":0},{"$f":"'K80 - time schedule'!AF43","v":0},{"$f":"'K80 - time schedule'!AG43","v":0},{"$f":"'K80 - time schedule'!AH43","v":0},{"$f":"'K80 - time schedule'!AI43","v":0},{"$f":"'K80 - time schedule'!AJ43","v":0},{"$f":"'K80 - time schedule'!AK43","v":0},{"$f":"'K80 - time schedule'!AL43","v":0},{"$f":"'K80 - time schedule'!AM43","v":0},{"$f":"'K80 - time schedule'!AN43","v":0},{"$f":"'K80 - time schedule'!AO43","v":0},{"$f":"'K80 - time schedule'!AP43","v":0},{"$f":"'K80 - time schedule'!AQ43","v":0},{"$f":"'K80 - time schedule'!AR43","v":0},{"$f":"'K80 - time schedule'!AS43","v":0},{"$f":"'K80 - time schedule'!AT43","v":0},{"$f":"'K80 - time schedule'!AU43","v":0},{"$f":"'K80 - time schedule'!AV43","v":0},{"$f":"'K80 - time schedule'!AW43","v":0},{"$f":"'K80 - time schedule'!AX43","v":0},{"$f":"'K80 - time schedule'!AY43","v":0},{"$f":"'K80 - time schedule'!AZ43","v":0},{"$f":"'K80 - time schedule'!BA43","v":0},{"$f":"'K80 - time schedule'!BB43","v":0},{"$f":"'K80 - time schedule'!BC43","v":0},{"$f":"'K80 - time schedule'!BD43","v":0},{"$f":"'K80 - time schedule'!BE43","v":0},{"$f":"'K80 - time schedule'!BF43","v":0},{"$f":"'K80 - time schedule'!BG43","v":0},{"$f":"'K80 - time schedule'!BH43","v":0},{"$f":"'K80 - time schedule'!BI43","v":0},{"$f":"'K80 - time schedule'!BJ43","v":0},{"$f":"'K80 - time schedule'!BK43","v":0},{"$f":"'K80 - time schedule'!BL43","v":0},{"$f":"'K80 - time schedule'!BM43","v":0},{"$f":"'K80 - time schedule'!BN43","v":0},{"$f":"'K80 - time schedule'!BO43","v":0},{"$f":"'K80 - time schedule'!BP43","v":0},{"$f":"'K80 - time schedule'!BQ43","v":0},{"$f":"'K80 - time schedule'!BR43","v":0},{"$f":"'K80 - time schedule'!BS43","v":0},{"$f":"'K80 - time schedule'!BT43","v":0},{"$f":"'K80 - time schedule'!BU43","v":0},{"$f":"'K80 - time schedule'!BV43","v":0},{"$f":"'K80 - time schedule'!BW43","v":0},{"$f":"'K80 - time schedule'!BX43","v":0},{"$f":"'K80 - time schedule'!BY43","v":0},{"$f":"'K80 - time schedule'!BZ43","v":0},{"$f":"'K80 - time schedule'!CA43","v":0},{"$f":"'K80 - time schedule'!CB43","v":0},{"$f":"'K80 - time schedule'!CC43","v":0},{"$f":"'K80 - time schedule'!CD43","v":0},{"$f":"'K80 - time schedule'!CE43","v":0},{"$f":"'K80 - time schedule'!CF43","v":0},{"$f":"'K80 - time schedule'!CG43","v":0},{"$f":"'K80 - time schedule'!CH43","v":0},{"$f":"'K80 - time schedule'!CI43","v":0},{"$f":"'K80 - time schedule'!CJ43","v":0},{"$f":"'K80 - time schedule'!CK43","v":0},{"$f":"'K80 - time schedule'!CL43","v":0},{"$f":"'K80 - time schedule'!CM43","v":0},{"$f":"'K80 - time schedule'!CN43","v":0},{"$f":"'K80 - time schedule'!CO43","v":0},{"$f":"'K80 - time schedule'!CP43","v":0},{"$f":"'K80 - time schedule'!CQ43","v":0},{"$f":"'K80 - time schedule'!CR43","v":0},{"$f":"'K80 - time schedule'!CS43","v":0},{"$f":"'K80 - time schedule'!CT43","v":0},{"$f":"'K80 - time schedule'!CU43","v":0},{"$f":"'K80 - time schedule'!CV43","v":0},{"$f":"'K80 - time schedule'!CW43","v":0},{"$f":"'K80 - time schedule'!CX43","v":0},{"$f":"'K80 - time schedule'!CY43","v":0},{"$f":"'K80 - time schedule'!CZ43","v":0},{"$f":"'K80 - time schedule'!DA43","v":0},{"$f":"'K80 - time schedule'!DB43","v":0},{"$f":"'K80 - time schedule'!DC43","v":0},{"$f":"'K80 - time schedule'!DD43","v":0},{"$f":"'K80 - time schedule'!DE43","v":0},{"$f":"'K80 - time schedule'!DF43","v":0},{"$f":"'K80 - time schedule'!DG43","v":0},{"$f":"'K80 - time schedule'!DH43","v":0},{"$f":"'K80 - time schedule'!DI43","v":0},{"$f":"'K80 - time schedule'!DJ43","v":0},{"$f":"'K80 - time schedule'!DK43","v":0},{"$f":"'K80 - time schedule'!DL43","v":0},{"$f":"'K80 - time schedule'!DM43","v":0},{"$f":"'K80 - time schedule'!DN43","v":0},{"$f":"'K80 - time schedule'!DO43","v":0},{"$f":"'K80 - time schedule'!DP43","v":0},{"$f":"'K80 - time schedule'!DQ43","v":0},{"$f":"'K80 - time schedule'!DR43","v":0},{"$f":"'K80 - time schedule'!DS43","v":0},{"$f":"'K80 - time schedule'!DT43","v":0},{"$f":"'K80 - time schedule'!DU43","v":0},{"$f":"'K80 - time schedule'!DV43","v":0},{"$f":"'K80 - time schedule'!DW43","v":0},{"$f":"'K80 - time schedule'!DX43","v":0},{"$f":"'K80 - time schedule'!DY43","v":0},{"$f":"'K80 - time schedule'!DZ43","v":0},{"$f":"'K80 - time schedule'!EA43","v":0},{"$f":"'K80 - time schedule'!EB43","v":0},{"$f":"'K80 - time schedule'!EC43","v":0},{"$f":"'K80 - time schedule'!ED43","v":0},{"$f":"'K80 - time schedule'!EE43","v":0},{"$f":"'K80 - time schedule'!EF43","v":0},{"$f":"'K80 - time schedule'!EG43","v":0},{"$f":"'K80 - time schedule'!EH43","v":0},{"$f":"'K80 - time schedule'!EI43","v":0},{"$f":"'K80 - time schedule'!EJ43","v":0},{"$f":"'K80 - time schedule'!EK43","v":0},{"$f":"'K80 - time schedule'!EL43","v":0},{"$f":"'K80 - time schedule'!EM43","v":0},{"$f":"'K80 - time schedule'!EN43","v":0},{"$f":"'K80 - time schedule'!EO43","v":0},{"$f":"'K80 - time schedule'!EP43","v":0},{"$f":"'K80 - time schedule'!EQ43","v":0},{"$f":"'K80 - time schedule'!ER43","v":0},{"$f":"'K80 - time schedule'!ES43","v":0},{"$f":"'K80 - time schedule'!ET43","v":0},{"$f":"'K80 - time schedule'!EU43","v":0},{"$f":"'K80 - time schedule'!EV43","v":0},{"$f":"'K80 - time schedule'!EW43","v":0},{"$f":"'K80 - time schedule'!EX43","v":0},{"$f":"'K80 - time schedule'!EY43","v":0},{"$f":"'K80 - time schedule'!EZ43","v":0},{"$f":"'K80 - time schedule'!FA43","v":0},{"$f":"'K80 - time schedule'!FB43","v":0},{"$f":"'K80 - time schedule'!FC43","v":0},{"$f":"'K80 - time schedule'!FD43","v":0},{"$f":"'K80 - time schedule'!FE43","v":0},{"$f":"'K80 - time schedule'!FF43","v":0},{"$f":"'K80 - time schedule'!FG43","v":0},{"$f":"'K80 - time schedule'!FH43","v":0},{"$f":"'K80 - time schedule'!FI43","v":0},{"$f":"'K80 - time schedule'!FJ43","v":0},{"$f":"'K80 - time schedule'!FK43","v":0},{"$f":"'K80 - time schedule'!FL43","v":0},{"$f":"'K80 - time schedule'!FM43","v":0},{"$f":"'K80 - time schedule'!FN43","v":0},{"$f":"'K80 - time schedule'!FO43","v":0},{"$f":"'K80 - time schedule'!FP43","v":0},{"$f":"'K80 - time schedule'!FQ43","v":0},{"$f":"'K80 - time schedule'!FR43","v":0},{"$f":"'K80 - time schedule'!FS43","v":0},{"$f":"'K80 - time schedule'!FT43","v":0},{"$f":"'K80 - time schedule'!FU43","v":0},{"$f":"'K80 - time schedule'!FV43","v":0},{"$f":"'K80 - time schedule'!FW43","v":0},{"$f":"'K80 - time schedule'!FX43","v":0},{"$f":"'K80 - time schedule'!FY43","v":0},{"$f":"'K80 - time schedule'!FZ43","v":0},{"$f":"'K80 - time schedule'!GA43","v":0},{"$f":"'K80 - time schedule'!GB43","v":0},{"$f":"'K80 - time schedule'!GC43","v":0},{"$f":"'K80 - time schedule'!GD43","v":0},{"$f":"'K80 - time schedule'!GE43","v":0},{"$f":"'K80 - time schedule'!GF43","v":0},{"$f":"'K20 - time schedule'!GG51","v":0},{"$f":"'K20 - time schedule'!GH51","v":0},{"$f":"'K20 - time schedule'!GI51","v":0},{"$f":"'K20 - time schedule'!GJ51","v":0},{"$f":"'K20 - time schedule'!GK51","v":0},{"$f":"'K20 - time schedule'!GL51","v":0},{"$f":"'K20 - time schedule'!GM51","v":0},{"$f":"'K20 - time schedule'!GN51","v":0},{"$f":"'K20 - time schedule'!GO51","v":0},{"$f":"'K20 - time schedule'!GP51","v":0},{"$f":"'K20 - time schedule'!GQ51","v":0},{"$f":"'K20 - time schedule'!GR51","v":0},{"$f":"'K20 - time schedule'!GS51","v":0},{"$f":"'K20 - time schedule'!GT51","v":0},{"$f":"'K20 - time schedule'!GU51","v":0},{"$f":"'K20 - time schedule'!GV51","v":0},{"$f":"'K20 - time schedule'!GW51","v":0},{"$f":"'K20 - time schedule'!GX51","v":0},{"$f":"'K20 - time schedule'!GY51","v":0},{"$f":"'K20 - time schedule'!GZ51","v":0},{"$f":"'K20 - time schedule'!HA51","v":0},{"$f":"'K20 - time schedule'!HB51","v":0},{"$f":"'K20 - time schedule'!HC51","v":0},{"$f":"'K20 - time schedule'!HD51","v":0},{"$f":"'K20 - time schedule'!HE51","v":0},{"$f":"'K20 - time schedule'!HF51","v":0},{"$f":"'K20 - time schedule'!HG51","v":0},{"$f":"'K20 - time schedule'!HH51","v":0},{"$f":"'K20 - time schedule'!HI51","v":0},{"$f":"'K20 - time schedule'!HJ51","v":0},{"$f":"'K20 - time schedule'!HK51","v":0},{"$f":"'K20 - time schedule'!HL51","v":0},{"$f":"'K20 - time schedule'!HM51","v":0},{"$f":"'K20 - time schedule'!HN51","v":0},{"$f":"'K20 - time schedule'!HO51","v":0},{"$f":"'K20 - time schedule'!HP51","v":0},{"$f":"'K20 - time schedule'!HQ51","v":0},{"$f":"'K20 - time schedule'!HR51","v":0},{"$f":"'K20 - time schedule'!HS51","v":0},{"$f":"'K20 - time schedule'!HT51","v":0},{"$f":"'K20 - time schedule'!HU51","v":0},{"$f":"'K20 - time schedule'!HV51","v":0},{"$f":"'K20 - time schedule'!HW51","v":0},{"$f":"'K20 - time schedule'!HX51","v":0},{"$f":"'K20 - time schedule'!HY51","v":0},{"$f":"'K20 - time schedule'!HZ51","v":0},{"$f":"'K20 - time schedule'!IA51","v":0},{"$f":"'K20 - time schedule'!IB51","v":0},{"$f":"'K20 - time schedule'!IC51","v":0},{"$f":"'K20 - time schedule'!ID51","v":0},{"$f":"'K20 - time schedule'!IE51","v":0},{"$f":"'K20 - time schedule'!IF51","v":0},{"$f":"'K20 - time schedule'!IG51","v":0},{"$f":"'K20 - time schedule'!IH51","v":0},{"$f":"'K20 - time schedule'!II51","v":0},{"$f":"'K20 - time schedule'!IJ51","v":0},{"$f":"'K20 - time schedule'!IK51","v":0},{"$f":"'K20 - time schedule'!IL51","v":0},{"$f":"'K20 - time schedule'!IM51","v":0},{"$f":"'K20 - time schedule'!IN51","v":0},{"$f":"'K20 - time schedule'!IO51","v":0},{"$f":"'K20 - time schedule'!IP51","v":0},{"$f":"'K20 - time schedule'!IQ51","v":0},{"$f":"'K20 - time schedule'!IR51","v":0},{"$f":"'K20 - time schedule'!IS51","v":0},{"$f":"'K20 - time schedule'!IT51","v":0},{"$f":"'K20 - time schedule'!IU51","v":0},{"$f":"'K20 - time schedule'!IV51","v":0},{"$f":"'K20 - time schedule'!IW51","v":0},{"$f":"'K20 - time schedule'!IX51","v":0},{"$f":"'K20 - time schedule'!IY51","v":0},{"$f":"'K20 - time schedule'!IZ51","v":0},{"$f":"'K20 - time schedule'!JA51","v":0},{"$f":"'K20 - time schedule'!JB51","v":0},{"$f":"'K20 - time schedule'!JC51","v":0},{"$f":"'K20 - time schedule'!JD51","v":0},{"$f":"'K20 - time schedule'!JE51","v":0},{"$f":"'K20 - time schedule'!JF51","v":0},{"$f":"'K20 - time schedule'!JG51","v":0},{"$f":"'K20 - time schedule'!JH51","v":0},{"$f":"'K20 - time schedule'!JI51","v":0},{"$f":"'K20 - time schedule'!JJ51","v":0},{"$f":"'K20 - time schedule'!JK51","v":0},{"$f":"'K20 - time schedule'!JL51","v":0},{"$f":"'K20 - time schedule'!JM51","v":0},{"$f":"'K20 - time schedule'!JN51","v":0},{"$f":"'K20 - time schedule'!JO51","v":0},{"$f":"'K20 - time schedule'!JP51","v":0},{"$f":"'K20 - time schedule'!JQ51","v":0},{"$f":"'K20 - time schedule'!JR51","v":0},{"$f":"'K20 - time schedule'!JS51","v":0},{"$f":"'K20 - time schedule'!JT51","v":0},{"$f":"'K20 - time schedule'!JU51","v":0},{"$f":"'K20 - time schedule'!JV51","v":0},{"$f":"'K20 - time schedule'!JW51","v":0},{"$f":"'K20 - time schedule'!JX51","v":0},{"$f":"'K20 - time schedule'!JY51","v":0},{"$f":"'K20 - time schedule'!JZ51","v":0},{"$f":"'K20 - time schedule'!KA51","v":0},{"$f":"'K20 - time schedule'!KB51","v":0},{"$f":"'K20 - time schedule'!KC51","v":0},{"$f":"'K20 - time schedule'!KD51","v":0},{"$f":"'K20 - time schedule'!KE51","v":0},{"$f":"'K20 - time schedule'!KF51","v":0},{"$f":"'K20 - time schedule'!KG51","v":0},{"$f":"'K20 - time schedule'!KH51","v":0},{"$f":"'K20 - time schedule'!KI51","v":0},{"$f":"'K20 - time schedule'!KJ51","v":0},{"$f":"'K20 - time schedule'!KK51","v":0},{"$f":"'K20 - time schedule'!KL51","v":0},{"$f":"'K20 - time schedule'!KM51","v":0},{"$f":"'K20 - time schedule'!KN51","v":0},{"$f":"'K20 - time schedule'!KO51","v":0},{"$f":"'K20 - time schedule'!KP51","v":0},{"$f":"'K20 - time schedule'!KQ51","v":0},{"$f":"'K20 - time schedule'!KR51","v":0},{"$f":"'K20 - time schedule'!KS51","v":0},{"$f":"'K20 - time schedule'!KT51","v":0}]
["Boiler room K80 - ash management (transport piping, silos)","K80","EUR",{"$f":"'K80 - time schedule'!G45","v":0},{"$f":"'K80 - time schedule'!H45","v":0},{"$f":"'K80 - time schedule'!I45","v":0},{"$f":"'K80 - time schedule'!J45","v":0},{"$f":"'K80 - time schedule'!K45","v":0},{"$f":"'K80 - time schedule'!L45","v":0},{"$f":"'K80 - time schedule'!M45","v":0},{"$f":"'K80 - time schedule'!N45","v":0},{"$f":"'K80 - time schedule'!O45","v":0},{"$f":"'K80 - time schedule'!P45","v":0},{"$f":"'K80 - time schedule'!Q45","v":0},{"$f":"'K80 - time schedule'!R45","v":0},{"$f":"'K80 - time schedule'!S45","v":0},{"$f":"'K80 - time schedule'!T45","v":0},{"$f":"'K80 - time schedule'!U45","v":0},{"$f":"'K80 - time schedule'!V45","v":0},{"$f":"'K80 - time schedule'!W45","v":0},{"$f":"'K80 - time schedule'!X45","v":0},{"$f":"'K80 - time schedule'!Y45","v":0},{"$f":"'K80 - time schedule'!Z45","v":0},{"$f":"'K80 - time schedule'!AA45","v":0},{"$f":"'K80 - time schedule'!AB45","v":0},{"$f":"'K80 - time schedule'!AC45","v":0},{"$f":"'K80 - time schedule'!AD45","v":0},{"$f":"'K80 - time schedule'!AE45","v":0},{"$f":"'K80 - time schedule'!AF45","v":0},{"$f":"'K80 - time schedule'!AG45","v":0},{"$f":"'K80 - time schedule'!AH45","v":0},{"$f":"'K80 - time schedule'!AI45","v":0},{"$f":"'K80 - time schedule'!AJ45","v":0},{"$f":"'K80 - time schedule'!AK45","v":0},{"$f":"'K80 - time schedule'!AL45","v":0},{"$f":"'K80 - time schedule'!AM45","v":0},{"$f":"'K80 - time schedule'!AN45","v":0},{"$f":"'K80 - time schedule'!AO45","v":0},{"$f":"'K80 - time schedule'!AP45","v":0},{"$f":"'K80 - time schedule'!AQ45","v":0},{"$f":"'K80 - time schedule'!AR45","v":0},{"$f":"'K80 - time schedule'!AS45","v":0},{"$f":"'K80 - time schedule'!AT45","v":0},{"$f":"'K80 - time schedule'!AU45","v":0},{"$f":"'K80 - time schedule'!AV45","v":0},{"$f":"'K80 - time schedule'!AW45","v":0},{"$f":"'K80 - time schedule'!AX45","v":0},{"$f":"'K80 - time schedule'!AY45","v":0},{"$f":"'K80 - time schedule'!AZ45","v":0},{"$f":"'K80 - time schedule'!BA45","v":0},{"$f":"'K80 - time schedule'!BB45","v":0},{"$f":"'K80 - time schedule'!BC45","v":0},{"$f":"'K80 - time schedule'!BD45","v":0},{"$f":"'K80 - time schedule'!BE45","v":0},{"$f":"'K80 - time schedule'!BF45","v":0},{"$f":"'K80 - time schedule'!BG45","v":0},{"$f":"'K80 - time schedule'!BH45","v":0},{"$f":"'K80 - time schedule'!BI45","v":0},{"$f":"'K80 - time schedule'!BJ45","v":0},{"$f":"'K80 - time schedule'!BK45","v":0},{"$f":"'K80 - time schedule'!BL45","v":0},{"$f":"'K80 - time schedule'!BM45","v":0},{"$f":"'K80 - time schedule'!BN45","v":0},{"$f":"'K80 - time schedule'!BO45","v":0},{"$f":"'K80 - time schedule'!BP45","v":0},{"$f":"'K80 - time schedule'!BQ45","v":0},{"$f":"'K80 - time schedule'!BR45","v":0},{"$f":"'K80 - time schedule'!BS45","v":0},{"$f":"'K80 - time schedule'!BT45","v":0},{"$f":"'K80 - time schedule'!BU45","v":0},{"$f":"'K80 - time schedule'!BV45","v":0},{"$f":"'K80 - time schedule'!BW45","v":0},{"$f":"'K80 - time schedule'!BX45","v":0},{"$f":"'K80 - time schedule'!BY45","v":0},{"$f":"'K80 - time schedule'!BZ45","v":0},{"$f":"'K80 - time schedule'!CA45","v":0},{"$f":"'K80 - time schedule'!CB45","v":0},{"$f":"'K80 - time schedule'!CC45","v":0},{"$f":"'K80 - time schedule'!CD45","v":0},{"$f":"'K80 - time schedule'!CE45","v":0},{"$f":"'K80 - time schedule'!CF45","v":0},{"$f":"'K80 - time schedule'!CG45","v":0},{"$f":"'K80 - time schedule'!CH45","v":0},{"$f":"'K80 - time schedule'!CI45","v":0},{"$f":"'K80 - time schedule'!CJ45","v":0},{"$f":"'K80 - time schedule'!CK45","v":0},{"$f":"'K80 - time schedule'!CL45","v":0},{"$f":"'K80 - time schedule'!CM45","v":0},{"$f":"'K80 - time schedule'!CN45","v":0},{"$f":"'K80 - time schedule'!CO45","v":0},{"$f":"'K80 - time schedule'!CP45","v":0},{"$f":"'K80 - time schedule'!CQ45","v":0},{"$f":"'K80 - time schedule'!CR45","v":0},{"$f":"'K80 - time schedule'!CS45","v":0},{"$f":"'K80 - time schedule'!CT45","v":0},{"$f":"'K80 - time schedule'!CU45","v":0},{"$f":"'K80 - time schedule'!CV45","v":0},{"$f":"'K80 - time schedule'!CW45","v":0},{"$f":"'K80 - time schedule'!CX45","v":0},{"$f":"'K80 - time schedule'!CY45","v":0},{"$f":"'K80 - time schedule'!CZ45","v":0},{"$f":"'K80 - time schedule'!DA45","v":0},{"$f":"'K80 - time schedule'!DB45","v":0},{"$f":"'K80 - time schedule'!DC45","v":0},{"$f":"'K80 - time schedule'!DD45","v":0},{"$f":"'K80 - time schedule'!DE45","v":0},{"$f":"'K80 - time schedule'!DF45","v":0},{"$f":"'K80 - time schedule'!DG45","v":0},{"$f":"'K80 - time schedule'!DH45","v":0},{"$f":"'K80 - time schedule'!DI45","v":0},{"$f":"'K80 - time schedule'!DJ45","v":0},{"$f":"'K80 - time schedule'!DK45","v":0},{"$f":"'K80 - time schedule'!DL45","v":0},{"$f":"'K80 - time schedule'!DM45","v":0},{"$f":"'K80 - time schedule'!DN45","v":0},{"$f":"'K80 - time schedule'!DO45","v":0},{"$f":"'K80 - time schedule'!DP45","v":0},{"$f":"'K80 - time schedule'!DQ45","v":0},{"$f":"'K80 - time schedule'!DR45","v":0},{"$f":"'K80 - time schedule'!DS45","v":0},{"$f":"'K80 - time schedule'!DT45","v":0},{"$f":"'K80 - time schedule'!DU45","v":0},{"$f":"'K80 - time schedule'!DV45","v":0},{"$f":"'K80 - time schedule'!DW45","v":0},{"$f":"'K80 - time schedule'!DX45","v":0},{"$f":"'K80 - time schedule'!DY45","v":0},{"$f":"'K80 - time schedule'!DZ45","v":0},{"$f":"'K80 - time schedule'!EA45","v":0},{"$f":"'K80 - time schedule'!EB45","v":0},{"$f":"'K80 - time schedule'!EC45","v":0},{"$f":"'K80 - time schedule'!ED45","v":0},{"$f":"'K80 - time schedule'!EE45","v":0},{"$f":"'K80 - time schedule'!EF45","v":0},{"$f":"'K80 - time schedule'!EG45","v":0},{"$f":"'K80 - time schedule'!EH45","v":0},{"$f":"'K80 - time schedule'!EI45","v":0},{"$f":"'K80 - time schedule'!EJ45","v":0},{"$f":"'K80 - time schedule'!EK45","v":0},{"$f":"'K80 - time schedule'!EL45","v":0},{"$f":"'K80 - time schedule'!EM45","v":0},{"$f":"'K80 - time schedule'!EN45","v":0},{"$f":"'K80 - time schedule'!EO45","v":0},{"$f":"'K80 - time schedule'!EP45","v":0},{"$f":"'K80 - time schedule'!EQ45","v":0},{"$f":"'K80 - time schedule'!ER45","v":0},{"$f":"'K80 - time schedule'!ES45","v":0},{"$f":"'K80 - time schedule'!ET45","v":0},{"$f":"'K80 - time schedule'!EU45","v":0},{"$f":"'K80 - time schedule'!EV45","v":0},{"$f":"'K80 - time schedule'!EW45","v":0},{"$f":"'K80 - time schedule'!EX45","v":0},{"$f":"'K80 - time schedule'!EY45","v":0},{"$f":"'K80 - time schedule'!EZ45","v":0},{"$f":"'K80 - time schedule'!FA45","v":0},{"$f":"'K80 - time schedule'!FB45","v":0},{"$f":"'K80 - time schedule'!FC45","v":0},{"$f":"'K80 - time schedule'!FD45","v":0},{"$f":"'K80 - time schedule'!FE45","v":0},{"$f":"'K80 - time schedule'!FF45","v":0},{"$f":"'K80 - time schedule'!FG45","v":0},{"$f":"'K80 - time schedule'!FH45","v":0},{"$f":"'K80 - time schedule'!FI45","v":0},{"$f":"'K80 - time schedule'!FJ45","v":0},{"$f":"'K80 - time schedule'!FK45","v":0},{"$f":"'K80 - time schedule'!FL45","v":0},{"$f":"'K80 - time schedule'!FM45","v":0},{"$f":"'K80 - time schedule'!FN45","v":0},{"$f":"'K80 - time schedule'!FO45","v":0},{"$f":"'K80 - time schedule'!FP45","v":0},{"$f":"'K80 - time schedule'!FQ45","v":0},{"$f":"'K80 - time schedule'!FR45","v":0},{"$f":"'K80 - time schedule'!FS45","v":0},{"$f":"'K80 - time schedule'!FT45","v":0},{"$f":"'K80 - time schedule'!FU45","v":0},{"$f":"'K80 - time schedule'!FV45","v":0},{"$f":"'K80 - time schedule'!FW45","v":0},{"$f":"'K80 - time schedule'!FX45","v":0},{"$f":"'K80 - time schedule'!FY45","v":0},{"$f":"'K80 - time schedule'!FZ45","v":0},{"$f":"'K80 - time schedule'!GA45","v":0},{"$f":"'K80 - time schedule'!GB45","v":0},{"$f":"'K80 - time schedule'!GC45","v":0},{"$f":"'K80 - time schedule'!GD45","v":0},{"$f":"'K80 - time schedule'!GE45","v":0},{"$f":"'K80 - time schedule'!GF45","v":0},{"$f":"'K20 - time schedule'!GG52","v":0},{"$f":"'K20 - time schedule'!GH52","v":0},{"$f":"'K20 - time schedule'!GI52","v":0},{"$f":"'K20 - time schedule'!GJ52","v":0},{"$f":"'K20 - time schedule'!GK52","v":0},{"$f":"'K20 - time schedule'!GL52","v":0},{"$f":"'K20 - time schedule'!GM52","v":0},{"$f":"'K20 - time schedule'!GN52","v":0},{"$f":"'K20 - time schedule'!GO52","v":0},{"$f":"'K20 - time schedule'!GP52","v":0},{"$f":"'K20 - time schedule'!GQ52","v":0},{"$f":"'K20 - time schedule'!GR52","v":0},{"$f":"'K20 - time schedule'!GS52","v":0},{"$f":"'K20 - time schedule'!GT52","v":0},{"$f":"'K20 - time schedule'!GU52","v":0},{"$f":"'K20 - time schedule'!GV52","v":0},{"$f":"'K20 - time schedule'!GW52","v":0},{"$f":"'K20 - time schedule'!GX52","v":0},{"$f":"'K20 - time schedule'!GY52","v":0},{"$f":"'K20 - time schedule'!GZ52","v":0},{"$f":"'K20 - time schedule'!HA52","v":0},{"$f":"'K20 - time schedule'!HB52","v":0},{"$f":"'K20 - time schedule'!HC52","v":0},{"$f":"'K20 - time schedule'!HD52","v":0},{"$f":"'K20 - time schedule'!HE52","v":0},{"$f":"'K20 - time schedule'!HF52","v":0},{"$f":"'K20 - time schedule'!HG52","v":0},{"$f":"'K20 - time schedule'!HH52","v":0},{"$f":"'K20 - time schedule'!HI52","v":0},{"$f":"'K20 - time schedule'!HJ52","v":0},{"$f":"'K20 - time schedule'!HK52","v":0},{"$f":"'K20 - time schedule'!HL52","v":0},{"$f":"'K20 - time schedule'!HM52","v":0},{"$f":"'K20 - time schedule'!HN52","v":0},{"$f":"'K20 - time schedule'!HO52","v":0},{"$f":"'K20 - time schedule'!HP52","v":0},{"$f":"'K20 - time schedule'!HQ52","v":0},{"$f":"'K20 - time schedule'!HR52","v":0},{"$f":"'K20 - time schedule'!HS52","v":0},{"$f":"'K20 - time schedule'!HT52","v":0},{"$f":"'K20 - time schedule'!HU52","v":0},{"$f":"'K20 - time schedule'!HV52","v":0},{"$f":"'K20 - time schedule'!HW52","v":0},{"$f":"'K20 - time schedule'!HX52","v":0},{"$f":"'K20 - time schedule'!HY52","v":0},{"$f":"'K20 - time schedule'!HZ52","v":0},{"$f":"'K20 - time schedule'!IA52","v":0},{"$f":"'K20 - time schedule'!IB52","v":0},{"$f":"'K20 - time schedule'!IC52","v":0},{"$f":"'K20 - time schedule'!ID52","v":0},{"$f":"'K20 - time schedule'!IE52","v":0},{"$f":"'K20 - time schedule'!IF52","v":0},{"$f":"'K20 - time schedule'!IG52","v":0},{"$f":"'K20 - time schedule'!IH52","v":0},{"$f":"'K20 - time schedule'!II52","v":0},{"$f":"'K20 - time schedule'!IJ52","v":0},{"$f":"'K20 - time schedule'!IK52","v":0},{"$f":"'K20 - time schedule'!IL52","v":0},{"$f":"'K20 - time schedule'!IM52","v":0},{"$f":"'K20 - time schedule'!IN52","v":0},{"$f":"'K20 - time schedule'!IO52","v":0},{"$f":"'K20 - time schedule'!IP52","v":0},{"$f":"'K20 - time schedule'!IQ52","v":0},{"$f":"'K20 - time schedule'!IR52","v":0},{"$f":"'K20 - time schedule'!IS52","v":0},{"$f":"'K20 - time schedule'!IT52","v":0},{"$f":"'K20 - time schedule'!IU52","v":0},{"$f":"'K20 - time schedule'!IV52","v":0},{"$f":"'K20 - time schedule'!IW52","v":0},{"$f":"'K20 - time schedule'!IX52","v":0},{"$f":"'K20 - time schedule'!IY52","v":0},{"$f":"'K20 - time schedule'!IZ52","v":0},{"$f":"'K20 - time schedule'!JA52","v":0},{"$f":"'K20 - time schedule'!JB52","v":0},{"$f":"'K20 - time schedule'!JC52","v":0},{"$f":"'K20 - time schedule'!JD52","v":0},{"$f":"'K20 - time schedule'!JE52","v":0},{"$f":"'K20 - time schedule'!JF52","v":0},{"$f":"'K20 - time schedule'!JG52","v":0},{"$f":"'K20 - time schedule'!JH52","v":0},{"$f":"'K20 - time schedule'!JI52","v":0},{"$f":"'K20 - time schedule'!JJ52","v":0},{"$f":"'K20 - time schedule'!JK52","v":0},{"$f":"'K20 - time schedule'!JL52","v":0},{"$f":"'K20 - time schedule'!JM52","v":0},{"$f":"'K20 - time schedule'!JN52","v":0},{"$f":"'K20 - time schedule'!JO52","v":0},{"$f":"'K20 - time schedule'!JP52","v":0},{"$f":"'K20 - time schedule'!JQ52","v":0},{"$f":"'K20 - time schedule'!JR52","v":0},{"$f":"'K20 - time schedule'!JS52","v":0},{"$f":"'K20 - time schedule'!JT52","v":0},{"$f":"'K20 - time schedule'!JU52","v":0},{"$f":"'K20 - time schedule'!JV52","v":0},{"$f":"'K20 - time schedule'!JW52","v":0},{"$f":"'K20 - time schedule'!JX52","v":0},{"$f":"'K20 - time schedule'!JY52","v":0},{"$f":"'K20 - time schedule'!JZ52","v":0},{"$f":"'K20 - time schedule'!KA52","v":0},{"$f":"'K20 - time schedule'!KB52","v":0},{"$f":"'K20 - time schedule'!KC52","v":0},{"$f":"'K20 - time schedule'!KD52","v":0},{"$f":"'K20 - time schedule'!KE52","v":0},{"$f":"'K20 - time schedule'!KF52","v":0},{"$f":"'K20 - time schedule'!KG52","v":0},{"$f":"'K20 - time schedule'!KH52","v":0},{"$f":"'K20 - time schedule'!KI52","v":0},{"$f":"'K20 - time schedule'!KJ52","v":0},{"$f":"'K20 - time schedule'!KK52","v":0},{"$f":"'K20 - time schedule'!KL52","v":0},{"$f":"'K20 - time schedule'!KM52","v":0},{"$f":"'K20 - time schedule'!KN52","v":0},{"$f":"'K20 - time schedule'!KO52","v":0},{"$f":"'K20 - time schedule'!KP52","v":0},{"$f":"'K20 - time schedule'!KQ52","v":0},{"$f":"'K20 - time schedule'!KR52","v":0},{"$f":"'K20 - time schedule'!KS52","v":0},{"$f":"'K20 - time schedule'!KT52","v":0}]
["Boiler room K80 - other above not specified items","K80","EUR",{"$f":"'K80 - time schedule'!G47","v":0},{"$f":"'K80 - time schedule'!H47","v":0},{"$f":"'K80 - time schedule'!I47","v":0},{"$f":"'K80 - time schedule'!J47","v":0},{"$f":"'K80 - time schedule'!K47","v":0},{"$f":"'K80 - time schedule'!L47","v":0},{"$f":"'K80 - time schedule'!M47","v":0},{"$f":"'K80 - time schedule'!N47","v":0},{"$f":"'K80 - time schedule'!O47","v":0},{"$f":"'K80 - time schedule'!P47","v":0},{"$f":"'K80 - time schedule'!Q47","v":0},{"$f":"'K80 - time schedule'!R47","v":0},{"$f":"'K80 - time schedule'!S47","v":0},{"$f":"'K80 - time schedule'!T47","v":0},{"$f":"'K80 - time schedule'!U47","v":0},{"$f":"'K80 - time schedule'!V47","v":0},{"$f":"'K80 - time schedule'!W47","v":0},{"$f":"'K80 - time schedule'!X47","v":0},{"$f":"'K80 - time schedule'!Y47","v":0},{"$f":"'K80 - time schedule'!Z47","v":0},{"$f":"'K80 - time schedule'!AA47","v":0},{"$f":"'K80 - time schedule'!AB47","v":0},{"$f":"'K80 - time schedule'!AC47","v":0},{"$f":"'K80 - time schedule'!AD47","v":0},{"$f":"'K80 - time schedule'!AE47","v":0},{"$f":"'K80 - time schedule'!AF47","v":0},{"$f":"'K80 - time schedule'!AG47","v":0},{"$f":"'K80 - time schedule'!AH47","v":0},{"$f":"'K80 - time schedule'!AI47","v":0},{"$f":"'K80 - time schedule'!AJ47","v":0},{"$f":"'K80 - time schedule'!AK47","v":0},{"$f":"'K80 - time schedule'!AL47","v":0},{"$f":"'K80 - time schedule'!AM47","v":0},{"$f":"'K80 - time schedule'!AN47","v":0},{"$f":"'K80 - time schedule'!AO47","v":0},{"$f":"'K80 - time schedule'!AP47","v":0},{"$f":"'K80 - time schedule'!AQ47","v":0},{"$f":"'K80 - time schedule'!AR47","v":0},{"$f":"'K80 - time schedule'!AS47","v":0},{"$f":"'K80 - time schedule'!AT47","v":0},{"$f":"'K80 - time schedule'!AU47","v":0},{"$f":"'K80 - time schedule'!AV47","v":0},{"$f":"'K80 - time schedule'!AW47","v":0},{"$f":"'K80 - time schedule'!AX47","v":0},{"$f":"'K80 - time schedule'!AY47","v":0},{"$f":"'K80 - time schedule'!AZ47","v":0},{"$f":"'K80 - time schedule'!BA47","v":0},{"$f":"'K80 - time schedule'!BB47","v":0},{"$f":"'K80 - time schedule'!BC47","v":0},{"$f":"'K80 - time schedule'!BD47","v":0},{"$f":"'K80 - time schedule'!BE47","v":0},{"$f":"'K80 - time schedule'!BF47","v":0},{"$f":"'K80 - time schedule'!BG47","v":0},{"$f":"'K80 - time schedule'!BH47","v":0},{"$f":"'K80 - time schedule'!BI47","v":0},{"$f":"'K80 - time schedule'!BJ47","v":0},{"$f":"'K80 - time schedule'!BK47","v":0},{"$f":"'K80 - time schedule'!BL47","v":0},{"$f":"'K80 - time schedule'!BM47","v":0},{"$f":"'K80 - time schedule'!BN47","v":0},{"$f":"'K80 - time schedule'!BO47","v":0},{"$f":"'K80 - time schedule'!BP47","v":0},{"$f":"'K80 - time schedule'!BQ47","v":0},{"$f":"'K80 - time schedule'!BR47","v":0},{"$f":"'K80 - time schedule'!BS47","v":0},{"$f":"'K80 - time schedule'!BT47","v":0},{"$f":"'K80 - time schedule'!BU47","v":0},{"$f":"'K80 - time schedule'!BV47","v":0},{"$f":"'K80 - time schedule'!BW47","v":0},{"$f":"'K80 - time schedule'!BX47","v":0},{"$f":"'K80 - time schedule'!BY47","v":0},{"$f":"'K80 - time schedule'!BZ47","v":0},{"$f":"'K80 - time schedule'!CA47","v":0},{"$f":"'K80 - time schedule'!CB47","v":0},{"$f":"'K80 - time schedule'!CC47","v":0},{"$f":"'K80 - time schedule'!CD47","v":0},{"$f":"'K80 - time schedule'!CE47","v":0},{"$f":"'K80 - time schedule'!CF47","v":0},{"$f":"'K80 - time schedule'!CG47","v":0},{"$f":"'K80 - time schedule'!CH47","v":0},{"$f":"'K80 - time schedule'!CI47","v":0},{"$f":"'K80 - time schedule'!CJ47","v":0},{"$f":"'K80 - time schedule'!CK47","v":0},{"$f":"'K80 - time schedule'!CL47","v":0},{"$f":"'K80 - time schedule'!CM47","v":0},{"$f":"'K80 - time schedule'!CN47","v":0},{"$f":"'K80 - time schedule'!CO47","v":0},{"$f":"'K80 - time schedule'!CP47","v":0},{"$f":"'K80 - time schedule'!CQ47","v":0},{"$f":"'K80 - time schedule'!CR47","v":0},{"$f":"'K80 - time schedule'!CS47","v":0},{"$f":"'K80 - time schedule'!CT47","v":0},{"$f":"'K80 - time schedule'!CU47","v":0},{"$f":"'K80 - time schedule'!CV47","v":0},{"$f":"'K80 - time schedule'!CW47","v":0},{"$f":"'K80 - time schedule'!CX47","v":0},{"$f":"'K80 - time schedule'!CY47","v":0},{"$f":"'K80 - time schedule'!CZ47","v":0},{"$f":"'K80 - time schedule'!DA47","v":0},{"$f":"'K80 - time schedule'!DB47","v":0},{"$f":"'K80 - time schedule'!DC47","v":0},{"$f":"'K80 - time schedule'!DD47","v":0},{"$f":"'K80 - time schedule'!DE47","v":0},{"$f":"'K80 - time schedule'!DF47","v":0},{"$f":"'K80 - time schedule'!DG47","v":0},{"$f":"'K80 - time schedule'!DH47","v":0},{"$f":"'K80 - time schedule'!DI47","v":0},{"$f":"'K80 - time schedule'!DJ47","v":0},{"$f":"'K80 - time schedule'!DK47","v":0},{"$f":"'K80 - time schedule'!DL47","v":0},{"$f":"'K80 - time schedule'!DM47","v":0},{"$f":"'K80 - time schedule'!DN47","v":0},{"$f":"'K80 - time schedule'!DO47","v":0},{"$f":"'K80 - time schedule'!DP47","v":0},{"$f":"'K80 - time schedule'!DQ47","v":0},{"$f":"'K80 - time schedule'!DR47","v":0},{"$f":"'K80 - time schedule'!DS47","v":0},{"$f":"'K80 - time schedule'!DT47","v":0},{"$f":"'K80 - time schedule'!DU47","v":0},{"$f":"'K80 - time schedule'!DV47","v":0},{"$f":"'K80 - time schedule'!DW47","v":0},{"$f":"'K80 - time schedule'!DX47","v":0},{"$f":"'K80 - time schedule'!DY47","v":0},{"$f":"'K80 - time schedule'!DZ47","v":0},{"$f":"'K80 - time schedule'!EA47","v":0},{"$f":"'K80 - time schedule'!EB47","v":0},{"$f":"'K80 - time schedule'!EC47","v":0},{"$f":"'K80 - time schedule'!ED47","v":0},{"$f":"'K80 - time schedule'!EE47","v":0},{"$f":"'K80 - time schedule'!EF47","v":0},{"$f":"'K80 - time schedule'!EG47","v":0},{"$f":"'K80 - time schedule'!EH47","v":0},{"$f":"'K80 - time schedule'!EI47","v":0},{"$f":"'K80 - time schedule'!EJ47","v":0},{"$f":"'K80 - time schedule'!EK47","v":0},{"$f":"'K80 - time schedule'!EL47","v":0},{"$f":"'K80 - time schedule'!EM47","v":0},{"$f":"'K80 - time schedule'!EN47","v":0},{"$f":"'K80 - time schedule'!EO47","v":0},{"$f":"'K80 - time schedule'!EP47","v":0},{"$f":"'K80 - time schedule'!EQ47","v":0},{"$f":"'K80 - time schedule'!ER47","v":0},{"$f":"'K80 - time schedule'!ES47","v":0},{"$f":"'K80 - time schedule'!ET47","v":0},{"$f":"'K80 - time schedule'!EU47","v":0},{"$f":"'K80 - time schedule'!EV47","v":0},{"$f":"'K80 - time schedule'!EW47","v":0},{"$f":"'K80 - time schedule'!EX47","v":0},{"$f":"'K80 - time schedule'!EY47","v":0},{"$f":"'K80 - time schedule'!EZ47","v":0},{"$f":"'K80 - time schedule'!FA47","v":0},{"$f":"'K80 - time schedule'!FB47","v":0},{"$f":"'K80 - time schedule'!FC47","v":0},{"$f":"'K80 - time schedule'!FD47","v":0},{"$f":"'K80 - time schedule'!FE47","v":0},{"$f":"'K80 - time schedule'!FF47","v":0},{"$f":"'K80 - time schedule'!FG47","v":0},{"$f":"'K80 - time schedule'!FH47","v":0},{"$f":"'K80 - time schedule'!FI47","v":0},{"$f":"'K80 - time schedule'!FJ47","v":0},{"$f":"'K80 - time schedule'!FK47","v":0},{"$f":"'K80 - time schedule'!FL47","v":0},{"$f":"'K80 - time schedule'!FM47","v":0},{"$f":"'K80 - time schedule'!FN47","v":0},{"$f":"'K80 - time schedule'!FO47","v":0},{"$f":"'K80 - time schedule'!FP47","v":0},{"$f":"'K80 - time schedule'!FQ47","v":0},{"$f":"'K80 - time schedule'!FR47","v":0},{"$f":"'K80 - time schedule'!FS47","v":0},{"$f":"'K80 - time schedule'!FT47","v":0},{"$f":"'K80 - time schedule'!FU47","v":0},{"$f":"'K80 - time schedule'!FV47","v":0},{"$f":"'K80 - time schedule'!FW47","v":0},{"$f":"'K80 - time schedule'!FX47","v":0},{"$f":"'K80 - time schedule'!FY47","v":0},{"$f":"'K80 - time schedule'!FZ47","v":0},{"$f":"'K80 - time schedule'!GA47","v":0},{"$f":"'K80 - time schedule'!GB47","v":0},{"$f":"'K80 - time schedule'!GC47","v":0},{"$f":"'K80 - time schedule'!GD47","v":0},{"$f":"'K80 - time schedule'!GE47","v":0},{"$f":"'K80 - time schedule'!GF47","v":0},{"$f":"'K20 - time schedule'!GG53","v":0},{"$f":"'K20 - time schedule'!GH53","v":0},{"$f":"'K20 - time schedule'!GI53","v":0},{"$f":"'K20 - time schedule'!GJ53","v":0},{"$f":"'K20 - time schedule'!GK53","v":0},{"$f":"'K20 - time schedule'!GL53","v":0},{"$f":"'K20 - time schedule'!GM53","v":0},{"$f":"'K20 - time schedule'!GN53","v":0},{"$f":"'K20 - time schedule'!GO53","v":0},{"$f":"'K20 - time schedule'!GP53","v":0},{"$f":"'K20 - time schedule'!GQ53","v":0},{"$f":"'K20 - time schedule'!GR53","v":0},{"$f":"'K20 - time schedule'!GS53","v":0},{"$f":"'K20 - time schedule'!GT53","v":0},{"$f":"'K20 - time schedule'!GU53","v":0},{"$f":"'K20 - time schedule'!GV53","v":0},{"$f":"'K20 - time schedule'!GW53","v":0},{"$f":"'K20 - time schedule'!GX53","v":0},{"$f":"'K20 - time schedule'!GY53","v":0},{"$f":"'K20 - time schedule'!GZ53","v":0},{"$f":"'K20 - time schedule'!HA53","v":0},{"$f":"'K20 - time schedule'!HB53","v":0},{"$f":"'K20 - time schedule'!HC53","v":0},{"$f":"'K20 - time schedule'!HD53","v":0},{"$f":"'K20 - time schedule'!HE53","v":0},{"$f":"'K20 - time schedule'!HF53","v":0},{"$f":"'K20 - time schedule'!HG53","v":0},{"$f":"'K20 - time schedule'!HH53","v":0},{"$f":"'K20 - time schedule'!HI53","v":0},{"$f":"'K20 - time schedule'!HJ53","v":0},{"$f":"'K20 - time schedule'!HK53","v":0},{"$f":"'K20 - time schedule'!HL53","v":0},{"$f":"'K20 - time schedule'!HM53","v":0},{"$f":"'K20 - time schedule'!HN53","v":0},{"$f":"'K20 - time schedule'!HO53","v":0},{"$f":"'K20 - time schedule'!HP53","v":0},{"$f":"'K20 - time schedule'!HQ53","v":0},{"$f":"'K20 - time schedule'!HR53","v":0},{"$f":"'K20 - time schedule'!HS53","v":0},{"$f":"'K20 - time schedule'!HT53","v":0},{"$f":"'K20 - time schedule'!HU53","v":0},{"$f":"'K20 - time schedule'!HV53","v":0},{"$f":"'K20 - time schedule'!HW53","v":0},{"$f":"'K20 - time schedule'!HX53","v":0},{"$f":"'K20 - time schedule'!HY53","v":0},{"$f":"'K20 - time schedule'!HZ53","v":0},{"$f":"'K20 - time schedule'!IA53","v":0},{"$f":"'K20 - time schedule'!IB53","v":0},{"$f":"'K20 - time schedule'!IC53","v":0},{"$f":"'K20 - time schedule'!ID53","v":0},{"$f":"'K20 - time schedule'!IE53","v":0},{"$f":"'K20 - time schedule'!IF53","v":0},{"$f":"'K20 - time schedule'!IG53","v":0},{"$f":"'K20 - time schedule'!IH53","v":0},{"$f":"'K20 - time schedule'!II53","v":0},{"$f":"'K20 - time schedule'!IJ53","v":0},{"$f":"'K20 - time schedule'!IK53","v":0},{"$f":"'K20 - time schedule'!IL53","v":0},{"$f":"'K20 - time schedule'!IM53","v":0},{"$f":"'K20 - time schedule'!IN53","v":0},{"$f":"'K20 - time schedule'!IO53","v":0},{"$f":"'K20 - time schedule'!IP53","v":0},{"$f":"'K20 - time schedule'!IQ53","v":0},{"$f":"'K20 - time schedule'!IR53","v":0},{"$f":"'K20 - time schedule'!IS53","v":0},{"$f":"'K20 - time schedule'!IT53","v":0},{"$f":"'K20 - time schedule'!IU53","v":0},{"$f":"'K20 - time schedule'!IV53","v":0},{"$f":"'K20 - time schedule'!IW53","v":0},{"$f":"'K20 - time schedule'!IX53","v":0},{"$f":"'K20 - time schedule'!IY53","v":0},{"$f":"'K20 - time schedule'!IZ53","v":0},{"$f":"'K20 - time schedule'!JA53","v":0},{"$f":"'K20 - time schedule'!JB53","v":0},{"$f":"'K20 - time schedule'!JC53","v":0},{"$f":"'K20 - time schedule'!JD53","v":0},{"$f":"'K20 - time schedule'!JE53","v":0},{"$f":"'K20 - time schedule'!JF53","v":0},{"$f":"'K20 - time schedule'!JG53","v":0},{"$f":"'K20 - time schedule'!JH53","v":0},{"$f":"'K20 - time schedule'!JI53","v":0},{"$f":"'K20 - time schedule'!JJ53","v":0},{"$f":"'K20 - time schedule'!JK53","v":0},{"$f":"'K20 - time schedule'!JL53","v":0},{"$f":"'K20 - time schedule'!JM53","v":0},{"$f":"'K20 - time schedule'!JN53","v":0},{"$f":"'K20 - time schedule'!JO53","v":0},{"$f":"'K20 - time schedule'!JP53","v":0},{"$f":"'K20 - time schedule'!JQ53","v":0},{"$f":"'K20 - time schedule'!JR53","v":0},{"$f":"'K20 - time schedule'!JS53","v":0},{"$f":"'K20 - time schedule'!JT53","v":0},{"$f":"'K20 - time schedule'!JU53","v":0},{"$f":"'K20 - time schedule'!JV53","v":0},{"$f":"'K20 - time schedule'!JW53","v":0},{"$f":"'K20 - time schedule'!JX53","v":0},{"$f":"'K20 - time schedule'!JY53","v":0},{"$f":"'K20 - time schedule'!JZ53","v":0},{"$f":"'K20 - time schedule'!KA53","v":0},{"$f":"'K20 - time schedule'!KB53","v":0},{"$f":"'K20 - time schedule'!KC53","v":0},{"$f":"'K20 - time schedule'!KD53","v":0},{"$f":"'K20 - time schedule'!KE53","v":0},{"$f":"'K20 - time schedule'!KF53","v":0},{"$f":"'K20 - time schedule'!KG53","v":0},{"$f":"'K20 - time schedule'!KH53","v":0},{"$f":"'K20 - time schedule'!KI53","v":0},{"$f":"'K20 - time schedule'!KJ53","v":0},{"$f":"'K20 - time schedule'!KK53","v":0},{"$f":"'K20 - time schedule'!KL53","v":0},{"$f":"'K20 - time schedule'!KM53","v":0},{"$f":"'K20 - time schedule'!KN53","v":0},{"$f":"'K20 - time schedule'!KO53","v":0},{"$f":"'K20 - time schedule'!KP53","v":0},{"$f":"'K20 - time schedule'!KQ53","v":0},{"$f":"'K20 - time schedule'!KR53","v":0},{"$f":"'K20 - time schedule'!KS53","v":0},{"$f":"'K20 - time schedule'!KT53","v":0}]
["Boiler room K80 - operating staff training","K80","EUR",{"$f":"'K80 - time schedule'!G51","v":0},{"$f":"'K80 - time schedule'!H51","v":0},{"$f":"'K80 - time schedule'!I51","v":0},{"$f":"'K80 - time schedule'!J51","v":0},{"$f":"'K80 - time schedule'!K51","v":0},{"$f":"'K80 - time schedule'!L51","v":0},{"$f":"'K80 - time schedule'!M51","v":0},{"$f":"'K80 - time schedule'!N51","v":0},{"$f":"'K80 - time schedule'!O51","v":0},{"$f":"'K80 - time schedule'!P51","v":0},{"$f":"'K80 - time schedule'!Q51","v":0},{"$f":"'K80 - time schedule'!R51","v":0},{"$f":"'K80 - time schedule'!S51","v":0},{"$f":"'K80 - time schedule'!T51","v":0},{"$f":"'K80 - time schedule'!U51","v":0},{"$f":"'K80 - time schedule'!V51","v":0},{"$f":"'K80 - time schedule'!W51","v":0},{"$f":"'K80 - time schedule'!X51","v":0},{"$f":"'K80 - time schedule'!Y51","v":0},{"$f":"'K80 - time schedule'!Z51","v":0},{"$f":"'K80 - time schedule'!AA51","v":0},{"$f":"'K80 - time schedule'!AB51","v":0},{"$f":"'K80 - time schedule'!AC51","v":0},{"$f":"'K80 - time schedule'!AD51","v":0},{"$f":"'K80 - time schedule'!AE51","v":0},{"$f":"'K80 - time schedule'!AF51","v":0},{"$f":"'K80 - time schedule'!AG51","v":0},{"$f":"'K80 - time schedule'!AH51","v":0},{"$f":"'K80 - time schedule'!AI51","v":0},{"$f":"'K80 - time schedule'!AJ51","v":0},{"$f":"'K80 - time schedule'!AK51","v":0},{"$f":"'K80 - time schedule'!AL51","v":0},{"$f":"'K80 - time schedule'!AM51","v":0},{"$f":"'K80 - time schedule'!AN51","v":0},{"$f":"'K80 - time schedule'!AO51","v":0},{"$f":"'K80 - time schedule'!AP51","v":0},{"$f":"'K80 - time schedule'!AQ51","v":0},{"$f":"'K80 - time schedule'!AR51","v":0},{"$f":"'K80 - time schedule'!AS51","v":0},{"$f":"'K80 - time schedule'!AT51","v":0},{"$f":"'K80 - time schedule'!AU51","v":0},{"$f":"'K80 - time schedule'!AV51","v":0},{"$f":"'K80 - time schedule'!AW51","v":0},{"$f":"'K80 - time schedule'!AX51","v":0},{"$f":"'K80 - time schedule'!AY51","v":0},{"$f":"'K80 - time schedule'!AZ51","v":0},{"$f":"'K80 - time schedule'!BA51","v":0},{"$f":"'K80 - time schedule'!BB51","v":0},{"$f":"'K80 - time schedule'!BC51","v":0},{"$f":"'K80 - time schedule'!BD51","v":0},{"$f":"'K80 - time schedule'!BE51","v":0},{"$f":"'K80 - time schedule'!BF51","v":0},{"$f":"'K80 - time schedule'!BG51","v":0},{"$f":"'K80 - time schedule'!BH51","v":0},{"$f":"'K80 - time schedule'!BI51","v":0},{"$f":"'K80 - time schedule'!BJ51","v":0},{"$f":"'K80 - time schedule'!BK51","v":0},{"$f":"'K80 - time schedule'!BL51","v":0},{"$f":"'K80 - time schedule'!BM51","v":0},{"$f":"'K80 - time schedule'!BN51","v":0},{"$f":"'K80 - time schedule'!BO51","v":0},{"$f":"'K80 - time schedule'!BP51","v":0},{"$f":"'K80 - time schedule'!BQ51","v":0},{"$f":"'K80 - time schedule'!BR51","v":0},{"$f":"'K80 - time schedule'!BS51","v":0},{"$f":"'K80 - time schedule'!BT51","v":0},{"$f":"'K80 - time schedule'!BU51","v":0},{"$f":"'K80 - time schedule'!BV51","v":0},{"$f":"'K80 - time schedule'!BW51","v":0},{"$f":"'K80 - time schedule'!BX51","v":0},{"$f":"'K80 - time schedule'!BY51","v":0},{"$f":"'K80 - time schedule'!BZ51","v":0},{"$f":"'K80 - time schedule'!CA51","v":0},{"$f":"'K80 - time schedule'!CB51","v":0},{"$f":"'K80 - time schedule'!CC51","v":0},{"$f":"'K80 - time schedule'!CD51","v":0},{"$f":"'K80 - time schedule'!CE51","v":0},{"$f":"'K80 - time schedule'!CF51","v":0},{"$f":"'K80 - time schedule'!CG51","v":0},{"$f":"'K80 - time schedule'!CH51","v":0},{"$f":"'K80 - time schedule'!CI51","v":0},{"$f":"'K80 - time schedule'!CJ51","v":0},{"$f":"'K80 - time schedule'!CK51","v":0},{"$f":"'K80 - time schedule'!CL51","v":0},{"$f":"'K80 - time schedule'!CM51","v":0},{"$f":"'K80 - time schedule'!CN51","v":0},{"$f":"'K80 - time schedule'!CO51","v":0},{"$f":"'K80 - time schedule'!CP51","v":0},{"$f":"'K80 - time schedule'!CQ51","v":0},{"$f":"'K80 - time schedule'!CR51","v":0},{"$f":"'K80 - time schedule'!CS51","v":0},{"$f":"'K80 - time schedule'!CT51","v":0},{"$f":"'K80 - time schedule'!CU51","v":0},{"$f":"'K80 - time schedule'!CV51","v":0},{"$f":"'K80 - time schedule'!CW51","v":0},{"$f":"'K80 - time schedule'!CX51","v":0},{"$f":"'K80 - time schedule'!CY51","v":0},{"$f":"'K80 - time schedule'!CZ51","v":0},{"$f":"'K80 - time schedule'!DA51","v":0},{"$f":"'K80 - time schedule'!DB51","v":0},{"$f":"'K80 - time schedule'!DC51","v":0},{"$f":"'K80 - time schedule'!DD51","v":0},{"$f":"'K80 - time schedule'!DE51","v":0},{"$f":"'K80 - time schedule'!DF51","v":0},{"$f":"'K80 - time schedule'!DG51","v":0},{"$f":"'K80 - time schedule'!DH51","v":0},{"$f":"'K80 - time schedule'!DI51","v":0},{"$f":"'K80 - time schedule'!DJ51","v":0},{"$f":"'K80 - time schedule'!DK51","v":0},{"$f":"'K80 - time schedule'!DL51","v":0},{"$f":"'K80 - time schedule'!DM51","v":0},{"$f":"'K80 - time schedule'!DN51","v":0},{"$f":"'K80 - time schedule'!DO51","v":0},{"$f":"'K80 - time schedule'!DP51","v":0},{"$f":"'K80 - time schedule'!DQ51","v":0},{"$f":"'K80 - time schedule'!DR51","v":0},{"$f":"'K80 - time schedule'!DS51","v":0},{"$f":"'K80 - time schedule'!DT51","v":0},{"$f":"'K80 - time schedule'!DU51","v":0},{"$f":"'K80 - time schedule'!DV51","v":0},{"$f":"'K80 - time schedule'!DW51","v":0},{"$f":"'K80 - time schedule'!DX51","v":0},{"$f":"'K80 - time schedule'!DY51","v":0},{"$f":"'K80 - time schedule'!DZ51","v":0},{"$f":"'K80 - time schedule'!EA51","v":0},{"$f":"'K80 - time schedule'!EB51","v":0},{"$f":"'K80 - time schedule'!EC51","v":0},{"$f":"'K80 - time schedule'!ED51","v":0},{"$f":"'K80 - time schedule'!EE51","v":0},{"$f":"'K80 - time schedule'!EF51","v":0},{"$f":"'K80 - time schedule'!EG51","v":0},{"$f":"'K80 - time schedule'!EH51","v":0},{"$f":"'K80 - time schedule'!EI51","v":0},{"$f":"'K80 - time schedule'!EJ51","v":0},{"$f":"'K80 - time schedule'!EK51","v":0},{"$f":"'K80 - time schedule'!EL51","v":0},{"$f":"'K80 - time schedule'!EM51","v":0},{"$f":"'K80 - time schedule'!EN51","v":0},{"$f":"'K80 - time schedule'!EO51","v":0},{"$f":"'K80 - time schedule'!EP51","v":0},{"$f":"'K80 - time schedule'!EQ51","v":0},{"$f":"'K80 - time schedule'!ER51","v":0},{"$f":"'K80 - time schedule'!ES51","v":0},{"$f":"'K80 - time schedule'!ET51","v":0},{"$f":"'K80 - time schedule'!EU51","v":0},{"$f":"'K80 - time schedule'!EV51","v":0},{"$f":"'K80 - time schedule'!EW51","v":0},{"$f":"'K80 - time schedule'!EX51","v":0},{"$f":"'K80 - time schedule'!EY51","v":0},{"$f":"'K80 - time schedule'!EZ51","v":0},{"$f":"'K80 - time schedule'!FA51","v":0},{"$f":"'K80 - time schedule'!FB51","v":0},{"$f":"'K80 - time schedule'!FC51","v":0},{"$f":"'K80 - time schedule'!FD51","v":0},{"$f":"'K80 - time schedule'!FE51","v":0},{"$f":"'K80 - time schedule'!FF51","v":0},{"$f":"'K80 - time schedule'!FG51","v":0},{"$f":"'K80 - time schedule'!FH51","v":0},{"$f":"'K80 - time schedule'!FI51","v":0},{"$f":"'K80 - time schedule'!FJ51","v":0},{"$f":"'K80 - time schedule'!FK51","v":0},{"$f":"'K80 - time schedule'!FL51","v":0},{"$f":"'K80 - time schedule'!FM51","v":0},{"$f":"'K80 - time schedule'!FN51","v":0},{"$f":"'K80 - time schedule'!FO51","v":0},{"$f":"'K80 - time schedule'!FP51","v":0},{"$f":"'K80 - time schedule'!FQ51","v":0},{"$f":"'K80 - time schedule'!FR51","v":0},{"$f":"'K80 - time schedule'!FS51","v":0},{"$f":"'K80 - time schedule'!FT51","v":0},{"$f":"'K80 - time schedule'!FU51","v":0},{"$f":"'K80 - time schedule'!FV51","v":0},{"$f":"'K80 - time schedule'!FW51","v":0},{"$f":"'K80 - time schedule'!FX51","v":0},{"$f":"'K80 - time schedule'!FY51","v":0},{"$f":"'K80 - time schedule'!FZ51","v":0},{"$f":"'K80 - time schedule'!GA51","v":0},{"$f":"'K80 - time schedule'!GB51","v":0},{"$f":"'K80 - time schedule'!GC51","v":0},{"$f":"'K80 - time schedule'!GD51","v":0},{"$f":"'K80 - time schedule'!GE51","v":0},{"$f":"'K80 - time schedule'!GF51","v":0},{"$f":"'K20 - time schedule'!GG54","v":0},{"$f":"'K20 - time schedule'!GH54","v":0},{"$f":"'K20 - time schedule'!GI54","v":0},{"$f":"'K20 - time schedule'!GJ54","v":0},{"$f":"'K20 - time schedule'!GK54","v":0},{"$f":"'K20 - time schedule'!GL54","v":0},{"$f":"'K20 - time schedule'!GM54","v":0},{"$f":"'K20 - time schedule'!GN54","v":0},{"$f":"'K20 - time schedule'!GO54","v":0},{"$f":"'K20 - time schedule'!GP54","v":0},{"$f":"'K20 - time schedule'!GQ54","v":0},{"$f":"'K20 - time schedule'!GR54","v":0},{"$f":"'K20 - time schedule'!GS54","v":0},{"$f":"'K20 - time schedule'!GT54","v":0},{"$f":"'K20 - time schedule'!GU54","v":0},{"$f":"'K20 - time schedule'!GV54","v":0},{"$f":"'K20 - time schedule'!GW54","v":0},{"$f":"'K20 - time schedule'!GX54","v":0},{"$f":"'K20 - time schedule'!GY54","v":0},{"$f":"'K20 - time schedule'!GZ54","v":0},{"$f":"'K20 - time schedule'!HA54","v":0},{"$f":"'K20 - time schedule'!HB54","v":0},{"$f":"'K20 - time schedule'!HC54","v":0},{"$f":"'K20 - time schedule'!HD54","v":0},{"$f":"'K20 - time schedule'!HE54","v":0},{"$f":"'K20 - time schedule'!HF54","v":0},{"$f":"'K20 - time schedule'!HG54","v":0},{"$f":"'K20 - time schedule'!HH54","v":0},{"$f":"'K20 - time schedule'!HI54","v":0},{"$f":"'K20 - time schedule'!HJ54","v":0},{"$f":"'K20 - time schedule'!HK54","v":0},{"$f":"'K20 - time schedule'!HL54","v":0},{"$f":"'K20 - time schedule'!HM54","v":0},{"$f":"'K20 - time schedule'!HN54","v":0},{"$f":"'K20 - time schedule'!HO54","v":0},{"$f":"'K20 - time schedule'!HP54","v":0},{"$f":"'K20 - time schedule'!HQ54","v":0},{"$f":"'K20 - time schedule'!HR54","v":0},{"$f":"'K20 - time schedule'!HS54","v":0},{"$f":"'K20 - time schedule'!HT54","v":0},{"$f":"'K20 - time schedule'!HU54","v":0},{"$f":"'K20 - time schedule'!HV54","v":0},{"$f":"'K20 - time schedule'!HW54","v":0},{"$f":"'K20 - time schedule'!HX54","v":0},{"$f":"'K20 - time schedule'!HY54","v":0},{"$f":"'K20 - time schedule'!HZ54","v":0},{"$f":"'K20 - time schedule'!IA54","v":0},{"$f":"'K20 - time schedule'!IB54","v":0},{"$f":"'K20 - time schedule'!IC54","v":0},{"$f":"'K20 - time schedule'!ID54","v":0},{"$f":"'K20 - time schedule'!IE54","v":0},{"$f":"'K20 - time schedule'!IF54","v":0},{"$f":"'K20 - time schedule'!IG54","v":0},{"$f":"'K20 - time schedule'!IH54","v":0},{"$f":"'K20 - time schedule'!II54","v":0},{"$f":"'K20 - time schedule'!IJ54","v":0},{"$f":"'K20 - time schedule'!IK54","v":0},{"$f":"'K20 - time schedule'!IL54","v":0},{"$f":"'K20 - time schedule'!IM54","v":0},{"$f":"'K20 - time schedule'!IN54","v":0},{"$f":"'K20 - time schedule'!IO54","v":0},{"$f":"'K20 - time schedule'!IP54","v":0},{"$f":"'K20 - time schedule'!IQ54","v":0},{"$f":"'K20 - time schedule'!IR54","v":0},{"$f":"'K20 - time schedule'!IS54","v":0},{"$f":"'K20 - time schedule'!IT54","v":0},{"$f":"'K20 - time schedule'!IU54","v":0},{"$f":"'K20 - time schedule'!IV54","v":0},{"$f":"'K20 - time schedule'!IW54","v":0},{"$f":"'K20 - time schedule'!IX54","v":0},{"$f":"'K20 - time schedule'!IY54","v":0},{"$f":"'K20 - time schedule'!IZ54","v":0},{"$f":"'K20 - time schedule'!JA54","v":0},{"$f":"'K20 - time schedule'!JB54","v":0},{"$f":"'K20 - time schedule'!JC54","v":0},{"$f":"'K20 - time schedule'!JD54","v":0},{"$f":"'K20 - time schedule'!JE54","v":0},{"$f":"'K20 - time schedule'!JF54","v":0},{"$f":"'K20 - time schedule'!JG54","v":0},{"$f":"'K20 - time schedule'!JH54","v":0},{"$f":"'K20 - time schedule'!JI54","v":0},{"$f":"'K20 - time schedule'!JJ54","v":0},{"$f":"'K20 - time schedule'!JK54","v":0},{"$f":"'K20 - time schedule'!JL54","v":0},{"$f":"'K20 - time schedule'!JM54","v":0},{"$f":"'K20 - time schedule'!JN54","v":0},{"$f":"'K20 - time schedule'!JO54","v":0},{"$f":"'K20 - time schedule'!JP54","v":0},{"$f":"'K20 - time schedule'!JQ54","v":0},{"$f":"'K20 - time schedule'!JR54","v":0},{"$f":"'K20 - time schedule'!JS54","v":0},{"$f":"'K20 - time schedule'!JT54","v":0},{"$f":"'K20 - time schedule'!JU54","v":0},{"$f":"'K20 - time schedule'!JV54","v":0},{"$f":"'K20 - time schedule'!JW54","v":0},{"$f":"'K20 - time schedule'!JX54","v":0},{"$f":"'K20 - time schedule'!JY54","v":0},{"$f":"'K20 - time schedule'!JZ54","v":0},{"$f":"'K20 - time schedule'!KA54","v":0},{"$f":"'K20 - time schedule'!KB54","v":0},{"$f":"'K20 - time schedule'!KC54","v":0},{"$f":"'K20 - time schedule'!KD54","v":0},{"$f":"'K20 - time schedule'!KE54","v":0},{"$f":"'K20 - time schedule'!KF54","v":0},{"$f":"'K20 - time schedule'!KG54","v":0},{"$f":"'K20 - time schedule'!KH54","v":0},{"$f":"'K20 - time schedule'!KI54","v":0},{"$f":"'K20 - time schedule'!KJ54","v":0},{"$f":"'K20 - time schedule'!KK54","v":0},{"$f":"'K20 - time schedule'!KL54","v":0},{"$f":"'K20 - time schedule'!KM54","v":0},{"$f":"'K20 - time schedule'!KN54","v":0},{"$f":"'K20 - time schedule'!KO54","v":0},{"$f":"'K20 - time schedule'!KP54","v":0},{"$f":"'K20 - time schedule'!KQ54","v":0},{"$f":"'K20 - time schedule'!KR54","v":0},{"$f":"'K20 - time schedule'!KS54","v":0},{"$f":"'K20 - time schedule'!KT54","v":0}]
["Boiler room K80 - comprehensive testing","K80","EUR",{"$f":"'K80 - time schedule'!G54","v":0},{"$f":"'K80 - time schedule'!H54","v":0},{"$f":"'K80 - time schedule'!I54","v":0},{"$f":"'K80 - time schedule'!J54","v":0},{"$f":"'K80 - time schedule'!K54","v":0},{"$f":"'K80 - time schedule'!L54","v":0},{"$f":"'K80 - time schedule'!M54","v":0},{"$f":"'K80 - time schedule'!N54","v":0},{"$f":"'K80 - time schedule'!O54","v":0},{"$f":"'K80 - time schedule'!P54","v":0},{"$f":"'K80 - time schedule'!Q54","v":0},{"$f":"'K80 - time schedule'!R54","v":0},{"$f":"'K80 - time schedule'!S54","v":0},{"$f":"'K80 - time schedule'!T54","v":0},{"$f":"'K80 - time schedule'!U54","v":0},{"$f":"'K80 - time schedule'!V54","v":0},{"$f":"'K80 - time schedule'!W54","v":0},{"$f":"'K80 - time schedule'!X54","v":0},{"$f":"'K80 - time schedule'!Y54","v":0},{"$f":"'K80 - time schedule'!Z54","v":0},{"$f":"'K80 - time schedule'!AA54","v":0},{"$f":"'K80 - time schedule'!AB54","v":0},{"$f":"'K80 - time schedule'!AC54","v":0},{"$f":"'K80 - time schedule'!AD54","v":0},{"$f":"'K80 - time schedule'!AE54","v":0},{"$f":"'K80 - time schedule'!AF54","v":0},{"$f":"'K80 - time schedule'!AG54","v":0},{"$f":"'K80 - time schedule'!AH54","v":0},{"$f":"'K80 - time schedule'!AI54","v":0},{"$f":"'K80 - time schedule'!AJ54","v":0},{"$f":"'K80 - time schedule'!AK54","v":0},{"$f":"'K80 - time schedule'!AL54","v":0},{"$f":"'K80 - time schedule'!AM54","v":0},{"$f":"'K80 - time schedule'!AN54","v":0},{"$f":"'K80 - time schedule'!AO54","v":0},{"$f":"'K80 - time schedule'!AP54","v":0},{"$f":"'K80 - time schedule'!AQ54","v":0},{"$f":"'K80 - time schedule'!AR54","v":0},{"$f":"'K80 - time schedule'!AS54","v":0},{"$f":"'K80 - time schedule'!AT54","v":0},{"$f":"'K80 - time schedule'!AU54","v":0},{"$f":"'K80 - time schedule'!AV54","v":0},{"$f":"'K80 - time schedule'!AW54","v":0},{"$f":"'K80 - time schedule'!AX54","v":0},{"$f":"'K80 - time schedule'!AY54","v":0},{"$f":"'K80 - time schedule'!AZ54","v":0},{"$f":"'K80 - time schedule'!BA54","v":0},{"$f":"'K80 - time schedule'!BB54","v":0},{"$f":"'K80 - time schedule'!BC54","v":0},{"$f":"'K80 - time schedule'!BD54","v":0},{"$f":"'K80 - time schedule'!BE54","v":0},{"$f":"'K80 - time schedule'!BF54","v":0},{"$f":"'K80 - time schedule'!BG54","v":0},{"$f":"'K80 - time schedule'!BH54","v":0},{"$f":"'K80 - time schedule'!BI54","v":0},{"$f":"'K80 - time schedule'!BJ54","v":0},{"$f":"'K80 - time schedule'!BK54","v":0},{"$f":"'K80 - time schedule'!BL54","v":0},{"$f":"'K80 - time schedule'!BM54","v":0},{"$f":"'K80 - time schedule'!BN54","v":0},{"$f":"'K80 - time schedule'!BO54","v":0},{"$f":"'K80 - time schedule'!BP54","v":0},{"$f":"'K80 - time schedule'!BQ54","v":0},{"$f":"'K80 - time schedule'!BR54","v":0},{"$f":"'K80 - time schedule'!BS54","v":0},{"$f":"'K80 - time schedule'!BT54","v":0},{"$f":"'K80 - time schedule'!BU54","v":0},{"$f":"'K80 - time schedule'!BV54","v":0},{"$f":"'K80 - time schedule'!BW54","v":0},{"$f":"'K80 - time schedule'!BX54","v":0},{"$f":"'K80 - time schedule'!BY54","v":0},{"$f":"'K80 - time schedule'!BZ54","v":0},{"$f":"'K80 - time schedule'!CA54","v":0},{"$f":"'K80 - time schedule'!CB54","v":0},{"$f":"'K80 - time schedule'!CC54","v":0},{"$f":"'K80 - time schedule'!CD54","v":0},{"$f":"'K80 - time schedule'!CE54","v":0},{"$f":"'K80 - time schedule'!CF54","v":0},{"$f":"'K80 - time schedule'!CG54","v":0},{"$f":"'K80 - time schedule'!CH54","v":0},{"$f":"'K80 - time schedule'!CI54","v":0},{"$f":"'K80 - time schedule'!CJ54","v":0},{"$f":"'K80 - time schedule'!CK54","v":0},{"$f":"'K80 - time schedule'!CL54","v":0},{"$f":"'K80 - time schedule'!CM54","v":0},{"$f":"'K80 - time schedule'!CN54","v":0},{"$f":"'K80 - time schedule'!CO54","v":0},{"$f":"'K80 - time schedule'!CP54","v":0},{"$f":"'K80 - time schedule'!CQ54","v":0},{"$f":"'K80 - time schedule'!CR54","v":0},{"$f":"'K80 - time schedule'!CS54","v":0},{"$f":"'K80 - time schedule'!CT54","v":0},{"$f":"'K80 - time schedule'!CU54","v":0},{"$f":"'K80 - time schedule'!CV54","v":0},{"$f":"'K80 - time schedule'!CW54","v":0},{"$f":"'K80 - time schedule'!CX54","v":0},{"$f":"'K80 - time schedule'!CY54","v":0},{"$f":"'K80 - time schedule'!CZ54","v":0},{"$f":"'K80 - time schedule'!DA54","v":0},{"$f":"'K80 - time schedule'!DB54","v":0},{"$f":"'K80 - time schedule'!DC54","v":0},{"$f":"'K80 - time schedule'!DD54","v":0},{"$f":"'K80 - time schedule'!DE54","v":0},{"$f":"'K80 - time schedule'!DF54","v":0},{"$f":"'K80 - time schedule'!DG54","v":0},{"$f":"'K80 - time schedule'!DH54","v":0},{"$f":"'K80 - time schedule'!DI54","v":0},{"$f":"'K80 - time schedule'!DJ54","v":0},{"$f":"'K80 - time schedule'!DK54","v":0},{"$f":"'K80 - time schedule'!DL54","v":0},{"$f":"'K80 - time schedule'!DM54","v":0},{"$f":"'K80 - time schedule'!DN54","v":0},{"$f":"'K80 - time schedule'!DO54","v":0},{"$f":"'K80 - time schedule'!DP54","v":0},{"$f":"'K80 - time schedule'!DQ54","v":0},{"$f":"'K80 - time schedule'!DR54","v":0},{"$f":"'K80 - time schedule'!DS54","v":0},{"$f":"'K80 - time schedule'!DT54","v":0},{"$f":"'K80 - time schedule'!DU54","v":0},{"$f":"'K80 - time schedule'!DV54","v":0},{"$f":"'K80 - time schedule'!DW54","v":0},{"$f":"'K80 - time schedule'!DX54","v":0},{"$f":"'K80 - time schedule'!DY54","v":0},{"$f":"'K80 - time schedule'!DZ54","v":0},{"$f":"'K80 - time schedule'!EA54","v":0},{"$f":"'K80 - time schedule'!EB54","v":0},{"$f":"'K80 - time schedule'!EC54","v":0},{"$f":"'K80 - time schedule'!ED54","v":0},{"$f":"'K80 - time schedule'!EE54","v":0},{"$f":"'K80 - time schedule'!EF54","v":0},{"$f":"'K80 - time schedule'!EG54","v":0},{"$f":"'K80 - time schedule'!EH54","v":0},{"$f":"'K80 - time schedule'!EI54","v":0},{"$f":"'K80 - time schedule'!EJ54","v":0},{"$f":"'K80 - time schedule'!EK54","v":0},{"$f":"'K80 - time schedule'!EL54","v":0},{"$f":"'K80 - time schedule'!EM54","v":0},{"$f":"'K80 - time schedule'!EN54","v":0},{"$f":"'K80 - time schedule'!EO54","v":0},{"$f":"'K80 - time schedule'!EP54","v":0},{"$f":"'K80 - time schedule'!EQ54","v":0},{"$f":"'K80 - time schedule'!ER54","v":0},{"$f":"'K80 - time schedule'!ES54","v":0},{"$f":"'K80 - time schedule'!ET54","v":0},{"$f":"'K80 - time schedule'!EU54","v":0},{"$f":"'K80 - time schedule'!EV54","v":0},{"$f":"'K80 - time schedule'!EW54","v":0},{"$f":"'K80 - time schedule'!EX54","v":0},{"$f":"'K80 - time schedule'!EY54","v":0},{"$f":"'K80 - time schedule'!EZ54","v":0},{"$f":"'K80 - time schedule'!FA54","v":0},{"$f":"'K80 - time schedule'!FB54","v":0},{"$f":"'K80 - time schedule'!FC54","v":0},{"$f":"'K80 - time schedule'!FD54","v":0},{"$f":"'K80 - time schedule'!FE54","v":0},{"$f":"'K80 - time schedule'!FF54","v":0},{"$f":"'K80 - time schedule'!FG54","v":0},{"$f":"'K80 - time schedule'!FH54","v":0},{"$f":"'K80 - time schedule'!FI54","v":0},{"$f":"'K80 - time schedule'!FJ54","v":0},{"$f":"'K80 - time schedule'!FK54","v":0},{"$f":"'K80 - time schedule'!FL54","v":0},{"$f":"'K80 - time schedule'!FM54","v":0},{"$f":"'K80 - time schedule'!FN54","v":0},{"$f":"'K80 - time schedule'!FO54","v":0},{"$f":"'K80 - time schedule'!FP54","v":0},{"$f":"'K80 - time schedule'!FQ54","v":0},{"$f":"'K80 - time schedule'!FR54","v":0},{"$f":"'K80 - time schedule'!FS54","v":0},{"$f":"'K80 - time schedule'!FT54","v":0},{"$f":"'K80 - time schedule'!FU54","v":0},{"$f":"'K80 - time schedule'!FV54","v":0},{"$f":"'K80 - time schedule'!FW54","v":0},{"$f":"'K80 - time schedule'!FX54","v":0},{"$f":"'K80 - time schedule'!FY54","v":0},{"$f":"'K80 - time schedule'!FZ54","v":0},{"$f":"'K80 - time schedule'!GA54","v":0},{"$f":"'K80 - time schedule'!GB54","v":0},{"$f":"'K80 - time schedule'!GC54","v":0},{"$f":"'K80 - time schedule'!GD54","v":0},{"$f":"'K80 - time schedule'!GE54","v":0},{"$f":"'K80 - time schedule'!GF54","v":0},{"$f":"'K20 - time schedule'!GG55","v":0},{"$f":"'K20 - time schedule'!GH55","v":0},{"$f":"'K20 - time schedule'!GI55","v":0},{"$f":"'K20 - time schedule'!GJ55","v":0},{"$f":"'K20 - time schedule'!GK55","v":0},{"$f":"'K20 - time schedule'!GL55","v":0},{"$f":"'K20 - time schedule'!GM55","v":0},{"$f":"'K20 - time schedule'!GN55","v":0},{"$f":"'K20 - time schedule'!GO55","v":0},{"$f":"'K20 - time schedule'!GP55","v":0},{"$f":"'K20 - time schedule'!GQ55","v":0},{"$f":"'K20 - time schedule'!GR55","v":0},{"$f":"'K20 - time schedule'!GS55","v":0},{"$f":"'K20 - time schedule'!GT55","v":0},{"$f":"'K20 - time schedule'!GU55","v":0},{"$f":"'K20 - time schedule'!GV55","v":0},{"$f":"'K20 - time schedule'!GW55","v":0},{"$f":"'K20 - time schedule'!GX55","v":0},{"$f":"'K20 - time schedule'!GY55","v":0},{"$f":"'K20 - time schedule'!GZ55","v":0},{"$f":"'K20 - time schedule'!HA55","v":0},{"$f":"'K20 - time schedule'!HB55","v":0},{"$f":"'K20 - time schedule'!HC55","v":0},{"$f":"'K20 - time schedule'!HD55","v":0},{"$f":"'K20 - time schedule'!HE55","v":0},{"$f":"'K20 - time schedule'!HF55","v":0},{"$f":"'K20 - time schedule'!HG55","v":0},{"$f":"'K20 - time schedule'!HH55","v":0},{"$f":"'K20 - time schedule'!HI55","v":0},{"$f":"'K20 - time schedule'!HJ55","v":0},{"$f":"'K20 - time schedule'!HK55","v":0},{"$f":"'K20 - time schedule'!HL55","v":0},{"$f":"'K20 - time schedule'!HM55","v":0},{"$f":"'K20 - time schedule'!HN55","v":0},{"$f":"'K20 - time schedule'!HO55","v":0},{"$f":"'K20 - time schedule'!HP55","v":0},{"$f":"'K20 - time schedule'!HQ55","v":0},{"$f":"'K20 - time schedule'!HR55","v":0},{"$f":"'K20 - time schedule'!HS55","v":0},{"$f":"'K20 - time schedule'!HT55","v":0},{"$f":"'K20 - time schedule'!HU55","v":0},{"$f":"'K20 - time schedule'!HV55","v":0},{"$f":"'K20 - time schedule'!HW55","v":0},{"$f":"'K20 - time schedule'!HX55","v":0},{"$f":"'K20 - time schedule'!HY55","v":0},{"$f":"'K20 - time schedule'!HZ55","v":0},{"$f":"'K20 - time schedule'!IA55","v":0},{"$f":"'K20 - time schedule'!IB55","v":0},{"$f":"'K20 - time schedule'!IC55","v":0},{"$f":"'K20 - time schedule'!ID55","v":0},{"$f":"'K20 - time schedule'!IE55","v":0},{"$f":"'K20 - time schedule'!IF55","v":0},{"$f":"'K20 - time schedule'!IG55","v":0},{"$f":"'K20 - time schedule'!IH55","v":0},{"$f":"'K20 - time schedule'!II55","v":0},{"$f":"'K20 - time schedule'!IJ55","v":0},{"$f":"'K20 - time schedule'!IK55","v":0},{"$f":"'K20 - time schedule'!IL55","v":0},{"$f":"'K20 - time schedule'!IM55","v":0},{"$f":"'K20 - time schedule'!IN55","v":0},{"$f":"'K20 - time schedule'!IO55","v":0},{"$f":"'K20 - time schedule'!IP55","v":0},{"$f":"'K20 - time schedule'!IQ55","v":0},{"$f":"'K20 - time schedule'!IR55","v":0},{"$f":"'K20 - time schedule'!IS55","v":0},{"$f":"'K20 - time schedule'!IT55","v":0},{"$f":"'K20 - time schedule'!IU55","v":0},{"$f":"'K20 - time schedule'!IV55","v":0},{"$f":"'K20 - time schedule'!IW55","v":0},{"$f":"'K20 - time schedule'!IX55","v":0},{"$f":"'K20 - time schedule'!IY55","v":0},{"$f":"'K20 - time schedule'!IZ55","v":0},{"$f":"'K20 - time schedule'!JA55","v":0},{"$f":"'K20 - time schedule'!JB55","v":0},{"$f":"'K20 - time schedule'!JC55","v":0},{"$f":"'K20 - time schedule'!JD55","v":0},{"$f":"'K20 - time schedule'!JE55","v":0},{"$f":"'K20 - time schedule'!JF55","v":0},{"$f":"'K20 - time schedule'!JG55","v":0},{"$f":"'K20 - time schedule'!JH55","v":0},{"$f":"'K20 - time schedule'!JI55","v":0},{"$f":"'K20 - time schedule'!JJ55","v":0},{"$f":"'K20 - time schedule'!JK55","v":0},{"$f":"'K20 - time schedule'!JL55","v":0},{"$f":"'K20 - time schedule'!JM55","v":0},{"$f":"'K20 - time schedule'!JN55","v":0},{"$f":"'K20 - time schedule'!JO55","v":0},{"$f":"'K20 - time schedule'!JP55","v":0},{"$f":"'K20 - time schedule'!JQ55","v":0},{"$f":"'K20 - time schedule'!JR55","v":0},{"$f":"'K20 - time schedule'!JS55","v":0},{"$f":"'K20 - time schedule'!JT55","v":0},{"$f":"'K20 - time schedule'!JU55","v":0},{"$f":"'K20 - time schedule'!JV55","v":0},{"$f":"'K20 - time schedule'!JW55","v":0},{"$f":"'K20 - time schedule'!JX55","v":0},{"$f":"'K20 - time schedule'!JY55","v":0},{"$f":"'K20 - time schedule'!JZ55","v":0},{"$f":"'K20 - time schedule'!KA55","v":0},{"$f":"'K20 - time schedule'!KB55","v":0},{"$f":"'K20 - time schedule'!KC55","v":0},{"$f":"'K20 - time schedule'!KD55","v":0},{"$f":"'K20 - time schedule'!KE55","v":0},{"$f":"'K20 - time schedule'!KF55","v":0},{"$f":"'K20 - time schedule'!KG55","v":0},{"$f":"'K20 - time schedule'!KH55","v":0},{"$f":"'K20 - time schedule'!KI55","v":0},{"$f":"'K20 - time schedule'!KJ55","v":0},{"$f":"'K20 - time schedule'!KK55","v":0},{"$f":"'K20 - time schedule'!KL55","v":0},{"$f":"'K20 - time schedule'!KM55","v":0},{"$f":"'K20 - time schedule'!KN55","v":0},{"$f":"'K20 - time schedule'!KO55","v":0},{"$f":"'K20 - time schedule'!KP55","v":0},{"$f":"'K20 - time schedule'!KQ55","v":0},{"$f":"'K20 - time schedule'!KR55","v":0},{"$f":"'K20 - time schedule'!KS55","v":0},{"$f":"'K20 - time schedule'!KT55","v":0}]
["Boiler room K80 - trial operation","K80","EUR",{"$f":"'K80 - time schedule'!G56","v":0},{"$f":"'K80 - time schedule'!H56","v":0},{"$f":"'K80 - time schedule'!I56","v":0},{"$f":"'K80 - time schedule'!J56","v":0},{"$f":"'K80 - time schedule'!K56","v":0},{"$f":"'K80 - time schedule'!L56","v":0},{"$f":"'K80 - time schedule'!M56","v":0},{"$f":"'K80 - time schedule'!N56","v":0},{"$f":"'K80 - time schedule'!O56","v":0},{"$f":"'K80 - time schedule'!P56","v":0},{"$f":"'K80 - time schedule'!Q56","v":0},{"$f":"'K80 - time schedule'!R56","v":0},{"$f":"'K80 - time schedule'!S56","v":0},{"$f":"'K80 - time schedule'!T56","v":0},{"$f":"'K80 - time schedule'!U56","v":0},{"$f":"'K80 - time schedule'!V56","v":0},{"$f":"'K80 - time schedule'!W56","v":0},{"$f":"'K80 - time schedule'!X56","v":0},{"$f":"'K80 - time schedule'!Y56","v":0},{"$f":"'K80 - time schedule'!Z56","v":0},{"$f":"'K80 - time schedule'!AA56","v":0},{"$f":"'K80 - time schedule'!AB56","v":0},{"$f":"'K80 - time schedule'!AC56","v":0},{"$f":"'K80 - time schedule'!AD56","v":0},{"$f":"'K80 - time schedule'!AE56","v":0},{"$f":"'K80 - time schedule'!AF56","v":0},{"$f":"'K80 - time schedule'!AG56","v":0},{"$f":"'K80 - time schedule'!AH56","v":0},{"$f":"'K80 - time schedule'!AI56","v":0},{"$f":"'K80 - time schedule'!AJ56","v":0},{"$f":"'K80 - time schedule'!AK56","v":0},{"$f":"'K80 - time schedule'!AL56","v":0},{"$f":"'K80 - time schedule'!AM56","v":0},{"$f":"'K80 - time schedule'!AN56","v":0},{"$f":"'K80 - time schedule'!AO56","v":0},{"$f":"'K80 - time schedule'!AP56","v":0},{"$f":"'K80 - time schedule'!AQ56","v":0},{"$f":"'K80 - time schedule'!AR56","v":0},{"$f":"'K80 - time schedule'!AS56","v":0},{"$f":"'K80 - time schedule'!AT56","v":0},{"$f":"'K80 - time schedule'!AU56","v":0},{"$f":"'K80 - time schedule'!AV56","v":0},{"$f":"'K80 - time schedule'!AW56","v":0},{"$f":"'K80 - time schedule'!AX56","v":0},{"$f":"'K80 - time schedule'!AY56","v":0},{"$f":"'K80 - time schedule'!AZ56","v":0},{"$f":"'K80 - time schedule'!BA56","v":0},{"$f":"'K80 - time schedule'!BB56","v":0},{"$f":"'K80 - time schedule'!BC56","v":0},{"$f":"'K80 - time schedule'!BD56","v":0},{"$f":"'K80 - time schedule'!BE56","v":0},{"$f":"'K80 - time schedule'!BF56","v":0},{"$f":"'K80 - time schedule'!BG56","v":0},{"$f":"'K80 - time schedule'!BH56","v":0},{"$f":"'K80 - time schedule'!BI56","v":0},{"$f":"'K80 - time schedule'!BJ56","v":0},{"$f":"'K80 - time schedule'!BK56","v":0},{"$f":"'K80 - time schedule'!BL56","v":0},{"$f":"'K80 - time schedule'!BM56","v":0},{"$f":"'K80 - time schedule'!BN56","v":0},{"$f":"'K80 - time schedule'!BO56","v":0},{"$f":"'K80 - time schedule'!BP56","v":0},{"$f":"'K80 - time schedule'!BQ56","v":0},{"$f":"'K80 - time schedule'!BR56","v":0},{"$f":"'K80 - time schedule'!BS56","v":0},{"$f":"'K80 - time schedule'!BT56","v":0},{"$f":"'K80 - time schedule'!BU56","v":0},{"$f":"'K80 - time schedule'!BV56","v":0},{"$f":"'K80 - time schedule'!BW56","v":0},{"$f":"'K80 - time schedule'!BX56","v":0},{"$f":"'K80 - time schedule'!BY56","v":0},{"$f":"'K80 - time schedule'!BZ56","v":0},{"$f":"'K80 - time schedule'!CA56","v":0},{"$f":"'K80 - time schedule'!CB56","v":0},{"$f":"'K80 - time schedule'!CC56","v":0},{"$f":"'K80 - time schedule'!CD56","v":0},{"$f":"'K80 - time schedule'!CE56","v":0},{"$f":"'K80 - time schedule'!CF56","v":0},{"$f":"'K80 - time schedule'!CG56","v":0},{"$f":"'K80 - time schedule'!CH56","v":0},{"$f":"'K80 - time schedule'!CI56","v":0},{"$f":"'K80 - time schedule'!CJ56","v":0},{"$f":"'K80 - time schedule'!CK56","v":0},{"$f":"'K80 - time schedule'!CL56","v":0},{"$f":"'K80 - time schedule'!CM56","v":0},{"$f":"'K80 - time schedule'!CN56","v":0},{"$f":"'K80 - time schedule'!CO56","v":0},{"$f":"'K80 - time schedule'!CP56","v":0},{"$f":"'K80 - time schedule'!CQ56","v":0},{"$f":"'K80 - time schedule'!CR56","v":0},{"$f":"'K80 - time schedule'!CS56","v":0},{"$f":"'K80 - time schedule'!CT56","v":0},{"$f":"'K80 - time schedule'!CU56","v":0},{"$f":"'K80 - time schedule'!CV56","v":0},{"$f":"'K80 - time schedule'!CW56","v":0},{"$f":"'K80 - time schedule'!CX56","v":0},{"$f":"'K80 - time schedule'!CY56","v":0},{"$f":"'K80 - time schedule'!CZ56","v":0},{"$f":"'K80 - time schedule'!DA56","v":0},{"$f":"'K80 - time schedule'!DB56","v":0},{"$f":"'K80 - time schedule'!DC56","v":0},{"$f":"'K80 - time schedule'!DD56","v":0},{"$f":"'K80 - time schedule'!DE56","v":0},{"$f":"'K80 - time schedule'!DF56","v":0},{"$f":"'K80 - time schedule'!DG56","v":0},{"$f":"'K80 - time schedule'!DH56","v":0},{"$f":"'K80 - time schedule'!DI56","v":0},{"$f":"'K80 - time schedule'!DJ56","v":0},{"$f":"'K80 - time schedule'!DK56","v":0},{"$f":"'K80 - time schedule'!DL56","v":0},{"$f":"'K80 - time schedule'!DM56","v":0},{"$f":"'K80 - time schedule'!DN56","v":0},{"$f":"'K80 - time schedule'!DO56","v":0},{"$f":"'K80 - time schedule'!DP56","v":0},{"$f":"'K80 - time schedule'!DQ56","v":0},{"$f":"'K80 - time schedule'!DR56","v":0},{"$f":"'K80 - time schedule'!DS56","v":0},{"$f":"'K80 - time schedule'!DT56","v":0},{"$f":"'K80 - time schedule'!DU56","v":0},{"$f":"'K80 - time schedule'!DV56","v":0},{"$f":"'K80 - time schedule'!DW56","v":0},{"$f":"'K80 - time schedule'!DX56","v":0},{"$f":"'K80 - time schedule'!DY56","v":0},{"$f":"'K80 - time schedule'!DZ56","v":0},{"$f":"'K80 - time schedule'!EA56","v":0},{"$f":"'K80 - time schedule'!EB56","v":0},{"$f":"'K80 - time schedule'!EC56","v":0},{"$f":"'K80 - time schedule'!ED56","v":0},{"$f":"'K80 - time schedule'!EE56","v":0},{"$f":"'K80 - time schedule'!EF56","v":0},{"$f":"'K80 - time schedule'!EG56","v":0},{"$f":"'K80 - time schedule'!EH56","v":0},{"$f":"'K80 - time schedule'!EI56","v":0},{"$f":"'K80 - time schedule'!EJ56","v":0},{"$f":"'K80 - time schedule'!EK56","v":0},{"$f":"'K80 - time schedule'!EL56","v":0},{"$f":"'K80 - time schedule'!EM56","v":0},{"$f":"'K80 - time schedule'!EN56","v":0},{"$f":"'K80 - time schedule'!EO56","v":0},{"$f":"'K80 - time schedule'!EP56","v":0},{"$f":"'K80 - time schedule'!EQ56","v":0},{"$f":"'K80 - time schedule'!ER56","v":0},{"$f":"'K80 - time schedule'!ES56","v":0},{"$f":"'K80 - time schedule'!ET56","v":0},{"$f":"'K80 - time schedule'!EU56","v":0},{"$f":"'K80 - time schedule'!EV56","v":0},{"$f":"'K80 - time schedule'!EW56","v":0},{"$f":"'K80 - time schedule'!EX56","v":0},{"$f":"'K80 - time schedule'!EY56","v":0},{"$f":"'K80 - time schedule'!EZ56","v":0},{"$f":"'K80 - time schedule'!FA56","v":0},{"$f":"'K80 - time schedule'!FB56","v":0},{"$f":"'K80 - time schedule'!FC56","v":0},{"$f":"'K80 - time schedule'!FD56","v":0},{"$f":"'K80 - time schedule'!FE56","v":0},{"$f":"'K80 - time schedule'!FF56","v":0},{"$f":"'K80 - time schedule'!FG56","v":0},{"$f":"'K80 - time schedule'!FH56","v":0},{"$f":"'K80 - time schedule'!FI56","v":0},{"$f":"'K80 - time schedule'!FJ56","v":0},{"$f":"'K80 - time schedule'!FK56","v":0},{"$f":"'K80 - time schedule'!FL56","v":0},{"$f":"'K80 - time schedule'!FM56","v":0},{"$f":"'K80 - time schedule'!FN56","v":0},{"$f":"'K80 - time schedule'!FO56","v":0},{"$f":"'K80 - time schedule'!FP56","v":0},{"$f":"'K80 - time schedule'!FQ56","v":0},{"$f":"'K80 - time schedule'!FR56","v":0},{"$f":"'K80 - time schedule'!FS56","v":0},{"$f":"'K80 - time schedule'!FT56","v":0},{"$f":"'K80 - time schedule'!FU56","v":0},{"$f":"'K80 - time schedule'!FV56","v":0},{"$f":"'K80 - time schedule'!FW56","v":0},{"$f":"'K80 - time schedule'!FX56","v":0},{"$f":"'K80 - time schedule'!FY56","v":0},{"$f":"'K80 - time schedule'!FZ56","v":0},{"$f":"'K80 - time schedule'!GA56","v":0},{"$f":"'K80 - time schedule'!GB56","v":0},{"$f":"'K80 - time schedule'!GC56","v":0},{"$f":"'K80 - time schedule'!GD56","v":0},{"$f":"'K80 - time schedule'!GE56","v":0},{"$f":"'K80 - time schedule'!GF56","v":0},{"$f":"'K20 - time schedule'!GG56","v":0},{"$f":"'K20 - time schedule'!GH56","v":0},{"$f":"'K20 - time schedule'!GI56","v":0},{"$f":"'K20 - time schedule'!GJ56","v":0},{"$f":"'K20 - time schedule'!GK56","v":0},{"$f":"'K20 - time schedule'!GL56","v":0},{"$f":"'K20 - time schedule'!GM56","v":0},{"$f":"'K20 - time schedule'!GN56","v":0},{"$f":"'K20 - time schedule'!GO56","v":0},{"$f":"'K20 - time schedule'!GP56","v":0},{"$f":"'K20 - time schedule'!GQ56","v":0},{"$f":"'K20 - time schedule'!GR56","v":0},{"$f":"'K20 - time schedule'!GS56","v":0},{"$f":"'K20 - time schedule'!GT56","v":0},{"$f":"'K20 - time schedule'!GU56","v":0},{"$f":"'K20 - time schedule'!GV56","v":0},{"$f":"'K20 - time schedule'!GW56","v":0},{"$f":"'K20 - time schedule'!GX56","v":0},{"$f":"'K20 - time schedule'!GY56","v":0},{"$f":"'K20 - time schedule'!GZ56","v":0},{"$f":"'K20 - time schedule'!HA56","v":0},{"$f":"'K20 - time schedule'!HB56","v":0},{"$f":"'K20 - time schedule'!HC56","v":0},{"$f":"'K20 - time schedule'!HD56","v":0},{"$f":"'K20 - time schedule'!HE56","v":0},{"$f":"'K20 - time schedule'!HF56","v":0},{"$f":"'K20 - time schedule'!HG56","v":0},{"$f":"'K20 - time schedule'!HH56","v":0},{"$f":"'K20 - time schedule'!HI56","v":0},{"$f":"'K20 - time schedule'!HJ56","v":0},{"$f":"'K20 - time schedule'!HK56","v":0},{"$f":"'K20 - time schedule'!HL56","v":0},{"$f":"'K20 - time schedule'!HM56","v":0},{"$f":"'K20 - time schedule'!HN56","v":0},{"$f":"'K20 - time schedule'!HO56","v":0},{"$f":"'K20 - time schedule'!HP56","v":0},{"$f":"'K20 - time schedule'!HQ56","v":0},{"$f":"'K20 - time schedule'!HR56","v":0},{"$f":"'K20 - time schedule'!HS56","v":0},{"$f":"'K20 - time schedule'!HT56","v":0},{"$f":"'K20 - time schedule'!HU56","v":0},{"$f":"'K20 - time schedule'!HV56","v":0},{"$f":"'K20 - time schedule'!HW56","v":0},{"$f":"'K20 - time schedule'!HX56","v":0},{"$f":"'K20 - time schedule'!HY56","v":0},{"$f":"'K20 - time schedule'!HZ56","v":0},{"$f":"'K20 - time schedule'!IA56","v":0},{"$f":"'K20 - time schedule'!IB56","v":0},{"$f":"'K20 - time schedule'!IC56","v":0},{"$f":"'K20 - time schedule'!ID56","v":0},{"$f":"'K20 - time schedule'!IE56","v":0},{"$f":"'K20 - time schedule'!IF56","v":0},{"$f":"'K20 - time schedule'!IG56","v":0},{"$f":"'K20 - time schedule'!IH56","v":0},{"$f":"'K20 - time schedule'!II56","v":0},{"$f":"'K20 - time schedule'!IJ56","v":0},{"$f":"'K20 - time schedule'!IK56","v":0},{"$f":"'K20 - time schedule'!IL56","v":0},{"$f":"'K20 - time schedule'!IM56","v":0},{"$f":"'K20 - time schedule'!IN56","v":0},{"$f":"'K20 - time schedule'!IO56","v":0},{"$f":"'K20 - time schedule'!IP56","v":0},{"$f":"'K20 - time schedule'!IQ56","v":0},{"$f":"'K20 - time schedule'!IR56","v":0},{"$f":"'K20 - time schedule'!IS56","v":0},{"$f":"'K20 - time schedule'!IT56","v":0},{"$f":"'K20 - time schedule'!IU56","v":0},{"$f":"'K20 - time schedule'!IV56","v":0},{"$f":"'K20 - time schedule'!IW56","v":0},{"$f":"'K20 - time schedule'!IX56","v":0},{"$f":"'K20 - time schedule'!IY56","v":0},{"$f":"'K20 - time schedule'!IZ56","v":0},{"$f":"'K20 - time schedule'!JA56","v":0},{"$f":"'K20 - time schedule'!JB56","v":0},{"$f":"'K20 - time schedule'!JC56","v":0},{"$f":"'K20 - time schedule'!JD56","v":0},{"$f":"'K20 - time schedule'!JE56","v":0},{"$f":"'K20 - time schedule'!JF56","v":0},{"$f":"'K20 - time schedule'!JG56","v":0},{"$f":"'K20 - time schedule'!JH56","v":0},{"$f":"'K20 - time schedule'!JI56","v":0},{"$f":"'K20 - time schedule'!JJ56","v":0},{"$f":"'K20 - time schedule'!JK56","v":0},{"$f":"'K20 - time schedule'!JL56","v":0},{"$f":"'K20 - time schedule'!JM56","v":0},{"$f":"'K20 - time schedule'!JN56","v":0},{"$f":"'K20 - time schedule'!JO56","v":0},{"$f":"'K20 - time schedule'!JP56","v":0},{"$f":"'K20 - time schedule'!JQ56","v":0},{"$f":"'K20 - time schedule'!JR56","v":0},{"$f":"'K20 - time schedule'!JS56","v":0},{"$f":"'K20 - time schedule'!JT56","v":0},{"$f":"'K20 - time schedule'!JU56","v":0},{"$f":"'K20 - time schedule'!JV56","v":0},{"$f":"'K20 - time schedule'!JW56","v":0},{"$f":"'K20 - time schedule'!JX56","v":0},{"$f":"'K20 - time schedule'!JY56","v":0},{"$f":"'K20 - time schedule'!JZ56","v":0},{"$f":"'K20 - time schedule'!KA56","v":0},{"$f":"'K20 - time schedule'!KB56","v":0},{"$f":"'K20 - time schedule'!KC56","v":0},{"$f":"'K20 - time schedule'!KD56","v":0},{"$f":"'K20 - time schedule'!KE56","v":0},{"$f":"'K20 - time schedule'!KF56","v":0},{"$f":"'K20 - time schedule'!KG56","v":0},{"$f":"'K20 - time schedule'!KH56","v":0},{"$f":"'K20 - time schedule'!KI56","v":0},{"$f":"'K20 - time schedule'!KJ56","v":0},{"$f":"'K20 - time schedule'!KK56","v":0},{"$f":"'K20 - time schedule'!KL56","v":0},{"$f":"'K20 - time schedule'!KM56","v":0},{"$f":"'K20 - time schedule'!KN56","v":0},{"$f":"'K20 - time schedule'!KO56","v":0},{"$f":"'K20 - time schedule'!KP56","v":0},{"$f":"'K20 - time schedule'!KQ56","v":0},{"$f":"'K20 - time schedule'!KR56","v":0},{"$f":"'K20 - time schedule'!KS56","v":0},{"$f":"'K20 - time schedule'!KT56","v":0}]
["Boiler room K80 - guarantee test A","K80","EUR",{"$f":"'K80 - time schedule'!G58","v":0},{"$f":"'K80 - time schedule'!H58","v":0},{"$f":"'K80 - time schedule'!I58","v":0},{"$f":"'K80 - time schedule'!J58","v":0},{"$f":"'K80 - time schedule'!K58","v":0},{"$f":"'K80 - time schedule'!L58","v":0},{"$f":"'K80 - time schedule'!M58","v":0},{"$f":"'K80 - time schedule'!N58","v":0},{"$f":"'K80 - time schedule'!O58","v":0},{"$f":"'K80 - time schedule'!P58","v":0},{"$f":"'K80 - time schedule'!Q58","v":0},{"$f":"'K80 - time schedule'!R58","v":0},{"$f":"'K80 - time schedule'!S58","v":0},{"$f":"'K80 - time schedule'!T58","v":0},{"$f":"'K80 - time schedule'!U58","v":0},{"$f":"'K80 - time schedule'!V58","v":0},{"$f":"'K80 - time schedule'!W58","v":0},{"$f":"'K80 - time schedule'!X58","v":0},{"$f":"'K80 - time schedule'!Y58","v":0},{"$f":"'K80 - time schedule'!Z58","v":0},{"$f":"'K80 - time schedule'!AA58","v":0},{"$f":"'K80 - time schedule'!AB58","v":0},{"$f":"'K80 - time schedule'!AC58","v":0},{"$f":"'K80 - time schedule'!AD58","v":0},{"$f":"'K80 - time schedule'!AE58","v":0},{"$f":"'K80 - time schedule'!AF58","v":0},{"$f":"'K80 - time schedule'!AG58","v":0},{"$f":"'K80 - time schedule'!AH58","v":0},{"$f":"'K80 - time schedule'!AI58","v":0},{"$f":"'K80 - time schedule'!AJ58","v":0},{"$f":"'K80 - time schedule'!AK58","v":0},{"$f":"'K80 - time schedule'!AL58","v":0},{"$f":"'K80 - time schedule'!AM58","v":0},{"$f":"'K80 - time schedule'!AN58","v":0},{"$f":"'K80 - time schedule'!AO58","v":0},{"$f":"'K80 - time schedule'!AP58","v":0},{"$f":"'K80 - time schedule'!AQ58","v":0},{"$f":"'K80 - time schedule'!AR58","v":0},{"$f":"'K80 - time schedule'!AS58","v":0},{"$f":"'K80 - time schedule'!AT58","v":0},{"$f":"'K80 - time schedule'!AU58","v":0},{"$f":"'K80 - time schedule'!AV58","v":0},{"$f":"'K80 - time schedule'!AW58","v":0},{"$f":"'K80 - time schedule'!AX58","v":0},{"$f":"'K80 - time schedule'!AY58","v":0},{"$f":"'K80 - time schedule'!AZ58","v":0},{"$f":"'K80 - time schedule'!BA58","v":0},{"$f":"'K80 - time schedule'!BB58","v":0},{"$f":"'K80 - time schedule'!BC58","v":0},{"$f":"'K80 - time schedule'!BD58","v":0},{"$f":"'K80 - time schedule'!BE58","v":0},{"$f":"'K80 - time schedule'!BF58","v":0},{"$f":"'K80 - time schedule'!BG58","v":0},{"$f":"'K80 - time schedule'!BH58","v":0},{"$f":"'K80 - time schedule'!BI58","v":0},{"$f":"'K80 - time schedule'!BJ58","v":0},{"$f":"'K80 - time schedule'!BK58","v":0},{"$f":"'K80 - time schedule'!BL58","v":0},{"$f":"'K80 - time schedule'!BM58","v":0},{"$f":"'K80 - time schedule'!BN58","v":0},{"$f":"'K80 - time schedule'!BO58","v":0},{"$f":"'K80 - time schedule'!BP58","v":0},{"$f":"'K80 - time schedule'!BQ58","v":0},{"$f":"'K80 - time schedule'!BR58","v":0},{"$f":"'K80 - time schedule'!BS58","v":0},{"$f":"'K80 - time schedule'!BT58","v":0},{"$f":"'K80 - time schedule'!BU58","v":0},{"$f":"'K80 - time schedule'!BV58","v":0},{"$f":"'K80 - time schedule'!BW58","v":0},{"$f":"'K80 - time schedule'!BX58","v":0},{"$f":"'K80 - time schedule'!BY58","v":0},{"$f":"'K80 - time schedule'!BZ58","v":0},{"$f":"'K80 - time schedule'!CA58","v":0},{"$f":"'K80 - time schedule'!CB58","v":0},{"$f":"'K80 - time schedule'!CC58","v":0},{"$f":"'K80 - time schedule'!CD58","v":0},{"$f":"'K80 - time schedule'!CE58","v":0},{"$f":"'K80 - time schedule'!CF58","v":0},{"$f":"'K80 - time schedule'!CG58","v":0},{"$f":"'K80 - time schedule'!CH58","v":0},{"$f":"'K80 - time schedule'!CI58","v":0},{"$f":"'K80 - time schedule'!CJ58","v":0},{"$f":"'K80 - time schedule'!CK58","v":0},{"$f":"'K80 - time schedule'!CL58","v":0},{"$f":"'K80 - time schedule'!CM58","v":0},{"$f":"'K80 - time schedule'!CN58","v":0},{"$f":"'K80 - time schedule'!CO58","v":0},{"$f":"'K80 - time schedule'!CP58","v":0},{"$f":"'K80 - time schedule'!CQ58","v":0},{"$f":"'K80 - time schedule'!CR58","v":0},{"$f":"'K80 - time schedule'!CS58","v":0},{"$f":"'K80 - time schedule'!CT58","v":0},{"$f":"'K80 - time schedule'!CU58","v":0},{"$f":"'K80 - time schedule'!CV58","v":0},{"$f":"'K80 - time schedule'!CW58","v":0},{"$f":"'K80 - time schedule'!CX58","v":0},{"$f":"'K80 - time schedule'!CY58","v":0},{"$f":"'K80 - time schedule'!CZ58","v":0},{"$f":"'K80 - time schedule'!DA58","v":0},{"$f":"'K80 - time schedule'!DB58","v":0},{"$f":"'K80 - time schedule'!DC58","v":0},{"$f":"'K80 - time schedule'!DD58","v":0},{"$f":"'K80 - time schedule'!DE58","v":0},{"$f":"'K80 - time schedule'!DF58","v":0},{"$f":"'K80 - time schedule'!DG58","v":0},{"$f":"'K80 - time schedule'!DH58","v":0},{"$f":"'K80 - time schedule'!DI58","v":0},{"$f":"'K80 - time schedule'!DJ58","v":0},{"$f":"'K80 - time schedule'!DK58","v":0},{"$f":"'K80 - time schedule'!DL58","v":0},{"$f":"'K80 - time schedule'!DM58","v":0},{"$f":"'K80 - time schedule'!DN58","v":0},{"$f":"'K80 - time schedule'!DO58","v":0},{"$f":"'K80 - time schedule'!DP58","v":0},{"$f":"'K80 - time schedule'!DQ58","v":0},{"$f":"'K80 - time schedule'!DR58","v":0},{"$f":"'K80 - time schedule'!DS58","v":0},{"$f":"'K80 - time schedule'!DT58","v":0},{"$f":"'K80 - time schedule'!DU58","v":0},{"$f":"'K80 - time schedule'!DV58","v":0},{"$f":"'K80 - time schedule'!DW58","v":0},{"$f":"'K80 - time schedule'!DX58","v":0},{"$f":"'K80 - time schedule'!DY58","v":0},{"$f":"'K80 - time schedule'!DZ58","v":0},{"$f":"'K80 - time schedule'!EA58","v":0},{"$f":"'K80 - time schedule'!EB58","v":0},{"$f":"'K80 - time schedule'!EC58","v":0},{"$f":"'K80 - time schedule'!ED58","v":0},{"$f":"'K80 - time schedule'!EE58","v":0},{"$f":"'K80 - time schedule'!EF58","v":0},{"$f":"'K80 - time schedule'!EG58","v":0},{"$f":"'K80 - time schedule'!EH58","v":0},{"$f":"'K80 - time schedule'!EI58","v":0},{"$f":"'K80 - time schedule'!EJ58","v":0},{"$f":"'K80 - time schedule'!EK58","v":0},{"$f":"'K80 - time schedule'!EL58","v":0},{"$f":"'K80 - time schedule'!EM58","v":0},{"$f":"'K80 - time schedule'!EN58","v":0},{"$f":"'K80 - time schedule'!EO58","v":0},{"$f":"'K80 - time schedule'!EP58","v":0},{"$f":"'K80 - time schedule'!EQ58","v":0},{"$f":"'K80 - time schedule'!ER58","v":0},{"$f":"'K80 - time schedule'!ES58","v":0},{"$f":"'K80 - time schedule'!ET58","v":0},{"$f":"'K80 - time schedule'!EU58","v":0},{"$f":"'K80 - time schedule'!EV58","v":0},{"$f":"'K80 - time schedule'!EW58","v":0},{"$f":"'K80 - time schedule'!EX58","v":0},{"$f":"'K80 - time schedule'!EY58","v":0},{"$f":"'K80 - time schedule'!EZ58","v":0},{"$f":"'K80 - time schedule'!FA58","v":0},{"$f":"'K80 - time schedule'!FB58","v":0},{"$f":"'K80 - time schedule'!FC58","v":0},{"$f":"'K80 - time schedule'!FD58","v":0},{"$f":"'K80 - time schedule'!FE58","v":0},{"$f":"'K80 - time schedule'!FF58","v":0},{"$f":"'K80 - time schedule'!FG58","v":0},{"$f":"'K80 - time schedule'!FH58","v":0},{"$f":"'K80 - time schedule'!FI58","v":0},{"$f":"'K80 - time schedule'!FJ58","v":0},{"$f":"'K80 - time schedule'!FK58","v":0},{"$f":"'K80 - time schedule'!FL58","v":0},{"$f":"'K80 - time schedule'!FM58","v":0},{"$f":"'K80 - time schedule'!FN58","v":0},{"$f":"'K80 - time schedule'!FO58","v":0},{"$f":"'K80 - time schedule'!FP58","v":0},{"$f":"'K80 - time schedule'!FQ58","v":0},{"$f":"'K80 - time schedule'!FR58","v":0},{"$f":"'K80 - time schedule'!FS58","v":0},{"$f":"'K80 - time schedule'!FT58","v":0},{"$f":"'K80 - time schedule'!FU58","v":0},{"$f":"'K80 - time schedule'!FV58","v":0},{"$f":"'K80 - time schedule'!FW58","v":0},{"$f":"'K80 - time schedule'!FX58","v":0},{"$f":"'K80 - time schedule'!FY58","v":0},{"$f":"'K80 - time schedule'!FZ58","v":0},{"$f":"'K80 - time schedule'!GA58","v":0},{"$f":"'K80 - time schedule'!GB58","v":0},{"$f":"'K80 - time schedule'!GC58","v":0},{"$f":"'K80 - time schedule'!GD58","v":0},{"$f":"'K80 - time schedule'!GE58","v":0},{"$f":"'K80 - time schedule'!GF58","v":0},{"$f":"'K20 - time schedule'!GG57","v":0},{"$f":"'K20 - time schedule'!GH57","v":0},{"$f":"'K20 - time schedule'!GI57","v":0},{"$f":"'K20 - time schedule'!GJ57","v":0},{"$f":"'K20 - time schedule'!GK57","v":0},{"$f":"'K20 - time schedule'!GL57","v":0},{"$f":"'K20 - time schedule'!GM57","v":0},{"$f":"'K20 - time schedule'!GN57","v":0},{"$f":"'K20 - time schedule'!GO57","v":0},{"$f":"'K20 - time schedule'!GP57","v":0},{"$f":"'K20 - time schedule'!GQ57","v":0},{"$f":"'K20 - time schedule'!GR57","v":0},{"$f":"'K20 - time schedule'!GS57","v":0},{"$f":"'K20 - time schedule'!GT57","v":0},{"$f":"'K20 - time schedule'!GU57","v":0},{"$f":"'K20 - time schedule'!GV57","v":0},{"$f":"'K20 - time schedule'!GW57","v":0},{"$f":"'K20 - time schedule'!GX57","v":0},{"$f":"'K20 - time schedule'!GY57","v":0},{"$f":"'K20 - time schedule'!GZ57","v":0},{"$f":"'K20 - time schedule'!HA57","v":0},{"$f":"'K20 - time schedule'!HB57","v":0},{"$f":"'K20 - time schedule'!HC57","v":0},{"$f":"'K20 - time schedule'!HD57","v":0},{"$f":"'K20 - time schedule'!HE57","v":0},{"$f":"'K20 - time schedule'!HF57","v":0},{"$f":"'K20 - time schedule'!HG57","v":0},{"$f":"'K20 - time schedule'!HH57","v":0},{"$f":"'K20 - time schedule'!HI57","v":0},{"$f":"'K20 - time schedule'!HJ57","v":0},{"$f":"'K20 - time schedule'!HK57","v":0},{"$f":"'K20 - time schedule'!HL57","v":0},{"$f":"'K20 - time schedule'!HM57","v":0},{"$f":"'K20 - time schedule'!HN57","v":0},{"$f":"'K20 - time schedule'!HO57","v":0},{"$f":"'K20 - time schedule'!HP57","v":0},{"$f":"'K20 - time schedule'!HQ57","v":0},{"$f":"'K20 - time schedule'!HR57","v":0},{"$f":"'K20 - time schedule'!HS57","v":0},{"$f":"'K20 - time schedule'!HT57","v":0},{"$f":"'K20 - time schedule'!HU57","v":0},{"$f":"'K20 - time schedule'!HV57","v":0},{"$f":"'K20 - time schedule'!HW57","v":0},{"$f":"'K20 - time schedule'!HX57","v":0},{"$f":"'K20 - time schedule'!HY57","v":0},{"$f":"'K20 - time schedule'!HZ57","v":0},{"$f":"'K20 - time schedule'!IA57","v":0},{"$f":"'K20 - time schedule'!IB57","v":0},{"$f":"'K20 - time schedule'!IC57","v":0},{"$f":"'K20 - time schedule'!ID57","v":0},{"$f":"'K20 - time schedule'!IE57","v":0},{"$f":"'K20 - time schedule'!IF57","v":0},{"$f":"'K20 - time schedule'!IG57","v":0},{"$f":"'K20 - time schedule'!IH57","v":0},{"$f":"'K20 - time schedule'!II57","v":0},{"$f":"'K20 - time schedule'!IJ57","v":0},{"$f":"'K20 - time schedule'!IK57","v":0},{"$f":"'K20 - time schedule'!IL57","v":0},{"$f":"'K20 - time schedule'!IM57","v":0},{"$f":"'K20 - time schedule'!IN57","v":0},{"$f":"'K20 - time schedule'!IO57","v":0},{"$f":"'K20 - time schedule'!IP57","v":0},{"$f":"'K20 - time schedule'!IQ57","v":0},{"$f":"'K20 - time schedule'!IR57","v":0},{"$f":"'K20 - time schedule'!IS57","v":0},{"$f":"'K20 - time schedule'!IT57","v":0},{"$f":"'K20 - time schedule'!IU57","v":0},{"$f":"'K20 - time schedule'!IV57","v":0},{"$f":"'K20 - time schedule'!IW57","v":0},{"$f":"'K20 - time schedule'!IX57","v":0},{"$f":"'K20 - time schedule'!IY57","v":0},{"$f":"'K20 - time schedule'!IZ57","v":0},{"$f":"'K20 - time schedule'!JA57","v":0},{"$f":"'K20 - time schedule'!JB57","v":0},{"$f":"'K20 - time schedule'!JC57","v":0},{"$f":"'K20 - time schedule'!JD57","v":0},{"$f":"'K20 - time schedule'!JE57","v":0},{"$f":"'K20 - time schedule'!JF57","v":0},{"$f":"'K20 - time schedule'!JG57","v":0},{"$f":"'K20 - time schedule'!JH57","v":0},{"$f":"'K20 - time schedule'!JI57","v":0},{"$f":"'K20 - time schedule'!JJ57","v":0},{"$f":"'K20 - time schedule'!JK57","v":0},{"$f":"'K20 - time schedule'!JL57","v":0},{"$f":"'K20 - time schedule'!JM57","v":0},{"$f":"'K20 - time schedule'!JN57","v":0},{"$f":"'K20 - time schedule'!JO57","v":0},{"$f":"'K20 - time schedule'!JP57","v":0},{"$f":"'K20 - time schedule'!JQ57","v":0},{"$f":"'K20 - time schedule'!JR57","v":0},{"$f":"'K20 - time schedule'!JS57","v":0},{"$f":"'K20 - time schedule'!JT57","v":0},{"$f":"'K20 - time schedule'!JU57","v":0},{"$f":"'K20 - time schedule'!JV57","v":0},{"$f":"'K20 - time schedule'!JW57","v":0},{"$f":"'K20 - time schedule'!JX57","v":0},{"$f":"'K20 - time schedule'!JY57","v":0},{"$f":"'K20 - time schedule'!JZ57","v":0},{"$f":"'K20 - time schedule'!KA57","v":0},{"$f":"'K20 - time schedule'!KB57","v":0},{"$f":"'K20 - time schedule'!KC57","v":0},{"$f":"'K20 - time schedule'!KD57","v":0},{"$f":"'K20 - time schedule'!KE57","v":0},{"$f":"'K20 - time schedule'!KF57","v":0},{"$f":"'K20 - time schedule'!KG57","v":0},{"$f":"'K20 - time schedule'!KH57","v":0},{"$f":"'K20 - time schedule'!KI57","v":0},{"$f":"'K20 - time schedule'!KJ57","v":0},{"$f":"'K20 - time schedule'!KK57","v":0},{"$f":"'K20 - time schedule'!KL57","v":0},{"$f":"'K20 - time schedule'!KM57","v":0},{"$f":"'K20 - time schedule'!KN57","v":0},{"$f":"'K20 - time schedule'!KO57","v":0},{"$f":"'K20 - time schedule'!KP57","v":0},{"$f":"'K20 - time schedule'!KQ57","v":0},{"$f":"'K20 - time schedule'!KR57","v":0},{"$f":"'K20 - time schedule'!KS57","v":0},{"$f":"'K20 - time schedule'!KT57","v":0}]
["Boiler room K80 - preliminary acceptance of the Work PAC","K80","EUR",{"$f":"'K80 - time schedule'!G60","v":0},{"$f":"'K80 - time schedule'!H60","v":0},{"$f":"'K80 - time schedule'!I60","v":0},{"$f":"'K80 - time schedule'!J60","v":0},{"$f":"'K80 - time schedule'!K60","v":0},{"$f":"'K80 - time schedule'!L60","v":0},{"$f":"'K80 - time schedule'!M60","v":0},{"$f":"'K80 - time schedule'!N60","v":0},{"$f":"'K80 - time schedule'!O60","v":0},{"$f":"'K80 - time schedule'!P60","v":0},{"$f":"'K80 - time schedule'!Q60","v":0},{"$f":"'K80 - time schedule'!R60","v":0},{"$f":"'K80 - time schedule'!S60","v":0},{"$f":"'K80 - time schedule'!T60","v":0},{"$f":"'K80 - time schedule'!U60","v":0},{"$f":"'K80 - time schedule'!V60","v":0},{"$f":"'K80 - time schedule'!W60","v":0},{"$f":"'K80 - time schedule'!X60","v":0},{"$f":"'K80 - time schedule'!Y60","v":0},{"$f":"'K80 - time schedule'!Z60","v":0},{"$f":"'K80 - time schedule'!AA60","v":0},{"$f":"'K80 - time schedule'!AB60","v":0},{"$f":"'K80 - time schedule'!AC60","v":0},{"$f":"'K80 - time schedule'!AD60","v":0},{"$f":"'K80 - time schedule'!AE60","v":0},{"$f":"'K80 - time schedule'!AF60","v":0},{"$f":"'K80 - time schedule'!AG60","v":0},{"$f":"'K80 - time schedule'!AH60","v":0},{"$f":"'K80 - time schedule'!AI60","v":0},{"$f":"'K80 - time schedule'!AJ60","v":0},{"$f":"'K80 - time schedule'!AK60","v":0},{"$f":"'K80 - time schedule'!AL60","v":0},{"$f":"'K80 - time schedule'!AM60","v":0},{"$f":"'K80 - time schedule'!AN60","v":0},{"$f":"'K80 - time schedule'!AO60","v":0},{"$f":"'K80 - time schedule'!AP60","v":0},{"$f":"'K80 - time schedule'!AQ60","v":0},{"$f":"'K80 - time schedule'!AR60","v":0},{"$f":"'K80 - time schedule'!AS60","v":0},{"$f":"'K80 - time schedule'!AT60","v":0},{"$f":"'K80 - time schedule'!AU60","v":0},{"$f":"'K80 - time schedule'!AV60","v":0},{"$f":"'K80 - time schedule'!AW60","v":0},{"$f":"'K80 - time schedule'!AX60","v":0},{"$f":"'K80 - time schedule'!AY60","v":0},{"$f":"'K80 - time schedule'!AZ60","v":0},{"$f":"'K80 - time schedule'!BA60","v":0},{"$f":"'K80 - time schedule'!BB60","v":0},{"$f":"'K80 - time schedule'!BC60","v":0},{"$f":"'K80 - time schedule'!BD60","v":0},{"$f":"'K80 - time schedule'!BE60","v":0},{"$f":"'K80 - time schedule'!BF60","v":0},{"$f":"'K80 - time schedule'!BG60","v":0},{"$f":"'K80 - time schedule'!BH60","v":0},{"$f":"'K80 - time schedule'!BI60","v":0},{"$f":"'K80 - time schedule'!BJ60","v":0},{"$f":"'K80 - time schedule'!BK60","v":0},{"$f":"'K80 - time schedule'!BL60","v":0},{"$f":"'K80 - time schedule'!BM60","v":0},{"$f":"'K80 - time schedule'!BN60","v":0},{"$f":"'K80 - time schedule'!BO60","v":0},{"$f":"'K80 - time schedule'!BP60","v":0},{"$f":"'K80 - time schedule'!BQ60","v":0},{"$f":"'K80 - time schedule'!BR60","v":0},{"$f":"'K80 - time schedule'!BS60","v":0},{"$f":"'K80 - time schedule'!BT60","v":0},{"$f":"'K80 - time schedule'!BU60","v":0},{"$f":"'K80 - time schedule'!BV60","v":0},{"$f":"'K80 - time schedule'!BW60","v":0},{"$f":"'K80 - time schedule'!BX60","v":0},{"$f":"'K80 - time schedule'!BY60","v":0},{"$f":"'K80 - time schedule'!BZ60","v":0},{"$f":"'K80 - time schedule'!CA60","v":0},{"$f":"'K80 - time schedule'!CB60","v":0},{"$f":"'K80 - time schedule'!CC60","v":0},{"$f":"'K80 - time schedule'!CD60","v":0},{"$f":"'K80 - time schedule'!CE60","v":0},{"$f":"'K80 - time schedule'!CF60","v":0},{"$f":"'K80 - time schedule'!CG60","v":0},{"$f":"'K80 - time schedule'!CH60","v":0},{"$f":"'K80 - time schedule'!CI60","v":0},{"$f":"'K80 - time schedule'!CJ60","v":0},{"$f":"'K80 - time schedule'!CK60","v":0},{"$f":"'K80 - time schedule'!CL60","v":0},{"$f":"'K80 - time schedule'!CM60","v":0},{"$f":"'K80 - time schedule'!CN60","v":0},{"$f":"'K80 - time schedule'!CO60","v":0},{"$f":"'K80 - time schedule'!CP60","v":0},{"$f":"'K80 - time schedule'!CQ60","v":0},{"$f":"'K80 - time schedule'!CR60","v":0},{"$f":"'K80 - time schedule'!CS60","v":0},{"$f":"'K80 - time schedule'!CT60","v":0},{"$f":"'K80 - time schedule'!CU60","v":0},{"$f":"'K80 - time schedule'!CV60","v":0},{"$f":"'K80 - time schedule'!CW60","v":0},{"$f":"'K80 - time schedule'!CX60","v":0},{"$f":"'K80 - time schedule'!CY60","v":0},{"$f":"'K80 - time schedule'!CZ60","v":0},{"$f":"'K80 - time schedule'!DA60","v":0},{"$f":"'K80 - time schedule'!DB60","v":0},{"$f":"'K80 - time schedule'!DC60","v":0},{"$f":"'K80 - time schedule'!DD60","v":0},{"$f":"'K80 - time schedule'!DE60","v":0},{"$f":"'K80 - time schedule'!DF60","v":0},{"$f":"'K80 - time schedule'!DG60","v":0},{"$f":"'K80 - time schedule'!DH60","v":0},{"$f":"'K80 - time schedule'!DI60","v":0},{"$f":"'K80 - time schedule'!DJ60","v":0},{"$f":"'K80 - time schedule'!DK60","v":0},{"$f":"'K80 - time schedule'!DL60","v":0},{"$f":"'K80 - time schedule'!DM60","v":0},{"$f":"'K80 - time schedule'!DN60","v":0},{"$f":"'K80 - time schedule'!DO60","v":0},{"$f":"'K80 - time schedule'!DP60","v":0},{"$f":"'K80 - time schedule'!DQ60","v":0},{"$f":"'K80 - time schedule'!DR60","v":0},{"$f":"'K80 - time schedule'!DS60","v":0},{"$f":"'K80 - time schedule'!DT60","v":0},{"$f":"'K80 - time schedule'!DU60","v":0},{"$f":"'K80 - time schedule'!DV60","v":0},{"$f":"'K80 - time schedule'!DW60","v":0},{"$f":"'K80 - time schedule'!DX60","v":0},{"$f":"'K80 - time schedule'!DY60","v":0},{"$f":"'K80 - time schedule'!DZ60","v":0},{"$f":"'K80 - time schedule'!EA60","v":0},{"$f":"'K80 - time schedule'!EB60","v":0},{"$f":"'K80 - time schedule'!EC60","v":0},{"$f":"'K80 - time schedule'!ED60","v":0},{"$f":"'K80 - time schedule'!EE60","v":0},{"$f":"'K80 - time schedule'!EF60","v":0},{"$f":"'K80 - time schedule'!EG60","v":0},{"$f":"'K80 - time schedule'!EH60","v":0},{"$f":"'K80 - time schedule'!EI60","v":0},{"$f":"'K80 - time schedule'!EJ60","v":0},{"$f":"'K80 - time schedule'!EK60","v":0},{"$f":"'K80 - time schedule'!EL60","v":0},{"$f":"'K80 - time schedule'!EM60","v":0},{"$f":"'K80 - time schedule'!EN60","v":0},{"$f":"'K80 - time schedule'!EO60","v":0},{"$f":"'K80 - time schedule'!EP60","v":0},{"$f":"'K80 - time schedule'!EQ60","v":0},{"$f":"'K80 - time schedule'!ER60","v":0},{"$f":"'K80 - time schedule'!ES60","v":0},{"$f":"'K80 - time schedule'!ET60","v":0},{"$f":"'K80 - time schedule'!EU60","v":0},{"$f":"'K80 - time schedule'!EV60","v":0},{"$f":"'K80 - time schedule'!EW60","v":0},{"$f":"'K80 - time schedule'!EX60","v":0},{"$f":"'K80 - time schedule'!EY60","v":0},{"$f":"'K80 - time schedule'!EZ60","v":0},{"$f":"'K80 - time schedule'!FA60","v":0},{"$f":"'K80 - time schedule'!FB60","v":0},{"$f":"'K80 - time schedule'!FC60","v":0},{"$f":"'K80 - time schedule'!FD60","v":0},{"$f":"'K80 - time schedule'!FE60","v":0},{"$f":"'K80 - time schedule'!FF60","v":0},{"$f":"'K80 - time schedule'!FG60","v":0},{"$f":"'K80 - time schedule'!FH60","v":0},{"$f":"'K80 - time schedule'!FI60","v":0},{"$f":"'K80 - time schedule'!FJ60","v":0},{"$f":"'K80 - time schedule'!FK60","v":0},{"$f":"'K80 - time schedule'!FL60","v":0},{"$f":"'K80 - time schedule'!FM60","v":0},{"$f":"'K80 - time schedule'!FN60","v":0},{"$f":"'K80 - time schedule'!FO60","v":0},{"$f":"'K80 - time schedule'!FP60","v":0},{"$f":"'K80 - time schedule'!FQ60","v":0},{"$f":"'K80 - time schedule'!FR60","v":0},{"$f":"'K80 - time schedule'!FS60","v":0},{"$f":"'K80 - time schedule'!FT60","v":0},{"$f":"'K80 - time schedule'!FU60","v":0},{"$f":"'K80 - time schedule'!FV60","v":0},{"$f":"'K80 - time schedule'!FW60","v":0},{"$f":"'K80 - time schedule'!FX60","v":0},{"$f":"'K80 - time schedule'!FY60","v":0},{"$f":"'K80 - time schedule'!FZ60","v":0},{"$f":"'K80 - time schedule'!GA60","v":0},{"$f":"'K80 - time schedule'!GB60","v":0},{"$f":"'K80 - time schedule'!GC60","v":0},{"$f":"'K80 - time schedule'!GD60","v":0},{"$f":"'K80 - time schedule'!GE60","v":0},{"$f":"'K80 - time schedule'!GF60","v":0},{"$f":"'K20 - time schedule'!GG58","v":0},{"$f":"'K20 - time schedule'!GH58","v":0},{"$f":"'K20 - time schedule'!GI58","v":0},{"$f":"'K20 - time schedule'!GJ58","v":0},{"$f":"'K20 - time schedule'!GK58","v":0},{"$f":"'K20 - time schedule'!GL58","v":0},{"$f":"'K20 - time schedule'!GM58","v":0},{"$f":"'K20 - time schedule'!GN58","v":0},{"$f":"'K20 - time schedule'!GO58","v":0},{"$f":"'K20 - time schedule'!GP58","v":0},{"$f":"'K20 - time schedule'!GQ58","v":0},{"$f":"'K20 - time schedule'!GR58","v":0},{"$f":"'K20 - time schedule'!GS58","v":0},{"$f":"'K20 - time schedule'!GT58","v":0},{"$f":"'K20 - time schedule'!GU58","v":0},{"$f":"'K20 - time schedule'!GV58","v":0},{"$f":"'K20 - time schedule'!GW58","v":0},{"$f":"'K20 - time schedule'!GX58","v":0},{"$f":"'K20 - time schedule'!GY58","v":0},{"$f":"'K20 - time schedule'!GZ58","v":0},{"$f":"'K20 - time schedule'!HA58","v":0},{"$f":"'K20 - time schedule'!HB58","v":0},{"$f":"'K20 - time schedule'!HC58","v":0},{"$f":"'K20 - time schedule'!HD58","v":0},{"$f":"'K20 - time schedule'!HE58","v":0},{"$f":"'K20 - time schedule'!HF58","v":0},{"$f":"'K20 - time schedule'!HG58","v":0},{"$f":"'K20 - time schedule'!HH58","v":0},{"$f":"'K20 - time schedule'!HI58","v":0},{"$f":"'K20 - time schedule'!HJ58","v":0},{"$f":"'K20 - time schedule'!HK58","v":0},{"$f":"'K20 - time schedule'!HL58","v":0},{"$f":"'K20 - time schedule'!HM58","v":0},{"$f":"'K20 - time schedule'!HN58","v":0},{"$f":"'K20 - time schedule'!HO58","v":0},{"$f":"'K20 - time schedule'!HP58","v":0},{"$f":"'K20 - time schedule'!HQ58","v":0},{"$f":"'K20 - time schedule'!HR58","v":0},{"$f":"'K20 - time schedule'!HS58","v":0},{"$f":"'K20 - time schedule'!HT58","v":0},{"$f":"'K20 - time schedule'!HU58","v":0},{"$f":"'K20 - time schedule'!HV58","v":0},{"$f":"'K20 - time schedule'!HW58","v":0},{"$f":"'K20 - time schedule'!HX58","v":0},{"$f":"'K20 - time schedule'!HY58","v":0},{"$f":"'K20 - time schedule'!HZ58","v":0},{"$f":"'K20 - time schedule'!IA58","v":0},{"$f":"'K20 - time schedule'!IB58","v":0},{"$f":"'K20 - time schedule'!IC58","v":0},{"$f":"'K20 - time schedule'!ID58","v":0},{"$f":"'K20 - time schedule'!IE58","v":0},{"$f":"'K20 - time schedule'!IF58","v":0},{"$f":"'K20 - time schedule'!IG58","v":0},{"$f":"'K20 - time schedule'!IH58","v":0},{"$f":"'K20 - time schedule'!II58","v":0},{"$f":"'K20 - time schedule'!IJ58","v":0},{"$f":"'K20 - time schedule'!IK58","v":0},{"$f":"'K20 - time schedule'!IL58","v":0},{"$f":"'K20 - time schedule'!IM58","v":0},{"$f":"'K20 - time schedule'!IN58","v":0},{"$f":"'K20 - time schedule'!IO58","v":0},{"$f":"'K20 - time schedule'!IP58","v":0},{"$f":"'K20 - time schedule'!IQ58","v":0},{"$f":"'K20 - time schedule'!IR58","v":0},{"$f":"'K20 - time schedule'!IS58","v":0},{"$f":"'K20 - time schedule'!IT58","v":0},{"$f":"'K20 - time schedule'!IU58","v":0},{"$f":"'K20 - time schedule'!IV58","v":0},{"$f":"'K20 - time schedule'!IW58","v":0},{"$f":"'K20 - time schedule'!IX58","v":0},{"$f":"'K20 - time schedule'!IY58","v":0},{"$f":"'K20 - time schedule'!IZ58","v":0},{"$f":"'K20 - time schedule'!JA58","v":0},{"$f":"'K20 - time schedule'!JB58","v":0},{"$f":"'K20 - time schedule'!JC58","v":0},{"$f":"'K20 - time schedule'!JD58","v":0},{"$f":"'K20 - time schedule'!JE58","v":0},{"$f":"'K20 - time schedule'!JF58","v":0},{"$f":"'K20 - time schedule'!JG58","v":0},{"$f":"'K20 - time schedule'!JH58","v":0},{"$f":"'K20 - time schedule'!JI58","v":0},{"$f":"'K20 - time schedule'!JJ58","v":0},{"$f":"'K20 - time schedule'!JK58","v":0},{"$f":"'K20 - time schedule'!JL58","v":0},{"$f":"'K20 - time schedule'!JM58","v":0},{"$f":"'K20 - time schedule'!JN58","v":0},{"$f":"'K20 - time schedule'!JO58","v":0},{"$f":"'K20 - time schedule'!JP58","v":0},{"$f":"'K20 - time schedule'!JQ58","v":0},{"$f":"'K20 - time schedule'!JR58","v":0},{"$f":"'K20 - time schedule'!JS58","v":0},{"$f":"'K20 - time schedule'!JT58","v":0},{"$f":"'K20 - time schedule'!JU58","v":0},{"$f":"'K20 - time schedule'!JV58","v":0},{"$f":"'K20 - time schedule'!JW58","v":0},{"$f":"'K20 - time schedule'!JX58","v":0},{"$f":"'K20 - time schedule'!JY58","v":0},{"$f":"'K20 - time schedule'!JZ58","v":0},{"$f":"'K20 - time schedule'!KA58","v":0},{"$f":"'K20 - time schedule'!KB58","v":0},{"$f":"'K20 - time schedule'!KC58","v":0},{"$f":"'K20 - time schedule'!KD58","v":0},{"$f":"'K20 - time schedule'!KE58","v":0},{"$f":"'K20 - time schedule'!KF58","v":0},{"$f":"'K20 - time schedule'!KG58","v":0},{"$f":"'K20 - time schedule'!KH58","v":0},{"$f":"'K20 - time schedule'!KI58","v":0},{"$f":"'K20 - time schedule'!KJ58","v":0},{"$f":"'K20 - time schedule'!KK58","v":0},{"$f":"'K20 - time schedule'!KL58","v":0},{"$f":"'K20 - time schedule'!KM58","v":0},{"$f":"'K20 - time schedule'!KN58","v":0},{"$f":"'K20 - time schedule'!KO58","v":0},{"$f":"'K20 - time schedule'!KP58","v":0},{"$f":"'K20 - time schedule'!KQ58","v":0},{"$f":"'K20 - time schedule'!KR58","v":0},{"$f":"'K20 - time schedule'!KS58","v":0},{"$f":"'K20 - time schedule'!KT58","v":0}]
["Boiler room K80 - guarantee test B","K80","EUR",{"$f":"'K80 - time schedule'!G62","v":0},{"$f":"'K80 - time schedule'!H62","v":0},{"$f":"'K80 - time schedule'!I62","v":0},{"$f":"'K80 - time schedule'!J62","v":0},{"$f":"'K80 - time schedule'!K62","v":0},{"$f":"'K80 - time schedule'!L62","v":0},{"$f":"'K80 - time schedule'!M62","v":0},{"$f":"'K80 - time schedule'!N62","v":0},{"$f":"'K80 - time schedule'!O62","v":0},{"$f":"'K80 - time schedule'!P62","v":0},{"$f":"'K80 - time schedule'!Q62","v":0},{"$f":"'K80 - time schedule'!R62","v":0},{"$f":"'K80 - time schedule'!S62","v":0},{"$f":"'K80 - time schedule'!T62","v":0},{"$f":"'K80 - time schedule'!U62","v":0},{"$f":"'K80 - time schedule'!V62","v":0},{"$f":"'K80 - time schedule'!W62","v":0},{"$f":"'K80 - time schedule'!X62","v":0},{"$f":"'K80 - time schedule'!Y62","v":0},{"$f":"'K80 - time schedule'!Z62","v":0},{"$f":"'K80 - time schedule'!AA62","v":0},{"$f":"'K80 - time schedule'!AB62","v":0},{"$f":"'K80 - time schedule'!AC62","v":0},{"$f":"'K80 - time schedule'!AD62","v":0},{"$f":"'K80 - time schedule'!AE62","v":0},{"$f":"'K80 - time schedule'!AF62","v":0},{"$f":"'K80 - time schedule'!AG62","v":0},{"$f":"'K80 - time schedule'!AH62","v":0},{"$f":"'K80 - time schedule'!AI62","v":0},{"$f":"'K80 - time schedule'!AJ62","v":0},{"$f":"'K80 - time schedule'!AK62","v":0},{"$f":"'K80 - time schedule'!AL62","v":0},{"$f":"'K80 - time schedule'!AM62","v":0},{"$f":"'K80 - time schedule'!AN62","v":0},{"$f":"'K80 - time schedule'!AO62","v":0},{"$f":"'K80 - time schedule'!AP62","v":0},{"$f":"'K80 - time schedule'!AQ62","v":0},{"$f":"'K80 - time schedule'!AR62","v":0},{"$f":"'K80 - time schedule'!AS62","v":0},{"$f":"'K80 - time schedule'!AT62","v":0},{"$f":"'K80 - time schedule'!AU62","v":0},{"$f":"'K80 - time schedule'!AV62","v":0},{"$f":"'K80 - time schedule'!AW62","v":0},{"$f":"'K80 - time schedule'!AX62","v":0},{"$f":"'K80 - time schedule'!AY62","v":0},{"$f":"'K80 - time schedule'!AZ62","v":0},{"$f":"'K80 - time schedule'!BA62","v":0},{"$f":"'K80 - time schedule'!BB62","v":0},{"$f":"'K80 - time schedule'!BC62","v":0},{"$f":"'K80 - time schedule'!BD62","v":0},{"$f":"'K80 - time schedule'!BE62","v":0},{"$f":"'K80 - time schedule'!BF62","v":0},{"$f":"'K80 - time schedule'!BG62","v":0},{"$f":"'K80 - time schedule'!BH62","v":0},{"$f":"'K80 - time schedule'!BI62","v":0},{"$f":"'K80 - time schedule'!BJ62","v":0},{"$f":"'K80 - time schedule'!BK62","v":0},{"$f":"'K80 - time schedule'!BL62","v":0},{"$f":"'K80 - time schedule'!BM62","v":0},{"$f":"'K80 - time schedule'!BN62","v":0},{"$f":"'K80 - time schedule'!BO62","v":0},{"$f":"'K80 - time schedule'!BP62","v":0},{"$f":"'K80 - time schedule'!BQ62","v":0},{"$f":"'K80 - time schedule'!BR62","v":0},{"$f":"'K80 - time schedule'!BS62","v":0},{"$f":"'K80 - time schedule'!BT62","v":0},{"$f":"'K80 - time schedule'!BU62","v":0},{"$f":"'K80 - time schedule'!BV62","v":0},{"$f":"'K80 - time schedule'!BW62","v":0},{"$f":"'K80 - time schedule'!BX62","v":0},{"$f":"'K80 - time schedule'!BY62","v":0},{"$f":"'K80 - time schedule'!BZ62","v":0},{"$f":"'K80 - time schedule'!CA62","v":0},{"$f":"'K80 - time schedule'!CB62","v":0},{"$f":"'K80 - time schedule'!CC62","v":0},{"$f":"'K80 - time schedule'!CD62","v":0},{"$f":"'K80 - time schedule'!CE62","v":0},{"$f":"'K80 - time schedule'!CF62","v":0},{"$f":"'K80 - time schedule'!CG62","v":0},{"$f":"'K80 - time schedule'!CH62","v":0},{"$f":"'K80 - time schedule'!CI62","v":0},{"$f":"'K80 - time schedule'!CJ62","v":0},{"$f":"'K80 - time schedule'!CK62","v":0},{"$f":"'K80 - time schedule'!CL62","v":0},{"$f":"'K80 - time schedule'!CM62","v":0},{"$f":"'K80 - time schedule'!CN62","v":0},{"$f":"'K80 - time schedule'!CO62","v":0},{"$f":"'K80 - time schedule'!CP62","v":0},{"$f":"'K80 - time schedule'!CQ62","v":0},{"$f":"'K80 - time schedule'!CR62","v":0},{"$f":"'K80 - time schedule'!CS62","v":0},{"$f":"'K80 - time schedule'!CT62","v":0},{"$f":"'K80 - time schedule'!CU62","v":0},{"$f":"'K80 - time schedule'!CV62","v":0},{"$f":"'K80 - time schedule'!CW62","v":0},{"$f":"'K80 - time schedule'!CX62","v":0},{"$f":"'K80 - time schedule'!CY62","v":0},{"$f":"'K80 - time schedule'!CZ62","v":0},{"$f":"'K80 - time schedule'!DA62","v":0},{"$f":"'K80 - time schedule'!DB62","v":0},{"$f":"'K80 - time schedule'!DC62","v":0},{"$f":"'K80 - time schedule'!DD62","v":0},{"$f":"'K80 - time schedule'!DE62","v":0},{"$f":"'K80 - time schedule'!DF62","v":0},{"$f":"'K80 - time schedule'!DG62","v":0},{"$f":"'K80 - time schedule'!DH62","v":0},{"$f":"'K80 - time schedule'!DI62","v":0},{"$f":"'K80 - time schedule'!DJ62","v":0},{"$f":"'K80 - time schedule'!DK62","v":0},{"$f":"'K80 - time schedule'!DL62","v":0},{"$f":"'K80 - time schedule'!DM62","v":0},{"$f":"'K80 - time schedule'!DN62","v":0},{"$f":"'K80 - time schedule'!DO62","v":0},{"$f":"'K80 - time schedule'!DP62","v":0},{"$f":"'K80 - time schedule'!DQ62","v":0},{"$f":"'K80 - time schedule'!DR62","v":0},{"$f":"'K80 - time schedule'!DS62","v":0},{"$f":"'K80 - time schedule'!DT62","v":0},{"$f":"'K80 - time schedule'!DU62","v":0},{"$f":"'K80 - time schedule'!DV62","v":0},{"$f":"'K80 - time schedule'!DW62","v":0},{"$f":"'K80 - time schedule'!DX62","v":0},{"$f":"'K80 - time schedule'!DY62","v":0},{"$f":"'K80 - time schedule'!DZ62","v":0},{"$f":"'K80 - time schedule'!EA62","v":0},{"$f":"'K80 - time schedule'!EB62","v":0},{"$f":"'K80 - time schedule'!EC62","v":0},{"$f":"'K80 - time schedule'!ED62","v":0},{"$f":"'K80 - time schedule'!EE62","v":0},{"$f":"'K80 - time schedule'!EF62","v":0},{"$f":"'K80 - time schedule'!EG62","v":0},{"$f":"'K80 - time schedule'!EH62","v":0},{"$f":"'K80 - time schedule'!EI62","v":0},{"$f":"'K80 - time schedule'!EJ62","v":0},{"$f":"'K80 - time schedule'!EK62","v":0},{"$f":"'K80 - time schedule'!EL62","v":0},{"$f":"'K80 - time schedule'!EM62","v":0},{"$f":"'K80 - time schedule'!EN62","v":0},{"$f":"'K80 - time schedule'!EO62","v":0},{"$f":"'K80 - time schedule'!EP62","v":0},{"$f":"'K80 - time schedule'!EQ62","v":0},{"$f":"'K80 - time schedule'!ER62","v":0},{"$f":"'K80 - time schedule'!ES62","v":0},{"$f":"'K80 - time schedule'!ET62","v":0},{"$f":"'K80 - time schedule'!EU62","v":0},{"$f":"'K80 - time schedule'!EV62","v":0},{"$f":"'K80 - time schedule'!EW62","v":0},{"$f":"'K80 - time schedule'!EX62","v":0},{"$f":"'K80 - time schedule'!EY62","v":0},{"$f":"'K80 - time schedule'!EZ62","v":0},{"$f":"'K80 - time schedule'!FA62","v":0},{"$f":"'K80 - time schedule'!FB62","v":0},{"$f":"'K80 - time schedule'!FC62","v":0},{"$f":"'K80 - time schedule'!FD62","v":0},{"$f":"'K80 - time schedule'!FE62","v":0},{"$f":"'K80 - time schedule'!FF62","v":0},{"$f":"'K80 - time schedule'!FG62","v":0},{"$f":"'K80 - time schedule'!FH62","v":0},{"$f":"'K80 - time schedule'!FI62","v":0},{"$f":"'K80 - time schedule'!FJ62","v":0},{"$f":"'K80 - time schedule'!FK62","v":0},{"$f":"'K80 - time schedule'!FL62","v":0},{"$f":"'K80 - time schedule'!FM62","v":0},{"$f":"'K80 - time schedule'!FN62","v":0},{"$f":"'K80 - time schedule'!FO62","v":0},{"$f":"'K80 - time schedule'!FP62","v":0},{"$f":"'K80 - time schedule'!FQ62","v":0},{"$f":"'K80 - time schedule'!FR62","v":0},{"$f":"'K80 - time schedule'!FS62","v":0},{"$f":"'K80 - time schedule'!FT62","v":0},{"$f":"'K80 - time schedule'!FU62","v":0},{"$f":"'K80 - time schedule'!FV62","v":0},{"$f":"'K80 - time schedule'!FW62","v":0},{"$f":"'K80 - time schedule'!FX62","v":0},{"$f":"'K80 - time schedule'!FY62","v":0},{"$f":"'K80 - time schedule'!FZ62","v":0},{"$f":"'K80 - time schedule'!GA62","v":0},{"$f":"'K80 - time schedule'!GB62","v":0},{"$f":"'K80 - time schedule'!GC62","v":0},{"$f":"'K80 - time schedule'!GD62","v":0},{"$f":"'K80 - time schedule'!GE62","v":0},{"$f":"'K80 - time schedule'!GF62","v":0},{"$f":"'K20 - time schedule'!GG59","v":0},{"$f":"'K20 - time schedule'!GH59","v":0},{"$f":"'K20 - time schedule'!GI59","v":0},{"$f":"'K20 - time schedule'!GJ59","v":0},{"$f":"'K20 - time schedule'!GK59","v":0},{"$f":"'K20 - time schedule'!GL59","v":0},{"$f":"'K20 - time schedule'!GM59","v":0},{"$f":"'K20 - time schedule'!GN59","v":0},{"$f":"'K20 - time schedule'!GO59","v":0},{"$f":"'K20 - time schedule'!GP59","v":0},{"$f":"'K20 - time schedule'!GQ59","v":0},{"$f":"'K20 - time schedule'!GR59","v":0},{"$f":"'K20 - time schedule'!GS59","v":0},{"$f":"'K20 - time schedule'!GT59","v":0},{"$f":"'K20 - time schedule'!GU59","v":0},{"$f":"'K20 - time schedule'!GV59","v":0},{"$f":"'K20 - time schedule'!GW59","v":0},{"$f":"'K20 - time schedule'!GX59","v":0},{"$f":"'K20 - time schedule'!GY59","v":0},{"$f":"'K20 - time schedule'!GZ59","v":0},{"$f":"'K20 - time schedule'!HA59","v":0},{"$f":"'K20 - time schedule'!HB59","v":0},{"$f":"'K20 - time schedule'!HC59","v":0},{"$f":"'K20 - time schedule'!HD59","v":0},{"$f":"'K20 - time schedule'!HE59","v":0},{"$f":"'K20 - time schedule'!HF59","v":0},{"$f":"'K20 - time schedule'!HG59","v":0},{"$f":"'K20 - time schedule'!HH59","v":0},{"$f":"'K20 - time schedule'!HI59","v":0},{"$f":"'K20 - time schedule'!HJ59","v":0},{"$f":"'K20 - time schedule'!HK59","v":0},{"$f":"'K20 - time schedule'!HL59","v":0},{"$f":"'K20 - time schedule'!HM59","v":0},{"$f":"'K20 - time schedule'!HN59","v":0},{"$f":"'K20 - time schedule'!HO59","v":0},{"$f":"'K20 - time schedule'!HP59","v":0},{"$f":"'K20 - time schedule'!HQ59","v":0},{"$f":"'K20 - time schedule'!HR59","v":0},{"$f":"'K20 - time schedule'!HS59","v":0},{"$f":"'K20 - time schedule'!HT59","v":0},{"$f":"'K20 - time schedule'!HU59","v":0},{"$f":"'K20 - time schedule'!HV59","v":0},{"$f":"'K20 - time schedule'!HW59","v":0},{"$f":"'K20 - time schedule'!HX59","v":0},{"$f":"'K20 - time schedule'!HY59","v":0},{"$f":"'K20 - time schedule'!HZ59","v":0},{"$f":"'K20 - time schedule'!IA59","v":0},{"$f":"'K20 - time schedule'!IB59","v":0},{"$f":"'K20 - time schedule'!IC59","v":0},{"$f":"'K20 - time schedule'!ID59","v":0},{"$f":"'K20 - time schedule'!IE59","v":0},{"$f":"'K20 - time schedule'!IF59","v":0},{"$f":"'K20 - time schedule'!IG59","v":0},{"$f":"'K20 - time schedule'!IH59","v":0},{"$f":"'K20 - time schedule'!II59","v":0},{"$f":"'K20 - time schedule'!IJ59","v":0},{"$f":"'K20 - time schedule'!IK59","v":0},{"$f":"'K20 - time schedule'!IL59","v":0},{"$f":"'K20 - time schedule'!IM59","v":0},{"$f":"'K20 - time schedule'!IN59","v":0},{"$f":"'K20 - time schedule'!IO59","v":0},{"$f":"'K20 - time schedule'!IP59","v":0},{"$f":"'K20 - time schedule'!IQ59","v":0},{"$f":"'K20 - time schedule'!IR59","v":0},{"$f":"'K20 - time schedule'!IS59","v":0},{"$f":"'K20 - time schedule'!IT59","v":0},{"$f":"'K20 - time schedule'!IU59","v":0},{"$f":"'K20 - time schedule'!IV59","v":0},{"$f":"'K20 - time schedule'!IW59","v":0},{"$f":"'K20 - time schedule'!IX59","v":0},{"$f":"'K20 - time schedule'!IY59","v":0},{"$f":"'K20 - time schedule'!IZ59","v":0},{"$f":"'K20 - time schedule'!JA59","v":0},{"$f":"'K20 - time schedule'!JB59","v":0},{"$f":"'K20 - time schedule'!JC59","v":0},{"$f":"'K20 - time schedule'!JD59","v":0},{"$f":"'K20 - time schedule'!JE59","v":0},{"$f":"'K20 - time schedule'!JF59","v":0},{"$f":"'K20 - time schedule'!JG59","v":0},{"$f":"'K20 - time schedule'!JH59","v":0},{"$f":"'K20 - time schedule'!JI59","v":0},{"$f":"'K20 - time schedule'!JJ59","v":0},{"$f":"'K20 - time schedule'!JK59","v":0},{"$f":"'K20 - time schedule'!JL59","v":0},{"$f":"'K20 - time schedule'!JM59","v":0},{"$f":"'K20 - time schedule'!JN59","v":0},{"$f":"'K20 - time schedule'!JO59","v":0},{"$f":"'K20 - time schedule'!JP59","v":0},{"$f":"'K20 - time schedule'!JQ59","v":0},{"$f":"'K20 - time schedule'!JR59","v":0},{"$f":"'K20 - time schedule'!JS59","v":0},{"$f":"'K20 - time schedule'!JT59","v":0},{"$f":"'K20 - time schedule'!JU59","v":0},{"$f":"'K20 - time schedule'!JV59","v":0},{"$f":"'K20 - time schedule'!JW59","v":0},{"$f":"'K20 - time schedule'!JX59","v":0},{"$f":"'K20 - time schedule'!JY59","v":0},{"$f":"'K20 - time schedule'!JZ59","v":0},{"$f":"'K20 - time schedule'!KA59","v":0},{"$f":"'K20 - time schedule'!KB59","v":0},{"$f":"'K20 - time schedule'!KC59","v":0},{"$f":"'K20 - time schedule'!KD59","v":0},{"$f":"'K20 - time schedule'!KE59","v":0},{"$f":"'K20 - time schedule'!KF59","v":0},{"$f":"'K20 - time schedule'!KG59","v":0},{"$f":"'K20 - time schedule'!KH59","v":0},{"$f":"'K20 - time schedule'!KI59","v":0},{"$f":"'K20 - time schedule'!KJ59","v":0},{"$f":"'K20 - time schedule'!KK59","v":0},{"$f":"'K20 - time schedule'!KL59","v":0},{"$f":"'K20 - time schedule'!KM59","v":0},{"$f":"'K20 - time schedule'!KN59","v":0},{"$f":"'K20 - time schedule'!KO59","v":0},{"$f":"'K20 - time schedule'!KP59","v":0},{"$f":"'K20 - time schedule'!KQ59","v":0},{"$f":"'K20 - time schedule'!KR59","v":0},{"$f":"'K20 - time schedule'!KS59","v":0},{"$f":"'K20 - time schedule'!KT59","v":0}]
["Boiler room K80 - final acceptance of the Work FAC","K80","EUR",{"$f":"'K80 - time schedule'!G64","v":0},{"$f":"'K80 - time schedule'!H64","v":0},{"$f":"'K80 - time schedule'!I64","v":0},{"$f":"'K80 - time schedule'!J64","v":0},{"$f":"'K80 - time schedule'!K64","v":0},{"$f":"'K80 - time schedule'!L64","v":0},{"$f":"'K80 - time schedule'!M64","v":0},{"$f":"'K80 - time schedule'!N64","v":0},{"$f":"'K80 - time schedule'!O64","v":0},{"$f":"'K80 - time schedule'!P64","v":0},{"$f":"'K80 - time schedule'!Q64","v":0},{"$f":"'K80 - time schedule'!R64","v":0},{"$f":"'K80 - time schedule'!S64","v":0},{"$f":"'K80 - time schedule'!T64","v":0},{"$f":"'K80 - time schedule'!U64","v":0},{"$f":"'K80 - time schedule'!V64","v":0},{"$f":"'K80 - time schedule'!W64","v":0},{"$f":"'K80 - time schedule'!X64","v":0},{"$f":"'K80 - time schedule'!Y64","v":0},{"$f":"'K80 - time schedule'!Z64","v":0},{"$f":"'K80 - time schedule'!AA64","v":0},{"$f":"'K80 - time schedule'!AB64","v":0},{"$f":"'K80 - time schedule'!AC64","v":0},{"$f":"'K80 - time schedule'!AD64","v":0},{"$f":"'K80 - time schedule'!AE64","v":0},{"$f":"'K80 - time schedule'!AF64","v":0},{"$f":"'K80 - time schedule'!AG64","v":0},{"$f":"'K80 - time schedule'!AH64","v":0},{"$f":"'K80 - time schedule'!AI64","v":0},{"$f":"'K80 - time schedule'!AJ64","v":0},{"$f":"'K80 - time schedule'!AK64","v":0},{"$f":"'K80 - time schedule'!AL64","v":0},{"$f":"'K80 - time schedule'!AM64","v":0},{"$f":"'K80 - time schedule'!AN64","v":0},{"$f":"'K80 - time schedule'!AO64","v":0},{"$f":"'K80 - time schedule'!AP64","v":0},{"$f":"'K80 - time schedule'!AQ64","v":0},{"$f":"'K80 - time schedule'!AR64","v":0},{"$f":"'K80 - time schedule'!AS64","v":0},{"$f":"'K80 - time schedule'!AT64","v":0},{"$f":"'K80 - time schedule'!AU64","v":0},{"$f":"'K80 - time schedule'!AV64","v":0},{"$f":"'K80 - time schedule'!AW64","v":0},{"$f":"'K80 - time schedule'!AX64","v":0},{"$f":"'K80 - time schedule'!AY64","v":0},{"$f":"'K80 - time schedule'!AZ64","v":0},{"$f":"'K80 - time schedule'!BA64","v":0},{"$f":"'K80 - time schedule'!BB64","v":0},{"$f":"'K80 - time schedule'!BC64","v":0},{"$f":"'K80 - time schedule'!BD64","v":0},{"$f":"'K80 - time schedule'!BE64","v":0},{"$f":"'K80 - time schedule'!BF64","v":0},{"$f":"'K80 - time schedule'!BG64","v":0},{"$f":"'K80 - time schedule'!BH64","v":0},{"$f":"'K80 - time schedule'!BI64","v":0},{"$f":"'K80 - time schedule'!BJ64","v":0},{"$f":"'K80 - time schedule'!BK64","v":0},{"$f":"'K80 - time schedule'!BL64","v":0},{"$f":"'K80 - time schedule'!BM64","v":0},{"$f":"'K80 - time schedule'!BN64","v":0},{"$f":"'K80 - time schedule'!BO64","v":0},{"$f":"'K80 - time schedule'!BP64","v":0},{"$f":"'K80 - time schedule'!BQ64","v":0},{"$f":"'K80 - time schedule'!BR64","v":0},{"$f":"'K80 - time schedule'!BS64","v":0},{"$f":"'K80 - time schedule'!BT64","v":0},{"$f":"'K80 - time schedule'!BU64","v":0},{"$f":"'K80 - time schedule'!BV64","v":0},{"$f":"'K80 - time schedule'!BW64","v":0},{"$f":"'K80 - time schedule'!BX64","v":0},{"$f":"'K80 - time schedule'!BY64","v":0},{"$f":"'K80 - time schedule'!BZ64","v":0},{"$f":"'K80 - time schedule'!CA64","v":0},{"$f":"'K80 - time schedule'!CB64","v":0},{"$f":"'K80 - time schedule'!CC64","v":0},{"$f":"'K80 - time schedule'!CD64","v":0},{"$f":"'K80 - time schedule'!CE64","v":0},{"$f":"'K80 - time schedule'!CF64","v":0},{"$f":"'K80 - time schedule'!CG64","v":0},{"$f":"'K80 - time schedule'!CH64","v":0},{"$f":"'K80 - time schedule'!CI64","v":0},{"$f":"'K80 - time schedule'!CJ64","v":0},{"$f":"'K80 - time schedule'!CK64","v":0},{"$f":"'K80 - time schedule'!CL64","v":0},{"$f":"'K80 - time schedule'!CM64","v":0},{"$f":"'K80 - time schedule'!CN64","v":0},{"$f":"'K80 - time schedule'!CO64","v":0},{"$f":"'K80 - time schedule'!CP64","v":0},{"$f":"'K80 - time schedule'!CQ64","v":0},{"$f":"'K80 - time schedule'!CR64","v":0},{"$f":"'K80 - time schedule'!CS64","v":0},{"$f":"'K80 - time schedule'!CT64","v":0},{"$f":"'K80 - time schedule'!CU64","v":0},{"$f":"'K80 - time schedule'!CV64","v":0},{"$f":"'K80 - time schedule'!CW64","v":0},{"$f":"'K80 - time schedule'!CX64","v":0},{"$f":"'K80 - time schedule'!CY64","v":0},{"$f":"'K80 - time schedule'!CZ64","v":0},{"$f":"'K80 - time schedule'!DA64","v":0},{"$f":"'K80 - time schedule'!DB64","v":0},{"$f":"'K80 - time schedule'!DC64","v":0},{"$f":"'K80 - time schedule'!DD64","v":0},{"$f":"'K80 - time schedule'!DE64","v":0},{"$f":"'K80 - time schedule'!DF64","v":0},{"$f":"'K80 - time schedule'!DG64","v":0},{"$f":"'K80 - time schedule'!DH64","v":0},{"$f":"'K80 - time schedule'!DI64","v":0},{"$f":"'K80 - time schedule'!DJ64","v":0},{"$f":"'K80 - time schedule'!DK64","v":0},{"$f":"'K80 - time schedule'!DL64","v":0},{"$f":"'K80 - time schedule'!DM64","v":0},{"$f":"'K80 - time schedule'!DN64","v":0},{"$f":"'K80 - time schedule'!DO64","v":0},{"$f":"'K80 - time schedule'!DP64","v":0},{"$f":"'K80 - time schedule'!DQ64","v":0},{"$f":"'K80 - time schedule'!DR64","v":0},{"$f":"'K80 - time schedule'!DS64","v":0},{"$f":"'K80 - time schedule'!DT64","v":0},{"$f":"'K80 - time schedule'!DU64","v":0},{"$f":"'K80 - time schedule'!DV64","v":0},{"$f":"'K80 - time schedule'!DW64","v":0},{"$f":"'K80 - time schedule'!DX64","v":0},{"$f":"'K80 - time schedule'!DY64","v":0},{"$f":"'K80 - time schedule'!DZ64","v":0},{"$f":"'K80 - time schedule'!EA64","v":0},{"$f":"'K80 - time schedule'!EB64","v":0},{"$f":"'K80 - time schedule'!EC64","v":0},{"$f":"'K80 - time schedule'!ED64","v":0},{"$f":"'K80 - time schedule'!EE64","v":0},{"$f":"'K80 - time schedule'!EF64","v":0},{"$f":"'K80 - time schedule'!EG64","v":0},{"$f":"'K80 - time schedule'!EH64","v":0},{"$f":"'K80 - time schedule'!EI64","v":0},{"$f":"'K80 - time schedule'!EJ64","v":0},{"$f":"'K80 - time schedule'!EK64","v":0},{"$f":"'K80 - time schedule'!EL64","v":0},{"$f":"'K80 - time schedule'!EM64","v":0},{"$f":"'K80 - time schedule'!EN64","v":0},{"$f":"'K80 - time schedule'!EO64","v":0},{"$f":"'K80 - time schedule'!EP64","v":0},{"$f":"'K80 - time schedule'!EQ64","v":0},{"$f":"'K80 - time schedule'!ER64","v":0},{"$f":"'K80 - time schedule'!ES64","v":0},{"$f":"'K80 - time schedule'!ET64","v":0},{"$f":"'K80 - time schedule'!EU64","v":0},{"$f":"'K80 - time schedule'!EV64","v":0},{"$f":"'K80 - time schedule'!EW64","v":0},{"$f":"'K80 - time schedule'!EX64","v":0},{"$f":"'K80 - time schedule'!EY64","v":0},{"$f":"'K80 - time schedule'!EZ64","v":0},{"$f":"'K80 - time schedule'!FA64","v":0},{"$f":"'K80 - time schedule'!FB64","v":0},{"$f":"'K80 - time schedule'!FC64","v":0},{"$f":"'K80 - time schedule'!FD64","v":0},{"$f":"'K80 - time schedule'!FE64","v":0},{"$f":"'K80 - time schedule'!FF64","v":0},{"$f":"'K80 - time schedule'!FG64","v":0},{"$f":"'K80 - time schedule'!FH64","v":0},{"$f":"'K80 - time schedule'!FI64","v":0},{"$f":"'K80 - time schedule'!FJ64","v":0},{"$f":"'K80 - time schedule'!FK64","v":0},{"$f":"'K80 - time schedule'!FL64","v":0},{"$f":"'K80 - time schedule'!FM64","v":0},{"$f":"'K80 - time schedule'!FN64","v":0},{"$f":"'K80 - time schedule'!FO64","v":0},{"$f":"'K80 - time schedule'!FP64","v":0},{"$f":"'K80 - time schedule'!FQ64","v":0},{"$f":"'K80 - time schedule'!FR64","v":0},{"$f":"'K80 - time schedule'!FS64","v":0},{"$f":"'K80 - time schedule'!FT64","v":0},{"$f":"'K80 - time schedule'!FU64","v":0},{"$f":"'K80 - time schedule'!FV64","v":0},{"$f":"'K80 - time schedule'!FW64","v":0},{"$f":"'K80 - time schedule'!FX64","v":0},{"$f":"'K80 - time schedule'!FY64","v":0},{"$f":"'K80 - time schedule'!FZ64","v":0},{"$f":"'K80 - time schedule'!GA64","v":0},{"$f":"'K80 - time schedule'!GB64","v":0},{"$f":"'K80 - time schedule'!GC64","v":0},{"$f":"'K80 - time schedule'!GD64","v":0},{"$f":"'K80 - time schedule'!GE64","v":0},{"$f":"'K80 - time schedule'!GF64","v":0},{"$f":"'K20 - time schedule'!GG60","v":0},{"$f":"'K20 - time schedule'!GH60","v":0},{"$f":"'K20 - time schedule'!GI60","v":0},{"$f":"'K20 - time schedule'!GJ60","v":0},{"$f":"'K20 - time schedule'!GK60","v":0},{"$f":"'K20 - time schedule'!GL60","v":0},{"$f":"'K20 - time schedule'!GM60","v":0},{"$f":"'K20 - time schedule'!GN60","v":0},{"$f":"'K20 - time schedule'!GO60","v":0},{"$f":"'K20 - time schedule'!GP60","v":0},{"$f":"'K20 - time schedule'!GQ60","v":0},{"$f":"'K20 - time schedule'!GR60","v":0},{"$f":"'K20 - time schedule'!GS60","v":0},{"$f":"'K20 - time schedule'!GT60","v":0},{"$f":"'K20 - time schedule'!GU60","v":0},{"$f":"'K20 - time schedule'!GV60","v":0},{"$f":"'K20 - time schedule'!GW60","v":0},{"$f":"'K20 - time schedule'!GX60","v":0},{"$f":"'K20 - time schedule'!GY60","v":0},{"$f":"'K20 - time schedule'!GZ60","v":0},{"$f":"'K20 - time schedule'!HA60","v":0},{"$f":"'K20 - time schedule'!HB60","v":0},{"$f":"'K20 - time schedule'!HC60","v":0},{"$f":"'K20 - time schedule'!HD60","v":0},{"$f":"'K20 - time schedule'!HE60","v":0},{"$f":"'K20 - time schedule'!HF60","v":0},{"$f":"'K20 - time schedule'!HG60","v":0},{"$f":"'K20 - time schedule'!HH60","v":0},{"$f":"'K20 - time schedule'!HI60","v":0},{"$f":"'K20 - time schedule'!HJ60","v":0},{"$f":"'K20 - time schedule'!HK60","v":0},{"$f":"'K20 - time schedule'!HL60","v":0},{"$f":"'K20 - time schedule'!HM60","v":0},{"$f":"'K20 - time schedule'!HN60","v":0},{"$f":"'K20 - time schedule'!HO60","v":0},{"$f":"'K20 - time schedule'!HP60","v":0},{"$f":"'K20 - time schedule'!HQ60","v":0},{"$f":"'K20 - time schedule'!HR60","v":0},{"$f":"'K20 - time schedule'!HS60","v":0},{"$f":"'K20 - time schedule'!HT60","v":0},{"$f":"'K20 - time schedule'!HU60","v":0},{"$f":"'K20 - time schedule'!HV60","v":0},{"$f":"'K20 - time schedule'!HW60","v":0},{"$f":"'K20 - time schedule'!HX60","v":0},{"$f":"'K20 - time schedule'!HY60","v":0},{"$f":"'K20 - time schedule'!HZ60","v":0},{"$f":"'K20 - time schedule'!IA60","v":0},{"$f":"'K20 - time schedule'!IB60","v":0},{"$f":"'K20 - time schedule'!IC60","v":0},{"$f":"'K20 - time schedule'!ID60","v":0},{"$f":"'K20 - time schedule'!IE60","v":0},{"$f":"'K20 - time schedule'!IF60","v":0},{"$f":"'K20 - time schedule'!IG60","v":0},{"$f":"'K20 - time schedule'!IH60","v":0},{"$f":"'K20 - time schedule'!II60","v":0},{"$f":"'K20 - time schedule'!IJ60","v":0},{"$f":"'K20 - time schedule'!IK60","v":0},{"$f":"'K20 - time schedule'!IL60","v":0},{"$f":"'K20 - time schedule'!IM60","v":0},{"$f":"'K20 - time schedule'!IN60","v":0},{"$f":"'K20 - time schedule'!IO60","v":0},{"$f":"'K20 - time schedule'!IP60","v":0},{"$f":"'K20 - time schedule'!IQ60","v":0},{"$f":"'K20 - time schedule'!IR60","v":0},{"$f":"'K20 - time schedule'!IS60","v":0},{"$f":"'K20 - time schedule'!IT60","v":0},{"$f":"'K20 - time schedule'!IU60","v":0},{"$f":"'K20 - time schedule'!IV60","v":0},{"$f":"'K20 - time schedule'!IW60","v":0},{"$f":"'K20 - time schedule'!IX60","v":0},{"$f":"'K20 - time schedule'!IY60","v":0},{"$f":"'K20 - time schedule'!IZ60","v":0},{"$f":"'K20 - time schedule'!JA60","v":0},{"$f":"'K20 - time schedule'!JB60","v":0},{"$f":"'K20 - time schedule'!JC60","v":0},{"$f":"'K20 - time schedule'!JD60","v":0},{"$f":"'K20 - time schedule'!JE60","v":0},{"$f":"'K20 - time schedule'!JF60","v":0},{"$f":"'K20 - time schedule'!JG60","v":0},{"$f":"'K20 - time schedule'!JH60","v":0},{"$f":"'K20 - time schedule'!JI60","v":0},{"$f":"'K20 - time schedule'!JJ60","v":0},{"$f":"'K20 - time schedule'!JK60","v":0},{"$f":"'K20 - time schedule'!JL60","v":0},{"$f":"'K20 - time schedule'!JM60","v":0},{"$f":"'K20 - time schedule'!JN60","v":0},{"$f":"'K20 - time schedule'!JO60","v":0},{"$f":"'K20 - time schedule'!JP60","v":0},{"$f":"'K20 - time schedule'!JQ60","v":0},{"$f":"'K20 - time schedule'!JR60","v":0},{"$f":"'K20 - time schedule'!JS60","v":0},{"$f":"'K20 - time schedule'!JT60","v":0},{"$f":"'K20 - time schedule'!JU60","v":0},{"$f":"'K20 - time schedule'!JV60","v":0},{"$f":"'K20 - time schedule'!JW60","v":0},{"$f":"'K20 - time schedule'!JX60","v":0},{"$f":"'K20 - time schedule'!JY60","v":0},{"$f":"'K20 - time schedule'!JZ60","v":0},{"$f":"'K20 - time schedule'!KA60","v":0},{"$f":"'K20 - time schedule'!KB60","v":0},{"$f":"'K20 - time schedule'!KC60","v":0},{"$f":"'K20 - time schedule'!KD60","v":0},{"$f":"'K20 - time schedule'!KE60","v":0},{"$f":"'K20 - time schedule'!KF60","v":0},{"$f":"'K20 - time schedule'!KG60","v":0},{"$f":"'K20 - time schedule'!KH60","v":0},{"$f":"'K20 - time schedule'!KI60","v":0},{"$f":"'K20 - time schedule'!KJ60","v":0},{"$f":"'K20 - time schedule'!KK60","v":0},{"$f":"'K20 - time schedule'!KL60","v":0},{"$f":"'K20 - time schedule'!KM60","v":0},{"$f":"'K20 - time schedule'!KN60","v":0},{"$f":"'K20 - time schedule'!KO60","v":0},{"$f":"'K20 - time schedule'!KP60","v":0},{"$f":"'K20 - time schedule'!KQ60","v":0},{"$f":"'K20 - time schedule'!KR60","v":0},{"$f":"'K20 - time schedule'!KS60","v":0},{"$f":"'K20 - time schedule'!KT60","v":0}]
["Boiler room K90 - binding technical specification for OB 6 (Construction)","K90","EUR",{"$f":"'K90 - time schedule'!G11","v":0},{"$f":"'K90 - time schedule'!H11","v":0},{"$f":"'K90 - time schedule'!I11","v":0},{"$f":"'K90 - time schedule'!J11","v":0},{"$f":"'K90 - time schedule'!K11","v":0},{"$f":"'K90 - time schedule'!L11","v":0},{"$f":"'K90 - time schedule'!M11","v":0},{"$f":"'K90 - time schedule'!N11","v":0},{"$f":"'K90 - time schedule'!O11","v":0},{"$f":"'K90 - time schedule'!P11","v":0},{"$f":"'K90 - time schedule'!Q11","v":0},{"$f":"'K90 - time schedule'!R11","v":0},{"$f":"'K90 - time schedule'!S11","v":0},{"$f":"'K90 - time schedule'!T11","v":0},{"$f":"'K90 - time schedule'!U11","v":0},{"$f":"'K90 - time schedule'!V11","v":0},{"$f":"'K90 - time schedule'!W11","v":0},{"$f":"'K90 - time schedule'!X11","v":0},{"$f":"'K90 - time schedule'!Y11","v":0},{"$f":"'K90 - time schedule'!Z11","v":0},{"$f":"'K90 - time schedule'!AA11","v":0},{"$f":"'K90 - time schedule'!AB11","v":0},{"$f":"'K90 - time schedule'!AC11","v":0},{"$f":"'K90 - time schedule'!AD11","v":0},{"$f":"'K90 - time schedule'!AE11","v":0},{"$f":"'K90 - time schedule'!AF11","v":0},{"$f":"'K90 - time schedule'!AG11","v":0},{"$f":"'K90 - time schedule'!AH11","v":0},{"$f":"'K90 - time schedule'!AI11","v":0},{"$f":"'K90 - time schedule'!AJ11","v":0},{"$f":"'K90 - time schedule'!AK11","v":0},{"$f":"'K90 - time schedule'!AL11","v":0},{"$f":"'K90 - time schedule'!AM11","v":0},{"$f":"'K90 - time schedule'!AN11","v":0},{"$f":"'K90 - time schedule'!AO11","v":0},{"$f":"'K90 - time schedule'!AP11","v":0},{"$f":"'K90 - time schedule'!AQ11","v":0},{"$f":"'K90 - time schedule'!AR11","v":0},{"$f":"'K90 - time schedule'!AS11","v":0},{"$f":"'K90 - time schedule'!AT11","v":0},{"$f":"'K90 - time schedule'!AU11","v":0},{"$f":"'K90 - time schedule'!AV11","v":0},{"$f":"'K90 - time schedule'!AW11","v":0},{"$f":"'K90 - time schedule'!AX11","v":0},{"$f":"'K90 - time schedule'!AY11","v":0},{"$f":"'K90 - time schedule'!AZ11","v":0},{"$f":"'K90 - time schedule'!BA11","v":0},{"$f":"'K90 - time schedule'!BB11","v":0},{"$f":"'K90 - time schedule'!BC11","v":0},{"$f":"'K90 - time schedule'!BD11","v":0},{"$f":"'K90 - time schedule'!BE11","v":0},{"$f":"'K90 - time schedule'!BF11","v":0},{"$f":"'K90 - time schedule'!BG11","v":0},{"$f":"'K90 - time schedule'!BH11","v":0},{"$f":"'K90 - time schedule'!BI11","v":0},{"$f":"'K90 - time schedule'!BJ11","v":0},{"$f":"'K90 - time schedule'!BK11","v":0},{"$f":"'K90 - time schedule'!BL11","v":0},{"$f":"'K90 - time schedule'!BM11","v":0},{"$f":"'K90 - time schedule'!BN11","v":0},{"$f":"'K90 - time schedule'!BO11","v":0},{"$f":"'K90 - time schedule'!BP11","v":0},{"$f":"'K90 - time schedule'!BQ11","v":0},{"$f":"'K90 - time schedule'!BR11","v":0},{"$f":"'K90 - time schedule'!BS11","v":0},{"$f":"'K90 - time schedule'!BT11","v":0},{"$f":"'K90 - time schedule'!BU11","v":0},{"$f":"'K90 - time schedule'!BV11","v":0},{"$f":"'K90 - time schedule'!BW11","v":0},{"$f":"'K90 - time schedule'!BX11","v":0},{"$f":"'K90 - time schedule'!BY11","v":0},{"$f":"'K90 - time schedule'!BZ11","v":0},{"$f":"'K90 - time schedule'!CA11","v":0},{"$f":"'K90 - time schedule'!CB11","v":0},{"$f":"'K90 - time schedule'!CC11","v":0},{"$f":"'K90 - time schedule'!CD11","v":0},{"$f":"'K90 - time schedule'!CE11","v":0},{"$f":"'K90 - time schedule'!CF11","v":0},{"$f":"'K90 - time schedule'!CG11","v":0},{"$f":"'K90 - time schedule'!CH11","v":0},{"$f":"'K90 - time schedule'!CI11","v":0},{"$f":"'K90 - time schedule'!CJ11","v":0},{"$f":"'K90 - time schedule'!CK11","v":0},{"$f":"'K90 - time schedule'!CL11","v":0},{"$f":"'K90 - time schedule'!CM11","v":0},{"$f":"'K90 - time schedule'!CN11","v":0},{"$f":"'K90 - time schedule'!CO11","v":0},{"$f":"'K90 - time schedule'!CP11","v":0},{"$f":"'K90 - time schedule'!CQ11","v":0},{"$f":"'K90 - time schedule'!CR11","v":0},{"$f":"'K90 - time schedule'!CS11","v":0},{"$f":"'K90 - time schedule'!CT11","v":0},{"$f":"'K90 - time schedule'!CU11","v":0},{"$f":"'K90 - time schedule'!CV11","v":0},{"$f":"'K90 - time schedule'!CW11","v":0},{"$f":"'K90 - time schedule'!CX11","v":0},{"$f":"'K90 - time schedule'!CY11","v":0},{"$f":"'K90 - time schedule'!CZ11","v":0},{"$f":"'K90 - time schedule'!DA11","v":0},{"$f":"'K90 - time schedule'!DB11","v":0},{"$f":"'K90 - time schedule'!DC11","v":0},{"$f":"'K90 - time schedule'!DD11","v":0},{"$f":"'K90 - time schedule'!DE11","v":0},{"$f":"'K90 - time schedule'!DF11","v":0},{"$f":"'K90 - time schedule'!DG11","v":0},{"$f":"'K90 - time schedule'!DH11","v":0},{"$f":"'K90 - time schedule'!DI11","v":0},{"$f":"'K90 - time schedule'!DJ11","v":0},{"$f":"'K90 - time schedule'!DK11","v":0},{"$f":"'K90 - time schedule'!DL11","v":0},{"$f":"'K90 - time schedule'!DM11","v":0},{"$f":"'K90 - time schedule'!DN11","v":0},{"$f":"'K90 - time schedule'!DO11","v":0},{"$f":"'K90 - time schedule'!DP11","v":0},{"$f":"'K90 - time schedule'!DQ11","v":0},{"$f":"'K90 - time schedule'!DR11","v":0},{"$f":"'K90 - time schedule'!DS11","v":0},{"$f":"'K90 - time schedule'!DT11","v":0},{"$f":"'K90 - time schedule'!DU11","v":0},{"$f":"'K90 - time schedule'!DV11","v":0},{"$f":"'K90 - time schedule'!DW11","v":0},{"$f":"'K90 - time schedule'!DX11","v":0},{"$f":"'K90 - time schedule'!DY11","v":0},{"$f":"'K90 - time schedule'!DZ11","v":0},{"$f":"'K90 - time schedule'!EA11","v":0},{"$f":"'K90 - time schedule'!EB11","v":0},{"$f":"'K90 - time schedule'!EC11","v":0},{"$f":"'K90 - time schedule'!ED11","v":0},{"$f":"'K90 - time schedule'!EE11","v":0},{"$f":"'K90 - time schedule'!EF11","v":0},{"$f":"'K90 - time schedule'!EG11","v":0},{"$f":"'K90 - time schedule'!EH11","v":0},{"$f":"'K90 - time schedule'!EI11","v":0},{"$f":"'K90 - time schedule'!EJ11","v":0},{"$f":"'K90 - time schedule'!EK11","v":0},{"$f":"'K90 - time schedule'!EL11","v":0},{"$f":"'K90 - time schedule'!EM11","v":0},{"$f":"'K90 - time schedule'!EN11","v":0},{"$f":"'K90 - time schedule'!EO11","v":0},{"$f":"'K90 - time schedule'!EP11","v":0},{"$f":"'K90 - time schedule'!EQ11","v":0},{"$f":"'K90 - time schedule'!ER11","v":0},{"$f":"'K90 - time schedule'!ES11","v":0},{"$f":"'K90 - time schedule'!ET11","v":0},{"$f":"'K90 - time schedule'!EU11","v":0},{"$f":"'K90 - time schedule'!EV11","v":0},{"$f":"'K90 - time schedule'!EW11","v":0},{"$f":"'K90 - time schedule'!EX11","v":0},{"$f":"'K90 - time schedule'!EY11","v":0},{"$f":"'K90 - time schedule'!EZ11","v":0},{"$f":"'K90 - time schedule'!FA11","v":0},{"$f":"'K90 - time schedule'!FB11","v":0},{"$f":"'K90 - time schedule'!FC11","v":0},{"$f":"'K90 - time schedule'!FD11","v":0},{"$f":"'K90 - time schedule'!FE11","v":0},{"$f":"'K90 - time schedule'!FF11","v":0},{"$f":"'K90 - time schedule'!FG11","v":0},{"$f":"'K90 - time schedule'!FH11","v":0},{"$f":"'K90 - time schedule'!FI11","v":0},{"$f":"'K90 - time schedule'!FJ11","v":0},{"$f":"'K90 - time schedule'!FK11","v":0},{"$f":"'K90 - time schedule'!FL11","v":0},{"$f":"'K90 - time schedule'!FM11","v":0},{"$f":"'K90 - time schedule'!FN11","v":0},{"$f":"'K90 - time schedule'!FO11","v":0},{"$f":"'K90 - time schedule'!FP11","v":0},{"$f":"'K90 - time schedule'!FQ11","v":0},{"$f":"'K90 - time schedule'!FR11","v":0},{"$f":"'K90 - time schedule'!FS11","v":0},{"$f":"'K90 - time schedule'!FT11","v":0},{"$f":"'K90 - time schedule'!FU11","v":0},{"$f":"'K90 - time schedule'!FV11","v":0},{"$f":"'K90 - time schedule'!FW11","v":0},{"$f":"'K90 - time schedule'!FX11","v":0},{"$f":"'K90 - time schedule'!FY11","v":0},{"$f":"'K90 - time schedule'!FZ11","v":0},{"$f":"'K90 - time schedule'!GA11","v":0},{"$f":"'K90 - time schedule'!GB11","v":0},{"$f":"'K90 - time schedule'!GC11","v":0},{"$f":"'K90 - time schedule'!GD11","v":0},{"$f":"'K90 - time schedule'!GE11","v":0},{"$f":"'K90 - time schedule'!GF11","v":0},{"$f":"'K20 - time schedule'!GG61","v":0},{"$f":"'K20 - time schedule'!GH61","v":0},{"$f":"'K20 - time schedule'!GI61","v":0},{"$f":"'K20 - time schedule'!GJ61","v":0},{"$f":"'K20 - time schedule'!GK61","v":0},{"$f":"'K20 - time schedule'!GL61","v":0},{"$f":"'K20 - time schedule'!GM61","v":0},{"$f":"'K20 - time schedule'!GN61","v":0},{"$f":"'K20 - time schedule'!GO61","v":0},{"$f":"'K20 - time schedule'!GP61","v":0},{"$f":"'K20 - time schedule'!GQ61","v":0},{"$f":"'K20 - time schedule'!GR61","v":0},{"$f":"'K20 - time schedule'!GS61","v":0},{"$f":"'K20 - time schedule'!GT61","v":0},{"$f":"'K20 - time schedule'!GU61","v":0},{"$f":"'K20 - time schedule'!GV61","v":0},{"$f":"'K20 - time schedule'!GW61","v":0},{"$f":"'K20 - time schedule'!GX61","v":0},{"$f":"'K20 - time schedule'!GY61","v":0},{"$f":"'K20 - time schedule'!GZ61","v":0},{"$f":"'K20 - time schedule'!HA61","v":0},{"$f":"'K20 - time schedule'!HB61","v":0},{"$f":"'K20 - time schedule'!HC61","v":0},{"$f":"'K20 - time schedule'!HD61","v":0},{"$f":"'K20 - time schedule'!HE61","v":0},{"$f":"'K20 - time schedule'!HF61","v":0},{"$f":"'K20 - time schedule'!HG61","v":0},{"$f":"'K20 - time schedule'!HH61","v":0},{"$f":"'K20 - time schedule'!HI61","v":0},{"$f":"'K20 - time schedule'!HJ61","v":0},{"$f":"'K20 - time schedule'!HK61","v":0},{"$f":"'K20 - time schedule'!HL61","v":0},{"$f":"'K20 - time schedule'!HM61","v":0},{"$f":"'K20 - time schedule'!HN61","v":0},{"$f":"'K20 - time schedule'!HO61","v":0},{"$f":"'K20 - time schedule'!HP61","v":0},{"$f":"'K20 - time schedule'!HQ61","v":0},{"$f":"'K20 - time schedule'!HR61","v":0},{"$f":"'K20 - time schedule'!HS61","v":0},{"$f":"'K20 - time schedule'!HT61","v":0},{"$f":"'K20 - time schedule'!HU61","v":0},{"$f":"'K20 - time schedule'!HV61","v":0},{"$f":"'K20 - time schedule'!HW61","v":0},{"$f":"'K20 - time schedule'!HX61","v":0},{"$f":"'K20 - time schedule'!HY61","v":0},{"$f":"'K20 - time schedule'!HZ61","v":0},{"$f":"'K20 - time schedule'!IA61","v":0},{"$f":"'K20 - time schedule'!IB61","v":0},{"$f":"'K20 - time schedule'!IC61","v":0},{"$f":"'K20 - time schedule'!ID61","v":0},{"$f":"'K20 - time schedule'!IE61","v":0},{"$f":"'K20 - time schedule'!IF61","v":0},{"$f":"'K20 - time schedule'!IG61","v":0},{"$f":"'K20 - time schedule'!IH61","v":0},{"$f":"'K20 - time schedule'!II61","v":0},{"$f":"'K20 - time schedule'!IJ61","v":0},{"$f":"'K20 - time schedule'!IK61","v":0},{"$f":"'K20 - time schedule'!IL61","v":0},{"$f":"'K20 - time schedule'!IM61","v":0},{"$f":"'K20 - time schedule'!IN61","v":0},{"$f":"'K20 - time schedule'!IO61","v":0},{"$f":"'K20 - time schedule'!IP61","v":0},{"$f":"'K20 - time schedule'!IQ61","v":0},{"$f":"'K20 - time schedule'!IR61","v":0},{"$f":"'K20 - time schedule'!IS61","v":0},{"$f":"'K20 - time schedule'!IT61","v":0},{"$f":"'K20 - time schedule'!IU61","v":0},{"$f":"'K20 - time schedule'!IV61","v":0},{"$f":"'K20 - time schedule'!IW61","v":0},{"$f":"'K20 - time schedule'!IX61","v":0},{"$f":"'K20 - time schedule'!IY61","v":0},{"$f":"'K20 - time schedule'!IZ61","v":0},{"$f":"'K20 - time schedule'!JA61","v":0},{"$f":"'K20 - time schedule'!JB61","v":0},{"$f":"'K20 - time schedule'!JC61","v":0},{"$f":"'K20 - time schedule'!JD61","v":0},{"$f":"'K20 - time schedule'!JE61","v":0},{"$f":"'K20 - time schedule'!JF61","v":0},{"$f":"'K20 - time schedule'!JG61","v":0},{"$f":"'K20 - time schedule'!JH61","v":0},{"$f":"'K20 - time schedule'!JI61","v":0},{"$f":"'K20 - time schedule'!JJ61","v":0},{"$f":"'K20 - time schedule'!JK61","v":0},{"$f":"'K20 - time schedule'!JL61","v":0},{"$f":"'K20 - time schedule'!JM61","v":0},{"$f":"'K20 - time schedule'!JN61","v":0},{"$f":"'K20 - time schedule'!JO61","v":0},{"$f":"'K20 - time schedule'!JP61","v":0},{"$f":"'K20 - time schedule'!JQ61","v":0},{"$f":"'K20 - time schedule'!JR61","v":0},{"$f":"'K20 - time schedule'!JS61","v":0},{"$f":"'K20 - time schedule'!JT61","v":0},{"$f":"'K20 - time schedule'!JU61","v":0},{"$f":"'K20 - time schedule'!JV61","v":0},{"$f":"'K20 - time schedule'!JW61","v":0},{"$f":"'K20 - time schedule'!JX61","v":0},{"$f":"'K20 - time schedule'!JY61","v":0},{"$f":"'K20 - time schedule'!JZ61","v":0},{"$f":"'K20 - time schedule'!KA61","v":0},{"$f":"'K20 - time schedule'!KB61","v":0},{"$f":"'K20 - time schedule'!KC61","v":0},{"$f":"'K20 - time schedule'!KD61","v":0},{"$f":"'K20 - time schedule'!KE61","v":0},{"$f":"'K20 - time schedule'!KF61","v":0},{"$f":"'K20 - time schedule'!KG61","v":0},{"$f":"'K20 - time schedule'!KH61","v":0},{"$f":"'K20 - time schedule'!KI61","v":0},{"$f":"'K20 - time schedule'!KJ61","v":0},{"$f":"'K20 - time schedule'!KK61","v":0},{"$f":"'K20 - time schedule'!KL61","v":0},{"$f":"'K20 - time schedule'!KM61","v":0},{"$f":"'K20 - time schedule'!KN61","v":0},{"$f":"'K20 - time schedule'!KO61","v":0},{"$f":"'K20 - time schedule'!KP61","v":0},{"$f":"'K20 - time schedule'!KQ61","v":0},{"$f":"'K20 - time schedule'!KR61","v":0},{"$f":"'K20 - time schedule'!KS61","v":0},{"$f":"'K20 - time schedule'!KT61","v":0}]
["Boiler room K90 - binding technical specification for OB 1 (Fuel management) ","K90","EUR",{"$f":"'K90 - time schedule'!G13","v":0},{"$f":"'K90 - time schedule'!H13","v":0},{"$f":"'K90 - time schedule'!I13","v":0},{"$f":"'K90 - time schedule'!J13","v":0},{"$f":"'K90 - time schedule'!K13","v":0},{"$f":"'K90 - time schedule'!L13","v":0},{"$f":"'K90 - time schedule'!M13","v":0},{"$f":"'K90 - time schedule'!N13","v":0},{"$f":"'K90 - time schedule'!O13","v":0},{"$f":"'K90 - time schedule'!P13","v":0},{"$f":"'K90 - time schedule'!Q13","v":0},{"$f":"'K90 - time schedule'!R13","v":0},{"$f":"'K90 - time schedule'!S13","v":0},{"$f":"'K90 - time schedule'!T13","v":0},{"$f":"'K90 - time schedule'!U13","v":0},{"$f":"'K90 - time schedule'!V13","v":0},{"$f":"'K90 - time schedule'!W13","v":0},{"$f":"'K90 - time schedule'!X13","v":0},{"$f":"'K90 - time schedule'!Y13","v":0},{"$f":"'K90 - time schedule'!Z13","v":0},{"$f":"'K90 - time schedule'!AA13","v":0},{"$f":"'K90 - time schedule'!AB13","v":0},{"$f":"'K90 - time schedule'!AC13","v":0},{"$f":"'K90 - time schedule'!AD13","v":0},{"$f":"'K90 - time schedule'!AE13","v":0},{"$f":"'K90 - time schedule'!AF13","v":0},{"$f":"'K90 - time schedule'!AG13","v":0},{"$f":"'K90 - time schedule'!AH13","v":0},{"$f":"'K90 - time schedule'!AI13","v":0},{"$f":"'K90 - time schedule'!AJ13","v":0},{"$f":"'K90 - time schedule'!AK13","v":0},{"$f":"'K90 - time schedule'!AL13","v":0},{"$f":"'K90 - time schedule'!AM13","v":0},{"$f":"'K90 - time schedule'!AN13","v":0},{"$f":"'K90 - time schedule'!AO13","v":0},{"$f":"'K90 - time schedule'!AP13","v":0},{"$f":"'K90 - time schedule'!AQ13","v":0},{"$f":"'K90 - time schedule'!AR13","v":0},{"$f":"'K90 - time schedule'!AS13","v":0},{"$f":"'K90 - time schedule'!AT13","v":0},{"$f":"'K90 - time schedule'!AU13","v":0},{"$f":"'K90 - time schedule'!AV13","v":0},{"$f":"'K90 - time schedule'!AW13","v":0},{"$f":"'K90 - time schedule'!AX13","v":0},{"$f":"'K90 - time schedule'!AY13","v":0},{"$f":"'K90 - time schedule'!AZ13","v":0},{"$f":"'K90 - time schedule'!BA13","v":0},{"$f":"'K90 - time schedule'!BB13","v":0},{"$f":"'K90 - time schedule'!BC13","v":0},{"$f":"'K90 - time schedule'!BD13","v":0},{"$f":"'K90 - time schedule'!BE13","v":0},{"$f":"'K90 - time schedule'!BF13","v":0},{"$f":"'K90 - time schedule'!BG13","v":0},{"$f":"'K90 - time schedule'!BH13","v":0},{"$f":"'K90 - time schedule'!BI13","v":0},{"$f":"'K90 - time schedule'!BJ13","v":0},{"$f":"'K90 - time schedule'!BK13","v":0},{"$f":"'K90 - time schedule'!BL13","v":0},{"$f":"'K90 - time schedule'!BM13","v":0},{"$f":"'K90 - time schedule'!BN13","v":0},{"$f":"'K90 - time schedule'!BO13","v":0},{"$f":"'K90 - time schedule'!BP13","v":0},{"$f":"'K90 - time schedule'!BQ13","v":0},{"$f":"'K90 - time schedule'!BR13","v":0},{"$f":"'K90 - time schedule'!BS13","v":0},{"$f":"'K90 - time schedule'!BT13","v":0},{"$f":"'K90 - time schedule'!BU13","v":0},{"$f":"'K90 - time schedule'!BV13","v":0},{"$f":"'K90 - time schedule'!BW13","v":0},{"$f":"'K90 - time schedule'!BX13","v":0},{"$f":"'K90 - time schedule'!BY13","v":0},{"$f":"'K90 - time schedule'!BZ13","v":0},{"$f":"'K90 - time schedule'!CA13","v":0},{"$f":"'K90 - time schedule'!CB13","v":0},{"$f":"'K90 - time schedule'!CC13","v":0},{"$f":"'K90 - time schedule'!CD13","v":0},{"$f":"'K90 - time schedule'!CE13","v":0},{"$f":"'K90 - time schedule'!CF13","v":0},{"$f":"'K90 - time schedule'!CG13","v":0},{"$f":"'K90 - time schedule'!CH13","v":0},{"$f":"'K90 - time schedule'!CI13","v":0},{"$f":"'K90 - time schedule'!CJ13","v":0},{"$f":"'K90 - time schedule'!CK13","v":0},{"$f":"'K90 - time schedule'!CL13","v":0},{"$f":"'K90 - time schedule'!CM13","v":0},{"$f":"'K90 - time schedule'!CN13","v":0},{"$f":"'K90 - time schedule'!CO13","v":0},{"$f":"'K90 - time schedule'!CP13","v":0},{"$f":"'K90 - time schedule'!CQ13","v":0},{"$f":"'K90 - time schedule'!CR13","v":0},{"$f":"'K90 - time schedule'!CS13","v":0},{"$f":"'K90 - time schedule'!CT13","v":0},{"$f":"'K90 - time schedule'!CU13","v":0},{"$f":"'K90 - time schedule'!CV13","v":0},{"$f":"'K90 - time schedule'!CW13","v":0},{"$f":"'K90 - time schedule'!CX13","v":0},{"$f":"'K90 - time schedule'!CY13","v":0},{"$f":"'K90 - time schedule'!CZ13","v":0},{"$f":"'K90 - time schedule'!DA13","v":0},{"$f":"'K90 - time schedule'!DB13","v":0},{"$f":"'K90 - time schedule'!DC13","v":0},{"$f":"'K90 - time schedule'!DD13","v":0},{"$f":"'K90 - time schedule'!DE13","v":0},{"$f":"'K90 - time schedule'!DF13","v":0},{"$f":"'K90 - time schedule'!DG13","v":0},{"$f":"'K90 - time schedule'!DH13","v":0},{"$f":"'K90 - time schedule'!DI13","v":0},{"$f":"'K90 - time schedule'!DJ13","v":0},{"$f":"'K90 - time schedule'!DK13","v":0},{"$f":"'K90 - time schedule'!DL13","v":0},{"$f":"'K90 - time schedule'!DM13","v":0},{"$f":"'K90 - time schedule'!DN13","v":0},{"$f":"'K90 - time schedule'!DO13","v":0},{"$f":"'K90 - time schedule'!DP13","v":0},{"$f":"'K90 - time schedule'!DQ13","v":0},{"$f":"'K90 - time schedule'!DR13","v":0},{"$f":"'K90 - time schedule'!DS13","v":0},{"$f":"'K90 - time schedule'!DT13","v":0},{"$f":"'K90 - time schedule'!DU13","v":0},{"$f":"'K90 - time schedule'!DV13","v":0},{"$f":"'K90 - time schedule'!DW13","v":0},{"$f":"'K90 - time schedule'!DX13","v":0},{"$f":"'K90 - time schedule'!DY13","v":0},{"$f":"'K90 - time schedule'!DZ13","v":0},{"$f":"'K90 - time schedule'!EA13","v":0},{"$f":"'K90 - time schedule'!EB13","v":0},{"$f":"'K90 - time schedule'!EC13","v":0},{"$f":"'K90 - time schedule'!ED13","v":0},{"$f":"'K90 - time schedule'!EE13","v":0},{"$f":"'K90 - time schedule'!EF13","v":0},{"$f":"'K90 - time schedule'!EG13","v":0},{"$f":"'K90 - time schedule'!EH13","v":0},{"$f":"'K90 - time schedule'!EI13","v":0},{"$f":"'K90 - time schedule'!EJ13","v":0},{"$f":"'K90 - time schedule'!EK13","v":0},{"$f":"'K90 - time schedule'!EL13","v":0},{"$f":"'K90 - time schedule'!EM13","v":0},{"$f":"'K90 - time schedule'!EN13","v":0},{"$f":"'K90 - time schedule'!EO13","v":0},{"$f":"'K90 - time schedule'!EP13","v":0},{"$f":"'K90 - time schedule'!EQ13","v":0},{"$f":"'K90 - time schedule'!ER13","v":0},{"$f":"'K90 - time schedule'!ES13","v":0},{"$f":"'K90 - time schedule'!ET13","v":0},{"$f":"'K90 - time schedule'!EU13","v":0},{"$f":"'K90 - time schedule'!EV13","v":0},{"$f":"'K90 - time schedule'!EW13","v":0},{"$f":"'K90 - time schedule'!EX13","v":0},{"$f":"'K90 - time schedule'!EY13","v":0},{"$f":"'K90 - time schedule'!EZ13","v":0},{"$f":"'K90 - time schedule'!FA13","v":0},{"$f":"'K90 - time schedule'!FB13","v":0},{"$f":"'K90 - time schedule'!FC13","v":0},{"$f":"'K90 - time schedule'!FD13","v":0},{"$f":"'K90 - time schedule'!FE13","v":0},{"$f":"'K90 - time schedule'!FF13","v":0},{"$f":"'K90 - time schedule'!FG13","v":0},{"$f":"'K90 - time schedule'!FH13","v":0},{"$f":"'K90 - time schedule'!FI13","v":0},{"$f":"'K90 - time schedule'!FJ13","v":0},{"$f":"'K90 - time schedule'!FK13","v":0},{"$f":"'K90 - time schedule'!FL13","v":0},{"$f":"'K90 - time schedule'!FM13","v":0},{"$f":"'K90 - time schedule'!FN13","v":0},{"$f":"'K90 - time schedule'!FO13","v":0},{"$f":"'K90 - time schedule'!FP13","v":0},{"$f":"'K90 - time schedule'!FQ13","v":0},{"$f":"'K90 - time schedule'!FR13","v":0},{"$f":"'K90 - time schedule'!FS13","v":0},{"$f":"'K90 - time schedule'!FT13","v":0},{"$f":"'K90 - time schedule'!FU13","v":0},{"$f":"'K90 - time schedule'!FV13","v":0},{"$f":"'K90 - time schedule'!FW13","v":0},{"$f":"'K90 - time schedule'!FX13","v":0},{"$f":"'K90 - time schedule'!FY13","v":0},{"$f":"'K90 - time schedule'!FZ13","v":0},{"$f":"'K90 - time schedule'!GA13","v":0},{"$f":"'K90 - time schedule'!GB13","v":0},{"$f":"'K90 - time schedule'!GC13","v":0},{"$f":"'K90 - time schedule'!GD13","v":0},{"$f":"'K90 - time schedule'!GE13","v":0},{"$f":"'K90 - time schedule'!GF13","v":0},{"$f":"'K20 - time schedule'!GG62","v":0},{"$f":"'K20 - time schedule'!GH62","v":0},{"$f":"'K20 - time schedule'!GI62","v":0},{"$f":"'K20 - time schedule'!GJ62","v":0},{"$f":"'K20 - time schedule'!GK62","v":0},{"$f":"'K20 - time schedule'!GL62","v":0},{"$f":"'K20 - time schedule'!GM62","v":0},{"$f":"'K20 - time schedule'!GN62","v":0},{"$f":"'K20 - time schedule'!GO62","v":0},{"$f":"'K20 - time schedule'!GP62","v":0},{"$f":"'K20 - time schedule'!GQ62","v":0},{"$f":"'K20 - time schedule'!GR62","v":0},{"$f":"'K20 - time schedule'!GS62","v":0},{"$f":"'K20 - time schedule'!GT62","v":0},{"$f":"'K20 - time schedule'!GU62","v":0},{"$f":"'K20 - time schedule'!GV62","v":0},{"$f":"'K20 - time schedule'!GW62","v":0},{"$f":"'K20 - time schedule'!GX62","v":0},{"$f":"'K20 - time schedule'!GY62","v":0},{"$f":"'K20 - time schedule'!GZ62","v":0},{"$f":"'K20 - time schedule'!HA62","v":0},{"$f":"'K20 - time schedule'!HB62","v":0},{"$f":"'K20 - time schedule'!HC62","v":0},{"$f":"'K20 - time schedule'!HD62","v":0},{"$f":"'K20 - time schedule'!HE62","v":0},{"$f":"'K20 - time schedule'!HF62","v":0},{"$f":"'K20 - time schedule'!HG62","v":0},{"$f":"'K20 - time schedule'!HH62","v":0},{"$f":"'K20 - time schedule'!HI62","v":0},{"$f":"'K20 - time schedule'!HJ62","v":0},{"$f":"'K20 - time schedule'!HK62","v":0},{"$f":"'K20 - time schedule'!HL62","v":0},{"$f":"'K20 - time schedule'!HM62","v":0},{"$f":"'K20 - time schedule'!HN62","v":0},{"$f":"'K20 - time schedule'!HO62","v":0},{"$f":"'K20 - time schedule'!HP62","v":0},{"$f":"'K20 - time schedule'!HQ62","v":0},{"$f":"'K20 - time schedule'!HR62","v":0},{"$f":"'K20 - time schedule'!HS62","v":0},{"$f":"'K20 - time schedule'!HT62","v":0},{"$f":"'K20 - time schedule'!HU62","v":0},{"$f":"'K20 - time schedule'!HV62","v":0},{"$f":"'K20 - time schedule'!HW62","v":0},{"$f":"'K20 - time schedule'!HX62","v":0},{"$f":"'K20 - time schedule'!HY62","v":0},{"$f":"'K20 - time schedule'!HZ62","v":0},{"$f":"'K20 - time schedule'!IA62","v":0},{"$f":"'K20 - time schedule'!IB62","v":0},{"$f":"'K20 - time schedule'!IC62","v":0},{"$f":"'K20 - time schedule'!ID62","v":0},{"$f":"'K20 - time schedule'!IE62","v":0},{"$f":"'K20 - time schedule'!IF62","v":0},{"$f":"'K20 - time schedule'!IG62","v":0},{"$f":"'K20 - time schedule'!IH62","v":0},{"$f":"'K20 - time schedule'!II62","v":0},{"$f":"'K20 - time schedule'!IJ62","v":0},{"$f":"'K20 - time schedule'!IK62","v":0},{"$f":"'K20 - time schedule'!IL62","v":0},{"$f":"'K20 - time schedule'!IM62","v":0},{"$f":"'K20 - time schedule'!IN62","v":0},{"$f":"'K20 - time schedule'!IO62","v":0},{"$f":"'K20 - time schedule'!IP62","v":0},{"$f":"'K20 - time schedule'!IQ62","v":0},{"$f":"'K20 - time schedule'!IR62","v":0},{"$f":"'K20 - time schedule'!IS62","v":0},{"$f":"'K20 - time schedule'!IT62","v":0},{"$f":"'K20 - time schedule'!IU62","v":0},{"$f":"'K20 - time schedule'!IV62","v":0},{"$f":"'K20 - time schedule'!IW62","v":0},{"$f":"'K20 - time schedule'!IX62","v":0},{"$f":"'K20 - time schedule'!IY62","v":0},{"$f":"'K20 - time schedule'!IZ62","v":0},{"$f":"'K20 - time schedule'!JA62","v":0},{"$f":"'K20 - time schedule'!JB62","v":0},{"$f":"'K20 - time schedule'!JC62","v":0},{"$f":"'K20 - time schedule'!JD62","v":0},{"$f":"'K20 - time schedule'!JE62","v":0},{"$f":"'K20 - time schedule'!JF62","v":0},{"$f":"'K20 - time schedule'!JG62","v":0},{"$f":"'K20 - time schedule'!JH62","v":0},{"$f":"'K20 - time schedule'!JI62","v":0},{"$f":"'K20 - time schedule'!JJ62","v":0},{"$f":"'K20 - time schedule'!JK62","v":0},{"$f":"'K20 - time schedule'!JL62","v":0},{"$f":"'K20 - time schedule'!JM62","v":0},{"$f":"'K20 - time schedule'!JN62","v":0},{"$f":"'K20 - time schedule'!JO62","v":0},{"$f":"'K20 - time schedule'!JP62","v":0},{"$f":"'K20 - time schedule'!JQ62","v":0},{"$f":"'K20 - time schedule'!JR62","v":0},{"$f":"'K20 - time schedule'!JS62","v":0},{"$f":"'K20 - time schedule'!JT62","v":0},{"$f":"'K20 - time schedule'!JU62","v":0},{"$f":"'K20 - time schedule'!JV62","v":0},{"$f":"'K20 - time schedule'!JW62","v":0},{"$f":"'K20 - time schedule'!JX62","v":0},{"$f":"'K20 - time schedule'!JY62","v":0},{"$f":"'K20 - time schedule'!JZ62","v":0},{"$f":"'K20 - time schedule'!KA62","v":0},{"$f":"'K20 - time schedule'!KB62","v":0},{"$f":"'K20 - time schedule'!KC62","v":0},{"$f":"'K20 - time schedule'!KD62","v":0},{"$f":"'K20 - time schedule'!KE62","v":0},{"$f":"'K20 - time schedule'!KF62","v":0},{"$f":"'K20 - time schedule'!KG62","v":0},{"$f":"'K20 - time schedule'!KH62","v":0},{"$f":"'K20 - time schedule'!KI62","v":0},{"$f":"'K20 - time schedule'!KJ62","v":0},{"$f":"'K20 - time schedule'!KK62","v":0},{"$f":"'K20 - time schedule'!KL62","v":0},{"$f":"'K20 - time schedule'!KM62","v":0},{"$f":"'K20 - time schedule'!KN62","v":0},{"$f":"'K20 - time schedule'!KO62","v":0},{"$f":"'K20 - time schedule'!KP62","v":0},{"$f":"'K20 - time schedule'!KQ62","v":0},{"$f":"'K20 - time schedule'!KR62","v":0},{"$f":"'K20 - time schedule'!KS62","v":0},{"$f":"'K20 - time schedule'!KT62","v":0}]
["Boiler room K90 - binding technical specification for other OBs, for other suppliers of technological units ","K90","EUR",{"$f":"'K90 - time schedule'!G15","v":0},{"$f":"'K90 - time schedule'!H15","v":0},{"$f":"'K90 - time schedule'!I15","v":0},{"$f":"'K90 - time schedule'!J15","v":0},{"$f":"'K90 - time schedule'!K15","v":0},{"$f":"'K90 - time schedule'!L15","v":0},{"$f":"'K90 - time schedule'!M15","v":0},{"$f":"'K90 - time schedule'!N15","v":0},{"$f":"'K90 - time schedule'!O15","v":0},{"$f":"'K90 - time schedule'!P15","v":0},{"$f":"'K90 - time schedule'!Q15","v":0},{"$f":"'K90 - time schedule'!R15","v":0},{"$f":"'K90 - time schedule'!S15","v":0},{"$f":"'K90 - time schedule'!T15","v":0},{"$f":"'K90 - time schedule'!U15","v":0},{"$f":"'K90 - time schedule'!V15","v":0},{"$f":"'K90 - time schedule'!W15","v":0},{"$f":"'K90 - time schedule'!X15","v":0},{"$f":"'K90 - time schedule'!Y15","v":0},{"$f":"'K90 - time schedule'!Z15","v":0},{"$f":"'K90 - time schedule'!AA15","v":0},{"$f":"'K90 - time schedule'!AB15","v":0},{"$f":"'K90 - time schedule'!AC15","v":0},{"$f":"'K90 - time schedule'!AD15","v":0},{"$f":"'K90 - time schedule'!AE15","v":0},{"$f":"'K90 - time schedule'!AF15","v":0},{"$f":"'K90 - time schedule'!AG15","v":0},{"$f":"'K90 - time schedule'!AH15","v":0},{"$f":"'K90 - time schedule'!AI15","v":0},{"$f":"'K90 - time schedule'!AJ15","v":0},{"$f":"'K90 - time schedule'!AK15","v":0},{"$f":"'K90 - time schedule'!AL15","v":0},{"$f":"'K90 - time schedule'!AM15","v":0},{"$f":"'K90 - time schedule'!AN15","v":0},{"$f":"'K90 - time schedule'!AO15","v":0},{"$f":"'K90 - time schedule'!AP15","v":0},{"$f":"'K90 - time schedule'!AQ15","v":0},{"$f":"'K90 - time schedule'!AR15","v":0},{"$f":"'K90 - time schedule'!AS15","v":0},{"$f":"'K90 - time schedule'!AT15","v":0},{"$f":"'K90 - time schedule'!AU15","v":0},{"$f":"'K90 - time schedule'!AV15","v":0},{"$f":"'K90 - time schedule'!AW15","v":0},{"$f":"'K90 - time schedule'!AX15","v":0},{"$f":"'K90 - time schedule'!AY15","v":0},{"$f":"'K90 - time schedule'!AZ15","v":0},{"$f":"'K90 - time schedule'!BA15","v":0},{"$f":"'K90 - time schedule'!BB15","v":0},{"$f":"'K90 - time schedule'!BC15","v":0},{"$f":"'K90 - time schedule'!BD15","v":0},{"$f":"'K90 - time schedule'!BE15","v":0},{"$f":"'K90 - time schedule'!BF15","v":0},{"$f":"'K90 - time schedule'!BG15","v":0},{"$f":"'K90 - time schedule'!BH15","v":0},{"$f":"'K90 - time schedule'!BI15","v":0},{"$f":"'K90 - time schedule'!BJ15","v":0},{"$f":"'K90 - time schedule'!BK15","v":0},{"$f":"'K90 - time schedule'!BL15","v":0},{"$f":"'K90 - time schedule'!BM15","v":0},{"$f":"'K90 - time schedule'!BN15","v":0},{"$f":"'K90 - time schedule'!BO15","v":0},{"$f":"'K90 - time schedule'!BP15","v":0},{"$f":"'K90 - time schedule'!BQ15","v":0},{"$f":"'K90 - time schedule'!BR15","v":0},{"$f":"'K90 - time schedule'!BS15","v":0},{"$f":"'K90 - time schedule'!BT15","v":0},{"$f":"'K90 - time schedule'!BU15","v":0},{"$f":"'K90 - time schedule'!BV15","v":0},{"$f":"'K90 - time schedule'!BW15","v":0},{"$f":"'K90 - time schedule'!BX15","v":0},{"$f":"'K90 - time schedule'!BY15","v":0},{"$f":"'K90 - time schedule'!BZ15","v":0},{"$f":"'K90 - time schedule'!CA15","v":0},{"$f":"'K90 - time schedule'!CB15","v":0},{"$f":"'K90 - time schedule'!CC15","v":0},{"$f":"'K90 - time schedule'!CD15","v":0},{"$f":"'K90 - time schedule'!CE15","v":0},{"$f":"'K90 - time schedule'!CF15","v":0},{"$f":"'K90 - time schedule'!CG15","v":0},{"$f":"'K90 - time schedule'!CH15","v":0},{"$f":"'K90 - time schedule'!CI15","v":0},{"$f":"'K90 - time schedule'!CJ15","v":0},{"$f":"'K90 - time schedule'!CK15","v":0},{"$f":"'K90 - time schedule'!CL15","v":0},{"$f":"'K90 - time schedule'!CM15","v":0},{"$f":"'K90 - time schedule'!CN15","v":0},{"$f":"'K90 - time schedule'!CO15","v":0},{"$f":"'K90 - time schedule'!CP15","v":0},{"$f":"'K90 - time schedule'!CQ15","v":0},{"$f":"'K90 - time schedule'!CR15","v":0},{"$f":"'K90 - time schedule'!CS15","v":0},{"$f":"'K90 - time schedule'!CT15","v":0},{"$f":"'K90 - time schedule'!CU15","v":0},{"$f":"'K90 - time schedule'!CV15","v":0},{"$f":"'K90 - time schedule'!CW15","v":0},{"$f":"'K90 - time schedule'!CX15","v":0},{"$f":"'K90 - time schedule'!CY15","v":0},{"$f":"'K90 - time schedule'!CZ15","v":0},{"$f":"'K90 - time schedule'!DA15","v":0},{"$f":"'K90 - time schedule'!DB15","v":0},{"$f":"'K90 - time schedule'!DC15","v":0},{"$f":"'K90 - time schedule'!DD15","v":0},{"$f":"'K90 - time schedule'!DE15","v":0},{"$f":"'K90 - time schedule'!DF15","v":0},{"$f":"'K90 - time schedule'!DG15","v":0},{"$f":"'K90 - time schedule'!DH15","v":0},{"$f":"'K90 - time schedule'!DI15","v":0},{"$f":"'K90 - time schedule'!DJ15","v":0},{"$f":"'K90 - time schedule'!DK15","v":0},{"$f":"'K90 - time schedule'!DL15","v":0},{"$f":"'K90 - time schedule'!DM15","v":0},{"$f":"'K90 - time schedule'!DN15","v":0},{"$f":"'K90 - time schedule'!DO15","v":0},{"$f":"'K90 - time schedule'!DP15","v":0},{"$f":"'K90 - time schedule'!DQ15","v":0},{"$f":"'K90 - time schedule'!DR15","v":0},{"$f":"'K90 - time schedule'!DS15","v":0},{"$f":"'K90 - time schedule'!DT15","v":0},{"$f":"'K90 - time schedule'!DU15","v":0},{"$f":"'K90 - time schedule'!DV15","v":0},{"$f":"'K90 - time schedule'!DW15","v":0},{"$f":"'K90 - time schedule'!DX15","v":0},{"$f":"'K90 - time schedule'!DY15","v":0},{"$f":"'K90 - time schedule'!DZ15","v":0},{"$f":"'K90 - time schedule'!EA15","v":0},{"$f":"'K90 - time schedule'!EB15","v":0},{"$f":"'K90 - time schedule'!EC15","v":0},{"$f":"'K90 - time schedule'!ED15","v":0},{"$f":"'K90 - time schedule'!EE15","v":0},{"$f":"'K90 - time schedule'!EF15","v":0},{"$f":"'K90 - time schedule'!EG15","v":0},{"$f":"'K90 - time schedule'!EH15","v":0},{"$f":"'K90 - time schedule'!EI15","v":0},{"$f":"'K90 - time schedule'!EJ15","v":0},{"$f":"'K90 - time schedule'!EK15","v":0},{"$f":"'K90 - time schedule'!EL15","v":0},{"$f":"'K90 - time schedule'!EM15","v":0},{"$f":"'K90 - time schedule'!EN15","v":0},{"$f":"'K90 - time schedule'!EO15","v":0},{"$f":"'K90 - time schedule'!EP15","v":0},{"$f":"'K90 - time schedule'!EQ15","v":0},{"$f":"'K90 - time schedule'!ER15","v":0},{"$f":"'K90 - time schedule'!ES15","v":0},{"$f":"'K90 - time schedule'!ET15","v":0},{"$f":"'K90 - time schedule'!EU15","v":0},{"$f":"'K90 - time schedule'!EV15","v":0},{"$f":"'K90 - time schedule'!EW15","v":0},{"$f":"'K90 - time schedule'!EX15","v":0},{"$f":"'K90 - time schedule'!EY15","v":0},{"$f":"'K90 - time schedule'!EZ15","v":0},{"$f":"'K90 - time schedule'!FA15","v":0},{"$f":"'K90 - time schedule'!FB15","v":0},{"$f":"'K90 - time schedule'!FC15","v":0},{"$f":"'K90 - time schedule'!FD15","v":0},{"$f":"'K90 - time schedule'!FE15","v":0},{"$f":"'K90 - time schedule'!FF15","v":0},{"$f":"'K90 - time schedule'!FG15","v":0},{"$f":"'K90 - time schedule'!FH15","v":0},{"$f":"'K90 - time schedule'!FI15","v":0},{"$f":"'K90 - time schedule'!FJ15","v":0},{"$f":"'K90 - time schedule'!FK15","v":0},{"$f":"'K90 - time schedule'!FL15","v":0},{"$f":"'K90 - time schedule'!FM15","v":0},{"$f":"'K90 - time schedule'!FN15","v":0},{"$f":"'K90 - time schedule'!FO15","v":0},{"$f":"'K90 - time schedule'!FP15","v":0},{"$f":"'K90 - time schedule'!FQ15","v":0},{"$f":"'K90 - time schedule'!FR15","v":0},{"$f":"'K90 - time schedule'!FS15","v":0},{"$f":"'K90 - time schedule'!FT15","v":0},{"$f":"'K90 - time schedule'!FU15","v":0},{"$f":"'K90 - time schedule'!FV15","v":0},{"$f":"'K90 - time schedule'!FW15","v":0},{"$f":"'K90 - time schedule'!FX15","v":0},{"$f":"'K90 - time schedule'!FY15","v":0},{"$f":"'K90 - time schedule'!FZ15","v":0},{"$f":"'K90 - time schedule'!GA15","v":0},{"$f":"'K90 - time schedule'!GB15","v":0},{"$f":"'K90 - time schedule'!GC15","v":0},{"$f":"'K90 - time schedule'!GD15","v":0},{"$f":"'K90 - time schedule'!GE15","v":0},{"$f":"'K90 - time schedule'!GF15","v":0},{"$f":"'K20 - time schedule'!GG63","v":0},{"$f":"'K20 - time schedule'!GH63","v":0},{"$f":"'K20 - time schedule'!GI63","v":0},{"$f":"'K20 - time schedule'!GJ63","v":0},{"$f":"'K20 - time schedule'!GK63","v":0},{"$f":"'K20 - time schedule'!GL63","v":0},{"$f":"'K20 - time schedule'!GM63","v":0},{"$f":"'K20 - time schedule'!GN63","v":0},{"$f":"'K20 - time schedule'!GO63","v":0},{"$f":"'K20 - time schedule'!GP63","v":0},{"$f":"'K20 - time schedule'!GQ63","v":0},{"$f":"'K20 - time schedule'!GR63","v":0},{"$f":"'K20 - time schedule'!GS63","v":0},{"$f":"'K20 - time schedule'!GT63","v":0},{"$f":"'K20 - time schedule'!GU63","v":0},{"$f":"'K20 - time schedule'!GV63","v":0},{"$f":"'K20 - time schedule'!GW63","v":0},{"$f":"'K20 - time schedule'!GX63","v":0},{"$f":"'K20 - time schedule'!GY63","v":0},{"$f":"'K20 - time schedule'!GZ63","v":0},{"$f":"'K20 - time schedule'!HA63","v":0},{"$f":"'K20 - time schedule'!HB63","v":0},{"$f":"'K20 - time schedule'!HC63","v":0},{"$f":"'K20 - time schedule'!HD63","v":0},{"$f":"'K20 - time schedule'!HE63","v":0},{"$f":"'K20 - time schedule'!HF63","v":0},{"$f":"'K20 - time schedule'!HG63","v":0},{"$f":"'K20 - time schedule'!HH63","v":0},{"$f":"'K20 - time schedule'!HI63","v":0},{"$f":"'K20 - time schedule'!HJ63","v":0},{"$f":"'K20 - time schedule'!HK63","v":0},{"$f":"'K20 - time schedule'!HL63","v":0},{"$f":"'K20 - time schedule'!HM63","v":0},{"$f":"'K20 - time schedule'!HN63","v":0},{"$f":"'K20 - time schedule'!HO63","v":0},{"$f":"'K20 - time schedule'!HP63","v":0},{"$f":"'K20 - time schedule'!HQ63","v":0},{"$f":"'K20 - time schedule'!HR63","v":0},{"$f":"'K20 - time schedule'!HS63","v":0},{"$f":"'K20 - time schedule'!HT63","v":0},{"$f":"'K20 - time schedule'!HU63","v":0},{"$f":"'K20 - time schedule'!HV63","v":0},{"$f":"'K20 - time schedule'!HW63","v":0},{"$f":"'K20 - time schedule'!HX63","v":0},{"$f":"'K20 - time schedule'!HY63","v":0},{"$f":"'K20 - time schedule'!HZ63","v":0},{"$f":"'K20 - time schedule'!IA63","v":0},{"$f":"'K20 - time schedule'!IB63","v":0},{"$f":"'K20 - time schedule'!IC63","v":0},{"$f":"'K20 - time schedule'!ID63","v":0},{"$f":"'K20 - time schedule'!IE63","v":0},{"$f":"'K20 - time schedule'!IF63","v":0},{"$f":"'K20 - time schedule'!IG63","v":0},{"$f":"'K20 - time schedule'!IH63","v":0},{"$f":"'K20 - time schedule'!II63","v":0},{"$f":"'K20 - time schedule'!IJ63","v":0},{"$f":"'K20 - time schedule'!IK63","v":0},{"$f":"'K20 - time schedule'!IL63","v":0},{"$f":"'K20 - time schedule'!IM63","v":0},{"$f":"'K20 - time schedule'!IN63","v":0},{"$f":"'K20 - time schedule'!IO63","v":0},{"$f":"'K20 - time schedule'!IP63","v":0},{"$f":"'K20 - time schedule'!IQ63","v":0},{"$f":"'K20 - time schedule'!IR63","v":0},{"$f":"'K20 - time schedule'!IS63","v":0},{"$f":"'K20 - time schedule'!IT63","v":0},{"$f":"'K20 - time schedule'!IU63","v":0},{"$f":"'K20 - time schedule'!IV63","v":0},{"$f":"'K20 - time schedule'!IW63","v":0},{"$f":"'K20 - time schedule'!IX63","v":0},{"$f":"'K20 - time schedule'!IY63","v":0},{"$f":"'K20 - time schedule'!IZ63","v":0},{"$f":"'K20 - time schedule'!JA63","v":0},{"$f":"'K20 - time schedule'!JB63","v":0},{"$f":"'K20 - time schedule'!JC63","v":0},{"$f":"'K20 - time schedule'!JD63","v":0},{"$f":"'K20 - time schedule'!JE63","v":0},{"$f":"'K20 - time schedule'!JF63","v":0},{"$f":"'K20 - time schedule'!JG63","v":0},{"$f":"'K20 - time schedule'!JH63","v":0},{"$f":"'K20 - time schedule'!JI63","v":0},{"$f":"'K20 - time schedule'!JJ63","v":0},{"$f":"'K20 - time schedule'!JK63","v":0},{"$f":"'K20 - time schedule'!JL63","v":0},{"$f":"'K20 - time schedule'!JM63","v":0},{"$f":"'K20 - time schedule'!JN63","v":0},{"$f":"'K20 - time schedule'!JO63","v":0},{"$f":"'K20 - time schedule'!JP63","v":0},{"$f":"'K20 - time schedule'!JQ63","v":0},{"$f":"'K20 - time schedule'!JR63","v":0},{"$f":"'K20 - time schedule'!JS63","v":0},{"$f":"'K20 - time schedule'!JT63","v":0},{"$f":"'K20 - time schedule'!JU63","v":0},{"$f":"'K20 - time schedule'!JV63","v":0},{"$f":"'K20 - time schedule'!JW63","v":0},{"$f":"'K20 - time schedule'!JX63","v":0},{"$f":"'K20 - time schedule'!JY63","v":0},{"$f":"'K20 - time schedule'!JZ63","v":0},{"$f":"'K20 - time schedule'!KA63","v":0},{"$f":"'K20 - time schedule'!KB63","v":0},{"$f":"'K20 - time schedule'!KC63","v":0},{"$f":"'K20 - time schedule'!KD63","v":0},{"$f":"'K20 - time schedule'!KE63","v":0},{"$f":"'K20 - time schedule'!KF63","v":0},{"$f":"'K20 - time schedule'!KG63","v":0},{"$f":"'K20 - time schedule'!KH63","v":0},{"$f":"'K20 - time schedule'!KI63","v":0},{"$f":"'K20 - time schedule'!KJ63","v":0},{"$f":"'K20 - time schedule'!KK63","v":0},{"$f":"'K20 - time schedule'!KL63","v":0},{"$f":"'K20 - time schedule'!KM63","v":0},{"$f":"'K20 - time schedule'!KN63","v":0},{"$f":"'K20 - time schedule'!KO63","v":0},{"$f":"'K20 - time schedule'!KP63","v":0},{"$f":"'K20 - time schedule'!KQ63","v":0},{"$f":"'K20 - time schedule'!KR63","v":0},{"$f":"'K20 - time schedule'!KS63","v":0},{"$f":"'K20 - time schedule'!KT63","v":0}]
["Boiler room K90 - approved implementation documentation","K90","EUR",{"$f":"'K90 - time schedule'!G17","v":0},{"$f":"'K90 - time schedule'!H17","v":0},{"$f":"'K90 - time schedule'!I17","v":0},{"$f":"'K90 - time schedule'!J17","v":0},{"$f":"'K90 - time schedule'!K17","v":0},{"$f":"'K90 - time schedule'!L17","v":0},{"$f":"'K90 - time schedule'!M17","v":0},{"$f":"'K90 - time schedule'!N17","v":0},{"$f":"'K90 - time schedule'!O17","v":0},{"$f":"'K90 - time schedule'!P17","v":0},{"$f":"'K90 - time schedule'!Q17","v":0},{"$f":"'K90 - time schedule'!R17","v":0},{"$f":"'K90 - time schedule'!S17","v":0},{"$f":"'K90 - time schedule'!T17","v":0},{"$f":"'K90 - time schedule'!U17","v":0},{"$f":"'K90 - time schedule'!V17","v":0},{"$f":"'K90 - time schedule'!W17","v":0},{"$f":"'K90 - time schedule'!X17","v":0},{"$f":"'K90 - time schedule'!Y17","v":0},{"$f":"'K90 - time schedule'!Z17","v":0},{"$f":"'K90 - time schedule'!AA17","v":0},{"$f":"'K90 - time schedule'!AB17","v":0},{"$f":"'K90 - time schedule'!AC17","v":0},{"$f":"'K90 - time schedule'!AD17","v":0},{"$f":"'K90 - time schedule'!AE17","v":0},{"$f":"'K90 - time schedule'!AF17","v":0},{"$f":"'K90 - time schedule'!AG17","v":0},{"$f":"'K90 - time schedule'!AH17","v":0},{"$f":"'K90 - time schedule'!AI17","v":0},{"$f":"'K90 - time schedule'!AJ17","v":0},{"$f":"'K90 - time schedule'!AK17","v":0},{"$f":"'K90 - time schedule'!AL17","v":0},{"$f":"'K90 - time schedule'!AM17","v":0},{"$f":"'K90 - time schedule'!AN17","v":0},{"$f":"'K90 - time schedule'!AO17","v":0},{"$f":"'K90 - time schedule'!AP17","v":0},{"$f":"'K90 - time schedule'!AQ17","v":0},{"$f":"'K90 - time schedule'!AR17","v":0},{"$f":"'K90 - time schedule'!AS17","v":0},{"$f":"'K90 - time schedule'!AT17","v":0},{"$f":"'K90 - time schedule'!AU17","v":0},{"$f":"'K90 - time schedule'!AV17","v":0},{"$f":"'K90 - time schedule'!AW17","v":0},{"$f":"'K90 - time schedule'!AX17","v":0},{"$f":"'K90 - time schedule'!AY17","v":0},{"$f":"'K90 - time schedule'!AZ17","v":0},{"$f":"'K90 - time schedule'!BA17","v":0},{"$f":"'K90 - time schedule'!BB17","v":0},{"$f":"'K90 - time schedule'!BC17","v":0},{"$f":"'K90 - time schedule'!BD17","v":0},{"$f":"'K90 - time schedule'!BE17","v":0},{"$f":"'K90 - time schedule'!BF17","v":0},{"$f":"'K90 - time schedule'!BG17","v":0},{"$f":"'K90 - time schedule'!BH17","v":0},{"$f":"'K90 - time schedule'!BI17","v":0},{"$f":"'K90 - time schedule'!BJ17","v":0},{"$f":"'K90 - time schedule'!BK17","v":0},{"$f":"'K90 - time schedule'!BL17","v":0},{"$f":"'K90 - time schedule'!BM17","v":0},{"$f":"'K90 - time schedule'!BN17","v":0},{"$f":"'K90 - time schedule'!BO17","v":0},{"$f":"'K90 - time schedule'!BP17","v":0},{"$f":"'K90 - time schedule'!BQ17","v":0},{"$f":"'K90 - time schedule'!BR17","v":0},{"$f":"'K90 - time schedule'!BS17","v":0},{"$f":"'K90 - time schedule'!BT17","v":0},{"$f":"'K90 - time schedule'!BU17","v":0},{"$f":"'K90 - time schedule'!BV17","v":0},{"$f":"'K90 - time schedule'!BW17","v":0},{"$f":"'K90 - time schedule'!BX17","v":0},{"$f":"'K90 - time schedule'!BY17","v":0},{"$f":"'K90 - time schedule'!BZ17","v":0},{"$f":"'K90 - time schedule'!CA17","v":0},{"$f":"'K90 - time schedule'!CB17","v":0},{"$f":"'K90 - time schedule'!CC17","v":0},{"$f":"'K90 - time schedule'!CD17","v":0},{"$f":"'K90 - time schedule'!CE17","v":0},{"$f":"'K90 - time schedule'!CF17","v":0},{"$f":"'K90 - time schedule'!CG17","v":0},{"$f":"'K90 - time schedule'!CH17","v":0},{"$f":"'K90 - time schedule'!CI17","v":0},{"$f":"'K90 - time schedule'!CJ17","v":0},{"$f":"'K90 - time schedule'!CK17","v":0},{"$f":"'K90 - time schedule'!CL17","v":0},{"$f":"'K90 - time schedule'!CM17","v":0},{"$f":"'K90 - time schedule'!CN17","v":0},{"$f":"'K90 - time schedule'!CO17","v":0},{"$f":"'K90 - time schedule'!CP17","v":0},{"$f":"'K90 - time schedule'!CQ17","v":0},{"$f":"'K90 - time schedule'!CR17","v":0},{"$f":"'K90 - time schedule'!CS17","v":0},{"$f":"'K90 - time schedule'!CT17","v":0},{"$f":"'K90 - time schedule'!CU17","v":0},{"$f":"'K90 - time schedule'!CV17","v":0},{"$f":"'K90 - time schedule'!CW17","v":0},{"$f":"'K90 - time schedule'!CX17","v":0},{"$f":"'K90 - time schedule'!CY17","v":0},{"$f":"'K90 - time schedule'!CZ17","v":0},{"$f":"'K90 - time schedule'!DA17","v":0},{"$f":"'K90 - time schedule'!DB17","v":0},{"$f":"'K90 - time schedule'!DC17","v":0},{"$f":"'K90 - time schedule'!DD17","v":0},{"$f":"'K90 - time schedule'!DE17","v":0},{"$f":"'K90 - time schedule'!DF17","v":0},{"$f":"'K90 - time schedule'!DG17","v":0},{"$f":"'K90 - time schedule'!DH17","v":0},{"$f":"'K90 - time schedule'!DI17","v":0},{"$f":"'K90 - time schedule'!DJ17","v":0},{"$f":"'K90 - time schedule'!DK17","v":0},{"$f":"'K90 - time schedule'!DL17","v":0},{"$f":"'K90 - time schedule'!DM17","v":0},{"$f":"'K90 - time schedule'!DN17","v":0},{"$f":"'K90 - time schedule'!DO17","v":0},{"$f":"'K90 - time schedule'!DP17","v":0},{"$f":"'K90 - time schedule'!DQ17","v":0},{"$f":"'K90 - time schedule'!DR17","v":0},{"$f":"'K90 - time schedule'!DS17","v":0},{"$f":"'K90 - time schedule'!DT17","v":0},{"$f":"'K90 - time schedule'!DU17","v":0},{"$f":"'K90 - time schedule'!DV17","v":0},{"$f":"'K90 - time schedule'!DW17","v":0},{"$f":"'K90 - time schedule'!DX17","v":0},{"$f":"'K90 - time schedule'!DY17","v":0},{"$f":"'K90 - time schedule'!DZ17","v":0},{"$f":"'K90 - time schedule'!EA17","v":0},{"$f":"'K90 - time schedule'!EB17","v":0},{"$f":"'K90 - time schedule'!EC17","v":0},{"$f":"'K90 - time schedule'!ED17","v":0},{"$f":"'K90 - time schedule'!EE17","v":0},{"$f":"'K90 - time schedule'!EF17","v":0},{"$f":"'K90 - time schedule'!EG17","v":0},{"$f":"'K90 - time schedule'!EH17","v":0},{"$f":"'K90 - time schedule'!EI17","v":0},{"$f":"'K90 - time schedule'!EJ17","v":0},{"$f":"'K90 - time schedule'!EK17","v":0},{"$f":"'K90 - time schedule'!EL17","v":0},{"$f":"'K90 - time schedule'!EM17","v":0},{"$f":"'K90 - time schedule'!EN17","v":0},{"$f":"'K90 - time schedule'!EO17","v":0},{"$f":"'K90 - time schedule'!EP17","v":0},{"$f":"'K90 - time schedule'!EQ17","v":0},{"$f":"'K90 - time schedule'!ER17","v":0},{"$f":"'K90 - time schedule'!ES17","v":0},{"$f":"'K90 - time schedule'!ET17","v":0},{"$f":"'K90 - time schedule'!EU17","v":0},{"$f":"'K90 - time schedule'!EV17","v":0},{"$f":"'K90 - time schedule'!EW17","v":0},{"$f":"'K90 - time schedule'!EX17","v":0},{"$f":"'K90 - time schedule'!EY17","v":0},{"$f":"'K90 - time schedule'!EZ17","v":0},{"$f":"'K90 - time schedule'!FA17","v":0},{"$f":"'K90 - time schedule'!FB17","v":0},{"$f":"'K90 - time schedule'!FC17","v":0},{"$f":"'K90 - time schedule'!FD17","v":0},{"$f":"'K90 - time schedule'!FE17","v":0},{"$f":"'K90 - time schedule'!FF17","v":0},{"$f":"'K90 - time schedule'!FG17","v":0},{"$f":"'K90 - time schedule'!FH17","v":0},{"$f":"'K90 - time schedule'!FI17","v":0},{"$f":"'K90 - time schedule'!FJ17","v":0},{"$f":"'K90 - time schedule'!FK17","v":0},{"$f":"'K90 - time schedule'!FL17","v":0},{"$f":"'K90 - time schedule'!FM17","v":0},{"$f":"'K90 - time schedule'!FN17","v":0},{"$f":"'K90 - time schedule'!FO17","v":0},{"$f":"'K90 - time schedule'!FP17","v":0},{"$f":"'K90 - time schedule'!FQ17","v":0},{"$f":"'K90 - time schedule'!FR17","v":0},{"$f":"'K90 - time schedule'!FS17","v":0},{"$f":"'K90 - time schedule'!FT17","v":0},{"$f":"'K90 - time schedule'!FU17","v":0},{"$f":"'K90 - time schedule'!FV17","v":0},{"$f":"'K90 - time schedule'!FW17","v":0},{"$f":"'K90 - time schedule'!FX17","v":0},{"$f":"'K90 - time schedule'!FY17","v":0},{"$f":"'K90 - time schedule'!FZ17","v":0},{"$f":"'K90 - time schedule'!GA17","v":0},{"$f":"'K90 - time schedule'!GB17","v":0},{"$f":"'K90 - time schedule'!GC17","v":0},{"$f":"'K90 - time schedule'!GD17","v":0},{"$f":"'K90 - time schedule'!GE17","v":0},{"$f":"'K90 - time schedule'!GF17","v":0},{"$f":"'K20 - time schedule'!GG64","v":0},{"$f":"'K20 - time schedule'!GH64","v":0},{"$f":"'K20 - time schedule'!GI64","v":0},{"$f":"'K20 - time schedule'!GJ64","v":0},{"$f":"'K20 - time schedule'!GK64","v":0},{"$f":"'K20 - time schedule'!GL64","v":0},{"$f":"'K20 - time schedule'!GM64","v":0},{"$f":"'K20 - time schedule'!GN64","v":0},{"$f":"'K20 - time schedule'!GO64","v":0},{"$f":"'K20 - time schedule'!GP64","v":0},{"$f":"'K20 - time schedule'!GQ64","v":0},{"$f":"'K20 - time schedule'!GR64","v":0},{"$f":"'K20 - time schedule'!GS64","v":0},{"$f":"'K20 - time schedule'!GT64","v":0},{"$f":"'K20 - time schedule'!GU64","v":0},{"$f":"'K20 - time schedule'!GV64","v":0},{"$f":"'K20 - time schedule'!GW64","v":0},{"$f":"'K20 - time schedule'!GX64","v":0},{"$f":"'K20 - time schedule'!GY64","v":0},{"$f":"'K20 - time schedule'!GZ64","v":0},{"$f":"'K20 - time schedule'!HA64","v":0},{"$f":"'K20 - time schedule'!HB64","v":0},{"$f":"'K20 - time schedule'!HC64","v":0},{"$f":"'K20 - time schedule'!HD64","v":0},{"$f":"'K20 - time schedule'!HE64","v":0},{"$f":"'K20 - time schedule'!HF64","v":0},{"$f":"'K20 - time schedule'!HG64","v":0},{"$f":"'K20 - time schedule'!HH64","v":0},{"$f":"'K20 - time schedule'!HI64","v":0},{"$f":"'K20 - time schedule'!HJ64","v":0},{"$f":"'K20 - time schedule'!HK64","v":0},{"$f":"'K20 - time schedule'!HL64","v":0},{"$f":"'K20 - time schedule'!HM64","v":0},{"$f":"'K20 - time schedule'!HN64","v":0},{"$f":"'K20 - time schedule'!HO64","v":0},{"$f":"'K20 - time schedule'!HP64","v":0},{"$f":"'K20 - time schedule'!HQ64","v":0},{"$f":"'K20 - time schedule'!HR64","v":0},{"$f":"'K20 - time schedule'!HS64","v":0},{"$f":"'K20 - time schedule'!HT64","v":0},{"$f":"'K20 - time schedule'!HU64","v":0},{"$f":"'K20 - time schedule'!HV64","v":0},{"$f":"'K20 - time schedule'!HW64","v":0},{"$f":"'K20 - time schedule'!HX64","v":0},{"$f":"'K20 - time schedule'!HY64","v":0},{"$f":"'K20 - time schedule'!HZ64","v":0},{"$f":"'K20 - time schedule'!IA64","v":0},{"$f":"'K20 - time schedule'!IB64","v":0},{"$f":"'K20 - time schedule'!IC64","v":0},{"$f":"'K20 - time schedule'!ID64","v":0},{"$f":"'K20 - time schedule'!IE64","v":0},{"$f":"'K20 - time schedule'!IF64","v":0},{"$f":"'K20 - time schedule'!IG64","v":0},{"$f":"'K20 - time schedule'!IH64","v":0},{"$f":"'K20 - time schedule'!II64","v":0},{"$f":"'K20 - time schedule'!IJ64","v":0},{"$f":"'K20 - time schedule'!IK64","v":0},{"$f":"'K20 - time schedule'!IL64","v":0},{"$f":"'K20 - time schedule'!IM64","v":0},{"$f":"'K20 - time schedule'!IN64","v":0},{"$f":"'K20 - time schedule'!IO64","v":0},{"$f":"'K20 - time schedule'!IP64","v":0},{"$f":"'K20 - time schedule'!IQ64","v":0},{"$f":"'K20 - time schedule'!IR64","v":0},{"$f":"'K20 - time schedule'!IS64","v":0},{"$f":"'K20 - time schedule'!IT64","v":0},{"$f":"'K20 - time schedule'!IU64","v":0},{"$f":"'K20 - time schedule'!IV64","v":0},{"$f":"'K20 - time schedule'!IW64","v":0},{"$f":"'K20 - time schedule'!IX64","v":0},{"$f":"'K20 - time schedule'!IY64","v":0},{"$f":"'K20 - time schedule'!IZ64","v":0},{"$f":"'K20 - time schedule'!JA64","v":0},{"$f":"'K20 - time schedule'!JB64","v":0},{"$f":"'K20 - time schedule'!JC64","v":0},{"$f":"'K20 - time schedule'!JD64","v":0},{"$f":"'K20 - time schedule'!JE64","v":0},{"$f":"'K20 - time schedule'!JF64","v":0},{"$f":"'K20 - time schedule'!JG64","v":0},{"$f":"'K20 - time schedule'!JH64","v":0},{"$f":"'K20 - time schedule'!JI64","v":0},{"$f":"'K20 - time schedule'!JJ64","v":0},{"$f":"'K20 - time schedule'!JK64","v":0},{"$f":"'K20 - time schedule'!JL64","v":0},{"$f":"'K20 - time schedule'!JM64","v":0},{"$f":"'K20 - time schedule'!JN64","v":0},{"$f":"'K20 - time schedule'!JO64","v":0},{"$f":"'K20 - time schedule'!JP64","v":0},{"$f":"'K20 - time schedule'!JQ64","v":0},{"$f":"'K20 - time schedule'!JR64","v":0},{"$f":"'K20 - time schedule'!JS64","v":0},{"$f":"'K20 - time schedule'!JT64","v":0},{"$f":"'K20 - time schedule'!JU64","v":0},{"$f":"'K20 - time schedule'!JV64","v":0},{"$f":"'K20 - time schedule'!JW64","v":0},{"$f":"'K20 - time schedule'!JX64","v":0},{"$f":"'K20 - time schedule'!JY64","v":0},{"$f":"'K20 - time schedule'!JZ64","v":0},{"$f":"'K20 - time schedule'!KA64","v":0},{"$f":"'K20 - time schedule'!KB64","v":0},{"$f":"'K20 - time schedule'!KC64","v":0},{"$f":"'K20 - time schedule'!KD64","v":0},{"$f":"'K20 - time schedule'!KE64","v":0},{"$f":"'K20 - time schedule'!KF64","v":0},{"$f":"'K20 - time schedule'!KG64","v":0},{"$f":"'K20 - time schedule'!KH64","v":0},{"$f":"'K20 - time schedule'!KI64","v":0},{"$f":"'K20 - time schedule'!KJ64","v":0},{"$f":"'K20 - time schedule'!KK64","v":0},{"$f":"'K20 - time schedule'!KL64","v":0},{"$f":"'K20 - time schedule'!KM64","v":0},{"$f":"'K20 - time schedule'!KN64","v":0},{"$f":"'K20 - time schedule'!KO64","v":0},{"$f":"'K20 - time schedule'!KP64","v":0},{"$f":"'K20 - time schedule'!KQ64","v":0},{"$f":"'K20 - time schedule'!KR64","v":0},{"$f":"'K20 - time schedule'!KS64","v":0},{"$f":"'K20 - time schedule'!KT64","v":0}]
["Boiler room K90 - dismantling","K90","EUR",{"$f":"'K90 - time schedule'!G21","v":0},{"$f":"'K90 - time schedule'!H21","v":0},{"$f":"'K90 - time schedule'!I21","v":0},{"$f":"'K90 - time schedule'!J21","v":0},{"$f":"'K90 - time schedule'!K21","v":0},{"$f":"'K90 - time schedule'!L21","v":0},{"$f":"'K90 - time schedule'!M21","v":0},{"$f":"'K90 - time schedule'!N21","v":0},{"$f":"'K90 - time schedule'!O21","v":0},{"$f":"'K90 - time schedule'!P21","v":0},{"$f":"'K90 - time schedule'!Q21","v":0},{"$f":"'K90 - time schedule'!R21","v":0},{"$f":"'K90 - time schedule'!S21","v":0},{"$f":"'K90 - time schedule'!T21","v":0},{"$f":"'K90 - time schedule'!U21","v":0},{"$f":"'K90 - time schedule'!V21","v":0},{"$f":"'K90 - time schedule'!W21","v":0},{"$f":"'K90 - time schedule'!X21","v":0},{"$f":"'K90 - time schedule'!Y21","v":0},{"$f":"'K90 - time schedule'!Z21","v":0},{"$f":"'K90 - time schedule'!AA21","v":0},{"$f":"'K90 - time schedule'!AB21","v":0},{"$f":"'K90 - time schedule'!AC21","v":0},{"$f":"'K90 - time schedule'!AD21","v":0},{"$f":"'K90 - time schedule'!AE21","v":0},{"$f":"'K90 - time schedule'!AF21","v":0},{"$f":"'K90 - time schedule'!AG21","v":0},{"$f":"'K90 - time schedule'!AH21","v":0},{"$f":"'K90 - time schedule'!AI21","v":0},{"$f":"'K90 - time schedule'!AJ21","v":0},{"$f":"'K90 - time schedule'!AK21","v":0},{"$f":"'K90 - time schedule'!AL21","v":0},{"$f":"'K90 - time schedule'!AM21","v":0},{"$f":"'K90 - time schedule'!AN21","v":0},{"$f":"'K90 - time schedule'!AO21","v":0},{"$f":"'K90 - time schedule'!AP21","v":0},{"$f":"'K90 - time schedule'!AQ21","v":0},{"$f":"'K90 - time schedule'!AR21","v":0},{"$f":"'K90 - time schedule'!AS21","v":0},{"$f":"'K90 - time schedule'!AT21","v":0},{"$f":"'K90 - time schedule'!AU21","v":0},{"$f":"'K90 - time schedule'!AV21","v":0},{"$f":"'K90 - time schedule'!AW21","v":0},{"$f":"'K90 - time schedule'!AX21","v":0},{"$f":"'K90 - time schedule'!AY21","v":0},{"$f":"'K90 - time schedule'!AZ21","v":0},{"$f":"'K90 - time schedule'!BA21","v":0},{"$f":"'K90 - time schedule'!BB21","v":0},{"$f":"'K90 - time schedule'!BC21","v":0},{"$f":"'K90 - time schedule'!BD21","v":0},{"$f":"'K90 - time schedule'!BE21","v":0},{"$f":"'K90 - time schedule'!BF21","v":0},{"$f":"'K90 - time schedule'!BG21","v":0},{"$f":"'K90 - time schedule'!BH21","v":0},{"$f":"'K90 - time schedule'!BI21","v":0},{"$f":"'K90 - time schedule'!BJ21","v":0},{"$f":"'K90 - time schedule'!BK21","v":0},{"$f":"'K90 - time schedule'!BL21","v":0},{"$f":"'K90 - time schedule'!BM21","v":0},{"$f":"'K90 - time schedule'!BN21","v":0},{"$f":"'K90 - time schedule'!BO21","v":0},{"$f":"'K90 - time schedule'!BP21","v":0},{"$f":"'K90 - time schedule'!BQ21","v":0},{"$f":"'K90 - time schedule'!BR21","v":0},{"$f":"'K90 - time schedule'!BS21","v":0},{"$f":"'K90 - time schedule'!BT21","v":0},{"$f":"'K90 - time schedule'!BU21","v":0},{"$f":"'K90 - time schedule'!BV21","v":0},{"$f":"'K90 - time schedule'!BW21","v":0},{"$f":"'K90 - time schedule'!BX21","v":0},{"$f":"'K90 - time schedule'!BY21","v":0},{"$f":"'K90 - time schedule'!BZ21","v":0},{"$f":"'K90 - time schedule'!CA21","v":0},{"$f":"'K90 - time schedule'!CB21","v":0},{"$f":"'K90 - time schedule'!CC21","v":0},{"$f":"'K90 - time schedule'!CD21","v":0},{"$f":"'K90 - time schedule'!CE21","v":0},{"$f":"'K90 - time schedule'!CF21","v":0},{"$f":"'K90 - time schedule'!CG21","v":0},{"$f":"'K90 - time schedule'!CH21","v":0},{"$f":"'K90 - time schedule'!CI21","v":0},{"$f":"'K90 - time schedule'!CJ21","v":0},{"$f":"'K90 - time schedule'!CK21","v":0},{"$f":"'K90 - time schedule'!CL21","v":0},{"$f":"'K90 - time schedule'!CM21","v":0},{"$f":"'K90 - time schedule'!CN21","v":0},{"$f":"'K90 - time schedule'!CO21","v":0},{"$f":"'K90 - time schedule'!CP21","v":0},{"$f":"'K90 - time schedule'!CQ21","v":0},{"$f":"'K90 - time schedule'!CR21","v":0},{"$f":"'K90 - time schedule'!CS21","v":0},{"$f":"'K90 - time schedule'!CT21","v":0},{"$f":"'K90 - time schedule'!CU21","v":0},{"$f":"'K90 - time schedule'!CV21","v":0},{"$f":"'K90 - time schedule'!CW21","v":0},{"$f":"'K90 - time schedule'!CX21","v":0},{"$f":"'K90 - time schedule'!CY21","v":0},{"$f":"'K90 - time schedule'!CZ21","v":0},{"$f":"'K90 - time schedule'!DA21","v":0},{"$f":"'K90 - time schedule'!DB21","v":0},{"$f":"'K90 - time schedule'!DC21","v":0},{"$f":"'K90 - time schedule'!DD21","v":0},{"$f":"'K90 - time schedule'!DE21","v":0},{"$f":"'K90 - time schedule'!DF21","v":0},{"$f":"'K90 - time schedule'!DG21","v":0},{"$f":"'K90 - time schedule'!DH21","v":0},{"$f":"'K90 - time schedule'!DI21","v":0},{"$f":"'K90 - time schedule'!DJ21","v":0},{"$f":"'K90 - time schedule'!DK21","v":0},{"$f":"'K90 - time schedule'!DL21","v":0},{"$f":"'K90 - time schedule'!DM21","v":0},{"$f":"'K90 - time schedule'!DN21","v":0},{"$f":"'K90 - time schedule'!DO21","v":0},{"$f":"'K90 - time schedule'!DP21","v":0},{"$f":"'K90 - time schedule'!DQ21","v":0},{"$f":"'K90 - time schedule'!DR21","v":0},{"$f":"'K90 - time schedule'!DS21","v":0},{"$f":"'K90 - time schedule'!DT21","v":0},{"$f":"'K90 - time schedule'!DU21","v":0},{"$f":"'K90 - time schedule'!DV21","v":0},{"$f":"'K90 - time schedule'!DW21","v":0},{"$f":"'K90 - time schedule'!DX21","v":0},{"$f":"'K90 - time schedule'!DY21","v":0},{"$f":"'K90 - time schedule'!DZ21","v":0},{"$f":"'K90 - time schedule'!EA21","v":0},{"$f":"'K90 - time schedule'!EB21","v":0},{"$f":"'K90 - time schedule'!EC21","v":0},{"$f":"'K90 - time schedule'!ED21","v":0},{"$f":"'K90 - time schedule'!EE21","v":0},{"$f":"'K90 - time schedule'!EF21","v":0},{"$f":"'K90 - time schedule'!EG21","v":0},{"$f":"'K90 - time schedule'!EH21","v":0},{"$f":"'K90 - time schedule'!EI21","v":0},{"$f":"'K90 - time schedule'!EJ21","v":0},{"$f":"'K90 - time schedule'!EK21","v":0},{"$f":"'K90 - time schedule'!EL21","v":0},{"$f":"'K90 - time schedule'!EM21","v":0},{"$f":"'K90 - time schedule'!EN21","v":0},{"$f":"'K90 - time schedule'!EO21","v":0},{"$f":"'K90 - time schedule'!EP21","v":0},{"$f":"'K90 - time schedule'!EQ21","v":0},{"$f":"'K90 - time schedule'!ER21","v":0},{"$f":"'K90 - time schedule'!ES21","v":0},{"$f":"'K90 - time schedule'!ET21","v":0},{"$f":"'K90 - time schedule'!EU21","v":0},{"$f":"'K90 - time schedule'!EV21","v":0},{"$f":"'K90 - time schedule'!EW21","v":0},{"$f":"'K90 - time schedule'!EX21","v":0},{"$f":"'K90 - time schedule'!EY21","v":0},{"$f":"'K90 - time schedule'!EZ21","v":0},{"$f":"'K90 - time schedule'!FA21","v":0},{"$f":"'K90 - time schedule'!FB21","v":0},{"$f":"'K90 - time schedule'!FC21","v":0},{"$f":"'K90 - time schedule'!FD21","v":0},{"$f":"'K90 - time schedule'!FE21","v":0},{"$f":"'K90 - time schedule'!FF21","v":0},{"$f":"'K90 - time schedule'!FG21","v":0},{"$f":"'K90 - time schedule'!FH21","v":0},{"$f":"'K90 - time schedule'!FI21","v":0},{"$f":"'K90 - time schedule'!FJ21","v":0},{"$f":"'K90 - time schedule'!FK21","v":0},{"$f":"'K90 - time schedule'!FL21","v":0},{"$f":"'K90 - time schedule'!FM21","v":0},{"$f":"'K90 - time schedule'!FN21","v":0},{"$f":"'K90 - time schedule'!FO21","v":0},{"$f":"'K90 - time schedule'!FP21","v":0},{"$f":"'K90 - time schedule'!FQ21","v":0},{"$f":"'K90 - time schedule'!FR21","v":0},{"$f":"'K90 - time schedule'!FS21","v":0},{"$f":"'K90 - time schedule'!FT21","v":0},{"$f":"'K90 - time schedule'!FU21","v":0},{"$f":"'K90 - time schedule'!FV21","v":0},{"$f":"'K90 - time schedule'!FW21","v":0},{"$f":"'K90 - time schedule'!FX21","v":0},{"$f":"'K90 - time schedule'!FY21","v":0},{"$f":"'K90 - time schedule'!FZ21","v":0},{"$f":"'K90 - time schedule'!GA21","v":0},{"$f":"'K90 - time schedule'!GB21","v":0},{"$f":"'K90 - time schedule'!GC21","v":0},{"$f":"'K90 - time schedule'!GD21","v":0},{"$f":"'K90 - time schedule'!GE21","v":0},{"$f":"'K90 - time schedule'!GF21","v":0},{"$f":"'K20 - time schedule'!GG65","v":0},{"$f":"'K20 - time schedule'!GH65","v":0},{"$f":"'K20 - time schedule'!GI65","v":0},{"$f":"'K20 - time schedule'!GJ65","v":0},{"$f":"'K20 - time schedule'!GK65","v":0},{"$f":"'K20 - time schedule'!GL65","v":0},{"$f":"'K20 - time schedule'!GM65","v":0},{"$f":"'K20 - time schedule'!GN65","v":0},{"$f":"'K20 - time schedule'!GO65","v":0},{"$f":"'K20 - time schedule'!GP65","v":0},{"$f":"'K20 - time schedule'!GQ65","v":0},{"$f":"'K20 - time schedule'!GR65","v":0},{"$f":"'K20 - time schedule'!GS65","v":0},{"$f":"'K20 - time schedule'!GT65","v":0},{"$f":"'K20 - time schedule'!GU65","v":0},{"$f":"'K20 - time schedule'!GV65","v":0},{"$f":"'K20 - time schedule'!GW65","v":0},{"$f":"'K20 - time schedule'!GX65","v":0},{"$f":"'K20 - time schedule'!GY65","v":0},{"$f":"'K20 - time schedule'!GZ65","v":0},{"$f":"'K20 - time schedule'!HA65","v":0},{"$f":"'K20 - time schedule'!HB65","v":0},{"$f":"'K20 - time schedule'!HC65","v":0},{"$f":"'K20 - time schedule'!HD65","v":0},{"$f":"'K20 - time schedule'!HE65","v":0},{"$f":"'K20 - time schedule'!HF65","v":0},{"$f":"'K20 - time schedule'!HG65","v":0},{"$f":"'K20 - time schedule'!HH65","v":0},{"$f":"'K20 - time schedule'!HI65","v":0},{"$f":"'K20 - time schedule'!HJ65","v":0},{"$f":"'K20 - time schedule'!HK65","v":0},{"$f":"'K20 - time schedule'!HL65","v":0},{"$f":"'K20 - time schedule'!HM65","v":0},{"$f":"'K20 - time schedule'!HN65","v":0},{"$f":"'K20 - time schedule'!HO65","v":0},{"$f":"'K20 - time schedule'!HP65","v":0},{"$f":"'K20 - time schedule'!HQ65","v":0},{"$f":"'K20 - time schedule'!HR65","v":0},{"$f":"'K20 - time schedule'!HS65","v":0},{"$f":"'K20 - time schedule'!HT65","v":0},{"$f":"'K20 - time schedule'!HU65","v":0},{"$f":"'K20 - time schedule'!HV65","v":0},{"$f":"'K20 - time schedule'!HW65","v":0},{"$f":"'K20 - time schedule'!HX65","v":0},{"$f":"'K20 - time schedule'!HY65","v":0},{"$f":"'K20 - time schedule'!HZ65","v":0},{"$f":"'K20 - time schedule'!IA65","v":0},{"$f":"'K20 - time schedule'!IB65","v":0},{"$f":"'K20 - time schedule'!IC65","v":0},{"$f":"'K20 - time schedule'!ID65","v":0},{"$f":"'K20 - time schedule'!IE65","v":0},{"$f":"'K20 - time schedule'!IF65","v":0},{"$f":"'K20 - time schedule'!IG65","v":0},{"$f":"'K20 - time schedule'!IH65","v":0},{"$f":"'K20 - time schedule'!II65","v":0},{"$f":"'K20 - time schedule'!IJ65","v":0},{"$f":"'K20 - time schedule'!IK65","v":0},{"$f":"'K20 - time schedule'!IL65","v":0},{"$f":"'K20 - time schedule'!IM65","v":0},{"$f":"'K20 - time schedule'!IN65","v":0},{"$f":"'K20 - time schedule'!IO65","v":0},{"$f":"'K20 - time schedule'!IP65","v":0},{"$f":"'K20 - time schedule'!IQ65","v":0},{"$f":"'K20 - time schedule'!IR65","v":0},{"$f":"'K20 - time schedule'!IS65","v":0},{"$f":"'K20 - time schedule'!IT65","v":0},{"$f":"'K20 - time schedule'!IU65","v":0},{"$f":"'K20 - time schedule'!IV65","v":0},{"$f":"'K20 - time schedule'!IW65","v":0},{"$f":"'K20 - time schedule'!IX65","v":0},{"$f":"'K20 - time schedule'!IY65","v":0},{"$f":"'K20 - time schedule'!IZ65","v":0},{"$f":"'K20 - time schedule'!JA65","v":0},{"$f":"'K20 - time schedule'!JB65","v":0},{"$f":"'K20 - time schedule'!JC65","v":0},{"$f":"'K20 - time schedule'!JD65","v":0},{"$f":"'K20 - time schedule'!JE65","v":0},{"$f":"'K20 - time schedule'!JF65","v":0},{"$f":"'K20 - time schedule'!JG65","v":0},{"$f":"'K20 - time schedule'!JH65","v":0},{"$f":"'K20 - time schedule'!JI65","v":0},{"$f":"'K20 - time schedule'!JJ65","v":0},{"$f":"'K20 - time schedule'!JK65","v":0},{"$f":"'K20 - time schedule'!JL65","v":0},{"$f":"'K20 - time schedule'!JM65","v":0},{"$f":"'K20 - time schedule'!JN65","v":0},{"$f":"'K20 - time schedule'!JO65","v":0},{"$f":"'K20 - time schedule'!JP65","v":0},{"$f":"'K20 - time schedule'!JQ65","v":0},{"$f":"'K20 - time schedule'!JR65","v":0},{"$f":"'K20 - time schedule'!JS65","v":0},{"$f":"'K20 - time schedule'!JT65","v":0},{"$f":"'K20 - time schedule'!JU65","v":0},{"$f":"'K20 - time schedule'!JV65","v":0},{"$f":"'K20 - time schedule'!JW65","v":0},{"$f":"'K20 - time schedule'!JX65","v":0},{"$f":"'K20 - time schedule'!JY65","v":0},{"$f":"'K20 - time schedule'!JZ65","v":0},{"$f":"'K20 - time schedule'!KA65","v":0},{"$f":"'K20 - time schedule'!KB65","v":0},{"$f":"'K20 - time schedule'!KC65","v":0},{"$f":"'K20 - time schedule'!KD65","v":0},{"$f":"'K20 - time schedule'!KE65","v":0},{"$f":"'K20 - time schedule'!KF65","v":0},{"$f":"'K20 - time schedule'!KG65","v":0},{"$f":"'K20 - time schedule'!KH65","v":0},{"$f":"'K20 - time schedule'!KI65","v":0},{"$f":"'K20 - time schedule'!KJ65","v":0},{"$f":"'K20 - time schedule'!KK65","v":0},{"$f":"'K20 - time schedule'!KL65","v":0},{"$f":"'K20 - time schedule'!KM65","v":0},{"$f":"'K20 - time schedule'!KN65","v":0},{"$f":"'K20 - time schedule'!KO65","v":0},{"$f":"'K20 - time schedule'!KP65","v":0},{"$f":"'K20 - time schedule'!KQ65","v":0},{"$f":"'K20 - time schedule'!KR65","v":0},{"$f":"'K20 - time schedule'!KS65","v":0},{"$f":"'K20 - time schedule'!KT65","v":0}]
["Boiler room K90 - supply of combustion air","K90","EUR",{"$f":"'K90 - time schedule'!G23","v":0},{"$f":"'K90 - time schedule'!H23","v":0},{"$f":"'K90 - time schedule'!I23","v":0},{"$f":"'K90 - time schedule'!J23","v":0},{"$f":"'K90 - time schedule'!K23","v":0},{"$f":"'K90 - time schedule'!L23","v":0},{"$f":"'K90 - time schedule'!M23","v":0},{"$f":"'K90 - time schedule'!N23","v":0},{"$f":"'K90 - time schedule'!O23","v":0},{"$f":"'K90 - time schedule'!P23","v":0},{"$f":"'K90 - time schedule'!Q23","v":0},{"$f":"'K90 - time schedule'!R23","v":0},{"$f":"'K90 - time schedule'!S23","v":0},{"$f":"'K90 - time schedule'!T23","v":0},{"$f":"'K90 - time schedule'!U23","v":0},{"$f":"'K90 - time schedule'!V23","v":0},{"$f":"'K90 - time schedule'!W23","v":0},{"$f":"'K90 - time schedule'!X23","v":0},{"$f":"'K90 - time schedule'!Y23","v":0},{"$f":"'K90 - time schedule'!Z23","v":0},{"$f":"'K90 - time schedule'!AA23","v":0},{"$f":"'K90 - time schedule'!AB23","v":0},{"$f":"'K90 - time schedule'!AC23","v":0},{"$f":"'K90 - time schedule'!AD23","v":0},{"$f":"'K90 - time schedule'!AE23","v":0},{"$f":"'K90 - time schedule'!AF23","v":0},{"$f":"'K90 - time schedule'!AG23","v":0},{"$f":"'K90 - time schedule'!AH23","v":0},{"$f":"'K90 - time schedule'!AI23","v":0},{"$f":"'K90 - time schedule'!AJ23","v":0},{"$f":"'K90 - time schedule'!AK23","v":0},{"$f":"'K90 - time schedule'!AL23","v":0},{"$f":"'K90 - time schedule'!AM23","v":0},{"$f":"'K90 - time schedule'!AN23","v":0},{"$f":"'K90 - time schedule'!AO23","v":0},{"$f":"'K90 - time schedule'!AP23","v":0},{"$f":"'K90 - time schedule'!AQ23","v":0},{"$f":"'K90 - time schedule'!AR23","v":0},{"$f":"'K90 - time schedule'!AS23","v":0},{"$f":"'K90 - time schedule'!AT23","v":0},{"$f":"'K90 - time schedule'!AU23","v":0},{"$f":"'K90 - time schedule'!AV23","v":0},{"$f":"'K90 - time schedule'!AW23","v":0},{"$f":"'K90 - time schedule'!AX23","v":0},{"$f":"'K90 - time schedule'!AY23","v":0},{"$f":"'K90 - time schedule'!AZ23","v":0},{"$f":"'K90 - time schedule'!BA23","v":0},{"$f":"'K90 - time schedule'!BB23","v":0},{"$f":"'K90 - time schedule'!BC23","v":0},{"$f":"'K90 - time schedule'!BD23","v":0},{"$f":"'K90 - time schedule'!BE23","v":0},{"$f":"'K90 - time schedule'!BF23","v":0},{"$f":"'K90 - time schedule'!BG23","v":0},{"$f":"'K90 - time schedule'!BH23","v":0},{"$f":"'K90 - time schedule'!BI23","v":0},{"$f":"'K90 - time schedule'!BJ23","v":0},{"$f":"'K90 - time schedule'!BK23","v":0},{"$f":"'K90 - time schedule'!BL23","v":0},{"$f":"'K90 - time schedule'!BM23","v":0},{"$f":"'K90 - time schedule'!BN23","v":0},{"$f":"'K90 - time schedule'!BO23","v":0},{"$f":"'K90 - time schedule'!BP23","v":0},{"$f":"'K90 - time schedule'!BQ23","v":0},{"$f":"'K90 - time schedule'!BR23","v":0},{"$f":"'K90 - time schedule'!BS23","v":0},{"$f":"'K90 - time schedule'!BT23","v":0},{"$f":"'K90 - time schedule'!BU23","v":0},{"$f":"'K90 - time schedule'!BV23","v":0},{"$f":"'K90 - time schedule'!BW23","v":0},{"$f":"'K90 - time schedule'!BX23","v":0},{"$f":"'K90 - time schedule'!BY23","v":0},{"$f":"'K90 - time schedule'!BZ23","v":0},{"$f":"'K90 - time schedule'!CA23","v":0},{"$f":"'K90 - time schedule'!CB23","v":0},{"$f":"'K90 - time schedule'!CC23","v":0},{"$f":"'K90 - time schedule'!CD23","v":0},{"$f":"'K90 - time schedule'!CE23","v":0},{"$f":"'K90 - time schedule'!CF23","v":0},{"$f":"'K90 - time schedule'!CG23","v":0},{"$f":"'K90 - time schedule'!CH23","v":0},{"$f":"'K90 - time schedule'!CI23","v":0},{"$f":"'K90 - time schedule'!CJ23","v":0},{"$f":"'K90 - time schedule'!CK23","v":0},{"$f":"'K90 - time schedule'!CL23","v":0},{"$f":"'K90 - time schedule'!CM23","v":0},{"$f":"'K90 - time schedule'!CN23","v":0},{"$f":"'K90 - time schedule'!CO23","v":0},{"$f":"'K90 - time schedule'!CP23","v":0},{"$f":"'K90 - time schedule'!CQ23","v":0},{"$f":"'K90 - time schedule'!CR23","v":0},{"$f":"'K90 - time schedule'!CS23","v":0},{"$f":"'K90 - time schedule'!CT23","v":0},{"$f":"'K90 - time schedule'!CU23","v":0},{"$f":"'K90 - time schedule'!CV23","v":0},{"$f":"'K90 - time schedule'!CW23","v":0},{"$f":"'K90 - time schedule'!CX23","v":0},{"$f":"'K90 - time schedule'!CY23","v":0},{"$f":"'K90 - time schedule'!CZ23","v":0},{"$f":"'K90 - time schedule'!DA23","v":0},{"$f":"'K90 - time schedule'!DB23","v":0},{"$f":"'K90 - time schedule'!DC23","v":0},{"$f":"'K90 - time schedule'!DD23","v":0},{"$f":"'K90 - time schedule'!DE23","v":0},{"$f":"'K90 - time schedule'!DF23","v":0},{"$f":"'K90 - time schedule'!DG23","v":0},{"$f":"'K90 - time schedule'!DH23","v":0},{"$f":"'K90 - time schedule'!DI23","v":0},{"$f":"'K90 - time schedule'!DJ23","v":0},{"$f":"'K90 - time schedule'!DK23","v":0},{"$f":"'K90 - time schedule'!DL23","v":0},{"$f":"'K90 - time schedule'!DM23","v":0},{"$f":"'K90 - time schedule'!DN23","v":0},{"$f":"'K90 - time schedule'!DO23","v":0},{"$f":"'K90 - time schedule'!DP23","v":0},{"$f":"'K90 - time schedule'!DQ23","v":0},{"$f":"'K90 - time schedule'!DR23","v":0},{"$f":"'K90 - time schedule'!DS23","v":0},{"$f":"'K90 - time schedule'!DT23","v":0},{"$f":"'K90 - time schedule'!DU23","v":0},{"$f":"'K90 - time schedule'!DV23","v":0},{"$f":"'K90 - time schedule'!DW23","v":0},{"$f":"'K90 - time schedule'!DX23","v":0},{"$f":"'K90 - time schedule'!DY23","v":0},{"$f":"'K90 - time schedule'!DZ23","v":0},{"$f":"'K90 - time schedule'!EA23","v":0},{"$f":"'K90 - time schedule'!EB23","v":0},{"$f":"'K90 - time schedule'!EC23","v":0},{"$f":"'K90 - time schedule'!ED23","v":0},{"$f":"'K90 - time schedule'!EE23","v":0},{"$f":"'K90 - time schedule'!EF23","v":0},{"$f":"'K90 - time schedule'!EG23","v":0},{"$f":"'K90 - time schedule'!EH23","v":0},{"$f":"'K90 - time schedule'!EI23","v":0},{"$f":"'K90 - time schedule'!EJ23","v":0},{"$f":"'K90 - time schedule'!EK23","v":0},{"$f":"'K90 - time schedule'!EL23","v":0},{"$f":"'K90 - time schedule'!EM23","v":0},{"$f":"'K90 - time schedule'!EN23","v":0},{"$f":"'K90 - time schedule'!EO23","v":0},{"$f":"'K90 - time schedule'!EP23","v":0},{"$f":"'K90 - time schedule'!EQ23","v":0},{"$f":"'K90 - time schedule'!ER23","v":0},{"$f":"'K90 - time schedule'!ES23","v":0},{"$f":"'K90 - time schedule'!ET23","v":0},{"$f":"'K90 - time schedule'!EU23","v":0},{"$f":"'K90 - time schedule'!EV23","v":0},{"$f":"'K90 - time schedule'!EW23","v":0},{"$f":"'K90 - time schedule'!EX23","v":0},{"$f":"'K90 - time schedule'!EY23","v":0},{"$f":"'K90 - time schedule'!EZ23","v":0},{"$f":"'K90 - time schedule'!FA23","v":0},{"$f":"'K90 - time schedule'!FB23","v":0},{"$f":"'K90 - time schedule'!FC23","v":0},{"$f":"'K90 - time schedule'!FD23","v":0},{"$f":"'K90 - time schedule'!FE23","v":0},{"$f":"'K90 - time schedule'!FF23","v":0},{"$f":"'K90 - time schedule'!FG23","v":0},{"$f":"'K90 - time schedule'!FH23","v":0},{"$f":"'K90 - time schedule'!FI23","v":0},{"$f":"'K90 - time schedule'!FJ23","v":0},{"$f":"'K90 - time schedule'!FK23","v":0},{"$f":"'K90 - time schedule'!FL23","v":0},{"$f":"'K90 - time schedule'!FM23","v":0},{"$f":"'K90 - time schedule'!FN23","v":0},{"$f":"'K90 - time schedule'!FO23","v":0},{"$f":"'K90 - time schedule'!FP23","v":0},{"$f":"'K90 - time schedule'!FQ23","v":0},{"$f":"'K90 - time schedule'!FR23","v":0},{"$f":"'K90 - time schedule'!FS23","v":0},{"$f":"'K90 - time schedule'!FT23","v":0},{"$f":"'K90 - time schedule'!FU23","v":0},{"$f":"'K90 - time schedule'!FV23","v":0},{"$f":"'K90 - time schedule'!FW23","v":0},{"$f":"'K90 - time schedule'!FX23","v":0},{"$f":"'K90 - time schedule'!FY23","v":0},{"$f":"'K90 - time schedule'!FZ23","v":0},{"$f":"'K90 - time schedule'!GA23","v":0},{"$f":"'K90 - time schedule'!GB23","v":0},{"$f":"'K90 - time schedule'!GC23","v":0},{"$f":"'K90 - time schedule'!GD23","v":0},{"$f":"'K90 - time schedule'!GE23","v":0},{"$f":"'K90 - time schedule'!GF23","v":0},{"$f":"'K20 - time schedule'!GG66","v":0},{"$f":"'K20 - time schedule'!GH66","v":0},{"$f":"'K20 - time schedule'!GI66","v":0},{"$f":"'K20 - time schedule'!GJ66","v":0},{"$f":"'K20 - time schedule'!GK66","v":0},{"$f":"'K20 - time schedule'!GL66","v":0},{"$f":"'K20 - time schedule'!GM66","v":0},{"$f":"'K20 - time schedule'!GN66","v":0},{"$f":"'K20 - time schedule'!GO66","v":0},{"$f":"'K20 - time schedule'!GP66","v":0},{"$f":"'K20 - time schedule'!GQ66","v":0},{"$f":"'K20 - time schedule'!GR66","v":0},{"$f":"'K20 - time schedule'!GS66","v":0},{"$f":"'K20 - time schedule'!GT66","v":0},{"$f":"'K20 - time schedule'!GU66","v":0},{"$f":"'K20 - time schedule'!GV66","v":0},{"$f":"'K20 - time schedule'!GW66","v":0},{"$f":"'K20 - time schedule'!GX66","v":0},{"$f":"'K20 - time schedule'!GY66","v":0},{"$f":"'K20 - time schedule'!GZ66","v":0},{"$f":"'K20 - time schedule'!HA66","v":0},{"$f":"'K20 - time schedule'!HB66","v":0},{"$f":"'K20 - time schedule'!HC66","v":0},{"$f":"'K20 - time schedule'!HD66","v":0},{"$f":"'K20 - time schedule'!HE66","v":0},{"$f":"'K20 - time schedule'!HF66","v":0},{"$f":"'K20 - time schedule'!HG66","v":0},{"$f":"'K20 - time schedule'!HH66","v":0},{"$f":"'K20 - time schedule'!HI66","v":0},{"$f":"'K20 - time schedule'!HJ66","v":0},{"$f":"'K20 - time schedule'!HK66","v":0},{"$f":"'K20 - time schedule'!HL66","v":0},{"$f":"'K20 - time schedule'!HM66","v":0},{"$f":"'K20 - time schedule'!HN66","v":0},{"$f":"'K20 - time schedule'!HO66","v":0},{"$f":"'K20 - time schedule'!HP66","v":0},{"$f":"'K20 - time schedule'!HQ66","v":0},{"$f":"'K20 - time schedule'!HR66","v":0},{"$f":"'K20 - time schedule'!HS66","v":0},{"$f":"'K20 - time schedule'!HT66","v":0},{"$f":"'K20 - time schedule'!HU66","v":0},{"$f":"'K20 - time schedule'!HV66","v":0},{"$f":"'K20 - time schedule'!HW66","v":0},{"$f":"'K20 - time schedule'!HX66","v":0},{"$f":"'K20 - time schedule'!HY66","v":0},{"$f":"'K20 - time schedule'!HZ66","v":0},{"$f":"'K20 - time schedule'!IA66","v":0},{"$f":"'K20 - time schedule'!IB66","v":0},{"$f":"'K20 - time schedule'!IC66","v":0},{"$f":"'K20 - time schedule'!ID66","v":0},{"$f":"'K20 - time schedule'!IE66","v":0},{"$f":"'K20 - time schedule'!IF66","v":0},{"$f":"'K20 - time schedule'!IG66","v":0},{"$f":"'K20 - time schedule'!IH66","v":0},{"$f":"'K20 - time schedule'!II66","v":0},{"$f":"'K20 - time schedule'!IJ66","v":0},{"$f":"'K20 - time schedule'!IK66","v":0},{"$f":"'K20 - time schedule'!IL66","v":0},{"$f":"'K20 - time schedule'!IM66","v":0},{"$f":"'K20 - time schedule'!IN66","v":0},{"$f":"'K20 - time schedule'!IO66","v":0},{"$f":"'K20 - time schedule'!IP66","v":0},{"$f":"'K20 - time schedule'!IQ66","v":0},{"$f":"'K20 - time schedule'!IR66","v":0},{"$f":"'K20 - time schedule'!IS66","v":0},{"$f":"'K20 - time schedule'!IT66","v":0},{"$f":"'K20 - time schedule'!IU66","v":0},{"$f":"'K20 - time schedule'!IV66","v":0},{"$f":"'K20 - time schedule'!IW66","v":0},{"$f":"'K20 - time schedule'!IX66","v":0},{"$f":"'K20 - time schedule'!IY66","v":0},{"$f":"'K20 - time schedule'!IZ66","v":0},{"$f":"'K20 - time schedule'!JA66","v":0},{"$f":"'K20 - time schedule'!JB66","v":0},{"$f":"'K20 - time schedule'!JC66","v":0},{"$f":"'K20 - time schedule'!JD66","v":0},{"$f":"'K20 - time schedule'!JE66","v":0},{"$f":"'K20 - time schedule'!JF66","v":0},{"$f":"'K20 - time schedule'!JG66","v":0},{"$f":"'K20 - time schedule'!JH66","v":0},{"$f":"'K20 - time schedule'!JI66","v":0},{"$f":"'K20 - time schedule'!JJ66","v":0},{"$f":"'K20 - time schedule'!JK66","v":0},{"$f":"'K20 - time schedule'!JL66","v":0},{"$f":"'K20 - time schedule'!JM66","v":0},{"$f":"'K20 - time schedule'!JN66","v":0},{"$f":"'K20 - time schedule'!JO66","v":0},{"$f":"'K20 - time schedule'!JP66","v":0},{"$f":"'K20 - time schedule'!JQ66","v":0},{"$f":"'K20 - time schedule'!JR66","v":0},{"$f":"'K20 - time schedule'!JS66","v":0},{"$f":"'K20 - time schedule'!JT66","v":0},{"$f":"'K20 - time schedule'!JU66","v":0},{"$f":"'K20 - time schedule'!JV66","v":0},{"$f":"'K20 - time schedule'!JW66","v":0},{"$f":"'K20 - time schedule'!JX66","v":0},{"$f":"'K20 - time schedule'!JY66","v":0},{"$f":"'K20 - time schedule'!JZ66","v":0},{"$f":"'K20 - time schedule'!KA66","v":0},{"$f":"'K20 - time schedule'!KB66","v":0},{"$f":"'K20 - time schedule'!KC66","v":0},{"$f":"'K20 - time schedule'!KD66","v":0},{"$f":"'K20 - time schedule'!KE66","v":0},{"$f":"'K20 - time schedule'!KF66","v":0},{"$f":"'K20 - time schedule'!KG66","v":0},{"$f":"'K20 - time schedule'!KH66","v":0},{"$f":"'K20 - time schedule'!KI66","v":0},{"$f":"'K20 - time schedule'!KJ66","v":0},{"$f":"'K20 - time schedule'!KK66","v":0},{"$f":"'K20 - time schedule'!KL66","v":0},{"$f":"'K20 - time schedule'!KM66","v":0},{"$f":"'K20 - time schedule'!KN66","v":0},{"$f":"'K20 - time schedule'!KO66","v":0},{"$f":"'K20 - time schedule'!KP66","v":0},{"$f":"'K20 - time schedule'!KQ66","v":0},{"$f":"'K20 - time schedule'!KR66","v":0},{"$f":"'K20 - time schedule'!KS66","v":0},{"$f":"'K20 - time schedule'!KT66","v":0}]
["Boiler room K90 - fuel silos, including transport of fuel to the boiler","K90","EUR",{"$f":"'K90 - time schedule'!G25","v":0},{"$f":"'K90 - time schedule'!H25","v":0},{"$f":"'K90 - time schedule'!I25","v":0},{"$f":"'K90 - time schedule'!J25","v":0},{"$f":"'K90 - time schedule'!K25","v":0},{"$f":"'K90 - time schedule'!L25","v":0},{"$f":"'K90 - time schedule'!M25","v":0},{"$f":"'K90 - time schedule'!N25","v":0},{"$f":"'K90 - time schedule'!O25","v":0},{"$f":"'K90 - time schedule'!P25","v":0},{"$f":"'K90 - time schedule'!Q25","v":0},{"$f":"'K90 - time schedule'!R25","v":0},{"$f":"'K90 - time schedule'!S25","v":0},{"$f":"'K90 - time schedule'!T25","v":0},{"$f":"'K90 - time schedule'!U25","v":0},{"$f":"'K90 - time schedule'!V25","v":0},{"$f":"'K90 - time schedule'!W25","v":0},{"$f":"'K90 - time schedule'!X25","v":0},{"$f":"'K90 - time schedule'!Y25","v":0},{"$f":"'K90 - time schedule'!Z25","v":0},{"$f":"'K90 - time schedule'!AA25","v":0},{"$f":"'K90 - time schedule'!AB25","v":0},{"$f":"'K90 - time schedule'!AC25","v":0},{"$f":"'K90 - time schedule'!AD25","v":0},{"$f":"'K90 - time schedule'!AE25","v":0},{"$f":"'K90 - time schedule'!AF25","v":0},{"$f":"'K90 - time schedule'!AG25","v":0},{"$f":"'K90 - time schedule'!AH25","v":0},{"$f":"'K90 - time schedule'!AI25","v":0},{"$f":"'K90 - time schedule'!AJ25","v":0},{"$f":"'K90 - time schedule'!AK25","v":0},{"$f":"'K90 - time schedule'!AL25","v":0},{"$f":"'K90 - time schedule'!AM25","v":0},{"$f":"'K90 - time schedule'!AN25","v":0},{"$f":"'K90 - time schedule'!AO25","v":0},{"$f":"'K90 - time schedule'!AP25","v":0},{"$f":"'K90 - time schedule'!AQ25","v":0},{"$f":"'K90 - time schedule'!AR25","v":0},{"$f":"'K90 - time schedule'!AS25","v":0},{"$f":"'K90 - time schedule'!AT25","v":0},{"$f":"'K90 - time schedule'!AU25","v":0},{"$f":"'K90 - time schedule'!AV25","v":0},{"$f":"'K90 - time schedule'!AW25","v":0},{"$f":"'K90 - time schedule'!AX25","v":0},{"$f":"'K90 - time schedule'!AY25","v":0},{"$f":"'K90 - time schedule'!AZ25","v":0},{"$f":"'K90 - time schedule'!BA25","v":0},{"$f":"'K90 - time schedule'!BB25","v":0},{"$f":"'K90 - time schedule'!BC25","v":0},{"$f":"'K90 - time schedule'!BD25","v":0},{"$f":"'K90 - time schedule'!BE25","v":0},{"$f":"'K90 - time schedule'!BF25","v":0},{"$f":"'K90 - time schedule'!BG25","v":0},{"$f":"'K90 - time schedule'!BH25","v":0},{"$f":"'K90 - time schedule'!BI25","v":0},{"$f":"'K90 - time schedule'!BJ25","v":0},{"$f":"'K90 - time schedule'!BK25","v":0},{"$f":"'K90 - time schedule'!BL25","v":0},{"$f":"'K90 - time schedule'!BM25","v":0},{"$f":"'K90 - time schedule'!BN25","v":0},{"$f":"'K90 - time schedule'!BO25","v":0},{"$f":"'K90 - time schedule'!BP25","v":0},{"$f":"'K90 - time schedule'!BQ25","v":0},{"$f":"'K90 - time schedule'!BR25","v":0},{"$f":"'K90 - time schedule'!BS25","v":0},{"$f":"'K90 - time schedule'!BT25","v":0},{"$f":"'K90 - time schedule'!BU25","v":0},{"$f":"'K90 - time schedule'!BV25","v":0},{"$f":"'K90 - time schedule'!BW25","v":0},{"$f":"'K90 - time schedule'!BX25","v":0},{"$f":"'K90 - time schedule'!BY25","v":0},{"$f":"'K90 - time schedule'!BZ25","v":0},{"$f":"'K90 - time schedule'!CA25","v":0},{"$f":"'K90 - time schedule'!CB25","v":0},{"$f":"'K90 - time schedule'!CC25","v":0},{"$f":"'K90 - time schedule'!CD25","v":0},{"$f":"'K90 - time schedule'!CE25","v":0},{"$f":"'K90 - time schedule'!CF25","v":0},{"$f":"'K90 - time schedule'!CG25","v":0},{"$f":"'K90 - time schedule'!CH25","v":0},{"$f":"'K90 - time schedule'!CI25","v":0},{"$f":"'K90 - time schedule'!CJ25","v":0},{"$f":"'K90 - time schedule'!CK25","v":0},{"$f":"'K90 - time schedule'!CL25","v":0},{"$f":"'K90 - time schedule'!CM25","v":0},{"$f":"'K90 - time schedule'!CN25","v":0},{"$f":"'K90 - time schedule'!CO25","v":0},{"$f":"'K90 - time schedule'!CP25","v":0},{"$f":"'K90 - time schedule'!CQ25","v":0},{"$f":"'K90 - time schedule'!CR25","v":0},{"$f":"'K90 - time schedule'!CS25","v":0},{"$f":"'K90 - time schedule'!CT25","v":0},{"$f":"'K90 - time schedule'!CU25","v":0},{"$f":"'K90 - time schedule'!CV25","v":0},{"$f":"'K90 - time schedule'!CW25","v":0},{"$f":"'K90 - time schedule'!CX25","v":0},{"$f":"'K90 - time schedule'!CY25","v":0},{"$f":"'K90 - time schedule'!CZ25","v":0},{"$f":"'K90 - time schedule'!DA25","v":0},{"$f":"'K90 - time schedule'!DB25","v":0},{"$f":"'K90 - time schedule'!DC25","v":0},{"$f":"'K90 - time schedule'!DD25","v":0},{"$f":"'K90 - time schedule'!DE25","v":0},{"$f":"'K90 - time schedule'!DF25","v":0},{"$f":"'K90 - time schedule'!DG25","v":0},{"$f":"'K90 - time schedule'!DH25","v":0},{"$f":"'K90 - time schedule'!DI25","v":0},{"$f":"'K90 - time schedule'!DJ25","v":0},{"$f":"'K90 - time schedule'!DK25","v":0},{"$f":"'K90 - time schedule'!DL25","v":0},{"$f":"'K90 - time schedule'!DM25","v":0},{"$f":"'K90 - time schedule'!DN25","v":0},{"$f":"'K90 - time schedule'!DO25","v":0},{"$f":"'K90 - time schedule'!DP25","v":0},{"$f":"'K90 - time schedule'!DQ25","v":0},{"$f":"'K90 - time schedule'!DR25","v":0},{"$f":"'K90 - time schedule'!DS25","v":0},{"$f":"'K90 - time schedule'!DT25","v":0},{"$f":"'K90 - time schedule'!DU25","v":0},{"$f":"'K90 - time schedule'!DV25","v":0},{"$f":"'K90 - time schedule'!DW25","v":0},{"$f":"'K90 - time schedule'!DX25","v":0},{"$f":"'K90 - time schedule'!DY25","v":0},{"$f":"'K90 - time schedule'!DZ25","v":0},{"$f":"'K90 - time schedule'!EA25","v":0},{"$f":"'K90 - time schedule'!EB25","v":0},{"$f":"'K90 - time schedule'!EC25","v":0},{"$f":"'K90 - time schedule'!ED25","v":0},{"$f":"'K90 - time schedule'!EE25","v":0},{"$f":"'K90 - time schedule'!EF25","v":0},{"$f":"'K90 - time schedule'!EG25","v":0},{"$f":"'K90 - time schedule'!EH25","v":0},{"$f":"'K90 - time schedule'!EI25","v":0},{"$f":"'K90 - time schedule'!EJ25","v":0},{"$f":"'K90 - time schedule'!EK25","v":0},{"$f":"'K90 - time schedule'!EL25","v":0},{"$f":"'K90 - time schedule'!EM25","v":0},{"$f":"'K90 - time schedule'!EN25","v":0},{"$f":"'K90 - time schedule'!EO25","v":0},{"$f":"'K90 - time schedule'!EP25","v":0},{"$f":"'K90 - time schedule'!EQ25","v":0},{"$f":"'K90 - time schedule'!ER25","v":0},{"$f":"'K90 - time schedule'!ES25","v":0},{"$f":"'K90 - time schedule'!ET25","v":0},{"$f":"'K90 - time schedule'!EU25","v":0},{"$f":"'K90 - time schedule'!EV25","v":0},{"$f":"'K90 - time schedule'!EW25","v":0},{"$f":"'K90 - time schedule'!EX25","v":0},{"$f":"'K90 - time schedule'!EY25","v":0},{"$f":"'K90 - time schedule'!EZ25","v":0},{"$f":"'K90 - time schedule'!FA25","v":0},{"$f":"'K90 - time schedule'!FB25","v":0},{"$f":"'K90 - time schedule'!FC25","v":0},{"$f":"'K90 - time schedule'!FD25","v":0},{"$f":"'K90 - time schedule'!FE25","v":0},{"$f":"'K90 - time schedule'!FF25","v":0},{"$f":"'K90 - time schedule'!FG25","v":0},{"$f":"'K90 - time schedule'!FH25","v":0},{"$f":"'K90 - time schedule'!FI25","v":0},{"$f":"'K90 - time schedule'!FJ25","v":0},{"$f":"'K90 - time schedule'!FK25","v":0},{"$f":"'K90 - time schedule'!FL25","v":0},{"$f":"'K90 - time schedule'!FM25","v":0},{"$f":"'K90 - time schedule'!FN25","v":0},{"$f":"'K90 - time schedule'!FO25","v":0},{"$f":"'K90 - time schedule'!FP25","v":0},{"$f":"'K90 - time schedule'!FQ25","v":0},{"$f":"'K90 - time schedule'!FR25","v":0},{"$f":"'K90 - time schedule'!FS25","v":0},{"$f":"'K90 - time schedule'!FT25","v":0},{"$f":"'K90 - time schedule'!FU25","v":0},{"$f":"'K90 - time schedule'!FV25","v":0},{"$f":"'K90 - time schedule'!FW25","v":0},{"$f":"'K90 - time schedule'!FX25","v":0},{"$f":"'K90 - time schedule'!FY25","v":0},{"$f":"'K90 - time schedule'!FZ25","v":0},{"$f":"'K90 - time schedule'!GA25","v":0},{"$f":"'K90 - time schedule'!GB25","v":0},{"$f":"'K90 - time schedule'!GC25","v":0},{"$f":"'K90 - time schedule'!GD25","v":0},{"$f":"'K90 - time schedule'!GE25","v":0},{"$f":"'K90 - time schedule'!GF25","v":0},{"$f":"'K20 - time schedule'!GG67","v":0},{"$f":"'K20 - time schedule'!GH67","v":0},{"$f":"'K20 - time schedule'!GI67","v":0},{"$f":"'K20 - time schedule'!GJ67","v":0},{"$f":"'K20 - time schedule'!GK67","v":0},{"$f":"'K20 - time schedule'!GL67","v":0},{"$f":"'K20 - time schedule'!GM67","v":0},{"$f":"'K20 - time schedule'!GN67","v":0},{"$f":"'K20 - time schedule'!GO67","v":0},{"$f":"'K20 - time schedule'!GP67","v":0},{"$f":"'K20 - time schedule'!GQ67","v":0},{"$f":"'K20 - time schedule'!GR67","v":0},{"$f":"'K20 - time schedule'!GS67","v":0},{"$f":"'K20 - time schedule'!GT67","v":0},{"$f":"'K20 - time schedule'!GU67","v":0},{"$f":"'K20 - time schedule'!GV67","v":0},{"$f":"'K20 - time schedule'!GW67","v":0},{"$f":"'K20 - time schedule'!GX67","v":0},{"$f":"'K20 - time schedule'!GY67","v":0},{"$f":"'K20 - time schedule'!GZ67","v":0},{"$f":"'K20 - time schedule'!HA67","v":0},{"$f":"'K20 - time schedule'!HB67","v":0},{"$f":"'K20 - time schedule'!HC67","v":0},{"$f":"'K20 - time schedule'!HD67","v":0},{"$f":"'K20 - time schedule'!HE67","v":0},{"$f":"'K20 - time schedule'!HF67","v":0},{"$f":"'K20 - time schedule'!HG67","v":0},{"$f":"'K20 - time schedule'!HH67","v":0},{"$f":"'K20 - time schedule'!HI67","v":0},{"$f":"'K20 - time schedule'!HJ67","v":0},{"$f":"'K20 - time schedule'!HK67","v":0},{"$f":"'K20 - time schedule'!HL67","v":0},{"$f":"'K20 - time schedule'!HM67","v":0},{"$f":"'K20 - time schedule'!HN67","v":0},{"$f":"'K20 - time schedule'!HO67","v":0},{"$f":"'K20 - time schedule'!HP67","v":0},{"$f":"'K20 - time schedule'!HQ67","v":0},{"$f":"'K20 - time schedule'!HR67","v":0},{"$f":"'K20 - time schedule'!HS67","v":0},{"$f":"'K20 - time schedule'!HT67","v":0},{"$f":"'K20 - time schedule'!HU67","v":0},{"$f":"'K20 - time schedule'!HV67","v":0},{"$f":"'K20 - time schedule'!HW67","v":0},{"$f":"'K20 - time schedule'!HX67","v":0},{"$f":"'K20 - time schedule'!HY67","v":0},{"$f":"'K20 - time schedule'!HZ67","v":0},{"$f":"'K20 - time schedule'!IA67","v":0},{"$f":"'K20 - time schedule'!IB67","v":0},{"$f":"'K20 - time schedule'!IC67","v":0},{"$f":"'K20 - time schedule'!ID67","v":0},{"$f":"'K20 - time schedule'!IE67","v":0},{"$f":"'K20 - time schedule'!IF67","v":0},{"$f":"'K20 - time schedule'!IG67","v":0},{"$f":"'K20 - time schedule'!IH67","v":0},{"$f":"'K20 - time schedule'!II67","v":0},{"$f":"'K20 - time schedule'!IJ67","v":0},{"$f":"'K20 - time schedule'!IK67","v":0},{"$f":"'K20 - time schedule'!IL67","v":0},{"$f":"'K20 - time schedule'!IM67","v":0},{"$f":"'K20 - time schedule'!IN67","v":0},{"$f":"'K20 - time schedule'!IO67","v":0},{"$f":"'K20 - time schedule'!IP67","v":0},{"$f":"'K20 - time schedule'!IQ67","v":0},{"$f":"'K20 - time schedule'!IR67","v":0},{"$f":"'K20 - time schedule'!IS67","v":0},{"$f":"'K20 - time schedule'!IT67","v":0},{"$f":"'K20 - time schedule'!IU67","v":0},{"$f":"'K20 - time schedule'!IV67","v":0},{"$f":"'K20 - time schedule'!IW67","v":0},{"$f":"'K20 - time schedule'!IX67","v":0},{"$f":"'K20 - time schedule'!IY67","v":0},{"$f":"'K20 - time schedule'!IZ67","v":0},{"$f":"'K20 - time schedule'!JA67","v":0},{"$f":"'K20 - time schedule'!JB67","v":0},{"$f":"'K20 - time schedule'!JC67","v":0},{"$f":"'K20 - time schedule'!JD67","v":0},{"$f":"'K20 - time schedule'!JE67","v":0},{"$f":"'K20 - time schedule'!JF67","v":0},{"$f":"'K20 - time schedule'!JG67","v":0},{"$f":"'K20 - time schedule'!JH67","v":0},{"$f":"'K20 - time schedule'!JI67","v":0},{"$f":"'K20 - time schedule'!JJ67","v":0},{"$f":"'K20 - time schedule'!JK67","v":0},{"$f":"'K20 - time schedule'!JL67","v":0},{"$f":"'K20 - time schedule'!JM67","v":0},{"$f":"'K20 - time schedule'!JN67","v":0},{"$f":"'K20 - time schedule'!JO67","v":0},{"$f":"'K20 - time schedule'!JP67","v":0},{"$f":"'K20 - time schedule'!JQ67","v":0},{"$f":"'K20 - time schedule'!JR67","v":0},{"$f":"'K20 - time schedule'!JS67","v":0},{"$f":"'K20 - time schedule'!JT67","v":0},{"$f":"'K20 - time schedule'!JU67","v":0},{"$f":"'K20 - time schedule'!JV67","v":0},{"$f":"'K20 - time schedule'!JW67","v":0},{"$f":"'K20 - time schedule'!JX67","v":0},{"$f":"'K20 - time schedule'!JY67","v":0},{"$f":"'K20 - time schedule'!JZ67","v":0},{"$f":"'K20 - time schedule'!KA67","v":0},{"$f":"'K20 - time schedule'!KB67","v":0},{"$f":"'K20 - time schedule'!KC67","v":0},{"$f":"'K20 - time schedule'!KD67","v":0},{"$f":"'K20 - time schedule'!KE67","v":0},{"$f":"'K20 - time schedule'!KF67","v":0},{"$f":"'K20 - time schedule'!KG67","v":0},{"$f":"'K20 - time schedule'!KH67","v":0},{"$f":"'K20 - time schedule'!KI67","v":0},{"$f":"'K20 - time schedule'!KJ67","v":0},{"$f":"'K20 - time schedule'!KK67","v":0},{"$f":"'K20 - time schedule'!KL67","v":0},{"$f":"'K20 - time schedule'!KM67","v":0},{"$f":"'K20 - time schedule'!KN67","v":0},{"$f":"'K20 - time schedule'!KO67","v":0},{"$f":"'K20 - time schedule'!KP67","v":0},{"$f":"'K20 - time schedule'!KQ67","v":0},{"$f":"'K20 - time schedule'!KR67","v":0},{"$f":"'K20 - time schedule'!KS67","v":0},{"$f":"'K20 - time schedule'!KT67","v":0}]
["Boiler room K90 - air heating","K90","EUR",{"$f":"'K90 - time schedule'!G27","v":0},{"$f":"'K90 - time schedule'!H27","v":0},{"$f":"'K90 - time schedule'!I27","v":0},{"$f":"'K90 - time schedule'!J27","v":0},{"$f":"'K90 - time schedule'!K27","v":0},{"$f":"'K90 - time schedule'!L27","v":0},{"$f":"'K90 - time schedule'!M27","v":0},{"$f":"'K90 - time schedule'!N27","v":0},{"$f":"'K90 - time schedule'!O27","v":0},{"$f":"'K90 - time schedule'!P27","v":0},{"$f":"'K90 - time schedule'!Q27","v":0},{"$f":"'K90 - time schedule'!R27","v":0},{"$f":"'K90 - time schedule'!S27","v":0},{"$f":"'K90 - time schedule'!T27","v":0},{"$f":"'K90 - time schedule'!U27","v":0},{"$f":"'K90 - time schedule'!V27","v":0},{"$f":"'K90 - time schedule'!W27","v":0},{"$f":"'K90 - time schedule'!X27","v":0},{"$f":"'K90 - time schedule'!Y27","v":0},{"$f":"'K90 - time schedule'!Z27","v":0},{"$f":"'K90 - time schedule'!AA27","v":0},{"$f":"'K90 - time schedule'!AB27","v":0},{"$f":"'K90 - time schedule'!AC27","v":0},{"$f":"'K90 - time schedule'!AD27","v":0},{"$f":"'K90 - time schedule'!AE27","v":0},{"$f":"'K90 - time schedule'!AF27","v":0},{"$f":"'K90 - time schedule'!AG27","v":0},{"$f":"'K90 - time schedule'!AH27","v":0},{"$f":"'K90 - time schedule'!AI27","v":0},{"$f":"'K90 - time schedule'!AJ27","v":0},{"$f":"'K90 - time schedule'!AK27","v":0},{"$f":"'K90 - time schedule'!AL27","v":0},{"$f":"'K90 - time schedule'!AM27","v":0},{"$f":"'K90 - time schedule'!AN27","v":0},{"$f":"'K90 - time schedule'!AO27","v":0},{"$f":"'K90 - time schedule'!AP27","v":0},{"$f":"'K90 - time schedule'!AQ27","v":0},{"$f":"'K90 - time schedule'!AR27","v":0},{"$f":"'K90 - time schedule'!AS27","v":0},{"$f":"'K90 - time schedule'!AT27","v":0},{"$f":"'K90 - time schedule'!AU27","v":0},{"$f":"'K90 - time schedule'!AV27","v":0},{"$f":"'K90 - time schedule'!AW27","v":0},{"$f":"'K90 - time schedule'!AX27","v":0},{"$f":"'K90 - time schedule'!AY27","v":0},{"$f":"'K90 - time schedule'!AZ27","v":0},{"$f":"'K90 - time schedule'!BA27","v":0},{"$f":"'K90 - time schedule'!BB27","v":0},{"$f":"'K90 - time schedule'!BC27","v":0},{"$f":"'K90 - time schedule'!BD27","v":0},{"$f":"'K90 - time schedule'!BE27","v":0},{"$f":"'K90 - time schedule'!BF27","v":0},{"$f":"'K90 - time schedule'!BG27","v":0},{"$f":"'K90 - time schedule'!BH27","v":0},{"$f":"'K90 - time schedule'!BI27","v":0},{"$f":"'K90 - time schedule'!BJ27","v":0},{"$f":"'K90 - time schedule'!BK27","v":0},{"$f":"'K90 - time schedule'!BL27","v":0},{"$f":"'K90 - time schedule'!BM27","v":0},{"$f":"'K90 - time schedule'!BN27","v":0},{"$f":"'K90 - time schedule'!BO27","v":0},{"$f":"'K90 - time schedule'!BP27","v":0},{"$f":"'K90 - time schedule'!BQ27","v":0},{"$f":"'K90 - time schedule'!BR27","v":0},{"$f":"'K90 - time schedule'!BS27","v":0},{"$f":"'K90 - time schedule'!BT27","v":0},{"$f":"'K90 - time schedule'!BU27","v":0},{"$f":"'K90 - time schedule'!BV27","v":0},{"$f":"'K90 - time schedule'!BW27","v":0},{"$f":"'K90 - time schedule'!BX27","v":0},{"$f":"'K90 - time schedule'!BY27","v":0},{"$f":"'K90 - time schedule'!BZ27","v":0},{"$f":"'K90 - time schedule'!CA27","v":0},{"$f":"'K90 - time schedule'!CB27","v":0},{"$f":"'K90 - time schedule'!CC27","v":0},{"$f":"'K90 - time schedule'!CD27","v":0},{"$f":"'K90 - time schedule'!CE27","v":0},{"$f":"'K90 - time schedule'!CF27","v":0},{"$f":"'K90 - time schedule'!CG27","v":0},{"$f":"'K90 - time schedule'!CH27","v":0},{"$f":"'K90 - time schedule'!CI27","v":0},{"$f":"'K90 - time schedule'!CJ27","v":0},{"$f":"'K90 - time schedule'!CK27","v":0},{"$f":"'K90 - time schedule'!CL27","v":0},{"$f":"'K90 - time schedule'!CM27","v":0},{"$f":"'K90 - time schedule'!CN27","v":0},{"$f":"'K90 - time schedule'!CO27","v":0},{"$f":"'K90 - time schedule'!CP27","v":0},{"$f":"'K90 - time schedule'!CQ27","v":0},{"$f":"'K90 - time schedule'!CR27","v":0},{"$f":"'K90 - time schedule'!CS27","v":0},{"$f":"'K90 - time schedule'!CT27","v":0},{"$f":"'K90 - time schedule'!CU27","v":0},{"$f":"'K90 - time schedule'!CV27","v":0},{"$f":"'K90 - time schedule'!CW27","v":0},{"$f":"'K90 - time schedule'!CX27","v":0},{"$f":"'K90 - time schedule'!CY27","v":0},{"$f":"'K90 - time schedule'!CZ27","v":0},{"$f":"'K90 - time schedule'!DA27","v":0},{"$f":"'K90 - time schedule'!DB27","v":0},{"$f":"'K90 - time schedule'!DC27","v":0},{"$f":"'K90 - time schedule'!DD27","v":0},{"$f":"'K90 - time schedule'!DE27","v":0},{"$f":"'K90 - time schedule'!DF27","v":0},{"$f":"'K90 - time schedule'!DG27","v":0},{"$f":"'K90 - time schedule'!DH27","v":0},{"$f":"'K90 - time schedule'!DI27","v":0},{"$f":"'K90 - time schedule'!DJ27","v":0},{"$f":"'K90 - time schedule'!DK27","v":0},{"$f":"'K90 - time schedule'!DL27","v":0},{"$f":"'K90 - time schedule'!DM27","v":0},{"$f":"'K90 - time schedule'!DN27","v":0},{"$f":"'K90 - time schedule'!DO27","v":0},{"$f":"'K90 - time schedule'!DP27","v":0},{"$f":"'K90 - time schedule'!DQ27","v":0},{"$f":"'K90 - time schedule'!DR27","v":0},{"$f":"'K90 - time schedule'!DS27","v":0},{"$f":"'K90 - time schedule'!DT27","v":0},{"$f":"'K90 - time schedule'!DU27","v":0},{"$f":"'K90 - time schedule'!DV27","v":0},{"$f":"'K90 - time schedule'!DW27","v":0},{"$f":"'K90 - time schedule'!DX27","v":0},{"$f":"'K90 - time schedule'!DY27","v":0},{"$f":"'K90 - time schedule'!DZ27","v":0},{"$f":"'K90 - time schedule'!EA27","v":0},{"$f":"'K90 - time schedule'!EB27","v":0},{"$f":"'K90 - time schedule'!EC27","v":0},{"$f":"'K90 - time schedule'!ED27","v":0},{"$f":"'K90 - time schedule'!EE27","v":0},{"$f":"'K90 - time schedule'!EF27","v":0},{"$f":"'K90 - time schedule'!EG27","v":0},{"$f":"'K90 - time schedule'!EH27","v":0},{"$f":"'K90 - time schedule'!EI27","v":0},{"$f":"'K90 - time schedule'!EJ27","v":0},{"$f":"'K90 - time schedule'!EK27","v":0},{"$f":"'K90 - time schedule'!EL27","v":0},{"$f":"'K90 - time schedule'!EM27","v":0},{"$f":"'K90 - time schedule'!EN27","v":0},{"$f":"'K90 - time schedule'!EO27","v":0},{"$f":"'K90 - time schedule'!EP27","v":0},{"$f":"'K90 - time schedule'!EQ27","v":0},{"$f":"'K90 - time schedule'!ER27","v":0},{"$f":"'K90 - time schedule'!ES27","v":0},{"$f":"'K90 - time schedule'!ET27","v":0},{"$f":"'K90 - time schedule'!EU27","v":0},{"$f":"'K90 - time schedule'!EV27","v":0},{"$f":"'K90 - time schedule'!EW27","v":0},{"$f":"'K90 - time schedule'!EX27","v":0},{"$f":"'K90 - time schedule'!EY27","v":0},{"$f":"'K90 - time schedule'!EZ27","v":0},{"$f":"'K90 - time schedule'!FA27","v":0},{"$f":"'K90 - time schedule'!FB27","v":0},{"$f":"'K90 - time schedule'!FC27","v":0},{"$f":"'K90 - time schedule'!FD27","v":0},{"$f":"'K90 - time schedule'!FE27","v":0},{"$f":"'K90 - time schedule'!FF27","v":0},{"$f":"'K90 - time schedule'!FG27","v":0},{"$f":"'K90 - time schedule'!FH27","v":0},{"$f":"'K90 - time schedule'!FI27","v":0},{"$f":"'K90 - time schedule'!FJ27","v":0},{"$f":"'K90 - time schedule'!FK27","v":0},{"$f":"'K90 - time schedule'!FL27","v":0},{"$f":"'K90 - time schedule'!FM27","v":0},{"$f":"'K90 - time schedule'!FN27","v":0},{"$f":"'K90 - time schedule'!FO27","v":0},{"$f":"'K90 - time schedule'!FP27","v":0},{"$f":"'K90 - time schedule'!FQ27","v":0},{"$f":"'K90 - time schedule'!FR27","v":0},{"$f":"'K90 - time schedule'!FS27","v":0},{"$f":"'K90 - time schedule'!FT27","v":0},{"$f":"'K90 - time schedule'!FU27","v":0},{"$f":"'K90 - time schedule'!FV27","v":0},{"$f":"'K90 - time schedule'!FW27","v":0},{"$f":"'K90 - time schedule'!FX27","v":0},{"$f":"'K90 - time schedule'!FY27","v":0},{"$f":"'K90 - time schedule'!FZ27","v":0},{"$f":"'K90 - time schedule'!GA27","v":0},{"$f":"'K90 - time schedule'!GB27","v":0},{"$f":"'K90 - time schedule'!GC27","v":0},{"$f":"'K90 - time schedule'!GD27","v":0},{"$f":"'K90 - time schedule'!GE27","v":0},{"$f":"'K90 - time schedule'!GF27","v":0},{"$f":"'K20 - time schedule'!GG68","v":0},{"$f":"'K20 - time schedule'!GH68","v":0},{"$f":"'K20 - time schedule'!GI68","v":0},{"$f":"'K20 - time schedule'!GJ68","v":0},{"$f":"'K20 - time schedule'!GK68","v":0},{"$f":"'K20 - time schedule'!GL68","v":0},{"$f":"'K20 - time schedule'!GM68","v":0},{"$f":"'K20 - time schedule'!GN68","v":0},{"$f":"'K20 - time schedule'!GO68","v":0},{"$f":"'K20 - time schedule'!GP68","v":0},{"$f":"'K20 - time schedule'!GQ68","v":0},{"$f":"'K20 - time schedule'!GR68","v":0},{"$f":"'K20 - time schedule'!GS68","v":0},{"$f":"'K20 - time schedule'!GT68","v":0},{"$f":"'K20 - time schedule'!GU68","v":0},{"$f":"'K20 - time schedule'!GV68","v":0},{"$f":"'K20 - time schedule'!GW68","v":0},{"$f":"'K20 - time schedule'!GX68","v":0},{"$f":"'K20 - time schedule'!GY68","v":0},{"$f":"'K20 - time schedule'!GZ68","v":0},{"$f":"'K20 - time schedule'!HA68","v":0},{"$f":"'K20 - time schedule'!HB68","v":0},{"$f":"'K20 - time schedule'!HC68","v":0},{"$f":"'K20 - time schedule'!HD68","v":0},{"$f":"'K20 - time schedule'!HE68","v":0},{"$f":"'K20 - time schedule'!HF68","v":0},{"$f":"'K20 - time schedule'!HG68","v":0},{"$f":"'K20 - time schedule'!HH68","v":0},{"$f":"'K20 - time schedule'!HI68","v":0},{"$f":"'K20 - time schedule'!HJ68","v":0},{"$f":"'K20 - time schedule'!HK68","v":0},{"$f":"'K20 - time schedule'!HL68","v":0},{"$f":"'K20 - time schedule'!HM68","v":0},{"$f":"'K20 - time schedule'!HN68","v":0},{"$f":"'K20 - time schedule'!HO68","v":0},{"$f":"'K20 - time schedule'!HP68","v":0},{"$f":"'K20 - time schedule'!HQ68","v":0},{"$f":"'K20 - time schedule'!HR68","v":0},{"$f":"'K20 - time schedule'!HS68","v":0},{"$f":"'K20 - time schedule'!HT68","v":0},{"$f":"'K20 - time schedule'!HU68","v":0},{"$f":"'K20 - time schedule'!HV68","v":0},{"$f":"'K20 - time schedule'!HW68","v":0},{"$f":"'K20 - time schedule'!HX68","v":0},{"$f":"'K20 - time schedule'!HY68","v":0},{"$f":"'K20 - time schedule'!HZ68","v":0},{"$f":"'K20 - time schedule'!IA68","v":0},{"$f":"'K20 - time schedule'!IB68","v":0},{"$f":"'K20 - time schedule'!IC68","v":0},{"$f":"'K20 - time schedule'!ID68","v":0},{"$f":"'K20 - time schedule'!IE68","v":0},{"$f":"'K20 - time schedule'!IF68","v":0},{"$f":"'K20 - time schedule'!IG68","v":0},{"$f":"'K20 - time schedule'!IH68","v":0},{"$f":"'K20 - time schedule'!II68","v":0},{"$f":"'K20 - time schedule'!IJ68","v":0},{"$f":"'K20 - time schedule'!IK68","v":0},{"$f":"'K20 - time schedule'!IL68","v":0},{"$f":"'K20 - time schedule'!IM68","v":0},{"$f":"'K20 - time schedule'!IN68","v":0},{"$f":"'K20 - time schedule'!IO68","v":0},{"$f":"'K20 - time schedule'!IP68","v":0},{"$f":"'K20 - time schedule'!IQ68","v":0},{"$f":"'K20 - time schedule'!IR68","v":0},{"$f":"'K20 - time schedule'!IS68","v":0},{"$f":"'K20 - time schedule'!IT68","v":0},{"$f":"'K20 - time schedule'!IU68","v":0},{"$f":"'K20 - time schedule'!IV68","v":0},{"$f":"'K20 - time schedule'!IW68","v":0},{"$f":"'K20 - time schedule'!IX68","v":0},{"$f":"'K20 - time schedule'!IY68","v":0},{"$f":"'K20 - time schedule'!IZ68","v":0},{"$f":"'K20 - time schedule'!JA68","v":0},{"$f":"'K20 - time schedule'!JB68","v":0},{"$f":"'K20 - time schedule'!JC68","v":0},{"$f":"'K20 - time schedule'!JD68","v":0},{"$f":"'K20 - time schedule'!JE68","v":0},{"$f":"'K20 - time schedule'!JF68","v":0},{"$f":"'K20 - time schedule'!JG68","v":0},{"$f":"'K20 - time schedule'!JH68","v":0},{"$f":"'K20 - time schedule'!JI68","v":0},{"$f":"'K20 - time schedule'!JJ68","v":0},{"$f":"'K20 - time schedule'!JK68","v":0},{"$f":"'K20 - time schedule'!JL68","v":0},{"$f":"'K20 - time schedule'!JM68","v":0},{"$f":"'K20 - time schedule'!JN68","v":0},{"$f":"'K20 - time schedule'!JO68","v":0},{"$f":"'K20 - time schedule'!JP68","v":0},{"$f":"'K20 - time schedule'!JQ68","v":0},{"$f":"'K20 - time schedule'!JR68","v":0},{"$f":"'K20 - time schedule'!JS68","v":0},{"$f":"'K20 - time schedule'!JT68","v":0},{"$f":"'K20 - time schedule'!JU68","v":0},{"$f":"'K20 - time schedule'!JV68","v":0},{"$f":"'K20 - time schedule'!JW68","v":0},{"$f":"'K20 - time schedule'!JX68","v":0},{"$f":"'K20 - time schedule'!JY68","v":0},{"$f":"'K20 - time schedule'!JZ68","v":0},{"$f":"'K20 - time schedule'!KA68","v":0},{"$f":"'K20 - time schedule'!KB68","v":0},{"$f":"'K20 - time schedule'!KC68","v":0},{"$f":"'K20 - time schedule'!KD68","v":0},{"$f":"'K20 - time schedule'!KE68","v":0},{"$f":"'K20 - time schedule'!KF68","v":0},{"$f":"'K20 - time schedule'!KG68","v":0},{"$f":"'K20 - time schedule'!KH68","v":0},{"$f":"'K20 - time schedule'!KI68","v":0},{"$f":"'K20 - time schedule'!KJ68","v":0},{"$f":"'K20 - time schedule'!KK68","v":0},{"$f":"'K20 - time schedule'!KL68","v":0},{"$f":"'K20 - time schedule'!KM68","v":0},{"$f":"'K20 - time schedule'!KN68","v":0},{"$f":"'K20 - time schedule'!KO68","v":0},{"$f":"'K20 - time schedule'!KP68","v":0},{"$f":"'K20 - time schedule'!KQ68","v":0},{"$f":"'K20 - time schedule'!KR68","v":0},{"$f":"'K20 - time schedule'!KS68","v":0},{"$f":"'K20 - time schedule'!KT68","v":0}]
["Boiler room K90 - overheating","K90","EUR",{"$f":"'K90 - time schedule'!G29","v":0},{"$f":"'K90 - time schedule'!H29","v":0},{"$f":"'K90 - time schedule'!I29","v":0},{"$f":"'K90 - time schedule'!J29","v":0},{"$f":"'K90 - time schedule'!K29","v":0},{"$f":"'K90 - time schedule'!L29","v":0},{"$f":"'K90 - time schedule'!M29","v":0},{"$f":"'K90 - time schedule'!N29","v":0},{"$f":"'K90 - time schedule'!O29","v":0},{"$f":"'K90 - time schedule'!P29","v":0},{"$f":"'K90 - time schedule'!Q29","v":0},{"$f":"'K90 - time schedule'!R29","v":0},{"$f":"'K90 - time schedule'!S29","v":0},{"$f":"'K90 - time schedule'!T29","v":0},{"$f":"'K90 - time schedule'!U29","v":0},{"$f":"'K90 - time schedule'!V29","v":0},{"$f":"'K90 - time schedule'!W29","v":0},{"$f":"'K90 - time schedule'!X29","v":0},{"$f":"'K90 - time schedule'!Y29","v":0},{"$f":"'K90 - time schedule'!Z29","v":0},{"$f":"'K90 - time schedule'!AA29","v":0},{"$f":"'K90 - time schedule'!AB29","v":0},{"$f":"'K90 - time schedule'!AC29","v":0},{"$f":"'K90 - time schedule'!AD29","v":0},{"$f":"'K90 - time schedule'!AE29","v":0},{"$f":"'K90 - time schedule'!AF29","v":0},{"$f":"'K90 - time schedule'!AG29","v":0},{"$f":"'K90 - time schedule'!AH29","v":0},{"$f":"'K90 - time schedule'!AI29","v":0},{"$f":"'K90 - time schedule'!AJ29","v":0},{"$f":"'K90 - time schedule'!AK29","v":0},{"$f":"'K90 - time schedule'!AL29","v":0},{"$f":"'K90 - time schedule'!AM29","v":0},{"$f":"'K90 - time schedule'!AN29","v":0},{"$f":"'K90 - time schedule'!AO29","v":0},{"$f":"'K90 - time schedule'!AP29","v":0},{"$f":"'K90 - time schedule'!AQ29","v":0},{"$f":"'K90 - time schedule'!AR29","v":0},{"$f":"'K90 - time schedule'!AS29","v":0},{"$f":"'K90 - time schedule'!AT29","v":0},{"$f":"'K90 - time schedule'!AU29","v":0},{"$f":"'K90 - time schedule'!AV29","v":0},{"$f":"'K90 - time schedule'!AW29","v":0},{"$f":"'K90 - time schedule'!AX29","v":0},{"$f":"'K90 - time schedule'!AY29","v":0},{"$f":"'K90 - time schedule'!AZ29","v":0},{"$f":"'K90 - time schedule'!BA29","v":0},{"$f":"'K90 - time schedule'!BB29","v":0},{"$f":"'K90 - time schedule'!BC29","v":0},{"$f":"'K90 - time schedule'!BD29","v":0},{"$f":"'K90 - time schedule'!BE29","v":0},{"$f":"'K90 - time schedule'!BF29","v":0},{"$f":"'K90 - time schedule'!BG29","v":0},{"$f":"'K90 - time schedule'!BH29","v":0},{"$f":"'K90 - time schedule'!BI29","v":0},{"$f":"'K90 - time schedule'!BJ29","v":0},{"$f":"'K90 - time schedule'!BK29","v":0},{"$f":"'K90 - time schedule'!BL29","v":0},{"$f":"'K90 - time schedule'!BM29","v":0},{"$f":"'K90 - time schedule'!BN29","v":0},{"$f":"'K90 - time schedule'!BO29","v":0},{"$f":"'K90 - time schedule'!BP29","v":0},{"$f":"'K90 - time schedule'!BQ29","v":0},{"$f":"'K90 - time schedule'!BR29","v":0},{"$f":"'K90 - time schedule'!BS29","v":0},{"$f":"'K90 - time schedule'!BT29","v":0},{"$f":"'K90 - time schedule'!BU29","v":0},{"$f":"'K90 - time schedule'!BV29","v":0},{"$f":"'K90 - time schedule'!BW29","v":0},{"$f":"'K90 - time schedule'!BX29","v":0},{"$f":"'K90 - time schedule'!BY29","v":0},{"$f":"'K90 - time schedule'!BZ29","v":0},{"$f":"'K90 - time schedule'!CA29","v":0},{"$f":"'K90 - time schedule'!CB29","v":0},{"$f":"'K90 - time schedule'!CC29","v":0},{"$f":"'K90 - time schedule'!CD29","v":0},{"$f":"'K90 - time schedule'!CE29","v":0},{"$f":"'K90 - time schedule'!CF29","v":0},{"$f":"'K90 - time schedule'!CG29","v":0},{"$f":"'K90 - time schedule'!CH29","v":0},{"$f":"'K90 - time schedule'!CI29","v":0},{"$f":"'K90 - time schedule'!CJ29","v":0},{"$f":"'K90 - time schedule'!CK29","v":0},{"$f":"'K90 - time schedule'!CL29","v":0},{"$f":"'K90 - time schedule'!CM29","v":0},{"$f":"'K90 - time schedule'!CN29","v":0},{"$f":"'K90 - time schedule'!CO29","v":0},{"$f":"'K90 - time schedule'!CP29","v":0},{"$f":"'K90 - time schedule'!CQ29","v":0},{"$f":"'K90 - time schedule'!CR29","v":0},{"$f":"'K90 - time schedule'!CS29","v":0},{"$f":"'K90 - time schedule'!CT29","v":0},{"$f":"'K90 - time schedule'!CU29","v":0},{"$f":"'K90 - time schedule'!CV29","v":0},{"$f":"'K90 - time schedule'!CW29","v":0},{"$f":"'K90 - time schedule'!CX29","v":0},{"$f":"'K90 - time schedule'!CY29","v":0},{"$f":"'K90 - time schedule'!CZ29","v":0},{"$f":"'K90 - time schedule'!DA29","v":0},{"$f":"'K90 - time schedule'!DB29","v":0},{"$f":"'K90 - time schedule'!DC29","v":0},{"$f":"'K90 - time schedule'!DD29","v":0},{"$f":"'K90 - time schedule'!DE29","v":0},{"$f":"'K90 - time schedule'!DF29","v":0},{"$f":"'K90 - time schedule'!DG29","v":0},{"$f":"'K90 - time schedule'!DH29","v":0},{"$f":"'K90 - time schedule'!DI29","v":0},{"$f":"'K90 - time schedule'!DJ29","v":0},{"$f":"'K90 - time schedule'!DK29","v":0},{"$f":"'K90 - time schedule'!DL29","v":0},{"$f":"'K90 - time schedule'!DM29","v":0},{"$f":"'K90 - time schedule'!DN29","v":0},{"$f":"'K90 - time schedule'!DO29","v":0},{"$f":"'K90 - time schedule'!DP29","v":0},{"$f":"'K90 - time schedule'!DQ29","v":0},{"$f":"'K90 - time schedule'!DR29","v":0},{"$f":"'K90 - time schedule'!DS29","v":0},{"$f":"'K90 - time schedule'!DT29","v":0},{"$f":"'K90 - time schedule'!DU29","v":0},{"$f":"'K90 - time schedule'!DV29","v":0},{"$f":"'K90 - time schedule'!DW29","v":0},{"$f":"'K90 - time schedule'!DX29","v":0},{"$f":"'K90 - time schedule'!DY29","v":0},{"$f":"'K90 - time schedule'!DZ29","v":0},{"$f":"'K90 - time schedule'!EA29","v":0},{"$f":"'K90 - time schedule'!EB29","v":0},{"$f":"'K90 - time schedule'!EC29","v":0},{"$f":"'K90 - time schedule'!ED29","v":0},{"$f":"'K90 - time schedule'!EE29","v":0},{"$f":"'K90 - time schedule'!EF29","v":0},{"$f":"'K90 - time schedule'!EG29","v":0},{"$f":"'K90 - time schedule'!EH29","v":0},{"$f":"'K90 - time schedule'!EI29","v":0},{"$f":"'K90 - time schedule'!EJ29","v":0},{"$f":"'K90 - time schedule'!EK29","v":0},{"$f":"'K90 - time schedule'!EL29","v":0},{"$f":"'K90 - time schedule'!EM29","v":0},{"$f":"'K90 - time schedule'!EN29","v":0},{"$f":"'K90 - time schedule'!EO29","v":0},{"$f":"'K90 - time schedule'!EP29","v":0},{"$f":"'K90 - time schedule'!EQ29","v":0},{"$f":"'K90 - time schedule'!ER29","v":0},{"$f":"'K90 - time schedule'!ES29","v":0},{"$f":"'K90 - time schedule'!ET29","v":0},{"$f":"'K90 - time schedule'!EU29","v":0},{"$f":"'K90 - time schedule'!EV29","v":0},{"$f":"'K90 - time schedule'!EW29","v":0},{"$f":"'K90 - time schedule'!EX29","v":0},{"$f":"'K90 - time schedule'!EY29","v":0},{"$f":"'K90 - time schedule'!EZ29","v":0},{"$f":"'K90 - time schedule'!FA29","v":0},{"$f":"'K90 - time schedule'!FB29","v":0},{"$f":"'K90 - time schedule'!FC29","v":0},{"$f":"'K90 - time schedule'!FD29","v":0},{"$f":"'K90 - time schedule'!FE29","v":0},{"$f":"'K90 - time schedule'!FF29","v":0},{"$f":"'K90 - time schedule'!FG29","v":0},{"$f":"'K90 - time schedule'!FH29","v":0},{"$f":"'K90 - time schedule'!FI29","v":0},{"$f":"'K90 - time schedule'!FJ29","v":0},{"$f":"'K90 - time schedule'!FK29","v":0},{"$f":"'K90 - time schedule'!FL29","v":0},{"$f":"'K90 - time schedule'!FM29","v":0},{"$f":"'K90 - time schedule'!FN29","v":0},{"$f":"'K90 - time schedule'!FO29","v":0},{"$f":"'K90 - time schedule'!FP29","v":0},{"$f":"'K90 - time schedule'!FQ29","v":0},{"$f":"'K90 - time schedule'!FR29","v":0},{"$f":"'K90 - time schedule'!FS29","v":0},{"$f":"'K90 - time schedule'!FT29","v":0},{"$f":"'K90 - time schedule'!FU29","v":0},{"$f":"'K90 - time schedule'!FV29","v":0},{"$f":"'K90 - time schedule'!FW29","v":0},{"$f":"'K90 - time schedule'!FX29","v":0},{"$f":"'K90 - time schedule'!FY29","v":0},{"$f":"'K90 - time schedule'!FZ29","v":0},{"$f":"'K90 - time schedule'!GA29","v":0},{"$f":"'K90 - time schedule'!GB29","v":0},{"$f":"'K90 - time schedule'!GC29","v":0},{"$f":"'K90 - time schedule'!GD29","v":0},{"$f":"'K90 - time schedule'!GE29","v":0},{"$f":"'K90 - time schedule'!GF29","v":0},{"$f":"'K20 - time schedule'!GG69","v":0},{"$f":"'K20 - time schedule'!GH69","v":0},{"$f":"'K20 - time schedule'!GI69","v":0},{"$f":"'K20 - time schedule'!GJ69","v":0},{"$f":"'K20 - time schedule'!GK69","v":0},{"$f":"'K20 - time schedule'!GL69","v":0},{"$f":"'K20 - time schedule'!GM69","v":0},{"$f":"'K20 - time schedule'!GN69","v":0},{"$f":"'K20 - time schedule'!GO69","v":0},{"$f":"'K20 - time schedule'!GP69","v":0},{"$f":"'K20 - time schedule'!GQ69","v":0},{"$f":"'K20 - time schedule'!GR69","v":0},{"$f":"'K20 - time schedule'!GS69","v":0},{"$f":"'K20 - time schedule'!GT69","v":0},{"$f":"'K20 - time schedule'!GU69","v":0},{"$f":"'K20 - time schedule'!GV69","v":0},{"$f":"'K20 - time schedule'!GW69","v":0},{"$f":"'K20 - time schedule'!GX69","v":0},{"$f":"'K20 - time schedule'!GY69","v":0},{"$f":"'K20 - time schedule'!GZ69","v":0},{"$f":"'K20 - time schedule'!HA69","v":0},{"$f":"'K20 - time schedule'!HB69","v":0},{"$f":"'K20 - time schedule'!HC69","v":0},{"$f":"'K20 - time schedule'!HD69","v":0},{"$f":"'K20 - time schedule'!HE69","v":0},{"$f":"'K20 - time schedule'!HF69","v":0},{"$f":"'K20 - time schedule'!HG69","v":0},{"$f":"'K20 - time schedule'!HH69","v":0},{"$f":"'K20 - time schedule'!HI69","v":0},{"$f":"'K20 - time schedule'!HJ69","v":0},{"$f":"'K20 - time schedule'!HK69","v":0},{"$f":"'K20 - time schedule'!HL69","v":0},{"$f":"'K20 - time schedule'!HM69","v":0},{"$f":"'K20 - time schedule'!HN69","v":0},{"$f":"'K20 - time schedule'!HO69","v":0},{"$f":"'K20 - time schedule'!HP69","v":0},{"$f":"'K20 - time schedule'!HQ69","v":0},{"$f":"'K20 - time schedule'!HR69","v":0},{"$f":"'K20 - time schedule'!HS69","v":0},{"$f":"'K20 - time schedule'!HT69","v":0},{"$f":"'K20 - time schedule'!HU69","v":0},{"$f":"'K20 - time schedule'!HV69","v":0},{"$f":"'K20 - time schedule'!HW69","v":0},{"$f":"'K20 - time schedule'!HX69","v":0},{"$f":"'K20 - time schedule'!HY69","v":0},{"$f":"'K20 - time schedule'!HZ69","v":0},{"$f":"'K20 - time schedule'!IA69","v":0},{"$f":"'K20 - time schedule'!IB69","v":0},{"$f":"'K20 - time schedule'!IC69","v":0},{"$f":"'K20 - time schedule'!ID69","v":0},{"$f":"'K20 - time schedule'!IE69","v":0},{"$f":"'K20 - time schedule'!IF69","v":0},{"$f":"'K20 - time schedule'!IG69","v":0},{"$f":"'K20 - time schedule'!IH69","v":0},{"$f":"'K20 - time schedule'!II69","v":0},{"$f":"'K20 - time schedule'!IJ69","v":0},{"$f":"'K20 - time schedule'!IK69","v":0},{"$f":"'K20 - time schedule'!IL69","v":0},{"$f":"'K20 - time schedule'!IM69","v":0},{"$f":"'K20 - time schedule'!IN69","v":0},{"$f":"'K20 - time schedule'!IO69","v":0},{"$f":"'K20 - time schedule'!IP69","v":0},{"$f":"'K20 - time schedule'!IQ69","v":0},{"$f":"'K20 - time schedule'!IR69","v":0},{"$f":"'K20 - time schedule'!IS69","v":0},{"$f":"'K20 - time schedule'!IT69","v":0},{"$f":"'K20 - time schedule'!IU69","v":0},{"$f":"'K20 - time schedule'!IV69","v":0},{"$f":"'K20 - time schedule'!IW69","v":0},{"$f":"'K20 - time schedule'!IX69","v":0},{"$f":"'K20 - time schedule'!IY69","v":0},{"$f":"'K20 - time schedule'!IZ69","v":0},{"$f":"'K20 - time schedule'!JA69","v":0},{"$f":"'K20 - time schedule'!JB69","v":0},{"$f":"'K20 - time schedule'!JC69","v":0},{"$f":"'K20 - time schedule'!JD69","v":0},{"$f":"'K20 - time schedule'!JE69","v":0},{"$f":"'K20 - time schedule'!JF69","v":0},{"$f":"'K20 - time schedule'!JG69","v":0},{"$f":"'K20 - time schedule'!JH69","v":0},{"$f":"'K20 - time schedule'!JI69","v":0},{"$f":"'K20 - time schedule'!JJ69","v":0},{"$f":"'K20 - time schedule'!JK69","v":0},{"$f":"'K20 - time schedule'!JL69","v":0},{"$f":"'K20 - time schedule'!JM69","v":0},{"$f":"'K20 - time schedule'!JN69","v":0},{"$f":"'K20 - time schedule'!JO69","v":0},{"$f":"'K20 - time schedule'!JP69","v":0},{"$f":"'K20 - time schedule'!JQ69","v":0},{"$f":"'K20 - time schedule'!JR69","v":0},{"$f":"'K20 - time schedule'!JS69","v":0},{"$f":"'K20 - time schedule'!JT69","v":0},{"$f":"'K20 - time schedule'!JU69","v":0},{"$f":"'K20 - time schedule'!JV69","v":0},{"$f":"'K20 - time schedule'!JW69","v":0},{"$f":"'K20 - time schedule'!JX69","v":0},{"$f":"'K20 - time schedule'!JY69","v":0},{"$f":"'K20 - time schedule'!JZ69","v":0},{"$f":"'K20 - time schedule'!KA69","v":0},{"$f":"'K20 - time schedule'!KB69","v":0},{"$f":"'K20 - time schedule'!KC69","v":0},{"$f":"'K20 - time schedule'!KD69","v":0},{"$f":"'K20 - time schedule'!KE69","v":0},{"$f":"'K20 - time schedule'!KF69","v":0},{"$f":"'K20 - time schedule'!KG69","v":0},{"$f":"'K20 - time schedule'!KH69","v":0},{"$f":"'K20 - time schedule'!KI69","v":0},{"$f":"'K20 - time schedule'!KJ69","v":0},{"$f":"'K20 - time schedule'!KK69","v":0},{"$f":"'K20 - time schedule'!KL69","v":0},{"$f":"'K20 - time schedule'!KM69","v":0},{"$f":"'K20 - time schedule'!KN69","v":0},{"$f":"'K20 - time schedule'!KO69","v":0},{"$f":"'K20 - time schedule'!KP69","v":0},{"$f":"'K20 - time schedule'!KQ69","v":0},{"$f":"'K20 - time schedule'!KR69","v":0},{"$f":"'K20 - time schedule'!KS69","v":0},{"$f":"'K20 - time schedule'!KT69","v":0}]
["Boiler room K90 - economizer","K90","EUR",{"$f":"'K90 - time schedule'!G31","v":0},{"$f":"'K90 - time schedule'!H31","v":0},{"$f":"'K90 - time schedule'!I31","v":0},{"$f":"'K90 - time schedule'!J31","v":0},{"$f":"'K90 - time schedule'!K31","v":0},{"$f":"'K90 - time schedule'!L31","v":0},{"$f":"'K90 - time schedule'!M31","v":0},{"$f":"'K90 - time schedule'!N31","v":0},{"$f":"'K90 - time schedule'!O31","v":0},{"$f":"'K90 - time schedule'!P31","v":0},{"$f":"'K90 - time schedule'!Q31","v":0},{"$f":"'K90 - time schedule'!R31","v":0},{"$f":"'K90 - time schedule'!S31","v":0},{"$f":"'K90 - time schedule'!T31","v":0},{"$f":"'K90 - time schedule'!U31","v":0},{"$f":"'K90 - time schedule'!V31","v":0},{"$f":"'K90 - time schedule'!W31","v":0},{"$f":"'K90 - time schedule'!X31","v":0},{"$f":"'K90 - time schedule'!Y31","v":0},{"$f":"'K90 - time schedule'!Z31","v":0},{"$f":"'K90 - time schedule'!AA31","v":0},{"$f":"'K90 - time schedule'!AB31","v":0},{"$f":"'K90 - time schedule'!AC31","v":0},{"$f":"'K90 - time schedule'!AD31","v":0},{"$f":"'K90 - time schedule'!AE31","v":0},{"$f":"'K90 - time schedule'!AF31","v":0},{"$f":"'K90 - time schedule'!AG31","v":0},{"$f":"'K90 - time schedule'!AH31","v":0},{"$f":"'K90 - time schedule'!AI31","v":0},{"$f":"'K90 - time schedule'!AJ31","v":0},{"$f":"'K90 - time schedule'!AK31","v":0},{"$f":"'K90 - time schedule'!AL31","v":0},{"$f":"'K90 - time schedule'!AM31","v":0},{"$f":"'K90 - time schedule'!AN31","v":0},{"$f":"'K90 - time schedule'!AO31","v":0},{"$f":"'K90 - time schedule'!AP31","v":0},{"$f":"'K90 - time schedule'!AQ31","v":0},{"$f":"'K90 - time schedule'!AR31","v":0},{"$f":"'K90 - time schedule'!AS31","v":0},{"$f":"'K90 - time schedule'!AT31","v":0},{"$f":"'K90 - time schedule'!AU31","v":0},{"$f":"'K90 - time schedule'!AV31","v":0},{"$f":"'K90 - time schedule'!AW31","v":0},{"$f":"'K90 - time schedule'!AX31","v":0},{"$f":"'K90 - time schedule'!AY31","v":0},{"$f":"'K90 - time schedule'!AZ31","v":0},{"$f":"'K90 - time schedule'!BA31","v":0},{"$f":"'K90 - time schedule'!BB31","v":0},{"$f":"'K90 - time schedule'!BC31","v":0},{"$f":"'K90 - time schedule'!BD31","v":0},{"$f":"'K90 - time schedule'!BE31","v":0},{"$f":"'K90 - time schedule'!BF31","v":0},{"$f":"'K90 - time schedule'!BG31","v":0},{"$f":"'K90 - time schedule'!BH31","v":0},{"$f":"'K90 - time schedule'!BI31","v":0},{"$f":"'K90 - time schedule'!BJ31","v":0},{"$f":"'K90 - time schedule'!BK31","v":0},{"$f":"'K90 - time schedule'!BL31","v":0},{"$f":"'K90 - time schedule'!BM31","v":0},{"$f":"'K90 - time schedule'!BN31","v":0},{"$f":"'K90 - time schedule'!BO31","v":0},{"$f":"'K90 - time schedule'!BP31","v":0},{"$f":"'K90 - time schedule'!BQ31","v":0},{"$f":"'K90 - time schedule'!BR31","v":0},{"$f":"'K90 - time schedule'!BS31","v":0},{"$f":"'K90 - time schedule'!BT31","v":0},{"$f":"'K90 - time schedule'!BU31","v":0},{"$f":"'K90 - time schedule'!BV31","v":0},{"$f":"'K90 - time schedule'!BW31","v":0},{"$f":"'K90 - time schedule'!BX31","v":0},{"$f":"'K90 - time schedule'!BY31","v":0},{"$f":"'K90 - time schedule'!BZ31","v":0},{"$f":"'K90 - time schedule'!CA31","v":0},{"$f":"'K90 - time schedule'!CB31","v":0},{"$f":"'K90 - time schedule'!CC31","v":0},{"$f":"'K90 - time schedule'!CD31","v":0},{"$f":"'K90 - time schedule'!CE31","v":0},{"$f":"'K90 - time schedule'!CF31","v":0},{"$f":"'K90 - time schedule'!CG31","v":0},{"$f":"'K90 - time schedule'!CH31","v":0},{"$f":"'K90 - time schedule'!CI31","v":0},{"$f":"'K90 - time schedule'!CJ31","v":0},{"$f":"'K90 - time schedule'!CK31","v":0},{"$f":"'K90 - time schedule'!CL31","v":0},{"$f":"'K90 - time schedule'!CM31","v":0},{"$f":"'K90 - time schedule'!CN31","v":0},{"$f":"'K90 - time schedule'!CO31","v":0},{"$f":"'K90 - time schedule'!CP31","v":0},{"$f":"'K90 - time schedule'!CQ31","v":0},{"$f":"'K90 - time schedule'!CR31","v":0},{"$f":"'K90 - time schedule'!CS31","v":0},{"$f":"'K90 - time schedule'!CT31","v":0},{"$f":"'K90 - time schedule'!CU31","v":0},{"$f":"'K90 - time schedule'!CV31","v":0},{"$f":"'K90 - time schedule'!CW31","v":0},{"$f":"'K90 - time schedule'!CX31","v":0},{"$f":"'K90 - time schedule'!CY31","v":0},{"$f":"'K90 - time schedule'!CZ31","v":0},{"$f":"'K90 - time schedule'!DA31","v":0},{"$f":"'K90 - time schedule'!DB31","v":0},{"$f":"'K90 - time schedule'!DC31","v":0},{"$f":"'K90 - time schedule'!DD31","v":0},{"$f":"'K90 - time schedule'!DE31","v":0},{"$f":"'K90 - time schedule'!DF31","v":0},{"$f":"'K90 - time schedule'!DG31","v":0},{"$f":"'K90 - time schedule'!DH31","v":0},{"$f":"'K90 - time schedule'!DI31","v":0},{"$f":"'K90 - time schedule'!DJ31","v":0},{"$f":"'K90 - time schedule'!DK31","v":0},{"$f":"'K90 - time schedule'!DL31","v":0},{"$f":"'K90 - time schedule'!DM31","v":0},{"$f":"'K90 - time schedule'!DN31","v":0},{"$f":"'K90 - time schedule'!DO31","v":0},{"$f":"'K90 - time schedule'!DP31","v":0},{"$f":"'K90 - time schedule'!DQ31","v":0},{"$f":"'K90 - time schedule'!DR31","v":0},{"$f":"'K90 - time schedule'!DS31","v":0},{"$f":"'K90 - time schedule'!DT31","v":0},{"$f":"'K90 - time schedule'!DU31","v":0},{"$f":"'K90 - time schedule'!DV31","v":0},{"$f":"'K90 - time schedule'!DW31","v":0},{"$f":"'K90 - time schedule'!DX31","v":0},{"$f":"'K90 - time schedule'!DY31","v":0},{"$f":"'K90 - time schedule'!DZ31","v":0},{"$f":"'K90 - time schedule'!EA31","v":0},{"$f":"'K90 - time schedule'!EB31","v":0},{"$f":"'K90 - time schedule'!EC31","v":0},{"$f":"'K90 - time schedule'!ED31","v":0},{"$f":"'K90 - time schedule'!EE31","v":0},{"$f":"'K90 - time schedule'!EF31","v":0},{"$f":"'K90 - time schedule'!EG31","v":0},{"$f":"'K90 - time schedule'!EH31","v":0},{"$f":"'K90 - time schedule'!EI31","v":0},{"$f":"'K90 - time schedule'!EJ31","v":0},{"$f":"'K90 - time schedule'!EK31","v":0},{"$f":"'K90 - time schedule'!EL31","v":0},{"$f":"'K90 - time schedule'!EM31","v":0},{"$f":"'K90 - time schedule'!EN31","v":0},{"$f":"'K90 - time schedule'!EO31","v":0},{"$f":"'K90 - time schedule'!EP31","v":0},{"$f":"'K90 - time schedule'!EQ31","v":0},{"$f":"'K90 - time schedule'!ER31","v":0},{"$f":"'K90 - time schedule'!ES31","v":0},{"$f":"'K90 - time schedule'!ET31","v":0},{"$f":"'K90 - time schedule'!EU31","v":0},{"$f":"'K90 - time schedule'!EV31","v":0},{"$f":"'K90 - time schedule'!EW31","v":0},{"$f":"'K90 - time schedule'!EX31","v":0},{"$f":"'K90 - time schedule'!EY31","v":0},{"$f":"'K90 - time schedule'!EZ31","v":0},{"$f":"'K90 - time schedule'!FA31","v":0},{"$f":"'K90 - time schedule'!FB31","v":0},{"$f":"'K90 - time schedule'!FC31","v":0},{"$f":"'K90 - time schedule'!FD31","v":0},{"$f":"'K90 - time schedule'!FE31","v":0},{"$f":"'K90 - time schedule'!FF31","v":0},{"$f":"'K90 - time schedule'!FG31","v":0},{"$f":"'K90 - time schedule'!FH31","v":0},{"$f":"'K90 - time schedule'!FI31","v":0},{"$f":"'K90 - time schedule'!FJ31","v":0},{"$f":"'K90 - time schedule'!FK31","v":0},{"$f":"'K90 - time schedule'!FL31","v":0},{"$f":"'K90 - time schedule'!FM31","v":0},{"$f":"'K90 - time schedule'!FN31","v":0},{"$f":"'K90 - time schedule'!FO31","v":0},{"$f":"'K90 - time schedule'!FP31","v":0},{"$f":"'K90 - time schedule'!FQ31","v":0},{"$f":"'K90 - time schedule'!FR31","v":0},{"$f":"'K90 - time schedule'!FS31","v":0},{"$f":"'K90 - time schedule'!FT31","v":0},{"$f":"'K90 - time schedule'!FU31","v":0},{"$f":"'K90 - time schedule'!FV31","v":0},{"$f":"'K90 - time schedule'!FW31","v":0},{"$f":"'K90 - time schedule'!FX31","v":0},{"$f":"'K90 - time schedule'!FY31","v":0},{"$f":"'K90 - time schedule'!FZ31","v":0},{"$f":"'K90 - time schedule'!GA31","v":0},{"$f":"'K90 - time schedule'!GB31","v":0},{"$f":"'K90 - time schedule'!GC31","v":0},{"$f":"'K90 - time schedule'!GD31","v":0},{"$f":"'K90 - time schedule'!GE31","v":0},{"$f":"'K90 - time schedule'!GF31","v":0},{"$f":"'K20 - time schedule'!GG70","v":0},{"$f":"'K20 - time schedule'!GH70","v":0},{"$f":"'K20 - time schedule'!GI70","v":0},{"$f":"'K20 - time schedule'!GJ70","v":0},{"$f":"'K20 - time schedule'!GK70","v":0},{"$f":"'K20 - time schedule'!GL70","v":0},{"$f":"'K20 - time schedule'!GM70","v":0},{"$f":"'K20 - time schedule'!GN70","v":0},{"$f":"'K20 - time schedule'!GO70","v":0},{"$f":"'K20 - time schedule'!GP70","v":0},{"$f":"'K20 - time schedule'!GQ70","v":0},{"$f":"'K20 - time schedule'!GR70","v":0},{"$f":"'K20 - time schedule'!GS70","v":0},{"$f":"'K20 - time schedule'!GT70","v":0},{"$f":"'K20 - time schedule'!GU70","v":0},{"$f":"'K20 - time schedule'!GV70","v":0},{"$f":"'K20 - time schedule'!GW70","v":0},{"$f":"'K20 - time schedule'!GX70","v":0},{"$f":"'K20 - time schedule'!GY70","v":0},{"$f":"'K20 - time schedule'!GZ70","v":0},{"$f":"'K20 - time schedule'!HA70","v":0},{"$f":"'K20 - time schedule'!HB70","v":0},{"$f":"'K20 - time schedule'!HC70","v":0},{"$f":"'K20 - time schedule'!HD70","v":0},{"$f":"'K20 - time schedule'!HE70","v":0},{"$f":"'K20 - time schedule'!HF70","v":0},{"$f":"'K20 - time schedule'!HG70","v":0},{"$f":"'K20 - time schedule'!HH70","v":0},{"$f":"'K20 - time schedule'!HI70","v":0},{"$f":"'K20 - time schedule'!HJ70","v":0},{"$f":"'K20 - time schedule'!HK70","v":0},{"$f":"'K20 - time schedule'!HL70","v":0},{"$f":"'K20 - time schedule'!HM70","v":0},{"$f":"'K20 - time schedule'!HN70","v":0},{"$f":"'K20 - time schedule'!HO70","v":0},{"$f":"'K20 - time schedule'!HP70","v":0},{"$f":"'K20 - time schedule'!HQ70","v":0},{"$f":"'K20 - time schedule'!HR70","v":0},{"$f":"'K20 - time schedule'!HS70","v":0},{"$f":"'K20 - time schedule'!HT70","v":0},{"$f":"'K20 - time schedule'!HU70","v":0},{"$f":"'K20 - time schedule'!HV70","v":0},{"$f":"'K20 - time schedule'!HW70","v":0},{"$f":"'K20 - time schedule'!HX70","v":0},{"$f":"'K20 - time schedule'!HY70","v":0},{"$f":"'K20 - time schedule'!HZ70","v":0},{"$f":"'K20 - time schedule'!IA70","v":0},{"$f":"'K20 - time schedule'!IB70","v":0},{"$f":"'K20 - time schedule'!IC70","v":0},{"$f":"'K20 - time schedule'!ID70","v":0},{"$f":"'K20 - time schedule'!IE70","v":0},{"$f":"'K20 - time schedule'!IF70","v":0},{"$f":"'K20 - time schedule'!IG70","v":0},{"$f":"'K20 - time schedule'!IH70","v":0},{"$f":"'K20 - time schedule'!II70","v":0},{"$f":"'K20 - time schedule'!IJ70","v":0},{"$f":"'K20 - time schedule'!IK70","v":0},{"$f":"'K20 - time schedule'!IL70","v":0},{"$f":"'K20 - time schedule'!IM70","v":0},{"$f":"'K20 - time schedule'!IN70","v":0},{"$f":"'K20 - time schedule'!IO70","v":0},{"$f":"'K20 - time schedule'!IP70","v":0},{"$f":"'K20 - time schedule'!IQ70","v":0},{"$f":"'K20 - time schedule'!IR70","v":0},{"$f":"'K20 - time schedule'!IS70","v":0},{"$f":"'K20 - time schedule'!IT70","v":0},{"$f":"'K20 - time schedule'!IU70","v":0},{"$f":"'K20 - time schedule'!IV70","v":0},{"$f":"'K20 - time schedule'!IW70","v":0},{"$f":"'K20 - time schedule'!IX70","v":0},{"$f":"'K20 - time schedule'!IY70","v":0},{"$f":"'K20 - time schedule'!IZ70","v":0},{"$f":"'K20 - time schedule'!JA70","v":0},{"$f":"'K20 - time schedule'!JB70","v":0},{"$f":"'K20 - time schedule'!JC70","v":0},{"$f":"'K20 - time schedule'!JD70","v":0},{"$f":"'K20 - time schedule'!JE70","v":0},{"$f":"'K20 - time schedule'!JF70","v":0},{"$f":"'K20 - time schedule'!JG70","v":0},{"$f":"'K20 - time schedule'!JH70","v":0},{"$f":"'K20 - time schedule'!JI70","v":0},{"$f":"'K20 - time schedule'!JJ70","v":0},{"$f":"'K20 - time schedule'!JK70","v":0},{"$f":"'K20 - time schedule'!JL70","v":0},{"$f":"'K20 - time schedule'!JM70","v":0},{"$f":"'K20 - time schedule'!JN70","v":0},{"$f":"'K20 - time schedule'!JO70","v":0},{"$f":"'K20 - time schedule'!JP70","v":0},{"$f":"'K20 - time schedule'!JQ70","v":0},{"$f":"'K20 - time schedule'!JR70","v":0},{"$f":"'K20 - time schedule'!JS70","v":0},{"$f":"'K20 - time schedule'!JT70","v":0},{"$f":"'K20 - time schedule'!JU70","v":0},{"$f":"'K20 - time schedule'!JV70","v":0},{"$f":"'K20 - time schedule'!JW70","v":0},{"$f":"'K20 - time schedule'!JX70","v":0},{"$f":"'K20 - time schedule'!JY70","v":0},{"$f":"'K20 - time schedule'!JZ70","v":0},{"$f":"'K20 - time schedule'!KA70","v":0},{"$f":"'K20 - time schedule'!KB70","v":0},{"$f":"'K20 - time schedule'!KC70","v":0},{"$f":"'K20 - time schedule'!KD70","v":0},{"$f":"'K20 - time schedule'!KE70","v":0},{"$f":"'K20 - time schedule'!KF70","v":0},{"$f":"'K20 - time schedule'!KG70","v":0},{"$f":"'K20 - time schedule'!KH70","v":0},{"$f":"'K20 - time schedule'!KI70","v":0},{"$f":"'K20 - time schedule'!KJ70","v":0},{"$f":"'K20 - time schedule'!KK70","v":0},{"$f":"'K20 - time schedule'!KL70","v":0},{"$f":"'K20 - time schedule'!KM70","v":0},{"$f":"'K20 - time schedule'!KN70","v":0},{"$f":"'K20 - time schedule'!KO70","v":0},{"$f":"'K20 - time schedule'!KP70","v":0},{"$f":"'K20 - time schedule'!KQ70","v":0},{"$f":"'K20 - time schedule'!KR70","v":0},{"$f":"'K20 - time schedule'!KS70","v":0},{"$f":"'K20 - time schedule'!KT70","v":0}]
["Boiler room K90 - lining","K90","EUR",{"$f":"'K90 - time schedule'!G33","v":0},{"$f":"'K90 - time schedule'!H33","v":0},{"$f":"'K90 - time schedule'!I33","v":0},{"$f":"'K90 - time schedule'!J33","v":0},{"$f":"'K90 - time schedule'!K33","v":0},{"$f":"'K90 - time schedule'!L33","v":0},{"$f":"'K90 - time schedule'!M33","v":0},{"$f":"'K90 - time schedule'!N33","v":0},{"$f":"'K90 - time schedule'!O33","v":0},{"$f":"'K90 - time schedule'!P33","v":0},{"$f":"'K90 - time schedule'!Q33","v":0},{"$f":"'K90 - time schedule'!R33","v":0},{"$f":"'K90 - time schedule'!S33","v":0},{"$f":"'K90 - time schedule'!T33","v":0},{"$f":"'K90 - time schedule'!U33","v":0},{"$f":"'K90 - time schedule'!V33","v":0},{"$f":"'K90 - time schedule'!W33","v":0},{"$f":"'K90 - time schedule'!X33","v":0},{"$f":"'K90 - time schedule'!Y33","v":0},{"$f":"'K90 - time schedule'!Z33","v":0},{"$f":"'K90 - time schedule'!AA33","v":0},{"$f":"'K90 - time schedule'!AB33","v":0},{"$f":"'K90 - time schedule'!AC33","v":0},{"$f":"'K90 - time schedule'!AD33","v":0},{"$f":"'K90 - time schedule'!AE33","v":0},{"$f":"'K90 - time schedule'!AF33","v":0},{"$f":"'K90 - time schedule'!AG33","v":0},{"$f":"'K90 - time schedule'!AH33","v":0},{"$f":"'K90 - time schedule'!AI33","v":0},{"$f":"'K90 - time schedule'!AJ33","v":0},{"$f":"'K90 - time schedule'!AK33","v":0},{"$f":"'K90 - time schedule'!AL33","v":0},{"$f":"'K90 - time schedule'!AM33","v":0},{"$f":"'K90 - time schedule'!AN33","v":0},{"$f":"'K90 - time schedule'!AO33","v":0},{"$f":"'K90 - time schedule'!AP33","v":0},{"$f":"'K90 - time schedule'!AQ33","v":0},{"$f":"'K90 - time schedule'!AR33","v":0},{"$f":"'K90 - time schedule'!AS33","v":0},{"$f":"'K90 - time schedule'!AT33","v":0},{"$f":"'K90 - time schedule'!AU33","v":0},{"$f":"'K90 - time schedule'!AV33","v":0},{"$f":"'K90 - time schedule'!AW33","v":0},{"$f":"'K90 - time schedule'!AX33","v":0},{"$f":"'K90 - time schedule'!AY33","v":0},{"$f":"'K90 - time schedule'!AZ33","v":0},{"$f":"'K90 - time schedule'!BA33","v":0},{"$f":"'K90 - time schedule'!BB33","v":0},{"$f":"'K90 - time schedule'!BC33","v":0},{"$f":"'K90 - time schedule'!BD33","v":0},{"$f":"'K90 - time schedule'!BE33","v":0},{"$f":"'K90 - time schedule'!BF33","v":0},{"$f":"'K90 - time schedule'!BG33","v":0},{"$f":"'K90 - time schedule'!BH33","v":0},{"$f":"'K90 - time schedule'!BI33","v":0},{"$f":"'K90 - time schedule'!BJ33","v":0},{"$f":"'K90 - time schedule'!BK33","v":0},{"$f":"'K90 - time schedule'!BL33","v":0},{"$f":"'K90 - time schedule'!BM33","v":0},{"$f":"'K90 - time schedule'!BN33","v":0},{"$f":"'K90 - time schedule'!BO33","v":0},{"$f":"'K90 - time schedule'!BP33","v":0},{"$f":"'K90 - time schedule'!BQ33","v":0},{"$f":"'K90 - time schedule'!BR33","v":0},{"$f":"'K90 - time schedule'!BS33","v":0},{"$f":"'K90 - time schedule'!BT33","v":0},{"$f":"'K90 - time schedule'!BU33","v":0},{"$f":"'K90 - time schedule'!BV33","v":0},{"$f":"'K90 - time schedule'!BW33","v":0},{"$f":"'K90 - time schedule'!BX33","v":0},{"$f":"'K90 - time schedule'!BY33","v":0},{"$f":"'K90 - time schedule'!BZ33","v":0},{"$f":"'K90 - time schedule'!CA33","v":0},{"$f":"'K90 - time schedule'!CB33","v":0},{"$f":"'K90 - time schedule'!CC33","v":0},{"$f":"'K90 - time schedule'!CD33","v":0},{"$f":"'K90 - time schedule'!CE33","v":0},{"$f":"'K90 - time schedule'!CF33","v":0},{"$f":"'K90 - time schedule'!CG33","v":0},{"$f":"'K90 - time schedule'!CH33","v":0},{"$f":"'K90 - time schedule'!CI33","v":0},{"$f":"'K90 - time schedule'!CJ33","v":0},{"$f":"'K90 - time schedule'!CK33","v":0},{"$f":"'K90 - time schedule'!CL33","v":0},{"$f":"'K90 - time schedule'!CM33","v":0},{"$f":"'K90 - time schedule'!CN33","v":0},{"$f":"'K90 - time schedule'!CO33","v":0},{"$f":"'K90 - time schedule'!CP33","v":0},{"$f":"'K90 - time schedule'!CQ33","v":0},{"$f":"'K90 - time schedule'!CR33","v":0},{"$f":"'K90 - time schedule'!CS33","v":0},{"$f":"'K90 - time schedule'!CT33","v":0},{"$f":"'K90 - time schedule'!CU33","v":0},{"$f":"'K90 - time schedule'!CV33","v":0},{"$f":"'K90 - time schedule'!CW33","v":0},{"$f":"'K90 - time schedule'!CX33","v":0},{"$f":"'K90 - time schedule'!CY33","v":0},{"$f":"'K90 - time schedule'!CZ33","v":0},{"$f":"'K90 - time schedule'!DA33","v":0},{"$f":"'K90 - time schedule'!DB33","v":0},{"$f":"'K90 - time schedule'!DC33","v":0},{"$f":"'K90 - time schedule'!DD33","v":0},{"$f":"'K90 - time schedule'!DE33","v":0},{"$f":"'K90 - time schedule'!DF33","v":0},{"$f":"'K90 - time schedule'!DG33","v":0},{"$f":"'K90 - time schedule'!DH33","v":0},{"$f":"'K90 - time schedule'!DI33","v":0},{"$f":"'K90 - time schedule'!DJ33","v":0},{"$f":"'K90 - time schedule'!DK33","v":0},{"$f":"'K90 - time schedule'!DL33","v":0},{"$f":"'K90 - time schedule'!DM33","v":0},{"$f":"'K90 - time schedule'!DN33","v":0},{"$f":"'K90 - time schedule'!DO33","v":0},{"$f":"'K90 - time schedule'!DP33","v":0},{"$f":"'K90 - time schedule'!DQ33","v":0},{"$f":"'K90 - time schedule'!DR33","v":0},{"$f":"'K90 - time schedule'!DS33","v":0},{"$f":"'K90 - time schedule'!DT33","v":0},{"$f":"'K90 - time schedule'!DU33","v":0},{"$f":"'K90 - time schedule'!DV33","v":0},{"$f":"'K90 - time schedule'!DW33","v":0},{"$f":"'K90 - time schedule'!DX33","v":0},{"$f":"'K90 - time schedule'!DY33","v":0},{"$f":"'K90 - time schedule'!DZ33","v":0},{"$f":"'K90 - time schedule'!EA33","v":0},{"$f":"'K90 - time schedule'!EB33","v":0},{"$f":"'K90 - time schedule'!EC33","v":0},{"$f":"'K90 - time schedule'!ED33","v":0},{"$f":"'K90 - time schedule'!EE33","v":0},{"$f":"'K90 - time schedule'!EF33","v":0},{"$f":"'K90 - time schedule'!EG33","v":0},{"$f":"'K90 - time schedule'!EH33","v":0},{"$f":"'K90 - time schedule'!EI33","v":0},{"$f":"'K90 - time schedule'!EJ33","v":0},{"$f":"'K90 - time schedule'!EK33","v":0},{"$f":"'K90 - time schedule'!EL33","v":0},{"$f":"'K90 - time schedule'!EM33","v":0},{"$f":"'K90 - time schedule'!EN33","v":0},{"$f":"'K90 - time schedule'!EO33","v":0},{"$f":"'K90 - time schedule'!EP33","v":0},{"$f":"'K90 - time schedule'!EQ33","v":0},{"$f":"'K90 - time schedule'!ER33","v":0},{"$f":"'K90 - time schedule'!ES33","v":0},{"$f":"'K90 - time schedule'!ET33","v":0},{"$f":"'K90 - time schedule'!EU33","v":0},{"$f":"'K90 - time schedule'!EV33","v":0},{"$f":"'K90 - time schedule'!EW33","v":0},{"$f":"'K90 - time schedule'!EX33","v":0},{"$f":"'K90 - time schedule'!EY33","v":0},{"$f":"'K90 - time schedule'!EZ33","v":0},{"$f":"'K90 - time schedule'!FA33","v":0},{"$f":"'K90 - time schedule'!FB33","v":0},{"$f":"'K90 - time schedule'!FC33","v":0},{"$f":"'K90 - time schedule'!FD33","v":0},{"$f":"'K90 - time schedule'!FE33","v":0},{"$f":"'K90 - time schedule'!FF33","v":0},{"$f":"'K90 - time schedule'!FG33","v":0},{"$f":"'K90 - time schedule'!FH33","v":0},{"$f":"'K90 - time schedule'!FI33","v":0},{"$f":"'K90 - time schedule'!FJ33","v":0},{"$f":"'K90 - time schedule'!FK33","v":0},{"$f":"'K90 - time schedule'!FL33","v":0},{"$f":"'K90 - time schedule'!FM33","v":0},{"$f":"'K90 - time schedule'!FN33","v":0},{"$f":"'K90 - time schedule'!FO33","v":0},{"$f":"'K90 - time schedule'!FP33","v":0},{"$f":"'K90 - time schedule'!FQ33","v":0},{"$f":"'K90 - time schedule'!FR33","v":0},{"$f":"'K90 - time schedule'!FS33","v":0},{"$f":"'K90 - time schedule'!FT33","v":0},{"$f":"'K90 - time schedule'!FU33","v":0},{"$f":"'K90 - time schedule'!FV33","v":0},{"$f":"'K90 - time schedule'!FW33","v":0},{"$f":"'K90 - time schedule'!FX33","v":0},{"$f":"'K90 - time schedule'!FY33","v":0},{"$f":"'K90 - time schedule'!FZ33","v":0},{"$f":"'K90 - time schedule'!GA33","v":0},{"$f":"'K90 - time schedule'!GB33","v":0},{"$f":"'K90 - time schedule'!GC33","v":0},{"$f":"'K90 - time schedule'!GD33","v":0},{"$f":"'K90 - time schedule'!GE33","v":0},{"$f":"'K90 - time schedule'!GF33","v":0},{"$f":"'K20 - time schedule'!GG71","v":0},{"$f":"'K20 - time schedule'!GH71","v":0},{"$f":"'K20 - time schedule'!GI71","v":0},{"$f":"'K20 - time schedule'!GJ71","v":0},{"$f":"'K20 - time schedule'!GK71","v":0},{"$f":"'K20 - time schedule'!GL71","v":0},{"$f":"'K20 - time schedule'!GM71","v":0},{"$f":"'K20 - time schedule'!GN71","v":0},{"$f":"'K20 - time schedule'!GO71","v":0},{"$f":"'K20 - time schedule'!GP71","v":0},{"$f":"'K20 - time schedule'!GQ71","v":0},{"$f":"'K20 - time schedule'!GR71","v":0},{"$f":"'K20 - time schedule'!GS71","v":0},{"$f":"'K20 - time schedule'!GT71","v":0},{"$f":"'K20 - time schedule'!GU71","v":0},{"$f":"'K20 - time schedule'!GV71","v":0},{"$f":"'K20 - time schedule'!GW71","v":0},{"$f":"'K20 - time schedule'!GX71","v":0},{"$f":"'K20 - time schedule'!GY71","v":0},{"$f":"'K20 - time schedule'!GZ71","v":0},{"$f":"'K20 - time schedule'!HA71","v":0},{"$f":"'K20 - time schedule'!HB71","v":0},{"$f":"'K20 - time schedule'!HC71","v":0},{"$f":"'K20 - time schedule'!HD71","v":0},{"$f":"'K20 - time schedule'!HE71","v":0},{"$f":"'K20 - time schedule'!HF71","v":0},{"$f":"'K20 - time schedule'!HG71","v":0},{"$f":"'K20 - time schedule'!HH71","v":0},{"$f":"'K20 - time schedule'!HI71","v":0},{"$f":"'K20 - time schedule'!HJ71","v":0},{"$f":"'K20 - time schedule'!HK71","v":0},{"$f":"'K20 - time schedule'!HL71","v":0},{"$f":"'K20 - time schedule'!HM71","v":0},{"$f":"'K20 - time schedule'!HN71","v":0},{"$f":"'K20 - time schedule'!HO71","v":0},{"$f":"'K20 - time schedule'!HP71","v":0},{"$f":"'K20 - time schedule'!HQ71","v":0},{"$f":"'K20 - time schedule'!HR71","v":0},{"$f":"'K20 - time schedule'!HS71","v":0},{"$f":"'K20 - time schedule'!HT71","v":0},{"$f":"'K20 - time schedule'!HU71","v":0},{"$f":"'K20 - time schedule'!HV71","v":0},{"$f":"'K20 - time schedule'!HW71","v":0},{"$f":"'K20 - time schedule'!HX71","v":0},{"$f":"'K20 - time schedule'!HY71","v":0},{"$f":"'K20 - time schedule'!HZ71","v":0},{"$f":"'K20 - time schedule'!IA71","v":0},{"$f":"'K20 - time schedule'!IB71","v":0},{"$f":"'K20 - time schedule'!IC71","v":0},{"$f":"'K20 - time schedule'!ID71","v":0},{"$f":"'K20 - time schedule'!IE71","v":0},{"$f":"'K20 - time schedule'!IF71","v":0},{"$f":"'K20 - time schedule'!IG71","v":0},{"$f":"'K20 - time schedule'!IH71","v":0},{"$f":"'K20 - time schedule'!II71","v":0},{"$f":"'K20 - time schedule'!IJ71","v":0},{"$f":"'K20 - time schedule'!IK71","v":0},{"$f":"'K20 - time schedule'!IL71","v":0},{"$f":"'K20 - time schedule'!IM71","v":0},{"$f":"'K20 - time schedule'!IN71","v":0},{"$f":"'K20 - time schedule'!IO71","v":0},{"$f":"'K20 - time schedule'!IP71","v":0},{"$f":"'K20 - time schedule'!IQ71","v":0},{"$f":"'K20 - time schedule'!IR71","v":0},{"$f":"'K20 - time schedule'!IS71","v":0},{"$f":"'K20 - time schedule'!IT71","v":0},{"$f":"'K20 - time schedule'!IU71","v":0},{"$f":"'K20 - time schedule'!IV71","v":0},{"$f":"'K20 - time schedule'!IW71","v":0},{"$f":"'K20 - time schedule'!IX71","v":0},{"$f":"'K20 - time schedule'!IY71","v":0},{"$f":"'K20 - time schedule'!IZ71","v":0},{"$f":"'K20 - time schedule'!JA71","v":0},{"$f":"'K20 - time schedule'!JB71","v":0},{"$f":"'K20 - time schedule'!JC71","v":0},{"$f":"'K20 - time schedule'!JD71","v":0},{"$f":"'K20 - time schedule'!JE71","v":0},{"$f":"'K20 - time schedule'!JF71","v":0},{"$f":"'K20 - time schedule'!JG71","v":0},{"$f":"'K20 - time schedule'!JH71","v":0},{"$f":"'K20 - time schedule'!JI71","v":0},{"$f":"'K20 - time schedule'!JJ71","v":0},{"$f":"'K20 - time schedule'!JK71","v":0},{"$f":"'K20 - time schedule'!JL71","v":0},{"$f":"'K20 - time schedule'!JM71","v":0},{"$f":"'K20 - time schedule'!JN71","v":0},{"$f":"'K20 - time schedule'!JO71","v":0},{"$f":"'K20 - time schedule'!JP71","v":0},{"$f":"'K20 - time schedule'!JQ71","v":0},{"$f":"'K20 - time schedule'!JR71","v":0},{"$f":"'K20 - time schedule'!JS71","v":0},{"$f":"'K20 - time schedule'!JT71","v":0},{"$f":"'K20 - time schedule'!JU71","v":0},{"$f":"'K20 - time schedule'!JV71","v":0},{"$f":"'K20 - time schedule'!JW71","v":0},{"$f":"'K20 - time schedule'!JX71","v":0},{"$f":"'K20 - time schedule'!JY71","v":0},{"$f":"'K20 - time schedule'!JZ71","v":0},{"$f":"'K20 - time schedule'!KA71","v":0},{"$f":"'K20 - time schedule'!KB71","v":0},{"$f":"'K20 - time schedule'!KC71","v":0},{"$f":"'K20 - time schedule'!KD71","v":0},{"$f":"'K20 - time schedule'!KE71","v":0},{"$f":"'K20 - time schedule'!KF71","v":0},{"$f":"'K20 - time schedule'!KG71","v":0},{"$f":"'K20 - time schedule'!KH71","v":0},{"$f":"'K20 - time schedule'!KI71","v":0},{"$f":"'K20 - time schedule'!KJ71","v":0},{"$f":"'K20 - time schedule'!KK71","v":0},{"$f":"'K20 - time schedule'!KL71","v":0},{"$f":"'K20 - time schedule'!KM71","v":0},{"$f":"'K20 - time schedule'!KN71","v":0},{"$f":"'K20 - time schedule'!KO71","v":0},{"$f":"'K20 - time schedule'!KP71","v":0},{"$f":"'K20 - time schedule'!KQ71","v":0},{"$f":"'K20 - time schedule'!KR71","v":0},{"$f":"'K20 - time schedule'!KS71","v":0},{"$f":"'K20 - time schedule'!KT71","v":0}]
["Boiler room K90 - bottom of combustion chamber","K90","EUR",{"$f":"'K90 - time schedule'!G35","v":0},{"$f":"'K90 - time schedule'!H35","v":0},{"$f":"'K90 - time schedule'!I35","v":0},{"$f":"'K90 - time schedule'!J35","v":0},{"$f":"'K90 - time schedule'!K35","v":0},{"$f":"'K90 - time schedule'!L35","v":0},{"$f":"'K90 - time schedule'!M35","v":0},{"$f":"'K90 - time schedule'!N35","v":0},{"$f":"'K90 - time schedule'!O35","v":0},{"$f":"'K90 - time schedule'!P35","v":0},{"$f":"'K90 - time schedule'!Q35","v":0},{"$f":"'K90 - time schedule'!R35","v":0},{"$f":"'K90 - time schedule'!S35","v":0},{"$f":"'K90 - time schedule'!T35","v":0},{"$f":"'K90 - time schedule'!U35","v":0},{"$f":"'K90 - time schedule'!V35","v":0},{"$f":"'K90 - time schedule'!W35","v":0},{"$f":"'K90 - time schedule'!X35","v":0},{"$f":"'K90 - time schedule'!Y35","v":0},{"$f":"'K90 - time schedule'!Z35","v":0},{"$f":"'K90 - time schedule'!AA35","v":0},{"$f":"'K90 - time schedule'!AB35","v":0},{"$f":"'K90 - time schedule'!AC35","v":0},{"$f":"'K90 - time schedule'!AD35","v":0},{"$f":"'K90 - time schedule'!AE35","v":0},{"$f":"'K90 - time schedule'!AF35","v":0},{"$f":"'K90 - time schedule'!AG35","v":0},{"$f":"'K90 - time schedule'!AH35","v":0},{"$f":"'K90 - time schedule'!AI35","v":0},{"$f":"'K90 - time schedule'!AJ35","v":0},{"$f":"'K90 - time schedule'!AK35","v":0},{"$f":"'K90 - time schedule'!AL35","v":0},{"$f":"'K90 - time schedule'!AM35","v":0},{"$f":"'K90 - time schedule'!AN35","v":0},{"$f":"'K90 - time schedule'!AO35","v":0},{"$f":"'K90 - time schedule'!AP35","v":0},{"$f":"'K90 - time schedule'!AQ35","v":0},{"$f":"'K90 - time schedule'!AR35","v":0},{"$f":"'K90 - time schedule'!AS35","v":0},{"$f":"'K90 - time schedule'!AT35","v":0},{"$f":"'K90 - time schedule'!AU35","v":0},{"$f":"'K90 - time schedule'!AV35","v":0},{"$f":"'K90 - time schedule'!AW35","v":0},{"$f":"'K90 - time schedule'!AX35","v":0},{"$f":"'K90 - time schedule'!AY35","v":0},{"$f":"'K90 - time schedule'!AZ35","v":0},{"$f":"'K90 - time schedule'!BA35","v":0},{"$f":"'K90 - time schedule'!BB35","v":0},{"$f":"'K90 - time schedule'!BC35","v":0},{"$f":"'K90 - time schedule'!BD35","v":0},{"$f":"'K90 - time schedule'!BE35","v":0},{"$f":"'K90 - time schedule'!BF35","v":0},{"$f":"'K90 - time schedule'!BG35","v":0},{"$f":"'K90 - time schedule'!BH35","v":0},{"$f":"'K90 - time schedule'!BI35","v":0},{"$f":"'K90 - time schedule'!BJ35","v":0},{"$f":"'K90 - time schedule'!BK35","v":0},{"$f":"'K90 - time schedule'!BL35","v":0},{"$f":"'K90 - time schedule'!BM35","v":0},{"$f":"'K90 - time schedule'!BN35","v":0},{"$f":"'K90 - time schedule'!BO35","v":0},{"$f":"'K90 - time schedule'!BP35","v":0},{"$f":"'K90 - time schedule'!BQ35","v":0},{"$f":"'K90 - time schedule'!BR35","v":0},{"$f":"'K90 - time schedule'!BS35","v":0},{"$f":"'K90 - time schedule'!BT35","v":0},{"$f":"'K90 - time schedule'!BU35","v":0},{"$f":"'K90 - time schedule'!BV35","v":0},{"$f":"'K90 - time schedule'!BW35","v":0},{"$f":"'K90 - time schedule'!BX35","v":0},{"$f":"'K90 - time schedule'!BY35","v":0},{"$f":"'K90 - time schedule'!BZ35","v":0},{"$f":"'K90 - time schedule'!CA35","v":0},{"$f":"'K90 - time schedule'!CB35","v":0},{"$f":"'K90 - time schedule'!CC35","v":0},{"$f":"'K90 - time schedule'!CD35","v":0},{"$f":"'K90 - time schedule'!CE35","v":0},{"$f":"'K90 - time schedule'!CF35","v":0},{"$f":"'K90 - time schedule'!CG35","v":0},{"$f":"'K90 - time schedule'!CH35","v":0},{"$f":"'K90 - time schedule'!CI35","v":0},{"$f":"'K90 - time schedule'!CJ35","v":0},{"$f":"'K90 - time schedule'!CK35","v":0},{"$f":"'K90 - time schedule'!CL35","v":0},{"$f":"'K90 - time schedule'!CM35","v":0},{"$f":"'K90 - time schedule'!CN35","v":0},{"$f":"'K90 - time schedule'!CO35","v":0},{"$f":"'K90 - time schedule'!CP35","v":0},{"$f":"'K90 - time schedule'!CQ35","v":0},{"$f":"'K90 - time schedule'!CR35","v":0},{"$f":"'K90 - time schedule'!CS35","v":0},{"$f":"'K90 - time schedule'!CT35","v":0},{"$f":"'K90 - time schedule'!CU35","v":0},{"$f":"'K90 - time schedule'!CV35","v":0},{"$f":"'K90 - time schedule'!CW35","v":0},{"$f":"'K90 - time schedule'!CX35","v":0},{"$f":"'K90 - time schedule'!CY35","v":0},{"$f":"'K90 - time schedule'!CZ35","v":0},{"$f":"'K90 - time schedule'!DA35","v":0},{"$f":"'K90 - time schedule'!DB35","v":0},{"$f":"'K90 - time schedule'!DC35","v":0},{"$f":"'K90 - time schedule'!DD35","v":0},{"$f":"'K90 - time schedule'!DE35","v":0},{"$f":"'K90 - time schedule'!DF35","v":0},{"$f":"'K90 - time schedule'!DG35","v":0},{"$f":"'K90 - time schedule'!DH35","v":0},{"$f":"'K90 - time schedule'!DI35","v":0},{"$f":"'K90 - time schedule'!DJ35","v":0},{"$f":"'K90 - time schedule'!DK35","v":0},{"$f":"'K90 - time schedule'!DL35","v":0},{"$f":"'K90 - time schedule'!DM35","v":0},{"$f":"'K90 - time schedule'!DN35","v":0},{"$f":"'K90 - time schedule'!DO35","v":0},{"$f":"'K90 - time schedule'!DP35","v":0},{"$f":"'K90 - time schedule'!DQ35","v":0},{"$f":"'K90 - time schedule'!DR35","v":0},{"$f":"'K90 - time schedule'!DS35","v":0},{"$f":"'K90 - time schedule'!DT35","v":0},{"$f":"'K90 - time schedule'!DU35","v":0},{"$f":"'K90 - time schedule'!DV35","v":0},{"$f":"'K90 - time schedule'!DW35","v":0},{"$f":"'K90 - time schedule'!DX35","v":0},{"$f":"'K90 - time schedule'!DY35","v":0},{"$f":"'K90 - time schedule'!DZ35","v":0},{"$f":"'K90 - time schedule'!EA35","v":0},{"$f":"'K90 - time schedule'!EB35","v":0},{"$f":"'K90 - time schedule'!EC35","v":0},{"$f":"'K90 - time schedule'!ED35","v":0},{"$f":"'K90 - time schedule'!EE35","v":0},{"$f":"'K90 - time schedule'!EF35","v":0},{"$f":"'K90 - time schedule'!EG35","v":0},{"$f":"'K90 - time schedule'!EH35","v":0},{"$f":"'K90 - time schedule'!EI35","v":0},{"$f":"'K90 - time schedule'!EJ35","v":0},{"$f":"'K90 - time schedule'!EK35","v":0},{"$f":"'K90 - time schedule'!EL35","v":0},{"$f":"'K90 - time schedule'!EM35","v":0},{"$f":"'K90 - time schedule'!EN35","v":0},{"$f":"'K90 - time schedule'!EO35","v":0},{"$f":"'K90 - time schedule'!EP35","v":0},{"$f":"'K90 - time schedule'!EQ35","v":0},{"$f":"'K90 - time schedule'!ER35","v":0},{"$f":"'K90 - time schedule'!ES35","v":0},{"$f":"'K90 - time schedule'!ET35","v":0},{"$f":"'K90 - time schedule'!EU35","v":0},{"$f":"'K90 - time schedule'!EV35","v":0},{"$f":"'K90 - time schedule'!EW35","v":0},{"$f":"'K90 - time schedule'!EX35","v":0},{"$f":"'K90 - time schedule'!EY35","v":0},{"$f":"'K90 - time schedule'!EZ35","v":0},{"$f":"'K90 - time schedule'!FA35","v":0},{"$f":"'K90 - time schedule'!FB35","v":0},{"$f":"'K90 - time schedule'!FC35","v":0},{"$f":"'K90 - time schedule'!FD35","v":0},{"$f":"'K90 - time schedule'!FE35","v":0},{"$f":"'K90 - time schedule'!FF35","v":0},{"$f":"'K90 - time schedule'!FG35","v":0},{"$f":"'K90 - time schedule'!FH35","v":0},{"$f":"'K90 - time schedule'!FI35","v":0},{"$f":"'K90 - time schedule'!FJ35","v":0},{"$f":"'K90 - time schedule'!FK35","v":0},{"$f":"'K90 - time schedule'!FL35","v":0},{"$f":"'K90 - time schedule'!FM35","v":0},{"$f":"'K90 - time schedule'!FN35","v":0},{"$f":"'K90 - time schedule'!FO35","v":0},{"$f":"'K90 - time schedule'!FP35","v":0},{"$f":"'K90 - time schedule'!FQ35","v":0},{"$f":"'K90 - time schedule'!FR35","v":0},{"$f":"'K90 - time schedule'!FS35","v":0},{"$f":"'K90 - time schedule'!FT35","v":0},{"$f":"'K90 - time schedule'!FU35","v":0},{"$f":"'K90 - time schedule'!FV35","v":0},{"$f":"'K90 - time schedule'!FW35","v":0},{"$f":"'K90 - time schedule'!FX35","v":0},{"$f":"'K90 - time schedule'!FY35","v":0},{"$f":"'K90 - time schedule'!FZ35","v":0},{"$f":"'K90 - time schedule'!GA35","v":0},{"$f":"'K90 - time schedule'!GB35","v":0},{"$f":"'K90 - time schedule'!GC35","v":0},{"$f":"'K90 - time schedule'!GD35","v":0},{"$f":"'K90 - time schedule'!GE35","v":0},{"$f":"'K90 - time schedule'!GF35","v":0},{"$f":"'K20 - time schedule'!GG72","v":0},{"$f":"'K20 - time schedule'!GH72","v":0},{"$f":"'K20 - time schedule'!GI72","v":0},{"$f":"'K20 - time schedule'!GJ72","v":0},{"$f":"'K20 - time schedule'!GK72","v":0},{"$f":"'K20 - time schedule'!GL72","v":0},{"$f":"'K20 - time schedule'!GM72","v":0},{"$f":"'K20 - time schedule'!GN72","v":0},{"$f":"'K20 - time schedule'!GO72","v":0},{"$f":"'K20 - time schedule'!GP72","v":0},{"$f":"'K20 - time schedule'!GQ72","v":0},{"$f":"'K20 - time schedule'!GR72","v":0},{"$f":"'K20 - time schedule'!GS72","v":0},{"$f":"'K20 - time schedule'!GT72","v":0},{"$f":"'K20 - time schedule'!GU72","v":0},{"$f":"'K20 - time schedule'!GV72","v":0},{"$f":"'K20 - time schedule'!GW72","v":0},{"$f":"'K20 - time schedule'!GX72","v":0},{"$f":"'K20 - time schedule'!GY72","v":0},{"$f":"'K20 - time schedule'!GZ72","v":0},{"$f":"'K20 - time schedule'!HA72","v":0},{"$f":"'K20 - time schedule'!HB72","v":0},{"$f":"'K20 - time schedule'!HC72","v":0},{"$f":"'K20 - time schedule'!HD72","v":0},{"$f":"'K20 - time schedule'!HE72","v":0},{"$f":"'K20 - time schedule'!HF72","v":0},{"$f":"'K20 - time schedule'!HG72","v":0},{"$f":"'K20 - time schedule'!HH72","v":0},{"$f":"'K20 - time schedule'!HI72","v":0},{"$f":"'K20 - time schedule'!HJ72","v":0},{"$f":"'K20 - time schedule'!HK72","v":0},{"$f":"'K20 - time schedule'!HL72","v":0},{"$f":"'K20 - time schedule'!HM72","v":0},{"$f":"'K20 - time schedule'!HN72","v":0},{"$f":"'K20 - time schedule'!HO72","v":0},{"$f":"'K20 - time schedule'!HP72","v":0},{"$f":"'K20 - time schedule'!HQ72","v":0},{"$f":"'K20 - time schedule'!HR72","v":0},{"$f":"'K20 - time schedule'!HS72","v":0},{"$f":"'K20 - time schedule'!HT72","v":0},{"$f":"'K20 - time schedule'!HU72","v":0},{"$f":"'K20 - time schedule'!HV72","v":0},{"$f":"'K20 - time schedule'!HW72","v":0},{"$f":"'K20 - time schedule'!HX72","v":0},{"$f":"'K20 - time schedule'!HY72","v":0},{"$f":"'K20 - time schedule'!HZ72","v":0},{"$f":"'K20 - time schedule'!IA72","v":0},{"$f":"'K20 - time schedule'!IB72","v":0},{"$f":"'K20 - time schedule'!IC72","v":0},{"$f":"'K20 - time schedule'!ID72","v":0},{"$f":"'K20 - time schedule'!IE72","v":0},{"$f":"'K20 - time schedule'!IF72","v":0},{"$f":"'K20 - time schedule'!IG72","v":0},{"$f":"'K20 - time schedule'!IH72","v":0},{"$f":"'K20 - time schedule'!II72","v":0},{"$f":"'K20 - time schedule'!IJ72","v":0},{"$f":"'K20 - time schedule'!IK72","v":0},{"$f":"'K20 - time schedule'!IL72","v":0},{"$f":"'K20 - time schedule'!IM72","v":0},{"$f":"'K20 - time schedule'!IN72","v":0},{"$f":"'K20 - time schedule'!IO72","v":0},{"$f":"'K20 - time schedule'!IP72","v":0},{"$f":"'K20 - time schedule'!IQ72","v":0},{"$f":"'K20 - time schedule'!IR72","v":0},{"$f":"'K20 - time schedule'!IS72","v":0},{"$f":"'K20 - time schedule'!IT72","v":0},{"$f":"'K20 - time schedule'!IU72","v":0},{"$f":"'K20 - time schedule'!IV72","v":0},{"$f":"'K20 - time schedule'!IW72","v":0},{"$f":"'K20 - time schedule'!IX72","v":0},{"$f":"'K20 - time schedule'!IY72","v":0},{"$f":"'K20 - time schedule'!IZ72","v":0},{"$f":"'K20 - time schedule'!JA72","v":0},{"$f":"'K20 - time schedule'!JB72","v":0},{"$f":"'K20 - time schedule'!JC72","v":0},{"$f":"'K20 - time schedule'!JD72","v":0},{"$f":"'K20 - time schedule'!JE72","v":0},{"$f":"'K20 - time schedule'!JF72","v":0},{"$f":"'K20 - time schedule'!JG72","v":0},{"$f":"'K20 - time schedule'!JH72","v":0},{"$f":"'K20 - time schedule'!JI72","v":0},{"$f":"'K20 - time schedule'!JJ72","v":0},{"$f":"'K20 - time schedule'!JK72","v":0},{"$f":"'K20 - time schedule'!JL72","v":0},{"$f":"'K20 - time schedule'!JM72","v":0},{"$f":"'K20 - time schedule'!JN72","v":0},{"$f":"'K20 - time schedule'!JO72","v":0},{"$f":"'K20 - time schedule'!JP72","v":0},{"$f":"'K20 - time schedule'!JQ72","v":0},{"$f":"'K20 - time schedule'!JR72","v":0},{"$f":"'K20 - time schedule'!JS72","v":0},{"$f":"'K20 - time schedule'!JT72","v":0},{"$f":"'K20 - time schedule'!JU72","v":0},{"$f":"'K20 - time schedule'!JV72","v":0},{"$f":"'K20 - time schedule'!JW72","v":0},{"$f":"'K20 - time schedule'!JX72","v":0},{"$f":"'K20 - time schedule'!JY72","v":0},{"$f":"'K20 - time schedule'!JZ72","v":0},{"$f":"'K20 - time schedule'!KA72","v":0},{"$f":"'K20 - time schedule'!KB72","v":0},{"$f":"'K20 - time schedule'!KC72","v":0},{"$f":"'K20 - time schedule'!KD72","v":0},{"$f":"'K20 - time schedule'!KE72","v":0},{"$f":"'K20 - time schedule'!KF72","v":0},{"$f":"'K20 - time schedule'!KG72","v":0},{"$f":"'K20 - time schedule'!KH72","v":0},{"$f":"'K20 - time schedule'!KI72","v":0},{"$f":"'K20 - time schedule'!KJ72","v":0},{"$f":"'K20 - time schedule'!KK72","v":0},{"$f":"'K20 - time schedule'!KL72","v":0},{"$f":"'K20 - time schedule'!KM72","v":0},{"$f":"'K20 - time schedule'!KN72","v":0},{"$f":"'K20 - time schedule'!KO72","v":0},{"$f":"'K20 - time schedule'!KP72","v":0},{"$f":"'K20 - time schedule'!KQ72","v":0},{"$f":"'K20 - time schedule'!KR72","v":0},{"$f":"'K20 - time schedule'!KS72","v":0},{"$f":"'K20 - time schedule'!KT72","v":0}]
["Boiler room K90 - flue lines, including fabric filter","K90","EUR",{"$f":"'K90 - time schedule'!G37","v":0},{"$f":"'K90 - time schedule'!H37","v":0},{"$f":"'K90 - time schedule'!I37","v":0},{"$f":"'K90 - time schedule'!J37","v":0},{"$f":"'K90 - time schedule'!K37","v":0},{"$f":"'K90 - time schedule'!L37","v":0},{"$f":"'K90 - time schedule'!M37","v":0},{"$f":"'K90 - time schedule'!N37","v":0},{"$f":"'K90 - time schedule'!O37","v":0},{"$f":"'K90 - time schedule'!P37","v":0},{"$f":"'K90 - time schedule'!Q37","v":0},{"$f":"'K90 - time schedule'!R37","v":0},{"$f":"'K90 - time schedule'!S37","v":0},{"$f":"'K90 - time schedule'!T37","v":0},{"$f":"'K90 - time schedule'!U37","v":0},{"$f":"'K90 - time schedule'!V37","v":0},{"$f":"'K90 - time schedule'!W37","v":0},{"$f":"'K90 - time schedule'!X37","v":0},{"$f":"'K90 - time schedule'!Y37","v":0},{"$f":"'K90 - time schedule'!Z37","v":0},{"$f":"'K90 - time schedule'!AA37","v":0},{"$f":"'K90 - time schedule'!AB37","v":0},{"$f":"'K90 - time schedule'!AC37","v":0},{"$f":"'K90 - time schedule'!AD37","v":0},{"$f":"'K90 - time schedule'!AE37","v":0},{"$f":"'K90 - time schedule'!AF37","v":0},{"$f":"'K90 - time schedule'!AG37","v":0},{"$f":"'K90 - time schedule'!AH37","v":0},{"$f":"'K90 - time schedule'!AI37","v":0},{"$f":"'K90 - time schedule'!AJ37","v":0},{"$f":"'K90 - time schedule'!AK37","v":0},{"$f":"'K90 - time schedule'!AL37","v":0},{"$f":"'K90 - time schedule'!AM37","v":0},{"$f":"'K90 - time schedule'!AN37","v":0},{"$f":"'K90 - time schedule'!AO37","v":0},{"$f":"'K90 - time schedule'!AP37","v":0},{"$f":"'K90 - time schedule'!AQ37","v":0},{"$f":"'K90 - time schedule'!AR37","v":0},{"$f":"'K90 - time schedule'!AS37","v":0},{"$f":"'K90 - time schedule'!AT37","v":0},{"$f":"'K90 - time schedule'!AU37","v":0},{"$f":"'K90 - time schedule'!AV37","v":0},{"$f":"'K90 - time schedule'!AW37","v":0},{"$f":"'K90 - time schedule'!AX37","v":0},{"$f":"'K90 - time schedule'!AY37","v":0},{"$f":"'K90 - time schedule'!AZ37","v":0},{"$f":"'K90 - time schedule'!BA37","v":0},{"$f":"'K90 - time schedule'!BB37","v":0},{"$f":"'K90 - time schedule'!BC37","v":0},{"$f":"'K90 - time schedule'!BD37","v":0},{"$f":"'K90 - time schedule'!BE37","v":0},{"$f":"'K90 - time schedule'!BF37","v":0},{"$f":"'K90 - time schedule'!BG37","v":0},{"$f":"'K90 - time schedule'!BH37","v":0},{"$f":"'K90 - time schedule'!BI37","v":0},{"$f":"'K90 - time schedule'!BJ37","v":0},{"$f":"'K90 - time schedule'!BK37","v":0},{"$f":"'K90 - time schedule'!BL37","v":0},{"$f":"'K90 - time schedule'!BM37","v":0},{"$f":"'K90 - time schedule'!BN37","v":0},{"$f":"'K90 - time schedule'!BO37","v":0},{"$f":"'K90 - time schedule'!BP37","v":0},{"$f":"'K90 - time schedule'!BQ37","v":0},{"$f":"'K90 - time schedule'!BR37","v":0},{"$f":"'K90 - time schedule'!BS37","v":0},{"$f":"'K90 - time schedule'!BT37","v":0},{"$f":"'K90 - time schedule'!BU37","v":0},{"$f":"'K90 - time schedule'!BV37","v":0},{"$f":"'K90 - time schedule'!BW37","v":0},{"$f":"'K90 - time schedule'!BX37","v":0},{"$f":"'K90 - time schedule'!BY37","v":0},{"$f":"'K90 - time schedule'!BZ37","v":0},{"$f":"'K90 - time schedule'!CA37","v":0},{"$f":"'K90 - time schedule'!CB37","v":0},{"$f":"'K90 - time schedule'!CC37","v":0},{"$f":"'K90 - time schedule'!CD37","v":0},{"$f":"'K90 - time schedule'!CE37","v":0},{"$f":"'K90 - time schedule'!CF37","v":0},{"$f":"'K90 - time schedule'!CG37","v":0},{"$f":"'K90 - time schedule'!CH37","v":0},{"$f":"'K90 - time schedule'!CI37","v":0},{"$f":"'K90 - time schedule'!CJ37","v":0},{"$f":"'K90 - time schedule'!CK37","v":0},{"$f":"'K90 - time schedule'!CL37","v":0},{"$f":"'K90 - time schedule'!CM37","v":0},{"$f":"'K90 - time schedule'!CN37","v":0},{"$f":"'K90 - time schedule'!CO37","v":0},{"$f":"'K90 - time schedule'!CP37","v":0},{"$f":"'K90 - time schedule'!CQ37","v":0},{"$f":"'K90 - time schedule'!CR37","v":0},{"$f":"'K90 - time schedule'!CS37","v":0},{"$f":"'K90 - time schedule'!CT37","v":0},{"$f":"'K90 - time schedule'!CU37","v":0},{"$f":"'K90 - time schedule'!CV37","v":0},{"$f":"'K90 - time schedule'!CW37","v":0},{"$f":"'K90 - time schedule'!CX37","v":0},{"$f":"'K90 - time schedule'!CY37","v":0},{"$f":"'K90 - time schedule'!CZ37","v":0},{"$f":"'K90 - time schedule'!DA37","v":0},{"$f":"'K90 - time schedule'!DB37","v":0},{"$f":"'K90 - time schedule'!DC37","v":0},{"$f":"'K90 - time schedule'!DD37","v":0},{"$f":"'K90 - time schedule'!DE37","v":0},{"$f":"'K90 - time schedule'!DF37","v":0},{"$f":"'K90 - time schedule'!DG37","v":0},{"$f":"'K90 - time schedule'!DH37","v":0},{"$f":"'K90 - time schedule'!DI37","v":0},{"$f":"'K90 - time schedule'!DJ37","v":0},{"$f":"'K90 - time schedule'!DK37","v":0},{"$f":"'K90 - time schedule'!DL37","v":0},{"$f":"'K90 - time schedule'!DM37","v":0},{"$f":"'K90 - time schedule'!DN37","v":0},{"$f":"'K90 - time schedule'!DO37","v":0},{"$f":"'K90 - time schedule'!DP37","v":0},{"$f":"'K90 - time schedule'!DQ37","v":0},{"$f":"'K90 - time schedule'!DR37","v":0},{"$f":"'K90 - time schedule'!DS37","v":0},{"$f":"'K90 - time schedule'!DT37","v":0},{"$f":"'K90 - time schedule'!DU37","v":0},{"$f":"'K90 - time schedule'!DV37","v":0},{"$f":"'K90 - time schedule'!DW37","v":0},{"$f":"'K90 - time schedule'!DX37","v":0},{"$f":"'K90 - time schedule'!DY37","v":0},{"$f":"'K90 - time schedule'!DZ37","v":0},{"$f":"'K90 - time schedule'!EA37","v":0},{"$f":"'K90 - time schedule'!EB37","v":0},{"$f":"'K90 - time schedule'!EC37","v":0},{"$f":"'K90 - time schedule'!ED37","v":0},{"$f":"'K90 - time schedule'!EE37","v":0},{"$f":"'K90 - time schedule'!EF37","v":0},{"$f":"'K90 - time schedule'!EG37","v":0},{"$f":"'K90 - time schedule'!EH37","v":0},{"$f":"'K90 - time schedule'!EI37","v":0},{"$f":"'K90 - time schedule'!EJ37","v":0},{"$f":"'K90 - time schedule'!EK37","v":0},{"$f":"'K90 - time schedule'!EL37","v":0},{"$f":"'K90 - time schedule'!EM37","v":0},{"$f":"'K90 - time schedule'!EN37","v":0},{"$f":"'K90 - time schedule'!EO37","v":0},{"$f":"'K90 - time schedule'!EP37","v":0},{"$f":"'K90 - time schedule'!EQ37","v":0},{"$f":"'K90 - time schedule'!ER37","v":0},{"$f":"'K90 - time schedule'!ES37","v":0},{"$f":"'K90 - time schedule'!ET37","v":0},{"$f":"'K90 - time schedule'!EU37","v":0},{"$f":"'K90 - time schedule'!EV37","v":0},{"$f":"'K90 - time schedule'!EW37","v":0},{"$f":"'K90 - time schedule'!EX37","v":0},{"$f":"'K90 - time schedule'!EY37","v":0},{"$f":"'K90 - time schedule'!EZ37","v":0},{"$f":"'K90 - time schedule'!FA37","v":0},{"$f":"'K90 - time schedule'!FB37","v":0},{"$f":"'K90 - time schedule'!FC37","v":0},{"$f":"'K90 - time schedule'!FD37","v":0},{"$f":"'K90 - time schedule'!FE37","v":0},{"$f":"'K90 - time schedule'!FF37","v":0},{"$f":"'K90 - time schedule'!FG37","v":0},{"$f":"'K90 - time schedule'!FH37","v":0},{"$f":"'K90 - time schedule'!FI37","v":0},{"$f":"'K90 - time schedule'!FJ37","v":0},{"$f":"'K90 - time schedule'!FK37","v":0},{"$f":"'K90 - time schedule'!FL37","v":0},{"$f":"'K90 - time schedule'!FM37","v":0},{"$f":"'K90 - time schedule'!FN37","v":0},{"$f":"'K90 - time schedule'!FO37","v":0},{"$f":"'K90 - time schedule'!FP37","v":0},{"$f":"'K90 - time schedule'!FQ37","v":0},{"$f":"'K90 - time schedule'!FR37","v":0},{"$f":"'K90 - time schedule'!FS37","v":0},{"$f":"'K90 - time schedule'!FT37","v":0},{"$f":"'K90 - time schedule'!FU37","v":0},{"$f":"'K90 - time schedule'!FV37","v":0},{"$f":"'K90 - time schedule'!FW37","v":0},{"$f":"'K90 - time schedule'!FX37","v":0},{"$f":"'K90 - time schedule'!FY37","v":0},{"$f":"'K90 - time schedule'!FZ37","v":0},{"$f":"'K90 - time schedule'!GA37","v":0},{"$f":"'K90 - time schedule'!GB37","v":0},{"$f":"'K90 - time schedule'!GC37","v":0},{"$f":"'K90 - time schedule'!GD37","v":0},{"$f":"'K90 - time schedule'!GE37","v":0},{"$f":"'K90 - time schedule'!GF37","v":0},{"$f":"'K20 - time schedule'!GG73","v":0},{"$f":"'K20 - time schedule'!GH73","v":0},{"$f":"'K20 - time schedule'!GI73","v":0},{"$f":"'K20 - time schedule'!GJ73","v":0},{"$f":"'K20 - time schedule'!GK73","v":0},{"$f":"'K20 - time schedule'!GL73","v":0},{"$f":"'K20 - time schedule'!GM73","v":0},{"$f":"'K20 - time schedule'!GN73","v":0},{"$f":"'K20 - time schedule'!GO73","v":0},{"$f":"'K20 - time schedule'!GP73","v":0},{"$f":"'K20 - time schedule'!GQ73","v":0},{"$f":"'K20 - time schedule'!GR73","v":0},{"$f":"'K20 - time schedule'!GS73","v":0},{"$f":"'K20 - time schedule'!GT73","v":0},{"$f":"'K20 - time schedule'!GU73","v":0},{"$f":"'K20 - time schedule'!GV73","v":0},{"$f":"'K20 - time schedule'!GW73","v":0},{"$f":"'K20 - time schedule'!GX73","v":0},{"$f":"'K20 - time schedule'!GY73","v":0},{"$f":"'K20 - time schedule'!GZ73","v":0},{"$f":"'K20 - time schedule'!HA73","v":0},{"$f":"'K20 - time schedule'!HB73","v":0},{"$f":"'K20 - time schedule'!HC73","v":0},{"$f":"'K20 - time schedule'!HD73","v":0},{"$f":"'K20 - time schedule'!HE73","v":0},{"$f":"'K20 - time schedule'!HF73","v":0},{"$f":"'K20 - time schedule'!HG73","v":0},{"$f":"'K20 - time schedule'!HH73","v":0},{"$f":"'K20 - time schedule'!HI73","v":0},{"$f":"'K20 - time schedule'!HJ73","v":0},{"$f":"'K20 - time schedule'!HK73","v":0},{"$f":"'K20 - time schedule'!HL73","v":0},{"$f":"'K20 - time schedule'!HM73","v":0},{"$f":"'K20 - time schedule'!HN73","v":0},{"$f":"'K20 - time schedule'!HO73","v":0},{"$f":"'K20 - time schedule'!HP73","v":0},{"$f":"'K20 - time schedule'!HQ73","v":0},{"$f":"'K20 - time schedule'!HR73","v":0},{"$f":"'K20 - time schedule'!HS73","v":0},{"$f":"'K20 - time schedule'!HT73","v":0},{"$f":"'K20 - time schedule'!HU73","v":0},{"$f":"'K20 - time schedule'!HV73","v":0},{"$f":"'K20 - time schedule'!HW73","v":0},{"$f":"'K20 - time schedule'!HX73","v":0},{"$f":"'K20 - time schedule'!HY73","v":0},{"$f":"'K20 - time schedule'!HZ73","v":0},{"$f":"'K20 - time schedule'!IA73","v":0},{"$f":"'K20 - time schedule'!IB73","v":0},{"$f":"'K20 - time schedule'!IC73","v":0},{"$f":"'K20 - time schedule'!ID73","v":0},{"$f":"'K20 - time schedule'!IE73","v":0},{"$f":"'K20 - time schedule'!IF73","v":0},{"$f":"'K20 - time schedule'!IG73","v":0},{"$f":"'K20 - time schedule'!IH73","v":0},{"$f":"'K20 - time schedule'!II73","v":0},{"$f":"'K20 - time schedule'!IJ73","v":0},{"$f":"'K20 - time schedule'!IK73","v":0},{"$f":"'K20 - time schedule'!IL73","v":0},{"$f":"'K20 - time schedule'!IM73","v":0},{"$f":"'K20 - time schedule'!IN73","v":0},{"$f":"'K20 - time schedule'!IO73","v":0},{"$f":"'K20 - time schedule'!IP73","v":0},{"$f":"'K20 - time schedule'!IQ73","v":0},{"$f":"'K20 - time schedule'!IR73","v":0},{"$f":"'K20 - time schedule'!IS73","v":0},{"$f":"'K20 - time schedule'!IT73","v":0},{"$f":"'K20 - time schedule'!IU73","v":0},{"$f":"'K20 - time schedule'!IV73","v":0},{"$f":"'K20 - time schedule'!IW73","v":0},{"$f":"'K20 - time schedule'!IX73","v":0},{"$f":"'K20 - time schedule'!IY73","v":0},{"$f":"'K20 - time schedule'!IZ73","v":0},{"$f":"'K20 - time schedule'!JA73","v":0},{"$f":"'K20 - time schedule'!JB73","v":0},{"$f":"'K20 - time schedule'!JC73","v":0},{"$f":"'K20 - time schedule'!JD73","v":0},{"$f":"'K20 - time schedule'!JE73","v":0},{"$f":"'K20 - time schedule'!JF73","v":0},{"$f":"'K20 - time schedule'!JG73","v":0},{"$f":"'K20 - time schedule'!JH73","v":0},{"$f":"'K20 - time schedule'!JI73","v":0},{"$f":"'K20 - time schedule'!JJ73","v":0},{"$f":"'K20 - time schedule'!JK73","v":0},{"$f":"'K20 - time schedule'!JL73","v":0},{"$f":"'K20 - time schedule'!JM73","v":0},{"$f":"'K20 - time schedule'!JN73","v":0},{"$f":"'K20 - time schedule'!JO73","v":0},{"$f":"'K20 - time schedule'!JP73","v":0},{"$f":"'K20 - time schedule'!JQ73","v":0},{"$f":"'K20 - time schedule'!JR73","v":0},{"$f":"'K20 - time schedule'!JS73","v":0},{"$f":"'K20 - time schedule'!JT73","v":0},{"$f":"'K20 - time schedule'!JU73","v":0},{"$f":"'K20 - time schedule'!JV73","v":0},{"$f":"'K20 - time schedule'!JW73","v":0},{"$f":"'K20 - time schedule'!JX73","v":0},{"$f":"'K20 - time schedule'!JY73","v":0},{"$f":"'K20 - time schedule'!JZ73","v":0},{"$f":"'K20 - time schedule'!KA73","v":0},{"$f":"'K20 - time schedule'!KB73","v":0},{"$f":"'K20 - time schedule'!KC73","v":0},{"$f":"'K20 - time schedule'!KD73","v":0},{"$f":"'K20 - time schedule'!KE73","v":0},{"$f":"'K20 - time schedule'!KF73","v":0},{"$f":"'K20 - time schedule'!KG73","v":0},{"$f":"'K20 - time schedule'!KH73","v":0},{"$f":"'K20 - time schedule'!KI73","v":0},{"$f":"'K20 - time schedule'!KJ73","v":0},{"$f":"'K20 - time schedule'!KK73","v":0},{"$f":"'K20 - time schedule'!KL73","v":0},{"$f":"'K20 - time schedule'!KM73","v":0},{"$f":"'K20 - time schedule'!KN73","v":0},{"$f":"'K20 - time schedule'!KO73","v":0},{"$f":"'K20 - time schedule'!KP73","v":0},{"$f":"'K20 - time schedule'!KQ73","v":0},{"$f":"'K20 - time schedule'!KR73","v":0},{"$f":"'K20 - time schedule'!KS73","v":0},{"$f":"'K20 - time schedule'!KT73","v":0}]
["Boiler room K90 - electrical installation","K90","EUR",{"$f":"'K90 - time schedule'!G39","v":0},{"$f":"'K90 - time schedule'!H39","v":0},{"$f":"'K90 - time schedule'!I39","v":0},{"$f":"'K90 - time schedule'!J39","v":0},{"$f":"'K90 - time schedule'!K39","v":0},{"$f":"'K90 - time schedule'!L39","v":0},{"$f":"'K90 - time schedule'!M39","v":0},{"$f":"'K90 - time schedule'!N39","v":0},{"$f":"'K90 - time schedule'!O39","v":0},{"$f":"'K90 - time schedule'!P39","v":0},{"$f":"'K90 - time schedule'!Q39","v":0},{"$f":"'K90 - time schedule'!R39","v":0},{"$f":"'K90 - time schedule'!S39","v":0},{"$f":"'K90 - time schedule'!T39","v":0},{"$f":"'K90 - time schedule'!U39","v":0},{"$f":"'K90 - time schedule'!V39","v":0},{"$f":"'K90 - time schedule'!W39","v":0},{"$f":"'K90 - time schedule'!X39","v":0},{"$f":"'K90 - time schedule'!Y39","v":0},{"$f":"'K90 - time schedule'!Z39","v":0},{"$f":"'K90 - time schedule'!AA39","v":0},{"$f":"'K90 - time schedule'!AB39","v":0},{"$f":"'K90 - time schedule'!AC39","v":0},{"$f":"'K90 - time schedule'!AD39","v":0},{"$f":"'K90 - time schedule'!AE39","v":0},{"$f":"'K90 - time schedule'!AF39","v":0},{"$f":"'K90 - time schedule'!AG39","v":0},{"$f":"'K90 - time schedule'!AH39","v":0},{"$f":"'K90 - time schedule'!AI39","v":0},{"$f":"'K90 - time schedule'!AJ39","v":0},{"$f":"'K90 - time schedule'!AK39","v":0},{"$f":"'K90 - time schedule'!AL39","v":0},{"$f":"'K90 - time schedule'!AM39","v":0},{"$f":"'K90 - time schedule'!AN39","v":0},{"$f":"'K90 - time schedule'!AO39","v":0},{"$f":"'K90 - time schedule'!AP39","v":0},{"$f":"'K90 - time schedule'!AQ39","v":0},{"$f":"'K90 - time schedule'!AR39","v":0},{"$f":"'K90 - time schedule'!AS39","v":0},{"$f":"'K90 - time schedule'!AT39","v":0},{"$f":"'K90 - time schedule'!AU39","v":0},{"$f":"'K90 - time schedule'!AV39","v":0},{"$f":"'K90 - time schedule'!AW39","v":0},{"$f":"'K90 - time schedule'!AX39","v":0},{"$f":"'K90 - time schedule'!AY39","v":0},{"$f":"'K90 - time schedule'!AZ39","v":0},{"$f":"'K90 - time schedule'!BA39","v":0},{"$f":"'K90 - time schedule'!BB39","v":0},{"$f":"'K90 - time schedule'!BC39","v":0},{"$f":"'K90 - time schedule'!BD39","v":0},{"$f":"'K90 - time schedule'!BE39","v":0},{"$f":"'K90 - time schedule'!BF39","v":0},{"$f":"'K90 - time schedule'!BG39","v":0},{"$f":"'K90 - time schedule'!BH39","v":0},{"$f":"'K90 - time schedule'!BI39","v":0},{"$f":"'K90 - time schedule'!BJ39","v":0},{"$f":"'K90 - time schedule'!BK39","v":0},{"$f":"'K90 - time schedule'!BL39","v":0},{"$f":"'K90 - time schedule'!BM39","v":0},{"$f":"'K90 - time schedule'!BN39","v":0},{"$f":"'K90 - time schedule'!BO39","v":0},{"$f":"'K90 - time schedule'!BP39","v":0},{"$f":"'K90 - time schedule'!BQ39","v":0},{"$f":"'K90 - time schedule'!BR39","v":0},{"$f":"'K90 - time schedule'!BS39","v":0},{"$f":"'K90 - time schedule'!BT39","v":0},{"$f":"'K90 - time schedule'!BU39","v":0},{"$f":"'K90 - time schedule'!BV39","v":0},{"$f":"'K90 - time schedule'!BW39","v":0},{"$f":"'K90 - time schedule'!BX39","v":0},{"$f":"'K90 - time schedule'!BY39","v":0},{"$f":"'K90 - time schedule'!BZ39","v":0},{"$f":"'K90 - time schedule'!CA39","v":0},{"$f":"'K90 - time schedule'!CB39","v":0},{"$f":"'K90 - time schedule'!CC39","v":0},{"$f":"'K90 - time schedule'!CD39","v":0},{"$f":"'K90 - time schedule'!CE39","v":0},{"$f":"'K90 - time schedule'!CF39","v":0},{"$f":"'K90 - time schedule'!CG39","v":0},{"$f":"'K90 - time schedule'!CH39","v":0},{"$f":"'K90 - time schedule'!CI39","v":0},{"$f":"'K90 - time schedule'!CJ39","v":0},{"$f":"'K90 - time schedule'!CK39","v":0},{"$f":"'K90 - time schedule'!CL39","v":0},{"$f":"'K90 - time schedule'!CM39","v":0},{"$f":"'K90 - time schedule'!CN39","v":0},{"$f":"'K90 - time schedule'!CO39","v":0},{"$f":"'K90 - time schedule'!CP39","v":0},{"$f":"'K90 - time schedule'!CQ39","v":0},{"$f":"'K90 - time schedule'!CR39","v":0},{"$f":"'K90 - time schedule'!CS39","v":0},{"$f":"'K90 - time schedule'!CT39","v":0},{"$f":"'K90 - time schedule'!CU39","v":0},{"$f":"'K90 - time schedule'!CV39","v":0},{"$f":"'K90 - time schedule'!CW39","v":0},{"$f":"'K90 - time schedule'!CX39","v":0},{"$f":"'K90 - time schedule'!CY39","v":0},{"$f":"'K90 - time schedule'!CZ39","v":0},{"$f":"'K90 - time schedule'!DA39","v":0},{"$f":"'K90 - time schedule'!DB39","v":0},{"$f":"'K90 - time schedule'!DC39","v":0},{"$f":"'K90 - time schedule'!DD39","v":0},{"$f":"'K90 - time schedule'!DE39","v":0},{"$f":"'K90 - time schedule'!DF39","v":0},{"$f":"'K90 - time schedule'!DG39","v":0},{"$f":"'K90 - time schedule'!DH39","v":0},{"$f":"'K90 - time schedule'!DI39","v":0},{"$f":"'K90 - time schedule'!DJ39","v":0},{"$f":"'K90 - time schedule'!DK39","v":0},{"$f":"'K90 - time schedule'!DL39","v":0},{"$f":"'K90 - time schedule'!DM39","v":0},{"$f":"'K90 - time schedule'!DN39","v":0},{"$f":"'K90 - time schedule'!DO39","v":0},{"$f":"'K90 - time schedule'!DP39","v":0},{"$f":"'K90 - time schedule'!DQ39","v":0},{"$f":"'K90 - time schedule'!DR39","v":0},{"$f":"'K90 - time schedule'!DS39","v":0},{"$f":"'K90 - time schedule'!DT39","v":0},{"$f":"'K90 - time schedule'!DU39","v":0},{"$f":"'K90 - time schedule'!DV39","v":0},{"$f":"'K90 - time schedule'!DW39","v":0},{"$f":"'K90 - time schedule'!DX39","v":0},{"$f":"'K90 - time schedule'!DY39","v":0},{"$f":"'K90 - time schedule'!DZ39","v":0},{"$f":"'K90 - time schedule'!EA39","v":0},{"$f":"'K90 - time schedule'!EB39","v":0},{"$f":"'K90 - time schedule'!EC39","v":0},{"$f":"'K90 - time schedule'!ED39","v":0},{"$f":"'K90 - time schedule'!EE39","v":0},{"$f":"'K90 - time schedule'!EF39","v":0},{"$f":"'K90 - time schedule'!EG39","v":0},{"$f":"'K90 - time schedule'!EH39","v":0},{"$f":"'K90 - time schedule'!EI39","v":0},{"$f":"'K90 - time schedule'!EJ39","v":0},{"$f":"'K90 - time schedule'!EK39","v":0},{"$f":"'K90 - time schedule'!EL39","v":0},{"$f":"'K90 - time schedule'!EM39","v":0},{"$f":"'K90 - time schedule'!EN39","v":0},{"$f":"'K90 - time schedule'!EO39","v":0},{"$f":"'K90 - time schedule'!EP39","v":0},{"$f":"'K90 - time schedule'!EQ39","v":0},{"$f":"'K90 - time schedule'!ER39","v":0},{"$f":"'K90 - time schedule'!ES39","v":0},{"$f":"'K90 - time schedule'!ET39","v":0},{"$f":"'K90 - time schedule'!EU39","v":0},{"$f":"'K90 - time schedule'!EV39","v":0},{"$f":"'K90 - time schedule'!EW39","v":0},{"$f":"'K90 - time schedule'!EX39","v":0},{"$f":"'K90 - time schedule'!EY39","v":0},{"$f":"'K90 - time schedule'!EZ39","v":0},{"$f":"'K90 - time schedule'!FA39","v":0},{"$f":"'K90 - time schedule'!FB39","v":0},{"$f":"'K90 - time schedule'!FC39","v":0},{"$f":"'K90 - time schedule'!FD39","v":0},{"$f":"'K90 - time schedule'!FE39","v":0},{"$f":"'K90 - time schedule'!FF39","v":0},{"$f":"'K90 - time schedule'!FG39","v":0},{"$f":"'K90 - time schedule'!FH39","v":0},{"$f":"'K90 - time schedule'!FI39","v":0},{"$f":"'K90 - time schedule'!FJ39","v":0},{"$f":"'K90 - time schedule'!FK39","v":0},{"$f":"'K90 - time schedule'!FL39","v":0},{"$f":"'K90 - time schedule'!FM39","v":0},{"$f":"'K90 - time schedule'!FN39","v":0},{"$f":"'K90 - time schedule'!FO39","v":0},{"$f":"'K90 - time schedule'!FP39","v":0},{"$f":"'K90 - time schedule'!FQ39","v":0},{"$f":"'K90 - time schedule'!FR39","v":0},{"$f":"'K90 - time schedule'!FS39","v":0},{"$f":"'K90 - time schedule'!FT39","v":0},{"$f":"'K90 - time schedule'!FU39","v":0},{"$f":"'K90 - time schedule'!FV39","v":0},{"$f":"'K90 - time schedule'!FW39","v":0},{"$f":"'K90 - time schedule'!FX39","v":0},{"$f":"'K90 - time schedule'!FY39","v":0},{"$f":"'K90 - time schedule'!FZ39","v":0},{"$f":"'K90 - time schedule'!GA39","v":0},{"$f":"'K90 - time schedule'!GB39","v":0},{"$f":"'K90 - time schedule'!GC39","v":0},{"$f":"'K90 - time schedule'!GD39","v":0},{"$f":"'K90 - time schedule'!GE39","v":0},{"$f":"'K90 - time schedule'!GF39","v":0},{"$f":"'K20 - time schedule'!GG74","v":0},{"$f":"'K20 - time schedule'!GH74","v":0},{"$f":"'K20 - time schedule'!GI74","v":0},{"$f":"'K20 - time schedule'!GJ74","v":0},{"$f":"'K20 - time schedule'!GK74","v":0},{"$f":"'K20 - time schedule'!GL74","v":0},{"$f":"'K20 - time schedule'!GM74","v":0},{"$f":"'K20 - time schedule'!GN74","v":0},{"$f":"'K20 - time schedule'!GO74","v":0},{"$f":"'K20 - time schedule'!GP74","v":0},{"$f":"'K20 - time schedule'!GQ74","v":0},{"$f":"'K20 - time schedule'!GR74","v":0},{"$f":"'K20 - time schedule'!GS74","v":0},{"$f":"'K20 - time schedule'!GT74","v":0},{"$f":"'K20 - time schedule'!GU74","v":0},{"$f":"'K20 - time schedule'!GV74","v":0},{"$f":"'K20 - time schedule'!GW74","v":0},{"$f":"'K20 - time schedule'!GX74","v":0},{"$f":"'K20 - time schedule'!GY74","v":0},{"$f":"'K20 - time schedule'!GZ74","v":0},{"$f":"'K20 - time schedule'!HA74","v":0},{"$f":"'K20 - time schedule'!HB74","v":0},{"$f":"'K20 - time schedule'!HC74","v":0},{"$f":"'K20 - time schedule'!HD74","v":0},{"$f":"'K20 - time schedule'!HE74","v":0},{"$f":"'K20 - time schedule'!HF74","v":0},{"$f":"'K20 - time schedule'!HG74","v":0},{"$f":"'K20 - time schedule'!HH74","v":0},{"$f":"'K20 - time schedule'!HI74","v":0},{"$f":"'K20 - time schedule'!HJ74","v":0},{"$f":"'K20 - time schedule'!HK74","v":0},{"$f":"'K20 - time schedule'!HL74","v":0},{"$f":"'K20 - time schedule'!HM74","v":0},{"$f":"'K20 - time schedule'!HN74","v":0},{"$f":"'K20 - time schedule'!HO74","v":0},{"$f":"'K20 - time schedule'!HP74","v":0},{"$f":"'K20 - time schedule'!HQ74","v":0},{"$f":"'K20 - time schedule'!HR74","v":0},{"$f":"'K20 - time schedule'!HS74","v":0},{"$f":"'K20 - time schedule'!HT74","v":0},{"$f":"'K20 - time schedule'!HU74","v":0},{"$f":"'K20 - time schedule'!HV74","v":0},{"$f":"'K20 - time schedule'!HW74","v":0},{"$f":"'K20 - time schedule'!HX74","v":0},{"$f":"'K20 - time schedule'!HY74","v":0},{"$f":"'K20 - time schedule'!HZ74","v":0},{"$f":"'K20 - time schedule'!IA74","v":0},{"$f":"'K20 - time schedule'!IB74","v":0},{"$f":"'K20 - time schedule'!IC74","v":0},{"$f":"'K20 - time schedule'!ID74","v":0},{"$f":"'K20 - time schedule'!IE74","v":0},{"$f":"'K20 - time schedule'!IF74","v":0},{"$f":"'K20 - time schedule'!IG74","v":0},{"$f":"'K20 - time schedule'!IH74","v":0},{"$f":"'K20 - time schedule'!II74","v":0},{"$f":"'K20 - time schedule'!IJ74","v":0},{"$f":"'K20 - time schedule'!IK74","v":0},{"$f":"'K20 - time schedule'!IL74","v":0},{"$f":"'K20 - time schedule'!IM74","v":0},{"$f":"'K20 - time schedule'!IN74","v":0},{"$f":"'K20 - time schedule'!IO74","v":0},{"$f":"'K20 - time schedule'!IP74","v":0},{"$f":"'K20 - time schedule'!IQ74","v":0},{"$f":"'K20 - time schedule'!IR74","v":0},{"$f":"'K20 - time schedule'!IS74","v":0},{"$f":"'K20 - time schedule'!IT74","v":0},{"$f":"'K20 - time schedule'!IU74","v":0},{"$f":"'K20 - time schedule'!IV74","v":0},{"$f":"'K20 - time schedule'!IW74","v":0},{"$f":"'K20 - time schedule'!IX74","v":0},{"$f":"'K20 - time schedule'!IY74","v":0},{"$f":"'K20 - time schedule'!IZ74","v":0},{"$f":"'K20 - time schedule'!JA74","v":0},{"$f":"'K20 - time schedule'!JB74","v":0},{"$f":"'K20 - time schedule'!JC74","v":0},{"$f":"'K20 - time schedule'!JD74","v":0},{"$f":"'K20 - time schedule'!JE74","v":0},{"$f":"'K20 - time schedule'!JF74","v":0},{"$f":"'K20 - time schedule'!JG74","v":0},{"$f":"'K20 - time schedule'!JH74","v":0},{"$f":"'K20 - time schedule'!JI74","v":0},{"$f":"'K20 - time schedule'!JJ74","v":0},{"$f":"'K20 - time schedule'!JK74","v":0},{"$f":"'K20 - time schedule'!JL74","v":0},{"$f":"'K20 - time schedule'!JM74","v":0},{"$f":"'K20 - time schedule'!JN74","v":0},{"$f":"'K20 - time schedule'!JO74","v":0},{"$f":"'K20 - time schedule'!JP74","v":0},{"$f":"'K20 - time schedule'!JQ74","v":0},{"$f":"'K20 - time schedule'!JR74","v":0},{"$f":"'K20 - time schedule'!JS74","v":0},{"$f":"'K20 - time schedule'!JT74","v":0},{"$f":"'K20 - time schedule'!JU74","v":0},{"$f":"'K20 - time schedule'!JV74","v":0},{"$f":"'K20 - time schedule'!JW74","v":0},{"$f":"'K20 - time schedule'!JX74","v":0},{"$f":"'K20 - time schedule'!JY74","v":0},{"$f":"'K20 - time schedule'!JZ74","v":0},{"$f":"'K20 - time schedule'!KA74","v":0},{"$f":"'K20 - time schedule'!KB74","v":0},{"$f":"'K20 - time schedule'!KC74","v":0},{"$f":"'K20 - time schedule'!KD74","v":0},{"$f":"'K20 - time schedule'!KE74","v":0},{"$f":"'K20 - time schedule'!KF74","v":0},{"$f":"'K20 - time schedule'!KG74","v":0},{"$f":"'K20 - time schedule'!KH74","v":0},{"$f":"'K20 - time schedule'!KI74","v":0},{"$f":"'K20 - time schedule'!KJ74","v":0},{"$f":"'K20 - time schedule'!KK74","v":0},{"$f":"'K20 - time schedule'!KL74","v":0},{"$f":"'K20 - time schedule'!KM74","v":0},{"$f":"'K20 - time schedule'!KN74","v":0},{"$f":"'K20 - time schedule'!KO74","v":0},{"$f":"'K20 - time schedule'!KP74","v":0},{"$f":"'K20 - time schedule'!KQ74","v":0},{"$f":"'K20 - time schedule'!KR74","v":0},{"$f":"'K20 - time schedule'!KS74","v":0},{"$f":"'K20 - time schedule'!KT74","v":0}]
["Boiler room K90 - management of automatic control system","K90","EUR",{"$f":"'K90 - time schedule'!G41","v":0},{"$f":"'K90 - time schedule'!H41","v":0},{"$f":"'K90 - time schedule'!I41","v":0},{"$f":"'K90 - time schedule'!J41","v":0},{"$f":"'K90 - time schedule'!K41","v":0},{"$f":"'K90 - time schedule'!L41","v":0},{"$f":"'K90 - time schedule'!M41","v":0},{"$f":"'K90 - time schedule'!N41","v":0},{"$f":"'K90 - time schedule'!O41","v":0},{"$f":"'K90 - time schedule'!P41","v":0},{"$f":"'K90 - time schedule'!Q41","v":0},{"$f":"'K90 - time schedule'!R41","v":0},{"$f":"'K90 - time schedule'!S41","v":0},{"$f":"'K90 - time schedule'!T41","v":0},{"$f":"'K90 - time schedule'!U41","v":0},{"$f":"'K90 - time schedule'!V41","v":0},{"$f":"'K90 - time schedule'!W41","v":0},{"$f":"'K90 - time schedule'!X41","v":0},{"$f":"'K90 - time schedule'!Y41","v":0},{"$f":"'K90 - time schedule'!Z41","v":0},{"$f":"'K90 - time schedule'!AA41","v":0},{"$f":"'K90 - time schedule'!AB41","v":0},{"$f":"'K90 - time schedule'!AC41","v":0},{"$f":"'K90 - time schedule'!AD41","v":0},{"$f":"'K90 - time schedule'!AE41","v":0},{"$f":"'K90 - time schedule'!AF41","v":0},{"$f":"'K90 - time schedule'!AG41","v":0},{"$f":"'K90 - time schedule'!AH41","v":0},{"$f":"'K90 - time schedule'!AI41","v":0},{"$f":"'K90 - time schedule'!AJ41","v":0},{"$f":"'K90 - time schedule'!AK41","v":0},{"$f":"'K90 - time schedule'!AL41","v":0},{"$f":"'K90 - time schedule'!AM41","v":0},{"$f":"'K90 - time schedule'!AN41","v":0},{"$f":"'K90 - time schedule'!AO41","v":0},{"$f":"'K90 - time schedule'!AP41","v":0},{"$f":"'K90 - time schedule'!AQ41","v":0},{"$f":"'K90 - time schedule'!AR41","v":0},{"$f":"'K90 - time schedule'!AS41","v":0},{"$f":"'K90 - time schedule'!AT41","v":0},{"$f":"'K90 - time schedule'!AU41","v":0},{"$f":"'K90 - time schedule'!AV41","v":0},{"$f":"'K90 - time schedule'!AW41","v":0},{"$f":"'K90 - time schedule'!AX41","v":0},{"$f":"'K90 - time schedule'!AY41","v":0},{"$f":"'K90 - time schedule'!AZ41","v":0},{"$f":"'K90 - time schedule'!BA41","v":0},{"$f":"'K90 - time schedule'!BB41","v":0},{"$f":"'K90 - time schedule'!BC41","v":0},{"$f":"'K90 - time schedule'!BD41","v":0},{"$f":"'K90 - time schedule'!BE41","v":0},{"$f":"'K90 - time schedule'!BF41","v":0},{"$f":"'K90 - time schedule'!BG41","v":0},{"$f":"'K90 - time schedule'!BH41","v":0},{"$f":"'K90 - time schedule'!BI41","v":0},{"$f":"'K90 - time schedule'!BJ41","v":0},{"$f":"'K90 - time schedule'!BK41","v":0},{"$f":"'K90 - time schedule'!BL41","v":0},{"$f":"'K90 - time schedule'!BM41","v":0},{"$f":"'K90 - time schedule'!BN41","v":0},{"$f":"'K90 - time schedule'!BO41","v":0},{"$f":"'K90 - time schedule'!BP41","v":0},{"$f":"'K90 - time schedule'!BQ41","v":0},{"$f":"'K90 - time schedule'!BR41","v":0},{"$f":"'K90 - time schedule'!BS41","v":0},{"$f":"'K90 - time schedule'!BT41","v":0},{"$f":"'K90 - time schedule'!BU41","v":0},{"$f":"'K90 - time schedule'!BV41","v":0},{"$f":"'K90 - time schedule'!BW41","v":0},{"$f":"'K90 - time schedule'!BX41","v":0},{"$f":"'K90 - time schedule'!BY41","v":0},{"$f":"'K90 - time schedule'!BZ41","v":0},{"$f":"'K90 - time schedule'!CA41","v":0},{"$f":"'K90 - time schedule'!CB41","v":0},{"$f":"'K90 - time schedule'!CC41","v":0},{"$f":"'K90 - time schedule'!CD41","v":0},{"$f":"'K90 - time schedule'!CE41","v":0},{"$f":"'K90 - time schedule'!CF41","v":0},{"$f":"'K90 - time schedule'!CG41","v":0},{"$f":"'K90 - time schedule'!CH41","v":0},{"$f":"'K90 - time schedule'!CI41","v":0},{"$f":"'K90 - time schedule'!CJ41","v":0},{"$f":"'K90 - time schedule'!CK41","v":0},{"$f":"'K90 - time schedule'!CL41","v":0},{"$f":"'K90 - time schedule'!CM41","v":0},{"$f":"'K90 - time schedule'!CN41","v":0},{"$f":"'K90 - time schedule'!CO41","v":0},{"$f":"'K90 - time schedule'!CP41","v":0},{"$f":"'K90 - time schedule'!CQ41","v":0},{"$f":"'K90 - time schedule'!CR41","v":0},{"$f":"'K90 - time schedule'!CS41","v":0},{"$f":"'K90 - time schedule'!CT41","v":0},{"$f":"'K90 - time schedule'!CU41","v":0},{"$f":"'K90 - time schedule'!CV41","v":0},{"$f":"'K90 - time schedule'!CW41","v":0},{"$f":"'K90 - time schedule'!CX41","v":0},{"$f":"'K90 - time schedule'!CY41","v":0},{"$f":"'K90 - time schedule'!CZ41","v":0},{"$f":"'K90 - time schedule'!DA41","v":0},{"$f":"'K90 - time schedule'!DB41","v":0},{"$f":"'K90 - time schedule'!DC41","v":0},{"$f":"'K90 - time schedule'!DD41","v":0},{"$f":"'K90 - time schedule'!DE41","v":0},{"$f":"'K90 - time schedule'!DF41","v":0},{"$f":"'K90 - time schedule'!DG41","v":0},{"$f":"'K90 - time schedule'!DH41","v":0},{"$f":"'K90 - time schedule'!DI41","v":0},{"$f":"'K90 - time schedule'!DJ41","v":0},{"$f":"'K90 - time schedule'!DK41","v":0},{"$f":"'K90 - time schedule'!DL41","v":0},{"$f":"'K90 - time schedule'!DM41","v":0},{"$f":"'K90 - time schedule'!DN41","v":0},{"$f":"'K90 - time schedule'!DO41","v":0},{"$f":"'K90 - time schedule'!DP41","v":0},{"$f":"'K90 - time schedule'!DQ41","v":0},{"$f":"'K90 - time schedule'!DR41","v":0},{"$f":"'K90 - time schedule'!DS41","v":0},{"$f":"'K90 - time schedule'!DT41","v":0},{"$f":"'K90 - time schedule'!DU41","v":0},{"$f":"'K90 - time schedule'!DV41","v":0},{"$f":"'K90 - time schedule'!DW41","v":0},{"$f":"'K90 - time schedule'!DX41","v":0},{"$f":"'K90 - time schedule'!DY41","v":0},{"$f":"'K90 - time schedule'!DZ41","v":0},{"$f":"'K90 - time schedule'!EA41","v":0},{"$f":"'K90 - time schedule'!EB41","v":0},{"$f":"'K90 - time schedule'!EC41","v":0},{"$f":"'K90 - time schedule'!ED41","v":0},{"$f":"'K90 - time schedule'!EE41","v":0},{"$f":"'K90 - time schedule'!EF41","v":0},{"$f":"'K90 - time schedule'!EG41","v":0},{"$f":"'K90 - time schedule'!EH41","v":0},{"$f":"'K90 - time schedule'!EI41","v":0},{"$f":"'K90 - time schedule'!EJ41","v":0},{"$f":"'K90 - time schedule'!EK41","v":0},{"$f":"'K90 - time schedule'!EL41","v":0},{"$f":"'K90 - time schedule'!EM41","v":0},{"$f":"'K90 - time schedule'!EN41","v":0},{"$f":"'K90 - time schedule'!EO41","v":0},{"$f":"'K90 - time schedule'!EP41","v":0},{"$f":"'K90 - time schedule'!EQ41","v":0},{"$f":"'K90 - time schedule'!ER41","v":0},{"$f":"'K90 - time schedule'!ES41","v":0},{"$f":"'K90 - time schedule'!ET41","v":0},{"$f":"'K90 - time schedule'!EU41","v":0},{"$f":"'K90 - time schedule'!EV41","v":0},{"$f":"'K90 - time schedule'!EW41","v":0},{"$f":"'K90 - time schedule'!EX41","v":0},{"$f":"'K90 - time schedule'!EY41","v":0},{"$f":"'K90 - time schedule'!EZ41","v":0},{"$f":"'K90 - time schedule'!FA41","v":0},{"$f":"'K90 - time schedule'!FB41","v":0},{"$f":"'K90 - time schedule'!FC41","v":0},{"$f":"'K90 - time schedule'!FD41","v":0},{"$f":"'K90 - time schedule'!FE41","v":0},{"$f":"'K90 - time schedule'!FF41","v":0},{"$f":"'K90 - time schedule'!FG41","v":0},{"$f":"'K90 - time schedule'!FH41","v":0},{"$f":"'K90 - time schedule'!FI41","v":0},{"$f":"'K90 - time schedule'!FJ41","v":0},{"$f":"'K90 - time schedule'!FK41","v":0},{"$f":"'K90 - time schedule'!FL41","v":0},{"$f":"'K90 - time schedule'!FM41","v":0},{"$f":"'K90 - time schedule'!FN41","v":0},{"$f":"'K90 - time schedule'!FO41","v":0},{"$f":"'K90 - time schedule'!FP41","v":0},{"$f":"'K90 - time schedule'!FQ41","v":0},{"$f":"'K90 - time schedule'!FR41","v":0},{"$f":"'K90 - time schedule'!FS41","v":0},{"$f":"'K90 - time schedule'!FT41","v":0},{"$f":"'K90 - time schedule'!FU41","v":0},{"$f":"'K90 - time schedule'!FV41","v":0},{"$f":"'K90 - time schedule'!FW41","v":0},{"$f":"'K90 - time schedule'!FX41","v":0},{"$f":"'K90 - time schedule'!FY41","v":0},{"$f":"'K90 - time schedule'!FZ41","v":0},{"$f":"'K90 - time schedule'!GA41","v":0},{"$f":"'K90 - time schedule'!GB41","v":0},{"$f":"'K90 - time schedule'!GC41","v":0},{"$f":"'K90 - time schedule'!GD41","v":0},{"$f":"'K90 - time schedule'!GE41","v":0},{"$f":"'K90 - time schedule'!GF41","v":0},{"$f":"'K20 - time schedule'!GG75","v":0},{"$f":"'K20 - time schedule'!GH75","v":0},{"$f":"'K20 - time schedule'!GI75","v":0},{"$f":"'K20 - time schedule'!GJ75","v":0},{"$f":"'K20 - time schedule'!GK75","v":0},{"$f":"'K20 - time schedule'!GL75","v":0},{"$f":"'K20 - time schedule'!GM75","v":0},{"$f":"'K20 - time schedule'!GN75","v":0},{"$f":"'K20 - time schedule'!GO75","v":0},{"$f":"'K20 - time schedule'!GP75","v":0},{"$f":"'K20 - time schedule'!GQ75","v":0},{"$f":"'K20 - time schedule'!GR75","v":0},{"$f":"'K20 - time schedule'!GS75","v":0},{"$f":"'K20 - time schedule'!GT75","v":0},{"$f":"'K20 - time schedule'!GU75","v":0},{"$f":"'K20 - time schedule'!GV75","v":0},{"$f":"'K20 - time schedule'!GW75","v":0},{"$f":"'K20 - time schedule'!GX75","v":0},{"$f":"'K20 - time schedule'!GY75","v":0},{"$f":"'K20 - time schedule'!GZ75","v":0},{"$f":"'K20 - time schedule'!HA75","v":0},{"$f":"'K20 - time schedule'!HB75","v":0},{"$f":"'K20 - time schedule'!HC75","v":0},{"$f":"'K20 - time schedule'!HD75","v":0},{"$f":"'K20 - time schedule'!HE75","v":0},{"$f":"'K20 - time schedule'!HF75","v":0},{"$f":"'K20 - time schedule'!HG75","v":0},{"$f":"'K20 - time schedule'!HH75","v":0},{"$f":"'K20 - time schedule'!HI75","v":0},{"$f":"'K20 - time schedule'!HJ75","v":0},{"$f":"'K20 - time schedule'!HK75","v":0},{"$f":"'K20 - time schedule'!HL75","v":0},{"$f":"'K20 - time schedule'!HM75","v":0},{"$f":"'K20 - time schedule'!HN75","v":0},{"$f":"'K20 - time schedule'!HO75","v":0},{"$f":"'K20 - time schedule'!HP75","v":0},{"$f":"'K20 - time schedule'!HQ75","v":0},{"$f":"'K20 - time schedule'!HR75","v":0},{"$f":"'K20 - time schedule'!HS75","v":0},{"$f":"'K20 - time schedule'!HT75","v":0},{"$f":"'K20 - time schedule'!HU75","v":0},{"$f":"'K20 - time schedule'!HV75","v":0},{"$f":"'K20 - time schedule'!HW75","v":0},{"$f":"'K20 - time schedule'!HX75","v":0},{"$f":"'K20 - time schedule'!HY75","v":0},{"$f":"'K20 - time schedule'!HZ75","v":0},{"$f":"'K20 - time schedule'!IA75","v":0},{"$f":"'K20 - time schedule'!IB75","v":0},{"$f":"'K20 - time schedule'!IC75","v":0},{"$f":"'K20 - time schedule'!ID75","v":0},{"$f":"'K20 - time schedule'!IE75","v":0},{"$f":"'K20 - time schedule'!IF75","v":0},{"$f":"'K20 - time schedule'!IG75","v":0},{"$f":"'K20 - time schedule'!IH75","v":0},{"$f":"'K20 - time schedule'!II75","v":0},{"$f":"'K20 - time schedule'!IJ75","v":0},{"$f":"'K20 - time schedule'!IK75","v":0},{"$f":"'K20 - time schedule'!IL75","v":0},{"$f":"'K20 - time schedule'!IM75","v":0},{"$f":"'K20 - time schedule'!IN75","v":0},{"$f":"'K20 - time schedule'!IO75","v":0},{"$f":"'K20 - time schedule'!IP75","v":0},{"$f":"'K20 - time schedule'!IQ75","v":0},{"$f":"'K20 - time schedule'!IR75","v":0},{"$f":"'K20 - time schedule'!IS75","v":0},{"$f":"'K20 - time schedule'!IT75","v":0},{"$f":"'K20 - time schedule'!IU75","v":0},{"$f":"'K20 - time schedule'!IV75","v":0},{"$f":"'K20 - time schedule'!IW75","v":0},{"$f":"'K20 - time schedule'!IX75","v":0},{"$f":"'K20 - time schedule'!IY75","v":0},{"$f":"'K20 - time schedule'!IZ75","v":0},{"$f":"'K20 - time schedule'!JA75","v":0},{"$f":"'K20 - time schedule'!JB75","v":0},{"$f":"'K20 - time schedule'!JC75","v":0},{"$f":"'K20 - time schedule'!JD75","v":0},{"$f":"'K20 - time schedule'!JE75","v":0},{"$f":"'K20 - time schedule'!JF75","v":0},{"$f":"'K20 - time schedule'!JG75","v":0},{"$f":"'K20 - time schedule'!JH75","v":0},{"$f":"'K20 - time schedule'!JI75","v":0},{"$f":"'K20 - time schedule'!JJ75","v":0},{"$f":"'K20 - time schedule'!JK75","v":0},{"$f":"'K20 - time schedule'!JL75","v":0},{"$f":"'K20 - time schedule'!JM75","v":0},{"$f":"'K20 - time schedule'!JN75","v":0},{"$f":"'K20 - time schedule'!JO75","v":0},{"$f":"'K20 - time schedule'!JP75","v":0},{"$f":"'K20 - time schedule'!JQ75","v":0},{"$f":"'K20 - time schedule'!JR75","v":0},{"$f":"'K20 - time schedule'!JS75","v":0},{"$f":"'K20 - time schedule'!JT75","v":0},{"$f":"'K20 - time schedule'!JU75","v":0},{"$f":"'K20 - time schedule'!JV75","v":0},{"$f":"'K20 - time schedule'!JW75","v":0},{"$f":"'K20 - time schedule'!JX75","v":0},{"$f":"'K20 - time schedule'!JY75","v":0},{"$f":"'K20 - time schedule'!JZ75","v":0},{"$f":"'K20 - time schedule'!KA75","v":0},{"$f":"'K20 - time schedule'!KB75","v":0},{"$f":"'K20 - time schedule'!KC75","v":0},{"$f":"'K20 - time schedule'!KD75","v":0},{"$f":"'K20 - time schedule'!KE75","v":0},{"$f":"'K20 - time schedule'!KF75","v":0},{"$f":"'K20 - time schedule'!KG75","v":0},{"$f":"'K20 - time schedule'!KH75","v":0},{"$f":"'K20 - time schedule'!KI75","v":0},{"$f":"'K20 - time schedule'!KJ75","v":0},{"$f":"'K20 - time schedule'!KK75","v":0},{"$f":"'K20 - time schedule'!KL75","v":0},{"$f":"'K20 - time schedule'!KM75","v":0},{"$f":"'K20 - time schedule'!KN75","v":0},{"$f":"'K20 - time schedule'!KO75","v":0},{"$f":"'K20 - time schedule'!KP75","v":0},{"$f":"'K20 - time schedule'!KQ75","v":0},{"$f":"'K20 - time schedule'!KR75","v":0},{"$f":"'K20 - time schedule'!KS75","v":0},{"$f":"'K20 - time schedule'!KT75","v":0}]
["Boiler room K90 - construction structures","K90","EUR",{"$f":"'K90 - time schedule'!G43","v":0},{"$f":"'K90 - time schedule'!H43","v":0},{"$f":"'K90 - time schedule'!I43","v":0},{"$f":"'K90 - time schedule'!J43","v":0},{"$f":"'K90 - time schedule'!K43","v":0},{"$f":"'K90 - time schedule'!L43","v":0},{"$f":"'K90 - time schedule'!M43","v":0},{"$f":"'K90 - time schedule'!N43","v":0},{"$f":"'K90 - time schedule'!O43","v":0},{"$f":"'K90 - time schedule'!P43","v":0},{"$f":"'K90 - time schedule'!Q43","v":0},{"$f":"'K90 - time schedule'!R43","v":0},{"$f":"'K90 - time schedule'!S43","v":0},{"$f":"'K90 - time schedule'!T43","v":0},{"$f":"'K90 - time schedule'!U43","v":0},{"$f":"'K90 - time schedule'!V43","v":0},{"$f":"'K90 - time schedule'!W43","v":0},{"$f":"'K90 - time schedule'!X43","v":0},{"$f":"'K90 - time schedule'!Y43","v":0},{"$f":"'K90 - time schedule'!Z43","v":0},{"$f":"'K90 - time schedule'!AA43","v":0},{"$f":"'K90 - time schedule'!AB43","v":0},{"$f":"'K90 - time schedule'!AC43","v":0},{"$f":"'K90 - time schedule'!AD43","v":0},{"$f":"'K90 - time schedule'!AE43","v":0},{"$f":"'K90 - time schedule'!AF43","v":0},{"$f":"'K90 - time schedule'!AG43","v":0},{"$f":"'K90 - time schedule'!AH43","v":0},{"$f":"'K90 - time schedule'!AI43","v":0},{"$f":"'K90 - time schedule'!AJ43","v":0},{"$f":"'K90 - time schedule'!AK43","v":0},{"$f":"'K90 - time schedule'!AL43","v":0},{"$f":"'K90 - time schedule'!AM43","v":0},{"$f":"'K90 - time schedule'!AN43","v":0},{"$f":"'K90 - time schedule'!AO43","v":0},{"$f":"'K90 - time schedule'!AP43","v":0},{"$f":"'K90 - time schedule'!AQ43","v":0},{"$f":"'K90 - time schedule'!AR43","v":0},{"$f":"'K90 - time schedule'!AS43","v":0},{"$f":"'K90 - time schedule'!AT43","v":0},{"$f":"'K90 - time schedule'!AU43","v":0},{"$f":"'K90 - time schedule'!AV43","v":0},{"$f":"'K90 - time schedule'!AW43","v":0},{"$f":"'K90 - time schedule'!AX43","v":0},{"$f":"'K90 - time schedule'!AY43","v":0},{"$f":"'K90 - time schedule'!AZ43","v":0},{"$f":"'K90 - time schedule'!BA43","v":0},{"$f":"'K90 - time schedule'!BB43","v":0},{"$f":"'K90 - time schedule'!BC43","v":0},{"$f":"'K90 - time schedule'!BD43","v":0},{"$f":"'K90 - time schedule'!BE43","v":0},{"$f":"'K90 - time schedule'!BF43","v":0},{"$f":"'K90 - time schedule'!BG43","v":0},{"$f":"'K90 - time schedule'!BH43","v":0},{"$f":"'K90 - time schedule'!BI43","v":0},{"$f":"'K90 - time schedule'!BJ43","v":0},{"$f":"'K90 - time schedule'!BK43","v":0},{"$f":"'K90 - time schedule'!BL43","v":0},{"$f":"'K90 - time schedule'!BM43","v":0},{"$f":"'K90 - time schedule'!BN43","v":0},{"$f":"'K90 - time schedule'!BO43","v":0},{"$f":"'K90 - time schedule'!BP43","v":0},{"$f":"'K90 - time schedule'!BQ43","v":0},{"$f":"'K90 - time schedule'!BR43","v":0},{"$f":"'K90 - time schedule'!BS43","v":0},{"$f":"'K90 - time schedule'!BT43","v":0},{"$f":"'K90 - time schedule'!BU43","v":0},{"$f":"'K90 - time schedule'!BV43","v":0},{"$f":"'K90 - time schedule'!BW43","v":0},{"$f":"'K90 - time schedule'!BX43","v":0},{"$f":"'K90 - time schedule'!BY43","v":0},{"$f":"'K90 - time schedule'!BZ43","v":0},{"$f":"'K90 - time schedule'!CA43","v":0},{"$f":"'K90 - time schedule'!CB43","v":0},{"$f":"'K90 - time schedule'!CC43","v":0},{"$f":"'K90 - time schedule'!CD43","v":0},{"$f":"'K90 - time schedule'!CE43","v":0},{"$f":"'K90 - time schedule'!CF43","v":0},{"$f":"'K90 - time schedule'!CG43","v":0},{"$f":"'K90 - time schedule'!CH43","v":0},{"$f":"'K90 - time schedule'!CI43","v":0},{"$f":"'K90 - time schedule'!CJ43","v":0},{"$f":"'K90 - time schedule'!CK43","v":0},{"$f":"'K90 - time schedule'!CL43","v":0},{"$f":"'K90 - time schedule'!CM43","v":0},{"$f":"'K90 - time schedule'!CN43","v":0},{"$f":"'K90 - time schedule'!CO43","v":0},{"$f":"'K90 - time schedule'!CP43","v":0},{"$f":"'K90 - time schedule'!CQ43","v":0},{"$f":"'K90 - time schedule'!CR43","v":0},{"$f":"'K90 - time schedule'!CS43","v":0},{"$f":"'K90 - time schedule'!CT43","v":0},{"$f":"'K90 - time schedule'!CU43","v":0},{"$f":"'K90 - time schedule'!CV43","v":0},{"$f":"'K90 - time schedule'!CW43","v":0},{"$f":"'K90 - time schedule'!CX43","v":0},{"$f":"'K90 - time schedule'!CY43","v":0},{"$f":"'K90 - time schedule'!CZ43","v":0},{"$f":"'K90 - time schedule'!DA43","v":0},{"$f":"'K90 - time schedule'!DB43","v":0},{"$f":"'K90 - time schedule'!DC43","v":0},{"$f":"'K90 - time schedule'!DD43","v":0},{"$f":"'K90 - time schedule'!DE43","v":0},{"$f":"'K90 - time schedule'!DF43","v":0},{"$f":"'K90 - time schedule'!DG43","v":0},{"$f":"'K90 - time schedule'!DH43","v":0},{"$f":"'K90 - time schedule'!DI43","v":0},{"$f":"'K90 - time schedule'!DJ43","v":0},{"$f":"'K90 - time schedule'!DK43","v":0},{"$f":"'K90 - time schedule'!DL43","v":0},{"$f":"'K90 - time schedule'!DM43","v":0},{"$f":"'K90 - time schedule'!DN43","v":0},{"$f":"'K90 - time schedule'!DO43","v":0},{"$f":"'K90 - time schedule'!DP43","v":0},{"$f":"'K90 - time schedule'!DQ43","v":0},{"$f":"'K90 - time schedule'!DR43","v":0},{"$f":"'K90 - time schedule'!DS43","v":0},{"$f":"'K90 - time schedule'!DT43","v":0},{"$f":"'K90 - time schedule'!DU43","v":0},{"$f":"'K90 - time schedule'!DV43","v":0},{"$f":"'K90 - time schedule'!DW43","v":0},{"$f":"'K90 - time schedule'!DX43","v":0},{"$f":"'K90 - time schedule'!DY43","v":0},{"$f":"'K90 - time schedule'!DZ43","v":0},{"$f":"'K90 - time schedule'!EA43","v":0},{"$f":"'K90 - time schedule'!EB43","v":0},{"$f":"'K90 - time schedule'!EC43","v":0},{"$f":"'K90 - time schedule'!ED43","v":0},{"$f":"'K90 - time schedule'!EE43","v":0},{"$f":"'K90 - time schedule'!EF43","v":0},{"$f":"'K90 - time schedule'!EG43","v":0},{"$f":"'K90 - time schedule'!EH43","v":0},{"$f":"'K90 - time schedule'!EI43","v":0},{"$f":"'K90 - time schedule'!EJ43","v":0},{"$f":"'K90 - time schedule'!EK43","v":0},{"$f":"'K90 - time schedule'!EL43","v":0},{"$f":"'K90 - time schedule'!EM43","v":0},{"$f":"'K90 - time schedule'!EN43","v":0},{"$f":"'K90 - time schedule'!EO43","v":0},{"$f":"'K90 - time schedule'!EP43","v":0},{"$f":"'K90 - time schedule'!EQ43","v":0},{"$f":"'K90 - time schedule'!ER43","v":0},{"$f":"'K90 - time schedule'!ES43","v":0},{"$f":"'K90 - time schedule'!ET43","v":0},{"$f":"'K90 - time schedule'!EU43","v":0},{"$f":"'K90 - time schedule'!EV43","v":0},{"$f":"'K90 - time schedule'!EW43","v":0},{"$f":"'K90 - time schedule'!EX43","v":0},{"$f":"'K90 - time schedule'!EY43","v":0},{"$f":"'K90 - time schedule'!EZ43","v":0},{"$f":"'K90 - time schedule'!FA43","v":0},{"$f":"'K90 - time schedule'!FB43","v":0},{"$f":"'K90 - time schedule'!FC43","v":0},{"$f":"'K90 - time schedule'!FD43","v":0},{"$f":"'K90 - time schedule'!FE43","v":0},{"$f":"'K90 - time schedule'!FF43","v":0},{"$f":"'K90 - time schedule'!FG43","v":0},{"$f":"'K90 - time schedule'!FH43","v":0},{"$f":"'K90 - time schedule'!FI43","v":0},{"$f":"'K90 - time schedule'!FJ43","v":0},{"$f":"'K90 - time schedule'!FK43","v":0},{"$f":"'K90 - time schedule'!FL43","v":0},{"$f":"'K90 - time schedule'!FM43","v":0},{"$f":"'K90 - time schedule'!FN43","v":0},{"$f":"'K90 - time schedule'!FO43","v":0},{"$f":"'K90 - time schedule'!FP43","v":0},{"$f":"'K90 - time schedule'!FQ43","v":0},{"$f":"'K90 - time schedule'!FR43","v":0},{"$f":"'K90 - time schedule'!FS43","v":0},{"$f":"'K90 - time schedule'!FT43","v":0},{"$f":"'K90 - time schedule'!FU43","v":0},{"$f":"'K90 - time schedule'!FV43","v":0},{"$f":"'K90 - time schedule'!FW43","v":0},{"$f":"'K90 - time schedule'!FX43","v":0},{"$f":"'K90 - time schedule'!FY43","v":0},{"$f":"'K90 - time schedule'!FZ43","v":0},{"$f":"'K90 - time schedule'!GA43","v":0},{"$f":"'K90 - time schedule'!GB43","v":0},{"$f":"'K90 - time schedule'!GC43","v":0},{"$f":"'K90 - time schedule'!GD43","v":0},{"$f":"'K90 - time schedule'!GE43","v":0},{"$f":"'K90 - time schedule'!GF43","v":0},{"$f":"'K20 - time schedule'!GG76","v":0},{"$f":"'K20 - time schedule'!GH76","v":0},{"$f":"'K20 - time schedule'!GI76","v":0},{"$f":"'K20 - time schedule'!GJ76","v":0},{"$f":"'K20 - time schedule'!GK76","v":0},{"$f":"'K20 - time schedule'!GL76","v":0},{"$f":"'K20 - time schedule'!GM76","v":0},{"$f":"'K20 - time schedule'!GN76","v":0},{"$f":"'K20 - time schedule'!GO76","v":0},{"$f":"'K20 - time schedule'!GP76","v":0},{"$f":"'K20 - time schedule'!GQ76","v":0},{"$f":"'K20 - time schedule'!GR76","v":0},{"$f":"'K20 - time schedule'!GS76","v":0},{"$f":"'K20 - time schedule'!GT76","v":0},{"$f":"'K20 - time schedule'!GU76","v":0},{"$f":"'K20 - time schedule'!GV76","v":0},{"$f":"'K20 - time schedule'!GW76","v":0},{"$f":"'K20 - time schedule'!GX76","v":0},{"$f":"'K20 - time schedule'!GY76","v":0},{"$f":"'K20 - time schedule'!GZ76","v":0},{"$f":"'K20 - time schedule'!HA76","v":0},{"$f":"'K20 - time schedule'!HB76","v":0},{"$f":"'K20 - time schedule'!HC76","v":0},{"$f":"'K20 - time schedule'!HD76","v":0},{"$f":"'K20 - time schedule'!HE76","v":0},{"$f":"'K20 - time schedule'!HF76","v":0},{"$f":"'K20 - time schedule'!HG76","v":0},{"$f":"'K20 - time schedule'!HH76","v":0},{"$f":"'K20 - time schedule'!HI76","v":0},{"$f":"'K20 - time schedule'!HJ76","v":0},{"$f":"'K20 - time schedule'!HK76","v":0},{"$f":"'K20 - time schedule'!HL76","v":0},{"$f":"'K20 - time schedule'!HM76","v":0},{"$f":"'K20 - time schedule'!HN76","v":0},{"$f":"'K20 - time schedule'!HO76","v":0},{"$f":"'K20 - time schedule'!HP76","v":0},{"$f":"'K20 - time schedule'!HQ76","v":0},{"$f":"'K20 - time schedule'!HR76","v":0},{"$f":"'K20 - time schedule'!HS76","v":0},{"$f":"'K20 - time schedule'!HT76","v":0},{"$f":"'K20 - time schedule'!HU76","v":0},{"$f":"'K20 - time schedule'!HV76","v":0},{"$f":"'K20 - time schedule'!HW76","v":0},{"$f":"'K20 - time schedule'!HX76","v":0},{"$f":"'K20 - time schedule'!HY76","v":0},{"$f":"'K20 - time schedule'!HZ76","v":0},{"$f":"'K20 - time schedule'!IA76","v":0},{"$f":"'K20 - time schedule'!IB76","v":0},{"$f":"'K20 - time schedule'!IC76","v":0},{"$f":"'K20 - time schedule'!ID76","v":0},{"$f":"'K20 - time schedule'!IE76","v":0},{"$f":"'K20 - time schedule'!IF76","v":0},{"$f":"'K20 - time schedule'!IG76","v":0},{"$f":"'K20 - time schedule'!IH76","v":0},{"$f":"'K20 - time schedule'!II76","v":0},{"$f":"'K20 - time schedule'!IJ76","v":0},{"$f":"'K20 - time schedule'!IK76","v":0},{"$f":"'K20 - time schedule'!IL76","v":0},{"$f":"'K20 - time schedule'!IM76","v":0},{"$f":"'K20 - time schedule'!IN76","v":0},{"$f":"'K20 - time schedule'!IO76","v":0},{"$f":"'K20 - time schedule'!IP76","v":0},{"$f":"'K20 - time schedule'!IQ76","v":0},{"$f":"'K20 - time schedule'!IR76","v":0},{"$f":"'K20 - time schedule'!IS76","v":0},{"$f":"'K20 - time schedule'!IT76","v":0},{"$f":"'K20 - time schedule'!IU76","v":0},{"$f":"'K20 - time schedule'!IV76","v":0},{"$f":"'K20 - time schedule'!IW76","v":0},{"$f":"'K20 - time schedule'!IX76","v":0},{"$f":"'K20 - time schedule'!IY76","v":0},{"$f":"'K20 - time schedule'!IZ76","v":0},{"$f":"'K20 - time schedule'!JA76","v":0},{"$f":"'K20 - time schedule'!JB76","v":0},{"$f":"'K20 - time schedule'!JC76","v":0},{"$f":"'K20 - time schedule'!JD76","v":0},{"$f":"'K20 - time schedule'!JE76","v":0},{"$f":"'K20 - time schedule'!JF76","v":0},{"$f":"'K20 - time schedule'!JG76","v":0},{"$f":"'K20 - time schedule'!JH76","v":0},{"$f":"'K20 - time schedule'!JI76","v":0},{"$f":"'K20 - time schedule'!JJ76","v":0},{"$f":"'K20 - time schedule'!JK76","v":0},{"$f":"'K20 - time schedule'!JL76","v":0},{"$f":"'K20 - time schedule'!JM76","v":0},{"$f":"'K20 - time schedule'!JN76","v":0},{"$f":"'K20 - time schedule'!JO76","v":0},{"$f":"'K20 - time schedule'!JP76","v":0},{"$f":"'K20 - time schedule'!JQ76","v":0},{"$f":"'K20 - time schedule'!JR76","v":0},{"$f":"'K20 - time schedule'!JS76","v":0},{"$f":"'K20 - time schedule'!JT76","v":0},{"$f":"'K20 - time schedule'!JU76","v":0},{"$f":"'K20 - time schedule'!JV76","v":0},{"$f":"'K20 - time schedule'!JW76","v":0},{"$f":"'K20 - time schedule'!JX76","v":0},{"$f":"'K20 - time schedule'!JY76","v":0},{"$f":"'K20 - time schedule'!JZ76","v":0},{"$f":"'K20 - time schedule'!KA76","v":0},{"$f":"'K20 - time schedule'!KB76","v":0},{"$f":"'K20 - time schedule'!KC76","v":0},{"$f":"'K20 - time schedule'!KD76","v":0},{"$f":"'K20 - time schedule'!KE76","v":0},{"$f":"'K20 - time schedule'!KF76","v":0},{"$f":"'K20 - time schedule'!KG76","v":0},{"$f":"'K20 - time schedule'!KH76","v":0},{"$f":"'K20 - time schedule'!KI76","v":0},{"$f":"'K20 - time schedule'!KJ76","v":0},{"$f":"'K20 - time schedule'!KK76","v":0},{"$f":"'K20 - time schedule'!KL76","v":0},{"$f":"'K20 - time schedule'!KM76","v":0},{"$f":"'K20 - time schedule'!KN76","v":0},{"$f":"'K20 - time schedule'!KO76","v":0},{"$f":"'K20 - time schedule'!KP76","v":0},{"$f":"'K20 - time schedule'!KQ76","v":0},{"$f":"'K20 - time schedule'!KR76","v":0},{"$f":"'K20 - time schedule'!KS76","v":0},{"$f":"'K20 - time schedule'!KT76","v":0}]
["Boiler room K90 - ash management (transport piping, silos)","K90","EUR",{"$f":"'K90 - time schedule'!G45","v":0},{"$f":"'K90 - time schedule'!H45","v":0},{"$f":"'K90 - time schedule'!I45","v":0},{"$f":"'K90 - time schedule'!J45","v":0},{"$f":"'K90 - time schedule'!K45","v":0},{"$f":"'K90 - time schedule'!L45","v":0},{"$f":"'K90 - time schedule'!M45","v":0},{"$f":"'K90 - time schedule'!N45","v":0},{"$f":"'K90 - time schedule'!O45","v":0},{"$f":"'K90 - time schedule'!P45","v":0},{"$f":"'K90 - time schedule'!Q45","v":0},{"$f":"'K90 - time schedule'!R45","v":0},{"$f":"'K90 - time schedule'!S45","v":0},{"$f":"'K90 - time schedule'!T45","v":0},{"$f":"'K90 - time schedule'!U45","v":0},{"$f":"'K90 - time schedule'!V45","v":0},{"$f":"'K90 - time schedule'!W45","v":0},{"$f":"'K90 - time schedule'!X45","v":0},{"$f":"'K90 - time schedule'!Y45","v":0},{"$f":"'K90 - time schedule'!Z45","v":0},{"$f":"'K90 - time schedule'!AA45","v":0},{"$f":"'K90 - time schedule'!AB45","v":0},{"$f":"'K90 - time schedule'!AC45","v":0},{"$f":"'K90 - time schedule'!AD45","v":0},{"$f":"'K90 - time schedule'!AE45","v":0},{"$f":"'K90 - time schedule'!AF45","v":0},{"$f":"'K90 - time schedule'!AG45","v":0},{"$f":"'K90 - time schedule'!AH45","v":0},{"$f":"'K90 - time schedule'!AI45","v":0},{"$f":"'K90 - time schedule'!AJ45","v":0},{"$f":"'K90 - time schedule'!AK45","v":0},{"$f":"'K90 - time schedule'!AL45","v":0},{"$f":"'K90 - time schedule'!AM45","v":0},{"$f":"'K90 - time schedule'!AN45","v":0},{"$f":"'K90 - time schedule'!AO45","v":0},{"$f":"'K90 - time schedule'!AP45","v":0},{"$f":"'K90 - time schedule'!AQ45","v":0},{"$f":"'K90 - time schedule'!AR45","v":0},{"$f":"'K90 - time schedule'!AS45","v":0},{"$f":"'K90 - time schedule'!AT45","v":0},{"$f":"'K90 - time schedule'!AU45","v":0},{"$f":"'K90 - time schedule'!AV45","v":0},{"$f":"'K90 - time schedule'!AW45","v":0},{"$f":"'K90 - time schedule'!AX45","v":0},{"$f":"'K90 - time schedule'!AY45","v":0},{"$f":"'K90 - time schedule'!AZ45","v":0},{"$f":"'K90 - time schedule'!BA45","v":0},{"$f":"'K90 - time schedule'!BB45","v":0},{"$f":"'K90 - time schedule'!BC45","v":0},{"$f":"'K90 - time schedule'!BD45","v":0},{"$f":"'K90 - time schedule'!BE45","v":0},{"$f":"'K90 - time schedule'!BF45","v":0},{"$f":"'K90 - time schedule'!BG45","v":0},{"$f":"'K90 - time schedule'!BH45","v":0},{"$f":"'K90 - time schedule'!BI45","v":0},{"$f":"'K90 - time schedule'!BJ45","v":0},{"$f":"'K90 - time schedule'!BK45","v":0},{"$f":"'K90 - time schedule'!BL45","v":0},{"$f":"'K90 - time schedule'!BM45","v":0},{"$f":"'K90 - time schedule'!BN45","v":0},{"$f":"'K90 - time schedule'!BO45","v":0},{"$f":"'K90 - time schedule'!BP45","v":0},{"$f":"'K90 - time schedule'!BQ45","v":0},{"$f":"'K90 - time schedule'!BR45","v":0},{"$f":"'K90 - time schedule'!BS45","v":0},{"$f":"'K90 - time schedule'!BT45","v":0},{"$f":"'K90 - time schedule'!BU45","v":0},{"$f":"'K90 - time schedule'!BV45","v":0},{"$f":"'K90 - time schedule'!BW45","v":0},{"$f":"'K90 - time schedule'!BX45","v":0},{"$f":"'K90 - time schedule'!BY45","v":0},{"$f":"'K90 - time schedule'!BZ45","v":0},{"$f":"'K90 - time schedule'!CA45","v":0},{"$f":"'K90 - time schedule'!CB45","v":0},{"$f":"'K90 - time schedule'!CC45","v":0},{"$f":"'K90 - time schedule'!CD45","v":0},{"$f":"'K90 - time schedule'!CE45","v":0},{"$f":"'K90 - time schedule'!CF45","v":0},{"$f":"'K90 - time schedule'!CG45","v":0},{"$f":"'K90 - time schedule'!CH45","v":0},{"$f":"'K90 - time schedule'!CI45","v":0},{"$f":"'K90 - time schedule'!CJ45","v":0},{"$f":"'K90 - time schedule'!CK45","v":0},{"$f":"'K90 - time schedule'!CL45","v":0},{"$f":"'K90 - time schedule'!CM45","v":0},{"$f":"'K90 - time schedule'!CN45","v":0},{"$f":"'K90 - time schedule'!CO45","v":0},{"$f":"'K90 - time schedule'!CP45","v":0},{"$f":"'K90 - time schedule'!CQ45","v":0},{"$f":"'K90 - time schedule'!CR45","v":0},{"$f":"'K90 - time schedule'!CS45","v":0},{"$f":"'K90 - time schedule'!CT45","v":0},{"$f":"'K90 - time schedule'!CU45","v":0},{"$f":"'K90 - time schedule'!CV45","v":0},{"$f":"'K90 - time schedule'!CW45","v":0},{"$f":"'K90 - time schedule'!CX45","v":0},{"$f":"'K90 - time schedule'!CY45","v":0},{"$f":"'K90 - time schedule'!CZ45","v":0},{"$f":"'K90 - time schedule'!DA45","v":0},{"$f":"'K90 - time schedule'!DB45","v":0},{"$f":"'K90 - time schedule'!DC45","v":0},{"$f":"'K90 - time schedule'!DD45","v":0},{"$f":"'K90 - time schedule'!DE45","v":0},{"$f":"'K90 - time schedule'!DF45","v":0},{"$f":"'K90 - time schedule'!DG45","v":0},{"$f":"'K90 - time schedule'!DH45","v":0},{"$f":"'K90 - time schedule'!DI45","v":0},{"$f":"'K90 - time schedule'!DJ45","v":0},{"$f":"'K90 - time schedule'!DK45","v":0},{"$f":"'K90 - time schedule'!DL45","v":0},{"$f":"'K90 - time schedule'!DM45","v":0},{"$f":"'K90 - time schedule'!DN45","v":0},{"$f":"'K90 - time schedule'!DO45","v":0},{"$f":"'K90 - time schedule'!DP45","v":0},{"$f":"'K90 - time schedule'!DQ45","v":0},{"$f":"'K90 - time schedule'!DR45","v":0},{"$f":"'K90 - time schedule'!DS45","v":0},{"$f":"'K90 - time schedule'!DT45","v":0},{"$f":"'K90 - time schedule'!DU45","v":0},{"$f":"'K90 - time schedule'!DV45","v":0},{"$f":"'K90 - time schedule'!DW45","v":0},{"$f":"'K90 - time schedule'!DX45","v":0},{"$f":"'K90 - time schedule'!DY45","v":0},{"$f":"'K90 - time schedule'!DZ45","v":0},{"$f":"'K90 - time schedule'!EA45","v":0},{"$f":"'K90 - time schedule'!EB45","v":0},{"$f":"'K90 - time schedule'!EC45","v":0},{"$f":"'K90 - time schedule'!ED45","v":0},{"$f":"'K90 - time schedule'!EE45","v":0},{"$f":"'K90 - time schedule'!EF45","v":0},{"$f":"'K90 - time schedule'!EG45","v":0},{"$f":"'K90 - time schedule'!EH45","v":0},{"$f":"'K90 - time schedule'!EI45","v":0},{"$f":"'K90 - time schedule'!EJ45","v":0},{"$f":"'K90 - time schedule'!EK45","v":0},{"$f":"'K90 - time schedule'!EL45","v":0},{"$f":"'K90 - time schedule'!EM45","v":0},{"$f":"'K90 - time schedule'!EN45","v":0},{"$f":"'K90 - time schedule'!EO45","v":0},{"$f":"'K90 - time schedule'!EP45","v":0},{"$f":"'K90 - time schedule'!EQ45","v":0},{"$f":"'K90 - time schedule'!ER45","v":0},{"$f":"'K90 - time schedule'!ES45","v":0},{"$f":"'K90 - time schedule'!ET45","v":0},{"$f":"'K90 - time schedule'!EU45","v":0},{"$f":"'K90 - time schedule'!EV45","v":0},{"$f":"'K90 - time schedule'!EW45","v":0},{"$f":"'K90 - time schedule'!EX45","v":0},{"$f":"'K90 - time schedule'!EY45","v":0},{"$f":"'K90 - time schedule'!EZ45","v":0},{"$f":"'K90 - time schedule'!FA45","v":0},{"$f":"'K90 - time schedule'!FB45","v":0},{"$f":"'K90 - time schedule'!FC45","v":0},{"$f":"'K90 - time schedule'!FD45","v":0},{"$f":"'K90 - time schedule'!FE45","v":0},{"$f":"'K90 - time schedule'!FF45","v":0},{"$f":"'K90 - time schedule'!FG45","v":0},{"$f":"'K90 - time schedule'!FH45","v":0},{"$f":"'K90 - time schedule'!FI45","v":0},{"$f":"'K90 - time schedule'!FJ45","v":0},{"$f":"'K90 - time schedule'!FK45","v":0},{"$f":"'K90 - time schedule'!FL45","v":0},{"$f":"'K90 - time schedule'!FM45","v":0},{"$f":"'K90 - time schedule'!FN45","v":0},{"$f":"'K90 - time schedule'!FO45","v":0},{"$f":"'K90 - time schedule'!FP45","v":0},{"$f":"'K90 - time schedule'!FQ45","v":0},{"$f":"'K90 - time schedule'!FR45","v":0},{"$f":"'K90 - time schedule'!FS45","v":0},{"$f":"'K90 - time schedule'!FT45","v":0},{"$f":"'K90 - time schedule'!FU45","v":0},{"$f":"'K90 - time schedule'!FV45","v":0},{"$f":"'K90 - time schedule'!FW45","v":0},{"$f":"'K90 - time schedule'!FX45","v":0},{"$f":"'K90 - time schedule'!FY45","v":0},{"$f":"'K90 - time schedule'!FZ45","v":0},{"$f":"'K90 - time schedule'!GA45","v":0},{"$f":"'K90 - time schedule'!GB45","v":0},{"$f":"'K90 - time schedule'!GC45","v":0},{"$f":"'K90 - time schedule'!GD45","v":0},{"$f":"'K90 - time schedule'!GE45","v":0},{"$f":"'K90 - time schedule'!GF45","v":0},{"$f":"'K20 - time schedule'!GG77","v":0},{"$f":"'K20 - time schedule'!GH77","v":0},{"$f":"'K20 - time schedule'!GI77","v":0},{"$f":"'K20 - time schedule'!GJ77","v":0},{"$f":"'K20 - time schedule'!GK77","v":0},{"$f":"'K20 - time schedule'!GL77","v":0},{"$f":"'K20 - time schedule'!GM77","v":0},{"$f":"'K20 - time schedule'!GN77","v":0},{"$f":"'K20 - time schedule'!GO77","v":0},{"$f":"'K20 - time schedule'!GP77","v":0},{"$f":"'K20 - time schedule'!GQ77","v":0},{"$f":"'K20 - time schedule'!GR77","v":0},{"$f":"'K20 - time schedule'!GS77","v":0},{"$f":"'K20 - time schedule'!GT77","v":0},{"$f":"'K20 - time schedule'!GU77","v":0},{"$f":"'K20 - time schedule'!GV77","v":0},{"$f":"'K20 - time schedule'!GW77","v":0},{"$f":"'K20 - time schedule'!GX77","v":0},{"$f":"'K20 - time schedule'!GY77","v":0},{"$f":"'K20 - time schedule'!GZ77","v":0},{"$f":"'K20 - time schedule'!HA77","v":0},{"$f":"'K20 - time schedule'!HB77","v":0},{"$f":"'K20 - time schedule'!HC77","v":0},{"$f":"'K20 - time schedule'!HD77","v":0},{"$f":"'K20 - time schedule'!HE77","v":0},{"$f":"'K20 - time schedule'!HF77","v":0},{"$f":"'K20 - time schedule'!HG77","v":0},{"$f":"'K20 - time schedule'!HH77","v":0},{"$f":"'K20 - time schedule'!HI77","v":0},{"$f":"'K20 - time schedule'!HJ77","v":0},{"$f":"'K20 - time schedule'!HK77","v":0},{"$f":"'K20 - time schedule'!HL77","v":0},{"$f":"'K20 - time schedule'!HM77","v":0},{"$f":"'K20 - time schedule'!HN77","v":0},{"$f":"'K20 - time schedule'!HO77","v":0},{"$f":"'K20 - time schedule'!HP77","v":0},{"$f":"'K20 - time schedule'!HQ77","v":0},{"$f":"'K20 - time schedule'!HR77","v":0},{"$f":"'K20 - time schedule'!HS77","v":0},{"$f":"'K20 - time schedule'!HT77","v":0},{"$f":"'K20 - time schedule'!HU77","v":0},{"$f":"'K20 - time schedule'!HV77","v":0},{"$f":"'K20 - time schedule'!HW77","v":0},{"$f":"'K20 - time schedule'!HX77","v":0},{"$f":"'K20 - time schedule'!HY77","v":0},{"$f":"'K20 - time schedule'!HZ77","v":0},{"$f":"'K20 - time schedule'!IA77","v":0},{"$f":"'K20 - time schedule'!IB77","v":0},{"$f":"'K20 - time schedule'!IC77","v":0},{"$f":"'K20 - time schedule'!ID77","v":0},{"$f":"'K20 - time schedule'!IE77","v":0},{"$f":"'K20 - time schedule'!IF77","v":0},{"$f":"'K20 - time schedule'!IG77","v":0},{"$f":"'K20 - time schedule'!IH77","v":0},{"$f":"'K20 - time schedule'!II77","v":0},{"$f":"'K20 - time schedule'!IJ77","v":0},{"$f":"'K20 - time schedule'!IK77","v":0},{"$f":"'K20 - time schedule'!IL77","v":0},{"$f":"'K20 - time schedule'!IM77","v":0},{"$f":"'K20 - time schedule'!IN77","v":0},{"$f":"'K20 - time schedule'!IO77","v":0},{"$f":"'K20 - time schedule'!IP77","v":0},{"$f":"'K20 - time schedule'!IQ77","v":0},{"$f":"'K20 - time schedule'!IR77","v":0},{"$f":"'K20 - time schedule'!IS77","v":0},{"$f":"'K20 - time schedule'!IT77","v":0},{"$f":"'K20 - time schedule'!IU77","v":0},{"$f":"'K20 - time schedule'!IV77","v":0},{"$f":"'K20 - time schedule'!IW77","v":0},{"$f":"'K20 - time schedule'!IX77","v":0},{"$f":"'K20 - time schedule'!IY77","v":0},{"$f":"'K20 - time schedule'!IZ77","v":0},{"$f":"'K20 - time schedule'!JA77","v":0},{"$f":"'K20 - time schedule'!JB77","v":0},{"$f":"'K20 - time schedule'!JC77","v":0},{"$f":"'K20 - time schedule'!JD77","v":0},{"$f":"'K20 - time schedule'!JE77","v":0},{"$f":"'K20 - time schedule'!JF77","v":0},{"$f":"'K20 - time schedule'!JG77","v":0},{"$f":"'K20 - time schedule'!JH77","v":0},{"$f":"'K20 - time schedule'!JI77","v":0},{"$f":"'K20 - time schedule'!JJ77","v":0},{"$f":"'K20 - time schedule'!JK77","v":0},{"$f":"'K20 - time schedule'!JL77","v":0},{"$f":"'K20 - time schedule'!JM77","v":0},{"$f":"'K20 - time schedule'!JN77","v":0},{"$f":"'K20 - time schedule'!JO77","v":0},{"$f":"'K20 - time schedule'!JP77","v":0},{"$f":"'K20 - time schedule'!JQ77","v":0},{"$f":"'K20 - time schedule'!JR77","v":0},{"$f":"'K20 - time schedule'!JS77","v":0},{"$f":"'K20 - time schedule'!JT77","v":0},{"$f":"'K20 - time schedule'!JU77","v":0},{"$f":"'K20 - time schedule'!JV77","v":0},{"$f":"'K20 - time schedule'!JW77","v":0},{"$f":"'K20 - time schedule'!JX77","v":0},{"$f":"'K20 - time schedule'!JY77","v":0},{"$f":"'K20 - time schedule'!JZ77","v":0},{"$f":"'K20 - time schedule'!KA77","v":0},{"$f":"'K20 - time schedule'!KB77","v":0},{"$f":"'K20 - time schedule'!KC77","v":0},{"$f":"'K20 - time schedule'!KD77","v":0},{"$f":"'K20 - time schedule'!KE77","v":0},{"$f":"'K20 - time schedule'!KF77","v":0},{"$f":"'K20 - time schedule'!KG77","v":0},{"$f":"'K20 - time schedule'!KH77","v":0},{"$f":"'K20 - time schedule'!KI77","v":0},{"$f":"'K20 - time schedule'!KJ77","v":0},{"$f":"'K20 - time schedule'!KK77","v":0},{"$f":"'K20 - time schedule'!KL77","v":0},{"$f":"'K20 - time schedule'!KM77","v":0},{"$f":"'K20 - time schedule'!KN77","v":0},{"$f":"'K20 - time schedule'!KO77","v":0},{"$f":"'K20 - time schedule'!KP77","v":0},{"$f":"'K20 - time schedule'!KQ77","v":0},{"$f":"'K20 - time schedule'!KR77","v":0},{"$f":"'K20 - time schedule'!KS77","v":0},{"$f":"'K20 - time schedule'!KT77","v":0}]
["Boiler room K90 - other above not specified items","K90","EUR",{"$f":"'K90 - time schedule'!G47","v":0},{"$f":"'K90 - time schedule'!H47","v":0},{"$f":"'K90 - time schedule'!I47","v":0},{"$f":"'K90 - time schedule'!J47","v":0},{"$f":"'K90 - time schedule'!K47","v":0},{"$f":"'K90 - time schedule'!L47","v":0},{"$f":"'K90 - time schedule'!M47","v":0},{"$f":"'K90 - time schedule'!N47","v":0},{"$f":"'K90 - time schedule'!O47","v":0},{"$f":"'K90 - time schedule'!P47","v":0},{"$f":"'K90 - time schedule'!Q47","v":0},{"$f":"'K90 - time schedule'!R47","v":0},{"$f":"'K90 - time schedule'!S47","v":0},{"$f":"'K90 - time schedule'!T47","v":0},{"$f":"'K90 - time schedule'!U47","v":0},{"$f":"'K90 - time schedule'!V47","v":0},{"$f":"'K90 - time schedule'!W47","v":0},{"$f":"'K90 - time schedule'!X47","v":0},{"$f":"'K90 - time schedule'!Y47","v":0},{"$f":"'K90 - time schedule'!Z47","v":0},{"$f":"'K90 - time schedule'!AA47","v":0},{"$f":"'K90 - time schedule'!AB47","v":0},{"$f":"'K90 - time schedule'!AC47","v":0},{"$f":"'K90 - time schedule'!AD47","v":0},{"$f":"'K90 - time schedule'!AE47","v":0},{"$f":"'K90 - time schedule'!AF47","v":0},{"$f":"'K90 - time schedule'!AG47","v":0},{"$f":"'K90 - time schedule'!AH47","v":0},{"$f":"'K90 - time schedule'!AI47","v":0},{"$f":"'K90 - time schedule'!AJ47","v":0},{"$f":"'K90 - time schedule'!AK47","v":0},{"$f":"'K90 - time schedule'!AL47","v":0},{"$f":"'K90 - time schedule'!AM47","v":0},{"$f":"'K90 - time schedule'!AN47","v":0},{"$f":"'K90 - time schedule'!AO47","v":0},{"$f":"'K90 - time schedule'!AP47","v":0},{"$f":"'K90 - time schedule'!AQ47","v":0},{"$f":"'K90 - time schedule'!AR47","v":0},{"$f":"'K90 - time schedule'!AS47","v":0},{"$f":"'K90 - time schedule'!AT47","v":0},{"$f":"'K90 - time schedule'!AU47","v":0},{"$f":"'K90 - time schedule'!AV47","v":0},{"$f":"'K90 - time schedule'!AW47","v":0},{"$f":"'K90 - time schedule'!AX47","v":0},{"$f":"'K90 - time schedule'!AY47","v":0},{"$f":"'K90 - time schedule'!AZ47","v":0},{"$f":"'K90 - time schedule'!BA47","v":0},{"$f":"'K90 - time schedule'!BB47","v":0},{"$f":"'K90 - time schedule'!BC47","v":0},{"$f":"'K90 - time schedule'!BD47","v":0},{"$f":"'K90 - time schedule'!BE47","v":0},{"$f":"'K90 - time schedule'!BF47","v":0},{"$f":"'K90 - time schedule'!BG47","v":0},{"$f":"'K90 - time schedule'!BH47","v":0},{"$f":"'K90 - time schedule'!BI47","v":0},{"$f":"'K90 - time schedule'!BJ47","v":0},{"$f":"'K90 - time schedule'!BK47","v":0},{"$f":"'K90 - time schedule'!BL47","v":0},{"$f":"'K90 - time schedule'!BM47","v":0},{"$f":"'K90 - time schedule'!BN47","v":0},{"$f":"'K90 - time schedule'!BO47","v":0},{"$f":"'K90 - time schedule'!BP47","v":0},{"$f":"'K90 - time schedule'!BQ47","v":0},{"$f":"'K90 - time schedule'!BR47","v":0},{"$f":"'K90 - time schedule'!BS47","v":0},{"$f":"'K90 - time schedule'!BT47","v":0},{"$f":"'K90 - time schedule'!BU47","v":0},{"$f":"'K90 - time schedule'!BV47","v":0},{"$f":"'K90 - time schedule'!BW47","v":0},{"$f":"'K90 - time schedule'!BX47","v":0},{"$f":"'K90 - time schedule'!BY47","v":0},{"$f":"'K90 - time schedule'!BZ47","v":0},{"$f":"'K90 - time schedule'!CA47","v":0},{"$f":"'K90 - time schedule'!CB47","v":0},{"$f":"'K90 - time schedule'!CC47","v":0},{"$f":"'K90 - time schedule'!CD47","v":0},{"$f":"'K90 - time schedule'!CE47","v":0},{"$f":"'K90 - time schedule'!CF47","v":0},{"$f":"'K90 - time schedule'!CG47","v":0},{"$f":"'K90 - time schedule'!CH47","v":0},{"$f":"'K90 - time schedule'!CI47","v":0},{"$f":"'K90 - time schedule'!CJ47","v":0},{"$f":"'K90 - time schedule'!CK47","v":0},{"$f":"'K90 - time schedule'!CL47","v":0},{"$f":"'K90 - time schedule'!CM47","v":0},{"$f":"'K90 - time schedule'!CN47","v":0},{"$f":"'K90 - time schedule'!CO47","v":0},{"$f":"'K90 - time schedule'!CP47","v":0},{"$f":"'K90 - time schedule'!CQ47","v":0},{"$f":"'K90 - time schedule'!CR47","v":0},{"$f":"'K90 - time schedule'!CS47","v":0},{"$f":"'K90 - time schedule'!CT47","v":0},{"$f":"'K90 - time schedule'!CU47","v":0},{"$f":"'K90 - time schedule'!CV47","v":0},{"$f":"'K90 - time schedule'!CW47","v":0},{"$f":"'K90 - time schedule'!CX47","v":0},{"$f":"'K90 - time schedule'!CY47","v":0},{"$f":"'K90 - time schedule'!CZ47","v":0},{"$f":"'K90 - time schedule'!DA47","v":0},{"$f":"'K90 - time schedule'!DB47","v":0},{"$f":"'K90 - time schedule'!DC47","v":0},{"$f":"'K90 - time schedule'!DD47","v":0},{"$f":"'K90 - time schedule'!DE47","v":0},{"$f":"'K90 - time schedule'!DF47","v":0},{"$f":"'K90 - time schedule'!DG47","v":0},{"$f":"'K90 - time schedule'!DH47","v":0},{"$f":"'K90 - time schedule'!DI47","v":0},{"$f":"'K90 - time schedule'!DJ47","v":0},{"$f":"'K90 - time schedule'!DK47","v":0},{"$f":"'K90 - time schedule'!DL47","v":0},{"$f":"'K90 - time schedule'!DM47","v":0},{"$f":"'K90 - time schedule'!DN47","v":0},{"$f":"'K90 - time schedule'!DO47","v":0},{"$f":"'K90 - time schedule'!DP47","v":0},{"$f":"'K90 - time schedule'!DQ47","v":0},{"$f":"'K90 - time schedule'!DR47","v":0},{"$f":"'K90 - time schedule'!DS47","v":0},{"$f":"'K90 - time schedule'!DT47","v":0},{"$f":"'K90 - time schedule'!DU47","v":0},{"$f":"'K90 - time schedule'!DV47","v":0},{"$f":"'K90 - time schedule'!DW47","v":0},{"$f":"'K90 - time schedule'!DX47","v":0},{"$f":"'K90 - time schedule'!DY47","v":0},{"$f":"'K90 - time schedule'!DZ47","v":0},{"$f":"'K90 - time schedule'!EA47","v":0},{"$f":"'K90 - time schedule'!EB47","v":0},{"$f":"'K90 - time schedule'!EC47","v":0},{"$f":"'K90 - time schedule'!ED47","v":0},{"$f":"'K90 - time schedule'!EE47","v":0},{"$f":"'K90 - time schedule'!EF47","v":0},{"$f":"'K90 - time schedule'!EG47","v":0},{"$f":"'K90 - time schedule'!EH47","v":0},{"$f":"'K90 - time schedule'!EI47","v":0},{"$f":"'K90 - time schedule'!EJ47","v":0},{"$f":"'K90 - time schedule'!EK47","v":0},{"$f":"'K90 - time schedule'!EL47","v":0},{"$f":"'K90 - time schedule'!EM47","v":0},{"$f":"'K90 - time schedule'!EN47","v":0},{"$f":"'K90 - time schedule'!EO47","v":0},{"$f":"'K90 - time schedule'!EP47","v":0},{"$f":"'K90 - time schedule'!EQ47","v":0},{"$f":"'K90 - time schedule'!ER47","v":0},{"$f":"'K90 - time schedule'!ES47","v":0},{"$f":"'K90 - time schedule'!ET47","v":0},{"$f":"'K90 - time schedule'!EU47","v":0},{"$f":"'K90 - time schedule'!EV47","v":0},{"$f":"'K90 - time schedule'!EW47","v":0},{"$f":"'K90 - time schedule'!EX47","v":0},{"$f":"'K90 - time schedule'!EY47","v":0},{"$f":"'K90 - time schedule'!EZ47","v":0},{"$f":"'K90 - time schedule'!FA47","v":0},{"$f":"'K90 - time schedule'!FB47","v":0},{"$f":"'K90 - time schedule'!FC47","v":0},{"$f":"'K90 - time schedule'!FD47","v":0},{"$f":"'K90 - time schedule'!FE47","v":0},{"$f":"'K90 - time schedule'!FF47","v":0},{"$f":"'K90 - time schedule'!FG47","v":0},{"$f":"'K90 - time schedule'!FH47","v":0},{"$f":"'K90 - time schedule'!FI47","v":0},{"$f":"'K90 - time schedule'!FJ47","v":0},{"$f":"'K90 - time schedule'!FK47","v":0},{"$f":"'K90 - time schedule'!FL47","v":0},{"$f":"'K90 - time schedule'!FM47","v":0},{"$f":"'K90 - time schedule'!FN47","v":0},{"$f":"'K90 - time schedule'!FO47","v":0},{"$f":"'K90 - time schedule'!FP47","v":0},{"$f":"'K90 - time schedule'!FQ47","v":0},{"$f":"'K90 - time schedule'!FR47","v":0},{"$f":"'K90 - time schedule'!FS47","v":0},{"$f":"'K90 - time schedule'!FT47","v":0},{"$f":"'K90 - time schedule'!FU47","v":0},{"$f":"'K90 - time schedule'!FV47","v":0},{"$f":"'K90 - time schedule'!FW47","v":0},{"$f":"'K90 - time schedule'!FX47","v":0},{"$f":"'K90 - time schedule'!FY47","v":0},{"$f":"'K90 - time schedule'!FZ47","v":0},{"$f":"'K90 - time schedule'!GA47","v":0},{"$f":"'K90 - time schedule'!GB47","v":0},{"$f":"'K90 - time schedule'!GC47","v":0},{"$f":"'K90 - time schedule'!GD47","v":0},{"$f":"'K90 - time schedule'!GE47","v":0},{"$f":"'K90 - time schedule'!GF47","v":0},{"$f":"'K20 - time schedule'!GG78","v":0},{"$f":"'K20 - time schedule'!GH78","v":0},{"$f":"'K20 - time schedule'!GI78","v":0},{"$f":"'K20 - time schedule'!GJ78","v":0},{"$f":"'K20 - time schedule'!GK78","v":0},{"$f":"'K20 - time schedule'!GL78","v":0},{"$f":"'K20 - time schedule'!GM78","v":0},{"$f":"'K20 - time schedule'!GN78","v":0},{"$f":"'K20 - time schedule'!GO78","v":0},{"$f":"'K20 - time schedule'!GP78","v":0},{"$f":"'K20 - time schedule'!GQ78","v":0},{"$f":"'K20 - time schedule'!GR78","v":0},{"$f":"'K20 - time schedule'!GS78","v":0},{"$f":"'K20 - time schedule'!GT78","v":0},{"$f":"'K20 - time schedule'!GU78","v":0},{"$f":"'K20 - time schedule'!GV78","v":0},{"$f":"'K20 - time schedule'!GW78","v":0},{"$f":"'K20 - time schedule'!GX78","v":0},{"$f":"'K20 - time schedule'!GY78","v":0},{"$f":"'K20 - time schedule'!GZ78","v":0},{"$f":"'K20 - time schedule'!HA78","v":0},{"$f":"'K20 - time schedule'!HB78","v":0},{"$f":"'K20 - time schedule'!HC78","v":0},{"$f":"'K20 - time schedule'!HD78","v":0},{"$f":"'K20 - time schedule'!HE78","v":0},{"$f":"'K20 - time schedule'!HF78","v":0},{"$f":"'K20 - time schedule'!HG78","v":0},{"$f":"'K20 - time schedule'!HH78","v":0},{"$f":"'K20 - time schedule'!HI78","v":0},{"$f":"'K20 - time schedule'!HJ78","v":0},{"$f":"'K20 - time schedule'!HK78","v":0},{"$f":"'K20 - time schedule'!HL78","v":0},{"$f":"'K20 - time schedule'!HM78","v":0},{"$f":"'K20 - time schedule'!HN78","v":0},{"$f":"'K20 - time schedule'!HO78","v":0},{"$f":"'K20 - time schedule'!HP78","v":0},{"$f":"'K20 - time schedule'!HQ78","v":0},{"$f":"'K20 - time schedule'!HR78","v":0},{"$f":"'K20 - time schedule'!HS78","v":0},{"$f":"'K20 - time schedule'!HT78","v":0},{"$f":"'K20 - time schedule'!HU78","v":0},{"$f":"'K20 - time schedule'!HV78","v":0},{"$f":"'K20 - time schedule'!HW78","v":0},{"$f":"'K20 - time schedule'!HX78","v":0},{"$f":"'K20 - time schedule'!HY78","v":0},{"$f":"'K20 - time schedule'!HZ78","v":0},{"$f":"'K20 - time schedule'!IA78","v":0},{"$f":"'K20 - time schedule'!IB78","v":0},{"$f":"'K20 - time schedule'!IC78","v":0},{"$f":"'K20 - time schedule'!ID78","v":0},{"$f":"'K20 - time schedule'!IE78","v":0},{"$f":"'K20 - time schedule'!IF78","v":0},{"$f":"'K20 - time schedule'!IG78","v":0},{"$f":"'K20 - time schedule'!IH78","v":0},{"$f":"'K20 - time schedule'!II78","v":0},{"$f":"'K20 - time schedule'!IJ78","v":0},{"$f":"'K20 - time schedule'!IK78","v":0},{"$f":"'K20 - time schedule'!IL78","v":0},{"$f":"'K20 - time schedule'!IM78","v":0},{"$f":"'K20 - time schedule'!IN78","v":0},{"$f":"'K20 - time schedule'!IO78","v":0},{"$f":"'K20 - time schedule'!IP78","v":0},{"$f":"'K20 - time schedule'!IQ78","v":0},{"$f":"'K20 - time schedule'!IR78","v":0},{"$f":"'K20 - time schedule'!IS78","v":0},{"$f":"'K20 - time schedule'!IT78","v":0},{"$f":"'K20 - time schedule'!IU78","v":0},{"$f":"'K20 - time schedule'!IV78","v":0},{"$f":"'K20 - time schedule'!IW78","v":0},{"$f":"'K20 - time schedule'!IX78","v":0},{"$f":"'K20 - time schedule'!IY78","v":0},{"$f":"'K20 - time schedule'!IZ78","v":0},{"$f":"'K20 - time schedule'!JA78","v":0},{"$f":"'K20 - time schedule'!JB78","v":0},{"$f":"'K20 - time schedule'!JC78","v":0},{"$f":"'K20 - time schedule'!JD78","v":0},{"$f":"'K20 - time schedule'!JE78","v":0},{"$f":"'K20 - time schedule'!JF78","v":0},{"$f":"'K20 - time schedule'!JG78","v":0},{"$f":"'K20 - time schedule'!JH78","v":0},{"$f":"'K20 - time schedule'!JI78","v":0},{"$f":"'K20 - time schedule'!JJ78","v":0},{"$f":"'K20 - time schedule'!JK78","v":0},{"$f":"'K20 - time schedule'!JL78","v":0},{"$f":"'K20 - time schedule'!JM78","v":0},{"$f":"'K20 - time schedule'!JN78","v":0},{"$f":"'K20 - time schedule'!JO78","v":0},{"$f":"'K20 - time schedule'!JP78","v":0},{"$f":"'K20 - time schedule'!JQ78","v":0},{"$f":"'K20 - time schedule'!JR78","v":0},{"$f":"'K20 - time schedule'!JS78","v":0},{"$f":"'K20 - time schedule'!JT78","v":0},{"$f":"'K20 - time schedule'!JU78","v":0},{"$f":"'K20 - time schedule'!JV78","v":0},{"$f":"'K20 - time schedule'!JW78","v":0},{"$f":"'K20 - time schedule'!JX78","v":0},{"$f":"'K20 - time schedule'!JY78","v":0},{"$f":"'K20 - time schedule'!JZ78","v":0},{"$f":"'K20 - time schedule'!KA78","v":0},{"$f":"'K20 - time schedule'!KB78","v":0},{"$f":"'K20 - time schedule'!KC78","v":0},{"$f":"'K20 - time schedule'!KD78","v":0},{"$f":"'K20 - time schedule'!KE78","v":0},{"$f":"'K20 - time schedule'!KF78","v":0},{"$f":"'K20 - time schedule'!KG78","v":0},{"$f":"'K20 - time schedule'!KH78","v":0},{"$f":"'K20 - time schedule'!KI78","v":0},{"$f":"'K20 - time schedule'!KJ78","v":0},{"$f":"'K20 - time schedule'!KK78","v":0},{"$f":"'K20 - time schedule'!KL78","v":0},{"$f":"'K20 - time schedule'!KM78","v":0},{"$f":"'K20 - time schedule'!KN78","v":0},{"$f":"'K20 - time schedule'!KO78","v":0},{"$f":"'K20 - time schedule'!KP78","v":0},{"$f":"'K20 - time schedule'!KQ78","v":0},{"$f":"'K20 - time schedule'!KR78","v":0},{"$f":"'K20 - time schedule'!KS78","v":0},{"$f":"'K20 - time schedule'!KT78","v":0}]
["Boiler room K90 - operating staff training","K90","EUR",{"$f":"'K90 - time schedule'!G51","v":0},{"$f":"'K90 - time schedule'!H51","v":0},{"$f":"'K90 - time schedule'!I51","v":0},{"$f":"'K90 - time schedule'!J51","v":0},{"$f":"'K90 - time schedule'!K51","v":0},{"$f":"'K90 - time schedule'!L51","v":0},{"$f":"'K90 - time schedule'!M51","v":0},{"$f":"'K90 - time schedule'!N51","v":0},{"$f":"'K90 - time schedule'!O51","v":0},{"$f":"'K90 - time schedule'!P51","v":0},{"$f":"'K90 - time schedule'!Q51","v":0},{"$f":"'K90 - time schedule'!R51","v":0},{"$f":"'K90 - time schedule'!S51","v":0},{"$f":"'K90 - time schedule'!T51","v":0},{"$f":"'K90 - time schedule'!U51","v":0},{"$f":"'K90 - time schedule'!V51","v":0},{"$f":"'K90 - time schedule'!W51","v":0},{"$f":"'K90 - time schedule'!X51","v":0},{"$f":"'K90 - time schedule'!Y51","v":0},{"$f":"'K90 - time schedule'!Z51","v":0},{"$f":"'K90 - time schedule'!AA51","v":0},{"$f":"'K90 - time schedule'!AB51","v":0},{"$f":"'K90 - time schedule'!AC51","v":0},{"$f":"'K90 - time schedule'!AD51","v":0},{"$f":"'K90 - time schedule'!AE51","v":0},{"$f":"'K90 - time schedule'!AF51","v":0},{"$f":"'K90 - time schedule'!AG51","v":0},{"$f":"'K90 - time schedule'!AH51","v":0},{"$f":"'K90 - time schedule'!AI51","v":0},{"$f":"'K90 - time schedule'!AJ51","v":0},{"$f":"'K90 - time schedule'!AK51","v":0},{"$f":"'K90 - time schedule'!AL51","v":0},{"$f":"'K90 - time schedule'!AM51","v":0},{"$f":"'K90 - time schedule'!AN51","v":0},{"$f":"'K90 - time schedule'!AO51","v":0},{"$f":"'K90 - time schedule'!AP51","v":0},{"$f":"'K90 - time schedule'!AQ51","v":0},{"$f":"'K90 - time schedule'!AR51","v":0},{"$f":"'K90 - time schedule'!AS51","v":0},{"$f":"'K90 - time schedule'!AT51","v":0},{"$f":"'K90 - time schedule'!AU51","v":0},{"$f":"'K90 - time schedule'!AV51","v":0},{"$f":"'K90 - time schedule'!AW51","v":0},{"$f":"'K90 - time schedule'!AX51","v":0},{"$f":"'K90 - time schedule'!AY51","v":0},{"$f":"'K90 - time schedule'!AZ51","v":0},{"$f":"'K90 - time schedule'!BA51","v":0},{"$f":"'K90 - time schedule'!BB51","v":0},{"$f":"'K90 - time schedule'!BC51","v":0},{"$f":"'K90 - time schedule'!BD51","v":0},{"$f":"'K90 - time schedule'!BE51","v":0},{"$f":"'K90 - time schedule'!BF51","v":0},{"$f":"'K90 - time schedule'!BG51","v":0},{"$f":"'K90 - time schedule'!BH51","v":0},{"$f":"'K90 - time schedule'!BI51","v":0},{"$f":"'K90 - time schedule'!BJ51","v":0},{"$f":"'K90 - time schedule'!BK51","v":0},{"$f":"'K90 - time schedule'!BL51","v":0},{"$f":"'K90 - time schedule'!BM51","v":0},{"$f":"'K90 - time schedule'!BN51","v":0},{"$f":"'K90 - time schedule'!BO51","v":0},{"$f":"'K90 - time schedule'!BP51","v":0},{"$f":"'K90 - time schedule'!BQ51","v":0},{"$f":"'K90 - time schedule'!BR51","v":0},{"$f":"'K90 - time schedule'!BS51","v":0},{"$f":"'K90 - time schedule'!BT51","v":0},{"$f":"'K90 - time schedule'!BU51","v":0},{"$f":"'K90 - time schedule'!BV51","v":0},{"$f":"'K90 - time schedule'!BW51","v":0},{"$f":"'K90 - time schedule'!BX51","v":0},{"$f":"'K90 - time schedule'!BY51","v":0},{"$f":"'K90 - time schedule'!BZ51","v":0},{"$f":"'K90 - time schedule'!CA51","v":0},{"$f":"'K90 - time schedule'!CB51","v":0},{"$f":"'K90 - time schedule'!CC51","v":0},{"$f":"'K90 - time schedule'!CD51","v":0},{"$f":"'K90 - time schedule'!CE51","v":0},{"$f":"'K90 - time schedule'!CF51","v":0},{"$f":"'K90 - time schedule'!CG51","v":0},{"$f":"'K90 - time schedule'!CH51","v":0},{"$f":"'K90 - time schedule'!CI51","v":0},{"$f":"'K90 - time schedule'!CJ51","v":0},{"$f":"'K90 - time schedule'!CK51","v":0},{"$f":"'K90 - time schedule'!CL51","v":0},{"$f":"'K90 - time schedule'!CM51","v":0},{"$f":"'K90 - time schedule'!CN51","v":0},{"$f":"'K90 - time schedule'!CO51","v":0},{"$f":"'K90 - time schedule'!CP51","v":0},{"$f":"'K90 - time schedule'!CQ51","v":0},{"$f":"'K90 - time schedule'!CR51","v":0},{"$f":"'K90 - time schedule'!CS51","v":0},{"$f":"'K90 - time schedule'!CT51","v":0},{"$f":"'K90 - time schedule'!CU51","v":0},{"$f":"'K90 - time schedule'!CV51","v":0},{"$f":"'K90 - time schedule'!CW51","v":0},{"$f":"'K90 - time schedule'!CX51","v":0},{"$f":"'K90 - time schedule'!CY51","v":0},{"$f":"'K90 - time schedule'!CZ51","v":0},{"$f":"'K90 - time schedule'!DA51","v":0},{"$f":"'K90 - time schedule'!DB51","v":0},{"$f":"'K90 - time schedule'!DC51","v":0},{"$f":"'K90 - time schedule'!DD51","v":0},{"$f":"'K90 - time schedule'!DE51","v":0},{"$f":"'K90 - time schedule'!DF51","v":0},{"$f":"'K90 - time schedule'!DG51","v":0},{"$f":"'K90 - time schedule'!DH51","v":0},{"$f":"'K90 - time schedule'!DI51","v":0},{"$f":"'K90 - time schedule'!DJ51","v":0},{"$f":"'K90 - time schedule'!DK51","v":0},{"$f":"'K90 - time schedule'!DL51","v":0},{"$f":"'K90 - time schedule'!DM51","v":0},{"$f":"'K90 - time schedule'!DN51","v":0},{"$f":"'K90 - time schedule'!DO51","v":0},{"$f":"'K90 - time schedule'!DP51","v":0},{"$f":"'K90 - time schedule'!DQ51","v":0},{"$f":"'K90 - time schedule'!DR51","v":0},{"$f":"'K90 - time schedule'!DS51","v":0},{"$f":"'K90 - time schedule'!DT51","v":0},{"$f":"'K90 - time schedule'!DU51","v":0},{"$f":"'K90 - time schedule'!DV51","v":0},{"$f":"'K90 - time schedule'!DW51","v":0},{"$f":"'K90 - time schedule'!DX51","v":0},{"$f":"'K90 - time schedule'!DY51","v":0},{"$f":"'K90 - time schedule'!DZ51","v":0},{"$f":"'K90 - time schedule'!EA51","v":0},{"$f":"'K90 - time schedule'!EB51","v":0},{"$f":"'K90 - time schedule'!EC51","v":0},{"$f":"'K90 - time schedule'!ED51","v":0},{"$f":"'K90 - time schedule'!EE51","v":0},{"$f":"'K90 - time schedule'!EF51","v":0},{"$f":"'K90 - time schedule'!EG51","v":0},{"$f":"'K90 - time schedule'!EH51","v":0},{"$f":"'K90 - time schedule'!EI51","v":0},{"$f":"'K90 - time schedule'!EJ51","v":0},{"$f":"'K90 - time schedule'!EK51","v":0},{"$f":"'K90 - time schedule'!EL51","v":0},{"$f":"'K90 - time schedule'!EM51","v":0},{"$f":"'K90 - time schedule'!EN51","v":0},{"$f":"'K90 - time schedule'!EO51","v":0},{"$f":"'K90 - time schedule'!EP51","v":0},{"$f":"'K90 - time schedule'!EQ51","v":0},{"$f":"'K90 - time schedule'!ER51","v":0},{"$f":"'K90 - time schedule'!ES51","v":0},{"$f":"'K90 - time schedule'!ET51","v":0},{"$f":"'K90 - time schedule'!EU51","v":0},{"$f":"'K90 - time schedule'!EV51","v":0},{"$f":"'K90 - time schedule'!EW51","v":0},{"$f":"'K90 - time schedule'!EX51","v":0},{"$f":"'K90 - time schedule'!EY51","v":0},{"$f":"'K90 - time schedule'!EZ51","v":0},{"$f":"'K90 - time schedule'!FA51","v":0},{"$f":"'K90 - time schedule'!FB51","v":0},{"$f":"'K90 - time schedule'!FC51","v":0},{"$f":"'K90 - time schedule'!FD51","v":0},{"$f":"'K90 - time schedule'!FE51","v":0},{"$f":"'K90 - time schedule'!FF51","v":0},{"$f":"'K90 - time schedule'!FG51","v":0},{"$f":"'K90 - time schedule'!FH51","v":0},{"$f":"'K90 - time schedule'!FI51","v":0},{"$f":"'K90 - time schedule'!FJ51","v":0},{"$f":"'K90 - time schedule'!FK51","v":0},{"$f":"'K90 - time schedule'!FL51","v":0},{"$f":"'K90 - time schedule'!FM51","v":0},{"$f":"'K90 - time schedule'!FN51","v":0},{"$f":"'K90 - time schedule'!FO51","v":0},{"$f":"'K90 - time schedule'!FP51","v":0},{"$f":"'K90 - time schedule'!FQ51","v":0},{"$f":"'K90 - time schedule'!FR51","v":0},{"$f":"'K90 - time schedule'!FS51","v":0},{"$f":"'K90 - time schedule'!FT51","v":0},{"$f":"'K90 - time schedule'!FU51","v":0},{"$f":"'K90 - time schedule'!FV51","v":0},{"$f":"'K90 - time schedule'!FW51","v":0},{"$f":"'K90 - time schedule'!FX51","v":0},{"$f":"'K90 - time schedule'!FY51","v":0},{"$f":"'K90 - time schedule'!FZ51","v":0},{"$f":"'K90 - time schedule'!GA51","v":0},{"$f":"'K90 - time schedule'!GB51","v":0},{"$f":"'K90 - time schedule'!GC51","v":0},{"$f":"'K90 - time schedule'!GD51","v":0},{"$f":"'K90 - time schedule'!GE51","v":0},{"$f":"'K90 - time schedule'!GF51","v":0},{"$f":"'K20 - time schedule'!GG79","v":0},{"$f":"'K20 - time schedule'!GH79","v":0},{"$f":"'K20 - time schedule'!GI79","v":0},{"$f":"'K20 - time schedule'!GJ79","v":0},{"$f":"'K20 - time schedule'!GK79","v":0},{"$f":"'K20 - time schedule'!GL79","v":0},{"$f":"'K20 - time schedule'!GM79","v":0},{"$f":"'K20 - time schedule'!GN79","v":0},{"$f":"'K20 - time schedule'!GO79","v":0},{"$f":"'K20 - time schedule'!GP79","v":0},{"$f":"'K20 - time schedule'!GQ79","v":0},{"$f":"'K20 - time schedule'!GR79","v":0},{"$f":"'K20 - time schedule'!GS79","v":0},{"$f":"'K20 - time schedule'!GT79","v":0},{"$f":"'K20 - time schedule'!GU79","v":0},{"$f":"'K20 - time schedule'!GV79","v":0},{"$f":"'K20 - time schedule'!GW79","v":0},{"$f":"'K20 - time schedule'!GX79","v":0},{"$f":"'K20 - time schedule'!GY79","v":0},{"$f":"'K20 - time schedule'!GZ79","v":0},{"$f":"'K20 - time schedule'!HA79","v":0},{"$f":"'K20 - time schedule'!HB79","v":0},{"$f":"'K20 - time schedule'!HC79","v":0},{"$f":"'K20 - time schedule'!HD79","v":0},{"$f":"'K20 - time schedule'!HE79","v":0},{"$f":"'K20 - time schedule'!HF79","v":0},{"$f":"'K20 - time schedule'!HG79","v":0},{"$f":"'K20 - time schedule'!HH79","v":0},{"$f":"'K20 - time schedule'!HI79","v":0},{"$f":"'K20 - time schedule'!HJ79","v":0},{"$f":"'K20 - time schedule'!HK79","v":0},{"$f":"'K20 - time schedule'!HL79","v":0},{"$f":"'K20 - time schedule'!HM79","v":0},{"$f":"'K20 - time schedule'!HN79","v":0},{"$f":"'K20 - time schedule'!HO79","v":0},{"$f":"'K20 - time schedule'!HP79","v":0},{"$f":"'K20 - time schedule'!HQ79","v":0},{"$f":"'K20 - time schedule'!HR79","v":0},{"$f":"'K20 - time schedule'!HS79","v":0},{"$f":"'K20 - time schedule'!HT79","v":0},{"$f":"'K20 - time schedule'!HU79","v":0},{"$f":"'K20 - time schedule'!HV79","v":0},{"$f":"'K20 - time schedule'!HW79","v":0},{"$f":"'K20 - time schedule'!HX79","v":0},{"$f":"'K20 - time schedule'!HY79","v":0},{"$f":"'K20 - time schedule'!HZ79","v":0},{"$f":"'K20 - time schedule'!IA79","v":0},{"$f":"'K20 - time schedule'!IB79","v":0},{"$f":"'K20 - time schedule'!IC79","v":0},{"$f":"'K20 - time schedule'!ID79","v":0},{"$f":"'K20 - time schedule'!IE79","v":0},{"$f":"'K20 - time schedule'!IF79","v":0},{"$f":"'K20 - time schedule'!IG79","v":0},{"$f":"'K20 - time schedule'!IH79","v":0},{"$f":"'K20 - time schedule'!II79","v":0},{"$f":"'K20 - time schedule'!IJ79","v":0},{"$f":"'K20 - time schedule'!IK79","v":0},{"$f":"'K20 - time schedule'!IL79","v":0},{"$f":"'K20 - time schedule'!IM79","v":0},{"$f":"'K20 - time schedule'!IN79","v":0},{"$f":"'K20 - time schedule'!IO79","v":0},{"$f":"'K20 - time schedule'!IP79","v":0},{"$f":"'K20 - time schedule'!IQ79","v":0},{"$f":"'K20 - time schedule'!IR79","v":0},{"$f":"'K20 - time schedule'!IS79","v":0},{"$f":"'K20 - time schedule'!IT79","v":0},{"$f":"'K20 - time schedule'!IU79","v":0},{"$f":"'K20 - time schedule'!IV79","v":0},{"$f":"'K20 - time schedule'!IW79","v":0},{"$f":"'K20 - time schedule'!IX79","v":0},{"$f":"'K20 - time schedule'!IY79","v":0},{"$f":"'K20 - time schedule'!IZ79","v":0},{"$f":"'K20 - time schedule'!JA79","v":0},{"$f":"'K20 - time schedule'!JB79","v":0},{"$f":"'K20 - time schedule'!JC79","v":0},{"$f":"'K20 - time schedule'!JD79","v":0},{"$f":"'K20 - time schedule'!JE79","v":0},{"$f":"'K20 - time schedule'!JF79","v":0},{"$f":"'K20 - time schedule'!JG79","v":0},{"$f":"'K20 - time schedule'!JH79","v":0},{"$f":"'K20 - time schedule'!JI79","v":0},{"$f":"'K20 - time schedule'!JJ79","v":0},{"$f":"'K20 - time schedule'!JK79","v":0},{"$f":"'K20 - time schedule'!JL79","v":0},{"$f":"'K20 - time schedule'!JM79","v":0},{"$f":"'K20 - time schedule'!JN79","v":0},{"$f":"'K20 - time schedule'!JO79","v":0},{"$f":"'K20 - time schedule'!JP79","v":0},{"$f":"'K20 - time schedule'!JQ79","v":0},{"$f":"'K20 - time schedule'!JR79","v":0},{"$f":"'K20 - time schedule'!JS79","v":0},{"$f":"'K20 - time schedule'!JT79","v":0},{"$f":"'K20 - time schedule'!JU79","v":0},{"$f":"'K20 - time schedule'!JV79","v":0},{"$f":"'K20 - time schedule'!JW79","v":0},{"$f":"'K20 - time schedule'!JX79","v":0},{"$f":"'K20 - time schedule'!JY79","v":0},{"$f":"'K20 - time schedule'!JZ79","v":0},{"$f":"'K20 - time schedule'!KA79","v":0},{"$f":"'K20 - time schedule'!KB79","v":0},{"$f":"'K20 - time schedule'!KC79","v":0},{"$f":"'K20 - time schedule'!KD79","v":0},{"$f":"'K20 - time schedule'!KE79","v":0},{"$f":"'K20 - time schedule'!KF79","v":0},{"$f":"'K20 - time schedule'!KG79","v":0},{"$f":"'K20 - time schedule'!KH79","v":0},{"$f":"'K20 - time schedule'!KI79","v":0},{"$f":"'K20 - time schedule'!KJ79","v":0},{"$f":"'K20 - time schedule'!KK79","v":0},{"$f":"'K20 - time schedule'!KL79","v":0},{"$f":"'K20 - time schedule'!KM79","v":0},{"$f":"'K20 - time schedule'!KN79","v":0},{"$f":"'K20 - time schedule'!KO79","v":0},{"$f":"'K20 - time schedule'!KP79","v":0},{"$f":"'K20 - time schedule'!KQ79","v":0},{"$f":"'K20 - time schedule'!KR79","v":0},{"$f":"'K20 - time schedule'!KS79","v":0},{"$f":"'K20 - time schedule'!KT79","v":0}]
["Boiler room K90 - comprehensive testing","K90","EUR",{"$f":"'K90 - time schedule'!G54","v":0},{"$f":"'K90 - time schedule'!H54","v":0},{"$f":"'K90 - time schedule'!I54","v":0},{"$f":"'K90 - time schedule'!J54","v":0},{"$f":"'K90 - time schedule'!K54","v":0},{"$f":"'K90 - time schedule'!L54","v":0},{"$f":"'K90 - time schedule'!M54","v":0},{"$f":"'K90 - time schedule'!N54","v":0},{"$f":"'K90 - time schedule'!O54","v":0},{"$f":"'K90 - time schedule'!P54","v":0},{"$f":"'K90 - time schedule'!Q54","v":0},{"$f":"'K90 - time schedule'!R54","v":0},{"$f":"'K90 - time schedule'!S54","v":0},{"$f":"'K90 - time schedule'!T54","v":0},{"$f":"'K90 - time schedule'!U54","v":0},{"$f":"'K90 - time schedule'!V54","v":0},{"$f":"'K90 - time schedule'!W54","v":0},{"$f":"'K90 - time schedule'!X54","v":0},{"$f":"'K90 - time schedule'!Y54","v":0},{"$f":"'K90 - time schedule'!Z54","v":0},{"$f":"'K90 - time schedule'!AA54","v":0},{"$f":"'K90 - time schedule'!AB54","v":0},{"$f":"'K90 - time schedule'!AC54","v":0},{"$f":"'K90 - time schedule'!AD54","v":0},{"$f":"'K90 - time schedule'!AE54","v":0},{"$f":"'K90 - time schedule'!AF54","v":0},{"$f":"'K90 - time schedule'!AG54","v":0},{"$f":"'K90 - time schedule'!AH54","v":0},{"$f":"'K90 - time schedule'!AI54","v":0},{"$f":"'K90 - time schedule'!AJ54","v":0},{"$f":"'K90 - time schedule'!AK54","v":0},{"$f":"'K90 - time schedule'!AL54","v":0},{"$f":"'K90 - time schedule'!AM54","v":0},{"$f":"'K90 - time schedule'!AN54","v":0},{"$f":"'K90 - time schedule'!AO54","v":0},{"$f":"'K90 - time schedule'!AP54","v":0},{"$f":"'K90 - time schedule'!AQ54","v":0},{"$f":"'K90 - time schedule'!AR54","v":0},{"$f":"'K90 - time schedule'!AS54","v":0},{"$f":"'K90 - time schedule'!AT54","v":0},{"$f":"'K90 - time schedule'!AU54","v":0},{"$f":"'K90 - time schedule'!AV54","v":0},{"$f":"'K90 - time schedule'!AW54","v":0},{"$f":"'K90 - time schedule'!AX54","v":0},{"$f":"'K90 - time schedule'!AY54","v":0},{"$f":"'K90 - time schedule'!AZ54","v":0},{"$f":"'K90 - time schedule'!BA54","v":0},{"$f":"'K90 - time schedule'!BB54","v":0},{"$f":"'K90 - time schedule'!BC54","v":0},{"$f":"'K90 - time schedule'!BD54","v":0},{"$f":"'K90 - time schedule'!BE54","v":0},{"$f":"'K90 - time schedule'!BF54","v":0},{"$f":"'K90 - time schedule'!BG54","v":0},{"$f":"'K90 - time schedule'!BH54","v":0},{"$f":"'K90 - time schedule'!BI54","v":0},{"$f":"'K90 - time schedule'!BJ54","v":0},{"$f":"'K90 - time schedule'!BK54","v":0},{"$f":"'K90 - time schedule'!BL54","v":0},{"$f":"'K90 - time schedule'!BM54","v":0},{"$f":"'K90 - time schedule'!BN54","v":0},{"$f":"'K90 - time schedule'!BO54","v":0},{"$f":"'K90 - time schedule'!BP54","v":0},{"$f":"'K90 - time schedule'!BQ54","v":0},{"$f":"'K90 - time schedule'!BR54","v":0},{"$f":"'K90 - time schedule'!BS54","v":0},{"$f":"'K90 - time schedule'!BT54","v":0},{"$f":"'K90 - time schedule'!BU54","v":0},{"$f":"'K90 - time schedule'!BV54","v":0},{"$f":"'K90 - time schedule'!BW54","v":0},{"$f":"'K90 - time schedule'!BX54","v":0},{"$f":"'K90 - time schedule'!BY54","v":0},{"$f":"'K90 - time schedule'!BZ54","v":0},{"$f":"'K90 - time schedule'!CA54","v":0},{"$f":"'K90 - time schedule'!CB54","v":0},{"$f":"'K90 - time schedule'!CC54","v":0},{"$f":"'K90 - time schedule'!CD54","v":0},{"$f":"'K90 - time schedule'!CE54","v":0},{"$f":"'K90 - time schedule'!CF54","v":0},{"$f":"'K90 - time schedule'!CG54","v":0},{"$f":"'K90 - time schedule'!CH54","v":0},{"$f":"'K90 - time schedule'!CI54","v":0},{"$f":"'K90 - time schedule'!CJ54","v":0},{"$f":"'K90 - time schedule'!CK54","v":0},{"$f":"'K90 - time schedule'!CL54","v":0},{"$f":"'K90 - time schedule'!CM54","v":0},{"$f":"'K90 - time schedule'!CN54","v":0},{"$f":"'K90 - time schedule'!CO54","v":0},{"$f":"'K90 - time schedule'!CP54","v":0},{"$f":"'K90 - time schedule'!CQ54","v":0},{"$f":"'K90 - time schedule'!CR54","v":0},{"$f":"'K90 - time schedule'!CS54","v":0},{"$f":"'K90 - time schedule'!CT54","v":0},{"$f":"'K90 - time schedule'!CU54","v":0},{"$f":"'K90 - time schedule'!CV54","v":0},{"$f":"'K90 - time schedule'!CW54","v":0},{"$f":"'K90 - time schedule'!CX54","v":0},{"$f":"'K90 - time schedule'!CY54","v":0},{"$f":"'K90 - time schedule'!CZ54","v":0},{"$f":"'K90 - time schedule'!DA54","v":0},{"$f":"'K90 - time schedule'!DB54","v":0},{"$f":"'K90 - time schedule'!DC54","v":0},{"$f":"'K90 - time schedule'!DD54","v":0},{"$f":"'K90 - time schedule'!DE54","v":0},{"$f":"'K90 - time schedule'!DF54","v":0},{"$f":"'K90 - time schedule'!DG54","v":0},{"$f":"'K90 - time schedule'!DH54","v":0},{"$f":"'K90 - time schedule'!DI54","v":0},{"$f":"'K90 - time schedule'!DJ54","v":0},{"$f":"'K90 - time schedule'!DK54","v":0},{"$f":"'K90 - time schedule'!DL54","v":0},{"$f":"'K90 - time schedule'!DM54","v":0},{"$f":"'K90 - time schedule'!DN54","v":0},{"$f":"'K90 - time schedule'!DO54","v":0},{"$f":"'K90 - time schedule'!DP54","v":0},{"$f":"'K90 - time schedule'!DQ54","v":0},{"$f":"'K90 - time schedule'!DR54","v":0},{"$f":"'K90 - time schedule'!DS54","v":0},{"$f":"'K90 - time schedule'!DT54","v":0},{"$f":"'K90 - time schedule'!DU54","v":0},{"$f":"'K90 - time schedule'!DV54","v":0},{"$f":"'K90 - time schedule'!DW54","v":0},{"$f":"'K90 - time schedule'!DX54","v":0},{"$f":"'K90 - time schedule'!DY54","v":0},{"$f":"'K90 - time schedule'!DZ54","v":0},{"$f":"'K90 - time schedule'!EA54","v":0},{"$f":"'K90 - time schedule'!EB54","v":0},{"$f":"'K90 - time schedule'!EC54","v":0},{"$f":"'K90 - time schedule'!ED54","v":0},{"$f":"'K90 - time schedule'!EE54","v":0},{"$f":"'K90 - time schedule'!EF54","v":0},{"$f":"'K90 - time schedule'!EG54","v":0},{"$f":"'K90 - time schedule'!EH54","v":0},{"$f":"'K90 - time schedule'!EI54","v":0},{"$f":"'K90 - time schedule'!EJ54","v":0},{"$f":"'K90 - time schedule'!EK54","v":0},{"$f":"'K90 - time schedule'!EL54","v":0},{"$f":"'K90 - time schedule'!EM54","v":0},{"$f":"'K90 - time schedule'!EN54","v":0},{"$f":"'K90 - time schedule'!EO54","v":0},{"$f":"'K90 - time schedule'!EP54","v":0},{"$f":"'K90 - time schedule'!EQ54","v":0},{"$f":"'K90 - time schedule'!ER54","v":0},{"$f":"'K90 - time schedule'!ES54","v":0},{"$f":"'K90 - time schedule'!ET54","v":0},{"$f":"'K90 - time schedule'!EU54","v":0},{"$f":"'K90 - time schedule'!EV54","v":0},{"$f":"'K90 - time schedule'!EW54","v":0},{"$f":"'K90 - time schedule'!EX54","v":0},{"$f":"'K90 - time schedule'!EY54","v":0},{"$f":"'K90 - time schedule'!EZ54","v":0},{"$f":"'K90 - time schedule'!FA54","v":0},{"$f":"'K90 - time schedule'!FB54","v":0},{"$f":"'K90 - time schedule'!FC54","v":0},{"$f":"'K90 - time schedule'!FD54","v":0},{"$f":"'K90 - time schedule'!FE54","v":0},{"$f":"'K90 - time schedule'!FF54","v":0},{"$f":"'K90 - time schedule'!FG54","v":0},{"$f":"'K90 - time schedule'!FH54","v":0},{"$f":"'K90 - time schedule'!FI54","v":0},{"$f":"'K90 - time schedule'!FJ54","v":0},{"$f":"'K90 - time schedule'!FK54","v":0},{"$f":"'K90 - time schedule'!FL54","v":0},{"$f":"'K90 - time schedule'!FM54","v":0},{"$f":"'K90 - time schedule'!FN54","v":0},{"$f":"'K90 - time schedule'!FO54","v":0},{"$f":"'K90 - time schedule'!FP54","v":0},{"$f":"'K90 - time schedule'!FQ54","v":0},{"$f":"'K90 - time schedule'!FR54","v":0},{"$f":"'K90 - time schedule'!FS54","v":0},{"$f":"'K90 - time schedule'!FT54","v":0},{"$f":"'K90 - time schedule'!FU54","v":0},{"$f":"'K90 - time schedule'!FV54","v":0},{"$f":"'K90 - time schedule'!FW54","v":0},{"$f":"'K90 - time schedule'!FX54","v":0},{"$f":"'K90 - time schedule'!FY54","v":0},{"$f":"'K90 - time schedule'!FZ54","v":0},{"$f":"'K90 - time schedule'!GA54","v":0},{"$f":"'K90 - time schedule'!GB54","v":0},{"$f":"'K90 - time schedule'!GC54","v":0},{"$f":"'K90 - time schedule'!GD54","v":0},{"$f":"'K90 - time schedule'!GE54","v":0},{"$f":"'K90 - time schedule'!GF54","v":0},{"$f":"'K20 - time schedule'!GG80","v":0},{"$f":"'K20 - time schedule'!GH80","v":0},{"$f":"'K20 - time schedule'!GI80","v":0},{"$f":"'K20 - time schedule'!GJ80","v":0},{"$f":"'K20 - time schedule'!GK80","v":0},{"$f":"'K20 - time schedule'!GL80","v":0},{"$f":"'K20 - time schedule'!GM80","v":0},{"$f":"'K20 - time schedule'!GN80","v":0},{"$f":"'K20 - time schedule'!GO80","v":0},{"$f":"'K20 - time schedule'!GP80","v":0},{"$f":"'K20 - time schedule'!GQ80","v":0},{"$f":"'K20 - time schedule'!GR80","v":0},{"$f":"'K20 - time schedule'!GS80","v":0},{"$f":"'K20 - time schedule'!GT80","v":0},{"$f":"'K20 - time schedule'!GU80","v":0},{"$f":"'K20 - time schedule'!GV80","v":0},{"$f":"'K20 - time schedule'!GW80","v":0},{"$f":"'K20 - time schedule'!GX80","v":0},{"$f":"'K20 - time schedule'!GY80","v":0},{"$f":"'K20 - time schedule'!GZ80","v":0},{"$f":"'K20 - time schedule'!HA80","v":0},{"$f":"'K20 - time schedule'!HB80","v":0},{"$f":"'K20 - time schedule'!HC80","v":0},{"$f":"'K20 - time schedule'!HD80","v":0},{"$f":"'K20 - time schedule'!HE80","v":0},{"$f":"'K20 - time schedule'!HF80","v":0},{"$f":"'K20 - time schedule'!HG80","v":0},{"$f":"'K20 - time schedule'!HH80","v":0},{"$f":"'K20 - time schedule'!HI80","v":0},{"$f":"'K20 - time schedule'!HJ80","v":0},{"$f":"'K20 - time schedule'!HK80","v":0},{"$f":"'K20 - time schedule'!HL80","v":0},{"$f":"'K20 - time schedule'!HM80","v":0},{"$f":"'K20 - time schedule'!HN80","v":0},{"$f":"'K20 - time schedule'!HO80","v":0},{"$f":"'K20 - time schedule'!HP80","v":0},{"$f":"'K20 - time schedule'!HQ80","v":0},{"$f":"'K20 - time schedule'!HR80","v":0},{"$f":"'K20 - time schedule'!HS80","v":0},{"$f":"'K20 - time schedule'!HT80","v":0},{"$f":"'K20 - time schedule'!HU80","v":0},{"$f":"'K20 - time schedule'!HV80","v":0},{"$f":"'K20 - time schedule'!HW80","v":0},{"$f":"'K20 - time schedule'!HX80","v":0},{"$f":"'K20 - time schedule'!HY80","v":0},{"$f":"'K20 - time schedule'!HZ80","v":0},{"$f":"'K20 - time schedule'!IA80","v":0},{"$f":"'K20 - time schedule'!IB80","v":0},{"$f":"'K20 - time schedule'!IC80","v":0},{"$f":"'K20 - time schedule'!ID80","v":0},{"$f":"'K20 - time schedule'!IE80","v":0},{"$f":"'K20 - time schedule'!IF80","v":0},{"$f":"'K20 - time schedule'!IG80","v":0},{"$f":"'K20 - time schedule'!IH80","v":0},{"$f":"'K20 - time schedule'!II80","v":0},{"$f":"'K20 - time schedule'!IJ80","v":0},{"$f":"'K20 - time schedule'!IK80","v":0},{"$f":"'K20 - time schedule'!IL80","v":0},{"$f":"'K20 - time schedule'!IM80","v":0},{"$f":"'K20 - time schedule'!IN80","v":0},{"$f":"'K20 - time schedule'!IO80","v":0},{"$f":"'K20 - time schedule'!IP80","v":0},{"$f":"'K20 - time schedule'!IQ80","v":0},{"$f":"'K20 - time schedule'!IR80","v":0},{"$f":"'K20 - time schedule'!IS80","v":0},{"$f":"'K20 - time schedule'!IT80","v":0},{"$f":"'K20 - time schedule'!IU80","v":0},{"$f":"'K20 - time schedule'!IV80","v":0},{"$f":"'K20 - time schedule'!IW80","v":0},{"$f":"'K20 - time schedule'!IX80","v":0},{"$f":"'K20 - time schedule'!IY80","v":0},{"$f":"'K20 - time schedule'!IZ80","v":0},{"$f":"'K20 - time schedule'!JA80","v":0},{"$f":"'K20 - time schedule'!JB80","v":0},{"$f":"'K20 - time schedule'!JC80","v":0},{"$f":"'K20 - time schedule'!JD80","v":0},{"$f":"'K20 - time schedule'!JE80","v":0},{"$f":"'K20 - time schedule'!JF80","v":0},{"$f":"'K20 - time schedule'!JG80","v":0},{"$f":"'K20 - time schedule'!JH80","v":0},{"$f":"'K20 - time schedule'!JI80","v":0},{"$f":"'K20 - time schedule'!JJ80","v":0},{"$f":"'K20 - time schedule'!JK80","v":0},{"$f":"'K20 - time schedule'!JL80","v":0},{"$f":"'K20 - time schedule'!JM80","v":0},{"$f":"'K20 - time schedule'!JN80","v":0},{"$f":"'K20 - time schedule'!JO80","v":0},{"$f":"'K20 - time schedule'!JP80","v":0},{"$f":"'K20 - time schedule'!JQ80","v":0},{"$f":"'K20 - time schedule'!JR80","v":0},{"$f":"'K20 - time schedule'!JS80","v":0},{"$f":"'K20 - time schedule'!JT80","v":0},{"$f":"'K20 - time schedule'!JU80","v":0},{"$f":"'K20 - time schedule'!JV80","v":0},{"$f":"'K20 - time schedule'!JW80","v":0},{"$f":"'K20 - time schedule'!JX80","v":0},{"$f":"'K20 - time schedule'!JY80","v":0},{"$f":"'K20 - time schedule'!JZ80","v":0},{"$f":"'K20 - time schedule'!KA80","v":0},{"$f":"'K20 - time schedule'!KB80","v":0},{"$f":"'K20 - time schedule'!KC80","v":0},{"$f":"'K20 - time schedule'!KD80","v":0},{"$f":"'K20 - time schedule'!KE80","v":0},{"$f":"'K20 - time schedule'!KF80","v":0},{"$f":"'K20 - time schedule'!KG80","v":0},{"$f":"'K20 - time schedule'!KH80","v":0},{"$f":"'K20 - time schedule'!KI80","v":0},{"$f":"'K20 - time schedule'!KJ80","v":0},{"$f":"'K20 - time schedule'!KK80","v":0},{"$f":"'K20 - time schedule'!KL80","v":0},{"$f":"'K20 - time schedule'!KM80","v":0},{"$f":"'K20 - time schedule'!KN80","v":0},{"$f":"'K20 - time schedule'!KO80","v":0},{"$f":"'K20 - time schedule'!KP80","v":0},{"$f":"'K20 - time schedule'!KQ80","v":0},{"$f":"'K20 - time schedule'!KR80","v":0},{"$f":"'K20 - time schedule'!KS80","v":0},{"$f":"'K20 - time schedule'!KT80","v":0}]
["Boiler room K90 - trial operation","K90","EUR",{"$f":"'K90 - time schedule'!G56","v":0},{"$f":"'K90 - time schedule'!H56","v":0},{"$f":"'K90 - time schedule'!I56","v":0},{"$f":"'K90 - time schedule'!J56","v":0},{"$f":"'K90 - time schedule'!K56","v":0},{"$f":"'K90 - time schedule'!L56","v":0},{"$f":"'K90 - time schedule'!M56","v":0},{"$f":"'K90 - time schedule'!N56","v":0},{"$f":"'K90 - time schedule'!O56","v":0},{"$f":"'K90 - time schedule'!P56","v":0},{"$f":"'K90 - time schedule'!Q56","v":0},{"$f":"'K90 - time schedule'!R56","v":0},{"$f":"'K90 - time schedule'!S56","v":0},{"$f":"'K90 - time schedule'!T56","v":0},{"$f":"'K90 - time schedule'!U56","v":0},{"$f":"'K90 - time schedule'!V56","v":0},{"$f":"'K90 - time schedule'!W56","v":0},{"$f":"'K90 - time schedule'!X56","v":0},{"$f":"'K90 - time schedule'!Y56","v":0},{"$f":"'K90 - time schedule'!Z56","v":0},{"$f":"'K90 - time schedule'!AA56","v":0},{"$f":"'K90 - time schedule'!AB56","v":0},{"$f":"'K90 - time schedule'!AC56","v":0},{"$f":"'K90 - time schedule'!AD56","v":0},{"$f":"'K90 - time schedule'!AE56","v":0},{"$f":"'K90 - time schedule'!AF56","v":0},{"$f":"'K90 - time schedule'!AG56","v":0},{"$f":"'K90 - time schedule'!AH56","v":0},{"$f":"'K90 - time schedule'!AI56","v":0},{"$f":"'K90 - time schedule'!AJ56","v":0},{"$f":"'K90 - time schedule'!AK56","v":0},{"$f":"'K90 - time schedule'!AL56","v":0},{"$f":"'K90 - time schedule'!AM56","v":0},{"$f":"'K90 - time schedule'!AN56","v":0},{"$f":"'K90 - time schedule'!AO56","v":0},{"$f":"'K90 - time schedule'!AP56","v":0},{"$f":"'K90 - time schedule'!AQ56","v":0},{"$f":"'K90 - time schedule'!AR56","v":0},{"$f":"'K90 - time schedule'!AS56","v":0},{"$f":"'K90 - time schedule'!AT56","v":0},{"$f":"'K90 - time schedule'!AU56","v":0},{"$f":"'K90 - time schedule'!AV56","v":0},{"$f":"'K90 - time schedule'!AW56","v":0},{"$f":"'K90 - time schedule'!AX56","v":0},{"$f":"'K90 - time schedule'!AY56","v":0},{"$f":"'K90 - time schedule'!AZ56","v":0},{"$f":"'K90 - time schedule'!BA56","v":0},{"$f":"'K90 - time schedule'!BB56","v":0},{"$f":"'K90 - time schedule'!BC56","v":0},{"$f":"'K90 - time schedule'!BD56","v":0},{"$f":"'K90 - time schedule'!BE56","v":0},{"$f":"'K90 - time schedule'!BF56","v":0},{"$f":"'K90 - time schedule'!BG56","v":0},{"$f":"'K90 - time schedule'!BH56","v":0},{"$f":"'K90 - time schedule'!BI56","v":0},{"$f":"'K90 - time schedule'!BJ56","v":0},{"$f":"'K90 - time schedule'!BK56","v":0},{"$f":"'K90 - time schedule'!BL56","v":0},{"$f":"'K90 - time schedule'!BM56","v":0},{"$f":"'K90 - time schedule'!BN56","v":0},{"$f":"'K90 - time schedule'!BO56","v":0},{"$f":"'K90 - time schedule'!BP56","v":0},{"$f":"'K90 - time schedule'!BQ56","v":0},{"$f":"'K90 - time schedule'!BR56","v":0},{"$f":"'K90 - time schedule'!BS56","v":0},{"$f":"'K90 - time schedule'!BT56","v":0},{"$f":"'K90 - time schedule'!BU56","v":0},{"$f":"'K90 - time schedule'!BV56","v":0},{"$f":"'K90 - time schedule'!BW56","v":0},{"$f":"'K90 - time schedule'!BX56","v":0},{"$f":"'K90 - time schedule'!BY56","v":0},{"$f":"'K90 - time schedule'!BZ56","v":0},{"$f":"'K90 - time schedule'!CA56","v":0},{"$f":"'K90 - time schedule'!CB56","v":0},{"$f":"'K90 - time schedule'!CC56","v":0},{"$f":"'K90 - time schedule'!CD56","v":0},{"$f":"'K90 - time schedule'!CE56","v":0},{"$f":"'K90 - time schedule'!CF56","v":0},{"$f":"'K90 - time schedule'!CG56","v":0},{"$f":"'K90 - time schedule'!CH56","v":0},{"$f":"'K90 - time schedule'!CI56","v":0},{"$f":"'K90 - time schedule'!CJ56","v":0},{"$f":"'K90 - time schedule'!CK56","v":0},{"$f":"'K90 - time schedule'!CL56","v":0},{"$f":"'K90 - time schedule'!CM56","v":0},{"$f":"'K90 - time schedule'!CN56","v":0},{"$f":"'K90 - time schedule'!CO56","v":0},{"$f":"'K90 - time schedule'!CP56","v":0},{"$f":"'K90 - time schedule'!CQ56","v":0},{"$f":"'K90 - time schedule'!CR56","v":0},{"$f":"'K90 - time schedule'!CS56","v":0},{"$f":"'K90 - time schedule'!CT56","v":0},{"$f":"'K90 - time schedule'!CU56","v":0},{"$f":"'K90 - time schedule'!CV56","v":0},{"$f":"'K90 - time schedule'!CW56","v":0},{"$f":"'K90 - time schedule'!CX56","v":0},{"$f":"'K90 - time schedule'!CY56","v":0},{"$f":"'K90 - time schedule'!CZ56","v":0},{"$f":"'K90 - time schedule'!DA56","v":0},{"$f":"'K90 - time schedule'!DB56","v":0},{"$f":"'K90 - time schedule'!DC56","v":0},{"$f":"'K90 - time schedule'!DD56","v":0},{"$f":"'K90 - time schedule'!DE56","v":0},{"$f":"'K90 - time schedule'!DF56","v":0},{"$f":"'K90 - time schedule'!DG56","v":0},{"$f":"'K90 - time schedule'!DH56","v":0},{"$f":"'K90 - time schedule'!DI56","v":0},{"$f":"'K90 - time schedule'!DJ56","v":0},{"$f":"'K90 - time schedule'!DK56","v":0},{"$f":"'K90 - time schedule'!DL56","v":0},{"$f":"'K90 - time schedule'!DM56","v":0},{"$f":"'K90 - time schedule'!DN56","v":0},{"$f":"'K90 - time schedule'!DO56","v":0},{"$f":"'K90 - time schedule'!DP56","v":0},{"$f":"'K90 - time schedule'!DQ56","v":0},{"$f":"'K90 - time schedule'!DR56","v":0},{"$f":"'K90 - time schedule'!DS56","v":0},{"$f":"'K90 - time schedule'!DT56","v":0},{"$f":"'K90 - time schedule'!DU56","v":0},{"$f":"'K90 - time schedule'!DV56","v":0},{"$f":"'K90 - time schedule'!DW56","v":0},{"$f":"'K90 - time schedule'!DX56","v":0},{"$f":"'K90 - time schedule'!DY56","v":0},{"$f":"'K90 - time schedule'!DZ56","v":0},{"$f":"'K90 - time schedule'!EA56","v":0},{"$f":"'K90 - time schedule'!EB56","v":0},{"$f":"'K90 - time schedule'!EC56","v":0},{"$f":"'K90 - time schedule'!ED56","v":0},{"$f":"'K90 - time schedule'!EE56","v":0},{"$f":"'K90 - time schedule'!EF56","v":0},{"$f":"'K90 - time schedule'!EG56","v":0},{"$f":"'K90 - time schedule'!EH56","v":0},{"$f":"'K90 - time schedule'!EI56","v":0},{"$f":"'K90 - time schedule'!EJ56","v":0},{"$f":"'K90 - time schedule'!EK56","v":0},{"$f":"'K90 - time schedule'!EL56","v":0},{"$f":"'K90 - time schedule'!EM56","v":0},{"$f":"'K90 - time schedule'!EN56","v":0},{"$f":"'K90 - time schedule'!EO56","v":0},{"$f":"'K90 - time schedule'!EP56","v":0},{"$f":"'K90 - time schedule'!EQ56","v":0},{"$f":"'K90 - time schedule'!ER56","v":0},{"$f":"'K90 - time schedule'!ES56","v":0},{"$f":"'K90 - time schedule'!ET56","v":0},{"$f":"'K90 - time schedule'!EU56","v":0},{"$f":"'K90 - time schedule'!EV56","v":0},{"$f":"'K90 - time schedule'!EW56","v":0},{"$f":"'K90 - time schedule'!EX56","v":0},{"$f":"'K90 - time schedule'!EY56","v":0},{"$f":"'K90 - time schedule'!EZ56","v":0},{"$f":"'K90 - time schedule'!FA56","v":0},{"$f":"'K90 - time schedule'!FB56","v":0},{"$f":"'K90 - time schedule'!FC56","v":0},{"$f":"'K90 - time schedule'!FD56","v":0},{"$f":"'K90 - time schedule'!FE56","v":0},{"$f":"'K90 - time schedule'!FF56","v":0},{"$f":"'K90 - time schedule'!FG56","v":0},{"$f":"'K90 - time schedule'!FH56","v":0},{"$f":"'K90 - time schedule'!FI56","v":0},{"$f":"'K90 - time schedule'!FJ56","v":0},{"$f":"'K90 - time schedule'!FK56","v":0},{"$f":"'K90 - time schedule'!FL56","v":0},{"$f":"'K90 - time schedule'!FM56","v":0},{"$f":"'K90 - time schedule'!FN56","v":0},{"$f":"'K90 - time schedule'!FO56","v":0},{"$f":"'K90 - time schedule'!FP56","v":0},{"$f":"'K90 - time schedule'!FQ56","v":0},{"$f":"'K90 - time schedule'!FR56","v":0},{"$f":"'K90 - time schedule'!FS56","v":0},{"$f":"'K90 - time schedule'!FT56","v":0},{"$f":"'K90 - time schedule'!FU56","v":0},{"$f":"'K90 - time schedule'!FV56","v":0},{"$f":"'K90 - time schedule'!FW56","v":0},{"$f":"'K90 - time schedule'!FX56","v":0},{"$f":"'K90 - time schedule'!FY56","v":0},{"$f":"'K90 - time schedule'!FZ56","v":0},{"$f":"'K90 - time schedule'!GA56","v":0},{"$f":"'K90 - time schedule'!GB56","v":0},{"$f":"'K90 - time schedule'!GC56","v":0},{"$f":"'K90 - time schedule'!GD56","v":0},{"$f":"'K90 - time schedule'!GE56","v":0},{"$f":"'K90 - time schedule'!GF56","v":0},{"$f":"'K20 - time schedule'!GG81","v":0},{"$f":"'K20 - time schedule'!GH81","v":0},{"$f":"'K20 - time schedule'!GI81","v":0},{"$f":"'K20 - time schedule'!GJ81","v":0},{"$f":"'K20 - time schedule'!GK81","v":0},{"$f":"'K20 - time schedule'!GL81","v":0},{"$f":"'K20 - time schedule'!GM81","v":0},{"$f":"'K20 - time schedule'!GN81","v":0},{"$f":"'K20 - time schedule'!GO81","v":0},{"$f":"'K20 - time schedule'!GP81","v":0},{"$f":"'K20 - time schedule'!GQ81","v":0},{"$f":"'K20 - time schedule'!GR81","v":0},{"$f":"'K20 - time schedule'!GS81","v":0},{"$f":"'K20 - time schedule'!GT81","v":0},{"$f":"'K20 - time schedule'!GU81","v":0},{"$f":"'K20 - time schedule'!GV81","v":0},{"$f":"'K20 - time schedule'!GW81","v":0},{"$f":"'K20 - time schedule'!GX81","v":0},{"$f":"'K20 - time schedule'!GY81","v":0},{"$f":"'K20 - time schedule'!GZ81","v":0},{"$f":"'K20 - time schedule'!HA81","v":0},{"$f":"'K20 - time schedule'!HB81","v":0},{"$f":"'K20 - time schedule'!HC81","v":0},{"$f":"'K20 - time schedule'!HD81","v":0},{"$f":"'K20 - time schedule'!HE81","v":0},{"$f":"'K20 - time schedule'!HF81","v":0},{"$f":"'K20 - time schedule'!HG81","v":0},{"$f":"'K20 - time schedule'!HH81","v":0},{"$f":"'K20 - time schedule'!HI81","v":0},{"$f":"'K20 - time schedule'!HJ81","v":0},{"$f":"'K20 - time schedule'!HK81","v":0},{"$f":"'K20 - time schedule'!HL81","v":0},{"$f":"'K20 - time schedule'!HM81","v":0},{"$f":"'K20 - time schedule'!HN81","v":0},{"$f":"'K20 - time schedule'!HO81","v":0},{"$f":"'K20 - time schedule'!HP81","v":0},{"$f":"'K20 - time schedule'!HQ81","v":0},{"$f":"'K20 - time schedule'!HR81","v":0},{"$f":"'K20 - time schedule'!HS81","v":0},{"$f":"'K20 - time schedule'!HT81","v":0},{"$f":"'K20 - time schedule'!HU81","v":0},{"$f":"'K20 - time schedule'!HV81","v":0},{"$f":"'K20 - time schedule'!HW81","v":0},{"$f":"'K20 - time schedule'!HX81","v":0},{"$f":"'K20 - time schedule'!HY81","v":0},{"$f":"'K20 - time schedule'!HZ81","v":0},{"$f":"'K20 - time schedule'!IA81","v":0},{"$f":"'K20 - time schedule'!IB81","v":0},{"$f":"'K20 - time schedule'!IC81","v":0},{"$f":"'K20 - time schedule'!ID81","v":0},{"$f":"'K20 - time schedule'!IE81","v":0},{"$f":"'K20 - time schedule'!IF81","v":0},{"$f":"'K20 - time schedule'!IG81","v":0},{"$f":"'K20 - time schedule'!IH81","v":0},{"$f":"'K20 - time schedule'!II81","v":0},{"$f":"'K20 - time schedule'!IJ81","v":0},{"$f":"'K20 - time schedule'!IK81","v":0},{"$f":"'K20 - time schedule'!IL81","v":0},{"$f":"'K20 - time schedule'!IM81","v":0},{"$f":"'K20 - time schedule'!IN81","v":0},{"$f":"'K20 - time schedule'!IO81","v":0},{"$f":"'K20 - time schedule'!IP81","v":0},{"$f":"'K20 - time schedule'!IQ81","v":0},{"$f":"'K20 - time schedule'!IR81","v":0},{"$f":"'K20 - time schedule'!IS81","v":0},{"$f":"'K20 - time schedule'!IT81","v":0},{"$f":"'K20 - time schedule'!IU81","v":0},{"$f":"'K20 - time schedule'!IV81","v":0},{"$f":"'K20 - time schedule'!IW81","v":0},{"$f":"'K20 - time schedule'!IX81","v":0},{"$f":"'K20 - time schedule'!IY81","v":0},{"$f":"'K20 - time schedule'!IZ81","v":0},{"$f":"'K20 - time schedule'!JA81","v":0},{"$f":"'K20 - time schedule'!JB81","v":0},{"$f":"'K20 - time schedule'!JC81","v":0},{"$f":"'K20 - time schedule'!JD81","v":0},{"$f":"'K20 - time schedule'!JE81","v":0},{"$f":"'K20 - time schedule'!JF81","v":0},{"$f":"'K20 - time schedule'!JG81","v":0},{"$f":"'K20 - time schedule'!JH81","v":0},{"$f":"'K20 - time schedule'!JI81","v":0},{"$f":"'K20 - time schedule'!JJ81","v":0},{"$f":"'K20 - time schedule'!JK81","v":0},{"$f":"'K20 - time schedule'!JL81","v":0},{"$f":"'K20 - time schedule'!JM81","v":0},{"$f":"'K20 - time schedule'!JN81","v":0},{"$f":"'K20 - time schedule'!JO81","v":0},{"$f":"'K20 - time schedule'!JP81","v":0},{"$f":"'K20 - time schedule'!JQ81","v":0},{"$f":"'K20 - time schedule'!JR81","v":0},{"$f":"'K20 - time schedule'!JS81","v":0},{"$f":"'K20 - time schedule'!JT81","v":0},{"$f":"'K20 - time schedule'!JU81","v":0},{"$f":"'K20 - time schedule'!JV81","v":0},{"$f":"'K20 - time schedule'!JW81","v":0},{"$f":"'K20 - time schedule'!JX81","v":0},{"$f":"'K20 - time schedule'!JY81","v":0},{"$f":"'K20 - time schedule'!JZ81","v":0},{"$f":"'K20 - time schedule'!KA81","v":0},{"$f":"'K20 - time schedule'!KB81","v":0},{"$f":"'K20 - time schedule'!KC81","v":0},{"$f":"'K20 - time schedule'!KD81","v":0},{"$f":"'K20 - time schedule'!KE81","v":0},{"$f":"'K20 - time schedule'!KF81","v":0},{"$f":"'K20 - time schedule'!KG81","v":0},{"$f":"'K20 - time schedule'!KH81","v":0},{"$f":"'K20 - time schedule'!KI81","v":0},{"$f":"'K20 - time schedule'!KJ81","v":0},{"$f":"'K20 - time schedule'!KK81","v":0},{"$f":"'K20 - time schedule'!KL81","v":0},{"$f":"'K20 - time schedule'!KM81","v":0},{"$f":"'K20 - time schedule'!KN81","v":0},{"$f":"'K20 - time schedule'!KO81","v":0},{"$f":"'K20 - time schedule'!KP81","v":0},{"$f":"'K20 - time schedule'!KQ81","v":0},{"$f":"'K20 - time schedule'!KR81","v":0},{"$f":"'K20 - time schedule'!KS81","v":0},{"$f":"'K20 - time schedule'!KT81","v":0}]
["Boiler room K90 - guarantee test A","K90","EUR",{"$f":"'K90 - time schedule'!G58","v":0},{"$f":"'K90 - time schedule'!H58","v":0},{"$f":"'K90 - time schedule'!I58","v":0},{"$f":"'K90 - time schedule'!J58","v":0},{"$f":"'K90 - time schedule'!K58","v":0},{"$f":"'K90 - time schedule'!L58","v":0},{"$f":"'K90 - time schedule'!M58","v":0},{"$f":"'K90 - time schedule'!N58","v":0},{"$f":"'K90 - time schedule'!O58","v":0},{"$f":"'K90 - time schedule'!P58","v":0},{"$f":"'K90 - time schedule'!Q58","v":0},{"$f":"'K90 - time schedule'!R58","v":0},{"$f":"'K90 - time schedule'!S58","v":0},{"$f":"'K90 - time schedule'!T58","v":0},{"$f":"'K90 - time schedule'!U58","v":0},{"$f":"'K90 - time schedule'!V58","v":0},{"$f":"'K90 - time schedule'!W58","v":0},{"$f":"'K90 - time schedule'!X58","v":0},{"$f":"'K90 - time schedule'!Y58","v":0},{"$f":"'K90 - time schedule'!Z58","v":0},{"$f":"'K90 - time schedule'!AA58","v":0},{"$f":"'K90 - time schedule'!AB58","v":0},{"$f":"'K90 - time schedule'!AC58","v":0},{"$f":"'K90 - time schedule'!AD58","v":0},{"$f":"'K90 - time schedule'!AE58","v":0},{"$f":"'K90 - time schedule'!AF58","v":0},{"$f":"'K90 - time schedule'!AG58","v":0},{"$f":"'K90 - time schedule'!AH58","v":0},{"$f":"'K90 - time schedule'!AI58","v":0},{"$f":"'K90 - time schedule'!AJ58","v":0},{"$f":"'K90 - time schedule'!AK58","v":0},{"$f":"'K90 - time schedule'!AL58","v":0},{"$f":"'K90 - time schedule'!AM58","v":0},{"$f":"'K90 - time schedule'!AN58","v":0},{"$f":"'K90 - time schedule'!AO58","v":0},{"$f":"'K90 - time schedule'!AP58","v":0},{"$f":"'K90 - time schedule'!AQ58","v":0},{"$f":"'K90 - time schedule'!AR58","v":0},{"$f":"'K90 - time schedule'!AS58","v":0},{"$f":"'K90 - time schedule'!AT58","v":0},{"$f":"'K90 - time schedule'!AU58","v":0},{"$f":"'K90 - time schedule'!AV58","v":0},{"$f":"'K90 - time schedule'!AW58","v":0},{"$f":"'K90 - time schedule'!AX58","v":0},{"$f":"'K90 - time schedule'!AY58","v":0},{"$f":"'K90 - time schedule'!AZ58","v":0},{"$f":"'K90 - time schedule'!BA58","v":0},{"$f":"'K90 - time schedule'!BB58","v":0},{"$f":"'K90 - time schedule'!BC58","v":0},{"$f":"'K90 - time schedule'!BD58","v":0},{"$f":"'K90 - time schedule'!BE58","v":0},{"$f":"'K90 - time schedule'!BF58","v":0},{"$f":"'K90 - time schedule'!BG58","v":0},{"$f":"'K90 - time schedule'!BH58","v":0},{"$f":"'K90 - time schedule'!BI58","v":0},{"$f":"'K90 - time schedule'!BJ58","v":0},{"$f":"'K90 - time schedule'!BK58","v":0},{"$f":"'K90 - time schedule'!BL58","v":0},{"$f":"'K90 - time schedule'!BM58","v":0},{"$f":"'K90 - time schedule'!BN58","v":0},{"$f":"'K90 - time schedule'!BO58","v":0},{"$f":"'K90 - time schedule'!BP58","v":0},{"$f":"'K90 - time schedule'!BQ58","v":0},{"$f":"'K90 - time schedule'!BR58","v":0},{"$f":"'K90 - time schedule'!BS58","v":0},{"$f":"'K90 - time schedule'!BT58","v":0},{"$f":"'K90 - time schedule'!BU58","v":0},{"$f":"'K90 - time schedule'!BV58","v":0},{"$f":"'K90 - time schedule'!BW58","v":0},{"$f":"'K90 - time schedule'!BX58","v":0},{"$f":"'K90 - time schedule'!BY58","v":0},{"$f":"'K90 - time schedule'!BZ58","v":0},{"$f":"'K90 - time schedule'!CA58","v":0},{"$f":"'K90 - time schedule'!CB58","v":0},{"$f":"'K90 - time schedule'!CC58","v":0},{"$f":"'K90 - time schedule'!CD58","v":0},{"$f":"'K90 - time schedule'!CE58","v":0},{"$f":"'K90 - time schedule'!CF58","v":0},{"$f":"'K90 - time schedule'!CG58","v":0},{"$f":"'K90 - time schedule'!CH58","v":0},{"$f":"'K90 - time schedule'!CI58","v":0},{"$f":"'K90 - time schedule'!CJ58","v":0},{"$f":"'K90 - time schedule'!CK58","v":0},{"$f":"'K90 - time schedule'!CL58","v":0},{"$f":"'K90 - time schedule'!CM58","v":0},{"$f":"'K90 - time schedule'!CN58","v":0},{"$f":"'K90 - time schedule'!CO58","v":0},{"$f":"'K90 - time schedule'!CP58","v":0},{"$f":"'K90 - time schedule'!CQ58","v":0},{"$f":"'K90 - time schedule'!CR58","v":0},{"$f":"'K90 - time schedule'!CS58","v":0},{"$f":"'K90 - time schedule'!CT58","v":0},{"$f":"'K90 - time schedule'!CU58","v":0},{"$f":"'K90 - time schedule'!CV58","v":0},{"$f":"'K90 - time schedule'!CW58","v":0},{"$f":"'K90 - time schedule'!CX58","v":0},{"$f":"'K90 - time schedule'!CY58","v":0},{"$f":"'K90 - time schedule'!CZ58","v":0},{"$f":"'K90 - time schedule'!DA58","v":0},{"$f":"'K90 - time schedule'!DB58","v":0},{"$f":"'K90 - time schedule'!DC58","v":0},{"$f":"'K90 - time schedule'!DD58","v":0},{"$f":"'K90 - time schedule'!DE58","v":0},{"$f":"'K90 - time schedule'!DF58","v":0},{"$f":"'K90 - time schedule'!DG58","v":0},{"$f":"'K90 - time schedule'!DH58","v":0},{"$f":"'K90 - time schedule'!DI58","v":0},{"$f":"'K90 - time schedule'!DJ58","v":0},{"$f":"'K90 - time schedule'!DK58","v":0},{"$f":"'K90 - time schedule'!DL58","v":0},{"$f":"'K90 - time schedule'!DM58","v":0},{"$f":"'K90 - time schedule'!DN58","v":0},{"$f":"'K90 - time schedule'!DO58","v":0},{"$f":"'K90 - time schedule'!DP58","v":0},{"$f":"'K90 - time schedule'!DQ58","v":0},{"$f":"'K90 - time schedule'!DR58","v":0},{"$f":"'K90 - time schedule'!DS58","v":0},{"$f":"'K90 - time schedule'!DT58","v":0},{"$f":"'K90 - time schedule'!DU58","v":0},{"$f":"'K90 - time schedule'!DV58","v":0},{"$f":"'K90 - time schedule'!DW58","v":0},{"$f":"'K90 - time schedule'!DX58","v":0},{"$f":"'K90 - time schedule'!DY58","v":0},{"$f":"'K90 - time schedule'!DZ58","v":0},{"$f":"'K90 - time schedule'!EA58","v":0},{"$f":"'K90 - time schedule'!EB58","v":0},{"$f":"'K90 - time schedule'!EC58","v":0},{"$f":"'K90 - time schedule'!ED58","v":0},{"$f":"'K90 - time schedule'!EE58","v":0},{"$f":"'K90 - time schedule'!EF58","v":0},{"$f":"'K90 - time schedule'!EG58","v":0},{"$f":"'K90 - time schedule'!EH58","v":0},{"$f":"'K90 - time schedule'!EI58","v":0},{"$f":"'K90 - time schedule'!EJ58","v":0},{"$f":"'K90 - time schedule'!EK58","v":0},{"$f":"'K90 - time schedule'!EL58","v":0},{"$f":"'K90 - time schedule'!EM58","v":0},{"$f":"'K90 - time schedule'!EN58","v":0},{"$f":"'K90 - time schedule'!EO58","v":0},{"$f":"'K90 - time schedule'!EP58","v":0},{"$f":"'K90 - time schedule'!EQ58","v":0},{"$f":"'K90 - time schedule'!ER58","v":0},{"$f":"'K90 - time schedule'!ES58","v":0},{"$f":"'K90 - time schedule'!ET58","v":0},{"$f":"'K90 - time schedule'!EU58","v":0},{"$f":"'K90 - time schedule'!EV58","v":0},{"$f":"'K90 - time schedule'!EW58","v":0},{"$f":"'K90 - time schedule'!EX58","v":0},{"$f":"'K90 - time schedule'!EY58","v":0},{"$f":"'K90 - time schedule'!EZ58","v":0},{"$f":"'K90 - time schedule'!FA58","v":0},{"$f":"'K90 - time schedule'!FB58","v":0},{"$f":"'K90 - time schedule'!FC58","v":0},{"$f":"'K90 - time schedule'!FD58","v":0},{"$f":"'K90 - time schedule'!FE58","v":0},{"$f":"'K90 - time schedule'!FF58","v":0},{"$f":"'K90 - time schedule'!FG58","v":0},{"$f":"'K90 - time schedule'!FH58","v":0},{"$f":"'K90 - time schedule'!FI58","v":0},{"$f":"'K90 - time schedule'!FJ58","v":0},{"$f":"'K90 - time schedule'!FK58","v":0},{"$f":"'K90 - time schedule'!FL58","v":0},{"$f":"'K90 - time schedule'!FM58","v":0},{"$f":"'K90 - time schedule'!FN58","v":0},{"$f":"'K90 - time schedule'!FO58","v":0},{"$f":"'K90 - time schedule'!FP58","v":0},{"$f":"'K90 - time schedule'!FQ58","v":0},{"$f":"'K90 - time schedule'!FR58","v":0},{"$f":"'K90 - time schedule'!FS58","v":0},{"$f":"'K90 - time schedule'!FT58","v":0},{"$f":"'K90 - time schedule'!FU58","v":0},{"$f":"'K90 - time schedule'!FV58","v":0},{"$f":"'K90 - time schedule'!FW58","v":0},{"$f":"'K90 - time schedule'!FX58","v":0},{"$f":"'K90 - time schedule'!FY58","v":0},{"$f":"'K90 - time schedule'!FZ58","v":0},{"$f":"'K90 - time schedule'!GA58","v":0},{"$f":"'K90 - time schedule'!GB58","v":0},{"$f":"'K90 - time schedule'!GC58","v":0},{"$f":"'K90 - time schedule'!GD58","v":0},{"$f":"'K90 - time schedule'!GE58","v":0},{"$f":"'K90 - time schedule'!GF58","v":0},{"$f":"'K20 - time schedule'!GG82","v":0},{"$f":"'K20 - time schedule'!GH82","v":0},{"$f":"'K20 - time schedule'!GI82","v":0},{"$f":"'K20 - time schedule'!GJ82","v":0},{"$f":"'K20 - time schedule'!GK82","v":0},{"$f":"'K20 - time schedule'!GL82","v":0},{"$f":"'K20 - time schedule'!GM82","v":0},{"$f":"'K20 - time schedule'!GN82","v":0},{"$f":"'K20 - time schedule'!GO82","v":0},{"$f":"'K20 - time schedule'!GP82","v":0},{"$f":"'K20 - time schedule'!GQ82","v":0},{"$f":"'K20 - time schedule'!GR82","v":0},{"$f":"'K20 - time schedule'!GS82","v":0},{"$f":"'K20 - time schedule'!GT82","v":0},{"$f":"'K20 - time schedule'!GU82","v":0},{"$f":"'K20 - time schedule'!GV82","v":0},{"$f":"'K20 - time schedule'!GW82","v":0},{"$f":"'K20 - time schedule'!GX82","v":0},{"$f":"'K20 - time schedule'!GY82","v":0},{"$f":"'K20 - time schedule'!GZ82","v":0},{"$f":"'K20 - time schedule'!HA82","v":0},{"$f":"'K20 - time schedule'!HB82","v":0},{"$f":"'K20 - time schedule'!HC82","v":0},{"$f":"'K20 - time schedule'!HD82","v":0},{"$f":"'K20 - time schedule'!HE82","v":0},{"$f":"'K20 - time schedule'!HF82","v":0},{"$f":"'K20 - time schedule'!HG82","v":0},{"$f":"'K20 - time schedule'!HH82","v":0},{"$f":"'K20 - time schedule'!HI82","v":0},{"$f":"'K20 - time schedule'!HJ82","v":0},{"$f":"'K20 - time schedule'!HK82","v":0},{"$f":"'K20 - time schedule'!HL82","v":0},{"$f":"'K20 - time schedule'!HM82","v":0},{"$f":"'K20 - time schedule'!HN82","v":0},{"$f":"'K20 - time schedule'!HO82","v":0},{"$f":"'K20 - time schedule'!HP82","v":0},{"$f":"'K20 - time schedule'!HQ82","v":0},{"$f":"'K20 - time schedule'!HR82","v":0},{"$f":"'K20 - time schedule'!HS82","v":0},{"$f":"'K20 - time schedule'!HT82","v":0},{"$f":"'K20 - time schedule'!HU82","v":0},{"$f":"'K20 - time schedule'!HV82","v":0},{"$f":"'K20 - time schedule'!HW82","v":0},{"$f":"'K20 - time schedule'!HX82","v":0},{"$f":"'K20 - time schedule'!HY82","v":0},{"$f":"'K20 - time schedule'!HZ82","v":0},{"$f":"'K20 - time schedule'!IA82","v":0},{"$f":"'K20 - time schedule'!IB82","v":0},{"$f":"'K20 - time schedule'!IC82","v":0},{"$f":"'K20 - time schedule'!ID82","v":0},{"$f":"'K20 - time schedule'!IE82","v":0},{"$f":"'K20 - time schedule'!IF82","v":0},{"$f":"'K20 - time schedule'!IG82","v":0},{"$f":"'K20 - time schedule'!IH82","v":0},{"$f":"'K20 - time schedule'!II82","v":0},{"$f":"'K20 - time schedule'!IJ82","v":0},{"$f":"'K20 - time schedule'!IK82","v":0},{"$f":"'K20 - time schedule'!IL82","v":0},{"$f":"'K20 - time schedule'!IM82","v":0},{"$f":"'K20 - time schedule'!IN82","v":0},{"$f":"'K20 - time schedule'!IO82","v":0},{"$f":"'K20 - time schedule'!IP82","v":0},{"$f":"'K20 - time schedule'!IQ82","v":0},{"$f":"'K20 - time schedule'!IR82","v":0},{"$f":"'K20 - time schedule'!IS82","v":0},{"$f":"'K20 - time schedule'!IT82","v":0},{"$f":"'K20 - time schedule'!IU82","v":0},{"$f":"'K20 - time schedule'!IV82","v":0},{"$f":"'K20 - time schedule'!IW82","v":0},{"$f":"'K20 - time schedule'!IX82","v":0},{"$f":"'K20 - time schedule'!IY82","v":0},{"$f":"'K20 - time schedule'!IZ82","v":0},{"$f":"'K20 - time schedule'!JA82","v":0},{"$f":"'K20 - time schedule'!JB82","v":0},{"$f":"'K20 - time schedule'!JC82","v":0},{"$f":"'K20 - time schedule'!JD82","v":0},{"$f":"'K20 - time schedule'!JE82","v":0},{"$f":"'K20 - time schedule'!JF82","v":0},{"$f":"'K20 - time schedule'!JG82","v":0},{"$f":"'K20 - time schedule'!JH82","v":0},{"$f":"'K20 - time schedule'!JI82","v":0},{"$f":"'K20 - time schedule'!JJ82","v":0},{"$f":"'K20 - time schedule'!JK82","v":0},{"$f":"'K20 - time schedule'!JL82","v":0},{"$f":"'K20 - time schedule'!JM82","v":0},{"$f":"'K20 - time schedule'!JN82","v":0},{"$f":"'K20 - time schedule'!JO82","v":0},{"$f":"'K20 - time schedule'!JP82","v":0},{"$f":"'K20 - time schedule'!JQ82","v":0},{"$f":"'K20 - time schedule'!JR82","v":0},{"$f":"'K20 - time schedule'!JS82","v":0},{"$f":"'K20 - time schedule'!JT82","v":0},{"$f":"'K20 - time schedule'!JU82","v":0},{"$f":"'K20 - time schedule'!JV82","v":0},{"$f":"'K20 - time schedule'!JW82","v":0},{"$f":"'K20 - time schedule'!JX82","v":0},{"$f":"'K20 - time schedule'!JY82","v":0},{"$f":"'K20 - time schedule'!JZ82","v":0},{"$f":"'K20 - time schedule'!KA82","v":0},{"$f":"'K20 - time schedule'!KB82","v":0},{"$f":"'K20 - time schedule'!KC82","v":0},{"$f":"'K20 - time schedule'!KD82","v":0},{"$f":"'K20 - time schedule'!KE82","v":0},{"$f":"'K20 - time schedule'!KF82","v":0},{"$f":"'K20 - time schedule'!KG82","v":0},{"$f":"'K20 - time schedule'!KH82","v":0},{"$f":"'K20 - time schedule'!KI82","v":0},{"$f":"'K20 - time schedule'!KJ82","v":0},{"$f":"'K20 - time schedule'!KK82","v":0},{"$f":"'K20 - time schedule'!KL82","v":0},{"$f":"'K20 - time schedule'!KM82","v":0},{"$f":"'K20 - time schedule'!KN82","v":0},{"$f":"'K20 - time schedule'!KO82","v":0},{"$f":"'K20 - time schedule'!KP82","v":0},{"$f":"'K20 - time schedule'!KQ82","v":0},{"$f":"'K20 - time schedule'!KR82","v":0},{"$f":"'K20 - time schedule'!KS82","v":0},{"$f":"'K20 - time schedule'!KT82","v":0}]
["Boiler room K90 - preliminary acceptance of the Work PAC","K90","EUR",{"$f":"'K90 - time schedule'!G60","v":0},{"$f":"'K90 - time schedule'!H60","v":0},{"$f":"'K90 - time schedule'!I60","v":0},{"$f":"'K90 - time schedule'!J60","v":0},{"$f":"'K90 - time schedule'!K60","v":0},{"$f":"'K90 - time schedule'!L60","v":0},{"$f":"'K90 - time schedule'!M60","v":0},{"$f":"'K90 - time schedule'!N60","v":0},{"$f":"'K90 - time schedule'!O60","v":0},{"$f":"'K90 - time schedule'!P60","v":0},{"$f":"'K90 - time schedule'!Q60","v":0},{"$f":"'K90 - time schedule'!R60","v":0},{"$f":"'K90 - time schedule'!S60","v":0},{"$f":"'K90 - time schedule'!T60","v":0},{"$f":"'K90 - time schedule'!U60","v":0},{"$f":"'K90 - time schedule'!V60","v":0},{"$f":"'K90 - time schedule'!W60","v":0},{"$f":"'K90 - time schedule'!X60","v":0},{"$f":"'K90 - time schedule'!Y60","v":0},{"$f":"'K90 - time schedule'!Z60","v":0},{"$f":"'K90 - time schedule'!AA60","v":0},{"$f":"'K90 - time schedule'!AB60","v":0},{"$f":"'K90 - time schedule'!AC60","v":0},{"$f":"'K90 - time schedule'!AD60","v":0},{"$f":"'K90 - time schedule'!AE60","v":0},{"$f":"'K90 - time schedule'!AF60","v":0},{"$f":"'K90 - time schedule'!AG60","v":0},{"$f":"'K90 - time schedule'!AH60","v":0},{"$f":"'K90 - time schedule'!AI60","v":0},{"$f":"'K90 - time schedule'!AJ60","v":0},{"$f":"'K90 - time schedule'!AK60","v":0},{"$f":"'K90 - time schedule'!AL60","v":0},{"$f":"'K90 - time schedule'!AM60","v":0},{"$f":"'K90 - time schedule'!AN60","v":0},{"$f":"'K90 - time schedule'!AO60","v":0},{"$f":"'K90 - time schedule'!AP60","v":0},{"$f":"'K90 - time schedule'!AQ60","v":0},{"$f":"'K90 - time schedule'!AR60","v":0},{"$f":"'K90 - time schedule'!AS60","v":0},{"$f":"'K90 - time schedule'!AT60","v":0},{"$f":"'K90 - time schedule'!AU60","v":0},{"$f":"'K90 - time schedule'!AV60","v":0},{"$f":"'K90 - time schedule'!AW60","v":0},{"$f":"'K90 - time schedule'!AX60","v":0},{"$f":"'K90 - time schedule'!AY60","v":0},{"$f":"'K90 - time schedule'!AZ60","v":0},{"$f":"'K90 - time schedule'!BA60","v":0},{"$f":"'K90 - time schedule'!BB60","v":0},{"$f":"'K90 - time schedule'!BC60","v":0},{"$f":"'K90 - time schedule'!BD60","v":0},{"$f":"'K90 - time schedule'!BE60","v":0},{"$f":"'K90 - time schedule'!BF60","v":0},{"$f":"'K90 - time schedule'!BG60","v":0},{"$f":"'K90 - time schedule'!BH60","v":0},{"$f":"'K90 - time schedule'!BI60","v":0},{"$f":"'K90 - time schedule'!BJ60","v":0},{"$f":"'K90 - time schedule'!BK60","v":0},{"$f":"'K90 - time schedule'!BL60","v":0},{"$f":"'K90 - time schedule'!BM60","v":0},{"$f":"'K90 - time schedule'!BN60","v":0},{"$f":"'K90 - time schedule'!BO60","v":0},{"$f":"'K90 - time schedule'!BP60","v":0},{"$f":"'K90 - time schedule'!BQ60","v":0},{"$f":"'K90 - time schedule'!BR60","v":0},{"$f":"'K90 - time schedule'!BS60","v":0},{"$f":"'K90 - time schedule'!BT60","v":0},{"$f":"'K90 - time schedule'!BU60","v":0},{"$f":"'K90 - time schedule'!BV60","v":0},{"$f":"'K90 - time schedule'!BW60","v":0},{"$f":"'K90 - time schedule'!BX60","v":0},{"$f":"'K90 - time schedule'!BY60","v":0},{"$f":"'K90 - time schedule'!BZ60","v":0},{"$f":"'K90 - time schedule'!CA60","v":0},{"$f":"'K90 - time schedule'!CB60","v":0},{"$f":"'K90 - time schedule'!CC60","v":0},{"$f":"'K90 - time schedule'!CD60","v":0},{"$f":"'K90 - time schedule'!CE60","v":0},{"$f":"'K90 - time schedule'!CF60","v":0},{"$f":"'K90 - time schedule'!CG60","v":0},{"$f":"'K90 - time schedule'!CH60","v":0},{"$f":"'K90 - time schedule'!CI60","v":0},{"$f":"'K90 - time schedule'!CJ60","v":0},{"$f":"'K90 - time schedule'!CK60","v":0},{"$f":"'K90 - time schedule'!CL60","v":0},{"$f":"'K90 - time schedule'!CM60","v":0},{"$f":"'K90 - time schedule'!CN60","v":0},{"$f":"'K90 - time schedule'!CO60","v":0},{"$f":"'K90 - time schedule'!CP60","v":0},{"$f":"'K90 - time schedule'!CQ60","v":0},{"$f":"'K90 - time schedule'!CR60","v":0},{"$f":"'K90 - time schedule'!CS60","v":0},{"$f":"'K90 - time schedule'!CT60","v":0},{"$f":"'K90 - time schedule'!CU60","v":0},{"$f":"'K90 - time schedule'!CV60","v":0},{"$f":"'K90 - time schedule'!CW60","v":0},{"$f":"'K90 - time schedule'!CX60","v":0},{"$f":"'K90 - time schedule'!CY60","v":0},{"$f":"'K90 - time schedule'!CZ60","v":0},{"$f":"'K90 - time schedule'!DA60","v":0},{"$f":"'K90 - time schedule'!DB60","v":0},{"$f":"'K90 - time schedule'!DC60","v":0},{"$f":"'K90 - time schedule'!DD60","v":0},{"$f":"'K90 - time schedule'!DE60","v":0},{"$f":"'K90 - time schedule'!DF60","v":0},{"$f":"'K90 - time schedule'!DG60","v":0},{"$f":"'K90 - time schedule'!DH60","v":0},{"$f":"'K90 - time schedule'!DI60","v":0},{"$f":"'K90 - time schedule'!DJ60","v":0},{"$f":"'K90 - time schedule'!DK60","v":0},{"$f":"'K90 - time schedule'!DL60","v":0},{"$f":"'K90 - time schedule'!DM60","v":0},{"$f":"'K90 - time schedule'!DN60","v":0},{"$f":"'K90 - time schedule'!DO60","v":0},{"$f":"'K90 - time schedule'!DP60","v":0},{"$f":"'K90 - time schedule'!DQ60","v":0},{"$f":"'K90 - time schedule'!DR60","v":0},{"$f":"'K90 - time schedule'!DS60","v":0},{"$f":"'K90 - time schedule'!DT60","v":0},{"$f":"'K90 - time schedule'!DU60","v":0},{"$f":"'K90 - time schedule'!DV60","v":0},{"$f":"'K90 - time schedule'!DW60","v":0},{"$f":"'K90 - time schedule'!DX60","v":0},{"$f":"'K90 - time schedule'!DY60","v":0},{"$f":"'K90 - time schedule'!DZ60","v":0},{"$f":"'K90 - time schedule'!EA60","v":0},{"$f":"'K90 - time schedule'!EB60","v":0},{"$f":"'K90 - time schedule'!EC60","v":0},{"$f":"'K90 - time schedule'!ED60","v":0},{"$f":"'K90 - time schedule'!EE60","v":0},{"$f":"'K90 - time schedule'!EF60","v":0},{"$f":"'K90 - time schedule'!EG60","v":0},{"$f":"'K90 - time schedule'!EH60","v":0},{"$f":"'K90 - time schedule'!EI60","v":0},{"$f":"'K90 - time schedule'!EJ60","v":0},{"$f":"'K90 - time schedule'!EK60","v":0},{"$f":"'K90 - time schedule'!EL60","v":0},{"$f":"'K90 - time schedule'!EM60","v":0},{"$f":"'K90 - time schedule'!EN60","v":0},{"$f":"'K90 - time schedule'!EO60","v":0},{"$f":"'K90 - time schedule'!EP60","v":0},{"$f":"'K90 - time schedule'!EQ60","v":0},{"$f":"'K90 - time schedule'!ER60","v":0},{"$f":"'K90 - time schedule'!ES60","v":0},{"$f":"'K90 - time schedule'!ET60","v":0},{"$f":"'K90 - time schedule'!EU60","v":0},{"$f":"'K90 - time schedule'!EV60","v":0},{"$f":"'K90 - time schedule'!EW60","v":0},{"$f":"'K90 - time schedule'!EX60","v":0},{"$f":"'K90 - time schedule'!EY60","v":0},{"$f":"'K90 - time schedule'!EZ60","v":0},{"$f":"'K90 - time schedule'!FA60","v":0},{"$f":"'K90 - time schedule'!FB60","v":0},{"$f":"'K90 - time schedule'!FC60","v":0},{"$f":"'K90 - time schedule'!FD60","v":0},{"$f":"'K90 - time schedule'!FE60","v":0},{"$f":"'K90 - time schedule'!FF60","v":0},{"$f":"'K90 - time schedule'!FG60","v":0},{"$f":"'K90 - time schedule'!FH60","v":0},{"$f":"'K90 - time schedule'!FI60","v":0},{"$f":"'K90 - time schedule'!FJ60","v":0},{"$f":"'K90 - time schedule'!FK60","v":0},{"$f":"'K90 - time schedule'!FL60","v":0},{"$f":"'K90 - time schedule'!FM60","v":0},{"$f":"'K90 - time schedule'!FN60","v":0},{"$f":"'K90 - time schedule'!FO60","v":0},{"$f":"'K90 - time schedule'!FP60","v":0},{"$f":"'K90 - time schedule'!FQ60","v":0},{"$f":"'K90 - time schedule'!FR60","v":0},{"$f":"'K90 - time schedule'!FS60","v":0},{"$f":"'K90 - time schedule'!FT60","v":0},{"$f":"'K90 - time schedule'!FU60","v":0},{"$f":"'K90 - time schedule'!FV60","v":0},{"$f":"'K90 - time schedule'!FW60","v":0},{"$f":"'K90 - time schedule'!FX60","v":0},{"$f":"'K90 - time schedule'!FY60","v":0},{"$f":"'K90 - time schedule'!FZ60","v":0},{"$f":"'K90 - time schedule'!GA60","v":0},{"$f":"'K90 - time schedule'!GB60","v":0},{"$f":"'K90 - time schedule'!GC60","v":0},{"$f":"'K90 - time schedule'!GD60","v":0},{"$f":"'K90 - time schedule'!GE60","v":0},{"$f":"'K90 - time schedule'!GF60","v":0},{"$f":"'K20 - time schedule'!GG83","v":0},{"$f":"'K20 - time schedule'!GH83","v":0},{"$f":"'K20 - time schedule'!GI83","v":0},{"$f":"'K20 - time schedule'!GJ83","v":0},{"$f":"'K20 - time schedule'!GK83","v":0},{"$f":"'K20 - time schedule'!GL83","v":0},{"$f":"'K20 - time schedule'!GM83","v":0},{"$f":"'K20 - time schedule'!GN83","v":0},{"$f":"'K20 - time schedule'!GO83","v":0},{"$f":"'K20 - time schedule'!GP83","v":0},{"$f":"'K20 - time schedule'!GQ83","v":0},{"$f":"'K20 - time schedule'!GR83","v":0},{"$f":"'K20 - time schedule'!GS83","v":0},{"$f":"'K20 - time schedule'!GT83","v":0},{"$f":"'K20 - time schedule'!GU83","v":0},{"$f":"'K20 - time schedule'!GV83","v":0},{"$f":"'K20 - time schedule'!GW83","v":0},{"$f":"'K20 - time schedule'!GX83","v":0},{"$f":"'K20 - time schedule'!GY83","v":0},{"$f":"'K20 - time schedule'!GZ83","v":0},{"$f":"'K20 - time schedule'!HA83","v":0},{"$f":"'K20 - time schedule'!HB83","v":0},{"$f":"'K20 - time schedule'!HC83","v":0},{"$f":"'K20 - time schedule'!HD83","v":0},{"$f":"'K20 - time schedule'!HE83","v":0},{"$f":"'K20 - time schedule'!HF83","v":0},{"$f":"'K20 - time schedule'!HG83","v":0},{"$f":"'K20 - time schedule'!HH83","v":0},{"$f":"'K20 - time schedule'!HI83","v":0},{"$f":"'K20 - time schedule'!HJ83","v":0},{"$f":"'K20 - time schedule'!HK83","v":0},{"$f":"'K20 - time schedule'!HL83","v":0},{"$f":"'K20 - time schedule'!HM83","v":0},{"$f":"'K20 - time schedule'!HN83","v":0},{"$f":"'K20 - time schedule'!HO83","v":0},{"$f":"'K20 - time schedule'!HP83","v":0},{"$f":"'K20 - time schedule'!HQ83","v":0},{"$f":"'K20 - time schedule'!HR83","v":0},{"$f":"'K20 - time schedule'!HS83","v":0},{"$f":"'K20 - time schedule'!HT83","v":0},{"$f":"'K20 - time schedule'!HU83","v":0},{"$f":"'K20 - time schedule'!HV83","v":0},{"$f":"'K20 - time schedule'!HW83","v":0},{"$f":"'K20 - time schedule'!HX83","v":0},{"$f":"'K20 - time schedule'!HY83","v":0},{"$f":"'K20 - time schedule'!HZ83","v":0},{"$f":"'K20 - time schedule'!IA83","v":0},{"$f":"'K20 - time schedule'!IB83","v":0},{"$f":"'K20 - time schedule'!IC83","v":0},{"$f":"'K20 - time schedule'!ID83","v":0},{"$f":"'K20 - time schedule'!IE83","v":0},{"$f":"'K20 - time schedule'!IF83","v":0},{"$f":"'K20 - time schedule'!IG83","v":0},{"$f":"'K20 - time schedule'!IH83","v":0},{"$f":"'K20 - time schedule'!II83","v":0},{"$f":"'K20 - time schedule'!IJ83","v":0},{"$f":"'K20 - time schedule'!IK83","v":0},{"$f":"'K20 - time schedule'!IL83","v":0},{"$f":"'K20 - time schedule'!IM83","v":0},{"$f":"'K20 - time schedule'!IN83","v":0},{"$f":"'K20 - time schedule'!IO83","v":0},{"$f":"'K20 - time schedule'!IP83","v":0},{"$f":"'K20 - time schedule'!IQ83","v":0},{"$f":"'K20 - time schedule'!IR83","v":0},{"$f":"'K20 - time schedule'!IS83","v":0},{"$f":"'K20 - time schedule'!IT83","v":0},{"$f":"'K20 - time schedule'!IU83","v":0},{"$f":"'K20 - time schedule'!IV83","v":0},{"$f":"'K20 - time schedule'!IW83","v":0},{"$f":"'K20 - time schedule'!IX83","v":0},{"$f":"'K20 - time schedule'!IY83","v":0},{"$f":"'K20 - time schedule'!IZ83","v":0},{"$f":"'K20 - time schedule'!JA83","v":0},{"$f":"'K20 - time schedule'!JB83","v":0},{"$f":"'K20 - time schedule'!JC83","v":0},{"$f":"'K20 - time schedule'!JD83","v":0},{"$f":"'K20 - time schedule'!JE83","v":0},{"$f":"'K20 - time schedule'!JF83","v":0},{"$f":"'K20 - time schedule'!JG83","v":0},{"$f":"'K20 - time schedule'!JH83","v":0},{"$f":"'K20 - time schedule'!JI83","v":0},{"$f":"'K20 - time schedule'!JJ83","v":0},{"$f":"'K20 - time schedule'!JK83","v":0},{"$f":"'K20 - time schedule'!JL83","v":0},{"$f":"'K20 - time schedule'!JM83","v":0},{"$f":"'K20 - time schedule'!JN83","v":0},{"$f":"'K20 - time schedule'!JO83","v":0},{"$f":"'K20 - time schedule'!JP83","v":0},{"$f":"'K20 - time schedule'!JQ83","v":0},{"$f":"'K20 - time schedule'!JR83","v":0},{"$f":"'K20 - time schedule'!JS83","v":0},{"$f":"'K20 - time schedule'!JT83","v":0},{"$f":"'K20 - time schedule'!JU83","v":0},{"$f":"'K20 - time schedule'!JV83","v":0},{"$f":"'K20 - time schedule'!JW83","v":0},{"$f":"'K20 - time schedule'!JX83","v":0},{"$f":"'K20 - time schedule'!JY83","v":0},{"$f":"'K20 - time schedule'!JZ83","v":0},{"$f":"'K20 - time schedule'!KA83","v":0},{"$f":"'K20 - time schedule'!KB83","v":0},{"$f":"'K20 - time schedule'!KC83","v":0},{"$f":"'K20 - time schedule'!KD83","v":0},{"$f":"'K20 - time schedule'!KE83","v":0},{"$f":"'K20 - time schedule'!KF83","v":0},{"$f":"'K20 - time schedule'!KG83","v":0},{"$f":"'K20 - time schedule'!KH83","v":0},{"$f":"'K20 - time schedule'!KI83","v":0},{"$f":"'K20 - time schedule'!KJ83","v":0},{"$f":"'K20 - time schedule'!KK83","v":0},{"$f":"'K20 - time schedule'!KL83","v":0},{"$f":"'K20 - time schedule'!KM83","v":0},{"$f":"'K20 - time schedule'!KN83","v":0},{"$f":"'K20 - time schedule'!KO83","v":0},{"$f":"'K20 - time schedule'!KP83","v":0},{"$f":"'K20 - time schedule'!KQ83","v":0},{"$f":"'K20 - time schedule'!KR83","v":0},{"$f":"'K20 - time schedule'!KS83","v":0},{"$f":"'K20 - time schedule'!KT83","v":0}]
["Boiler room K90 - guarantee test B","K90","EUR",{"$f":"'K90 - time schedule'!G62","v":0},{"$f":"'K90 - time schedule'!H62","v":0},{"$f":"'K90 - time schedule'!I62","v":0},{"$f":"'K90 - time schedule'!J62","v":0},{"$f":"'K90 - time schedule'!K62","v":0},{"$f":"'K90 - time schedule'!L62","v":0},{"$f":"'K90 - time schedule'!M62","v":0},{"$f":"'K90 - time schedule'!N62","v":0},{"$f":"'K90 - time schedule'!O62","v":0},{"$f":"'K90 - time schedule'!P62","v":0},{"$f":"'K90 - time schedule'!Q62","v":0},{"$f":"'K90 - time schedule'!R62","v":0},{"$f":"'K90 - time schedule'!S62","v":0},{"$f":"'K90 - time schedule'!T62","v":0},{"$f":"'K90 - time schedule'!U62","v":0},{"$f":"'K90 - time schedule'!V62","v":0},{"$f":"'K90 - time schedule'!W62","v":0},{"$f":"'K90 - time schedule'!X62","v":0},{"$f":"'K90 - time schedule'!Y62","v":0},{"$f":"'K90 - time schedule'!Z62","v":0},{"$f":"'K90 - time schedule'!AA62","v":0},{"$f":"'K90 - time schedule'!AB62","v":0},{"$f":"'K90 - time schedule'!AC62","v":0},{"$f":"'K90 - time schedule'!AD62","v":0},{"$f":"'K90 - time schedule'!AE62","v":0},{"$f":"'K90 - time schedule'!AF62","v":0},{"$f":"'K90 - time schedule'!AG62","v":0},{"$f":"'K90 - time schedule'!AH62","v":0},{"$f":"'K90 - time schedule'!AI62","v":0},{"$f":"'K90 - time schedule'!AJ62","v":0},{"$f":"'K90 - time schedule'!AK62","v":0},{"$f":"'K90 - time schedule'!AL62","v":0},{"$f":"'K90 - time schedule'!AM62","v":0},{"$f":"'K90 - time schedule'!AN62","v":0},{"$f":"'K90 - time schedule'!AO62","v":0},{"$f":"'K90 - time schedule'!AP62","v":0},{"$f":"'K90 - time schedule'!AQ62","v":0},{"$f":"'K90 - time schedule'!AR62","v":0},{"$f":"'K90 - time schedule'!AS62","v":0},{"$f":"'K90 - time schedule'!AT62","v":0},{"$f":"'K90 - time schedule'!AU62","v":0},{"$f":"'K90 - time schedule'!AV62","v":0},{"$f":"'K90 - time schedule'!AW62","v":0},{"$f":"'K90 - time schedule'!AX62","v":0},{"$f":"'K90 - time schedule'!AY62","v":0},{"$f":"'K90 - time schedule'!AZ62","v":0},{"$f":"'K90 - time schedule'!BA62","v":0},{"$f":"'K90 - time schedule'!BB62","v":0},{"$f":"'K90 - time schedule'!BC62","v":0},{"$f":"'K90 - time schedule'!BD62","v":0},{"$f":"'K90 - time schedule'!BE62","v":0},{"$f":"'K90 - time schedule'!BF62","v":0},{"$f":"'K90 - time schedule'!BG62","v":0},{"$f":"'K90 - time schedule'!BH62","v":0},{"$f":"'K90 - time schedule'!BI62","v":0},{"$f":"'K90 - time schedule'!BJ62","v":0},{"$f":"'K90 - time schedule'!BK62","v":0},{"$f":"'K90 - time schedule'!BL62","v":0},{"$f":"'K90 - time schedule'!BM62","v":0},{"$f":"'K90 - time schedule'!BN62","v":0},{"$f":"'K90 - time schedule'!BO62","v":0},{"$f":"'K90 - time schedule'!BP62","v":0},{"$f":"'K90 - time schedule'!BQ62","v":0},{"$f":"'K90 - time schedule'!BR62","v":0},{"$f":"'K90 - time schedule'!BS62","v":0},{"$f":"'K90 - time schedule'!BT62","v":0},{"$f":"'K90 - time schedule'!BU62","v":0},{"$f":"'K90 - time schedule'!BV62","v":0},{"$f":"'K90 - time schedule'!BW62","v":0},{"$f":"'K90 - time schedule'!BX62","v":0},{"$f":"'K90 - time schedule'!BY62","v":0},{"$f":"'K90 - time schedule'!BZ62","v":0},{"$f":"'K90 - time schedule'!CA62","v":0},{"$f":"'K90 - time schedule'!CB62","v":0},{"$f":"'K90 - time schedule'!CC62","v":0},{"$f":"'K90 - time schedule'!CD62","v":0},{"$f":"'K90 - time schedule'!CE62","v":0},{"$f":"'K90 - time schedule'!CF62","v":0},{"$f":"'K90 - time schedule'!CG62","v":0},{"$f":"'K90 - time schedule'!CH62","v":0},{"$f":"'K90 - time schedule'!CI62","v":0},{"$f":"'K90 - time schedule'!CJ62","v":0},{"$f":"'K90 - time schedule'!CK62","v":0},{"$f":"'K90 - time schedule'!CL62","v":0},{"$f":"'K90 - time schedule'!CM62","v":0},{"$f":"'K90 - time schedule'!CN62","v":0},{"$f":"'K90 - time schedule'!CO62","v":0},{"$f":"'K90 - time schedule'!CP62","v":0},{"$f":"'K90 - time schedule'!CQ62","v":0},{"$f":"'K90 - time schedule'!CR62","v":0},{"$f":"'K90 - time schedule'!CS62","v":0},{"$f":"'K90 - time schedule'!CT62","v":0},{"$f":"'K90 - time schedule'!CU62","v":0},{"$f":"'K90 - time schedule'!CV62","v":0},{"$f":"'K90 - time schedule'!CW62","v":0},{"$f":"'K90 - time schedule'!CX62","v":0},{"$f":"'K90 - time schedule'!CY62","v":0},{"$f":"'K90 - time schedule'!CZ62","v":0},{"$f":"'K90 - time schedule'!DA62","v":0},{"$f":"'K90 - time schedule'!DB62","v":0},{"$f":"'K90 - time schedule'!DC62","v":0},{"$f":"'K90 - time schedule'!DD62","v":0},{"$f":"'K90 - time schedule'!DE62","v":0},{"$f":"'K90 - time schedule'!DF62","v":0},{"$f":"'K90 - time schedule'!DG62","v":0},{"$f":"'K90 - time schedule'!DH62","v":0},{"$f":"'K90 - time schedule'!DI62","v":0},{"$f":"'K90 - time schedule'!DJ62","v":0},{"$f":"'K90 - time schedule'!DK62","v":0},{"$f":"'K90 - time schedule'!DL62","v":0},{"$f":"'K90 - time schedule'!DM62","v":0},{"$f":"'K90 - time schedule'!DN62","v":0},{"$f":"'K90 - time schedule'!DO62","v":0},{"$f":"'K90 - time schedule'!DP62","v":0},{"$f":"'K90 - time schedule'!DQ62","v":0},{"$f":"'K90 - time schedule'!DR62","v":0},{"$f":"'K90 - time schedule'!DS62","v":0},{"$f":"'K90 - time schedule'!DT62","v":0},{"$f":"'K90 - time schedule'!DU62","v":0},{"$f":"'K90 - time schedule'!DV62","v":0},{"$f":"'K90 - time schedule'!DW62","v":0},{"$f":"'K90 - time schedule'!DX62","v":0},{"$f":"'K90 - time schedule'!DY62","v":0},{"$f":"'K90 - time schedule'!DZ62","v":0},{"$f":"'K90 - time schedule'!EA62","v":0},{"$f":"'K90 - time schedule'!EB62","v":0},{"$f":"'K90 - time schedule'!EC62","v":0},{"$f":"'K90 - time schedule'!ED62","v":0},{"$f":"'K90 - time schedule'!EE62","v":0},{"$f":"'K90 - time schedule'!EF62","v":0},{"$f":"'K90 - time schedule'!EG62","v":0},{"$f":"'K90 - time schedule'!EH62","v":0},{"$f":"'K90 - time schedule'!EI62","v":0},{"$f":"'K90 - time schedule'!EJ62","v":0},{"$f":"'K90 - time schedule'!EK62","v":0},{"$f":"'K90 - time schedule'!EL62","v":0},{"$f":"'K90 - time schedule'!EM62","v":0},{"$f":"'K90 - time schedule'!EN62","v":0},{"$f":"'K90 - time schedule'!EO62","v":0},{"$f":"'K90 - time schedule'!EP62","v":0},{"$f":"'K90 - time schedule'!EQ62","v":0},{"$f":"'K90 - time schedule'!ER62","v":0},{"$f":"'K90 - time schedule'!ES62","v":0},{"$f":"'K90 - time schedule'!ET62","v":0},{"$f":"'K90 - time schedule'!EU62","v":0},{"$f":"'K90 - time schedule'!EV62","v":0},{"$f":"'K90 - time schedule'!EW62","v":0},{"$f":"'K90 - time schedule'!EX62","v":0},{"$f":"'K90 - time schedule'!EY62","v":0},{"$f":"'K90 - time schedule'!EZ62","v":0},{"$f":"'K90 - time schedule'!FA62","v":0},{"$f":"'K90 - time schedule'!FB62","v":0},{"$f":"'K90 - time schedule'!FC62","v":0},{"$f":"'K90 - time schedule'!FD62","v":0},{"$f":"'K90 - time schedule'!FE62","v":0},{"$f":"'K90 - time schedule'!FF62","v":0},{"$f":"'K90 - time schedule'!FG62","v":0},{"$f":"'K90 - time schedule'!FH62","v":0},{"$f":"'K90 - time schedule'!FI62","v":0},{"$f":"'K90 - time schedule'!FJ62","v":0},{"$f":"'K90 - time schedule'!FK62","v":0},{"$f":"'K90 - time schedule'!FL62","v":0},{"$f":"'K90 - time schedule'!FM62","v":0},{"$f":"'K90 - time schedule'!FN62","v":0},{"$f":"'K90 - time schedule'!FO62","v":0},{"$f":"'K90 - time schedule'!FP62","v":0},{"$f":"'K90 - time schedule'!FQ62","v":0},{"$f":"'K90 - time schedule'!FR62","v":0},{"$f":"'K90 - time schedule'!FS62","v":0},{"$f":"'K90 - time schedule'!FT62","v":0},{"$f":"'K90 - time schedule'!FU62","v":0},{"$f":"'K90 - time schedule'!FV62","v":0},{"$f":"'K90 - time schedule'!FW62","v":0},{"$f":"'K90 - time schedule'!FX62","v":0},{"$f":"'K90 - time schedule'!FY62","v":0},{"$f":"'K90 - time schedule'!FZ62","v":0},{"$f":"'K90 - time schedule'!GA62","v":0},{"$f":"'K90 - time schedule'!GB62","v":0},{"$f":"'K90 - time schedule'!GC62","v":0},{"$f":"'K90 - time schedule'!GD62","v":0},{"$f":"'K90 - time schedule'!GE62","v":0},{"$f":"'K90 - time schedule'!GF62","v":0},{"$f":"'K20 - time schedule'!GG84","v":0},{"$f":"'K20 - time schedule'!GH84","v":0},{"$f":"'K20 - time schedule'!GI84","v":0},{"$f":"'K20 - time schedule'!GJ84","v":0},{"$f":"'K20 - time schedule'!GK84","v":0},{"$f":"'K20 - time schedule'!GL84","v":0},{"$f":"'K20 - time schedule'!GM84","v":0},{"$f":"'K20 - time schedule'!GN84","v":0},{"$f":"'K20 - time schedule'!GO84","v":0},{"$f":"'K20 - time schedule'!GP84","v":0},{"$f":"'K20 - time schedule'!GQ84","v":0},{"$f":"'K20 - time schedule'!GR84","v":0},{"$f":"'K20 - time schedule'!GS84","v":0},{"$f":"'K20 - time schedule'!GT84","v":0},{"$f":"'K20 - time schedule'!GU84","v":0},{"$f":"'K20 - time schedule'!GV84","v":0},{"$f":"'K20 - time schedule'!GW84","v":0},{"$f":"'K20 - time schedule'!GX84","v":0},{"$f":"'K20 - time schedule'!GY84","v":0},{"$f":"'K20 - time schedule'!GZ84","v":0},{"$f":"'K20 - time schedule'!HA84","v":0},{"$f":"'K20 - time schedule'!HB84","v":0},{"$f":"'K20 - time schedule'!HC84","v":0},{"$f":"'K20 - time schedule'!HD84","v":0},{"$f":"'K20 - time schedule'!HE84","v":0},{"$f":"'K20 - time schedule'!HF84","v":0},{"$f":"'K20 - time schedule'!HG84","v":0},{"$f":"'K20 - time schedule'!HH84","v":0},{"$f":"'K20 - time schedule'!HI84","v":0},{"$f":"'K20 - time schedule'!HJ84","v":0},{"$f":"'K20 - time schedule'!HK84","v":0},{"$f":"'K20 - time schedule'!HL84","v":0},{"$f":"'K20 - time schedule'!HM84","v":0},{"$f":"'K20 - time schedule'!HN84","v":0},{"$f":"'K20 - time schedule'!HO84","v":0},{"$f":"'K20 - time schedule'!HP84","v":0},{"$f":"'K20 - time schedule'!HQ84","v":0},{"$f":"'K20 - time schedule'!HR84","v":0},{"$f":"'K20 - time schedule'!HS84","v":0},{"$f":"'K20 - time schedule'!HT84","v":0},{"$f":"'K20 - time schedule'!HU84","v":0},{"$f":"'K20 - time schedule'!HV84","v":0},{"$f":"'K20 - time schedule'!HW84","v":0},{"$f":"'K20 - time schedule'!HX84","v":0},{"$f":"'K20 - time schedule'!HY84","v":0},{"$f":"'K20 - time schedule'!HZ84","v":0},{"$f":"'K20 - time schedule'!IA84","v":0},{"$f":"'K20 - time schedule'!IB84","v":0},{"$f":"'K20 - time schedule'!IC84","v":0},{"$f":"'K20 - time schedule'!ID84","v":0},{"$f":"'K20 - time schedule'!IE84","v":0},{"$f":"'K20 - time schedule'!IF84","v":0},{"$f":"'K20 - time schedule'!IG84","v":0},{"$f":"'K20 - time schedule'!IH84","v":0},{"$f":"'K20 - time schedule'!II84","v":0},{"$f":"'K20 - time schedule'!IJ84","v":0},{"$f":"'K20 - time schedule'!IK84","v":0},{"$f":"'K20 - time schedule'!IL84","v":0},{"$f":"'K20 - time schedule'!IM84","v":0},{"$f":"'K20 - time schedule'!IN84","v":0},{"$f":"'K20 - time schedule'!IO84","v":0},{"$f":"'K20 - time schedule'!IP84","v":0},{"$f":"'K20 - time schedule'!IQ84","v":0},{"$f":"'K20 - time schedule'!IR84","v":0},{"$f":"'K20 - time schedule'!IS84","v":0},{"$f":"'K20 - time schedule'!IT84","v":0},{"$f":"'K20 - time schedule'!IU84","v":0},{"$f":"'K20 - time schedule'!IV84","v":0},{"$f":"'K20 - time schedule'!IW84","v":0},{"$f":"'K20 - time schedule'!IX84","v":0},{"$f":"'K20 - time schedule'!IY84","v":0},{"$f":"'K20 - time schedule'!IZ84","v":0},{"$f":"'K20 - time schedule'!JA84","v":0},{"$f":"'K20 - time schedule'!JB84","v":0},{"$f":"'K20 - time schedule'!JC84","v":0},{"$f":"'K20 - time schedule'!JD84","v":0},{"$f":"'K20 - time schedule'!JE84","v":0},{"$f":"'K20 - time schedule'!JF84","v":0},{"$f":"'K20 - time schedule'!JG84","v":0},{"$f":"'K20 - time schedule'!JH84","v":0},{"$f":"'K20 - time schedule'!JI84","v":0},{"$f":"'K20 - time schedule'!JJ84","v":0},{"$f":"'K20 - time schedule'!JK84","v":0},{"$f":"'K20 - time schedule'!JL84","v":0},{"$f":"'K20 - time schedule'!JM84","v":0},{"$f":"'K20 - time schedule'!JN84","v":0},{"$f":"'K20 - time schedule'!JO84","v":0},{"$f":"'K20 - time schedule'!JP84","v":0},{"$f":"'K20 - time schedule'!JQ84","v":0},{"$f":"'K20 - time schedule'!JR84","v":0},{"$f":"'K20 - time schedule'!JS84","v":0},{"$f":"'K20 - time schedule'!JT84","v":0},{"$f":"'K20 - time schedule'!JU84","v":0},{"$f":"'K20 - time schedule'!JV84","v":0},{"$f":"'K20 - time schedule'!JW84","v":0},{"$f":"'K20 - time schedule'!JX84","v":0},{"$f":"'K20 - time schedule'!JY84","v":0},{"$f":"'K20 - time schedule'!JZ84","v":0},{"$f":"'K20 - time schedule'!KA84","v":0},{"$f":"'K20 - time schedule'!KB84","v":0},{"$f":"'K20 - time schedule'!KC84","v":0},{"$f":"'K20 - time schedule'!KD84","v":0},{"$f":"'K20 - time schedule'!KE84","v":0},{"$f":"'K20 - time schedule'!KF84","v":0},{"$f":"'K20 - time schedule'!KG84","v":0},{"$f":"'K20 - time schedule'!KH84","v":0},{"$f":"'K20 - time schedule'!KI84","v":0},{"$f":"'K20 - time schedule'!KJ84","v":0},{"$f":"'K20 - time schedule'!KK84","v":0},{"$f":"'K20 - time schedule'!KL84","v":0},{"$f":"'K20 - time schedule'!KM84","v":0},{"$f":"'K20 - time schedule'!KN84","v":0},{"$f":"'K20 - time schedule'!KO84","v":0},{"$f":"'K20 - time schedule'!KP84","v":0},{"$f":"'K20 - time schedule'!KQ84","v":0},{"$f":"'K20 - time schedule'!KR84","v":0},{"$f":"'K20 - time schedule'!KS84","v":0},{"$f":"'K20 - time schedule'!KT84","v":0}]
["Boiler room K90 - final acceptance of the Work FAC","K90","EUR",{"$f":"'K90 - time schedule'!G64","v":0},{"$f":"'K90 - time schedule'!H64","v":0},{"$f":"'K90 - time schedule'!I64","v":0},{"$f":"'K90 - time schedule'!J64","v":0},{"$f":"'K90 - time schedule'!K64","v":0},{"$f":"'K90 - time schedule'!L64","v":0},{"$f":"'K90 - time schedule'!M64","v":0},{"$f":"'K90 - time schedule'!N64","v":0},{"$f":"'K90 - time schedule'!O64","v":0},{"$f":"'K90 - time schedule'!P64","v":0},{"$f":"'K90 - time schedule'!Q64","v":0},{"$f":"'K90 - time schedule'!R64","v":0},{"$f":"'K90 - time schedule'!S64","v":0},{"$f":"'K90 - time schedule'!T64","v":0},{"$f":"'K90 - time schedule'!U64","v":0},{"$f":"'K90 - time schedule'!V64","v":0},{"$f":"'K90 - time schedule'!W64","v":0},{"$f":"'K90 - time schedule'!X64","v":0},{"$f":"'K90 - time schedule'!Y64","v":0},{"$f":"'K90 - time schedule'!Z64","v":0},{"$f":"'K90 - time schedule'!AA64","v":0},{"$f":"'K90 - time schedule'!AB64","v":0},{"$f":"'K90 - time schedule'!AC64","v":0},{"$f":"'K90 - time schedule'!AD64","v":0},{"$f":"'K90 - time schedule'!AE64","v":0},{"$f":"'K90 - time schedule'!AF64","v":0},{"$f":"'K90 - time schedule'!AG64","v":0},{"$f":"'K90 - time schedule'!AH64","v":0},{"$f":"'K90 - time schedule'!AI64","v":0},{"$f":"'K90 - time schedule'!AJ64","v":0},{"$f":"'K90 - time schedule'!AK64","v":0},{"$f":"'K90 - time schedule'!AL64","v":0},{"$f":"'K90 - time schedule'!AM64","v":0},{"$f":"'K90 - time schedule'!AN64","v":0},{"$f":"'K90 - time schedule'!AO64","v":0},{"$f":"'K90 - time schedule'!AP64","v":0},{"$f":"'K90 - time schedule'!AQ64","v":0},{"$f":"'K90 - time schedule'!AR64","v":0},{"$f":"'K90 - time schedule'!AS64","v":0},{"$f":"'K90 - time schedule'!AT64","v":0},{"$f":"'K90 - time schedule'!AU64","v":0},{"$f":"'K90 - time schedule'!AV64","v":0},{"$f":"'K90 - time schedule'!AW64","v":0},{"$f":"'K90 - time schedule'!AX64","v":0},{"$f":"'K90 - time schedule'!AY64","v":0},{"$f":"'K90 - time schedule'!AZ64","v":0},{"$f":"'K90 - time schedule'!BA64","v":0},{"$f":"'K90 - time schedule'!BB64","v":0},{"$f":"'K90 - time schedule'!BC64","v":0},{"$f":"'K90 - time schedule'!BD64","v":0},{"$f":"'K90 - time schedule'!BE64","v":0},{"$f":"'K90 - time schedule'!BF64","v":0},{"$f":"'K90 - time schedule'!BG64","v":0},{"$f":"'K90 - time schedule'!BH64","v":0},{"$f":"'K90 - time schedule'!BI64","v":0},{"$f":"'K90 - time schedule'!BJ64","v":0},{"$f":"'K90 - time schedule'!BK64","v":0},{"$f":"'K90 - time schedule'!BL64","v":0},{"$f":"'K90 - time schedule'!BM64","v":0},{"$f":"'K90 - time schedule'!BN64","v":0},{"$f":"'K90 - time schedule'!BO64","v":0},{"$f":"'K90 - time schedule'!BP64","v":0},{"$f":"'K90 - time schedule'!BQ64","v":0},{"$f":"'K90 - time schedule'!BR64","v":0},{"$f":"'K90 - time schedule'!BS64","v":0},{"$f":"'K90 - time schedule'!BT64","v":0},{"$f":"'K90 - time schedule'!BU64","v":0},{"$f":"'K90 - time schedule'!BV64","v":0},{"$f":"'K90 - time schedule'!BW64","v":0},{"$f":"'K90 - time schedule'!BX64","v":0},{"$f":"'K90 - time schedule'!BY64","v":0},{"$f":"'K90 - time schedule'!BZ64","v":0},{"$f":"'K90 - time schedule'!CA64","v":0},{"$f":"'K90 - time schedule'!CB64","v":0},{"$f":"'K90 - time schedule'!CC64","v":0},{"$f":"'K90 - time schedule'!CD64","v":0},{"$f":"'K90 - time schedule'!CE64","v":0},{"$f":"'K90 - time schedule'!CF64","v":0},{"$f":"'K90 - time schedule'!CG64","v":0},{"$f":"'K90 - time schedule'!CH64","v":0},{"$f":"'K90 - time schedule'!CI64","v":0},{"$f":"'K90 - time schedule'!CJ64","v":0},{"$f":"'K90 - time schedule'!CK64","v":0},{"$f":"'K90 - time schedule'!CL64","v":0},{"$f":"'K90 - time schedule'!CM64","v":0},{"$f":"'K90 - time schedule'!CN64","v":0},{"$f":"'K90 - time schedule'!CO64","v":0},{"$f":"'K90 - time schedule'!CP64","v":0},{"$f":"'K90 - time schedule'!CQ64","v":0},{"$f":"'K90 - time schedule'!CR64","v":0},{"$f":"'K90 - time schedule'!CS64","v":0},{"$f":"'K90 - time schedule'!CT64","v":0},{"$f":"'K90 - time schedule'!CU64","v":0},{"$f":"'K90 - time schedule'!CV64","v":0},{"$f":"'K90 - time schedule'!CW64","v":0},{"$f":"'K90 - time schedule'!CX64","v":0},{"$f":"'K90 - time schedule'!CY64","v":0},{"$f":"'K90 - time schedule'!CZ64","v":0},{"$f":"'K90 - time schedule'!DA64","v":0},{"$f":"'K90 - time schedule'!DB64","v":0},{"$f":"'K90 - time schedule'!DC64","v":0},{"$f":"'K90 - time schedule'!DD64","v":0},{"$f":"'K90 - time schedule'!DE64","v":0},{"$f":"'K90 - time schedule'!DF64","v":0},{"$f":"'K90 - time schedule'!DG64","v":0},{"$f":"'K90 - time schedule'!DH64","v":0},{"$f":"'K90 - time schedule'!DI64","v":0},{"$f":"'K90 - time schedule'!DJ64","v":0},{"$f":"'K90 - time schedule'!DK64","v":0},{"$f":"'K90 - time schedule'!DL64","v":0},{"$f":"'K90 - time schedule'!DM64","v":0},{"$f":"'K90 - time schedule'!DN64","v":0},{"$f":"'K90 - time schedule'!DO64","v":0},{"$f":"'K90 - time schedule'!DP64","v":0},{"$f":"'K90 - time schedule'!DQ64","v":0},{"$f":"'K90 - time schedule'!DR64","v":0},{"$f":"'K90 - time schedule'!DS64","v":0},{"$f":"'K90 - time schedule'!DT64","v":0},{"$f":"'K90 - time schedule'!DU64","v":0},{"$f":"'K90 - time schedule'!DV64","v":0},{"$f":"'K90 - time schedule'!DW64","v":0},{"$f":"'K90 - time schedule'!DX64","v":0},{"$f":"'K90 - time schedule'!DY64","v":0},{"$f":"'K90 - time schedule'!DZ64","v":0},{"$f":"'K90 - time schedule'!EA64","v":0},{"$f":"'K90 - time schedule'!EB64","v":0},{"$f":"'K90 - time schedule'!EC64","v":0},{"$f":"'K90 - time schedule'!ED64","v":0},{"$f":"'K90 - time schedule'!EE64","v":0},{"$f":"'K90 - time schedule'!EF64","v":0},{"$f":"'K90 - time schedule'!EG64","v":0},{"$f":"'K90 - time schedule'!EH64","v":0},{"$f":"'K90 - time schedule'!EI64","v":0},{"$f":"'K90 - time schedule'!EJ64","v":0},{"$f":"'K90 - time schedule'!EK64","v":0},{"$f":"'K90 - time schedule'!EL64","v":0},{"$f":"'K90 - time schedule'!EM64","v":0},{"$f":"'K90 - time schedule'!EN64","v":0},{"$f":"'K90 - time schedule'!EO64","v":0},{"$f":"'K90 - time schedule'!EP64","v":0},{"$f":"'K90 - time schedule'!EQ64","v":0},{"$f":"'K90 - time schedule'!ER64","v":0},{"$f":"'K90 - time schedule'!ES64","v":0},{"$f":"'K90 - time schedule'!ET64","v":0},{"$f":"'K90 - time schedule'!EU64","v":0},{"$f":"'K90 - time schedule'!EV64","v":0},{"$f":"'K90 - time schedule'!EW64","v":0},{"$f":"'K90 - time schedule'!EX64","v":0},{"$f":"'K90 - time schedule'!EY64","v":0},{"$f":"'K90 - time schedule'!EZ64","v":0},{"$f":"'K90 - time schedule'!FA64","v":0},{"$f":"'K90 - time schedule'!FB64","v":0},{"$f":"'K90 - time schedule'!FC64","v":0},{"$f":"'K90 - time schedule'!FD64","v":0},{"$f":"'K90 - time schedule'!FE64","v":0},{"$f":"'K90 - time schedule'!FF64","v":0},{"$f":"'K90 - time schedule'!FG64","v":0},{"$f":"'K90 - time schedule'!FH64","v":0},{"$f":"'K90 - time schedule'!FI64","v":0},{"$f":"'K90 - time schedule'!FJ64","v":0},{"$f":"'K90 - time schedule'!FK64","v":0},{"$f":"'K90 - time schedule'!FL64","v":0},{"$f":"'K90 - time schedule'!FM64","v":0},{"$f":"'K90 - time schedule'!FN64","v":0},{"$f":"'K90 - time schedule'!FO64","v":0},{"$f":"'K90 - time schedule'!FP64","v":0},{"$f":"'K90 - time schedule'!FQ64","v":0},{"$f":"'K90 - time schedule'!FR64","v":0},{"$f":"'K90 - time schedule'!FS64","v":0},{"$f":"'K90 - time schedule'!FT64","v":0},{"$f":"'K90 - time schedule'!FU64","v":0},{"$f":"'K90 - time schedule'!FV64","v":0},{"$f":"'K90 - time schedule'!FW64","v":0},{"$f":"'K90 - time schedule'!FX64","v":0},{"$f":"'K90 - time schedule'!FY64","v":0},{"$f":"'K90 - time schedule'!FZ64","v":0},{"$f":"'K90 - time schedule'!GA64","v":0},{"$f":"'K90 - time schedule'!GB64","v":0},{"$f":"'K90 - time schedule'!GC64","v":0},{"$f":"'K90 - time schedule'!GD64","v":0},{"$f":"'K90 - time schedule'!GE64","v":0},{"$f":"'K90 - time schedule'!GF64","v":0},{"$f":"'K20 - time schedule'!GG85","v":0},{"$f":"'K20 - time schedule'!GH85","v":0},{"$f":"'K20 - time schedule'!GI85","v":0},{"$f":"'K20 - time schedule'!GJ85","v":0},{"$f":"'K20 - time schedule'!GK85","v":0},{"$f":"'K20 - time schedule'!GL85","v":0},{"$f":"'K20 - time schedule'!GM85","v":0},{"$f":"'K20 - time schedule'!GN85","v":0},{"$f":"'K20 - time schedule'!GO85","v":0},{"$f":"'K20 - time schedule'!GP85","v":0},{"$f":"'K20 - time schedule'!GQ85","v":0},{"$f":"'K20 - time schedule'!GR85","v":0},{"$f":"'K20 - time schedule'!GS85","v":0},{"$f":"'K20 - time schedule'!GT85","v":0},{"$f":"'K20 - time schedule'!GU85","v":0},{"$f":"'K20 - time schedule'!GV85","v":0},{"$f":"'K20 - time schedule'!GW85","v":0},{"$f":"'K20 - time schedule'!GX85","v":0},{"$f":"'K20 - time schedule'!GY85","v":0},{"$f":"'K20 - time schedule'!GZ85","v":0},{"$f":"'K20 - time schedule'!HA85","v":0},{"$f":"'K20 - time schedule'!HB85","v":0},{"$f":"'K20 - time schedule'!HC85","v":0},{"$f":"'K20 - time schedule'!HD85","v":0},{"$f":"'K20 - time schedule'!HE85","v":0},{"$f":"'K20 - time schedule'!HF85","v":0},{"$f":"'K20 - time schedule'!HG85","v":0},{"$f":"'K20 - time schedule'!HH85","v":0},{"$f":"'K20 - time schedule'!HI85","v":0},{"$f":"'K20 - time schedule'!HJ85","v":0},{"$f":"'K20 - time schedule'!HK85","v":0},{"$f":"'K20 - time schedule'!HL85","v":0},{"$f":"'K20 - time schedule'!HM85","v":0},{"$f":"'K20 - time schedule'!HN85","v":0},{"$f":"'K20 - time schedule'!HO85","v":0},{"$f":"'K20 - time schedule'!HP85","v":0},{"$f":"'K20 - time schedule'!HQ85","v":0},{"$f":"'K20 - time schedule'!HR85","v":0},{"$f":"'K20 - time schedule'!HS85","v":0},{"$f":"'K20 - time schedule'!HT85","v":0},{"$f":"'K20 - time schedule'!HU85","v":0},{"$f":"'K20 - time schedule'!HV85","v":0},{"$f":"'K20 - time schedule'!HW85","v":0},{"$f":"'K20 - time schedule'!HX85","v":0},{"$f":"'K20 - time schedule'!HY85","v":0},{"$f":"'K20 - time schedule'!HZ85","v":0},{"$f":"'K20 - time schedule'!IA85","v":0},{"$f":"'K20 - time schedule'!IB85","v":0},{"$f":"'K20 - time schedule'!IC85","v":0},{"$f":"'K20 - time schedule'!ID85","v":0},{"$f":"'K20 - time schedule'!IE85","v":0},{"$f":"'K20 - time schedule'!IF85","v":0},{"$f":"'K20 - time schedule'!IG85","v":0},{"$f":"'K20 - time schedule'!IH85","v":0},{"$f":"'K20 - time schedule'!II85","v":0},{"$f":"'K20 - time schedule'!IJ85","v":0},{"$f":"'K20 - time schedule'!IK85","v":0},{"$f":"'K20 - time schedule'!IL85","v":0},{"$f":"'K20 - time schedule'!IM85","v":0},{"$f":"'K20 - time schedule'!IN85","v":0},{"$f":"'K20 - time schedule'!IO85","v":0},{"$f":"'K20 - time schedule'!IP85","v":0},{"$f":"'K20 - time schedule'!IQ85","v":0},{"$f":"'K20 - time schedule'!IR85","v":0},{"$f":"'K20 - time schedule'!IS85","v":0},{"$f":"'K20 - time schedule'!IT85","v":0},{"$f":"'K20 - time schedule'!IU85","v":0},{"$f":"'K20 - time schedule'!IV85","v":0},{"$f":"'K20 - time schedule'!IW85","v":0},{"$f":"'K20 - time schedule'!IX85","v":0},{"$f":"'K20 - time schedule'!IY85","v":0},{"$f":"'K20 - time schedule'!IZ85","v":0},{"$f":"'K20 - time schedule'!JA85","v":0},{"$f":"'K20 - time schedule'!JB85","v":0},{"$f":"'K20 - time schedule'!JC85","v":0},{"$f":"'K20 - time schedule'!JD85","v":0},{"$f":"'K20 - time schedule'!JE85","v":0},{"$f":"'K20 - time schedule'!JF85","v":0},{"$f":"'K20 - time schedule'!JG85","v":0},{"$f":"'K20 - time schedule'!JH85","v":0},{"$f":"'K20 - time schedule'!JI85","v":0},{"$f":"'K20 - time schedule'!JJ85","v":0},{"$f":"'K20 - time schedule'!JK85","v":0},{"$f":"'K20 - time schedule'!JL85","v":0},{"$f":"'K20 - time schedule'!JM85","v":0},{"$f":"'K20 - time schedule'!JN85","v":0},{"$f":"'K20 - time schedule'!JO85","v":0},{"$f":"'K20 - time schedule'!JP85","v":0},{"$f":"'K20 - time schedule'!JQ85","v":0},{"$f":"'K20 - time schedule'!JR85","v":0},{"$f":"'K20 - time schedule'!JS85","v":0},{"$f":"'K20 - time schedule'!JT85","v":0},{"$f":"'K20 - time schedule'!JU85","v":0},{"$f":"'K20 - time schedule'!JV85","v":0},{"$f":"'K20 - time schedule'!JW85","v":0},{"$f":"'K20 - time schedule'!JX85","v":0},{"$f":"'K20 - time schedule'!JY85","v":0},{"$f":"'K20 - time schedule'!JZ85","v":0},{"$f":"'K20 - time schedule'!KA85","v":0},{"$f":"'K20 - time schedule'!KB85","v":0},{"$f":"'K20 - time schedule'!KC85","v":0},{"$f":"'K20 - time schedule'!KD85","v":0},{"$f":"'K20 - time schedule'!KE85","v":0},{"$f":"'K20 - time schedule'!KF85","v":0},{"$f":"'K20 - time schedule'!KG85","v":0},{"$f":"'K20 - time schedule'!KH85","v":0},{"$f":"'K20 - time schedule'!KI85","v":0},{"$f":"'K20 - time schedule'!KJ85","v":0},{"$f":"'K20 - time schedule'!KK85","v":0},{"$f":"'K20 - time schedule'!KL85","v":0},{"$f":"'K20 - time schedule'!KM85","v":0},{"$f":"'K20 - time schedule'!KN85","v":0},{"$f":"'K20 - time schedule'!KO85","v":0},{"$f":"'K20 - time schedule'!KP85","v":0},{"$f":"'K20 - time schedule'!KQ85","v":0},{"$f":"'K20 - time schedule'!KR85","v":0},{"$f":"'K20 - time schedule'!KS85","v":0},{"$f":"'K20 - time schedule'!KT85","v":0}]
[]
["Partial prices by week",null,null,{"$f":"SUM(D8:D82)","v":0},{"$f":"SUM(E8:E82)","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"SUM(BQ8:BQ82)","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"SUM(EC8:EC82)","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"SUM(GO8:GO82)","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,{"$f":"SUM(JA8:JA82)","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
["Partial prices by month",null,null,{"$f":"SUM(D84:G84)","v":0},null,null,null,{"$f":"SUM(H84:K84)","v":0},null,null,null,{"$f":"SUM(L84:O84)","v":0},null,null,null,{"$f":"SUM(P84:S84)","v":0},null,null,null,{"$f":"SUM(T84:W84)","v":0},null,null,null,{"$f":"SUM(X84:AA84)","v":0},null,null,null,{"$f":"SUM(AB84:AE84)","v":0},null,null,null,{"$f":"SUM(AF84:AI84)","v":0},null,null,null,{"$f":"SUM(AJ84:AM84)","v":0},null,null,null,{"$f":"SUM(AN84:AQ84)","v":0},null,null,null,{"$f":"SUM(AR84:AU84)","v":0},null,null,null,{"$f":"SUM(AV84:AY84)","v":0},null,null,null,{"$f":"SUM(AZ84:BC84)","v":0},null,null,null,{"$f":"SUM(BD84:BG84)","v":0},null,null,null,{"$f":"SUM(BH84:BK84)","v":0},null,null,null,{"$f":"SUM(BL84:BO84)","v":0},null,null,null,{"$f":"SUM(BP84:BS84)","v":0},null,null,null,{"$f":"SUM(BT84:BW84)","v":0},null,null,null,{"$f":"SUM(BX84:CA84)","v":0},null,null,null,{"$f":"SUM(CB84:CE84)","v":0},null,null,null,{"$f":"SUM(CF84:CI84)","v":0},null,null,null,{"$f":"SUM(CJ84:CM84)","v":0},null,null,null,{"$f":"SUM(CN84:CQ84)","v":0},null,null,null,{"$f":"SUM(CR84:CU84)","v":0},null,null,null,{"$f":"SUM(CV84:CY84)","v":0},null,null,null,{"$f":"SUM(CZ84:DC84)","v":0},null,null,null,{"$f":"SUM(DD84:DG84)","v":0},null,null,null,{"$f":"SUM(DH84:DK84)","v":0},null,null,null,{"$f":"SUM(DL84:DO84)","v":0},null,null,null,{"$f":"SUM(DP84:DS84)","v":0},null,null,null,{"$f":"SUM(DT84:DW84)","v":0},null,null,null,{"$f":"SUM(DX84:EA84)","v":0},null,null,null,{"$f":"SUM(EB84:EE84)","v":0},null,null,null,{"$f":"SUM(EF84:EI84)","v":0},null,null,null,{"$f":"SUM(EJ84:EM84)","v":0},null,null,null,{"$f":"SUM(EN84:EQ84)","v":0},null,null,null,{"$f":"SUM(ER84:EU84)","v":0},null,null,null,{"$f":"SUM(EV84:EY84)","v":0},null,null,null,{"$f":"SUM(EZ84:FC84)","v":0},null,null,null,{"$f":"SUM(FD84:FG84)","v":0},null,null,null,{"$f":"SUM(FH84:FK84)","v":0},null,null,null,{"$f":"SUM(FL84:FO84)","v":0},null,null,null,{"$f":"SUM(FP84:FS84)","v":0},null,null,null,{"$f":"SUM(FT84:FW84)","v":0},null,null,null,{"$f":"SUM(FX84:GA84)","v":0},null,null,null,{"$f":"SUM(GB84:GE84)","v":0},null,null,null,{"$f":"SUM(GF84:GI84)","v":0},null,null,null,{"$f":"SUM(GJ84:GM84)","v":0},null,null,null,{"$f":"SUM(GN84:GQ84)","v":0},null,null,null,{"$f":"SUM(GR84:GU84)","v":0},null,null,null,{"$f":"SUM(GV84:GY84)","v":0},null,null,null,{"$f":"SUM(GZ84:HC84)","v":0},null,null,null,{"$f":"SUM(HD84:HG84)","v":0},null,null,null,{"$f":"SUM(HH84:HK84)","v":0},null,null,null,{"$f":"SUM(HL84:HO84)","v":0},null,null,null,{"$f":"SUM(HP84:HS84)","v":0},null,null,null,{"$f":"SUM(HT84:HW84)","v":0},null,null,null,{"$f":"SUM(HX84:IA84)","v":0},null,null,null,{"$f":"SUM(IB84:IE84)","v":0},null,null,null,{"$f":"SUM(IF84:II84)","v":0},null,null,null,{"$f":"SUM(IJ84:IM84)","v":0},null,null,null,{"$f":"SUM(IN84:IQ84)","v":0},null,null,null,{"$f":"SUM(IR84:IU84)","v":0},null,null,null,{"$f":"SUM(IV84:IY84)","v":0},null,null,null,{"$f":"SUM(IZ84:JC84)","v":0},null,null,null,{"$f":"SUM(JD84:JG84)","v":0},null,null,null,{"$f":"SUM(JH84:JK84)","v":0},null,null,null,{"$f":"SUM(JL84:JO84)","v":0},null,null,null,{"$f":"SUM(JP84:JS84)","v":0},null,null,null,{"$f":"SUM(JT84:JW84)","v":0},null,null,null,{"$f":"SUM(JX84:KA84)","v":0},null,null,null,{"$f":"SUM(KB84:KE84)","v":0},null,null,null,{"$f":"SUM(KF84:KI84)","v":0},null,null,null,{"$f":"SUM(KJ84:KM84)","v":0},null,null,null,{"$f":"SUM(KN84:KQ84)","v":0}]
["Total price",null,null,{"$f":"SUM(D85:GG85)","v":0}]
[]
["Notes:"]
["The Contractor does not fill in any values on this sheet. The values are transfered from previous sheets."]
["Vstupní technická jednání "]
["Závazné technické parametry pro OB 6 (Stavba) "]
["Závazné technické parametry pro OB 1 (Palivové hospodářství) "]
["Závazné technické parametry pro ostatní OB, pro ostatní dodavatele technologických celků"]
["Odsouhlasená prováděcí dokumentace pro nový kotel K20"]
["Předání a převzetí staveniště pro K20"]
["neobsazeno"]
["Kotelna K20 - vlastní kotel včetně všech komponentů"]
["Kotelna K20 - provozní zásobníky paliva včetně dopravy štěpky do kotle"]
["Kotelna K20 - ventilátory (vzduchové, spalinové, recirkulační) včetně vnitřních spalinovodů"]
["Kotelna K20 - tkaninový filtr"]
["Kotelna K20 - technologie DSI"]
["Kotelna K20 - popelové hospodářství"]
["Kotelna K20 - elektroinstalace"]
["Kotelna K20 - ASŘ"]
["Kotelna K20 - kompresorová stanice"]
["Kotelna K20 - připojení médií"]
["Kotelna K20 - venkovní rozvody spalinovodů včetně napojení na komín"]
["Kotelna K20 - venkovní konstrukce potrubního mostu (připojení popelového hospodářství a SNCR)"]
["Kotelna K20 - opláštění a zastřešení, dokončení všech stavebních činností"]
["Kotelna K20 - další výše nevyjmenované položky"]
["Kotelna K20 - dokončení stavebních prací"]
["Kotelna K20 - ukončení montážních prací"]
["Kotelna K20 - školení zaměstnanců provozu"]
["Kotelna K20 - příprava ke kompexnímu vyzkoušení"]
["Kotelna K20 - komplexní vyzkoušení"]
["Kotelna K20 - zkušební provoz"]
["Kotelna K20 - garanční test A"]
["Kotelna K20 - předběžné převzetí díla PAC"]
["Kotelna K20 - garanční test B"]
["Kotelna K20 - finální převzetí díla FAC"]